## Cycle times & prices
VIRTUAL CYCLE TIME & PRICE GEOTECHNICAL SURVEY - LOT 1
| Project: | IJmuiden Ver Wind Farm Zone | [8 empty] | Intermediate Target Depths (m bsf) |  |  |  |  | PCPT | SCPT | DT | TC | VC |  | All
| Company: | Company name | [8 empty] | SB PCPT min target (for price) |  | 50 |  | Vessel 1 | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE
| Originator: | Originator name | [8 empty] | SB SCPT av. target (for price) |  | 50 |  | Vessel 2 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
[10 empty] | Note | BH min depth |  | 60 |  | Vessel 3 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
| I. Survey Area Ijmuiden Ver and Number of Tests | [8 empty] | I.0 |  |  |  |  | Vessel 4 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE
| Test type - Description |  |  |  | Target depth (m bsf) |  | Total Number | Short name |  |  | Test average duration |  |  |  | All | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE
| Seabed Cone Penetration Tests with Pore pressure measurement |  |  |  | 60 |  | 230 | SB PCPT |  |  | Test | Duration (hrs)
| Seabed Seismic Cone Penetration Tests |  |  |  | 60 |  | 59 | SB SCPT |  |  | DT | 0.25 |  |  | Overview of activities during the different survey phases
| Dissipation test performed during PCPT or SCPT testing, (total no of hours) |  |  |  | 60 |  | 39 | DT |  |  | TC | 0.25 |  |  | Part A | ¦PCPT | ¦SCPT | ¦DT | ¦TC | ¦VC |  | ¦PCPT¦SCPT¦DT¦TC¦VC¦
| Thermal conductivity tests (test every meter by location) |  |  |  | 6 |  | 68 | TC | [6 empty] | Part B | [6 empty] | ¦
| Vibrocores |  |  |  | 6 |  | 164 | VC |  |  | Allowed factor in WOW estimation between CTR and CPY |  |  |  | Part A | [6 empty] | ¦
[15 empty] | Part B | [6 empty] | ¦
| II. Vessels used for which equipment & Limiting condition and required weather window |  |  |  |  | Hs (m) | Vw (m/s) | Ww (hrs) |  |  | min | max
| Part A | Name of vessel 1 | [7 empty] | II.0 | 0.75 | 1.25 |  |  | Hs | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.75 | 3 | 3.5 | 4 | 4.5 | 5
| Part B | Name of vessel 2 | [12 empty] | Vw | 2 | 4 | 6 | 8 | 9 | 10 | 11 | 12 | 15 | 20 | 25
| Part C | Name of vessel 3 | [8 empty] | Error message if no price in remuneration section |  |  |  | Ww | 1 | 2 | 4 | 6 | 12 | 18 | 24 | 48 | 72
| Part D | Name of vessel 4
|  | PCPT: Piezoelectric Cone Penetration Test ¦ SCPT: Seismic Cone Penetration Test ¦ DT: Dissipation Testing ¦ TC: Thermal Conductivity and Shallow CPT ¦ VC: Vibrocoring | [8 empty] | FILL UNIT RATE
| III. Cycle Time Geotechnical Survey (excluding weather) |  |  | Max duration (days) | Unit | Cycle | Qty | Total (days) | (end) date | III.0 | Days between desired and ultimate report due date
Key dates
| 1a | COMMENCEMENT DATE WORK | [6 empty] | 2020-12-03 |  | 45 | [6 empty] | Scaling Factor | 1.95
| 1b | CLIENT provision of seabed CPT/VC plan | [6 empty] | 2021-01-18 | [8 empty] | Advanced scaling | 1.5
| Preparation | [9 empty] | Report max update/review time (days) | [6 empty] | Quantity of type of testing by borehole
| 2a | 1st revision of project documentation (PQP, PEP) | (Max: 3 weeks) | 21 | days |  | Fill number of days |  | 2020-12-03 |  |  |  | CTR |  | CPY |  |  |  | BH-I | BH-II | BH-III | BH-IV
| 2b | Review 1st revision project documentation (PQP, PEP) |  |  | days | 14 |  |  | 2020-12-17 |  |  |  | Seabed | Downhole | Seabed | Downhole |  | Sample | 114 | 20 | 117 | 10
| 2c | 2nd revision of project documentation (PQP, PEP) | (Max: 1 week) | 7 | days |  | Fill number of days |  | 2020-12-17 |  | 1 | Field | 7 | 14 | #N/A | #N/A |  | PCPT | 16 | 0 | 59 | 20
| 2d | Review 2nd revision project documentation (PQP, PEP) |  |  | days | 7 |  |  | 2020-12-24 |  | 2 | Interim | #N/A | 28 | #N/A | 14 |  | SCPT | 4 | 59 | 0 | 0
| 2e | Finalise project documentation (incl additional revisions/review rounds) | (Max: 3 days) | 3 | days |  | Fill number of days |  | 2020-12-24 |  | 3 | 1st draft | 35 | 49 | 21 | 21
| 2f | Review final version of project documentation (PQP, PEP) |  |  | days | 2 |  |  | 2020-12-26 |  | 4 | 2nd draft | 14 | 14 | 14 | 7 |  | Percentage of BH with SCPT testing
| 2g | Minimum number of days between finalization project documentation and start mobilization | (Min: 3 days) | 3 | days | 3 |  |  | 2020-12-27 | III.1 | 5 | final | 14 | 7 | 7 | 7 |  |  | BH-I | BH-II | BH-III | BH-IV
| 2h | Clearance of seabed investigation locations (days after CLIENT issues seabed CPT/VC plan) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2021-01-18 |  | 6 | cy 1st draft | #N/A | 196 | #N/A | 21 |  | SCPT (%) | 25% | 100% | 0% | 0%
[11 empty] | 7 | cy 2nd draft | #N/A | 21 | #N/A | 14
| PART A | Survey Campaign - Name of vessel 1 - Surveying ¦PCPT¦SCPT¦DT¦TC¦VC¦ | [8 empty] | 8 | cy final | #N/A | 7 | #N/A | 7 |  | % of push/piston sampling |  |  |  | 95%
| 3a | Start of Mobilisation |  |  |  |  | Fill Start date | [10 empty] | qty pf push/piston sampling |  |  |  | #REF!
| 3b | Mobilisation and transit to site | (Max: 1 week) | 7 | days |  | Fill number of days |  | 0 | [8 empty] | qty of hammer sampling |  |  |  | #REF!
| 3c | Start of survey WORK | [6 empty] | 0 |  | Total quantity | [6 empty] | qty of location with DH SCPT |  |  |  | #REF!
| 3d | Execution of seabed PCPT to target depth of 60m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 230 | 0 | 0 | III.2 | [7 empty] | qty DH SCPT |  |  |  | #REF!
| 3e | Re-positioning and re-testing of the seabed PCPT locations at the same location |  |  | hrs/retest |  | 23 | 0 | 0 |  | 230 | 0 | [5 empty] | qty DH PCPT |  |  |  | #REF!
| 3f | Execution of dissipation tests, excl. WoW |  |  | hrs |  | 39 | 1.625 | 1899-12-31 15:00 |  | 59 | 0 | [5 empty] | SCPT & PCPT swap within 1 BH |  |  |  | #REF!
| 3g | Execution of seabed SCPT to target depth of 60m,incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 59 | 0 | 1899-12-31 15:00 |  | 39 | 0 | [5 empty] | Probability extension BH-I to 80m |  |  |  | 30%
| 3h | Re-positioning and re-testing of the seabed SCPT locations at the same location |  |  | hrs/retest |  | 6 | 0 | 1899-12-31 15:00 |  | 68 | 0 | [5 empty] | Probability of seabed CPT to reach 60m |  |  |  | 70%
| 3i | Execution of thermal conductivity tests and PCPT to target depth of 6m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 68 | 0 | 1899-12-31 15:00 |  | 164 | 0 | [5 empty] | Depth Seabed CPT if early refusal (m) |  |  |  | 25
| 3j | Re-positioning and re-testing of the thermal conductivity test locations at the same location |  |  | hrs/retest |  | 6 | 0 | 1899-12-31 15:00 |  | TRUE | 0 | [5 empty] | % of possible additional locations |  |  |  | 15%
| 3k | Execution of vibrocoring campaign, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 164 | 0 | 1899-12-31 15:00 | [8 empty] | % of retest by locations |  |  |  | 10%
| 3l | Re-positioning and re-testing of the vibrocoring locations at the same location |  |  | hrs/retest |  | 16 | 0 | 1899-12-31 15:00 | [8 empty] | Number of VC by group |  |  |  | 5
| 3m | Offshore Completion Date PART A Name of vessel 1 ¦ Excluding WAITING ON WEATHER | [6 empty] | 1899-12-31 15:00 | III.3
| 3n | Offshore Completion Date PART A Name of vessel 1 ¦ Including WAITING ON WEATHER calculated by Client |  | 30 |  |  | WAITING ON WEATHER DAYS | Fill Hs, Vw, Ww (II.1)
| 3o | Offshore Completion Date PART A Name of vessel 1 ¦ Including WAITING ON WEATHER calculated by TENDERER |  |  |  |  | WAITING ON WEATHER DAYS |  | 1899-12-31 15:00
Explanation for difference between WOW calculated by CLIENT and WOW according to TENDERER.
| 4a | Start of Mobilisation |  |  |  |  | Fill Start date
| 4b | Mobilisation and transit to site | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 0
| 4c | Start of survey WORK | [6 empty] | 0
| 4d | Execution of seabed PCPT to target depth of 60m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 4e | Re-positioning and re-testing of 10% of the seabed PCPT locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 4f | Execution of dissipation tests, excl. WoW |  |  | hrs |  | 0 | 0 | 0
| 4g | Execution of seabed SCPT to target depth of 60m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 4h | Re-positioning and re-testing of 10% of the seabed SCPT locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 4i | Execution of thermal conductivity tests and PCPT to target depth of 6m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 4j | Re-positioning and re-testing of 10% of the thermal conductivity test locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 4k | Execution of vibrocoring campaign, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 4l | Re-positioning and re-testing of 10% of the vibrocoring locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 4m | Offshore Completion Date Name of vessel 2 ¦ Excluding WAITING ON WEATHER | [6 empty] | 2020-12-27
| 4n | Offshore Completion Date Name of vessel 2 ¦ Including WAITING ON WEATHER calculated by Client |  | 30 |  |  | WAITING ON WEATHER DAYS | Fill Hs, Vw, Ww (II.1)
| 4o | Offshore Completion Date Name of vessel 2 ¦ Including WAITING ON WEATHER calculated by TENDERER |  |  |  |  | WAITING ON WEATHER DAYS | 0 | 2020-12-27
Explanation for difference between WOW calculated by CLIENT and WOW according to TENDERER.
| 5a | Start of Mobilisation |  |  |  |  | Fill Start date
| 5b | Mobilisation and transit to site | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 0
| 5c | Start of survey WORK | [6 empty] | 0
| 5d | Execution of seabed PCPT to target depth of 60m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 5e | Re-positioning and re-testing of 10% of the seabed PCPT locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 5f | Execution of dissipation tests, excl. WoW |  |  | hrs |  | 0 | 0 | 0
| 5g | Execution of seabed SCPT to target depth of 60m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 5h | Re-positioning and re-testing of 10% of the seabed SCPT locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 5i | Execution of thermal conductivity tests and PCPT to target depth of 6m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 5j | Re-positioning and re-testing of 10% of the thermal conductivity test locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 5k | Execution of vibrocoring campaign, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 5l | Re-positioning and re-testing of 10% of the vibrocoring locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 5m | Offshore Completion Date Name of vessel 3 ¦ Excluding WAITING ON WEATHER | [6 empty] | 2020-12-27
| 5n | Offshore Completion Date Name of vessel 3 ¦ Including WAITING ON WEATHER calculated by Client |  | 7 |  |  | WAITING ON WEATHER DAYS | Fill Hs, Vw, Ww (II.1)
| 5o | Offshore Completion Date Name of vessel 3 ¦ Including WAITING ON WEATHER calculated by TENDERER |  |  |  |  | WAITING ON WEATHER DAYS | 0 | 2020-12-27
Explanation for difference between WOW calculated by CLIENT and WOW according to TENDERER.
| 6a | Start of Mobilisation |  |  |  |  | Fill Start date
| 6b | Mobilisation and transit to site | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 0
| 6c | Start of survey WORK | [6 empty] | 0
| 6d | Execution of seabed PCPT to target depth of 60m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 6e | Re-positioning and re-testing of 10% of the seabed PCPT locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 6f | Execution of dissipation tests, excl. WoW |  |  | hrs |  | 0 | 0 | 0
| 6g | Execution of seabed SCPT to target depth of 60m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 6h | Re-positioning and re-testing of 10% of the seabed SCPT locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 6i | Execution of thermal conductivity tests and PCPT to target depth of 6m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 6j | Re-positioning and re-testing of 10% of the thermal conductivity test locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 6k | Execution of vibrocoring campaign, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 0 | 0 | 0
| 6l | Re-positioning and re-testing of 10% of the vibrocoring locations at the same location |  |  | hrs/retest |  | 0 | 0 | 0
| 6m | Offshore Completion Date Name of vessel 4 ¦ Excluding WAITING ON WEATHER | [6 empty] | 2020-12-27
| 6n | Offshore Completion Date Name of vessel 4 ¦ Including WAITING ON WEATHER calculated by Client |  | 7 |  |  | WAITING ON WEATHER DAYS | Fill Hs, Vw, Ww (II.1)
| 6o | Offshore Completion Date Name of vessel 4 ¦ Including WAITING ON WEATHER calculated by TENDERER |  |  |  |  | WAITING ON WEATHER DAYS | 0 | 2020-12-27
Explanation for difference between WOW calculated by CLIENT and WOW according to TENDERER.
Data Processing and report
| 7a1 | Intermediate delivery milestone: preliminary CPT results of HPA - calculated by CLIENT based on 50% of duration | [6 empty] | 1960-06-29
| 7a | Intermediate delivery milestone: preliminary CPT results of HPA - determined by TENDERER |  |  |  |  | Fill Start date
| 7b | OFFSHORE COMPLETION DATE (including WAITING ON WEATHER) - Lot 1 (Seabed In Situ Testing & Seabed Sampling) | [6 empty] | 2020-12-27 | III.4
| 7c | Delivery of 1st Version (Field Report) "Seabed In Situ Testing Report" (days after OFFSHORE COMPLETION DATE) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2020-12-27 | III.5
| 7d | CLIENT review of 1st Version (Field Report) "Seabed In Situ Testing Report" |  |  | days | 14 |  |  | 2021-01-10
| 7e | Delivery of 2nd Version "Seabed In Situ Testing Report" |  |  | days |  | Fill number of days |  | 2021-01-10
| 7f | CLIENT review of 2nd Version "Seabed In Situ Testing Report" |  |  | days | 7 |  |  | 2021-01-17
| 7g | Delivery of Final Version "Seabed In Situ Testing Report" |  |  | days |  | Fill number of days |  | 2021-01-17
| 7h | Delivery of 1st Version (Field Report) "Seabed Sampling Report" (days after OFFSHORE COMPLETION DATE) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2020-12-27
| 7i | CLIENT review of 1st version "Seabed Sampling Report" |  |  | days | 7 |  |  | 2021-01-03
| 7j | Delivery of 2nd version "Seabed Sampling Report" (including onshore lab testing) | (Max: 8 weeks) | 56 | days |  | Fill number of days |  | 2021-01-03
| 7k | CLIENT review of 2nd version "Seabed Sampling Report" |  |  | days | 7 |  |  | 2021-01-10
| 7l | Delivery of Final version of "Seabed Sampling Report" |  |  | days |  | Fill number of days |  | 2021-01-10
| 7m | Delivery of 1st version "Operations Report (Lot 1)" (days after OFFSHORE COMPLETION DATE) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2020-12-27
| 7n | CLIENT review of 1st revision "Operations Report (Lot 1)" |  |  | days | 14 |  |  | 2021-01-10
| 7o | Delivery of Final Version of "Operations Report (Lot 1)" | (Max: 1 week) | 7 | days |  | Fill number of days |  | 2021-01-10
| 7p | Completion Date "Seabed In Situ Testing Report" | [6 empty] | 2021-01-17
| 7q | Completion Date "Seabed Sampling Report" | [6 empty] | 2021-01-10
| 7r | Completion Date "Seabed Operations Report" | [6 empty] | 2021-01-10
| TOTAL DURATION CYCLE TIME INCLUDING WEATHER - Seabed In Situ Testing | [6 empty] | 45 | days
| TOTAL DURATION CYCLE TIME INCLUDING WEATHER & LABORATORY TESTING - Seabed Sampling | [6 empty] | 38 | days
IV. Rates Geotechnical Site Survey - IJmuiden Ver
| ITEM |  |  |  |  | Unit Rate | Unit | Qty | Price
| 1 | Mobilisation/demobilisation of vessel(s), survey equipment and personnel to site
| 1.1 | Mob/demob vessel Name of vessel 1 incl. vessel equipment and personnel |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.2 | Mob/demob vessel Name of vessel 2 incl. vessel equipment and personnel |  |  |  |  | Lump sum | 0 | FILL UNIT RATE
| 1.3 | Mob/demob vessel Name of vessel 3 incl. vessel equipment and personnel |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.4 | Mob/demob vessel Name of vessel 4 incl. vessel equipment and personnel |  |  |  |  | Lump sum | 0 | FILL UNIT RATE
| 1.5 | Mob/demob of seabed PCPT equipment and personnel |  |  |  |  | Lump sum | 1 | FILL UNIT RATE | IV.0
| 1.6 | Mob/demob of seabed SCPT equipment and personnel |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.7 | Mob/demob of thermal conductivity test equipment and personnel |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.8 | Mob/demob of vibrocoring equipment and personnel |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 2 | Survey Operations incl transit from and to site excluding WOW
| 2.1 | Positioning and setting-up equipment at each location for seabed PCPT and dissipation tests |  |  |  |  | /location | 230 | FILL UNIT RATE
| 2.2 | Re-positioning and setting-up for any re-tests at same location (seabed PCPT and dissipation tests) |  |  |  |  | /location | 23 | FILL UNIT RATE
| 2.3 | Seabed PCPT performance (including any re-tests) for depths between 0-50 m |  |  |  |  | /m | 12650 | FILL UNIT RATE
| 2.4 | Seabed PCPT performance (including any re-tests) to a depth of between 50-60 m (amount includes bonus) |  |  |  |  | /m | 2300 | FILL UNIT RATE
| 2.5 | Execution of dissipation tests in seabed PCPT mode (N.B. number of tests will be limited by total time allowance) |  |  |  |  | /hour | 39 | FILL UNIT RATE
| 2.6 | Positioning and setting-up equipment at each location for seabed SCPT |  |  |  |  | /location | 59 | FILL UNIT RATE
| 2.7 | Re-positioning and setting-up for any re-tests at same location (seabed SCPT) |  |  |  |  | /location | 6 | FILL UNIT RATE
| 2.8 | Seabed SCPT performance excluding seismic tests (including any re-tests) for depths between 0-50 m |  |  |  |  | /m | 3250 | FILL UNIT RATE
| 2.9 | Seabed SCPT performance excluding seismic tests (including any re-tests) to a depth of between 50-60 m (amount includes bonus) |  |  |  |  | /m | 590 | FILL UNIT RATE
| 2.10 | Execution of seismic tests in seabed SCPT mode |  |  |  |  | /m | 3840 | FILL UNIT RATE | IV.1
| 2.11 | Positioning and setting-up equipment at each location for thermal conductivity cone testing |  |  |  |  | /location | 68 | FILL UNIT RATE
| 2.12 | Re-positioning and setting-up for any re-tests at same location (thermal conductivity tests) |  |  |  |  | /location | 7 | FILL UNIT RATE
| 2.13 | Seabed in situ thermal conductivity performance (including any re-tests and any associated data) for depths between 0-6m |  |  |  |  | /m | 408 | FILL UNIT RATE
| 2.14 | Execution of in situ thermal conductivity tests during pause in penetration |  |  |  |  | /hour | 102 | FILL UNIT RATE
| 2.15 | Positioning and setting-up equipment at vibrocore location |  |  |  |  | /location | 164 | FILL UNIT RATE | IV.1
| 2.16 | Execution of vibrocores (including any re-tests) to target depth of up to 6m |  |  |  |  | /m | 984 | FILL UNIT RATE
| 2.17 | Micro sitting for positioning at seabed CPT location due to unexpected high gradient of seabed frame preventing the work |  |  |  |  | /location | 23 | FILL UNIT RATE
| 2.18 | Port call for Name of vessel 1 during surveying PART A |  |  |  |  | /call | 0 | FILL UNIT RATE
| 2.19 | Port call for Name of vessel 2 during surveying PART B |  |  |  |  | /call | 1578 | FILL UNIT RATE
| 2.20 | Port call for Name of vessel 3 during surveying PART C |  |  |  |  | /call | 1578 | FILL UNIT RATE
| 2.21 | Port call for Name of vessel 4 during surveying PART D |  |  |  |  | /call | 1578 | FILL UNIT RATE
| 3 | Lab Testing
All Soil types
| 3.1 | Natural Moisture content |  |  |  |  | /test | 1476 | FILL UNIT RATE
| 3.2 | Bulk density |  |  |  |  | /test | 1476 | FILL UNIT RATE
| 3.3 | Particle density |  |  |  |  | /test | 492 | FILL UNIT RATE
| 3.4 | Carbonate content |  |  |  |  | /test | 32.8 | FILL UNIT RATE
| 3.5 | Organic content (dichromate) |  |  |  |  | /test | 32.8 | FILL UNIT RATE
| 3.6 | Organic content (loss on ignition) |  |  |  |  | /test | 32.8 | FILL UNIT RATE
| 3.7 | Organic and total carbon content (Elementary analysis) |  |  |  |  | /test | 32.8 | FILL UNIT RATE
| 3.8 | Electrical resistivity (as input for heat capacity calculations) |  |  |  |  | /test | 68 | FILL UNIT RATE
| 3.9 | Pore water salinity (as input for heat capacity calculations) |  |  |  |  | /test | 68 | FILL UNIT RATE
| 3.10 | Microscopic photography (as input for heat capacity calculations) |  |  |  |  | /test | 68 | FILL UNIT RATE
Granular Soil
| 3.11 | Particle size analysis (sieve) |  |  |  |  | /test | 984 | FILL UNIT RATE
| 3.12 | Particle size analysis (using sieve and hydrometer for fines fraction) |  |  |  |  | /test | 492 | FILL UNIT RATE
| 3.13 | Thermal conductivity tests on fully-saturated cohesionless samples using needle probe (ASTM D5334-14) |  |  |  |  | /test | 164 | FILL UNIT RATE
| 3.14 | Thermal conductivity tests on fully-saturated cohesionless samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). |  |  |  |  | /test | 20 | FILL UNIT RATE
| 3.15 | Shear box (set of 3 specimens with different normal stresses) |  |  |  |  | /test | 82 | FILL UNIT RATE
Cohesive Soil
| 3.16 | Particle size analysis (using hydrometer for fines and if applicable sieve) |  |  |  |  | /test | 50 | FILL UNIT RATE
| 3.17 | Atterberg limits (liquid and plastic limits, cone method) |  |  |  |  | /test | 50 | FILL UNIT RATE
| 3.18 | Thermal conductivity tests on fully-saturated undisturbed cohesive samples using needle probe (ASTM D5334-14) |  |  |  |  | /test | 15 | FILL UNIT RATE | IV.2
| 3.19 | Thermal conductivity tests on fully-saturated remoulded cohesive samples using needle probe (ASTM D5334-14) |  |  |  |  | /test | 15 | FILL UNIT RATE
| 3.20 | Thermal conductivity tests on fully-saturated undisturbed cohesive samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). |  |  |  |  | /test | 15 | FILL UNIT RATE
| 3.21 | Thermal conductivity tests on fully-saturated remoulded cohesive samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). |  |  |  |  | /test | 15 | FILL UNIT RATE
| 3.22 | Unconsolidated-undrained triaxial compression tests on undisturbed samples |  |  |  |  | /test | 50 | FILL UNIT RATE
| 3.23 | Unconsolidated-undrained triaxial compression tests on remoulded samples |  |  |  |  | /test | 50 | FILL UNIT RATE
Age dating
| 3.24 | Palynology analysis |  |  |  |  | /sample | 20 | FILL UNIT RATE
| 3.25 | Analysis of Algae |  |  |  |  | /sample | 20 | FILL UNIT RATE
| 3.26 | Analysis of Fungi |  |  |  |  | /sample | 20 | FILL UNIT RATE
| 3.27 | Analysis of Spores |  |  |  |  | /sample | 20 | FILL UNIT RATE
| 3.28 | Nanno- or micro-fossil analysis including Dinoflagellate Cysts and Foraminifera |  |  |  |  | /sample | 20 | FILL UNIT RATE
| 3.29 | Carbon dating analysis |  |  |  |  | /sample | 20 | FILL UNIT RATE
| 3.30 | Mollucs |  |  |  |  | /sample | 20 | FILL UNIT RATE
| 3.31 | Diatoms |  |  |  |  | /sample | 20 | FILL UNIT RATE
| 4 | Reporting
| 4.1 | Seabed In Situ Testing Report |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 4.2 | Seabed Sampling Report (including all results from lab testing programme, except for age dating) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 4.3 | Operations Report (Lot 1) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 4.4 | Age dating Report (including all results of age dating programme) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 4.5 | Additional reporting of any seabed PCPTs in excess of base scope |  |  |  |  | /location | 10 | FILL UNIT RATE
| 4.6 | Additional reporting of any seabed SCPTs in excess of base scope (excluding the seismic test results) |  |  |  |  | /location | 10 | FILL UNIT RATE
| 4.7 | Additional reporting of any seismic tests during seabed SCPTs in excess of base scope |  |  |  |  | /test | 300 | FILL UNIT RATE
| 4.8 | Additional reporting of any dissipation tests in excess of base scope |  |  |  |  | /test | 10 | FILL UNIT RATE
| 4.9 | Additional reporting of any in situ thermal conductivity tests in excess of base scope |  |  |  |  | /location | 5 | FILL UNIT RATE
| 4.10 | Additional reporting of any vibrocores in excess of base scope |  |  |  |  | /location | 10 | FILL UNIT RATE
| 4.11 | Additional reporting of age dating tests in excess of base scope |  |  |  |  | /test | 15 | FILL UNIT RATE
| 4.12 | Lab test processing/reporting and any other expenses associated with lab testing not covered by other items above |  |  |  |  | % of lab testing price |  | FILL UNIT RATE
| 5 | Waiting on Weather
| 5.1 | Waiting on Weather Name of vessel 1 during surveying PART A |  |  |  |  | /day | 0 | FILL UNIT RATE
| 5.2 | Waiting on Weather Name of vessel 2 during surveying PART B |  |  |  |  | /day | 0 | FILL UNIT RATE
| 5.3 | Waiting on Weather Name of vessel 1 during surveying PART C |  |  |  |  | /day | 0 | FILL UNIT RATE
| 5.4 | Waiting on Weather Name of vessel 2 during surveying PART D |  |  |  |  | /day | 0 | FILL UNIT RATE
| 6 | Other
| 6.1 | Project meetings to be held in CLIENT offices (Utrecht or The Hague) |  |  |  |  | /meeting | 15 | FILL UNIT RATE
| 6.2 | Additional UXO clearance measures for seabed PCPT/SCPT, in situ thermal conductivity tests, or vibrocores. |  |  |  |  | /location | 394 | FILL UNIT RATE
| 6.3 | Interaction with Lot 2 contractor and certification authorities (estimated 200hrs for senior level personnel) |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE
| 6.4 | Activities related to dissemination of results (webinar and Project Site Description) |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE | IV.4
V. INPUT FOR ASSESSMENT OF THE OFFER
INPUT FOR ASSESSMENT OF THE PRICE CRITERION - Fixed prices/rates
Weighing
| Option 1/3 | Total cost for executing the survey excluding WAITING ON WEATHER / risk sharing | Survey works |  |  |  | 0 | 50%
|  |  | Expected costs for WOW for Vessel 1 |  |  |  | FILL UNIT RATE
|  |  | Expected costs for WOW for Vessel 2 |  |  |  | 0
|  |  | Expected costs for WOW for Vessel 3 |  |  |  | 0 |  |  | IV.5
|  |  | Expected costs for WOW for Vessel 4 |  |  |  | 0
|  |  | Webinar Activities |  |  |  | FILL UNIT RATE
| Option 2 | Total cost for executing the survey including WAITING ON WEATHER | Survey works |  |  |  | 0 | 50% |  | V.0
Allowance for WOW for Vessel 1
|  |  | Allowance for WOW for Vessel 2 | [6 empty] | V.1
Allowance for WOW for Vessel 3
Allowance for WOW for Vessel 4
|  |  | Webinar Activities |  |  |  | FILL UNIT RATE
| TOTAL VIRTUAL PRICE for assessment | [6 empty] | 0
|  |  | Max. number of points that can be awarded |  |  |  |  | 20 |  | V.2
|  |  | Minimum Price (determined by CLIENT) |  |  |  |  | 6000000
|  |  | Maximum Price (determined by CLIENT) |  |  |  |  | 9000000
|  |  | Points gained for the TOTAL PRICE proposed: |  |  |  |  | 0 | Points
INPUT FOR ASSESSMENT OF THE COMPLETION DATE / CYCLE TIME CRITERION (Ability to finalize the offshore campaign at the preferred end date as set by CLIENT):
| Key Completion Dates |  | Desired date for delivery of preliminary CPT results of HPA |  |  |  |  | 2021-04-01
|  |  | Desired OFFSHORE COMPLETION DATE (7b) set by CLIENT (incl. WOW) |  |  |  |  | 2021-05-20
|  |  | Ultimate OFFSHORE COMPLETION DATE (7b) set by CLIENT (incl. WOW) |  |  |  |  | 2021-05-31
[7 empty] | OFFSHORE COMPLETION DATE determined by input TENDERER | 2020-12-27 |  | V.3
[7 empty] | Desired date for DELIVERY OF FINAL SEABED IN SITU TESTING REPORT set by CLIENT (incl. WOW) | 2021-06-14
[7 empty] | Ultimate date for DELIVERY OF FINAL SEABED IN SITU TESTING REPORT set by CLIENT (incl. WOW) | 2021-07-29
[7 empty] | DELIVERY OF FINAL SEABED IN SITU TESTING REPORT determined by input TENDERER | 2021-01-17
[7 empty] | TOTAL difference DELIVERY OF FINAL SEABED IN SITU TESTING REPORT from desired date (for assessment) | -148 | days
[7 empty] | Desired date for Delivery of FINAL SEABED SAMPLING REPORT including lab testing, set by CLIENT (incl. WOW) | 2021-07-18
[7 empty] | Ultimate date of FINAL SEABED SAMPLING REPORT including lab testing by CLIENT (incl. WOW) | 2021-09-01 |  | V.4
[7 empty] | DELIVERY OF FINAL SEABED SAMPLING REPORT Date determined by input TENDERER | 2021-01-10
[7 empty] | TOTAL difference DELIVERY OF FINAL SEABED SAMPLING REPORT from desired date (for assessment) | -189 | days | V.5
|  |  | Max. number of points that can be awarded |  |  |  |  | 12
[5 empty] | Points for the TOTAL CYCLE TIME proposed: |  |  | 12 | Points
V.5
| TOTAL POINTS GAINED BY TENDERER | [6 empty] | 12 | Points
VI. NOTES | [9 empty] | V.5
| I.0 | IN CASE A CELL IN THIS ANNEX 4a IS COLORED RED AS SHOWN IN THIS CELL THE PROPOSAL IS NOT VALID.
| I.0 | TENDERER to check verify whether: - The checkboxes for the different equipment items (PCPT¦SCPT¦DT¦TC¦VC) have been checked once; - The project documentation is finalized 3 days before the first mobilisation date as set by TENDERER; - The planned OFFSHORE COMPLETION DATE (incl. WAITING ON WEATHER) is not later than the ultimate date set by CLIENT; - The planned completion date for the final report is not later than the ultimate date set by CLIENT; - The TOTAL VIRTUAL PRICE is within the range set by CLIENT; - Cycle times are within ranges allowed by CLIENT
| I.0 | All numbers indicated in green are starting points set by CLIENT.
| I.0 | All numbers indicated in blue (yellow cells) are to be provided by TENDERER and will form part of the PRICING SCHEDULE / CONTRACT PRICE as included in Annex 6 - Contract Section IV (Remuneration), and/or KEY DATES as included in Annex 6 - Contract Section VI (Scope of Work). All quantities will be used for assessment purposes and will also be the basis for determining the final CONTRACT PRICE and KEY DATES for these activities to be carried out under the CONTRACT. IN CASE THE BLUE TEXT TURNS RED, THIS MEANS THAT TENDERER ENTERED A VALUE OUTSIDE THE ALLOWABLE RANGES. This colour coding is for convenience only; the TENDERER is responsible for ensuring that the correct values are submitted by the TENDERER.
| II.0 | TENDERER shall specify the vessels with which the survey shall be carried out and indicate which equipment is operated from which vessel. TENDERER may carry out the surveys with 1,2,3 or 4 vessels. In case TENDERER intends to carry out the survey in separate passes with one vessel, TENDERER shall specify the same vessel for different parts (as limitation might be different). In case the different parts are carried out with two vessels TENDERER shall specify the vessel used for each part. The PCPT ¦ SCPT ¦ DT ¦ TC ¦ VC check boxes must at least be checked once indicating which survey equipment will be used on which vessel during each Part. The combination of survey equipment items to run from one vessel shall be compliant with the Annex 6 - Contract Section VI (Scope of Work) At CONTRACT award, the values specified in this Annex 4 shall be taken over in Annex 6 - Contract Section IV (Remuneration)
| II.0 | TENDERER to provide limiting operational conditions and minimum required weather window to perform the survey for the vessels proposed. These data are input for adverse weather determination as specified in Annex 6 - Contract Section VII (Quality requirements & Administrative instructions) - chapter 8 TENDERER shall specify for each Part the limiting operational conditions of the vessel including equipment for the execution of the survey works. In case the same vessel is used for different Parts, different limiting operational conditions may be specified as a result of the different survey equipment used for each Part.
| II.0 | The Vibrocore have to be performed from the vessel used for Seabed CPT testing of for the borehole.
| II.1 | The workability % is automatically determined through extracting the workability at the specified limiting conditions from the persistence tables in tab [U10-wave]. TENDERER shall specify the number of WAITING ON WEATHER days to be included and if this deviates from the calculated value, an explanation should be provided. These days will be taken over as the WAITING ON WEATHER ALLOWANCE DAYS in Annex 6 - Contract Section IV (Remuneration)
| II.2 | TENDERER shall specify the cycle times for executing the works. Based upon these cycle times, the key dates are determined. At CONTRACT award these dates will be taken over in Annex 6 - Contract Section VI (Scope of Work) / Table 1 Please note that Liquidated Damages become applicable in case TENDERER fails to meet Key Dates as per Annex 6 - Contract Section III (Conditions of Contract)- Clause 42!
| III.1 | TENDERER to provide the number of days required for preparing & updating after review 1 & 2 of project documentation. Dates 2a-g are generated automatically based on these cycle times. Finalization of project documentation must be 3 days before the actual commencement of the offshore work (project documentation to comply with requirements as stated in Annex 6).
| III.1 | In case the finalization date of the project documentation is later than 3 days before the start of the mobilization, this cell is coloured red. This means that the time allowed for preparation is not sufficient in relation to the planned mobilisation date and as such the proposal not valid!
| III.2 | TENDERER to include the quantities of measurements to be performed with each vessel. Cell x is colored red if the total quantities do not match the values in cells J8-12.
| III.3 | The latest of the dates 3o, 4o, 5o and 6o is the OFFSHORE COMPLETION DATE (including WAITING IN WEATHER) and are compared to the desired offshore completion date for assessment.
The number of WAITING ON WEATHER DAYS is automatically determined in tab [WDT Calculation] based upon the end of mobilisation (incl. transit to site), limiting conditions and cycle times given by TENDERER and the persistence percentages given in tab [U10-wave]. The automatic calculation of WAITING ON WEATHER is for information only. The TENDERER shall specify the number of WAITING ON WEATHER DAYS, accounting more detailed limits than specified in this Annex 4. If there is a significant difference (>25%) between the automatically-calculated and TENDERER-calculated WAITING ON WEATHER days, TENDERER shall explain the reason for this difference. The explanation will be used in the evaluation of the vessel and equipment according to Annex 3. The number of WAITING ON WEATHER days shall be input for WAITING ON WEATHER ALLOWANCE DAYS dependent on the chosen weather downtime option and weather down time principles as specified in Annex 6 - Contract Section IV (Remuneration) and Annex 6 - Contract Section VII (Quality requirements & Administrative instructions).
| III.4 | IN CASE THE OFFSHORE COMPLETION DATE IS LATER THAN 31/5/2021 THIS CELL IS COLORED RED. THIS MEANS THAT THE OFFSHORE COMPLETION DATE IS LATER THAN THE ULTIMATE DUE DATE AND AS SUCH THE PROPOSAL NOT VALID!
| III.5 | Please note that CLIENT has set a maximum duration after the OFFSHORE COMPLETION DATE for delivery of the reports.
| IV.0 | At Contract award, all rates specified in this Annex 4a shall be taken over in the PRICING SCHEDULE in Annex 6 - Contract Section IV (Remuneration). See sheet [Remuneration Table] for the table and its format as will be used in Annex 6 - Contract Section IV (Remuneration)
| IV.1 | Price/m for PCPT/SCPT between 50 m and 60 m is automatically set to double that for PCPT from 0 m to 50 m (item 2.3 or 2.8)
| IV.2 | Thermal conductivity tests to include specific heat capacity. Tests include duplicate tests on two separate specimens from one sample and testing at five different densities.
| IV.3 | The automatically generated number of WAITING ON WEATHER days shall be input for adverse weather determinations as the WAITING ON WEATHER ALLOWANCE DAYS in case "Option 2: Lump sum including weather scenario" and "Option 3: Lump sum including risk sharing mechanism on weather downtime" is chosen. At Contract award the values specified in this Annex 4a shall be taken over in Annex 6 - Contract Section IV (Remuneration)
| IV.4 | Lump sum for Activities related to dissemination of results (webinar and Project Site Description) shall be paid upon completion of the webinar and PSD, in accordance with Annex 6 - Contract Section IV (Remuneration).
| V.0 | The number of points that can be awarded is determined through linear interpolation between the minimum and maximum price. IN CASE THE TOTAL VIRTUAL PRICE OFFERED IS HIGHER THAN THE MAXIMUM PRICE THEN THE PROPOSAL IS NOT VALID!
| V.1 | The cost for WAITING ON WEATHER are calculated automatically based upon the automatically generated number of WAITING ON WEATHER DAYS and the standby rates for the vessel(s) as specified by TENDERER under items 5.1 and 5.2. The cost determined here are used determining the TOTAL VIRTUAL PRICE as explained in the Tender Document section 5.2.6
| V.2 | TENDERER shall specify the allowance for WAITING ON WEATHER in case "Option 2: Lumpsum including weather" is chosen. This WAITING ON WEATHER ALLOWANCE shall cover all WEATHER DOWNTIME that could be encountered during the execution of the works. At Contract award the values specified in this Annex 4a shall be taken over in Annex 6 - Contract Section IV (Remuneration)
| V.3 | The TOTAL VIRTUAL PRICE is determined by averaging the weather down time scenarios. Weather downtime options and weather down time principles are specified in Annex 6 - Section IV (Remuneration) and Annex 6 - Section VII (Quality requirements & Administrative instructions). IN CASE THE TOTAL VIRTUAL PRICE OFFERED IS HIGHER THAN THE MAXIMUM PRICE THAN THE PROPOSAL IS NOT VALID!
| V.4 | The TENDERER gains points when able to complete the works and deliver the final report close to or before the date desired by CLIENT. The number of points that is awarded is determined through linear interpolation between the minimum and maximum number of days. In case the completion date is later than the Ultimate date set by CLIENT the proposal will be rejected! The weather downtime days as specified by the TENDERER are included in the calculation of the OFFSHORE COMPLETION DATES.
| V.5 | IN CASE THIS DATE IS LATER THAN IS LATER THAN THE ULTIMATE DUE DATE SET BY THE CLINET THIS CELL IS COLORED RED. THIS MEANS THE PROPOSAL NOT VALID!
Formulas:
Ww (hrs) = [Ww (hrs), row below]-buffer
DT
VC
TC
DT
VC
TC
SCPT
SCPT
PCPT
PCPT
DT
VC
TC
SCPT
PCPT
DT
VC
TC
SCPT
PCPT

## Key dates
in green, bold and underlined key date for which contractor is liable for liquidated damages in case of failure to complete these dates
No. | Description | Date
1a | COMMENCEMENT DATE WORK | 2020-12-03
2e | Project documentation final | 2020-12-24
3a | Start of Mobilisation - Lot 1 | 0
3c | Start of survey WORK - Lot 1 | 0
7a | Intermediate delivery milestone: preliminary CPT results of HPA | 0
7b | Offshore completion date - Lot 1 (incl. WAITING ON WEATHER)* | 2020-12-27
7m | 1st version "Operations Report (Lot 1)" | 2020-12-27
7o | Final Version of "Operations Report (Lot 1)" | 2021-01-10
7c | 1st Version (Field Report) "Seabed In Situ Testing Report"* | 2020-12-27
7e | 2nd Version "Seabed In Situ Testing Report"* | 2021-01-10
7g | Final Version "Seabed In Situ Testing Report"* | 2021-01-17
7h | Delivery of 1st Version (Field Report) "Seabed Sampling Report"* | 2020-12-27
7j | 2nd version "Seabed Sampling Report" (including onshore lab testing)* | 2021-01-03
7l | Final version of "Seabed Sampling Report"* | 2021-01-10
|  |  |  | Survey type | Dates
[5 empty] | Start Mob | Start work
|  |  | A | SB | 0 | 0
|  |  | B |  | 0 | 0
|  |  | C |  | 0 | 0
|  |  | D | SB | 0 | 0
|  |  | SB | SB | 0 | 0
|  |  | DH | DH | 0 | 0
Note on I28: [Opmerkingenthread] U kunt deze opmerkingenthread lezen in uw versie van Excel. Eventuele wijzigingen aan de thread gaan echter verloren als het bestand wordt geopend in een nieuwere versie van Excel. Meer informatie: https://go.microsoft.com/fwlink/?linkid=870924 Opmerking: This appears relate to DownHole work - remove?

## U10-wave
Weather window (%) |  | Month | January |  |  | February |  |  | March |  |  | April |  |  | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December
|  | Quantile | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80%
duration (h) | Hm0 (m) < | U10 (m/s) < | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12
1 | 0.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0.8 | 0 | 0 | 1.4 | 0.3 | 0 | 0.8 | 0.4 | 0 | 1.2 | 0.3 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 0 | 3.2 | 0.4 | 0 | 5.1 | 1.1 | 0 | 3 | 1.3 | 0 | 5.2 | 1.6 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 6.9 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.5 | 2 | 0.1 | 0 | 0 | 0.6 | 0.1 | 0 | 0.9 | 0.1 | 0 | 2.3 | 1 | 0.3 | 3.2 | 1.1 | 0.3 | 4.4 | 2.5 | 0.5 | 4.5 | 2.2 | 0.8 | 3.6 | 1.5 | 0.9 | 2.4 | 1 | 0.1 | 0.8 | 0 | 0 | 0.4 | 0 | 0 | 0.7 | 0.1 | 0
1 | 0.5 | 4 | 2 | 0.1 | 0 | 3.3 | 2.2 | 0 | 6 | 1.5 | 0 | 9.3 | 4.3 | 1.9 | 10.7 | 4.4 | 2.3 | 14 | 9.2 | 3.5 | 14.1 | 9 | 5.3 | 15.2 | 8.6 | 5.5 | 9.6 | 5 | 1.9 | 3.4 | 1.5 | 0 | 2.5 | 0.4 | 0 | 3 | 0.8 | 0
1 | 0.5 | 6 | 4.3 | 0.4 | 0 | 6 | 2.8 | 0 | 9.1 | 2.8 | 0.5 | 16.6 | 8.5 | 4.7 | 18.3 | 10.3 | 6.1 | 22.5 | 15.7 | 6.8 | 28.1 | 18.3 | 9 | 24.9 | 16 | 8.7 | 17 | 9 | 2.8 | 5.4 | 2.3 | 0.2 | 3.1 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 8 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.5 | 9 | 5.2 | 21.5 | 12.9 | 6.7 | 25.8 | 17.8 | 8 | 31.3 | 20.7 | 10.3 | 26.6 | 17.3 | 9.3 | 18.2 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 9 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 10 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 11 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 12 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 15 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 20 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 25 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.75 | 2 | 0.5 | 0.1 | 0 | 2 | 0.4 | 0 | 2.2 | 0.8 | 0.1 | 3.9 | 1.8 | 1.2 | 4.1 | 1.9 | 0.9 | 5.5 | 3.2 | 1.6 | 5.1 | 3 | 1.5 | 4.3 | 3 | 1.5 | 3.1 | 2.2 | 0.7 | 1.2 | 0.5 |  | 0.9 | 0.3 | 0 | 1.1 | 0.4 | 0
1 | 0.75 | 4 | 4.6 | 1.3 | 0.1 | 8.1 | 4.3 | 0.4 | 9.4 | 4.4 | 1.8 | 15.6 | 8.5 | 5.6 | 15.3 | 9.3 | 5.8 | 20.7 | 15.3 | 8.6 | 19.7 | 13.8 | 10.2 | 21 | 14.8 | 8.1 | 15 | 10.1 | 5.7 | 7.1 | 3.2 | 1 | 4.7 | 2.5 | 0.6 | 6 | 2.6 | 0.8
1 | 0.75 | 6 | 11.3 | 4.3 | 0.7 | 14.8 | 8.9 | 2 | 20.8 | 10.3 | 5.9 | 28.8 | 17.4 | 13.5 | 30.6 | 21.9 | 15.6 | 38.4 | 27.8 | 16.9 | 38 | 30.6 | 22.8 | 39.3 | 28.1 | 19.2 | 28.3 | 20.6 | 11.4 | 14.5 | 7.8 | 3.6 | 11.3 | 5.6 | 1.8 | 12.4 | 6.3 | 1.5
1 | 0.75 | 8 | 17.1 | 6 | 0.7 | 18.2 | 11.4 | 2.9 | 26.9 | 13.3 | 8.6 | 36.3 | 23.3 | 16.4 | 37.3 | 30.1 | 20.9 | 46.2 | 37.5 | 23.8 | 51.3 | 38.7 | 29.8 | 47.1 | 38.2 | 27 | 35.9 | 27.6 | 14 | 18.8 | 10.8 | 5.6 | 13.1 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 9 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.7 | 24.2 | 16.8 | 39.7 | 30.6 | 23.6 | 47.5 | 38.1 | 24.8 | 52.8 | 41.1 | 30.7 | 48.7 | 39.5 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.8 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 10 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.2 | 23.9 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.8 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 11 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.3 | 24 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.9 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 12 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.3 | 24 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.9 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 15 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.3 | 24 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.9 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 20 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.3 | 24 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.9 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 25 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.3 | 24 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.9 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 1 | 2 | 1.3 | 0.3 |  | 2.2 | 0.6 | 0.1 | 2.9 | 1.3 | 0.3 | 4.3 | 2.5 | 1.5 | 4.5 | 2.3 | 1.1 | 6 | 3.9 | 2 | 6 | 3.6 | 1.8 | 5.1 | 3.4 | 1.7 | 3.6 | 2.5 | 1.1 | 1.7 | 0.8 | 0.4 | 1.6 | 0.4 |  | 1.4 | 0.7 | 0.1
1 | 1 | 4 | 6.2 | 2.7 | 0.9 | 10.6 | 5.7 | 2 | 12.6 | 6.9 | 2.5 | 18.2 | 11.7 | 8 | 17.2 | 13 | 7.8 | 23.7 | 17.9 | 11.9 | 23 | 17.1 | 11.7 | 23.4 | 16.9 | 11.3 | 16.4 | 11.3 | 7.6 | 10.1 | 5.1 | 2.9 | 7.2 | 3.9 | 1.7 | 7.3 | 3.6 | 1.2
1 | 1 | 6 | 17.4 | 9 | 2.4 | 20.2 | 14.7 | 5.5 | 27.6 | 16.3 | 9 | 37.2 | 25.4 | 19.7 | 37.4 | 29 | 22.1 | 46.8 | 36.3 | 27.9 | 46.3 | 36.7 | 28.3 | 45.1 | 33.6 | 27.1 | 35.2 | 28.2 | 19.1 | 22.3 | 12.5 | 7.2 | 16.4 | 9.2 | 5.3 | 18.6 | 8.7 | 3.7
1 | 1 | 8 | 26.4 | 13.8 | 3.5 | 30.4 | 20.2 | 10.5 | 37.7 | 26.2 | 16.3 | 52.8 | 38.8 | 29.9 | 53.1 | 46.1 | 36.1 | 63.1 | 53.1 | 42.9 | 66.8 | 56.2 | 42.1 | 62.8 | 51.7 | 42.3 | 48.3 | 41.1 | 29.8 | 30.5 | 19.8 | 10.8 | 25.3 | 15.3 | 7.7 | 26.2 | 12.5 | 6.2
1 | 1 | 9 | 27 | 15.1 | 3.8 | 31.6 | 21.3 | 10.8 | 40.4 | 29.3 | 18.5 | 55.5 | 40.6 | 32.2 | 58.6 | 48.9 | 38.4 | 66.5 | 55.8 | 46.7 | 71.1 | 61.3 | 46.8 | 67.8 | 54.8 | 45.4 | 52.1 | 43.6 | 31.7 | 32.5 | 22.7 | 12.1 | 26.7 | 16.3 | 7.8 | 27.6 | 12.8 | 6.6
1 | 1 | 10 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.8 | 40.9 | 29.7 | 19.1 | 56.3 | 41.7 | 32.7 | 60.5 | 50.9 | 40 | 67.2 | 57.1 | 48.5 | 72.1 | 62.9 | 48.4 | 68.7 | 56 | 46.7 | 53.4 | 45.1 | 32.4 | 32.9 | 23.8 | 12.6 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1 | 11 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.9 | 40.9 | 30 | 19.1 | 56.5 | 41.8 | 32.9 | 60.6 | 51.1 | 40.3 | 67.3 | 57.1 | 48.6 | 72.3 | 62.9 | 48.5 | 69.2 | 56.3 | 46.9 | 53.6 | 45.4 | 32.4 | 32.9 | 23.8 | 12.7 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1 | 12 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.9 | 40.9 | 30 | 19.1 | 56.5 | 41.8 | 33 | 60.6 | 51.2 | 40.3 | 67.3 | 57.1 | 48.8 | 72.3 | 63 | 48.5 | 69.2 | 56.5 | 46.9 | 53.6 | 45.4 | 32.4 | 32.9 | 23.8 | 12.7 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1 | 15 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.9 | 40.9 | 30 | 19.1 | 56.5 | 41.8 | 33 | 60.6 | 51.3 | 40.3 | 67.3 | 57.1 | 48.8 | 72.3 | 63 | 48.5 | 69.2 | 56.5 | 46.9 | 53.6 | 45.4 | 32.4 | 32.9 | 23.8 | 12.7 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1 | 20 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.9 | 40.9 | 30 | 19.1 | 56.5 | 41.8 | 33 | 60.6 | 51.3 | 40.3 | 67.3 | 57.1 | 48.8 | 72.3 | 63 | 48.5 | 69.2 | 56.5 | 46.9 | 53.6 | 45.4 | 32.4 | 32.9 | 23.8 | 12.7 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1 | 25 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.9 | 40.9 | 30 | 19.1 | 56.5 | 41.8 | 33 | 60.6 | 51.3 | 40.3 | 67.3 | 57.1 | 48.8 | 72.3 | 63 | 48.5 | 69.2 | 56.5 | 46.9 | 53.6 | 45.4 | 32.4 | 32.9 | 23.8 | 12.7 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1.25 | 2 | 1.3 | 0.5 |  | 2.5 | 1 | 0.1 | 3 | 1.5 | 0.4 | 4.3 | 2.8 | 1.8 | 4.5 | 3.4 | 1.3 | 6 | 4.2 | 2.1 | 6 | 3.6 | 1.8 | 5.7 | 3.4 | 1.7 | 3.9 | 2.5 | 1.3 | 2.2 | 1.1 | 0.5 | 1.7 | 0.6 | 0.3 | 1.8 | 0.8 | 0.2
1 | 1.25 | 4 | 6.7 | 3.6 | 1.7 | 12.3 | 7.9 | 2.9 | 14.3 | 8.6 | 3.9 | 19.6 | 12.5 | 9.6 | 18.9 | 14.1 | 9.3 | 25.3 | 20 | 12.9 | 23.9 | 17.6 | 12.1 | 25.5 | 17.3 | 11.7 | 18 | 12.2 | 8.2 | 11.4 | 6 | 3.8 | 8.5 | 5 | 2.8 | 9.5 | 4.3 | 2.2
1 | 1.25 | 6 | 23.2 | 10.2 | 5.8 | 25.4 | 17.7 | 7.2 | 29 | 20.7 | 12.6 | 40.1 | 28.6 | 23.3 | 40 | 32.1 | 25.8 | 50.7 | 41.3 | 31.9 | 48.5 | 39.8 | 31 | 46.3 | 36.2 | 30.6 | 38.3 | 30.6 | 20.5 | 25.8 | 16.1 | 11 | 21.1 | 12.9 | 7.9 | 22.9 | 12 | 5.5
1 | 1.25 | 8 | 35.6 | 21.5 | 10.2 | 37.5 | 28.6 | 13.3 | 48.2 | 34.7 | 23.2 | 59.8 | 47.4 | 40.2 | 59.4 | 53.9 | 46.3 | 72.1 | 61.4 | 50.6 | 72.7 | 64.8 | 51.1 | 70.1 | 59.5 | 50.1 | 57.5 | 48.6 | 36.7 | 38.1 | 27.7 | 19.8 | 34 | 23.5 | 13.6 | 34.9 | 19.8 | 12.4
1 | 1.25 | 9 | 37.8 | 24.5 | 11.2 | 42.7 | 32.4 | 16.2 | 52.1 | 42.3 | 28.2 | 66.3 | 54.3 | 45.4 | 69.4 | 60.6 | 53.8 | 78.4 | 68.6 | 58.2 | 79.8 | 73.3 | 58.2 | 75.5 | 67.7 | 56.7 | 64.3 | 52.9 | 40.7 | 43.2 | 33.5 | 22.3 | 38.1 | 28.1 | 15.9 | 37.3 | 23 | 15
1 | 1.25 | 10 | 39.8 | 24.7 | 12.1 | 46.2 | 33.5 | 17 | 55.2 | 43.4 | 29.3 | 70.4 | 56.8 | 46.9 | 74.6 | 64.8 | 58.2 | 81.2 | 73.2 | 61.5 | 84.2 | 77.4 | 60.8 | 79 | 69.9 | 59.8 | 66.6 | 57.2 | 43.3 | 45.5 | 35.9 | 23.7 | 39.6 | 29 | 16.6 | 38.1 | 23.8 | 15.9
1 | 1.25 | 11 | 40.1 | 25 | 12.2 | 46.6 | 33.9 | 17.8 | 55.9 | 44.5 | 29.4 | 72.2 | 58.1 | 47.8 | 75.7 | 66.4 | 60.4 | 81.5 | 74.6 | 62.6 | 85.3 | 78.6 | 62.6 | 79.7 | 71.8 | 61.3 | 67 | 58.8 | 44.1 | 45.9 | 36.7 | 24 | 39.8 | 29.4 | 16.6 | 38.5 | 23.8 | 16
1 | 1.25 | 12 | 40.1 | 25 | 12.2 | 46.8 | 33.9 | 17.9 | 56.3 | 44.8 | 29.5 | 72.2 | 58.3 | 47.9 | 75.8 | 66.4 | 60.7 | 81.5 | 74.7 | 63.2 | 85.3 | 78.8 | 63.2 | 79.9 | 71.8 | 61.6 | 67.2 | 58.8 | 44.1 | 46 | 36.8 | 24 | 39.8 | 29.4 | 16.6 | 38.5 | 23.8 | 16
1 | 1.25 | 15 | 40.2 | 25 | 12.2 | 46.8 | 33.9 | 18 | 56.3 | 44.8 | 29.5 | 72.2 | 58.3 | 47.9 | 75.8 | 66.4 | 60.8 | 81.5 | 74.7 | 63.2 | 85.3 | 78.9 | 63.5 | 79.9 | 71.8 | 61.6 | 67.2 | 58.8 | 44.1 | 46 | 36.8 | 24 | 39.9 | 29.4 | 16.6 | 38.5 | 23.8 | 16
1 | 1.25 | 20 | 40.3 | 25 | 12.2 | 46.8 | 33.9 | 18 | 56.3 | 44.8 | 29.5 | 72.2 | 58.3 | 47.9 | 75.8 | 66.4 | 60.8 | 81.5 | 74.7 | 63.2 | 85.3 | 78.9 | 63.5 | 79.9 | 71.8 | 61.6 | 67.2 | 58.9 | 44.1 | 46 | 36.8 | 24 | 39.9 | 29.4 | 16.6 | 38.5 | 23.8 | 16
1 | 1.25 | 25 | 40.3 | 25 | 12.2 | 46.8 | 33.9 | 18 | 56.3 | 44.8 | 29.5 | 72.2 | 58.3 | 47.9 | 75.8 | 66.4 | 60.8 | 81.5 | 74.7 | 63.2 | 85.3 | 78.9 | 63.5 | 79.9 | 71.8 | 61.6 | 67.2 | 58.9 | 44.1 | 46 | 36.8 | 24 | 39.9 | 29.4 | 16.6 | 38.5 | 23.8 | 16
1 | 1.5 | 2 | 1.4 | 0.7 | 0.1 | 3.2 | 1.1 | 0.3 | 3.1 | 1.5 | 0.4 | 4.6 | 2.8 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 3.9 | 2.5 | 1.3 | 2.2 | 1.1 | 0.5 | 1.8 | 0.8 | 0.3 | 2.2 | 0.8 | 0.3
1 | 1.5 | 4 | 8.4 | 3.9 | 2.2 | 13.3 | 8.2 | 3.3 | 14.5 | 9 | 4.5 | 19.6 | 13.9 | 10.6 | 19.1 | 14.8 | 9.6 | 25.4 | 20.7 | 13.4 | 23.9 | 17.7 | 12.5 | 25.7 | 17.3 | 12.1 | 18.3 | 12.5 | 8.9 | 11.5 | 7 | 3.9 | 9.4 | 5.6 | 3.5 | 11.5 | 5.2 | 2.9
1 | 1.5 | 6 | 25.1 | 12.5 | 6.7 | 27.5 | 18.8 | 8.8 | 31 | 23 | 14.7 | 40.9 | 30.7 | 27.2 | 40.6 | 33.3 | 26.9 | 51.4 | 41.9 | 32.7 | 50.1 | 40.5 | 31.8 | 49.2 | 39 | 32 | 39.7 | 31.7 | 22 | 27.2 | 19.1 | 12.5 | 22 | 16 | 9.3 | 24.5 | 14.4 | 7.1
1 | 1.5 | 8 | 39.8 | 26.2 | 14.4 | 42.3 | 33.3 | 17.9 | 49.9 | 37.9 | 28.5 | 63 | 51 | 44.8 | 63.8 | 57.3 | 48.6 | 75 | 65.1 | 55.2 | 75.1 | 67.3 | 56.6 | 72.1 | 63.2 | 51.7 | 61.2 | 51.5 | 42.8 | 43.1 | 32.4 | 23.5 | 39.6 | 29.2 | 19.3 | 38.6 | 24.6 | 15.5
1 | 1.5 | 9 | 43.9 | 32.3 | 17.4 | 52.1 | 41.2 | 22.5 | 61.9 | 48 | 37.1 | 71 | 59.6 | 53.1 | 74.5 | 66.1 | 58.8 | 83 | 75.4 | 65.8 | 82.5 | 76.7 | 66.5 | 79.6 | 71.4 | 61.3 | 67.9 | 60 | 49.9 | 49.5 | 39.9 | 29.8 | 45.7 | 35.6 | 23.4 | 43.5 | 29 | 19.5
1 | 1.5 | 10 | 47.2 | 34.8 | 20.4 | 59.1 | 46.3 | 26.8 | 67.9 | 53.2 | 42 | 77.8 | 65.8 | 56.8 | 81 | 72.8 | 67.4 | 87.8 | 81.7 | 71.3 | 89.2 | 83.5 | 72.7 | 85.8 | 77.4 | 67.4 | 75.8 | 65.1 | 54.9 | 57.4 | 45.2 | 34.8 | 52.8 | 38.2 | 26.3 | 47.6 | 32.5 | 23.1
1 | 1.5 | 11 | 49.2 | 36 | 21.5 | 60.7 | 48.2 | 27.6 | 71.1 | 54.7 | 44 | 81.6 | 70 | 60.4 | 84 | 78.1 | 69.9 | 89.5 | 84 | 74.7 | 92.3 | 86.2 | 75.8 | 87.5 | 79.6 | 70.6 | 77.9 | 67.8 | 57.3 | 61 | 48.7 | 36.8 | 55.7 | 39.3 | 27.3 | 50.2 | 34.1 | 23.5
1 | 1.5 | 12 | 49.5 | 36.3 | 22.1 | 60.9 | 49 | 27.9 | 72.1 | 55.1 | 44.3 | 82.4 | 71.8 | 61.3 | 84.6 | 79.3 | 71.3 | 90 | 84.2 | 75.8 | 93.3 | 86.6 | 76.1 | 88 | 79.7 | 71.2 | 78.1 | 68.9 | 57.8 | 62 | 49.6 | 37.3 | 56 | 39.9 | 28.1 | 50.7 | 34.9 | 23.7
1 | 1.5 | 15 | 49.6 | 36.6 | 22.2 | 61 | 49 | 28 | 72.1 | 55.5 | 44.4 | 82.7 | 71.9 | 61.3 | 85.1 | 79.3 | 71.6 | 90 | 84.3 | 75.8 | 93.4 | 87.1 | 76.1 | 88.1 | 79.8 | 71.7 | 78.3 | 68.9 | 57.8 | 62.1 | 49.9 | 37.3 | 56.2 | 39.9 | 28.1 | 50.8 | 35.1 | 23.7
1 | 1.5 | 20 | 49.6 | 36.6 | 22.2 | 61 | 49 | 28 | 72.1 | 55.5 | 44.4 | 82.7 | 71.9 | 61.3 | 85.1 | 79.3 | 71.6 | 90 | 84.3 | 75.8 | 93.4 | 87.1 | 76.1 | 88.1 | 79.8 | 71.7 | 78.3 | 68.9 | 57.8 | 62.1 | 49.9 | 37.3 | 56.2 | 39.9 | 28.1 | 50.8 | 35.1 | 23.7
1 | 1.5 | 25 | 49.6 | 36.6 | 22.2 | 61 | 49 | 28 | 72.1 | 55.5 | 44.4 | 82.7 | 71.9 | 61.3 | 85.1 | 79.3 | 71.6 | 90 | 84.3 | 75.8 | 93.4 | 87.1 | 76.1 | 88.1 | 79.8 | 71.7 | 78.3 | 68.9 | 57.8 | 62.1 | 49.9 | 37.3 | 56.2 | 39.9 | 28.1 | 50.8 | 35.1 | 23.7
1 | 1.75 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.5 | 4.6 | 2.8 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4 | 2.8 | 1.3 | 2.3 | 1.2 | 0.5 | 1.9 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 1.75 | 4 | 8.8 | 4 | 2.5 | 13.8 | 8.6 | 3.9 | 14.7 | 9.1 | 6.1 | 19.6 | 14.4 | 10.9 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.3 | 11.6 | 7.3 | 4.2 | 9.8 | 6 | 3.5 | 12.3 | 5.6 | 2.9
1 | 1.75 | 6 | 25.8 | 13.8 | 7.7 | 28.7 | 20.5 | 11.2 | 31.1 | 23.9 | 17 | 42.5 | 32.2 | 27.3 | 40.8 | 34.3 | 27 | 51.6 | 42.5 | 33 | 50.1 | 40.5 | 32.3 | 49.3 | 39.1 | 32.1 | 39.9 | 32.1 | 22.6 | 27.4 | 19.5 | 12.8 | 23.2 | 17.5 | 10.5 | 25.2 | 15.3 | 7.4
1 | 1.75 | 8 | 42.3 | 28.9 | 16.2 | 45.6 | 36.6 | 21.5 | 51.7 | 41 | 34.8 | 64.3 | 53.5 | 47.6 | 64.6 | 59 | 49.5 | 76.3 | 65.6 | 57.6 | 75.6 | 67.6 | 58.4 | 72.4 | 63.8 | 52.7 | 63.4 | 53.3 | 45.4 | 45.3 | 33.7 | 25.9 | 42.4 | 32.4 | 20.5 | 40.3 | 27.7 | 17.8
1 | 1.75 | 9 | 49.9 | 34.8 | 21.3 | 56.4 | 46 | 27 | 66.4 | 50.7 | 41.9 | 72.3 | 63.2 | 57.8 | 76.2 | 67.9 | 61.1 | 85.4 | 76.9 | 68.1 | 83.6 | 78.6 | 68.9 | 82.2 | 72.3 | 62.9 | 71.6 | 63.5 | 54.5 | 52.6 | 41.7 | 34.7 | 49.5 | 39.3 | 27.6 | 48.3 | 32.5 | 22.9
1 | 1.75 | 10 | 53.8 | 40.6 | 28.2 | 65.6 | 52.2 | 31.2 | 73.9 | 59.7 | 46.4 | 82.6 | 72.9 | 64.4 | 84.4 | 75.8 | 71.4 | 90.8 | 85.3 | 76.3 | 90.8 | 85.3 | 77.4 | 89.2 | 78.5 | 71.3 | 78.3 | 68.5 | 59.8 | 61.1 | 49.7 | 41.8 | 57.3 | 45.1 | 32.8 | 55.5 | 39.1 | 28.9
1 | 1.75 | 11 | 57.7 | 43.5 | 33.6 | 68.6 | 57.9 | 34.4 | 77.4 | 65.9 | 51 | 87.5 | 77.8 | 69 | 88.7 | 82.8 | 77.9 | 93.6 | 88.8 | 81.5 | 95.8 | 89.5 | 81.3 | 91.5 | 83.9 | 76.6 | 82.2 | 74.6 | 64.6 | 69.3 | 57 | 47.1 | 62.4 | 49.4 | 35.3 | 58.6 | 42.6 | 30.6
1 | 1.75 | 12 | 59.4 | 45 | 36.6 | 71 | 60.1 | 36.4 | 79.9 | 67.2 | 54.4 | 87.8 | 80 | 70.1 | 90.8 | 85.9 | 81.7 | 94.5 | 89.6 | 84.2 | 96.6 | 91.1 | 82.6 | 93.4 | 85.1 | 79.3 | 83.8 | 76.3 | 66.6 | 72.9 | 59.5 | 49.8 | 64.8 | 50.1 | 37 | 61.3 | 43.4 | 31.4
1 | 1.75 | 15 | 60.3 | 45.6 | 37.1 | 71.8 | 61.2 | 37.8 | 81 | 67.7 | 56.4 | 88.7 | 80.4 | 70.7 | 91.4 | 87 | 82.9 | 94.7 | 90 | 84.6 | 96.8 | 91.7 | 83.1 | 93.5 | 85.3 | 79.8 | 84.4 | 77.1 | 67.3 | 74.2 | 60.2 | 51.8 | 65.7 | 50.1 | 38.3 | 61.8 | 44.1 | 31.8
1 | 1.75 | 20 | 60.4 | 45.6 | 37.1 | 71.8 | 61.2 | 37.8 | 81 | 67.7 | 56.4 | 88.7 | 80.4 | 70.7 | 91.4 | 87 | 82.9 | 94.7 | 90 | 84.6 | 96.8 | 91.7 | 83.1 | 93.5 | 85.3 | 79.9 | 84.4 | 77.1 | 67.3 | 74.2 | 60.2 | 51.8 | 65.8 | 50.1 | 38.3 | 61.8 | 44.1 | 31.8
1 | 1.75 | 25 | 60.4 | 45.6 | 37.1 | 71.8 | 61.2 | 37.8 | 81 | 67.7 | 56.4 | 88.7 | 80.4 | 70.7 | 91.4 | 87 | 82.9 | 94.7 | 90 | 84.6 | 96.8 | 91.7 | 83.1 | 93.5 | 85.3 | 79.9 | 84.4 | 77.1 | 67.3 | 74.2 | 60.2 | 51.8 | 65.8 | 50.1 | 38.3 | 61.8 | 44.1 | 31.8
1 | 2 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.3 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 2 | 4 | 9.2 | 4 | 2.6 | 13.8 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.4 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.3 | 11.7 | 7.4 | 4.6 | 9.8 | 6 | 3.9 | 12.6 | 5.6 | 2.9
1 | 2 | 6 | 26 | 14 | 8.4 | 29.2 | 20.8 | 11.3 | 31.3 | 23.9 | 17.3 | 43.2 | 32.9 | 27.4 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.6 | 49.3 | 39.1 | 32.1 | 40.1 | 32.1 | 23.1 | 27.5 | 20 | 12.8 | 23.3 | 17.8 | 10.7 | 26 | 15.9 | 8.1
1 | 2 | 8 | 43.5 | 29.3 | 17.4 | 48.1 | 37.4 | 22.3 | 53.5 | 42.1 | 35.7 | 64.3 | 56.1 | 48.8 | 65.1 | 59.1 | 51.1 | 76.4 | 66 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64 | 52.9 | 64 | 54.2 | 45.9 | 46.2 | 34.3 | 28.2 | 43.6 | 32.5 | 21.3 | 42.1 | 28.4 | 19.4
1 | 2 | 9 | 53.1 | 37.6 | 23.1 | 57.3 | 48.2 | 27.9 | 67.5 | 53.5 | 44 | 72.6 | 65.3 | 60.1 | 77.3 | 68.8 | 62.1 | 86.3 | 77.8 | 69.6 | 83.9 | 78.9 | 70.4 | 83.5 | 73.4 | 63.6 | 73.9 | 64.9 | 56.3 | 54.1 | 42.3 | 36.4 | 52.3 | 41.3 | 29.9 | 51.2 | 35.6 | 25
1 | 2 | 10 | 57.4 | 43.3 | 31.7 | 66.9 | 56.1 | 33.4 | 75.6 | 62.1 | 50.2 | 83.9 | 75 | 67.4 | 84.6 | 78.2 | 74 | 92.1 | 86.5 | 79.2 | 91.5 | 86.4 | 79.9 | 90.5 | 81.5 | 72.8 | 80.3 | 71 | 62.7 | 62.7 | 52.2 | 44.9 | 59.7 | 48.2 | 36.6 | 58 | 42.6 | 32.6
1 | 2 | 11 | 62.2 | 49.6 | 39.2 | 73.1 | 63.4 | 39.2 | 80.1 | 69.8 | 57.2 | 89.3 | 81.3 | 72.7 | 90.7 | 85.8 | 81.4 | 95.2 | 90.6 | 84.8 | 96.2 | 91.8 | 84 | 93.8 | 85.8 | 78.8 | 84.4 | 77.6 | 69.2 | 71.5 | 61.3 | 51.7 | 67.4 | 56.8 | 42.4 | 63.2 | 46.9 | 36.5
1 | 2 | 12 | 66.5 | 53.6 | 43.6 | 76.9 | 67.7 | 44.8 | 84.1 | 74.5 | 60.3 | 91.7 | 85.6 | 76.1 | 93.1 | 89.8 | 86.6 | 96.3 | 92.6 | 88.9 | 98.3 | 95.2 | 87.6 | 96.9 | 88.2 | 83 | 87.1 | 81.3 | 72.8 | 76 | 64.8 | 56.7 | 71.9 | 59.9 | 44.9 | 67.8 | 49.3 | 38.5
1 | 2 | 15 | 69.7 | 55.6 | 45.3 | 81.2 | 71.4 | 48.1 | 86 | 76.9 | 64.7 | 93.4 | 87.1 | 78.2 | 94.8 | 91.1 | 88.7 | 97 | 93.6 | 89.9 | 99.2 | 96.4 | 90.2 | 97.4 | 89.5 | 84.8 | 89.1 | 83.9 | 75.1 | 79.2 | 69.8 | 62.4 | 77.2 | 63.5 | 48.1 | 71 | 53.2 | 40
1 | 2 | 20 | 69.9 | 55.8 | 45.4 | 81.3 | 71.4 | 48.1 | 86 | 76.9 | 64.7 | 93.4 | 87.1 | 78.2 | 94.8 | 91.1 | 88.8 | 97 | 93.6 | 89.9 | 99.2 | 96.4 | 90.2 | 97.4 | 89.5 | 85 | 89.1 | 83.9 | 75.1 | 79.2 | 69.8 | 62.6 | 77.2 | 63.6 | 48.1 | 71 | 53.2 | 40.1
1 | 2 | 25 | 69.9 | 55.8 | 45.4 | 81.3 | 71.4 | 48.1 | 86 | 76.9 | 64.7 | 93.4 | 87.1 | 78.2 | 94.8 | 91.1 | 88.8 | 97 | 93.6 | 89.9 | 99.2 | 96.4 | 90.2 | 97.4 | 89.5 | 85 | 89.1 | 83.9 | 75.1 | 79.2 | 69.8 | 62.6 | 77.2 | 63.6 | 48.1 | 71 | 53.2 | 40.1
1 | 2.25 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 2.25 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 3.9 | 13.1 | 5.8 | 3
1 | 2.25 | 6 | 26 | 14 | 8.9 | 29.3 | 20.8 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.6 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.1 | 23.3 | 18.1 | 11.2 | 27 | 16.1 | 8.3
1 | 2.25 | 8 | 44.1 | 29.4 | 17.7 | 49.2 | 37.6 | 23.1 | 53.6 | 42.7 | 35.9 | 64.4 | 56.4 | 49 | 65.1 | 59.1 | 51.1 | 76.8 | 66.3 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.4 | 52.9 | 64.1 | 54.2 | 45.9 | 46.5 | 34.7 | 28.8 | 43.9 | 32.9 | 22 | 43.3 | 28.4 | 20.2
1 | 2.25 | 9 | 53.3 | 37.6 | 23.9 | 57.8 | 48.8 | 29.4 | 67.7 | 54.6 | 45 | 73.6 | 65.8 | 60.6 | 77.6 | 69 | 62.6 | 86.6 | 77.8 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 73.9 | 63.8 | 74 | 65 | 56.6 | 55 | 43.3 | 36.9 | 53.5 | 42.6 | 31.1 | 53 | 37.4 | 25.7
1 | 2.25 | 10 | 59.1 | 43.3 | 32.6 | 67.1 | 57.1 | 36.4 | 76 | 63.8 | 51.5 | 84.6 | 75.1 | 69.4 | 85.2 | 78.8 | 74.2 | 92.5 | 86.8 | 79.6 | 91.5 | 87 | 80.6 | 90.9 | 83.7 | 73.4 | 80.6 | 71.4 | 64.1 | 64.7 | 53.6 | 46 | 61.1 | 51.7 | 38.2 | 59.6 | 44.8 | 33.6
1 | 2.25 | 11 | 66.6 | 51.2 | 41.6 | 74.3 | 64.2 | 43.2 | 81.2 | 71.5 | 59.8 | 90 | 82.1 | 76.2 | 91.2 | 86.2 | 82.6 | 96 | 91.1 | 86 | 96.4 | 92.5 | 86.6 | 94.8 | 87.6 | 80.2 | 86.8 | 78.6 | 71.3 | 73 | 63.2 | 53.6 | 70.5 | 60.4 | 45.9 | 65.9 | 49.9 | 42.1
1 | 2.25 | 12 | 70.8 | 58.1 | 47.9 | 80.2 | 71.4 | 51.5 | 86.6 | 77.4 | 63.8 | 93.8 | 87.4 | 80.2 | 94.5 | 91.5 | 88.5 | 98.1 | 94.3 | 91 | 98.5 | 95.7 | 90.6 | 97.8 | 91.5 | 85.9 | 90.2 | 84.6 | 76 | 78.7 | 69.6 | 60.5 | 75.9 | 65.8 | 49.6 | 72.7 | 54.7 | 47.1
1 | 2.25 | 15 | 77.4 | 63 | 52.8 | 85.5 | 77.1 | 57.8 | 91.2 | 82.4 | 70.4 | 96.5 | 92.6 | 85.2 | 97 | 95.4 | 92.6 | 99.5 | 96.3 | 93.7 | 99.9 | 97.8 | 94.7 | 98.4 | 93.8 | 89.2 | 93.7 | 88.3 | 81.3 | 85.1 | 77.4 | 71.9 | 82.2 | 70.8 | 56.4 | 77.6 | 63.6 | 52
1 | 2.25 | 20 | 77.4 | 63.4 | 52.8 | 85.7 | 77.2 | 57.9 | 91.5 | 82.5 | 70.5 | 96.5 | 92.6 | 85.2 | 97 | 95.4 | 92.6 | 99.5 | 96.3 | 93.8 | 99.9 | 97.8 | 94.7 | 98.4 | 94 | 89.4 | 93.7 | 88.8 | 81.4 | 85.3 | 77.6 | 72 | 82.9 | 70.8 | 57.5 | 77.7 | 63.8 | 52.4
1 | 2.25 | 25 | 77.4 | 63.4 | 52.8 | 85.7 | 77.2 | 57.9 | 91.5 | 82.5 | 70.5 | 96.5 | 92.6 | 85.2 | 97 | 95.4 | 92.6 | 99.5 | 96.3 | 93.8 | 99.9 | 97.8 | 94.7 | 98.4 | 94 | 89.4 | 93.7 | 88.8 | 81.4 | 85.3 | 77.6 | 72 | 82.9 | 70.8 | 57.5 | 77.7 | 63.8 | 52.4
1 | 2.75 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 2.75 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 2.75 | 6 | 26 | 14 | 8.9 | 29.3 | 21.3 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.3 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 2.75 | 8 | 44.4 | 29.6 | 17.9 | 50.1 | 39.8 | 23.9 | 53.6 | 42.7 | 36 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.5 | 44.5 | 28.4 | 20.6
1 | 2.75 | 9 | 53.7 | 37.8 | 24.4 | 58 | 49.6 | 30.2 | 67.7 | 55.4 | 45.4 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.7 | 44.8 | 38.1 | 53.7 | 44.7 | 32.3 | 54.9 | 37.8 | 26.7
1 | 2.75 | 10 | 60.6 | 44.1 | 33.4 | 67.3 | 58.6 | 38.2 | 76.3 | 65.1 | 53.9 | 85.1 | 75.7 | 71.1 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 64.9 | 66.4 | 54.7 | 47.1 | 61.7 | 55 | 39 | 61.1 | 45.7 | 35.1
1 | 2.75 | 11 | 68.6 | 53.9 | 43.3 | 75.2 | 66.7 | 45.2 | 82.1 | 74.1 | 62.1 | 91.5 | 83.5 | 78.1 | 91.6 | 88 | 83.5 | 96.1 | 91.7 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 73.7 | 73.7 | 65.3 | 55.2 | 72.3 | 62.2 | 48.8 | 69.2 | 53.5 | 43.7
1 | 2.75 | 12 | 74 | 61.7 | 51.6 | 81.4 | 76.2 | 55.4 | 88.8 | 81.2 | 67.5 | 94.8 | 88.8 | 83.2 | 95.6 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.1 | 91.8 | 97.8 | 93.4 | 87.3 | 91.9 | 86.3 | 78.7 | 80 | 71.8 | 62.7 | 79.7 | 69.3 | 53.7 | 75.2 | 60.2 | 51.2
1 | 2.75 | 15 | 86.7 | 74.5 | 64.7 | 91.4 | 85.8 | 72.2 | 95.3 | 88.4 | 80.7 | 98.9 | 96 | 92.3 | 99.7 | 98.8 | 96.7 | 100 | 98.2 | 96.5 | 100 | 99.1 | 96.7 | 100 | 98 | 94.4 | 97.2 | 94.9 | 89.1 | 91.8 | 85.1 | 80.6 | 90.1 | 82.9 | 69.5 | 86.5 | 74.1 | 66.3
1 | 2.75 | 20 | 89.1 | 76.7 | 65.9 | 92.9 | 86.5 | 73.6 | 96.1 | 89.4 | 81.3 | 99.2 | 96.3 | 92.8 | 100 | 99.1 | 97.1 | 100 | 98.5 | 96.6 | 100 | 99.2 | 96.7 | 100 | 98 | 95.8 | 97.6 | 96.1 | 89.9 | 92.6 | 87.2 | 81.9 | 90.9 | 83.6 | 72.8 | 87.1 | 76.5 | 69.1
1 | 2.75 | 25 | 89.1 | 76.7 | 65.9 | 92.9 | 86.5 | 73.6 | 96.1 | 89.4 | 81.3 | 99.2 | 96.3 | 92.8 | 100 | 99.1 | 97.1 | 100 | 98.5 | 96.6 | 100 | 99.2 | 96.7 | 100 | 98 | 95.8 | 97.6 | 96.1 | 89.9 | 92.6 | 87.2 | 81.9 | 90.9 | 83.6 | 72.8 | 87.1 | 76.5 | 69.1
1 | 3 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 3 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 3 | 6 | 26 | 14 | 8.9 | 29.3 | 21.4 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.4 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 3 | 8 | 44.4 | 29.6 | 17.9 | 50.2 | 40 | 24 | 53.6 | 42.7 | 36 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.6 | 44.7 | 28.4 | 20.6
1 | 3 | 9 | 53.9 | 37.8 | 24.4 | 58 | 49.9 | 30.3 | 67.7 | 55.5 | 45.6 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.8 | 45 | 38.1 | 53.7 | 44.7 | 32.4 | 54.9 | 37.9 | 26.8
1 | 3 | 10 | 60.8 | 44.2 | 33.4 | 67.3 | 58.8 | 38.5 | 76.3 | 65.2 | 54 | 85.1 | 75.7 | 71.2 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 65.1 | 66.5 | 55.2 | 47.3 | 61.7 | 55.7 | 39.3 | 61.3 | 46.1 | 35.3
1 | 3 | 11 | 68.8 | 53.9 | 43.5 | 75.5 | 66.7 | 45.6 | 82.2 | 74.5 | 62.5 | 91.7 | 83.5 | 78.2 | 91.6 | 88 | 83.6 | 96.1 | 91.8 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 74.1 | 73.9 | 66.4 | 55.4 | 72.4 | 62.2 | 49.3 | 69.5 | 54.3 | 44.1
1 | 3 | 12 | 74.2 | 61.8 | 52.6 | 81.5 | 76.3 | 56.1 | 89.3 | 81.6 | 68.7 | 94.9 | 89.3 | 83.8 | 95.8 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.2 | 91.8 | 97.8 | 93.5 | 87.3 | 92 | 86.4 | 80.1 | 80.9 | 72.2 | 63.1 | 80.4 | 71.1 | 55.1 | 76.4 | 60.9 | 51.8
1 | 3 | 15 | 88.3 | 79.3 | 68.6 | 92.9 | 88.2 | 76.7 | 96.6 | 91 | 85.3 | 99.3 | 97.2 | 93.8 | 99.9 | 99.1 | 98.3 | 100 | 98.9 | 97 | 100 | 99.6 | 97.4 | 100 | 98.8 | 95.6 | 98.1 | 95.4 | 90.6 | 93.6 | 87.6 | 82.7 | 91.3 | 85.3 | 73.7 | 88.2 | 78.4 | 69.5
1 | 3 | 20 | 92.4 | 82.1 | 70.2 | 95.5 | 90.7 | 79.9 | 97.9 | 92.9 | 86.7 | 100 | 97.9 | 94.6 | 100 | 100 | 98.6 | 100 | 99.3 | 97.2 | 100 | 100 | 98.4 | 100 | 99.2 | 97.2 | 98.9 | 96.9 | 92.2 | 95.2 | 90.1 | 85.9 | 93.2 | 87.8 | 78.8 | 90.6 | 82.4 | 75.4
1 | 3 | 25 | 92.4 | 82.1 | 70.2 | 95.5 | 90.7 | 79.9 | 97.9 | 92.9 | 86.7 | 100 | 97.9 | 94.6 | 100 | 100 | 98.6 | 100 | 99.3 | 97.2 | 100 | 100 | 98.4 | 100 | 99.2 | 97.2 | 98.9 | 96.9 | 92.2 | 95.2 | 90.1 | 85.9 | 93.2 | 87.8 | 78.8 | 90.6 | 82.4 | 75.4
1 | 3.5 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 3.5 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 3.5 | 6 | 26 | 14 | 8.9 | 29.3 | 21.4 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.4 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 3.5 | 8 | 44.4 | 29.6 | 17.9 | 50.2 | 40 | 24 | 53.6 | 42.7 | 36.1 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.6 | 44.7 | 28.4 | 20.6
1 | 3.5 | 9 | 53.9 | 37.8 | 24.4 | 58 | 49.9 | 30.3 | 67.7 | 55.5 | 45.7 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.8 | 45 | 38.1 | 53.7 | 44.7 | 32.4 | 54.9 | 37.9 | 26.9
1 | 3.5 | 10 | 61.2 | 44.2 | 33.7 | 67.3 | 58.8 | 38.7 | 76.3 | 65.3 | 54 | 85.1 | 75.7 | 71.2 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 65.1 | 66.5 | 55.6 | 47.3 | 61.7 | 55.7 | 39.5 | 61.3 | 46.2 | 35.6
1 | 3.5 | 11 | 68.8 | 54 | 43.5 | 75.5 | 66.7 | 46 | 82.2 | 74.5 | 62.8 | 91.8 | 83.5 | 78.3 | 91.6 | 88 | 83.6 | 96.3 | 91.8 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 74.3 | 74.1 | 66.5 | 55.7 | 72.4 | 62.8 | 49.4 | 69.8 | 54.6 | 44.2
1 | 3.5 | 12 | 74.2 | 61.8 | 53 | 81.9 | 76.6 | 56.5 | 89.3 | 82 | 70.1 | 95 | 89.6 | 84.2 | 95.8 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.2 | 91.9 | 97.8 | 93.5 | 87.3 | 92.1 | 86.5 | 81 | 81 | 72.2 | 63.3 | 80.6 | 72.2 | 57.3 | 76.5 | 61.4 | 52.2
1 | 3.5 | 15 | 89.6 | 81.9 | 75 | 94.2 | 90.2 | 80.7 | 97.1 | 92.1 | 87.8 | 99.4 | 97.9 | 94.5 | 100 | 99.5 | 98.6 | 100 | 99.2 | 97.4 | 100 | 100 | 98.3 | 100 | 99.1 | 96.6 | 99 | 95.8 | 92.3 | 94.1 | 89.2 | 84.6 | 93.8 | 86.8 | 78.2 | 90.1 | 81.9 | 71.7
1 | 3.5 | 20 | 96.1 | 91.3 | 84.8 | 98.8 | 94.3 | 88.6 | 99.9 | 97.6 | 93.5 | 100 | 100 | 97.1 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.6 | 96 | 98.9 | 95.6 | 92.5 | 97.4 | 93.9 | 88.6 | 96.6 | 91.4 | 84.5
1 | 3.5 | 25 | 96.1 | 91.4 | 84.8 | 99 | 94.3 | 88.6 | 99.9 | 97.6 | 93.5 | 100 | 100 | 97.1 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.6 | 96 | 98.9 | 95.6 | 92.6 | 97.4 | 93.9 | 88.6 | 96.6 | 91.4 | 84.7
1 | 4 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 4 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 4 | 6 | 26 | 14 | 8.9 | 29.3 | 21.4 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.4 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 4 | 8 | 44.4 | 29.6 | 17.9 | 50.2 | 40 | 24 | 53.6 | 42.7 | 36.1 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.6 | 44.7 | 28.4 | 20.6
1 | 4 | 9 | 53.9 | 37.8 | 24.4 | 58 | 49.9 | 30.3 | 67.7 | 55.5 | 45.7 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.8 | 45 | 38.1 | 53.7 | 44.7 | 32.4 | 54.9 | 37.9 | 26.9
1 | 4 | 10 | 61.3 | 44.2 | 33.7 | 67.3 | 58.8 | 38.7 | 76.3 | 65.3 | 54 | 85.1 | 75.7 | 71.2 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 65.1 | 66.5 | 55.6 | 47.3 | 61.7 | 55.7 | 39.5 | 61.3 | 46.2 | 35.7
1 | 4 | 11 | 68.8 | 54.2 | 43.5 | 75.5 | 66.7 | 46 | 82.2 | 74.5 | 62.8 | 91.8 | 83.5 | 78.3 | 91.6 | 88 | 83.6 | 96.3 | 91.8 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 74.3 | 74.1 | 66.5 | 55.8 | 72.4 | 62.8 | 49.4 | 69.8 | 54.6 | 44.2
1 | 4 | 12 | 74.2 | 61.8 | 53 | 82.2 | 76.6 | 56.7 | 89.3 | 82 | 70.3 | 95 | 89.6 | 84.2 | 95.8 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.2 | 91.9 | 97.8 | 93.5 | 87.3 | 92.1 | 86.5 | 81 | 81 | 72.2 | 63.5 | 80.8 | 72.4 | 57.8 | 76.5 | 61.4 | 52.2
1 | 4 | 15 | 91 | 82.4 | 76.2 | 95.2 | 91.1 | 83 | 97.1 | 93.1 | 87.8 | 99.4 | 98.6 | 95.1 | 100 | 99.5 | 98.6 | 100 | 99.3 | 98.1 | 100 | 100 | 98.5 | 100 | 99.1 | 97 | 99 | 96.4 | 93 | 94.6 | 89.7 | 85.1 | 94.8 | 87.5 | 80.9 | 91.5 | 83.6 | 72.6
1 | 4 | 20 | 99 | 96 | 91.2 | 99.7 | 97.8 | 92.8 | 100 | 99.2 | 97 | 100 | 100 | 98.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.7 | 97.6 | 100 | 98 | 95.6 | 99.6 | 97.2 | 94.5 | 99.4 | 96 | 91.9
1 | 4 | 25 | 99 | 96.2 | 91.6 | 99.9 | 97.9 | 93.3 | 100 | 99.6 | 97.2 | 100 | 100 | 98.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.8 | 100 | 98.1 | 95.7 | 99.7 | 97.4 | 95.2 | 99.7 | 96.1 | 92.4
1 | 4.5 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 4.5 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 4.5 | 6 | 26 | 14 | 8.9 | 29.3 | 21.4 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.4 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 4.5 | 8 | 44.4 | 29.6 | 17.9 | 50.2 | 40 | 24 | 53.6 | 42.7 | 36.1 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.6 | 44.7 | 28.4 | 20.6
1 | 4.5 | 9 | 53.9 | 37.8 | 24.4 | 58 | 49.9 | 30.3 | 67.7 | 55.5 | 45.7 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.8 | 45 | 38.1 | 53.7 | 44.7 | 32.4 | 54.9 | 37.9 | 26.9
1 | 4.5 | 10 | 61.3 | 44.2 | 33.7 | 67.3 | 58.8 | 38.7 | 76.3 | 65.3 | 54 | 85.1 | 75.7 | 71.2 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 65.1 | 66.5 | 55.6 | 47.3 | 61.7 | 55.7 | 39.5 | 61.3 | 46.2 | 35.7
1 | 4.5 | 11 | 68.8 | 54.2 | 43.5 | 75.5 | 66.7 | 46 | 82.2 | 74.5 | 62.8 | 91.8 | 83.5 | 78.3 | 91.6 | 88 | 83.6 | 96.3 | 91.8 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 74.3 | 74.1 | 66.5 | 55.8 | 72.4 | 62.8 | 49.4 | 69.8 | 54.6 | 44.2
1 | 4.5 | 12 | 74.2 | 61.8 | 53 | 82.2 | 76.6 | 56.7 | 89.3 | 82 | 70.3 | 95 | 89.6 | 84.2 | 95.8 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.2 | 91.9 | 97.8 | 93.5 | 87.3 | 92.1 | 86.5 | 81 | 81 | 72.2 | 63.5 | 80.8 | 72.4 | 57.8 | 76.5 | 61.4 | 52.2
1 | 4.5 | 15 | 91.5 | 82.4 | 76.2 | 95.3 | 91.1 | 83 | 97.1 | 93.5 | 88.3 | 99.4 | 98.6 | 95.4 | 100 | 99.5 | 98.6 | 100 | 99.3 | 98.1 | 100 | 100 | 98.5 | 100 | 99.1 | 97 | 99 | 96.4 | 93.1 | 94.7 | 89.7 | 85.4 | 94.9 | 88.3 | 81.4 | 91.7 | 83.9 | 73
1 | 4.5 | 20 | 99.8 | 97.7 | 94 | 100 | 98.8 | 94.8 | 100 | 100 | 98.7 | 100 | 100 | 99.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 99.3 | 97.4 | 100 | 98.6 | 96.5 | 100 | 98.4 | 94.7
1 | 4.5 | 25 | 100 | 98.3 | 95.5 | 100 | 99.3 | 95.7 | 100 | 100 | 99 | 100 | 100 | 99.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.3 | 100 | 99.6 | 98.1 | 100 | 99.2 | 97.7 | 100 | 99.1 | 96.3
1 | 5 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 5 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 5 | 6 | 26 | 14 | 8.9 | 29.3 | 21.4 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.4 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 5 | 8 | 44.4 | 29.6 | 17.9 | 50.2 | 40 | 24 | 53.6 | 42.7 | 36.1 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.6 | 44.7 | 28.4 | 20.6
1 | 5 | 9 | 53.9 | 37.8 | 24.4 | 58 | 49.9 | 30.3 | 67.7 | 55.5 | 45.7 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.8 | 45 | 38.1 | 53.7 | 44.7 | 32.4 | 54.9 | 37.9 | 26.9
1 | 5 | 10 | 61.3 | 44.2 | 33.7 | 67.3 | 58.8 | 38.7 | 76.3 | 65.3 | 54 | 85.1 | 75.7 | 71.2 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 65.1 | 66.5 | 55.6 | 47.3 | 61.7 | 55.7 | 39.5 | 61.3 | 46.2 | 35.7
1 | 5 | 11 | 68.8 | 54.2 | 43.5 | 75.5 | 66.7 | 46 | 82.2 | 74.5 | 62.8 | 91.8 | 83.5 | 78.3 | 91.6 | 88 | 83.6 | 96.3 | 91.8 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 74.3 | 74.1 | 66.5 | 55.8 | 72.4 | 62.8 | 49.4 | 69.8 | 54.6 | 44.2
1 | 5 | 12 | 74.2 | 61.8 | 53 | 82.2 | 76.6 | 56.7 | 89.3 | 82 | 70.3 | 95 | 89.6 | 84.2 | 95.8 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.2 | 91.9 | 97.8 | 93.5 | 87.3 | 92.1 | 86.5 | 81 | 81 | 72.2 | 63.5 | 80.8 | 72.4 | 57.8 | 76.5 | 61.4 | 52.2
1 | 5 | 15 | 91.5 | 82.4 | 76.2 | 95.3 | 91.2 | 83 | 97.1 | 93.5 | 88.4 | 99.4 | 98.6 | 95.4 | 100 | 99.5 | 98.6 | 100 | 99.3 | 98.1 | 100 | 100 | 98.5 | 100 | 99.1 | 97 | 99 | 96.4 | 93.1 | 94.7 | 89.7 | 85.5 | 94.9 | 88.3 | 81.4 | 91.7 | 84.5 | 73
1 | 5 | 20 | 100 | 98 | 95.1 | 100 | 99.3 | 96.1 | 100 | 100 | 98.7 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.3 | 100 | 99.7 | 98.3 | 100 | 98.9 | 97.4 | 100 | 99.1 | 95.6
1 | 5 | 25 | 100 | 99.7 | 98.2 | 100 | 100 | 98 | 100 | 100 | 99.7 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.4 | 100 | 100 | 98.8 | 100 | 100 | 98.2
2 | 0.25 | 2 | [9 empty] | 0.3 |  |  | 0.7 |  |  | 1.2 | 0.1 |  | 0.7 | 0.4 |  | 1.1
2 | 0.25 | 4 | [9 empty] | 1.5 |  |  | 3 | 0.4 |  | 4.7 | 1 |  | 2.8 | 1.2 |  | 4.7 | 1.5 |  | 0.9
2 | 0.25 | 6 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.6 | 1.3 |  | 3.4 | 1.9 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 8 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 9 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 10 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 11 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 12 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 15 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 20 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 25 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.5 | 2 | 0.2 |  |  | 0.4 |  |  | 0.9 | 0.3 |  | 2.2 | 1 | 0.2 | 2.5 | 0.8 |  | 4 | 1.8 | 0.3 | 4.3 | 1.6 | 0.8 | 3.1 | 1.3 | 0.7 | 2.1 | 0.8 |  | 0.6 |  |  | 0.3 |  |  | 0.6 | 0.1
2 | 0.5 | 4 | 1.9 | 0.1 |  | 2.9 | 2.2 |  | 5.7 | 1.5 |  | 8.9 | 4.3 | 1.5 | 10.4 | 4.2 | 1.7 | 13.5 | 9 | 3.3 | 13.7 | 8.2 | 4.6 | 14.3 | 8.3 | 5.3 | 9 | 4.9 | 1.8 | 3.3 | 1.5 |  | 2.4 | 0.4 |  | 3 | 0.7
2 | 0.5 | 6 | 4.3 | 0.4 |  | 5.9 | 2.7 |  | 8.7 | 2.8 | 0.4 | 16.3 | 8.2 | 4.7 | 17.6 | 10.1 | 5.7 | 22.1 | 15 | 6.5 | 26.9 | 17.6 | 8.5 | 23.8 | 15.3 | 8.2 | 16.3 | 8.9 | 2.7 | 5.2 | 2.2 | 0.1 | 2.9 | 0.7 |  | 4 | 1.6
2 | 0.5 | 8 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.2 | 8.5 | 5.2 | 20.7 | 12.6 | 6.6 | 25.4 | 17.6 | 7.4 | 30.4 | 20.2 | 10.2 | 26 | 16.7 | 9 | 17.7 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 9 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.2 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 10 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 11 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 12 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 15 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 20 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 25 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.75 | 2 | 0.4 |  |  | 1.7 | 0.3 |  | 1.8 | 0.5 |  | 3.4 | 1.7 | 0.9 | 3.5 | 1.6 | 0.7 | 5 | 2.8 | 1.5 | 4.8 | 2.7 | 1.3 | 4.1 | 2.4 | 1.1 | 2.8 | 1.9 | 0.6 | 1.2 | 0.5 |  | 0.8 | 0.1 |  | 1.1 | 0.3
2 | 0.75 | 4 | 4.4 | 1.1 | 0.1 | 8 | 4.2 | 0.4 | 9.2 | 4.3 | 1.9 | 15.1 | 7.8 | 5.3 | 14.5 | 8.6 | 5.2 | 19.5 | 14.4 | 8.2 | 18.7 | 13.2 | 9.3 | 19.4 | 13.8 | 7.7 | 14.4 | 9.3 | 5.2 | 6.7 | 3.1 | 0.9 | 4.7 | 2.5 | 0.5 | 5.3 | 2.3 | 0.7
2 | 0.75 | 6 | 11.1 | 4.3 | 0.6 | 14.5 | 8.5 | 1.8 | 20.2 | 10.1 | 5.9 | 28.3 | 16.8 | 13 | 29.7 | 21.2 | 15.2 | 37.6 | 26.8 | 16.2 | 37.2 | 29.3 | 22.3 | 38.2 | 26.9 | 18.5 | 27.5 | 19.9 | 11 | 14.2 | 7.3 | 3.6 | 10.9 | 5 | 1.8 | 11.9 | 5.9 | 1.4
2 | 0.75 | 8 | 16.8 | 6 | 0.6 | 17.6 | 11.4 | 2.8 | 26.4 | 12.8 | 8.1 | 35.5 | 22.8 | 15.8 | 37 | 29.3 | 20.6 | 45.5 | 36.9 | 23.7 | 50.7 | 38.2 | 29.5 | 46.3 | 37.6 | 26.9 | 35.2 | 27.1 | 13.9 | 18.4 | 10.3 | 5.6 | 12.7 | 7.2 | 2 | 13.5 | 7.7 | 1.7
2 | 0.75 | 9 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 23.5 | 16.2 | 39.2 | 30.1 | 23.3 | 46.9 | 37.5 | 24.5 | 52.2 | 40.5 | 30.3 | 48.1 | 39.2 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.3 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 10 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.5 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.3 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 11 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.9 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.6 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 12 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.9 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.6 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 15 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.9 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.6 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 20 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.9 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.6 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 25 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.9 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.6 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 1 | 2 | 1.1 | 0.3 |  | 2.1 | 0.6 |  | 2.5 | 1.1 |  | 3.7 | 2.2 | 1.3 | 4 | 2 | 0.9 | 5.5 | 3.2 | 1.9 | 5.9 | 3.1 | 1.6 | 4.7 | 2.7 | 1.3 | 3.2 | 2.2 | 0.9 | 1.7 | 0.7 | 0.4 | 1.5 | 0.4 |  | 1.3 | 0.5
2 | 1 | 4 | 5.9 | 2.4 | 0.7 | 10.4 | 5.6 | 2 | 12.2 | 6.7 | 2.5 | 17.5 | 11.3 | 7.3 | 16.9 | 12.1 | 7.1 | 23 | 17.1 | 10.9 | 21.8 | 15.6 | 10.5 | 22 | 15.3 | 10.8 | 15.4 | 10.6 | 7.1 | 9.8 | 4.7 | 2.7 | 6.7 | 3.3 | 1.5 | 6.4 | 3.4 | 0.9
2 | 1 | 6 | 16.9 | 8.6 | 2.3 | 20.1 | 14.3 | 5.5 | 26.9 | 15.9 | 8.6 | 35.6 | 24.6 | 19.3 | 36.2 | 28.2 | 20.8 | 45.7 | 35 | 26.6 | 45.1 | 35.5 | 27.4 | 44 | 32.3 | 25.8 | 33.8 | 27.5 | 18.2 | 21.7 | 11.8 | 6.9 | 15.8 | 8.9 | 5 | 18.2 | 8.3 | 3.7
2 | 1 | 8 | 26.2 | 13.6 | 3.5 | 30 | 19.8 | 10.3 | 36.9 | 24.7 | 15.9 | 52.5 | 37.4 | 29.5 | 52.3 | 45 | 35.4 | 62.3 | 52.2 | 42.1 | 65.9 | 55.5 | 40.8 | 61.5 | 50.8 | 41.8 | 47.5 | 40.4 | 29.5 | 29.8 | 19.5 | 10.6 | 24.3 | 14.9 | 7.5 | 25.9 | 12.4 | 6
2 | 1 | 9 | 26.6 | 15.1 | 3.7 | 31.1 | 21 | 10.8 | 39.9 | 28.4 | 18.1 | 55.1 | 40 | 31.5 | 57.8 | 48.3 | 38.2 | 65.9 | 55.3 | 45.9 | 71 | 60.1 | 45.4 | 66.8 | 53.9 | 44.9 | 51.7 | 43.1 | 31.2 | 32.2 | 22.2 | 11.8 | 26 | 16 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 10 | 26.8 | 14.7 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.4 | 18.7 | 55.8 | 41.3 | 32.1 | 60.1 | 50.4 | 39.6 | 66.6 | 56.7 | 47.7 | 71.8 | 61.7 | 47.6 | 68.3 | 55 | 45.9 | 52.8 | 44.4 | 31.9 | 32.4 | 23.5 | 12.3 | 26.2 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 11 | 26.8 | 14.7 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.9 | 18.7 | 56.1 | 41.3 | 32.4 | 60.2 | 50.7 | 40 | 66.7 | 56.7 | 47.8 | 72.1 | 62.1 | 47.9 | 68.7 | 55.5 | 46.3 | 53 | 44.7 | 31.9 | 32.4 | 23.8 | 12.3 | 26.3 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 12 | 26.8 | 14.7 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.9 | 18.7 | 56.1 | 41.3 | 32.6 | 60.2 | 50.5 | 40 | 66.7 | 56.7 | 48 | 72.1 | 62.1 | 47.9 | 68.7 | 55.5 | 46.5 | 53 | 44.7 | 31.9 | 32.4 | 23.8 | 12.3 | 26.3 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 15 | 26.8 | 14.9 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.9 | 18.7 | 56.1 | 41.3 | 32.6 | 60.2 | 50.8 | 40 | 66.7 | 56.7 | 48 | 72.1 | 62.1 | 47.9 | 68.7 | 55.5 | 46.5 | 53 | 44.7 | 31.9 | 32.4 | 23.8 | 12.3 | 26.3 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 20 | 26.8 | 14.9 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.9 | 18.7 | 56.1 | 41.3 | 32.6 | 60.2 | 50.8 | 40 | 66.7 | 56.7 | 48 | 72.1 | 62.1 | 47.9 | 68.7 | 55.5 | 46.5 | 53 | 44.7 | 31.9 | 32.4 | 23.8 | 12.3 | 26.3 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 25 | 26.8 | 14.9 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.9 | 18.7 | 56.1 | 41.3 | 32.6 | 60.2 | 50.8 | 40 | 66.7 | 56.7 | 48 | 72.1 | 62.1 | 47.9 | 68.7 | 55.5 | 46.5 | 53 | 44.7 | 31.9 | 32.4 | 23.8 | 12.3 | 26.3 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1.25 | 2 | 1.2 | 0.5 |  | 2.3 | 0.9 | 0.1 | 2.6 | 1.2 | 0.3 | 3.8 | 2.5 | 1.5 | 4 | 2.8 | 1.1 | 5.9 | 3.3 | 1.9 | 5.9 | 3.5 | 1.6 | 5.2 | 2.7 | 1.5 | 3.5 | 2.2 | 1.2 | 1.9 | 0.8 | 0.4 | 1.5 | 0.7 | 0.1 | 1.7 | 0.7 | 0.2
2 | 1.25 | 4 | 6.4 | 3.1 | 1.6 | 11.6 | 7.6 | 2.9 | 13.8 | 7.9 | 3.5 | 18.7 | 11.9 | 9.2 | 17.7 | 13.7 | 8.8 | 23.7 | 19 | 12.4 | 22.8 | 16.3 | 11.1 | 23.7 | 16 | 11.4 | 16.9 | 11.4 | 7.6 | 10.5 | 5.6 | 3.6 | 8 | 4.6 | 2.5 | 8.5 | 3.9 | 1.7
2 | 1.25 | 6 | 22.1 | 9.7 | 5.7 | 24.6 | 16.8 | 7 | 28.2 | 19.8 | 12.1 | 38 | 27.9 | 22.4 | 38.9 | 30.9 | 25 | 49.7 | 40.6 | 30.7 | 47 | 38.6 | 29.3 | 45.3 | 34.9 | 29.6 | 37 | 29.7 | 19.2 | 24.9 | 15.1 | 10.5 | 20.4 | 12.6 | 7.7 | 21.8 | 11.8 | 5.4
2 | 1.25 | 8 | 34.8 | 21 | 9.7 | 36.8 | 28.1 | 12.7 | 47.5 | 34.8 | 22.8 | 58.9 | 46.1 | 39.4 | 58.4 | 53.2 | 45.3 | 71.3 | 60.8 | 49.2 | 72 | 63.6 | 50.3 | 69.2 | 58.2 | 49.3 | 56.3 | 47.2 | 36.3 | 36.5 | 26.7 | 19.1 | 32.9 | 23.1 | 13 | 35.2 | 18.8 | 11.9
2 | 1.25 | 9 | 37.1 | 23.8 | 10.7 | 42.2 | 30.8 | 15.7 | 51.3 | 41.9 | 27.5 | 65.3 | 52.8 | 44.8 | 68.8 | 60.1 | 52.8 | 77.7 | 67.5 | 57.6 | 78.9 | 72.4 | 56.8 | 75 | 66.8 | 55.9 | 63.9 | 52.1 | 40.3 | 42.8 | 32.8 | 21.8 | 37.5 | 27.4 | 15.2 | 36.9 | 22.6 | 14.5
2 | 1.25 | 10 | 38.9 | 24.1 | 11.6 | 45.4 | 33.2 | 16.8 | 54.7 | 43.1 | 28.8 | 70.1 | 56.1 | 46.4 | 74 | 64 | 57.3 | 80.8 | 72.4 | 60.6 | 83.2 | 76.6 | 60.3 | 78.3 | 69.4 | 59 | 65.9 | 56.3 | 42.8 | 45.4 | 34.9 | 23.1 | 39.1 | 28.6 | 16 | 37.8 | 23.4 | 15.6
2 | 1.25 | 11 | 39.2 | 24.6 | 11.8 | 45.8 | 33.5 | 17.2 | 55.2 | 44.1 | 28.8 | 72.1 | 57.4 | 47 | 75.1 | 66.1 | 59.5 | 81.2 | 74 | 61.6 | 84.8 | 77.8 | 61.8 | 79.2 | 71.2 | 60.9 | 66.4 | 58.3 | 43.5 | 45.5 | 36.3 | 23.5 | 39.4 | 29.3 | 16 | 38 | 23.4 | 15.7
2 | 1.25 | 12 | 39.2 | 24.6 | 11.8 | 45.9 | 33.5 | 17.2 | 55.6 | 44.4 | 28.9 | 72.1 | 57.9 | 47.3 | 75.1 | 66.1 | 59.8 | 81.2 | 74 | 62.4 | 84.8 | 78.1 | 62.6 | 79.3 | 71.5 | 61.1 | 66.8 | 58.3 | 43.6 | 45.5 | 36.6 | 23.5 | 39.4 | 29.3 | 16 | 38 | 23.4 | 15.7
2 | 1.25 | 15 | 39.4 | 24.6 | 11.8 | 45.9 | 33.5 | 17.4 | 55.6 | 44.4 | 28.9 | 72.1 | 57.9 | 47.3 | 75.2 | 66.1 | 59.9 | 81.2 | 74 | 62.4 | 84.8 | 78.1 | 62.9 | 79.3 | 71.5 | 61.1 | 66.8 | 58.3 | 43.6 | 45.5 | 36.6 | 23.5 | 39.4 | 29.3 | 16 | 38 | 23.4 | 15.7
2 | 1.25 | 20 | 39.4 | 24.6 | 11.8 | 45.9 | 33.5 | 17.4 | 55.6 | 44.4 | 28.9 | 72.1 | 57.9 | 47.3 | 75.2 | 66.1 | 59.9 | 81.2 | 74 | 62.4 | 84.8 | 78.1 | 62.9 | 79.3 | 71.5 | 61.1 | 66.8 | 58.6 | 43.6 | 45.5 | 36.6 | 23.5 | 39.4 | 29.3 | 16 | 38 | 23.4 | 15.7
2 | 1.25 | 25 | 39.4 | 24.6 | 11.8 | 45.9 | 33.5 | 17.4 | 55.6 | 44.4 | 28.9 | 72.1 | 57.9 | 47.3 | 75.2 | 66.1 | 59.9 | 81.2 | 74 | 62.4 | 84.8 | 78.1 | 62.9 | 79.3 | 71.5 | 61.1 | 66.8 | 58.6 | 43.6 | 45.5 | 36.6 | 23.5 | 39.4 | 29.3 | 16 | 38 | 23.4 | 15.7
2 | 1.5 | 2 | 1.3 | 0.5 |  | 2.7 | 0.7 | 0.3 | 2.7 | 1.3 | 0.3 | 3.9 | 2.5 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.6 | 2.2 | 1.3 | 2 | 0.8 | 0.4 | 1.5 | 0.7 | 0.1 | 1.9 | 0.9 | 0.3
2 | 1.5 | 4 | 7.9 | 3.6 | 1.9 | 12.5 | 7.7 | 3.3 | 13.8 | 8.3 | 4.1 | 18.7 | 12.9 | 9.9 | 17.9 | 14.1 | 9.2 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.3 | 23.9 | 16.1 | 11.6 | 17.5 | 11.9 | 8.2 | 10.8 | 6.3 | 3.9 | 8.9 | 5 | 3.1 | 10.5 | 4.4 | 2.5
2 | 1.5 | 6 | 24 | 12.1 | 6.4 | 26.7 | 17.7 | 8.7 | 29.8 | 21.8 | 14.4 | 38.5 | 29.4 | 25.6 | 39.4 | 32.3 | 25.6 | 50.4 | 41.1 | 31.4 | 49.1 | 39.4 | 30 | 47.7 | 37.9 | 30.8 | 38.2 | 30.7 | 21.2 | 26.4 | 18 | 11.8 | 20.8 | 15.1 | 8.9 | 23.9 | 14.2 | 6.8
2 | 1.5 | 8 | 39 | 24.9 | 13.6 | 42.1 | 32.7 | 17.2 | 49.1 | 38 | 27.7 | 62.2 | 50 | 44 | 62.4 | 56.7 | 47.8 | 74.1 | 64.7 | 53.9 | 74.6 | 66.3 | 55.5 | 70.8 | 61.8 | 50.9 | 60 | 50.4 | 41.6 | 42.6 | 31.2 | 23 | 38.4 | 27.9 | 18.7 | 38 | 23.4 | 15.1
2 | 1.5 | 9 | 43.1 | 31.6 | 16.9 | 51.1 | 40.4 | 21.3 | 60.9 | 47.2 | 35.9 | 70.3 | 58.8 | 52.2 | 73.7 | 65.3 | 57.3 | 82.5 | 74 | 64.7 | 81.6 | 76.2 | 65.2 | 79.2 | 70.6 | 60.4 | 67.3 | 59.6 | 49.2 | 48.1 | 39.1 | 29 | 44.9 | 34.7 | 22.6 | 43 | 28.4 | 18.5
2 | 1.5 | 10 | 46.7 | 33.9 | 19.8 | 58.4 | 44.9 | 26.4 | 66.6 | 52.3 | 41.5 | 76.8 | 65.1 | 56.2 | 80.9 | 72.4 | 66.7 | 87.2 | 81.7 | 70.9 | 88.7 | 82.9 | 72 | 85.2 | 76.6 | 66.7 | 74.6 | 63.6 | 54.3 | 56.9 | 44.4 | 34 | 52.4 | 37.8 | 25.3 | 47.2 | 31.6 | 22.5
2 | 1.5 | 11 | 48.5 | 34.9 | 21 | 59.8 | 47.3 | 26.7 | 70.9 | 53.9 | 43.3 | 80.9 | 69.2 | 59.9 | 83.5 | 77.6 | 69.2 | 89.2 | 83.6 | 74.2 | 92.1 | 86.2 | 75.3 | 87.1 | 79.4 | 69.9 | 77.2 | 67.1 | 56.9 | 60.1 | 48.5 | 36.2 | 54.7 | 39 | 26.7 | 50.2 | 33.9 | 23.1
2 | 1.5 | 12 | 48.8 | 35.2 | 21.8 | 60.3 | 48.5 | 27.4 | 71.4 | 54.7 | 43.5 | 82 | 70.8 | 60.7 | 83.9 | 78.8 | 70.8 | 89.7 | 84 | 75.3 | 93.1 | 86.4 | 75.5 | 87.6 | 79.6 | 70.7 | 77.6 | 68.5 | 57.2 | 61.3 | 49.5 | 36.9 | 55.2 | 39.3 | 27.5 | 50.4 | 34 | 23.4
2 | 1.5 | 15 | 48.9 | 35.8 | 21.8 | 60.3 | 48.5 | 27.2 | 71.5 | 54.7 | 43.9 | 82.3 | 70.8 | 60.8 | 84.5 | 78.8 | 71 | 89.7 | 84.2 | 75.2 | 93.2 | 86.8 | 75.5 | 87.6 | 79.6 | 71.2 | 77.8 | 68.5 | 57.2 | 61.5 | 49.6 | 36.9 | 55.5 | 39.3 | 27.6 | 50.5 | 34 | 23.4
2 | 1.5 | 20 | 49 | 35.8 | 21.8 | 60.3 | 48.5 | 27.2 | 71.5 | 54.7 | 43.9 | 82.3 | 70.8 | 60.8 | 84.5 | 78.8 | 71 | 89.7 | 84.2 | 75.2 | 93.3 | 86.8 | 75.5 | 87.6 | 79.6 | 71.2 | 77.8 | 68.5 | 57.2 | 61.5 | 49.6 | 36.9 | 55.5 | 39.3 | 27.6 | 50.5 | 34 | 23.4
2 | 1.5 | 25 | 49 | 35.8 | 21.8 | 60.3 | 48.5 | 27.2 | 71.5 | 54.7 | 43.9 | 82.3 | 70.8 | 60.8 | 84.5 | 78.8 | 71 | 89.7 | 84.2 | 75.2 | 93.3 | 86.8 | 75.5 | 87.6 | 79.6 | 71.2 | 77.8 | 68.5 | 57.2 | 61.5 | 49.6 | 36.9 | 55.5 | 39.3 | 27.6 | 50.5 | 34 | 23.4
2 | 1.75 | 2 | 1.3 | 0.7 | 0.1 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.5 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.4 | 1.8 | 0.8 | 0.1 | 2.2 | 1.1 | 0.3
2 | 1.75 | 4 | 8.4 | 3.8 | 2 | 13.1 | 8.2 | 3.5 | 14.1 | 8.5 | 5.6 | 18.7 | 13.2 | 10.1 | 18 | 14.5 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.2 | 16.1 | 11.6 | 17.5 | 12.5 | 8.6 | 10.8 | 6.5 | 4.1 | 9.3 | 5.4 | 3.2 | 11 | 5.4 | 2.6
2 | 1.75 | 6 | 24.6 | 13.3 | 7.7 | 27.9 | 19.8 | 10.8 | 30 | 22.7 | 16.6 | 41.5 | 31.1 | 26.2 | 39.6 | 33.3 | 26.5 | 50.6 | 41.7 | 31.7 | 49.1 | 39.4 | 30.4 | 47.8 | 38.2 | 31 | 38.7 | 31.5 | 21.8 | 26.7 | 18.8 | 12 | 22.3 | 16.4 | 9.9 | 24.5 | 14.9 | 7
2 | 1.75 | 8 | 41.5 | 27.4 | 15.5 | 45.2 | 35.6 | 20.8 | 50.6 | 40.3 | 33.4 | 63.9 | 52.9 | 46.7 | 63.5 | 58.5 | 48.6 | 75.4 | 65.1 | 56.1 | 75.2 | 66.8 | 56.7 | 70.8 | 62.8 | 51.4 | 62.7 | 52.4 | 44.1 | 44.7 | 32.8 | 25.1 | 41.1 | 31 | 19.2 | 39.5 | 26.3 | 17.3
2 | 1.75 | 9 | 48.9 | 34.5 | 20.4 | 55.6 | 45.4 | 26.3 | 64.9 | 49.6 | 40.5 | 71.8 | 62.4 | 57 | 75 | 66.8 | 59.9 | 85.1 | 76.4 | 67.5 | 82.7 | 77.6 | 67.8 | 81.1 | 71.8 | 62.1 | 71.3 | 62.4 | 53.6 | 51.9 | 41.1 | 33.7 | 48.4 | 38.2 | 27.1 | 46.9 | 32 | 21.9
2 | 1.75 | 10 | 53 | 39.4 | 27.2 | 64.7 | 51.3 | 31 | 73.3 | 58.1 | 45.2 | 82 | 72.1 | 63.5 | 83.9 | 75.3 | 70 | 90.3 | 84.7 | 75.8 | 90.1 | 84.7 | 76.4 | 88.5 | 77.7 | 70.3 | 77 | 68.1 | 58.7 | 60.1 | 48.5 | 40.9 | 56.6 | 44.3 | 32 | 55 | 38.3 | 27.4
2 | 1.75 | 11 | 57.3 | 43.3 | 32.8 | 67.9 | 57.3 | 33.3 | 77.1 | 65.5 | 50.6 | 87.3 | 76.9 | 68.5 | 88.1 | 82.5 | 77.2 | 93.4 | 88.5 | 80.9 | 95.4 | 89.1 | 81.1 | 90.8 | 83.6 | 76 | 81.7 | 74 | 64.2 | 68.4 | 56 | 46.1 | 61.8 | 48.5 | 34.9 | 58 | 41.9 | 30
2 | 1.75 | 12 | 59 | 44.5 | 35.8 | 70 | 59.5 | 35.6 | 79.3 | 66.3 | 53.6 | 87.7 | 79.3 | 69.6 | 90.6 | 85.2 | 80.8 | 94.3 | 89.3 | 83.8 | 96.4 | 91 | 82.3 | 93 | 84.8 | 78.5 | 83.6 | 75.6 | 66.1 | 72.8 | 58.6 | 49 | 63.8 | 49.6 | 36.6 | 60.9 | 42.9 | 30.9
2 | 1.75 | 15 | 59.8 | 45.4 | 36.5 | 70.8 | 60.7 | 36.7 | 80.4 | 67.1 | 55.8 | 88.3 | 79.7 | 70 | 91.2 | 86.6 | 82.3 | 94.7 | 89.7 | 84.4 | 96.4 | 91.5 | 82.6 | 93.3 | 85.2 | 79.5 | 84.3 | 76.5 | 66.9 | 74 | 59.9 | 51.1 | 65.1 | 49.7 | 37.8 | 61.5 | 43.1 | 31.2
2 | 1.75 | 20 | 59.8 | 45.4 | 36.5 | 70.8 | 60.7 | 36.7 | 80.4 | 67.1 | 55.8 | 88.3 | 79.7 | 70 | 91.2 | 86.6 | 82.3 | 94.7 | 89.7 | 84.4 | 96.4 | 91.5 | 82.6 | 93.3 | 85.2 | 79.5 | 84.3 | 76.5 | 66.9 | 74 | 59.9 | 51.1 | 65.1 | 49.7 | 37.8 | 61.5 | 43.1 | 31.2
2 | 1.75 | 25 | 59.8 | 45.4 | 36.5 | 70.8 | 60.7 | 36.7 | 80.4 | 67.1 | 55.8 | 88.3 | 79.7 | 70 | 91.2 | 86.6 | 82.3 | 94.7 | 89.7 | 84.4 | 96.4 | 91.5 | 82.6 | 93.3 | 85.2 | 79.5 | 84.3 | 76.5 | 66.9 | 74 | 59.9 | 51.1 | 65.1 | 49.7 | 37.8 | 61.5 | 43.1 | 31.2
2 | 2 | 2 | 1.4 | 0.7 | 0.1 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 2 | 4 | 8.9 | 3.8 | 2.2 | 13.5 | 8.2 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 8.6 | 11 | 6.9 | 4.2 | 9.3 | 5.6 | 3.6 | 11.8 | 5.4 | 2.6
2 | 2 | 6 | 24.9 | 13.6 | 8.3 | 28.1 | 19.8 | 10.8 | 30.1 | 22.8 | 16.9 | 41.6 | 31.7 | 26.7 | 39.7 | 33.3 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31 | 47.8 | 38.2 | 31 | 38.7 | 31.5 | 21.8 | 26.8 | 19.4 | 12 | 22.4 | 17.1 | 10.3 | 25.2 | 15.2 | 7.9
2 | 2 | 8 | 42.5 | 28.2 | 16.8 | 47.7 | 36.4 | 21.4 | 52.2 | 41.4 | 34.6 | 64 | 55 | 47.4 | 63.8 | 58.5 | 49.9 | 75.5 | 65.7 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.1 | 44.4 | 45.1 | 33.1 | 27.2 | 42.3 | 31.5 | 20.8 | 41 | 26.7 | 18.5
2 | 2 | 9 | 52.4 | 36.3 | 21.9 | 56.6 | 47.5 | 27.5 | 65.9 | 52 | 42.9 | 71.9 | 64.6 | 59.1 | 76.2 | 67.6 | 60.9 | 85.7 | 76.9 | 68.5 | 83.1 | 77.8 | 69.5 | 82.3 | 72.4 | 63.1 | 73 | 63.8 | 54.9 | 53.5 | 41.5 | 35.4 | 50.8 | 40 | 29.1 | 49.8 | 35.3 | 23.9
2 | 2 | 10 | 56.7 | 43 | 30.3 | 65.5 | 54.9 | 32.9 | 75.3 | 62 | 49.1 | 82.9 | 73.8 | 66.7 | 84.3 | 77.7 | 73 | 91.4 | 85.8 | 78.4 | 90.8 | 85.8 | 79.2 | 89.7 | 80.5 | 72.2 | 79.8 | 69.6 | 61.3 | 61.5 | 51.5 | 43.8 | 58.5 | 47.6 | 35.5 | 57.9 | 41.7 | 31
2 | 2 | 11 | 61.8 | 48.7 | 38.2 | 72.3 | 62.2 | 38.6 | 79.3 | 68.7 | 56.3 | 89.2 | 79.7 | 72 | 90.1 | 84.4 | 80.8 | 95 | 90.6 | 84.1 | 95.9 | 91.5 | 83.5 | 93.2 | 85.1 | 77.9 | 84.2 | 77.1 | 68.4 | 70.7 | 60.5 | 50.4 | 66.4 | 55.7 | 41.6 | 62.6 | 46.1 | 36
2 | 2 | 12 | 65.6 | 52.8 | 43 | 76.4 | 67.4 | 44 | 83.6 | 73.7 | 59.5 | 91.1 | 84.9 | 75.8 | 92.9 | 89.5 | 85.8 | 96.1 | 92.4 | 88.5 | 98.3 | 94.6 | 87 | 96.6 | 87.6 | 82.2 | 86.7 | 80.6 | 72.2 | 74.9 | 64 | 55.8 | 71.1 | 59.3 | 44.3 | 66.6 | 48.8 | 37.9
2 | 2 | 15 | 69.3 | 55.1 | 45.1 | 80.9 | 71.1 | 46.7 | 85.6 | 76.2 | 64 | 93.4 | 86.8 | 77.6 | 94.6 | 91 | 88.3 | 96.9 | 93.5 | 89.7 | 99.1 | 96.2 | 89.9 | 97.4 | 89 | 84.2 | 88.6 | 83.3 | 74.7 | 78.8 | 69.4 | 61.7 | 76.5 | 62.2 | 47.4 | 70.1 | 51.9 | 39.2
2 | 2 | 20 | 69.6 | 55.1 | 45.3 | 80.9 | 71.1 | 46.7 | 85.6 | 76.2 | 64 | 93.4 | 86.8 | 77.6 | 94.6 | 91 | 88.3 | 96.9 | 93.5 | 89.7 | 99.1 | 96.2 | 89.9 | 97.4 | 89 | 84.6 | 88.6 | 83.3 | 74.7 | 78.8 | 69.4 | 61.9 | 76.5 | 62.5 | 47.4 | 70.1 | 52 | 39.2
2 | 2 | 25 | 69.6 | 55.1 | 45.3 | 80.9 | 71.1 | 46.7 | 85.6 | 76.2 | 64 | 93.4 | 86.8 | 77.6 | 94.6 | 91 | 88.3 | 96.9 | 93.5 | 89.7 | 99.1 | 96.2 | 89.9 | 97.4 | 89 | 84.6 | 88.6 | 83.3 | 74.7 | 78.8 | 69.4 | 61.9 | 76.5 | 62.5 | 47.4 | 70.1 | 52 | 39.2
2 | 2.25 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 2.25 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.6 | 12.2 | 5.4 | 2.7
2 | 2.25 | 6 | 24.9 | 13.6 | 8.5 | 28.2 | 19.8 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.2 | 22.4 | 16.9 | 10.9 | 26.3 | 15.5 | 8.1
2 | 2.25 | 8 | 43.1 | 28.9 | 17.2 | 48.7 | 36.6 | 22.2 | 52.2 | 41.7 | 34.9 | 64 | 55.3 | 47.6 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34 | 27.7 | 42.7 | 31.8 | 21.1 | 42.3 | 26.7 | 19
2 | 2.25 | 9 | 52.5 | 36.7 | 22.8 | 57.2 | 47.8 | 28.7 | 65.9 | 53.2 | 43.4 | 72.8 | 65.3 | 59.6 | 76.6 | 67.6 | 61.7 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.1 | 63.3 | 73.1 | 63.9 | 55.1 | 54.3 | 42.9 | 35.6 | 52.1 | 41.7 | 30.1 | 51.5 | 36.7 | 24.6
2 | 2.25 | 10 | 58.6 | 43 | 31.4 | 65.9 | 56.1 | 35.3 | 75.7 | 62.6 | 50 | 83.5 | 74.2 | 68.4 | 84.5 | 78.2 | 73 | 91.8 | 86.1 | 78.6 | 90.8 | 86.3 | 79.9 | 90.1 | 83.2 | 72.6 | 80 | 69.9 | 63.3 | 63.4 | 53.1 | 45.4 | 60.1 | 51.3 | 36.8 | 59.2 | 43.7 | 32
2 | 2.25 | 11 | 65.9 | 50.7 | 40.6 | 73.6 | 63.4 | 42.3 | 80.2 | 71 | 59.1 | 89.8 | 80.8 | 75.5 | 90.6 | 85.8 | 82.2 | 95.9 | 90.8 | 85.3 | 96.2 | 91.8 | 85.9 | 94.2 | 86.8 | 79.3 | 86.8 | 77.6 | 70.5 | 72.2 | 62.1 | 52.2 | 69.4 | 59.2 | 44.7 | 64.9 | 49.1 | 40.9
2 | 2.25 | 12 | 69.7 | 57 | 46.9 | 79.2 | 70.5 | 51 | 86.2 | 76.7 | 62.7 | 93.6 | 86.5 | 80 | 94.4 | 91.3 | 87.7 | 98 | 94.2 | 90.6 | 98.3 | 95.3 | 89.9 | 97.5 | 91.1 | 85.5 | 89.9 | 84 | 75.4 | 77.9 | 68.7 | 59.3 | 75.3 | 65 | 48.7 | 71.9 | 53.5 | 46.2
2 | 2.25 | 15 | 77 | 62.5 | 52 | 85 | 76.5 | 56.9 | 90.8 | 81.9 | 69.6 | 96.4 | 92.5 | 84.7 | 96.8 | 95.3 | 92.4 | 99.4 | 96 | 93.5 | 99.9 | 97.6 | 94.5 | 98.3 | 93.4 | 88.8 | 93.5 | 88.2 | 81 | 84.5 | 76.9 | 71.5 | 82 | 70.4 | 55.2 | 77.2 | 63 | 50.9
2 | 2.25 | 20 | 76.9 | 62.9 | 52 | 85.3 | 77.1 | 56.9 | 91.1 | 82 | 69.8 | 96.4 | 92.5 | 84.7 | 96.9 | 95.3 | 92.4 | 99.4 | 96.1 | 93.7 | 99.9 | 97.6 | 94.6 | 98.3 | 93.7 | 89.1 | 93.6 | 88.5 | 81.2 | 84.7 | 77.2 | 71.5 | 82.6 | 70.6 | 56.3 | 77.3 | 63.3 | 51.4
2 | 2.25 | 25 | 76.9 | 62.9 | 52 | 85.3 | 77.1 | 56.9 | 91.1 | 82 | 69.8 | 96.4 | 92.5 | 84.7 | 96.9 | 95.3 | 92.4 | 99.4 | 96.1 | 93.7 | 99.9 | 97.6 | 94.6 | 98.3 | 93.7 | 89.1 | 93.6 | 88.5 | 81.2 | 84.7 | 77.2 | 71.5 | 82.6 | 70.6 | 56.3 | 77.3 | 63.3 | 51.4
2 | 2.75 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 2.75 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 2.75 | 6 | 24.9 | 13.6 | 8.5 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 2.75 | 8 | 43.3 | 28.9 | 17.4 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.4 | 27 | 19.3
2 | 2.75 | 9 | 52.7 | 36.6 | 23.2 | 57.3 | 48.6 | 29.7 | 65.9 | 53.2 | 43.9 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.6 | 36.5 | 53.1 | 43.3 | 31 | 53.9 | 37 | 25.5
2 | 2.75 | 10 | 60 | 43.3 | 32.3 | 65.9 | 57.4 | 37.5 | 76 | 63.8 | 52.2 | 84 | 74.7 | 70.5 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.2 | 65.7 | 53.9 | 46.3 | 61.1 | 53.3 | 37.7 | 60.9 | 44.1 | 33.5
2 | 2.75 | 11 | 67.1 | 52.8 | 42 | 74.5 | 65.5 | 44.2 | 80.8 | 73.4 | 61 | 90.8 | 83.2 | 77.4 | 91 | 87.8 | 82.9 | 96 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.6 | 80 | 87.5 | 78.3 | 72.8 | 73.1 | 64.5 | 54 | 71.2 | 60.8 | 47.5 | 68.4 | 52.8 | 42.9
2 | 2.75 | 12 | 73.1 | 60.2 | 50.8 | 80.1 | 75.3 | 54.4 | 88.3 | 80.5 | 66.4 | 94.5 | 87.9 | 82.9 | 95.3 | 92.1 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96 | 91.3 | 97.5 | 93 | 86.6 | 91.3 | 85.8 | 77.8 | 79.4 | 71.1 | 61.4 | 79.3 | 69 | 52.5 | 73.7 | 58.6 | 50.5
2 | 2.75 | 15 | 86.1 | 73.5 | 64.1 | 91.1 | 85.6 | 71.3 | 95 | 88.4 | 80.2 | 98.8 | 96 | 91.9 | 99.7 | 98.5 | 96.6 | 100 | 98.2 | 96.4 | 100 | 99.1 | 96.7 | 100 | 97.7 | 94.2 | 97.1 | 94.6 | 88.5 | 91.5 | 84.5 | 80.3 | 89.8 | 82.4 | 68.7 | 86.1 | 73.4 | 65.3
2 | 2.75 | 20 | 88.8 | 75.9 | 65.3 | 92.7 | 86.1 | 72.9 | 95.8 | 89.2 | 80.7 | 99.1 | 96.1 | 92.5 | 100 | 98.9 | 96.8 | 100 | 98.3 | 96.5 | 100 | 99.1 | 96.7 | 100 | 98 | 95.5 | 97.4 | 95.8 | 89.9 | 92.1 | 86.7 | 81.4 | 90.7 | 83.2 | 72.3 | 86.9 | 75.8 | 68.5
2 | 2.75 | 25 | 88.8 | 75.9 | 65.3 | 92.7 | 86.1 | 72.9 | 95.8 | 89.2 | 80.7 | 99.1 | 96.1 | 92.5 | 100 | 98.9 | 96.9 | 100 | 98.3 | 96.5 | 100 | 99.1 | 96.7 | 100 | 98 | 95.5 | 97.4 | 95.8 | 89.9 | 92.1 | 86.7 | 81.4 | 90.7 | 83.2 | 72.3 | 86.9 | 75.8 | 68.5
2 | 3 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 3 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 3 | 6 | 24.9 | 13.6 | 8.6 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 3 | 8 | 43.3 | 28.9 | 17.6 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.5 | 27 | 19.4
2 | 3 | 9 | 52.9 | 36.6 | 23.2 | 57.3 | 48.6 | 29.8 | 65.9 | 53.2 | 44.1 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.9 | 36.5 | 53.1 | 43.3 | 31 | 54 | 37.2 | 25.6
2 | 3 | 10 | 60.2 | 43.3 | 32.3 | 65.9 | 57.7 | 37.6 | 76 | 63.8 | 52.4 | 84 | 74.7 | 70.7 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.3 | 65.7 | 54.2 | 46.5 | 61.1 | 54.6 | 38.1 | 61 | 44.6 | 33.5
2 | 3 | 11 | 67.5 | 53.1 | 42 | 74.5 | 65.5 | 44.7 | 81 | 73.5 | 61.4 | 91 | 83.2 | 77.5 | 91 | 87.8 | 83 | 96 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.6 | 80 | 87.5 | 78.3 | 73 | 73.1 | 65.5 | 54.2 | 71.2 | 60.8 | 48.3 | 68.7 | 53.4 | 43.4
2 | 3 | 12 | 73.3 | 60.3 | 51.7 | 80.3 | 75.3 | 55.4 | 88.9 | 80.8 | 67.5 | 94.7 | 88.3 | 83.7 | 95.7 | 92.3 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96.2 | 91.4 | 97.5 | 93 | 86.8 | 91.5 | 86 | 79.4 | 80.3 | 71.4 | 61.8 | 79.7 | 70.4 | 53.9 | 75.1 | 60.1 | 50.6
2 | 3 | 15 | 87.5 | 78.2 | 67.7 | 92.8 | 87.8 | 76 | 96.3 | 90.6 | 84.7 | 99.2 | 97.2 | 93.5 | 99.9 | 98.9 | 98 | 100 | 98.9 | 96.9 | 100 | 99.6 | 97.3 | 100 | 98.7 | 95.4 | 97.9 | 95.1 | 90.5 | 93.1 | 87.1 | 81.9 | 91.1 | 85 | 73.2 | 87.8 | 78.1 | 68.5
2 | 3 | 20 | 92.3 | 81.6 | 69.7 | 95.5 | 90.5 | 79.2 | 97.8 | 92.9 | 86.3 | 100 | 97.8 | 94.5 | 100 | 100 | 98.5 | 100 | 99.2 | 97 | 100 | 100 | 98.4 | 100 | 99.2 | 97.1 | 98.8 | 96.8 | 92 | 95 | 89.8 | 85.5 | 92.9 | 87.5 | 78.2 | 90.4 | 82 | 75
2 | 3 | 25 | 92.3 | 81.6 | 69.7 | 95.5 | 90.5 | 79.2 | 97.8 | 92.9 | 86.3 | 100 | 97.8 | 94.5 | 100 | 100 | 98.5 | 100 | 99.2 | 97 | 100 | 100 | 98.4 | 100 | 99.2 | 97.1 | 98.8 | 96.9 | 92 | 95 | 89.8 | 85.5 | 92.9 | 87.5 | 78.2 | 90.4 | 82 | 75
2 | 3.5 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 3.5 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 3.5 | 6 | 24.9 | 13.6 | 8.6 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 3.5 | 8 | 43.3 | 28.9 | 17.6 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.5 | 27 | 19.4
2 | 3.5 | 9 | 52.9 | 36.6 | 23.2 | 57.3 | 48.6 | 29.8 | 65.9 | 53.2 | 44.6 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.9 | 36.5 | 53.1 | 43.3 | 31 | 54 | 37.2 | 25.6
2 | 3.5 | 10 | 60.5 | 43.3 | 32.7 | 65.9 | 57.7 | 38 | 76 | 64.1 | 52.4 | 84 | 74.7 | 70.7 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.3 | 65.7 | 54.4 | 46.5 | 61.1 | 54.6 | 38.2 | 61 | 44.6 | 33.8
2 | 3.5 | 11 | 67.5 | 53.2 | 42.2 | 74.5 | 65.5 | 44.9 | 81 | 73.8 | 61.9 | 91 | 83.2 | 77.5 | 91 | 87.8 | 83 | 96.3 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.9 | 80 | 87.5 | 78.3 | 73.5 | 73.1 | 65.6 | 54.3 | 71.2 | 61.8 | 48.2 | 69 | 53.6 | 43.5
2 | 3.5 | 12 | 73.3 | 60.3 | 52.2 | 81.3 | 75.3 | 55.8 | 88.9 | 81.5 | 69 | 94.7 | 88.9 | 84.1 | 95.7 | 92.3 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96.2 | 91.4 | 97.5 | 93 | 86.8 | 91.6 | 86.3 | 80.3 | 80.3 | 71.4 | 62 | 79.8 | 71.8 | 56 | 75.9 | 60.3 | 51
2 | 3.5 | 15 | 89.1 | 81.3 | 73.7 | 93.9 | 90.1 | 79.7 | 96.9 | 91.8 | 87.4 | 99.4 | 97.8 | 94.4 | 100 | 99.3 | 98.5 | 100 | 99 | 97.2 | 100 | 100 | 98.3 | 100 | 98.9 | 96.4 | 98.9 | 95.6 | 92.1 | 93.9 | 89 | 83.9 | 93.7 | 86.3 | 77.5 | 89.9 | 80.8 | 70.5
2 | 3.5 | 20 | 95.9 | 91.1 | 84.1 | 98.6 | 94 | 88.4 | 99.8 | 97.3 | 93.5 | 100 | 100 | 97.1 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.5 | 95.9 | 98.8 | 95.6 | 92 | 97.1 | 93.2 | 88 | 96.3 | 90.7 | 84.2
2 | 3.5 | 25 | 96 | 91.1 | 84.1 | 98.8 | 94 | 88.4 | 99.8 | 97.3 | 93.5 | 100 | 100 | 97.1 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.5 | 95.9 | 98.8 | 95.6 | 92.1 | 97.2 | 93.2 | 88 | 96.3 | 90.7 | 84.2
2 | 4 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 4 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 4 | 6 | 24.9 | 13.6 | 8.6 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 4 | 8 | 43.3 | 28.9 | 17.6 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.5 | 27 | 19.4
2 | 4 | 9 | 52.9 | 36.6 | 23.2 | 57.3 | 48.6 | 29.8 | 65.9 | 53.2 | 44.6 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.9 | 36.5 | 53.1 | 43.3 | 31 | 54 | 37.2 | 25.6
2 | 4 | 10 | 60.7 | 43.3 | 32.9 | 65.9 | 57.7 | 38 | 76 | 64.1 | 52.4 | 84 | 74.7 | 70.7 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.3 | 65.7 | 54.4 | 46.5 | 61.1 | 54.6 | 38.2 | 61 | 44.6 | 33.9
2 | 4 | 11 | 67.5 | 53.2 | 42.2 | 74.5 | 65.5 | 44.9 | 81 | 73.8 | 61.9 | 91 | 83.2 | 77.5 | 91 | 87.8 | 83 | 96.3 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.9 | 80 | 87.5 | 78.3 | 73.5 | 73.1 | 65.6 | 54.5 | 71.2 | 61.8 | 48.2 | 69 | 53.6 | 43.5
2 | 4 | 12 | 73.4 | 60.3 | 52.2 | 81.5 | 75.3 | 55.9 | 88.9 | 81.5 | 69.4 | 94.7 | 88.9 | 84.1 | 95.7 | 92.3 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96.2 | 91.4 | 97.5 | 93 | 86.8 | 91.6 | 86.3 | 80.3 | 80.3 | 71.4 | 62.2 | 79.9 | 71.9 | 56.7 | 75.9 | 60.3 | 51
2 | 4 | 15 | 90.6 | 81.5 | 75 | 94.6 | 90.9 | 81.9 | 97.1 | 92.6 | 87.4 | 99.4 | 98.3 | 94.9 | 100 | 99.5 | 98.5 | 100 | 99.2 | 98 | 100 | 100 | 98.5 | 100 | 98.9 | 96.9 | 98.9 | 96 | 92.7 | 94.1 | 89.4 | 84.6 | 94.5 | 87.2 | 80.3 | 90.9 | 82.5 | 71.7
2 | 4 | 20 | 99 | 95.7 | 90.8 | 99.6 | 97.8 | 92.4 | 100 | 99.2 | 96.9 | 100 | 100 | 98.2 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.7 | 97.6 | 100 | 98 | 95.6 | 99.5 | 97.1 | 94.2 | 99.3 | 95.4 | 91.3
2 | 4 | 25 | 98.9 | 96 | 91.1 | 99.8 | 97.8 | 92.9 | 100 | 99.6 | 97.2 | 100 | 100 | 98.2 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.6 | 100 | 98.1 | 95.6 | 99.5 | 97.2 | 95 | 99.6 | 95.8 | 92.2
2 | 4.5 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 4.5 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 4.5 | 6 | 24.9 | 13.6 | 8.6 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 4.5 | 8 | 43.3 | 28.9 | 17.6 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.5 | 27 | 19.4
2 | 4.5 | 9 | 52.9 | 36.6 | 23.2 | 57.3 | 48.6 | 29.8 | 65.9 | 53.2 | 44.6 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.9 | 36.5 | 53.1 | 43.3 | 31 | 54 | 37.2 | 25.6
2 | 4.5 | 10 | 60.7 | 43.3 | 32.9 | 65.9 | 57.7 | 38 | 76 | 64.1 | 52.4 | 84 | 74.7 | 70.7 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.3 | 65.7 | 54.4 | 46.5 | 61.1 | 54.6 | 38.2 | 61 | 44.6 | 33.9
2 | 4.5 | 11 | 67.5 | 53.2 | 42.2 | 74.5 | 65.5 | 44.9 | 81 | 73.8 | 61.9 | 91 | 83.2 | 77.5 | 91 | 87.8 | 83 | 96.3 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.9 | 80 | 87.5 | 78.3 | 73.5 | 73.1 | 65.6 | 54.5 | 71.2 | 61.8 | 48.2 | 69 | 53.6 | 43.5
2 | 4.5 | 12 | 73.4 | 60.3 | 52.2 | 81.5 | 75.3 | 55.9 | 88.9 | 81.5 | 69.4 | 94.7 | 88.9 | 84.1 | 95.7 | 92.3 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96.2 | 91.4 | 97.5 | 93 | 86.8 | 91.6 | 86.3 | 80.3 | 80.3 | 71.4 | 62.2 | 79.9 | 71.9 | 56.7 | 75.9 | 60.3 | 51
2 | 4.5 | 15 | 91 | 81.7 | 75 | 94.6 | 90.9 | 81.9 | 97.1 | 93 | 87.8 | 99.4 | 98.6 | 95.3 | 100 | 99.5 | 98.5 | 100 | 99.2 | 98.1 | 100 | 100 | 98.5 | 100 | 98.9 | 96.9 | 98.9 | 96 | 92.8 | 94.2 | 89.4 | 84.9 | 94.6 | 87.8 | 80.7 | 91.3 | 83.2 | 71.9
2 | 4.5 | 20 | 99.8 | 97.3 | 93.4 | 100 | 98.5 | 94.7 | 100 | 100 | 98.4 | 100 | 100 | 99.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.4 | 100 | 99.1 | 97.1 | 100 | 98.5 | 96.5 | 100 | 98.1 | 94.7
2 | 4.5 | 25 | 100 | 98.3 | 95.2 | 100 | 99.1 | 95.7 | 100 | 100 | 98.8 | 100 | 100 | 99.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.2 | 100 | 99.6 | 98 | 100 | 99.2 | 97.7 | 100 | 99.1 | 96.3
2 | 5 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 5 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 5 | 6 | 24.9 | 13.6 | 8.6 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 5 | 8 | 43.3 | 28.9 | 17.6 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.5 | 27 | 19.4
2 | 5 | 9 | 52.9 | 36.6 | 23.2 | 57.3 | 48.6 | 29.8 | 65.9 | 53.2 | 44.6 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.9 | 36.5 | 53.1 | 43.3 | 31 | 54 | 37.2 | 25.6
2 | 5 | 10 | 60.7 | 43.3 | 32.9 | 65.9 | 57.7 | 38 | 76 | 64.1 | 52.4 | 84 | 74.7 | 70.7 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.3 | 65.7 | 54.4 | 46.5 | 61.1 | 54.6 | 38.2 | 61 | 44.6 | 33.9
2 | 5 | 11 | 67.5 | 53.2 | 42.2 | 74.5 | 65.5 | 44.9 | 81 | 73.8 | 61.9 | 91 | 83.2 | 77.5 | 91 | 87.8 | 83 | 96.3 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.9 | 80 | 87.5 | 78.3 | 73.5 | 73.1 | 65.6 | 54.5 | 71.2 | 61.8 | 48.2 | 69 | 53.6 | 43.5
2 | 5 | 12 | 73.4 | 60.3 | 52.2 | 81.5 | 75.3 | 55.9 | 88.9 | 81.5 | 69.4 | 94.7 | 88.9 | 84.1 | 95.7 | 92.3 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96.2 | 91.4 | 97.5 | 93 | 86.8 | 91.6 | 86.3 | 80.3 | 80.3 | 71.4 | 62.2 | 79.9 | 71.9 | 56.7 | 75.9 | 60.3 | 51
2 | 5 | 15 | 91 | 81.7 | 75 | 94.6 | 90.9 | 81.9 | 97.1 | 93 | 87.9 | 99.4 | 98.6 | 95.3 | 100 | 99.5 | 98.5 | 100 | 99.2 | 98.1 | 100 | 100 | 98.5 | 100 | 98.9 | 96.9 | 98.9 | 96 | 92.8 | 94.2 | 89.4 | 85 | 94.6 | 87.8 | 80.7 | 91.3 | 83.6 | 71.9
2 | 5 | 20 | 100 | 97.8 | 94.9 | 100 | 99.3 | 95.7 | 100 | 100 | 98.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.3 | 100 | 99.6 | 98.2 | 100 | 98.8 | 97.1 | 100 | 98.9 | 95.2
2 | 5 | 25 | 100 | 99.7 | 98 | 100 | 100 | 97.9 | 100 | 100 | 99.6 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.4 | 100 | 100 | 98.6 | 100 | 100 | 98.2
4 | 0.25 | 2 | [12 empty] | 0.5 |  |  | 1 |  |  | 0.5 |  |  | 0.9
4 | 0.25 | 4 | [9 empty] | 1.5 |  |  | 2.9 | 0.4 |  | 4.3 | 1 |  | 2.5 | 0.9 |  | 4.2 | 1.5 |  | 0.8
4 | 0.25 | 6 | [9 empty] | 1.5 |  |  | 3.6 | 0.5 |  | 6.2 | 1 |  | 2.8 | 1.3 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 8 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 9 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 10 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 11 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 12 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 15 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 20 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 25 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.5 | 2 |  |  |  | 0.4 |  |  | 0.5 |  |  | 1.8 | 0.4 |  | 2.4 | 0.5 |  | 3 | 1.3 |  | 3.5 | 1.2 | 0.4 | 2.3 | 0.9 | 0.1 | 1.5 | 0.6 |  | 0.5 | [5 empty] | 0.3
4 | 0.5 | 4 | 1.6 |  |  | 2.7 | 1.8 |  | 4.7 | 0.9 |  | 8.3 | 3.8 | 1.1 | 9.8 | 3.4 | 1.1 | 12.2 | 7.8 | 2.6 | 12.3 | 7.1 | 4.2 | 13.2 | 7.3 | 4.1 | 8.1 | 4.4 | 1.4 | 3.1 | 1.5 |  | 2 | 0.4 |  | 2.7 | 0.5
4 | 0.5 | 6 | 4 | 0.4 |  | 5.1 | 2.7 |  | 8.4 | 2.3 | 0.4 | 15.2 | 7.9 | 4.3 | 15.5 | 9.5 | 5 | 20.6 | 13.9 | 6 | 25.7 | 16.3 | 7.9 | 21.3 | 14.8 | 8.2 | 15.3 | 7.9 | 2.2 | 4.7 | 1.9 | 0.1 | 2.6 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 8 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 16.5 | 7.9 | 4.5 | 19.6 | 11.7 | 6 | 23.8 | 16.5 | 6.7 | 29.2 | 19.1 | 9.4 | 25 | 16 | 8.4 | 16.9 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 9 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 10 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 11 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 12 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 15 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 20 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 25 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.75 | 2 | 0.5 |  |  | 1 |  |  | 1.6 | 0.5 |  | 2.8 | 1.3 | 0.4 | 2.8 | 1.2 | 0.4 | 4 | 1.9 | 1 | 4.1 | 2 | 0.8 | 3.4 | 1.3 | 0.4 | 2.2 | 1.1 | 0.4 | 0.5 | 0.4 |  | 0.6 |  |  | 0.5
4 | 0.75 | 4 | 4 | 0.9 |  | 7.1 | 3.7 | 0.1 | 8.4 | 3.5 | 0.8 | 13.4 | 6.9 | 4.3 | 13.1 | 7.7 | 4.2 | 17.7 | 12.6 | 6 | 16.5 | 11.8 | 7.1 | 17.3 | 12.2 | 6.6 | 12.5 | 7.9 | 4.6 | 5.6 | 2.6 | 0.7 | 3.6 | 1.9 | 0.1 | 4.7 | 2 | 0.4
4 | 0.75 | 6 | 10.1 | 3.6 | 0.6 | 14 | 7.9 | 1.6 | 18.8 | 8.6 | 5.6 | 27.7 | 16 | 11.9 | 27.7 | 19.4 | 14.1 | 35.9 | 24.2 | 14.7 | 35.5 | 28.2 | 20.4 | 36 | 25.8 | 17.2 | 26.1 | 18.6 | 10.6 | 13.8 | 6.3 | 3.2 | 10 | 4.2 | 1.5 | 11.3 | 5.4 | 1.3
4 | 0.75 | 8 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 12 | 7.7 | 34.6 | 22.1 | 14.9 | 36 | 28.2 | 19.3 | 44.1 | 34.6 | 22.7 | 48.6 | 37 | 28.1 | 45.4 | 36.8 | 26.5 | 33.9 | 25.4 | 12.9 | 17.4 | 9.5 | 5.1 | 11.9 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 9 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 22.6 | 15.3 | 37.9 | 29.2 | 22 | 45.8 | 36.3 | 23.7 | 50.2 | 39.2 | 29.3 | 46.7 | 37.8 | 26.8 | 34.5 | 25.4 | 13.3 | 17.4 | 9.9 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 10 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.4 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.9 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 11 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.7 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.8 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 12 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.7 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.8 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 15 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.7 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.8 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 20 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.7 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.8 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 25 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.7 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.8 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 1 | 2 | 0.9 |  |  | 1.6 |  |  | 1.7 | 0.8 |  | 3 | 1.5 | 0.6 | 3.2 | 1.3 | 0.5 | 4.2 | 2.2 | 1.1 | 4.4 | 2.3 | 1 | 3.8 | 1.7 | 0.7 | 2.5 | 1.5 | 0.6 | 0.9 | 0.4 |  | 1 |  |  | 1.2 | 0.4
4 | 1 | 4 | 5.5 | 2 | 0.1 | 9.4 | 4.2 | 1.6 | 10.4 | 5.9 | 1.6 | 15.7 | 9.6 | 6.4 | 14.7 | 11.3 | 5.9 | 20.6 | 14.9 | 9.3 | 19.6 | 13.4 | 8.2 | 19.2 | 13.4 | 9 | 13.6 | 9.4 | 6.3 | 8 | 4 | 2.3 | 6.2 | 2.9 | 1 | 5.9 | 3 | 0.9
4 | 1 | 6 | 15.6 | 7.8 | 2 | 18.8 | 12.6 | 5 | 26 | 15.3 | 7.6 | 33.7 | 23.3 | 17.7 | 33.5 | 26.7 | 18.7 | 44 | 32.5 | 24.2 | 42.6 | 33.3 | 25.1 | 41.9 | 30.4 | 24.1 | 31.8 | 25.6 | 16.7 | 20.4 | 10.3 | 6.2 | 14.5 | 8.2 | 4.8 | 17.3 | 7.8 | 3.1
4 | 1 | 8 | 25.6 | 12.9 | 3.2 | 28.8 | 19 | 10.1 | 36 | 23.4 | 14 | 51.7 | 35.6 | 28.2 | 50.7 | 43.3 | 33.8 | 60.8 | 50.6 | 40.6 | 64.7 | 54 | 39.1 | 59.4 | 49.9 | 41 | 45.4 | 38.5 | 28.3 | 28.5 | 17.6 | 10.1 | 23.5 | 14.3 | 7.3 | 25.7 | 12.1 | 5.9
4 | 1 | 9 | 25.9 | 13.4 | 3.2 | 29.6 | 20.4 | 10.5 | 38.8 | 27.6 | 17.3 | 54 | 38.6 | 30.4 | 56.1 | 47.2 | 36.5 | 64.6 | 53.8 | 44.9 | 70.1 | 58.7 | 43.9 | 64.9 | 52.6 | 44 | 50.8 | 41.4 | 30.7 | 30.9 | 20.7 | 11.3 | 25.1 | 15.6 | 7.6 | 26.9 | 12.1 | 6
4 | 1 | 10 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.6 | 54.5 | 40.3 | 31.4 | 59.2 | 49.7 | 37.7 | 65.7 | 56 | 46.4 | 71.1 | 60.3 | 46 | 66.9 | 53.2 | 44.9 | 52.3 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1 | 11 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.8 | 54.8 | 40.3 | 31.7 | 59.4 | 50.3 | 38.2 | 65.8 | 56.1 | 46.5 | 71.4 | 60.1 | 46.6 | 67.2 | 53.8 | 45.2 | 52.5 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1 | 12 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.8 | 54.8 | 40.3 | 31.7 | 59.4 | 50.3 | 38.2 | 65.8 | 56.1 | 46.9 | 71.4 | 60.1 | 46.6 | 67.2 | 53.8 | 45.6 | 52.5 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1 | 15 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.8 | 54.8 | 40.3 | 31.7 | 59.4 | 50.5 | 38.2 | 65.8 | 56.4 | 46.9 | 71.4 | 60.1 | 46.6 | 67.2 | 53.8 | 45.6 | 52.5 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1 | 20 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.8 | 54.8 | 40.3 | 31.7 | 59.4 | 50.5 | 38.2 | 65.8 | 56.4 | 46.9 | 71.4 | 60.1 | 46.6 | 67.2 | 53.8 | 45.6 | 52.5 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1 | 25 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.8 | 54.8 | 40.3 | 31.7 | 59.4 | 50.5 | 38.2 | 65.8 | 56.4 | 46.9 | 71.4 | 60.1 | 46.6 | 67.2 | 53.8 | 45.6 | 52.5 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1.25 | 2 | 0.9 |  |  | 1.9 | 0.4 |  | 1.7 | 0.8 |  | 3 | 1.8 | 0.9 | 3.2 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.3 | 1.7 | 0.7 | 2.5 | 1.5 | 0.6 | 1.4 | 0.5 |  | 1.3 | 0.4 |  | 1.3 | 0.4
4 | 1.25 | 4 | 6 | 2.8 | 1.1 | 10.8 | 6.4 | 2.4 | 12.3 | 6.7 | 2.9 | 16.3 | 10.3 | 7.8 | 15.9 | 11.8 | 7.3 | 20.9 | 16.5 | 10.3 | 20.1 | 15.1 | 8.6 | 21.3 | 14 | 9.1 | 15.4 | 10.3 | 6.7 | 9 | 4.8 | 2.7 | 7.1 | 3.9 | 1.7 | 7.6 | 3.5 | 1.3
4 | 1.25 | 6 | 20.2 | 8.6 | 5.1 | 22.6 | 15.3 | 6.3 | 26.9 | 18 | 11.1 | 36.1 | 26.3 | 20.8 | 36.4 | 28.5 | 22.3 | 47.7 | 39.2 | 27.8 | 44.9 | 36.8 | 27.2 | 43.3 | 32.7 | 27.2 | 34.4 | 27.8 | 17.7 | 23 | 14.5 | 9.1 | 18.5 | 11.7 | 6.9 | 20.4 | 10.3 | 5
4 | 1.25 | 8 | 34.2 | 19.8 | 9.1 | 34.7 | 26.8 | 12.3 | 45.5 | 32.1 | 21.6 | 57.8 | 45 | 38.1 | 57 | 51.3 | 42.7 | 69.8 | 58.8 | 46.5 | 69.9 | 61.3 | 46.8 | 66.7 | 56.7 | 46.9 | 54.2 | 45.4 | 34.9 | 34.1 | 24.6 | 17.9 | 31.5 | 21.7 | 11.8 | 33.7 | 17.9 | 10.9
4 | 1.25 | 9 | 35.8 | 22.8 | 10.1 | 40.5 | 29.2 | 15 | 49.9 | 40.1 | 26.3 | 63.7 | 50.4 | 43.2 | 66.5 | 59.3 | 50.7 | 76.6 | 66 | 55.4 | 76.4 | 70.7 | 55.3 | 73.7 | 65.9 | 54.5 | 62 | 51.3 | 39.2 | 41.5 | 31.7 | 21.1 | 36.9 | 25.7 | 13.9 | 36 | 21.2 | 13.9
4 | 1.25 | 10 | 38.3 | 23.3 | 11.3 | 43.8 | 32.3 | 15.7 | 52.5 | 42.3 | 27.5 | 68.7 | 55 | 45.3 | 72.9 | 62 | 55.4 | 79.8 | 71.3 | 58.9 | 82.1 | 75.4 | 58.7 | 76.9 | 68.5 | 58.4 | 65.4 | 55.1 | 42.2 | 44.8 | 33.2 | 22.2 | 38.3 | 27.1 | 14.5 | 37.2 | 22.2 | 15
4 | 1.25 | 11 | 38.2 | 23.8 | 11.3 | 45 | 32.3 | 16.5 | 53.7 | 43 | 27.5 | 70.9 | 56.5 | 45.7 | 73.9 | 64 | 57.7 | 80.8 | 73.5 | 60.2 | 84.1 | 76.6 | 60.2 | 78.3 | 70.7 | 59.9 | 65.8 | 57.4 | 42.7 | 45.1 | 34.9 | 22.7 | 38.7 | 28.3 | 14.9 | 37.1 | 22.7 | 15
4 | 1.25 | 12 | 38.2 | 23.8 | 11.3 | 45.1 | 32.3 | 16.5 | 53.8 | 43 | 27.6 | 70.9 | 56.8 | 45.7 | 73.9 | 64.5 | 58 | 80.8 | 73.5 | 60.9 | 84.1 | 77.3 | 60.7 | 78.5 | 70.7 | 60 | 66.5 | 57.4 | 42.7 | 45.1 | 34.9 | 22.7 | 38.7 | 28.3 | 15.1 | 37.1 | 22.7 | 15
4 | 1.25 | 15 | 38.5 | 23.8 | 11.3 | 45.1 | 32.3 | 16.5 | 53.8 | 43 | 27.6 | 70.9 | 56.8 | 45.7 | 74.3 | 64.5 | 58 | 80.8 | 73.5 | 60.9 | 84.1 | 77.3 | 61.2 | 78.5 | 70.7 | 60.1 | 66.5 | 57.4 | 42.7 | 45.1 | 34.9 | 22.7 | 38.8 | 28.3 | 15.1 | 37.1 | 22.7 | 15
4 | 1.25 | 20 | 38.4 | 23.8 | 11.3 | 45.1 | 32.3 | 16.5 | 53.8 | 43 | 27.6 | 70.9 | 56.8 | 45.7 | 74.3 | 64.5 | 58 | 80.8 | 73.5 | 60.9 | 84.1 | 77.3 | 61.2 | 78.5 | 70.7 | 60.1 | 66.5 | 57.5 | 42.7 | 45.1 | 34.9 | 22.7 | 38.8 | 28.3 | 15.1 | 37.1 | 22.7 | 15
4 | 1.25 | 25 | 38.4 | 23.8 | 11.3 | 45.1 | 32.3 | 16.5 | 53.8 | 43 | 27.6 | 70.9 | 56.8 | 45.7 | 74.3 | 64.5 | 58 | 80.8 | 73.5 | 60.9 | 84.1 | 77.3 | 61.2 | 78.5 | 70.7 | 60.1 | 66.5 | 57.5 | 42.7 | 45.1 | 34.9 | 22.7 | 38.8 | 28.3 | 15.1 | 37.1 | 22.7 | 15
4 | 1.5 | 2 | 0.9 | 0.4 |  | 2.2 | 0.4 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 1.7 | 0.7 | 2.5 | 1.5 | 0.8 | 1.4 | 0.5 | 0.4 | 1.3 | 0.4 |  | 1.4 | 0.4
4 | 1.5 | 4 | 7.5 | 3.4 | 1.3 | 11.5 | 6.4 | 2.8 | 12.4 | 7.3 | 3.5 | 16.4 | 11.4 | 8.6 | 16.3 | 12.6 | 7.7 | 21.3 | 18.1 | 10.7 | 20.1 | 15.1 | 8.8 | 21.4 | 14 | 9.7 | 16.2 | 10.6 | 7.3 | 9.3 | 5.4 | 3 | 8.2 | 4.6 | 2.5 | 9.6 | 4.3 | 1.8
4 | 1.5 | 6 | 22.1 | 10.6 | 5.8 | 24.8 | 16.1 | 7.8 | 27.9 | 18.8 | 12.8 | 36.4 | 27.8 | 23.5 | 36.7 | 29.8 | 23.5 | 48.8 | 39.7 | 28.6 | 46.9 | 37.4 | 27.7 | 44.2 | 35.6 | 28.6 | 36 | 28.8 | 18.9 | 24.6 | 17.6 | 10.8 | 19 | 13.9 | 7.9 | 22.2 | 13.2 | 5.9
4 | 1.5 | 8 | 37.4 | 23.1 | 12.7 | 40.6 | 31.3 | 15.9 | 47.5 | 35.8 | 25.3 | 61.5 | 48.1 | 42.1 | 60.5 | 55 | 46 | 72.6 | 62.1 | 51.4 | 73.3 | 64 | 53 | 68.1 | 60.6 | 48.9 | 57.8 | 48.9 | 39.7 | 41.2 | 29.6 | 21.6 | 35.8 | 26.5 | 17.5 | 37.5 | 22.2 | 13.8
4 | 1.5 | 9 | 40.9 | 30.5 | 15.4 | 48.6 | 39.2 | 20.1 | 58.8 | 44.9 | 33.6 | 69.5 | 57.4 | 51 | 72.3 | 63.8 | 55.3 | 81.3 | 72.1 | 62.6 | 79.5 | 73.9 | 63.9 | 78.5 | 68.3 | 58.7 | 66.1 | 57.8 | 47 | 47.3 | 36.8 | 27.5 | 44 | 33.1 | 20.9 | 42.2 | 26.5 | 17.1
4 | 1.5 | 10 | 45.4 | 32.3 | 18.5 | 56.2 | 42.7 | 25.4 | 63.4 | 50.7 | 40.4 | 75.3 | 63.2 | 54.8 | 80 | 71.4 | 64.4 | 86.1 | 80.8 | 70.3 | 87.7 | 81.9 | 70.9 | 84.1 | 75.4 | 65.4 | 72.6 | 62.9 | 52.6 | 55.2 | 42.7 | 32.8 | 50.5 | 36.4 | 23.9 | 46.9 | 30.5 | 21.1
4 | 1.5 | 11 | 47.6 | 34.1 | 20.3 | 57.7 | 46.4 | 26.1 | 70 | 52.6 | 42.1 | 80 | 67.6 | 58.3 | 82.9 | 76.2 | 68.4 | 88.7 | 82.8 | 72.7 | 91.5 | 85.6 | 74.7 | 86.7 | 78.2 | 69 | 75.6 | 66 | 55.6 | 58.6 | 46.8 | 35.4 | 52.8 | 36.9 | 25.6 | 48.9 | 32.5 | 22.5
4 | 1.5 | 12 | 47.8 | 34.1 | 21.1 | 58.5 | 47 | 26.5 | 69.9 | 53.1 | 42.4 | 81.2 | 70.3 | 59.8 | 83.1 | 78.1 | 69.6 | 89.2 | 83.1 | 74.2 | 92.8 | 85.9 | 74.9 | 87.1 | 79 | 69.7 | 75.9 | 67.4 | 56.2 | 59.5 | 47.7 | 35.9 | 53.7 | 37.1 | 26.4 | 48.9 | 32.7 | 23
4 | 1.5 | 15 | 47.8 | 34.1 | 21.2 | 58.5 | 47.6 | 26.5 | 69.9 | 53.1 | 42.6 | 81.7 | 70.3 | 59.8 | 83.4 | 78.1 | 69.6 | 89.2 | 83.6 | 74.1 | 92.8 | 86.4 | 74.9 | 87.3 | 79 | 69.9 | 75.9 | 67.4 | 56.2 | 59.5 | 48 | 35.9 | 54.4 | 37.1 | 26.4 | 49 | 33.1 | 23
4 | 1.5 | 20 | 48 | 34.1 | 21.2 | 58.5 | 47.6 | 26.5 | 69.9 | 53.1 | 42.6 | 81.7 | 70.3 | 59.8 | 83.4 | 78.1 | 69.6 | 89.2 | 83.6 | 74.1 | 92.8 | 86.4 | 74.9 | 87.3 | 79 | 69.9 | 75.9 | 67.4 | 56.2 | 59.5 | 48 | 35.9 | 54.4 | 37.1 | 26.4 | 49 | 33.1 | 23
4 | 1.5 | 25 | 48 | 34.1 | 21.2 | 58.5 | 47.6 | 26.5 | 69.9 | 53.1 | 42.6 | 81.7 | 70.3 | 59.8 | 83.4 | 78.1 | 69.6 | 89.2 | 83.6 | 74.1 | 92.8 | 86.4 | 74.9 | 87.3 | 79 | 69.9 | 75.9 | 67.4 | 56.2 | 59.5 | 48 | 35.9 | 54.4 | 37.1 | 26.4 | 49 | 33.1 | 23
4 | 1.75 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 1.75 | 4 | 7.8 | 3.4 | 1.6 | 11.8 | 6.8 | 3.2 | 12.5 | 7.3 | 4.1 | 16.4 | 11.8 | 8.6 | 16.3 | 13 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.4 | 3.4 | 8.3 | 4.7 | 2.5 | 9.7 | 4.6 | 2
4 | 1.75 | 6 | 22.9 | 11.8 | 6.6 | 25.8 | 17.9 | 8.8 | 28.1 | 20.3 | 15.4 | 38.8 | 29.2 | 24 | 37.2 | 30.8 | 24.2 | 48.8 | 39.7 | 29 | 46.9 | 37.6 | 28.3 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 24.8 | 17.6 | 11.2 | 20.8 | 14.9 | 8.7 | 22.6 | 13.7 | 6.2
4 | 1.75 | 8 | 39.5 | 25.7 | 14.6 | 43 | 34.1 | 19.4 | 48.5 | 38.3 | 30.4 | 63.3 | 50.6 | 44.9 | 61.8 | 55.9 | 46.7 | 73.5 | 63.2 | 53.9 | 73.4 | 64.5 | 54.2 | 68.1 | 61.3 | 49.7 | 60.4 | 50.4 | 41.7 | 43.4 | 31.3 | 23.9 | 38.5 | 29.3 | 18.2 | 38.2 | 24.7 | 16.5
4 | 1.75 | 9 | 47.1 | 33.1 | 19.1 | 54.2 | 42.1 | 24.7 | 62.2 | 46.8 | 38.9 | 71.3 | 60.7 | 55.5 | 73.2 | 65.7 | 57.9 | 83.3 | 75.3 | 65.6 | 80.9 | 75.5 | 66.6 | 80.3 | 70.2 | 60.3 | 70.3 | 60.3 | 51.4 | 50.9 | 39.4 | 31.8 | 46.3 | 36.3 | 25.9 | 44.6 | 30.6 | 20.4
4 | 1.75 | 10 | 51.4 | 37.9 | 25.4 | 62.4 | 50.6 | 29.4 | 71.7 | 56.3 | 44.1 | 81 | 70.1 | 62.3 | 82.9 | 73.3 | 68.2 | 89.4 | 83.5 | 75 | 89 | 83.5 | 75.1 | 87.5 | 76.5 | 68.1 | 75.2 | 66.8 | 57.6 | 58.1 | 46.9 | 38.3 | 54.8 | 42.5 | 30.3 | 53.3 | 36.6 | 25.7
4 | 1.75 | 11 | 55.9 | 42.1 | 31.8 | 67 | 56.6 | 31.7 | 76.3 | 64 | 49.1 | 86.7 | 75.6 | 67.5 | 87 | 81.2 | 75.5 | 92.6 | 87.4 | 80.1 | 95.1 | 88.4 | 80.4 | 89.7 | 83.1 | 74.6 | 80.9 | 72.5 | 62.4 | 67.1 | 54.3 | 44.3 | 60.2 | 47.4 | 33 | 57.1 | 40.1 | 29
4 | 1.75 | 12 | 58 | 43.1 | 34.6 | 69.1 | 58.3 | 33.9 | 78.8 | 64.7 | 51.7 | 87.1 | 78.3 | 68.6 | 89.9 | 84.7 | 79.3 | 94 | 88.9 | 82.6 | 95.8 | 89.5 | 82.1 | 92.6 | 83.9 | 77 | 82.1 | 74.4 | 65.3 | 72.1 | 57.5 | 47.8 | 62.1 | 49 | 35.1 | 59.7 | 40.9 | 29.1
4 | 1.75 | 15 | 58.3 | 44 | 35.1 | 69.4 | 59.8 | 35.2 | 79.9 | 66 | 54.8 | 87.5 | 78.6 | 69 | 90.6 | 86 | 81.1 | 94.5 | 89.4 | 83.6 | 96 | 90.2 | 82.3 | 93.1 | 84.4 | 78.7 | 83.2 | 75.8 | 65.6 | 73.5 | 59.1 | 49.2 | 63.6 | 49.4 | 36.6 | 60 | 42.1 | 29.5
4 | 1.75 | 20 | 58.3 | 44 | 35.1 | 69.4 | 59.8 | 35.2 | 79.9 | 66 | 54.8 | 87.5 | 78.6 | 69 | 90.6 | 86 | 81.1 | 94.5 | 89.4 | 83.6 | 96 | 90.2 | 82.3 | 93.1 | 84.4 | 78.7 | 83.2 | 75.8 | 65.6 | 73.5 | 59.1 | 49.2 | 63.6 | 49.4 | 36.6 | 60 | 42.1 | 29.5
4 | 1.75 | 25 | 58.3 | 44 | 35.1 | 69.4 | 59.8 | 35.2 | 79.9 | 66 | 54.8 | 87.5 | 78.6 | 69 | 90.6 | 86 | 81.1 | 94.5 | 89.4 | 83.6 | 96 | 90.2 | 82.3 | 93.1 | 84.4 | 78.7 | 83.2 | 75.8 | 65.6 | 73.5 | 59.1 | 49.2 | 63.6 | 49.4 | 36.6 | 60 | 42.1 | 29.5
4 | 2 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 2 | 4 | 7.9 | 3.4 | 1.6 | 12.1 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.8 | 3.4 | 8.3 | 4.7 | 2.6 | 10.6 | 4.6 | 2
4 | 2 | 6 | 23.1 | 12 | 6.7 | 25.9 | 18 | 8.9 | 28.4 | 20.3 | 15.4 | 39 | 29.2 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 24.8 | 18.3 | 11.2 | 20.8 | 15.7 | 9.2 | 23.5 | 13.7 | 6.8
4 | 2 | 8 | 40.1 | 26.1 | 15.6 | 44.9 | 34.6 | 20.2 | 50.2 | 39.2 | 31.6 | 63.3 | 53.1 | 45.1 | 62.1 | 56.5 | 47.6 | 73.6 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.3 | 49.9 | 61.1 | 50.8 | 42.4 | 44 | 31.9 | 25.3 | 40.2 | 29.4 | 19 | 39.1 | 25.1 | 17.5
4 | 2 | 9 | 50.9 | 34.7 | 20.6 | 54.9 | 45.5 | 25.9 | 63.4 | 48.9 | 41.2 | 71.3 | 62.8 | 57.4 | 74.6 | 65.7 | 58.4 | 84.4 | 76 | 66.2 | 81.4 | 76.6 | 68.1 | 80.9 | 71.2 | 60.5 | 71.4 | 61.7 | 53.6 | 52.7 | 40.1 | 33 | 48.5 | 38.3 | 26.7 | 47.1 | 33.1 | 22.5
4 | 2 | 10 | 55.7 | 41.8 | 27.3 | 63.3 | 54 | 31.8 | 73.7 | 59.9 | 46.9 | 82.1 | 72.2 | 64.9 | 83.4 | 75.9 | 71.3 | 90.3 | 84.6 | 77.3 | 89.7 | 84.5 | 78 | 88.5 | 78.9 | 70 | 78.1 | 68.2 | 59.6 | 59.1 | 50.5 | 42.3 | 57.9 | 46.1 | 33.6 | 56.8 | 39.4 | 29.1
4 | 2 | 11 | 60 | 47.2 | 35.6 | 71.2 | 61.3 | 37.1 | 78.1 | 66.9 | 54.6 | 88.9 | 78.5 | 70.9 | 89.6 | 83.7 | 79.6 | 94.3 | 90 | 83.2 | 95.6 | 90.5 | 82.9 | 92.7 | 84.5 | 76.6 | 83.8 | 75.1 | 66.6 | 69 | 58.2 | 48.7 | 64.3 | 53.9 | 40.3 | 61.4 | 44.8 | 34.5
4 | 2 | 12 | 63.9 | 51.5 | 41 | 74.4 | 66.4 | 41.9 | 83.3 | 72.2 | 57.8 | 90.9 | 83.6 | 74.9 | 92.5 | 88.7 | 84.6 | 95.7 | 91.9 | 87.7 | 97.7 | 94.1 | 85.1 | 96.4 | 87.2 | 81.4 | 86.1 | 79 | 70.7 | 74.4 | 63.4 | 53.9 | 68.8 | 58.2 | 42.6 | 65.5 | 46.9 | 36.6
4 | 2 | 15 | 67.4 | 53.5 | 44.2 | 79.9 | 70.3 | 44.6 | 84.6 | 74.9 | 62.7 | 92.7 | 86.1 | 76.9 | 94.3 | 90.3 | 87.3 | 96.9 | 92.8 | 89.3 | 98.9 | 95.8 | 89.2 | 96.9 | 87.9 | 83.7 | 88.2 | 82.6 | 73.7 | 77.6 | 68.3 | 60.5 | 74.9 | 59.6 | 46.1 | 68.8 | 50.9 | 38.1
4 | 2 | 20 | 67.8 | 53.5 | 44.6 | 79.9 | 70.3 | 44.6 | 84.6 | 74.9 | 62.7 | 92.8 | 86.1 | 76.9 | 94.3 | 90.3 | 87.4 | 96.9 | 92.8 | 89.3 | 98.9 | 95.8 | 89.2 | 96.9 | 87.9 | 83.8 | 88.2 | 82.6 | 73.7 | 77.8 | 68.3 | 60.6 | 74.9 | 59.6 | 46.1 | 68.8 | 50.9 | 38.1
4 | 2 | 25 | 67.8 | 53.5 | 44.6 | 79.9 | 70.3 | 44.6 | 84.6 | 74.9 | 62.7 | 92.8 | 86.1 | 76.9 | 94.3 | 90.3 | 87.4 | 96.9 | 92.8 | 89.3 | 98.9 | 95.8 | 89.2 | 96.9 | 87.9 | 83.8 | 88.2 | 82.6 | 73.7 | 77.8 | 68.3 | 60.6 | 74.9 | 59.6 | 46.1 | 68.8 | 50.9 | 38.1
4 | 2.25 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 2.25 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 4.7 | 2.2
4 | 2.25 | 6 | 23.5 | 12 | 7.3 | 26.3 | 18.6 | 9.5 | 28.4 | 20.4 | 15.4 | 39 | 29.3 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 9.7 | 24.3 | 13.7 | 7
4 | 2.25 | 8 | 40.5 | 26.5 | 15.8 | 46.4 | 35.2 | 21 | 50.2 | 39.7 | 31.8 | 63.3 | 53.6 | 45.1 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.3 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.1 | 40.9 | 30 | 19.3 | 40.2 | 25.7 | 17.8
4 | 2.25 | 9 | 50.9 | 34.7 | 21.5 | 55.5 | 46.1 | 26.7 | 63.3 | 50.1 | 41.2 | 71.3 | 63.5 | 57.7 | 74.9 | 66.3 | 58.7 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.2 | 60.5 | 71.8 | 61.7 | 53.6 | 52.6 | 40.6 | 33.9 | 50.2 | 39.3 | 28.3 | 49.5 | 34.1 | 22.5
4 | 2.25 | 10 | 56.9 | 41.9 | 28.6 | 64.4 | 55.2 | 33.3 | 74.2 | 61 | 48.1 | 82.2 | 72.6 | 67 | 83.7 | 76.3 | 71.3 | 90.9 | 84.7 | 77.8 | 89.7 | 84.8 | 78.8 | 89.2 | 81.9 | 70.5 | 78.1 | 68.6 | 62.3 | 60.8 | 52 | 43.5 | 58.3 | 48.6 | 35.1 | 57.4 | 41.5 | 29.5
4 | 2.25 | 11 | 64.5 | 48.9 | 37.9 | 72.7 | 62.2 | 40.3 | 78.8 | 69 | 57.3 | 89.3 | 79.4 | 74.3 | 90 | 84.7 | 81 | 95.1 | 90.6 | 84.4 | 95.7 | 90.5 | 84.4 | 93.5 | 86 | 77.9 | 85.7 | 76 | 68.9 | 71 | 61.2 | 50.6 | 67.6 | 56.8 | 42.2 | 63.3 | 47.3 | 38.9
4 | 2.25 | 12 | 68.6 | 55.5 | 45.1 | 77.6 | 70.1 | 48.7 | 84.7 | 75.5 | 61.3 | 93.3 | 86.3 | 78.6 | 94 | 90.6 | 86.7 | 97.6 | 93.2 | 89.8 | 97.9 | 94.9 | 88.3 | 97.4 | 90.1 | 84.5 | 89.4 | 83.2 | 74.4 | 76.5 | 67.2 | 57.3 | 73.9 | 63.2 | 47.1 | 69.7 | 52.7 | 45.3
4 | 2.25 | 15 | 75.9 | 60.8 | 50.7 | 84.5 | 75.1 | 55.1 | 90.1 | 80.8 | 68.6 | 96.4 | 91.7 | 83.5 | 96.5 | 95 | 91.8 | 99.3 | 95.4 | 93.1 | 99.9 | 97.4 | 94 | 98.2 | 93.1 | 88.1 | 93.3 | 87.8 | 80.3 | 83.6 | 75.8 | 69.6 | 81.4 | 68.5 | 53.7 | 76.5 | 62.2 | 49.3
4 | 2.25 | 20 | 75.9 | 61.2 | 50.7 | 84.9 | 75.7 | 55.1 | 90.3 | 81.2 | 68.8 | 96.4 | 91.7 | 83.5 | 96.6 | 95 | 91.8 | 99.3 | 95.4 | 93.1 | 99.9 | 97.4 | 94 | 98.2 | 93.1 | 88.4 | 93.3 | 88.2 | 80.4 | 83.8 | 76.5 | 69.7 | 81.8 | 68.5 | 55.1 | 76.5 | 62.8 | 50.1
4 | 2.25 | 25 | 75.9 | 61.2 | 50.7 | 84.9 | 75.7 | 55.1 | 90.3 | 81.2 | 68.8 | 96.4 | 91.7 | 83.5 | 96.6 | 95 | 91.8 | 99.3 | 95.4 | 93.1 | 99.9 | 97.4 | 94 | 98.2 | 93.1 | 88.4 | 93.3 | 88.2 | 80.4 | 83.8 | 76.5 | 69.7 | 81.8 | 68.5 | 55.1 | 76.5 | 62.8 | 50.1
4 | 2.75 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 2.75 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 2.75 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 2.75 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 20 | 41.5 | 26.2 | 18.1
4 | 2.75 | 9 | 50.9 | 34.8 | 21.7 | 55.6 | 46.7 | 27.4 | 63.3 | 50.5 | 41.6 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.2 | 34.5 | 50.4 | 41.3 | 29.3 | 51.4 | 34.7 | 23.7
4 | 2.75 | 10 | 58.4 | 41.9 | 29.3 | 64.4 | 56 | 36 | 74.6 | 62.1 | 49.8 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.9 | 50.3 | 35.9 | 59.2 | 42.1 | 31
4 | 2.75 | 11 | 65.7 | 51.2 | 38.5 | 73.3 | 63.4 | 42.3 | 79.3 | 71.4 | 58.6 | 89.5 | 82.5 | 75.7 | 90.5 | 86.6 | 82.1 | 95.3 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 86.6 | 78.5 | 86.6 | 76.3 | 71.3 | 71.8 | 62.6 | 52.6 | 69.2 | 59.9 | 45.6 | 66.1 | 51.3 | 40.4
4 | 2.75 | 12 | 71.8 | 58.6 | 49.5 | 79 | 73.7 | 52.2 | 86.7 | 78.2 | 65 | 93.9 | 86.8 | 82.1 | 95 | 91.4 | 87.8 | 98.3 | 93.6 | 91.4 | 98.2 | 95.7 | 90 | 97.4 | 91.8 | 85.7 | 90.9 | 84.7 | 76.3 | 78.5 | 70 | 59.3 | 77.6 | 67.1 | 50.2 | 72.6 | 57.3 | 49.2
4 | 2.75 | 15 | 85.2 | 73.1 | 62.7 | 90.2 | 83.9 | 70 | 94.3 | 87.8 | 79.2 | 98.8 | 95.4 | 91.1 | 99.6 | 98.4 | 96.3 | 100 | 98.2 | 96.3 | 100 | 98.8 | 96.4 | 100 | 97.4 | 94 | 96.5 | 93.5 | 88.1 | 91.3 | 83.9 | 78.9 | 88.7 | 81.4 | 67.7 | 85.5 | 73 | 63
4 | 2.75 | 20 | 88.9 | 74.6 | 64.3 | 92.3 | 85.8 | 72.1 | 95.8 | 88.7 | 80 | 99 | 96 | 91.8 | 100 | 98.9 | 96.7 | 100 | 98.1 | 96.3 | 100 | 99.1 | 96.4 | 100 | 98 | 95 | 97.4 | 95.3 | 89.7 | 91.7 | 85.9 | 80 | 90.2 | 82.2 | 70.9 | 85.8 | 74.6 | 66.8
4 | 2.75 | 25 | 88.9 | 74.6 | 64.3 | 92.3 | 85.8 | 72.1 | 95.8 | 88.7 | 80 | 99 | 96 | 91.8 | 100 | 98.9 | 96.7 | 100 | 98.1 | 96.3 | 100 | 99.1 | 96.4 | 100 | 98 | 95 | 97.4 | 95.3 | 89.7 | 91.7 | 85.9 | 80 | 90.2 | 82.2 | 70.9 | 85.8 | 74.6 | 66.8
4 | 3 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 3 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 3 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 3 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 19.9 | 41.5 | 26.2 | 18.1
4 | 3 | 9 | 51 | 34.8 | 21.7 | 55.6 | 47.3 | 27.4 | 63.3 | 50.5 | 41.6 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.5 | 34.5 | 50.4 | 41.3 | 29.3 | 51.4 | 35.2 | 23.7
4 | 3 | 10 | 58.6 | 41.9 | 29.3 | 64.4 | 56.5 | 36.2 | 74.6 | 62.1 | 50 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.8 | 51.9 | 36.2 | 59.6 | 42.9 | 31
4 | 3 | 11 | 65.8 | 51.2 | 38.8 | 73.3 | 63.4 | 42.5 | 79.8 | 71.4 | 59 | 89.9 | 82.5 | 76 | 90.5 | 86.6 | 82.1 | 95.3 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 87 | 78.5 | 86.6 | 76.3 | 71.3 | 71.8 | 62.9 | 52.6 | 69.2 | 59.9 | 45.9 | 66.8 | 51.3 | 40.8
4 | 3 | 12 | 72.5 | 60.1 | 50.4 | 79 | 73.7 | 53.1 | 87.8 | 79.3 | 66.1 | 94.3 | 87.1 | 83.1 | 95.4 | 91.4 | 88.1 | 98.3 | 93.6 | 91.5 | 98.2 | 96.1 | 90.4 | 97.4 | 92.1 | 85.7 | 90.9 | 84.7 | 78.3 | 78.5 | 70.6 | 60 | 77.8 | 68.8 | 52 | 73.5 | 58.1 | 49.2
4 | 3 | 15 | 87 | 76.2 | 66.4 | 91.8 | 87.2 | 74.6 | 96.1 | 89.9 | 83.3 | 99 | 96.5 | 92.6 | 99.9 | 98.8 | 97.8 | 100 | 98.6 | 96.7 | 100 | 99.3 | 96.9 | 100 | 98.3 | 95.3 | 97.7 | 94.4 | 90.1 | 92.8 | 86.2 | 81.2 | 90.5 | 84.2 | 72 | 86.9 | 76.7 | 66.6
4 | 3 | 20 | 91.6 | 80.6 | 69 | 95.1 | 90.2 | 78.2 | 97.5 | 92.9 | 85.4 | 100 | 97.5 | 94.1 | 100 | 100 | 98.4 | 100 | 99 | 96.8 | 100 | 100 | 98.2 | 100 | 99.1 | 96.8 | 98.6 | 96.5 | 91.3 | 94.4 | 89.5 | 84.5 | 92.6 | 86.9 | 76.8 | 89.9 | 81 | 73.6
4 | 3 | 25 | 91.6 | 80.6 | 69 | 95.1 | 90.2 | 78.2 | 97.5 | 92.9 | 85.4 | 100 | 97.5 | 94.1 | 100 | 100 | 98.4 | 100 | 99 | 96.8 | 100 | 100 | 98.2 | 100 | 99.1 | 96.8 | 98.6 | 96.5 | 91.3 | 94.4 | 89.5 | 84.5 | 92.6 | 86.9 | 76.8 | 89.9 | 81 | 73.6
4 | 3.5 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 3.5 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 3.5 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 3.5 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 19.9 | 41.5 | 26.2 | 18.1
4 | 3.5 | 9 | 51 | 34.8 | 21.7 | 55.6 | 47.3 | 27.4 | 63.3 | 50.5 | 41.7 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.5 | 34.5 | 50.4 | 41.3 | 29.4 | 51.4 | 35.2 | 23.8
4 | 3.5 | 10 | 58.9 | 41.9 | 29.9 | 64.4 | 56.5 | 36.4 | 74.6 | 62.1 | 50.5 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.8 | 51.9 | 36.3 | 59.6 | 42.9 | 31.2
4 | 3.5 | 11 | 65.8 | 51.2 | 39.2 | 73.3 | 63.4 | 42.6 | 79.8 | 71.4 | 59.5 | 89.9 | 82.5 | 76.3 | 90.5 | 86.6 | 82.1 | 95.7 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 87 | 78.5 | 86.6 | 76.3 | 71.4 | 71.8 | 62.9 | 53 | 69.2 | 59.9 | 45.9 | 67.2 | 51.9 | 41
4 | 3.5 | 12 | 72.5 | 60.1 | 50.8 | 79.8 | 73.7 | 53.7 | 87.8 | 79.7 | 67.5 | 94.3 | 87.9 | 83.5 | 95.4 | 91.4 | 88.1 | 98.3 | 94.2 | 91.5 | 98.2 | 96.1 | 90.4 | 97.4 | 92.1 | 85.7 | 91.1 | 85.3 | 79.6 | 78.5 | 70.6 | 60 | 77.9 | 69.3 | 53.8 | 74.4 | 59.1 | 49.4
4 | 3.5 | 15 | 88.4 | 79.8 | 72 | 93.3 | 89.3 | 78.4 | 96.4 | 91.3 | 85.8 | 99.4 | 97.8 | 94 | 100 | 99.2 | 98.2 | 100 | 98.8 | 97.1 | 100 | 100 | 98 | 100 | 98.5 | 96.2 | 98.7 | 95 | 91.6 | 93.4 | 87.9 | 82.9 | 93.1 | 85.3 | 76.2 | 88.5 | 78.9 | 69.1
4 | 3.5 | 20 | 95.4 | 90.3 | 82.7 | 98.5 | 93.9 | 87.5 | 99.8 | 97 | 92.9 | 100 | 100 | 96.8 | 100 | 100 | 100 | 100 | 100 | 98.4 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.2 | 95.5 | 98.6 | 94.9 | 91.2 | 97 | 92.6 | 87.1 | 96.1 | 90.1 | 83.2
4 | 3.5 | 25 | 95.5 | 90.7 | 82.7 | 98.8 | 93.9 | 87.5 | 99.8 | 97 | 92.9 | 100 | 100 | 96.8 | 100 | 100 | 100 | 100 | 100 | 98.4 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.2 | 95.5 | 98.6 | 94.9 | 91.2 | 97.2 | 92.6 | 87.1 | 96.1 | 90.1 | 83.5
4 | 4 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 4 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 4 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 4 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 19.9 | 41.5 | 26.2 | 18.1
4 | 4 | 9 | 51 | 34.8 | 21.7 | 55.6 | 47.3 | 27.4 | 63.3 | 50.5 | 41.7 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.5 | 34.5 | 50.4 | 41.3 | 29.4 | 51.4 | 35.2 | 23.8
4 | 4 | 10 | 58.9 | 41.9 | 29.9 | 64.4 | 56.5 | 36.4 | 74.6 | 62.1 | 50.5 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.8 | 51.9 | 36.3 | 59.6 | 42.9 | 31.2
4 | 4 | 11 | 66 | 51.2 | 39.2 | 73.3 | 63.4 | 42.6 | 79.8 | 71.4 | 59.6 | 89.9 | 82.5 | 76.3 | 90.5 | 86.6 | 82.1 | 95.7 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 87 | 78.5 | 86.6 | 76.3 | 71.4 | 71.8 | 62.9 | 53 | 69.2 | 59.9 | 45.9 | 67.2 | 51.9 | 41
4 | 4 | 12 | 72.7 | 60.1 | 50.8 | 79.8 | 73.7 | 53.9 | 87.8 | 79.7 | 67.5 | 94.3 | 87.9 | 83.5 | 95.4 | 91.4 | 88.1 | 98.3 | 94.2 | 91.5 | 98.2 | 96.1 | 90.4 | 97.4 | 92.1 | 85.7 | 91.1 | 85.3 | 79.6 | 78.5 | 70.6 | 60.3 | 78.1 | 69.3 | 54.3 | 74.4 | 59.1 | 49.4
4 | 4 | 15 | 89.5 | 80.4 | 73.2 | 93.9 | 89.9 | 79.7 | 96.4 | 92.2 | 86.4 | 99.4 | 98.1 | 94.4 | 100 | 99.3 | 98.2 | 100 | 98.9 | 97.6 | 100 | 100 | 98.2 | 100 | 98.7 | 96.5 | 98.7 | 95.6 | 92.2 | 93.5 | 88.7 | 84 | 93.9 | 86.1 | 78 | 90 | 81.2 | 70.1
4 | 4 | 20 | 98.5 | 95.4 | 90 | 99.4 | 97.5 | 92.2 | 100 | 99.2 | 96.5 | 100 | 100 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.7 | 97.4 | 100 | 97.8 | 95.1 | 99.3 | 96.8 | 93.5 | 99.1 | 94.9 | 90.4
4 | 4 | 25 | 98.5 | 95.7 | 90.2 | 99.8 | 97.3 | 92.5 | 100 | 99.3 | 96.8 | 100 | 100 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.4 | 100 | 98.1 | 95.2 | 99.3 | 96.9 | 94.2 | 99.3 | 95.2 | 91.4
4 | 4.5 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 4.5 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 4.5 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 4.5 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 19.9 | 41.5 | 26.2 | 18.1
4 | 4.5 | 9 | 51 | 34.8 | 21.7 | 55.6 | 47.3 | 27.4 | 63.3 | 50.5 | 41.7 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.5 | 34.5 | 50.4 | 41.3 | 29.4 | 51.4 | 35.2 | 23.8
4 | 4.5 | 10 | 58.9 | 41.9 | 29.9 | 64.4 | 56.5 | 36.4 | 74.6 | 62.1 | 50.5 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.8 | 51.9 | 36.3 | 59.6 | 42.9 | 31.2
4 | 4.5 | 11 | 66 | 51.2 | 39.2 | 73.3 | 63.4 | 42.6 | 79.8 | 71.4 | 59.6 | 89.9 | 82.5 | 76.3 | 90.5 | 86.6 | 82.1 | 95.7 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 87 | 78.5 | 86.6 | 76.3 | 71.4 | 71.8 | 62.9 | 53 | 69.2 | 59.9 | 45.9 | 67.2 | 51.9 | 41
4 | 4.5 | 12 | 72.7 | 60.1 | 50.8 | 79.8 | 73.7 | 53.9 | 87.8 | 79.7 | 67.5 | 94.3 | 87.9 | 83.5 | 95.4 | 91.4 | 88.1 | 98.3 | 94.2 | 91.5 | 98.2 | 96.1 | 90.4 | 97.4 | 92.1 | 85.7 | 91.1 | 85.3 | 79.6 | 78.5 | 70.6 | 60.3 | 78.1 | 69.3 | 54.3 | 74.4 | 59.1 | 49.4
4 | 4.5 | 15 | 89.9 | 80.4 | 73.2 | 93.9 | 89.9 | 79.7 | 96.4 | 92.2 | 86.8 | 99.4 | 98.3 | 94.8 | 100 | 99.3 | 98.2 | 100 | 98.9 | 97.8 | 100 | 100 | 98.2 | 100 | 98.7 | 96.5 | 98.7 | 95.7 | 92.2 | 93.7 | 88.7 | 84.2 | 94 | 86.7 | 78.6 | 90.5 | 82 | 70.5
4 | 4.5 | 20 | 99.8 | 97.3 | 93 | 100 | 98.5 | 94.4 | 100 | 100 | 98.3 | 100 | 100 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.4 | 100 | 98.8 | 96.5 | 100 | 98.3 | 96 | 100 | 97.6 | 93.9
4 | 4.5 | 25 | 100 | 98 | 94.8 | 100 | 99 | 95.1 | 100 | 100 | 98.8 | 100 | 100 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.2 | 100 | 99.6 | 97.8 | 100 | 98.9 | 97.1 | 100 | 98.8 | 95.7
4 | 5 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 5 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 5 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 5 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 19.9 | 41.5 | 26.2 | 18.1
4 | 5 | 9 | 51 | 34.8 | 21.7 | 55.6 | 47.3 | 27.4 | 63.3 | 50.5 | 41.7 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.5 | 34.5 | 50.4 | 41.3 | 29.4 | 51.4 | 35.2 | 23.8
4 | 5 | 10 | 58.9 | 41.9 | 29.9 | 64.4 | 56.5 | 36.4 | 74.6 | 62.1 | 50.5 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.8 | 51.9 | 36.3 | 59.6 | 42.9 | 31.2
4 | 5 | 11 | 66 | 51.2 | 39.2 | 73.3 | 63.4 | 42.6 | 79.8 | 71.4 | 59.6 | 89.9 | 82.5 | 76.3 | 90.5 | 86.6 | 82.1 | 95.7 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 87 | 78.5 | 86.6 | 76.3 | 71.4 | 71.8 | 62.9 | 53 | 69.2 | 59.9 | 45.9 | 67.2 | 51.9 | 41
4 | 5 | 12 | 72.7 | 60.1 | 50.8 | 79.8 | 73.7 | 53.9 | 87.8 | 79.7 | 67.5 | 94.3 | 87.9 | 83.5 | 95.4 | 91.4 | 88.1 | 98.3 | 94.2 | 91.5 | 98.2 | 96.1 | 90.4 | 97.4 | 92.1 | 85.7 | 91.1 | 85.3 | 79.6 | 78.5 | 70.6 | 60.3 | 78.1 | 69.3 | 54.3 | 74.4 | 59.1 | 49.4
4 | 5 | 15 | 89.9 | 80.4 | 73.2 | 93.9 | 90.3 | 79.7 | 96.4 | 92.2 | 86.8 | 99.4 | 98.3 | 94.8 | 100 | 99.3 | 98.2 | 100 | 98.9 | 97.8 | 100 | 100 | 98.2 | 100 | 98.7 | 96.5 | 98.7 | 95.7 | 92.2 | 93.7 | 88.7 | 84.6 | 94 | 86.9 | 78.6 | 90.5 | 82 | 70.5
4 | 5 | 20 | 100 | 97.4 | 94.1 | 100 | 99 | 95.4 | 100 | 100 | 98.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.2 | 100 | 99.5 | 97.7 | 100 | 98.8 | 96.8 | 100 | 98.4 | 94.4
4 | 5 | 25 | 100 | 99.5 | 97.6 | 100 | 100 | 97.3 | 100 | 100 | 99.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.1 | 100 | 100 | 98.3 | 100 | 100 | 98.1
6 | 0.25 | 2 | [12 empty] | 0.8 |  |  | 0.8 | [5 empty] | 0.7
6 | 0.25 | 4 | [9 empty] | 1.2 |  |  | 2.8 |  |  | 3.2 | 0.8 |  | 2.3 | 0.7 |  | 3.7 | 0.7 |  | 0.7
6 | 0.25 | 6 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 5.8 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 8 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 9 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 10 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 11 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 12 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 15 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 20 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 25 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.5 | 2 | [6 empty] | 0.5 |  |  | 1.5 |  |  | 1.5 | 0.7 |  | 2.8 | 0.7 |  | 2.2 | 0.7 |  | 2.2 | 0.7 |  | 1.4
6 | 0.5 | 4 | 0.7 |  |  | 2.5 | 1.6 |  | 4.2 | 0.8 |  | 7.1 | 3.8 | 1 | 8.8 | 3.5 | 0.7 | 11 | 6.9 | 2.2 | 11.4 | 6 | 3.8 | 12.2 | 6.9 | 3.9 | 7.1 | 3.8 | 1.4 | 2.8 | 1.3 |  | 1.5 |  |  | 2.2 | 0.5
6 | 0.5 | 6 | 4 |  |  | 5.3 | 2.4 |  | 7.4 | 2.2 |  | 13.6 | 6.4 | 3.7 | 14.6 | 9.1 | 4.5 | 19.8 | 13.8 | 5 | 23.8 | 15.6 | 7.2 | 21.3 | 14.2 | 7.5 | 14.2 | 6.9 | 2 | 4.8 | 1.5 |  | 2.4 |  |  | 3.1 | 1.3
6 | 0.5 | 8 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 18.8 | 10.8 | 5.7 | 23.2 | 14.6 | 6.2 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 9 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 10 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 11 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 12 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 15 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 20 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 25 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.75 | 2 |  |  |  | 0.9 |  |  | 0.8 |  |  | 1.5 | 0.8 |  | 2.2 | 0.7 |  | 3.1 | 1.4 |  | 2.8 | 1.3 |  | 2.2 | 0.8 | 0.7 | 1.5 | 0.8 |  | 0.7 |  |  | 0.5 |  |  | 0.8
6 | 0.75 | 4 | 2.7 | 0.7 |  | 5.9 | 3.3 |  | 7.7 | 3 | 1 | 12.3 | 6 | 3.9 | 12.2 | 6.6 | 2.8 | 15.5 | 11.5 | 6.7 | 14.7 | 9.9 | 6.7 | 16.4 | 10.1 | 5.2 | 12.4 | 7.2 | 4 | 4.4 | 2.3 | 0.2 | 3.1 | 1.9 |  | 4.3 | 1.5 | 0.2
6 | 0.75 | 6 | 9.7 | 3.8 | 0.2 | 13.1 | 7.4 | 1.6 | 18.3 | 6.9 | 4.9 | 27.2 | 15 | 10.5 | 27.3 | 18 | 13.2 | 34.7 | 24 | 13.6 | 34.4 | 25.1 | 19.1 | 35.7 | 22.6 | 14.6 | 24 | 17.9 | 9.8 | 12.8 | 5.8 | 2.9 | 8.9 | 4 | 1 | 10.7 | 5.1 | 1.3
6 | 0.75 | 8 | 15.7 | 5.2 | 0.2 | 16.7 | 10.3 | 2.5 | 25.2 | 11.4 | 7.5 | 33.1 | 20.8 | 13.6 | 35.1 | 27.3 | 18.8 | 42.6 | 33.3 | 20.9 | 48.1 | 36.2 | 27.2 | 44.2 | 35.5 | 24.9 | 32.7 | 24.2 | 12.4 | 15.9 | 8.6 | 4.8 | 11.5 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 9 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.1 | 7.6 | 33.1 | 21.7 | 13.6 | 37 | 28.4 | 20.7 | 44.9 | 34.6 | 22.3 | 49.5 | 38.4 | 29.3 | 45.6 | 37 | 25.6 | 33.5 | 24.2 | 12.4 | 15.9 | 9.1 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 10 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.2 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.1 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 11 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.3 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.3 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 12 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.3 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.3 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 15 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.3 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.3 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 20 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.3 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.3 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 25 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.3 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.3 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 1 | 2 | 0.8 |  |  | 1.6 |  |  | 1.5 |  |  | 2 | 0.8 | 0.7 | 2.2 | 0.8 |  | 3 | 1.4 | 0.7 | 3 | 1.7 |  | 2.7 | 0.8 | 0.7 | 2.2 | 1.4 |  | 0.8 |  |  | 0.8 |  |  | 0.8
6 | 1 | 4 | 4.5 | 1.5 |  | 8.6 | 3.9 | 1.6 | 9.8 | 4.4 | 1.5 | 13.4 | 8.2 | 5.9 | 13 | 8.9 | 5.1 | 18.2 | 13.9 | 8.4 | 17.7 | 12.1 | 7.9 | 17.5 | 12 | 7.5 | 13 | 8.8 | 5.3 | 6.8 | 3.6 | 2.2 | 5.2 | 2.4 | 0.7 | 4.3 | 2.8 | 0.7
6 | 1 | 6 | 14.3 | 7 | 1.6 | 18.1 | 10.9 | 4.2 | 24.3 | 14.1 | 7.2 | 31.1 | 21.1 | 15.8 | 31.5 | 23.8 | 17.2 | 40.5 | 31.7 | 22.3 | 41.1 | 32.3 | 23.7 | 40.1 | 28.6 | 22.3 | 30.7 | 24.7 | 14.4 | 18.9 | 9.7 | 5.5 | 12.9 | 7.2 | 4.9 | 15.5 | 7.7 | 2.9
6 | 1 | 8 | 24.9 | 12.1 | 3 | 27.8 | 17.7 | 9.7 | 35.6 | 23 | 14.3 | 49.7 | 33.9 | 27 | 48.6 | 42.7 | 32.5 | 59.1 | 48.3 | 39.5 | 62 | 51.5 | 37.2 | 58.6 | 48.8 | 39.1 | 45.2 | 37.6 | 27.7 | 27.8 | 16.7 | 9.2 | 22.2 | 13.5 | 6.7 | 23.4 | 10.9 | 5.1
6 | 1 | 9 | 25.7 | 13.3 | 3 | 28.7 | 20.4 | 10.1 | 37.4 | 24.7 | 15.5 | 54 | 38.9 | 28.7 | 55 | 45.4 | 33.9 | 62.9 | 52.8 | 43.2 | 69.1 | 56.9 | 42.9 | 63.8 | 50.8 | 42.7 | 49.8 | 40.3 | 28.9 | 29.6 | 19.4 | 10.4 | 24 | 14.7 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 10 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 26.2 | 16.8 | 54.5 | 38.8 | 29 | 56.9 | 46.9 | 36.1 | 64.3 | 54 | 45.1 | 70.3 | 58.2 | 44.6 | 65.3 | 52.4 | 44.1 | 50.4 | 41.9 | 29.8 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 11 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 27 | 16.7 | 54.5 | 38.8 | 29 | 56.9 | 47.6 | 36.4 | 64.4 | 54.3 | 45.1 | 70.5 | 59 | 45.7 | 65.6 | 52.4 | 44.6 | 50.4 | 41.9 | 29.9 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 12 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 27 | 16.7 | 54.5 | 38.8 | 29 | 56.9 | 47.6 | 36.4 | 64.4 | 54.3 | 45.1 | 70.6 | 59 | 45.9 | 65.6 | 52.4 | 44.6 | 50.4 | 41.9 | 29.9 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 15 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 27 | 16.7 | 54.5 | 38.8 | 29 | 56.9 | 47.6 | 36.4 | 64.4 | 54.3 | 45.1 | 70.6 | 59 | 45.9 | 65.6 | 52.4 | 44.6 | 50.4 | 41.9 | 29.9 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 20 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 27 | 16.7 | 54.5 | 38.8 | 29 | 56.9 | 47.6 | 36.4 | 64.4 | 54.3 | 45.1 | 70.6 | 59 | 45.9 | 65.6 | 52.4 | 44.6 | 50.4 | 41.9 | 29.9 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 25 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 27 | 16.7 | 54.5 | 38.8 | 29 | 56.9 | 47.6 | 36.4 | 64.4 | 54.3 | 45.1 | 70.6 | 59 | 45.9 | 65.6 | 52.4 | 44.6 | 50.4 | 41.9 | 29.9 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1.25 | 2 | 0.8 |  |  | 1.6 |  |  | 1.5 |  |  | 2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.3 | 0.7 | 2.2 | 1.4 |  | 1.2 |  |  | 0.8 |  |  | 1.3
6 | 1.25 | 4 | 5.7 | 2 | 0.7 | 9.6 | 5.5 | 2.4 | 11.2 | 5.9 | 2.2 | 14.8 | 9.2 | 6.6 | 13.9 | 9.8 | 6 | 18.4 | 15.4 | 8.6 | 18.4 | 12.8 | 7.9 | 19 | 13 | 8 | 14.6 | 9.3 | 5.4 | 8.3 | 4.3 | 2.2 | 6.2 | 3.1 | 1.5 | 6.1 | 3 | 0.7
6 | 1.25 | 6 | 19.2 | 7.7 | 3.9 | 22 | 13.4 | 5.3 | 25.5 | 16.5 | 9.8 | 33.6 | 23.6 | 18.4 | 34.3 | 26.6 | 21.6 | 45.3 | 35.7 | 26.3 | 43.4 | 34.4 | 25.2 | 41.2 | 30.4 | 24 | 33 | 27.4 | 16.5 | 20.8 | 12.8 | 8.2 | 17.3 | 10.3 | 6.4 | 18.7 | 9.8 | 3.8
6 | 1.25 | 8 | 32 | 18.5 | 7.9 | 33 | 26.3 | 11.6 | 44.1 | 31 | 19.9 | 55.1 | 42.5 | 35.5 | 55.5 | 49.5 | 40.9 | 68.6 | 57.4 | 45.9 | 68 | 59.4 | 45.4 | 65 | 55.2 | 46.2 | 53.4 | 43.3 | 34.6 | 34.8 | 23.3 | 16.7 | 30.1 | 20 | 11.4 | 32.8 | 17.3 | 9.8
6 | 1.25 | 9 | 34.6 | 21.8 | 9.5 | 40.1 | 28.9 | 13.5 | 48 | 37.9 | 24.2 | 62.4 | 49 | 41.6 | 65.3 | 57 | 49.4 | 75.4 | 64.3 | 54.4 | 75.4 | 68.4 | 53.7 | 72.7 | 64 | 52.5 | 60.4 | 49.7 | 38 | 41.1 | 29.3 | 20.2 | 35.2 | 24.2 | 14.3 | 34.6 | 20.6 | 12.2
6 | 1.25 | 10 | 37 | 22 | 10.5 | 43 | 31.3 | 15 | 51.7 | 41.4 | 25.9 | 68.2 | 53.2 | 43.8 | 71.2 | 61.2 | 53.7 | 78.2 | 69.7 | 58.3 | 81.3 | 74.2 | 58.4 | 76.1 | 67.6 | 56.5 | 64.3 | 54.3 | 40 | 43.4 | 32.9 | 21.6 | 37.3 | 26.1 | 14.4 | 35.6 | 21.2 | 14.2
6 | 1.25 | 11 | 37.6 | 23.5 | 10.5 | 43.6 | 31.3 | 16 | 51.6 | 42.1 | 25.9 | 70.4 | 55.6 | 44.6 | 73 | 63.8 | 56.3 | 79.3 | 71.5 | 59.7 | 82.9 | 75.7 | 59.3 | 76.6 | 68.8 | 58.5 | 64.9 | 56.3 | 41.4 | 43.6 | 33.5 | 22.3 | 37.8 | 26.1 | 14.3 | 35.6 | 21.1 | 14.7
6 | 1.25 | 12 | 37.6 | 23.5 | 10.5 | 43.6 | 31.3 | 16 | 52.7 | 42.3 | 25.9 | 70.4 | 55.6 | 44.8 | 73 | 63.8 | 56.5 | 79.4 | 71.5 | 59.9 | 82.9 | 75.7 | 59.7 | 77.1 | 69.6 | 58.9 | 64.9 | 56.3 | 41.4 | 43.6 | 33.5 | 22.3 | 38.1 | 26.1 | 14.3 | 35.6 | 21.1 | 14.7
6 | 1.25 | 15 | 37.6 | 23.5 | 10.5 | 43.6 | 31.3 | 16 | 52.7 | 42.3 | 25.9 | 70.4 | 55.6 | 44.8 | 72.9 | 63.8 | 56.5 | 79.4 | 71.5 | 59.9 | 82.9 | 75.7 | 60.1 | 77.1 | 69.6 | 58.9 | 64.9 | 56.3 | 41.4 | 43.6 | 33.5 | 22.3 | 38.1 | 26.1 | 14.3 | 35.6 | 21.1 | 14.7
6 | 1.25 | 20 | 37.6 | 23.5 | 10.5 | 43.6 | 31.3 | 16 | 52.7 | 42.3 | 25.9 | 70.4 | 55.6 | 44.8 | 72.9 | 63.8 | 56.5 | 79.4 | 71.5 | 59.9 | 82.9 | 75.7 | 60.1 | 77.1 | 69.6 | 58.9 | 64.9 | 56.3 | 41.4 | 43.6 | 33.5 | 22.3 | 38.1 | 26.1 | 14.3 | 35.6 | 21.1 | 14.7
6 | 1.25 | 25 | 37.6 | 23.5 | 10.5 | 43.6 | 31.3 | 16 | 52.7 | 42.3 | 25.9 | 70.4 | 55.6 | 44.8 | 72.9 | 63.8 | 56.5 | 79.4 | 71.5 | 59.9 | 82.9 | 75.7 | 60.1 | 77.1 | 69.6 | 58.9 | 64.9 | 56.3 | 41.4 | 43.6 | 33.5 | 22.3 | 38.1 | 26.1 | 14.3 | 35.6 | 21.1 | 14.7
6 | 1.5 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 |  |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.3 | 0.7 | 2.2 | 1.4 |  | 1.2 |  |  | 0.8 |  |  | 1.5
6 | 1.5 | 4 | 7.2 | 2.3 | 1.3 | 10.4 | 5.5 | 2.4 | 12 | 6.5 | 2.6 | 14.9 | 9.7 | 7.4 | 14.4 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8 | 19.3 | 13 | 8 | 15.1 | 9.6 | 5.8 | 8.8 | 4.4 | 2.5 | 6.3 | 3.2 | 1.5 | 7.9 | 3 | 1.3
6 | 1.5 | 6 | 21.3 | 9 | 5.1 | 23.2 | 13.4 | 6.7 | 26.7 | 18.1 | 10.6 | 35.2 | 25.1 | 20.4 | 35.2 | 27.7 | 22.4 | 45.8 | 35.7 | 27.6 | 45 | 34.8 | 25.8 | 42.7 | 31.7 | 25.1 | 33.3 | 27.8 | 16.6 | 22.1 | 15.7 | 9.1 | 18.1 | 13.3 | 7.9 | 19.9 | 11.8 | 4.7
6 | 1.5 | 8 | 35 | 21.5 | 11.4 | 39.6 | 29.8 | 15.1 | 45.4 | 33.9 | 23.7 | 59.9 | 46.3 | 40.9 | 59.8 | 52.4 | 44 | 71.3 | 60 | 49.9 | 70 | 61.4 | 50.4 | 66 | 58.6 | 47.5 | 56.2 | 45.8 | 37.9 | 39.5 | 27.6 | 20.3 | 34 | 24.9 | 15.7 | 35.9 | 20.6 | 12.6
6 | 1.5 | 9 | 40.9 | 28.6 | 14.9 | 46.8 | 37.5 | 19.9 | 56.7 | 44.4 | 32.7 | 67.2 | 54.9 | 49.8 | 70 | 62.2 | 53.4 | 79.5 | 70.8 | 61.9 | 77.9 | 73.5 | 61.2 | 76.8 | 66.7 | 56.6 | 64.7 | 56.7 | 46 | 46 | 35.1 | 25.7 | 42.3 | 31.7 | 19.3 | 40.8 | 25.3 | 17.1
6 | 1.5 | 10 | 45.3 | 31.2 | 17.2 | 55.5 | 40.9 | 23.9 | 62.7 | 50.3 | 38.8 | 74.3 | 61.4 | 54.5 | 78.1 | 69.2 | 62.4 | 84.9 | 79.6 | 69.1 | 85.9 | 81 | 70.2 | 83.6 | 73.7 | 63.8 | 71.4 | 61.4 | 50.7 | 52.9 | 39.8 | 31.9 | 48.9 | 36.3 | 23.2 | 44.9 | 29.8 | 20.1
6 | 1.5 | 11 | 46.4 | 32.5 | 18.8 | 57.7 | 44.5 | 24.2 | 67.1 | 52.3 | 40.8 | 78.1 | 66.7 | 57.5 | 82.2 | 74.5 | 67 | 87.9 | 81.9 | 71.4 | 90.3 | 84.8 | 73.2 | 85.8 | 78.5 | 68.1 | 74.7 | 65.7 | 54.1 | 56.5 | 45.4 | 33.6 | 52.5 | 36.9 | 23.9 | 47.4 | 31.2 | 21.5
6 | 1.5 | 12 | 46.8 | 33.3 | 19 | 58.2 | 45.5 | 24.3 | 67.8 | 52.3 | 41 | 79.1 | 67.6 | 58.5 | 82.4 | 76.2 | 68.9 | 88.7 | 82.1 | 73.2 | 91.8 | 85.5 | 73.4 | 86.6 | 78.5 | 69.4 | 75.7 | 66.5 | 54 | 57.5 | 46.6 | 34.3 | 52.8 | 37.1 | 24.3 | 48.5 | 31.6 | 22.3
6 | 1.5 | 15 | 47 | 34.1 | 19.1 | 58.3 | 45.5 | 24.3 | 67.8 | 52.7 | 41.5 | 79.8 | 67.6 | 58.6 | 82.4 | 76.7 | 68.9 | 88.7 | 82.2 | 73.2 | 92 | 85.6 | 73.4 | 86.8 | 78.5 | 70.2 | 75.6 | 67.4 | 54 | 58.3 | 46.5 | 34.3 | 52.7 | 37.1 | 24.5 | 48.4 | 32.8 | 22.3
6 | 1.5 | 20 | 47 | 34.1 | 19.1 | 58.3 | 45.5 | 24.3 | 67.8 | 52.7 | 41.5 | 79.8 | 67.6 | 58.6 | 82.4 | 76.7 | 68.9 | 88.7 | 82.2 | 73.2 | 92 | 85.6 | 73.4 | 86.8 | 78.5 | 70.2 | 75.6 | 67.4 | 54 | 58.3 | 46.5 | 34.3 | 52.7 | 37.1 | 24.5 | 48.4 | 32.8 | 22.3
6 | 1.5 | 25 | 47 | 34.1 | 19.1 | 58.3 | 45.5 | 24.3 | 67.8 | 52.7 | 41.5 | 79.8 | 67.6 | 58.6 | 82.4 | 76.7 | 68.9 | 88.7 | 82.2 | 73.2 | 92 | 85.6 | 73.4 | 86.8 | 78.5 | 70.2 | 75.6 | 67.4 | 54 | 58.3 | 46.5 | 34.3 | 52.7 | 37.1 | 24.5 | 48.4 | 32.8 | 22.3
6 | 1.75 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 1.75 | 4 | 7.2 | 2.3 | 1.4 | 10.6 | 5.8 | 2.4 | 12.4 | 6.6 | 3.2 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.3 | 9 | 4.6 | 3.5 | 7 | 3.8 | 1.7 | 8.3 | 3.6 | 1.4
6 | 1.75 | 6 | 21.8 | 10.6 | 5.7 | 23.5 | 14.9 | 8.5 | 27 | 19 | 12.7 | 36.2 | 27.1 | 21.8 | 35.2 | 28.9 | 23 | 45.8 | 37.1 | 27.6 | 45 | 34.8 | 25.8 | 43 | 32.5 | 25.2 | 33.8 | 28.8 | 17.4 | 22.5 | 17.2 | 9.4 | 18.8 | 14 | 8.8 | 20.4 | 13.3 | 5.1
6 | 1.75 | 8 | 37.1 | 24.2 | 13.9 | 41.3 | 32.1 | 18.8 | 47.4 | 37.2 | 27.4 | 60.9 | 48.3 | 42.3 | 60.6 | 53.2 | 45.4 | 71.3 | 61.8 | 52.5 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 47.7 | 58.4 | 47.4 | 38.9 | 42.1 | 30.1 | 22.3 | 37.2 | 26.5 | 16.5 | 36.2 | 23.4 | 13.6
6 | 1.75 | 9 | 46.3 | 32.5 | 17.4 | 52.3 | 40 | 23.8 | 59.9 | 46.2 | 36.6 | 69.4 | 59 | 54.1 | 72 | 64.5 | 55.4 | 82.6 | 72.6 | 64.2 | 80 | 74.7 | 63.4 | 77.4 | 68.3 | 57.9 | 68.5 | 58.1 | 49.7 | 49.8 | 37.4 | 30.1 | 45.8 | 33.5 | 23.6 | 43.4 | 28.5 | 18.7
6 | 1.75 | 10 | 51.2 | 35.9 | 23.2 | 60.2 | 48.4 | 29.5 | 70.1 | 55.2 | 42.7 | 78.7 | 67.6 | 61.1 | 81.7 | 73 | 66.4 | 87.8 | 82.1 | 73.6 | 87.9 | 82.9 | 74 | 86.8 | 75.7 | 67.6 | 73.6 | 65.6 | 56.7 | 55.5 | 45.3 | 35.8 | 52.6 | 41 | 29.5 | 51.3 | 35.3 | 23.7
6 | 1.75 | 11 | 55.3 | 41.7 | 29.5 | 65.9 | 54 | 31.2 | 75.3 | 61.2 | 47.9 | 86.3 | 74.3 | 66.4 | 86.3 | 79.2 | 74.2 | 92.2 | 87.6 | 78 | 94.4 | 87.9 | 79.7 | 90 | 82.1 | 73.5 | 79.3 | 71.3 | 62.5 | 65.2 | 53.8 | 42.3 | 58.1 | 46 | 33.2 | 56.5 | 39.8 | 28.6
6 | 1.75 | 12 | 56.9 | 42.5 | 32.9 | 67.6 | 57.1 | 34.2 | 78.1 | 64.7 | 51 | 86.4 | 76.3 | 67.8 | 89.4 | 84 | 77.8 | 93.8 | 88.3 | 81.2 | 95.6 | 89.2 | 81.2 | 92.2 | 84.1 | 76.4 | 81.4 | 74.2 | 64.7 | 71 | 56.6 | 46.1 | 61.5 | 47.9 | 34 | 58.8 | 39.7 | 29.6
6 | 1.75 | 15 | 57.6 | 42.5 | 33.8 | 68.8 | 58 | 34.6 | 78.3 | 65.6 | 53.1 | 86.9 | 76.7 | 68.4 | 89.9 | 85.8 | 79.7 | 94 | 88.3 | 82.3 | 95.8 | 90.2 | 81.8 | 92.2 | 84.1 | 77.6 | 83 | 74.6 | 65.3 | 73.4 | 57.5 | 47.8 | 62.8 | 47.8 | 36 | 59.2 | 41.1 | 29.6
6 | 1.75 | 20 | 57.8 | 42.5 | 33.8 | 68.8 | 58 | 34.6 | 78.3 | 65.6 | 53.1 | 86.9 | 76.7 | 68.4 | 89.9 | 85.8 | 79.7 | 94 | 88.3 | 82.3 | 95.8 | 90.2 | 81.8 | 92.2 | 84.1 | 77.6 | 83 | 74.6 | 65.3 | 73.4 | 57.5 | 47.8 | 62.8 | 47.8 | 36 | 59.2 | 41.1 | 29.6
6 | 1.75 | 25 | 57.8 | 42.5 | 33.8 | 68.8 | 58 | 34.6 | 78.3 | 65.6 | 53.1 | 86.9 | 76.7 | 68.4 | 89.9 | 85.8 | 79.7 | 94 | 88.3 | 82.3 | 95.8 | 90.2 | 81.8 | 92.2 | 84.1 | 77.6 | 83 | 74.6 | 65.3 | 73.4 | 57.5 | 47.8 | 62.8 | 47.8 | 36 | 59.2 | 41.1 | 29.6
6 | 2 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 2 | 4 | 7.2 | 2.3 | 1.4 | 10.9 | 5.8 | 2.4 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.4 | 9.2 | 5 | 3.5 | 7 | 4.3 | 1.7 | 8.8 | 3.8 | 1.4
6 | 2 | 6 | 21.8 | 10.6 | 6.1 | 24 | 15 | 9 | 27 | 19.2 | 12.7 | 36.2 | 27.2 | 22.6 | 35.2 | 29 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 34.8 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.7 | 9.9 | 18.8 | 14 | 9.4 | 21.3 | 13.8 | 5.3
6 | 2 | 8 | 38.1 | 25 | 15.3 | 43.1 | 33 | 19.8 | 49 | 38.3 | 28.7 | 60.9 | 50.7 | 43.8 | 60.8 | 53.5 | 45.4 | 71.3 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.4 | 48.1 | 39.2 | 42.6 | 30.9 | 23.2 | 37.8 | 28.1 | 17.3 | 37.8 | 24.2 | 14.9
6 | 2 | 9 | 49.4 | 32.7 | 19.2 | 54.2 | 41.5 | 24.7 | 60.5 | 47.3 | 38.9 | 70.4 | 60.8 | 55.4 | 72.7 | 64.9 | 56.4 | 83.4 | 73.5 | 65.4 | 80.2 | 75 | 64.8 | 79.1 | 69.4 | 58.8 | 69.6 | 60.3 | 50.9 | 50.9 | 37.4 | 31 | 48.1 | 36.5 | 25.3 | 46 | 31.5 | 20.6
6 | 2 | 10 | 54.8 | 39 | 26.5 | 61.7 | 52.5 | 29.9 | 70.8 | 58.7 | 45.7 | 79.9 | 71.3 | 64.2 | 81.9 | 75.5 | 68.5 | 89.5 | 83.6 | 76.9 | 88.5 | 83.9 | 76.1 | 87.5 | 77.6 | 68.6 | 77.8 | 66.4 | 59.2 | 58 | 49.3 | 39.7 | 55.6 | 44.2 | 32.7 | 54.9 | 37.8 | 27.2
6 | 2 | 11 | 59.7 | 43.5 | 34.4 | 70.1 | 60 | 34.1 | 76.9 | 66.1 | 52.9 | 87.5 | 76.8 | 69 | 88.2 | 82.4 | 78.2 | 94.3 | 89.2 | 82 | 95.7 | 89.9 | 82.2 | 92.1 | 83.7 | 75.4 | 82.3 | 74.2 | 65.4 | 67.4 | 57.8 | 46.9 | 63.5 | 51.3 | 38.1 | 60.1 | 43.4 | 33.3
6 | 2 | 12 | 64.3 | 48.1 | 40.3 | 73.2 | 65.1 | 41 | 81.8 | 70.8 | 55.5 | 89.9 | 81.9 | 72.8 | 92.4 | 88.4 | 83.3 | 95.7 | 91.4 | 87.7 | 97.7 | 93.3 | 85 | 94.9 | 87.2 | 80.3 | 85.3 | 79.2 | 70.5 | 73.3 | 61 | 52.4 | 68.6 | 57.1 | 40.5 | 63.3 | 46.6 | 34.8
6 | 2 | 15 | 66.5 | 51.9 | 43.5 | 79.5 | 69 | 44.3 | 84.1 | 74.1 | 61.1 | 92.1 | 85.6 | 74.9 | 94.2 | 90.1 | 87.1 | 96.6 | 92.8 | 88.7 | 98.8 | 95.4 | 88.8 | 96.7 | 87.9 | 82.7 | 87.3 | 81.9 | 72.2 | 77.5 | 67.3 | 58.6 | 73.1 | 59.6 | 45.3 | 68.1 | 50 | 35.5
6 | 2 | 20 | 66.5 | 51.9 | 43.5 | 79.5 | 69 | 44.3 | 84.1 | 74.1 | 61.1 | 92.1 | 85.6 | 74.9 | 94.2 | 90.1 | 87.2 | 96.6 | 92.8 | 88.7 | 98.8 | 95.4 | 88.8 | 96.7 | 87.9 | 82.7 | 87.3 | 81.9 | 72.2 | 77.5 | 67.5 | 58.7 | 73.1 | 59.6 | 45.3 | 68.1 | 50 | 35.5
6 | 2 | 25 | 66.5 | 51.9 | 43.5 | 79.5 | 69 | 44.3 | 84.1 | 74.1 | 61.1 | 92.1 | 85.6 | 74.9 | 94.2 | 90.1 | 87.2 | 96.6 | 92.8 | 88.7 | 98.8 | 95.4 | 88.8 | 96.7 | 87.9 | 82.7 | 87.3 | 81.9 | 72.2 | 77.5 | 67.5 | 58.7 | 73.1 | 59.6 | 45.3 | 68.1 | 50 | 35.5
6 | 2.25 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 2.25 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 1.7 | 9.9 | 3.8 | 1.4
6 | 2.25 | 6 | 21.7 | 10.6 | 6.6 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.3 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 21.6 | 13.8 | 5.9
6 | 2.25 | 8 | 39.1 | 25.8 | 16 | 44.4 | 33.9 | 20 | 49 | 39.4 | 29.5 | 60.9 | 51.3 | 43.8 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.3 | 28.9 | 17.6 | 38.4 | 24.2 | 16.5
6 | 2.25 | 9 | 49.4 | 32.7 | 19.9 | 54.2 | 42.4 | 25.5 | 60.8 | 48.1 | 39.1 | 70.4 | 62.1 | 55.7 | 72.7 | 64.8 | 57 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.8 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 51.9 | 39.2 | 31.7 | 48.7 | 36.5 | 26.9 | 47.2 | 33.3 | 21.8
6 | 2.25 | 10 | 56.2 | 40.2 | 26.9 | 62.5 | 54.3 | 32.9 | 71.7 | 58.7 | 46.9 | 80.7 | 72.1 | 65.9 | 82.5 | 75.7 | 68.7 | 90.2 | 83.8 | 77.2 | 88.5 | 84 | 76.7 | 88 | 80.2 | 69.4 | 77.8 | 67.2 | 60.8 | 59.2 | 50.7 | 41.5 | 56.1 | 46.8 | 33.4 | 55.9 | 41 | 28.6
6 | 2.25 | 11 | 62.2 | 46.8 | 36.2 | 72.1 | 60.3 | 37.3 | 77.8 | 68.3 | 56.3 | 87.9 | 77.9 | 72.3 | 89.8 | 83.2 | 79.5 | 94.8 | 89.6 | 82.8 | 95.7 | 90.3 | 83.1 | 93 | 85.1 | 76.7 | 84.8 | 74.6 | 67 | 68.4 | 59 | 49.2 | 66 | 54.4 | 41.3 | 62.2 | 46.2 | 36.6
6 | 2.25 | 12 | 67.8 | 53.2 | 43.3 | 75.8 | 67.6 | 47.8 | 84 | 74.7 | 59.4 | 92.4 | 85 | 77.5 | 93.1 | 89.1 | 85.3 | 97.6 | 92.2 | 88.7 | 97.6 | 94.5 | 88.3 | 97 | 89.5 | 83.7 | 88.4 | 81.9 | 72.9 | 75.2 | 65.5 | 56.4 | 73.2 | 62.1 | 44.4 | 69.7 | 50 | 41.8
6 | 2.25 | 15 | 75.5 | 60.1 | 49.2 | 83.1 | 74.3 | 54.3 | 90.1 | 81 | 67.4 | 95.9 | 91.9 | 82.9 | 96.2 | 94.4 | 91.3 | 99 | 95.1 | 92.6 | 99.8 | 97.2 | 93.3 | 98.2 | 92.6 | 87.6 | 92.6 | 87.1 | 79.8 | 82.7 | 75.8 | 69.1 | 80.1 | 68.1 | 52.4 | 75.6 | 61.2 | 47.8
6 | 2.25 | 20 | 75.8 | 60.2 | 49.2 | 83.8 | 75.1 | 54.3 | 90.4 | 80.9 | 67.6 | 96 | 91.9 | 82.9 | 96.2 | 94.4 | 91.3 | 99 | 95.3 | 92.6 | 99.8 | 97.2 | 93.3 | 98.2 | 92.5 | 88 | 92.5 | 87.1 | 79.8 | 82.8 | 75.8 | 69.2 | 80.9 | 67.9 | 53 | 75.6 | 61.8 | 48.4
6 | 2.25 | 25 | 75.8 | 60.2 | 49.2 | 83.8 | 75.1 | 54.3 | 90.4 | 80.9 | 67.6 | 96 | 91.9 | 82.9 | 96.2 | 94.4 | 91.3 | 99 | 95.3 | 92.6 | 99.8 | 97.2 | 93.3 | 98.2 | 92.5 | 88 | 92.5 | 87.1 | 79.8 | 82.8 | 75.8 | 69.2 | 80.9 | 67.9 | 53 | 75.6 | 61.8 | 48.4
6 | 2.75 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 2.75 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 2.75 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 2.75 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.5 | 49 | 39.2 | 29.5 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 2.75 | 9 | 49.4 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.1 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.5 | 40.1 | 32.5 | 48.8 | 39.4 | 27.4 | 49 | 33.3 | 22.2
6 | 2.75 | 10 | 57.9 | 40.2 | 27.9 | 62.7 | 55.4 | 34 | 71.7 | 59.8 | 48.6 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.3 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 60.8 | 62 | 51.7 | 42.4 | 57.2 | 48.8 | 34 | 57.2 | 41.8 | 29.3
6 | 2.75 | 11 | 63.9 | 49.3 | 37.5 | 72.4 | 61.1 | 39 | 78.4 | 69.8 | 57.2 | 88.2 | 80.7 | 74.9 | 90.5 | 84.9 | 79.9 | 94.9 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 68.9 | 71 | 60.6 | 50.6 | 67.6 | 57.6 | 42.6 | 65 | 48.8 | 39
6 | 2.75 | 12 | 70.7 | 57.1 | 46.6 | 77.2 | 72.5 | 50 | 85.7 | 78.1 | 62.4 | 93.9 | 86.5 | 81.1 | 94.5 | 90.7 | 87.1 | 97.9 | 93.6 | 89.9 | 97.9 | 95.6 | 89.1 | 97 | 91.4 | 84.7 | 89.5 | 83.3 | 75.6 | 77.3 | 69 | 57.6 | 75.3 | 66.8 | 48.8 | 71.2 | 55.6 | 46.7
6 | 2.75 | 15 | 84.4 | 72 | 61.8 | 89.5 | 83.3 | 68 | 93.9 | 87.2 | 77.5 | 98.5 | 95.1 | 91 | 99.6 | 98.3 | 96.2 | 100 | 97.9 | 96.2 | 100 | 98.7 | 96.2 | 100 | 96.9 | 93.8 | 96.5 | 93.8 | 86.9 | 90.2 | 82.4 | 78.1 | 88.1 | 80 | 65.6 | 83.9 | 70.4 | 61.5
6 | 2.75 | 20 | 87.6 | 73.7 | 63.2 | 91.6 | 84.6 | 69.5 | 94.9 | 88.3 | 77.9 | 99 | 96 | 91.5 | 100 | 98.5 | 96.3 | 100 | 98.1 | 96.2 | 100 | 98.9 | 96.3 | 100 | 97.4 | 94.4 | 96.9 | 94.9 | 88.5 | 91.3 | 84.7 | 79.8 | 89.9 | 81.3 | 69.7 | 86 | 73 | 66
6 | 2.75 | 25 | 87.6 | 73.7 | 63.2 | 91.6 | 84.6 | 69.5 | 94.9 | 88.3 | 77.9 | 99 | 96 | 91.5 | 100 | 98.5 | 96.8 | 100 | 98.1 | 96.2 | 100 | 98.9 | 96.3 | 100 | 97.4 | 94.4 | 96.9 | 94.9 | 88.5 | 91.3 | 84.7 | 79.8 | 89.9 | 81.3 | 69.7 | 86 | 73 | 66
6 | 3 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 3 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 3 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 3 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.4 | 49 | 39.2 | 30 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 3 | 9 | 49.5 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.1 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.8 | 40.1 | 32.5 | 48.8 | 39.4 | 27.6 | 49 | 33.3 | 22.4
6 | 3 | 10 | 58.1 | 40.2 | 27.9 | 62.7 | 55.4 | 34.2 | 71.7 | 59.8 | 48.9 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.4 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 61 | 62 | 51.7 | 43 | 57.9 | 49.6 | 34.2 | 58.3 | 41.8 | 29.8
6 | 3 | 11 | 64.6 | 49.3 | 37.4 | 72.4 | 61.1 | 39.9 | 78.4 | 69.8 | 57.4 | 88.2 | 80.7 | 75 | 90.5 | 84.9 | 79.9 | 95.2 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 69.3 | 71 | 61.7 | 50.6 | 67.6 | 57.8 | 44 | 65.3 | 50.7 | 39
6 | 3 | 12 | 71.3 | 57.7 | 46.7 | 77.2 | 72.8 | 51.4 | 86.9 | 78.9 | 63.2 | 93.9 | 86.5 | 81.4 | 94.7 | 90.7 | 88.1 | 97.9 | 93.6 | 90 | 97.9 | 95.6 | 89.6 | 97 | 91.4 | 84.7 | 89.5 | 84 | 76.7 | 77.5 | 69.2 | 58.4 | 75.3 | 66.9 | 50.1 | 72.5 | 57.3 | 46.7
6 | 3 | 15 | 85.5 | 75.9 | 65.8 | 91.4 | 86.6 | 72.9 | 94.8 | 89 | 82.2 | 99 | 96.4 | 91.9 | 99.9 | 98.8 | 97.4 | 100 | 98.3 | 96.4 | 100 | 99.3 | 96.9 | 100 | 98.1 | 94.8 | 97.5 | 93.9 | 90.2 | 91.9 | 85.1 | 79.8 | 89.6 | 81.8 | 70.4 | 85.7 | 75.3 | 64.3
6 | 3 | 20 | 90.8 | 79.4 | 67.6 | 95.1 | 89.1 | 76.9 | 97.1 | 91.5 | 85.1 | 100 | 97.2 | 93.6 | 100 | 100 | 98 | 100 | 99 | 97 | 100 | 100 | 97.9 | 100 | 98.8 | 96.7 | 98.3 | 96.3 | 91.3 | 94.1 | 89.4 | 84 | 92.2 | 87.5 | 76.2 | 88.5 | 79.2 | 71.2
6 | 3 | 25 | 90.8 | 79.4 | 67.6 | 95.1 | 89.1 | 76.9 | 97.1 | 91.5 | 85.1 | 100 | 97.2 | 93.6 | 100 | 100 | 98 | 100 | 99 | 97 | 100 | 100 | 97.9 | 100 | 98.8 | 96.7 | 98.3 | 96.3 | 91.3 | 94.1 | 89.4 | 84 | 92.2 | 87.5 | 76.2 | 88.5 | 79.2 | 71.2
6 | 3.5 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 3.5 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 3.5 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 3.5 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.4 | 49 | 39.2 | 30 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 3.5 | 9 | 49.5 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.7 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.8 | 40.1 | 32.5 | 48.8 | 39.4 | 27.6 | 49 | 33.3 | 22.4
6 | 3.5 | 10 | 58.1 | 40.2 | 27.9 | 62.7 | 55.4 | 34.2 | 71.7 | 59.8 | 49.1 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.4 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 61 | 62 | 51.7 | 43 | 57.9 | 50.6 | 34.2 | 58.3 | 41.8 | 29.8
6 | 3.5 | 11 | 64.7 | 49.3 | 37.4 | 72.4 | 61.1 | 40 | 78.4 | 69.9 | 57.4 | 88.2 | 80.7 | 75 | 90.5 | 84.9 | 79.9 | 95.2 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 69.3 | 71.1 | 62.1 | 51.4 | 67.6 | 58.6 | 44 | 65.6 | 50.5 | 39.4
6 | 3.5 | 12 | 71.3 | 57.8 | 46.7 | 77.4 | 72.8 | 51.9 | 86.9 | 79.6 | 65.5 | 93.9 | 86.5 | 81.5 | 94.7 | 90.7 | 88.1 | 97.9 | 93.6 | 90 | 97.9 | 95.6 | 89.6 | 97 | 91.4 | 84.7 | 89.7 | 84 | 77.6 | 77.5 | 69.8 | 58.4 | 75.3 | 67.8 | 51.8 | 73.5 | 57.7 | 47.1
6 | 3.5 | 15 | 87.5 | 78.9 | 69.1 | 92.7 | 88.2 | 77.2 | 95.8 | 90.1 | 84.3 | 99.3 | 97.5 | 93.8 | 100 | 99.1 | 98.4 | 100 | 98.3 | 97.1 | 100 | 100 | 98 | 100 | 98.5 | 95.1 | 98.4 | 94.6 | 91.4 | 92.8 | 87 | 81.2 | 92.4 | 83.6 | 75.2 | 88.1 | 77.8 | 67.6
6 | 3.5 | 20 | 95.6 | 89.8 | 81.6 | 98.5 | 92.8 | 86.2 | 99.8 | 96.8 | 92.1 | 100 | 100 | 96.6 | 100 | 100 | 100 | 100 | 100 | 98.1 | 100 | 100 | 99.3 | 100 | 100 | 98.5 | 100 | 97.9 | 95.1 | 98.1 | 94.5 | 90.2 | 96.8 | 92.4 | 86.6 | 96 | 89 | 81.9
6 | 3.5 | 25 | 95.7 | 90.1 | 81.6 | 98.5 | 92.8 | 86.2 | 99.8 | 96.8 | 92.1 | 100 | 100 | 96.6 | 100 | 100 | 100 | 100 | 100 | 98.1 | 100 | 100 | 99.3 | 100 | 100 | 98.4 | 100 | 97.9 | 95.1 | 98.1 | 94.5 | 90.2 | 96.9 | 92.4 | 86.6 | 96 | 89 | 82.2
6 | 4 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 4 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 4 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 4 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.4 | 49 | 39.2 | 30 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 4 | 9 | 49.5 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.7 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.8 | 40.1 | 32.5 | 48.8 | 39.4 | 27.6 | 49 | 33.3 | 22.4
6 | 4 | 10 | 58.1 | 40.2 | 27.9 | 62.7 | 55.4 | 34.2 | 71.7 | 59.8 | 49.1 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.4 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 61 | 62 | 51.7 | 43 | 57.9 | 50.6 | 34.2 | 58.3 | 41.8 | 29.8
6 | 4 | 11 | 64.8 | 49.3 | 37.4 | 72.4 | 61.1 | 40 | 78.4 | 69.9 | 57.4 | 88.2 | 80.7 | 75 | 90.5 | 84.9 | 79.9 | 95.2 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 69.3 | 71.1 | 62.1 | 51.4 | 67.6 | 58.6 | 44 | 65.6 | 50.5 | 39.4
6 | 4 | 12 | 71.3 | 57.8 | 46.7 | 77.4 | 72.8 | 51.9 | 86.9 | 79.6 | 65.6 | 93.9 | 86.5 | 81.5 | 94.7 | 90.7 | 88.1 | 97.9 | 93.6 | 90 | 97.9 | 95.6 | 89.6 | 97 | 91.4 | 84.7 | 89.7 | 84 | 77.6 | 77.5 | 69.8 | 58.4 | 75.3 | 67.8 | 52.9 | 73.5 | 57.7 | 47.1
6 | 4 | 15 | 88.5 | 79 | 70.4 | 93.1 | 88.8 | 78.2 | 96.1 | 90.7 | 84.4 | 99.3 | 97.8 | 94.1 | 100 | 99.2 | 98.4 | 100 | 98.9 | 97.1 | 100 | 100 | 98.3 | 100 | 98.7 | 95.7 | 98.4 | 94.9 | 91.8 | 93 | 87.8 | 82.3 | 93.3 | 85.1 | 76.8 | 89.1 | 80.8 | 68.3
6 | 4 | 20 | 98.3 | 95 | 89.4 | 99.6 | 96.9 | 90.9 | 100 | 98.7 | 96.3 | 100 | 100 | 98.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.7 | 97 | 100 | 97.6 | 95 | 99.5 | 96.7 | 93.2 | 99.1 | 94.6 | 89.6
6 | 4 | 25 | 98.3 | 94.9 | 89.6 | 99.8 | 97 | 91.1 | 100 | 99.1 | 96.4 | 100 | 100 | 98.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.2 | 100 | 97.6 | 95.2 | 99.5 | 96.8 | 94.1 | 99.2 | 94.9 | 91.7
6 | 4.5 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 4.5 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 4.5 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 4.5 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.4 | 49 | 39.2 | 30 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 4.5 | 9 | 49.5 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.7 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.8 | 40.1 | 32.5 | 48.8 | 39.4 | 27.6 | 49 | 33.3 | 22.4
6 | 4.5 | 10 | 58.1 | 40.2 | 27.9 | 62.7 | 55.4 | 34.2 | 71.7 | 59.8 | 49.1 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.4 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 61 | 62 | 51.7 | 43 | 57.9 | 50.6 | 34.2 | 58.3 | 41.8 | 29.8
6 | 4.5 | 11 | 64.8 | 49.3 | 37.4 | 72.4 | 61.1 | 40 | 78.4 | 69.9 | 57.4 | 88.2 | 80.7 | 75 | 90.5 | 84.9 | 79.9 | 95.2 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 69.3 | 71.1 | 62.1 | 51.4 | 67.6 | 58.6 | 44 | 65.6 | 50.5 | 39.4
6 | 4.5 | 12 | 71.3 | 57.8 | 46.7 | 77.4 | 72.8 | 51.9 | 86.9 | 79.6 | 65.6 | 93.9 | 86.5 | 81.5 | 94.7 | 90.7 | 88.1 | 97.9 | 93.6 | 90 | 97.9 | 95.6 | 89.6 | 97 | 91.4 | 84.7 | 89.7 | 84 | 77.6 | 77.5 | 69.8 | 58.4 | 75.3 | 67.8 | 52.9 | 73.5 | 57.7 | 47.1
6 | 4.5 | 15 | 89.1 | 79 | 70.4 | 93.1 | 89 | 78.2 | 96.1 | 91.1 | 84.5 | 99.3 | 98.2 | 94.6 | 100 | 99.2 | 98.4 | 100 | 98.9 | 97.7 | 100 | 100 | 98.3 | 100 | 98.7 | 95.7 | 98.4 | 95 | 91.8 | 93 | 87.8 | 82.5 | 93.3 | 85.7 | 77.3 | 89.1 | 80.8 | 68.4
6 | 4.5 | 20 | 99.5 | 96.9 | 92.4 | 100 | 98.1 | 94.1 | 100 | 99.5 | 98 | 100 | 100 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.9 | 100 | 98.8 | 96.5 | 100 | 98.5 | 95.5 | 100 | 97.8 | 93.3
6 | 4.5 | 25 | 100 | 97.8 | 94.3 | 100 | 98.9 | 94.9 | 100 | 100 | 98.4 | 100 | 100 | 98.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99 | 100 | 99.3 | 97.4 | 100 | 99 | 97 | 100 | 98.8 | 95.3
6 | 5 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 5 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 5 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 5 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.4 | 49 | 39.2 | 30 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 5 | 9 | 49.5 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.7 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.8 | 40.1 | 32.5 | 48.8 | 39.4 | 27.6 | 49 | 33.3 | 22.4
6 | 5 | 10 | 58.1 | 40.2 | 27.9 | 62.7 | 55.4 | 34.2 | 71.7 | 59.8 | 49.1 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.4 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 61 | 62 | 51.7 | 43 | 57.9 | 50.6 | 34.2 | 58.3 | 41.8 | 29.8
6 | 5 | 11 | 64.8 | 49.3 | 37.4 | 72.4 | 61.1 | 40 | 78.4 | 69.9 | 57.4 | 88.2 | 80.7 | 75 | 90.5 | 84.9 | 79.9 | 95.2 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 69.3 | 71.1 | 62.1 | 51.4 | 67.6 | 58.6 | 44 | 65.6 | 50.5 | 39.4
6 | 5 | 12 | 71.3 | 57.8 | 46.7 | 77.4 | 72.8 | 51.9 | 86.9 | 79.6 | 65.6 | 93.9 | 86.5 | 81.5 | 94.7 | 90.7 | 88.1 | 97.9 | 93.6 | 90 | 97.9 | 95.6 | 89.6 | 97 | 91.4 | 84.7 | 89.7 | 84 | 77.6 | 77.5 | 69.8 | 58.4 | 75.3 | 67.8 | 52.9 | 73.5 | 57.7 | 47.1
6 | 5 | 15 | 89.1 | 79 | 70.4 | 93.1 | 89.1 | 78.2 | 96.1 | 91.1 | 84.5 | 99.3 | 98.2 | 94.6 | 100 | 99.2 | 98.4 | 100 | 98.9 | 97.7 | 100 | 100 | 98.3 | 100 | 98.7 | 95.7 | 98.4 | 95 | 91.8 | 93 | 87.8 | 82.5 | 93.3 | 85.7 | 77.3 | 89.1 | 80.8 | 68.4
6 | 5 | 20 | 100 | 97.2 | 93.4 | 100 | 99 | 95.5 | 100 | 99.5 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.8 | 100 | 99.2 | 97.1 | 100 | 98.5 | 96.6 | 100 | 98.7 | 94
6 | 5 | 25 | 100 | 99.7 | 97.7 | 100 | 100 | 97.8 | 100 | 100 | 99.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99 | 100 | 100 | 98.2 | 100 | 100 | 97.9
12 | 0.25 | 2
12 | 0.25 | 4 | [12 empty] | 1.6 |  |  | 2.6 |  |  | 1.5 |  |  | 2.9
12 | 0.25 | 6 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 4.3 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 8 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 9 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 10 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 11 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 12 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 15 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 20 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 25 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.5 | 2 | [15 empty] | 1.5
12 | 0.5 | 4 |  |  |  | 1.6 |  |  | 2.6 |  |  | 5.8 | 1.7 |  | 6.6 | 1.5 |  | 8.1 | 4.6 | 1.5 | 7.8 | 3.4 | 1.5 | 9.1 | 4.7 | 1.5 | 5.8 | 3.1 |  | 1.6 |  |  | 1.5 |  |  | 1.5
12 | 0.5 | 6 | 4 |  |  | 3.4 | 1.6 |  | 5.7 | 1.5 |  | 11.1 | 4.9 | 1.8 | 12.1 | 6 | 3.1 | 16.1 | 11.3 | 3.2 | 20.1 | 12.4 | 5.9 | 16.8 | 11 | 6.1 | 11.2 | 5.6 | 1.5 | 3.1 | 1.5 |  | 1.6 |  |  | 3.1
12 | 0.5 | 8 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16 | 9.3 | 4.5 | 19.5 | 13.1 | 4.9 | 26 | 15.5 | 7.7 | 20.4 | 12.5 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 9 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 12.5 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 10 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 11 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 12 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 15 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 20 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 25 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.75 | 2 | [15 empty] | 1.5 |  |  | 1.5 |  |  | 1
12 | 0.75 | 4 | 1.6 |  |  | 4.4 | 1.6 |  | 6 | 1.5 |  | 7.9 | 3.3 | 2.1 | 8.2 | 3.1 |  | 11.3 | 7.9 | 3.1 | 10.9 | 7.5 | 3 | 12.3 | 7.5 | 3.5 | 9 | 4.7 | 1.5 | 3.1 | 1.5 |  | 3.1 | 1.5 |  | 3.1 | 1.5
12 | 0.75 | 6 | 8.8 | 3 |  | 11.4 | 5.1 | 1.6 | 16.3 | 4.7 | 3 | 23.5 | 11.9 | 7.7 | 24.6 | 14.1 | 8.5 | 29.7 | 19.6 | 11.1 | 29.9 | 20.6 | 15.2 | 30.4 | 19 | 12.3 | 21 | 16.1 | 8.1 | 10.3 | 4.7 | 1.7 | 6.2 | 3.2 |  | 8.8 | 4.6 | 1.3
12 | 0.75 | 8 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 9.3 | 4.6 | 30.4 | 17.9 | 11.4 | 31.8 | 22.7 | 16.8 | 40.7 | 30.3 | 19.2 | 42.7 | 33.9 | 23.2 | 41.1 | 30.8 | 21.5 | 30.5 | 21 | 11.2 | 13.5 | 6.3 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 9 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 34.4 | 25.9 | 17.6 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.2 | 14 | 6.9 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 10 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.9 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 11 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.6 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 12 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.6 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 15 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.6 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 20 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.6 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 25 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.6 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 1 | 2 | [9 empty] | 1.1 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5
12 | 1 | 4 | 2.9 | 0.8 |  | 6.7 | 3.3 | 0.5 | 7.4 | 3 |  | 10.7 | 6.1 | 3.1 | 9.3 | 4.6 | 1.5 | 14.1 | 9.4 | 4.7 | 12.4 | 7.8 | 3.1 | 13.2 | 7.7 | 4.6 | 9.6 | 6.3 | 3.1 | 3.1 | 1.5 |  | 4.3 | 1.5 |  | 3.1 | 1.5
12 | 1 | 6 | 10.8 | 5.4 | 1.5 | 15.6 | 8.6 | 3.2 | 18.8 | 11 | 4.5 | 26.4 | 16.8 | 11.8 | 27.9 | 18.3 | 13.3 | 37.4 | 28.2 | 16.7 | 35.8 | 25.1 | 18.3 | 36.3 | 23.1 | 17.4 | 25.8 | 20.8 | 12.6 | 14.8 | 7.7 | 3.1 | 11.1 | 6.3 | 3.2 | 12 | 4.7 | 1.5
12 | 1 | 8 | 21.4 | 10.9 | 1.5 | 24 | 15.9 | 6.2 | 32.9 | 19.2 | 11.4 | 45.4 | 30.6 | 23.1 | 45.4 | 36.7 | 27.4 | 54.3 | 42.6 | 33.9 | 59.1 | 47.3 | 33.2 | 57.3 | 45.2 | 36.2 | 40.2 | 31.7 | 26 | 25.4 | 13.8 | 6.7 | 19.8 | 10.8 | 5 | 21.7 | 10.6 | 4.5
12 | 1 | 9 | 23 | 12.5 | 1.5 | 25.3 | 17.4 | 8.5 | 33.6 | 21.9 | 12.6 | 51.2 | 34.6 | 25.8 | 49.5 | 41.8 | 29.2 | 60.1 | 48.2 | 39.8 | 64.6 | 53 | 38.7 | 59.7 | 47.8 | 39.5 | 45.6 | 35.7 | 27.5 | 26.7 | 16.3 | 8.3 | 21 | 11.5 | 5.6 | 23.4 | 11 | 4.6
12 | 1 | 10 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.3 | 12.9 | 52.5 | 35.1 | 26.7 | 52 | 44.1 | 32 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 39.6 | 62 | 49.6 | 40.9 | 47.5 | 37.4 | 28.3 | 27.9 | 17.1 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1 | 11 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.8 | 12.9 | 52.6 | 35.1 | 26.8 | 52 | 44.5 | 32.5 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 41.3 | 62.2 | 49.6 | 41.1 | 47.5 | 37.4 | 28.3 | 27.9 | 17.2 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1 | 12 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.8 | 12.9 | 52.6 | 35.1 | 26.8 | 52 | 44.5 | 32.5 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 41.9 | 62.2 | 49.6 | 41.1 | 47.5 | 37.4 | 28.3 | 27.9 | 17.2 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1 | 15 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.8 | 12.9 | 52.6 | 35.1 | 26.8 | 52 | 44.5 | 32.5 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 42.4 | 62.2 | 49.6 | 41.1 | 47.5 | 37.4 | 28.3 | 27.9 | 17.2 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1 | 20 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.8 | 12.9 | 52.6 | 35.1 | 26.8 | 52 | 44.5 | 32.5 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 42.4 | 62.2 | 49.6 | 41.1 | 47.5 | 37.4 | 28.3 | 27.9 | 17.2 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1 | 25 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.8 | 12.9 | 52.6 | 35.1 | 26.8 | 52 | 44.5 | 32.5 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 42.4 | 62.2 | 49.6 | 41.1 | 47.5 | 37.4 | 28.3 | 27.9 | 17.2 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1.25 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5
12 | 1.25 | 4 | 4 | 1.5 |  | 6.8 | 3.3 | 0.5 | 7.7 | 3.1 |  | 10.7 | 6.3 | 3.2 | 10.7 | 6 | 3 | 14.4 | 11 | 5.1 | 13.4 | 9.1 | 3.1 | 13.8 | 9 | 4.6 | 11.1 | 6.4 | 3.1 | 6.3 | 3 |  | 4.7 | 1.5 |  | 4.5 | 1.6
12 | 1.25 | 6 | 16.6 | 6 | 2.9 | 17.7 | 8.8 | 4.9 | 21.4 | 12.6 | 5.2 | 28.6 | 19.3 | 14.5 | 31 | 21.4 | 16.3 | 39.7 | 31.4 | 20.6 | 39 | 29.2 | 20.9 | 37 | 26.5 | 18.3 | 27.1 | 22.4 | 12.8 | 16.8 | 10.8 | 4.6 | 12.9 | 8.1 | 4.7 | 12.6 | 7.7 | 3
12 | 1.25 | 8 | 30.2 | 15.5 | 5.3 | 30.2 | 22.3 | 11 | 39.9 | 27.6 | 15.9 | 52.8 | 37.8 | 30.9 | 51.3 | 42.9 | 36.3 | 63.5 | 52.1 | 38 | 63.2 | 52.2 | 39.7 | 61 | 50.1 | 42.1 | 49 | 37.5 | 29 | 31.9 | 18.5 | 13.1 | 24.9 | 17.6 | 8.1 | 29.3 | 14.1 | 6.6
12 | 1.25 | 9 | 33.4 | 19.5 | 6.7 | 35.7 | 26.2 | 12.7 | 42.4 | 34.3 | 20.6 | 58.7 | 45.7 | 36.2 | 60.9 | 52.4 | 44.9 | 71.7 | 60.6 | 50.3 | 72.6 | 64 | 50.5 | 70.2 | 58.6 | 48.3 | 57.2 | 46.4 | 34.5 | 39 | 24.7 | 17.2 | 31.8 | 20.7 | 11.5 | 32.1 | 17.6 | 8.6
12 | 1.25 | 10 | 36.2 | 20 | 8 | 40.2 | 28.1 | 13.2 | 47.6 | 37.8 | 22.7 | 63.6 | 49.4 | 41.7 | 67.2 | 58.1 | 50 | 75.7 | 66 | 55.2 | 77.9 | 70.3 | 56.6 | 73 | 62.9 | 53.3 | 61.2 | 50.3 | 37.2 | 40.5 | 28.9 | 18.8 | 33.9 | 22.5 | 11.5 | 33.7 | 19.5 | 12.7
12 | 1.25 | 11 | 36.2 | 20 | 8 | 40.9 | 28.1 | 13.3 | 47.6 | 39.5 | 22.7 | 67.7 | 51 | 41.9 | 69.2 | 58.7 | 53.3 | 77.8 | 67.4 | 57.1 | 79.8 | 72.7 | 57.1 | 74.6 | 66.1 | 55.4 | 63 | 51.1 | 38.5 | 40.8 | 30.4 | 19.1 | 34.4 | 23.9 | 11.5 | 34 | 19.5 | 12.6
12 | 1.25 | 12 | 36.2 | 20 | 8 | 40.8 | 28.1 | 13.3 | 48.2 | 39.5 | 22.7 | 67.7 | 51 | 41.9 | 70 | 59.1 | 53.3 | 77.8 | 67.6 | 57.2 | 79.7 | 72.8 | 57.4 | 74.6 | 66.5 | 55.5 | 63 | 51.1 | 38.5 | 41.1 | 30.5 | 19.1 | 34.7 | 23.9 | 11.5 | 34 | 19.5 | 12.6
12 | 1.25 | 15 | 36.2 | 20 | 8 | 40.8 | 28.1 | 13.3 | 49.2 | 39.5 | 22.7 | 67.7 | 51 | 41.9 | 69.8 | 59.1 | 53.4 | 77.8 | 67.6 | 57.2 | 79.7 | 72.8 | 57.8 | 74.6 | 66.5 | 55.5 | 63 | 51.1 | 38.5 | 41.1 | 30.5 | 19.1 | 34.7 | 23.9 | 11.5 | 34 | 19.5 | 12.6
12 | 1.25 | 20 | 36.2 | 20 | 8 | 40.8 | 28.1 | 13.3 | 49.2 | 39.5 | 22.7 | 67.7 | 51 | 41.9 | 69.8 | 59.1 | 53.4 | 77.8 | 67.6 | 57.2 | 79.7 | 72.8 | 57.8 | 74.6 | 66.5 | 55.5 | 63 | 51.1 | 38.5 | 41.1 | 30.5 | 19.1 | 34.7 | 23.9 | 11.5 | 34 | 19.5 | 12.6
12 | 1.25 | 25 | 36.2 | 20 | 8 | 40.8 | 28.1 | 13.3 | 49.2 | 39.5 | 22.7 | 67.7 | 51 | 41.9 | 69.8 | 59.1 | 53.4 | 77.8 | 67.6 | 57.2 | 79.7 | 72.8 | 57.8 | 74.6 | 66.5 | 55.5 | 63 | 51.1 | 38.5 | 41.1 | 30.5 | 19.1 | 34.7 | 23.9 | 11.5 | 34 | 19.5 | 12.6
12 | 1.5 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5
12 | 1.5 | 4 | 5.6 | 1.5 |  | 7.9 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.3 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 13.8 | 9.1 | 4.6 | 11.1 | 6.4 | 3.1 | 7.1 | 3 | 1.5 | 4.7 | 1.5 |  | 7 | 1.6
12 | 1.5 | 6 | 18 | 7.7 | 2.9 | 19.3 | 10.3 | 4.9 | 23.2 | 13.8 | 7.6 | 29.9 | 20.6 | 16.2 | 31 | 23.8 | 17.1 | 40.6 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 37.4 | 26.6 | 18.7 | 28 | 23.8 | 12.8 | 18.3 | 12 | 5.6 | 14.4 | 9.6 | 5.2 | 13.9 | 9.3 | 3.1
12 | 1.5 | 8 | 31.6 | 17.6 | 9.1 | 37.1 | 24 | 13.1 | 42.1 | 29.6 | 19.5 | 56.9 | 41 | 34.8 | 54.3 | 46.2 | 38.8 | 67.7 | 54.9 | 43.8 | 64.7 | 55.6 | 43.4 | 62.6 | 53.8 | 43.5 | 52.3 | 40.4 | 31.6 | 36.4 | 21.8 | 17.2 | 29.6 | 21 | 12 | 31.9 | 17.2 | 9.6
12 | 1.5 | 9 | 36.7 | 24.6 | 10.8 | 41.4 | 31.5 | 16.3 | 51.2 | 37.8 | 26.8 | 63.8 | 51 | 44.5 | 65 | 58.3 | 48.6 | 77.1 | 64.9 | 56.8 | 75.8 | 69.5 | 56.9 | 72.4 | 63.7 | 51.2 | 61.9 | 50.6 | 40.3 | 43.8 | 30.6 | 21.9 | 36.9 | 27.4 | 17.3 | 38.9 | 23.7 | 13.2
12 | 1.5 | 10 | 40.8 | 28.2 | 14.9 | 49.8 | 38.5 | 21.9 | 56.7 | 45.3 | 35.2 | 70.6 | 57.8 | 51 | 73.9 | 65.9 | 57.3 | 83.1 | 77.1 | 67.6 | 82.5 | 78.1 | 66 | 81.3 | 70.7 | 59.4 | 66.3 | 59.2 | 47.1 | 48.7 | 36.2 | 26.6 | 44.1 | 29.3 | 19.4 | 41.2 | 27.4 | 16.4
12 | 1.5 | 11 | 43.6 | 30.6 | 16.2 | 53.5 | 40.5 | 21.9 | 61.2 | 49.7 | 36.6 | 76.4 | 63.1 | 53.8 | 79.9 | 71.4 | 63.2 | 86.4 | 80.7 | 67.5 | 88.8 | 82.4 | 69.9 | 84.3 | 76.1 | 64.6 | 71.6 | 61.8 | 50 | 52.4 | 41.8 | 29 | 48.3 | 32.8 | 21.9 | 45 | 28.6 | 18.2
12 | 1.5 | 12 | 44.8 | 30.6 | 17.2 | 54.1 | 42.1 | 22.4 | 61.9 | 49.6 | 36.6 | 77 | 63.6 | 55.9 | 80.5 | 73.1 | 65.8 | 86.9 | 81.1 | 69.9 | 90.2 | 83.3 | 70.9 | 84.6 | 76.1 | 66.4 | 71.6 | 63.9 | 49.8 | 53.7 | 42.3 | 29.6 | 49.8 | 32.8 | 21.6 | 45.3 | 28.6 | 18.7
12 | 1.5 | 15 | 44.8 | 30.6 | 17.2 | 54.1 | 42.1 | 22.4 | 61.9 | 49.6 | 36.6 | 78.2 | 63.5 | 55.8 | 80.5 | 73.1 | 65.8 | 86.9 | 81.3 | 69.8 | 90.2 | 83.3 | 70.9 | 85.4 | 76.1 | 66.4 | 71.6 | 63.8 | 49.8 | 53.7 | 42.3 | 30.4 | 49.7 | 32.8 | 22.2 | 45.3 | 28.8 | 18.7
12 | 1.5 | 20 | 44.8 | 30.6 | 17.2 | 54.1 | 42.1 | 22.4 | 61.9 | 49.6 | 36.6 | 78.2 | 63.5 | 55.8 | 80.5 | 73.1 | 65.8 | 86.9 | 81.3 | 69.8 | 90.2 | 83.3 | 70.9 | 85.4 | 76.1 | 66.4 | 71.6 | 63.8 | 49.8 | 53.7 | 42.3 | 30.4 | 49.7 | 32.8 | 22.2 | 45.3 | 28.8 | 18.7
12 | 1.5 | 25 | 44.8 | 30.6 | 17.2 | 54.1 | 42.1 | 22.4 | 61.9 | 49.6 | 36.6 | 78.2 | 63.5 | 55.8 | 80.5 | 73.1 | 65.8 | 86.9 | 81.3 | 69.8 | 90.2 | 83.3 | 70.9 | 85.4 | 76.1 | 66.4 | 71.6 | 63.8 | 49.8 | 53.7 | 42.3 | 30.4 | 49.7 | 32.8 | 22.2 | 45.3 | 28.8 | 18.7
12 | 1.75 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5
12 | 1.75 | 4 | 5.7 | 1.5 |  | 7.9 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.1 | 7.1 | 3 | 1.5 | 4.7 | 1.5 |  | 7.4 | 3
12 | 1.75 | 6 | 18.6 | 7.7 | 3 | 19.3 | 11.9 | 4.9 | 23.2 | 15.3 | 7.9 | 31.2 | 21.5 | 17.3 | 31 | 24.5 | 17.1 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 26.6 | 19.3 | 28.1 | 23.8 | 13.2 | 18.6 | 12.5 | 6.5 | 15.4 | 11.1 | 6.3 | 15.9 | 10.8 | 3.7
12 | 1.75 | 8 | 34 | 19.1 | 10.6 | 39 | 28.2 | 14.8 | 42.8 | 32.4 | 20.8 | 57.7 | 44 | 36.7 | 55.3 | 48 | 39.4 | 67.7 | 56.5 | 45.5 | 65.7 | 57.8 | 43.4 | 62.6 | 53.6 | 43.5 | 53.4 | 41.8 | 33.2 | 36.9 | 24.2 | 19.6 | 31.5 | 23.2 | 12.6 | 33 | 20 | 11.3
12 | 1.75 | 9 | 43.1 | 26.6 | 15.1 | 47.4 | 35.6 | 20 | 54 | 40.9 | 32 | 66.8 | 54.9 | 48.5 | 66.8 | 61.4 | 50.5 | 79 | 68.1 | 60 | 76.3 | 71.1 | 59.1 | 73 | 63.7 | 53.3 | 65.1 | 52.9 | 44.3 | 46.1 | 34 | 24.9 | 41.8 | 29.7 | 19.6 | 40.8 | 26.2 | 14.9
12 | 1.75 | 10 | 47.3 | 32.4 | 20.1 | 57.2 | 41.8 | 26.8 | 66.9 | 52 | 40.2 | 74.6 | 63.3 | 58.3 | 78.6 | 69.5 | 63 | 84.7 | 79.7 | 71.4 | 86 | 79.2 | 71.1 | 82.9 | 72.7 | 63.2 | 69.3 | 61.7 | 53.6 | 54.3 | 41.4 | 30.2 | 47.6 | 37.4 | 25 | 46.6 | 31.6 | 20.3
12 | 1.75 | 11 | 51.5 | 37.8 | 26.9 | 62.8 | 50.6 | 28.9 | 73.4 | 57.4 | 44.6 | 84.2 | 71.7 | 63.2 | 84.4 | 76.2 | 70 | 90.1 | 84.9 | 74.9 | 92.6 | 86 | 78 | 87.8 | 79.6 | 70.5 | 77.4 | 68.2 | 57.8 | 61.4 | 50.4 | 38.3 | 53.7 | 42.8 | 28.6 | 54.2 | 34.8 | 25.9
12 | 1.75 | 12 | 53.2 | 40.1 | 28.5 | 65.3 | 54.8 | 30.3 | 76.4 | 59 | 48.6 | 85.2 | 74.9 | 65.3 | 87.9 | 81.6 | 73.2 | 92 | 86.7 | 79 | 93.8 | 87.4 | 80.5 | 91.6 | 81 | 72.8 | 79 | 70.4 | 61 | 67.1 | 52.2 | 41.7 | 57.5 | 45.6 | 28.6 | 55.5 | 36.4 | 26
12 | 1.75 | 15 | 54.5 | 40.1 | 29.8 | 65.4 | 56 | 30.3 | 77.2 | 59.1 | 50.5 | 85.7 | 75.7 | 66.9 | 88.9 | 83.3 | 75.9 | 93 | 87.9 | 80.4 | 95.1 | 87.8 | 81.2 | 91.6 | 82.8 | 74 | 80.7 | 71.4 | 63 | 67.7 | 54.4 | 43.4 | 59 | 45.4 | 31.2 | 56.3 | 36.4 | 26
12 | 1.75 | 20 | 54.5 | 40.1 | 29.8 | 65.4 | 56 | 30.3 | 77.2 | 59.1 | 50.5 | 85.7 | 75.7 | 66.9 | 88.9 | 83.3 | 75.9 | 93 | 87.9 | 80.4 | 95.1 | 87.8 | 81.2 | 91.6 | 82.8 | 74 | 80.7 | 71.4 | 63 | 67.7 | 54.4 | 43.4 | 59 | 45.4 | 31.2 | 56.3 | 36.4 | 26
12 | 1.75 | 25 | 54.5 | 40.1 | 29.8 | 65.4 | 56 | 30.3 | 77.2 | 59.1 | 50.5 | 85.7 | 75.7 | 66.9 | 88.9 | 83.3 | 75.9 | 93 | 87.9 | 80.4 | 95.1 | 87.8 | 81.2 | 91.6 | 82.8 | 74 | 80.7 | 71.4 | 63 | 67.7 | 54.4 | 43.4 | 59 | 45.4 | 31.2 | 56.3 | 36.4 | 26
12 | 2 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 2 | 4 | 5.7 | 1.5 |  | 7.9 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.1 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.4 | 3
12 | 2 | 6 | 18.6 | 7.7 | 3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.1 | 6.3 | 17.8 | 10.8 | 3.7
12 | 2 | 8 | 35 | 19.5 | 12.6 | 39.8 | 28.3 | 17.2 | 43.6 | 33.2 | 22.3 | 57.7 | 45.8 | 36.7 | 56.6 | 48 | 40.6 | 67.7 | 56.9 | 45.5 | 66.2 | 57.8 | 44.3 | 62.6 | 53.6 | 43.5 | 53.9 | 42.2 | 33.2 | 38.3 | 26.5 | 19.6 | 32 | 24.3 | 13.7 | 33.5 | 20.4 | 11.5
12 | 2 | 9 | 44.5 | 27.8 | 15.2 | 48 | 37.5 | 20.7 | 55.4 | 42.5 | 33.1 | 67.7 | 56.5 | 50.4 | 68.4 | 62.2 | 52.1 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 59.7 | 73.9 | 65.1 | 53.4 | 66.5 | 55 | 44.8 | 46.7 | 34 | 25.4 | 43.6 | 32.4 | 20.9 | 41.3 | 27.6 | 16.5
12 | 2 | 10 | 50.9 | 35.9 | 22.3 | 57.5 | 47 | 27.4 | 66.9 | 53.5 | 40.8 | 76.1 | 66.9 | 60.5 | 78.9 | 72.3 | 63.8 | 86.4 | 81.3 | 72.9 | 87.6 | 79.7 | 73 | 83.8 | 75.8 | 64.3 | 73.1 | 63.1 | 55 | 54.4 | 44.2 | 34.7 | 51 | 39.4 | 27.9 | 49.4 | 32.1 | 22.4
12 | 2 | 11 | 56.3 | 39.7 | 28.8 | 65.9 | 55.5 | 30.7 | 74.7 | 62 | 49.7 | 85.9 | 73.9 | 66.3 | 86.6 | 79.4 | 74.7 | 92.1 | 87.1 | 79 | 94.2 | 88 | 81.2 | 91 | 81.5 | 72.1 | 79.8 | 70.3 | 59.5 | 63.1 | 53.8 | 41.2 | 59 | 48.1 | 35.3 | 55.9 | 38.7 | 29.2
12 | 2 | 12 | 61.4 | 44.5 | 34.3 | 71.5 | 61.6 | 34.6 | 79.9 | 67.5 | 51.4 | 89.7 | 80 | 69.7 | 91 | 85.3 | 80.1 | 95.1 | 89.9 | 85.3 | 96.3 | 91.8 | 82.2 | 93.9 | 84.8 | 77.2 | 84.1 | 74.4 | 66.1 | 70.7 | 59.1 | 49 | 64.9 | 54.7 | 36.7 | 61.6 | 42.9 | 31.8
12 | 2 | 15 | 63.5 | 47.2 | 37.8 | 75.9 | 65.5 | 39.6 | 82.2 | 70.6 | 58.5 | 90.7 | 83.6 | 72.1 | 93.2 | 88.8 | 84.3 | 95.8 | 92.1 | 87 | 98.4 | 94.6 | 86.7 | 95.6 | 86.8 | 81.9 | 85.8 | 80.3 | 69 | 75.7 | 63.7 | 54.8 | 68.6 | 56.7 | 41.1 | 64.1 | 45.7 | 32.7
12 | 2 | 20 | 63.5 | 47.2 | 37.8 | 75.9 | 65.5 | 39.6 | 82.2 | 70.6 | 58.5 | 90.7 | 83.6 | 72.1 | 93.2 | 88.8 | 84.3 | 95.8 | 92.1 | 87 | 98.4 | 94.6 | 86.7 | 95.6 | 86.8 | 81.9 | 86 | 80.3 | 69 | 75.7 | 63.7 | 54.9 | 68.6 | 56.7 | 41.1 | 64.1 | 46.1 | 32.7
12 | 2 | 25 | 63.5 | 47.2 | 37.8 | 75.9 | 65.5 | 39.6 | 82.2 | 70.6 | 58.5 | 90.7 | 83.6 | 72.1 | 93.2 | 88.8 | 84.3 | 95.8 | 92.1 | 87 | 98.4 | 94.6 | 86.7 | 95.6 | 86.8 | 81.9 | 86 | 80.3 | 69 | 75.7 | 63.7 | 54.9 | 68.6 | 56.7 | 41.1 | 64.1 | 46.1 | 32.7
12 | 2.25 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 2.25 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 2.25 | 6 | 18.5 | 7.7 | 3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.3 | 10.8 | 4.1
12 | 2.25 | 8 | 35.6 | 20.3 | 13.3 | 40.1 | 29.5 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.7 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 57.8 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.9
12 | 2.25 | 9 | 44.5 | 29 | 16.6 | 49.2 | 37.9 | 21.5 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.4 | 68.7 | 62.2 | 52.3 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 59.7 | 73.9 | 65.1 | 53.7 | 66.8 | 55.6 | 44.8 | 46.7 | 34 | 26.6 | 43.8 | 33.1 | 22.4 | 43.3 | 27.6 | 17.5
12 | 2.25 | 10 | 51.2 | 35.9 | 22.7 | 58.7 | 48.2 | 28.2 | 68.3 | 55.8 | 42.9 | 76.1 | 68.1 | 61.7 | 78.9 | 72.3 | 64.7 | 87 | 81.5 | 74.4 | 87.6 | 80.5 | 73 | 84.3 | 75.7 | 64.4 | 73.3 | 63.2 | 56.1 | 56.1 | 44.5 | 36.6 | 51.3 | 41.7 | 28.4 | 49.7 | 36.4 | 24.9
12 | 2.25 | 11 | 57.9 | 42.7 | 29.1 | 67.8 | 55.7 | 32.6 | 75.9 | 65.3 | 52.1 | 86.1 | 74.9 | 68.6 | 87.3 | 80 | 75.5 | 92.5 | 87.9 | 80.6 | 94.2 | 88 | 81.6 | 91.5 | 82.5 | 73.2 | 82.6 | 70.7 | 63.1 | 64.9 | 55.2 | 44.5 | 59.2 | 49 | 36.7 | 58.1 | 41.9 | 30.7
12 | 2.25 | 12 | 64.5 | 48.1 | 37.6 | 72.6 | 64.7 | 43 | 81.2 | 70.4 | 56 | 91.5 | 82.5 | 73.8 | 91.2 | 87 | 82.9 | 96.2 | 91.3 | 86.8 | 96.3 | 93.8 | 84 | 96.2 | 87.2 | 81.1 | 86.5 | 79 | 69.1 | 72.9 | 60.8 | 51.7 | 69.2 | 56.7 | 38.8 | 64.4 | 46.8 | 37.5
12 | 2.25 | 15 | 72.1 | 57 | 45.1 | 80.7 | 71 | 50.3 | 88.5 | 78.6 | 64.6 | 95.6 | 89.4 | 80.5 | 95.7 | 92.9 | 89.6 | 98.8 | 94.2 | 91.4 | 99.8 | 96.5 | 91.6 | 97.7 | 91.5 | 85.5 | 91 | 85.7 | 78.7 | 80.5 | 72 | 64 | 78.7 | 64 | 48 | 73.4 | 57.3 | 43.2
12 | 2.25 | 20 | 72.5 | 57.5 | 45.1 | 81.4 | 72 | 50.3 | 89.2 | 78.5 | 64.6 | 95.6 | 89.4 | 80.5 | 95.7 | 92.9 | 89.6 | 98.8 | 94.2 | 91.4 | 99.8 | 96.4 | 91.6 | 97.7 | 91.5 | 85.9 | 90.9 | 85.8 | 78.7 | 80.3 | 72 | 64 | 78.7 | 64 | 48.8 | 73.4 | 57.3 | 44.4
12 | 2.25 | 25 | 72.5 | 57.5 | 45.1 | 81.4 | 72 | 50.3 | 89.2 | 78.5 | 64.6 | 95.6 | 89.4 | 80.5 | 95.7 | 92.9 | 89.6 | 98.8 | 94.2 | 91.4 | 99.8 | 96.4 | 91.6 | 97.7 | 91.5 | 85.9 | 90.9 | 85.8 | 78.7 | 80.3 | 72 | 64 | 78.7 | 64 | 48.8 | 73.4 | 57.3 | 44.4
12 | 2.75 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 2.75 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 2.75 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 2.75 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 2.75 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 2.75 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 44.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 51.5 | 42.6 | 28.6 | 51.3 | 38 | 24.9
12 | 2.75 | 11 | 59.8 | 44.6 | 30.8 | 69 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 70.6 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.7 | 72.2 | 64.3 | 66.7 | 56.9 | 47.4 | 61.6 | 55.6 | 37.6 | 59.2 | 45 | 32.4
12 | 2.75 | 12 | 66.7 | 51.2 | 43.9 | 74.5 | 66.8 | 47.5 | 84.1 | 73.9 | 58 | 93.2 | 83.6 | 77.9 | 92.7 | 88.3 | 84.1 | 96.4 | 91.5 | 88.2 | 96.6 | 94.5 | 86.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 72.7 | 74.8 | 65.1 | 53.1 | 72.3 | 61.3 | 43.6 | 68.1 | 51.7 | 42.7
12 | 2.75 | 15 | 81.6 | 67.3 | 56.7 | 87.9 | 81.7 | 64.2 | 92.1 | 85.6 | 74.2 | 97.8 | 94.3 | 89.3 | 99.2 | 97.7 | 95.1 | 100 | 97.4 | 95.3 | 100 | 98.1 | 95.8 | 100 | 96.6 | 92.1 | 95.8 | 91.3 | 85.7 | 89.1 | 80 | 74.5 | 86.1 | 77.6 | 61.7 | 82.1 | 68 | 57.1
12 | 2.75 | 20 | 86.9 | 71.1 | 60.7 | 89.7 | 83 | 65.6 | 94.4 | 88.3 | 76.4 | 98.6 | 95.3 | 89.4 | 100 | 98 | 95.5 | 100 | 98.1 | 95.6 | 100 | 98.7 | 96.1 | 100 | 96.9 | 93.6 | 96.5 | 93.2 | 88.5 | 90.5 | 82 | 76.5 | 88 | 77.9 | 65 | 83.3 | 69.8 | 61.9
12 | 2.75 | 25 | 86.9 | 71.1 | 60.7 | 89.7 | 83 | 65.6 | 94.4 | 88.3 | 76.4 | 98.6 | 95.3 | 89.4 | 100 | 98 | 95.5 | 100 | 98.1 | 95.6 | 100 | 98.7 | 96.1 | 100 | 96.9 | 93.6 | 96.5 | 93.2 | 88.5 | 90.5 | 82 | 76.5 | 88 | 77.9 | 65 | 83.3 | 69.8 | 61.9
12 | 3 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 3 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 3 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 3 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 3 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 3 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 44.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 52 | 43.8 | 28.6 | 51.3 | 38 | 24.9
12 | 3 | 11 | 61.3 | 45.2 | 30.8 | 69 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 71.1 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.9 | 72.2 | 64.3 | 66.7 | 56.9 | 47.4 | 61.6 | 56.3 | 37.6 | 60.1 | 46 | 32.4
12 | 3 | 12 | 67.4 | 53 | 43.9 | 74.5 | 66.8 | 48 | 84.7 | 75.5 | 58 | 93.2 | 83.6 | 78.1 | 93.3 | 88.3 | 84.7 | 96.6 | 91.9 | 88.2 | 96.6 | 94.5 | 87.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 73.5 | 74.8 | 65.6 | 53.3 | 72.3 | 61.7 | 44.5 | 69.5 | 51.7 | 42.7
12 | 3 | 15 | 83.5 | 71.2 | 61.3 | 89.8 | 85.1 | 69.4 | 94.2 | 87.4 | 78.4 | 99 | 94.9 | 90.4 | 99.9 | 98.5 | 96.6 | 100 | 98.1 | 95.5 | 100 | 98.9 | 96.5 | 100 | 97.6 | 93.6 | 96.9 | 92.2 | 88.5 | 90.5 | 82 | 76.5 | 88.6 | 77.6 | 66.7 | 83.8 | 73.3 | 60.9
12 | 3 | 20 | 89.9 | 75.8 | 65.2 | 94.4 | 87.4 | 73.5 | 96.2 | 90.7 | 82 | 100 | 96.7 | 92.5 | 100 | 100 | 97.4 | 100 | 98.3 | 96.5 | 100 | 100 | 97 | 100 | 98.3 | 95.9 | 97.6 | 95.4 | 89.1 | 93.8 | 87.2 | 81.9 | 91.5 | 84.4 | 72.5 | 85.9 | 76.6 | 68.1
12 | 3 | 25 | 89.9 | 75.8 | 65.2 | 94.4 | 87.4 | 73.5 | 96.2 | 90.7 | 82 | 100 | 96.7 | 92.5 | 100 | 100 | 97.4 | 100 | 98.3 | 96.5 | 100 | 100 | 97 | 100 | 98.3 | 95.9 | 97.6 | 95.4 | 89.1 | 93.8 | 87.2 | 81.9 | 91.5 | 84.4 | 72.5 | 85.9 | 76.6 | 68.1
12 | 3.5 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 3.5 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 3.5 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 3.5 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 3.5 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 3.5 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 44.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 52 | 43.8 | 28.6 | 51.3 | 38 | 24.9
12 | 3.5 | 11 | 61.3 | 45.2 | 31 | 69.5 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 71.1 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.9 | 72.2 | 64.3 | 66.7 | 56.9 | 48.5 | 61.6 | 56.3 | 37.6 | 60.5 | 46 | 33.5
12 | 3.5 | 12 | 67.4 | 53 | 43.9 | 74.5 | 66.8 | 48.5 | 84.7 | 75.5 | 60.3 | 93.2 | 83.6 | 79.4 | 93.3 | 88.3 | 84.7 | 96.9 | 91.9 | 88.2 | 96.6 | 94.5 | 87.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 73.6 | 75.5 | 65.6 | 53.3 | 72.3 | 61.7 | 45.9 | 69.5 | 51.7 | 43.1
12 | 3.5 | 15 | 86.2 | 75.1 | 64.3 | 90.1 | 86.3 | 71.8 | 94.5 | 89.1 | 81.8 | 99.3 | 96.4 | 92.2 | 100 | 98.8 | 97.5 | 100 | 98.2 | 96.1 | 100 | 100 | 97.3 | 100 | 97.8 | 94.9 | 97.9 | 92.9 | 88.8 | 92 | 84.5 | 78.8 | 90.3 | 81.1 | 71 | 85.2 | 74.9 | 63.5
12 | 3.5 | 20 | 93.2 | 88.2 | 78.5 | 98.2 | 92.7 | 84.3 | 99.8 | 95.2 | 90 | 100 | 100 | 95.6 | 100 | 100 | 100 | 100 | 100 | 97.6 | 100 | 100 | 99.1 | 100 | 100 | 98.2 | 100 | 97.9 | 93.4 | 97.8 | 93.3 | 88.3 | 96.1 | 90.8 | 84.1 | 95.1 | 87.4 | 79.4
12 | 3.5 | 25 | 93.3 | 88.8 | 78.5 | 98.5 | 92.7 | 84.3 | 99.8 | 95.2 | 90 | 100 | 100 | 95.6 | 100 | 100 | 100 | 100 | 100 | 97.6 | 100 | 100 | 99.1 | 100 | 100 | 98.2 | 100 | 97.9 | 93.4 | 97.8 | 93.3 | 88.3 | 96.5 | 90.8 | 84.1 | 95 | 87.4 | 79.7
12 | 4 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 4 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 4 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 4 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 4 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 4 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 45.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 52 | 43.8 | 28.6 | 51.3 | 38 | 24.9
12 | 4 | 11 | 61.3 | 45.2 | 31 | 69.5 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 71.1 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.9 | 72.2 | 64.3 | 66.7 | 56.9 | 48.5 | 61.6 | 56.3 | 37.6 | 60.5 | 46 | 33.6
12 | 4 | 12 | 67.4 | 53 | 43.9 | 74.5 | 66.8 | 48.5 | 84.7 | 75.5 | 61.2 | 93.2 | 83.6 | 79.4 | 93.3 | 88.3 | 84.7 | 96.9 | 91.9 | 88.2 | 96.6 | 94.5 | 87.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 73.6 | 75.5 | 65.6 | 53.3 | 72.3 | 61.7 | 47.1 | 69.8 | 51.7 | 43.1
12 | 4 | 15 | 86.4 | 75.5 | 66.9 | 91.7 | 86.3 | 74.6 | 95 | 89.8 | 81.8 | 99.3 | 96.7 | 92.8 | 100 | 98.8 | 97.5 | 100 | 98.3 | 96.4 | 100 | 100 | 97.5 | 100 | 97.8 | 94.9 | 97.9 | 93.3 | 88.8 | 92 | 85.8 | 79.4 | 91.1 | 81.1 | 72.5 | 86.4 | 75.3 | 63.6
12 | 4 | 20 | 97.6 | 93.5 | 87.4 | 99.2 | 95.5 | 89.9 | 100 | 98.7 | 95.7 | 100 | 100 | 97.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.7 | 96.8 | 100 | 96.8 | 94 | 98.8 | 95.8 | 91.8 | 99.1 | 93.7 | 87.6
12 | 4 | 25 | 97.7 | 93.4 | 87.5 | 99.8 | 96.1 | 90.1 | 100 | 99.1 | 95.8 | 100 | 100 | 97.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 96.8 | 100 | 96.8 | 94 | 99 | 96 | 91.9 | 99 | 94 | 89.2
12 | 4.5 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 4.5 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 4.5 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 4.5 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 4.5 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 4.5 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 45.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 52 | 43.8 | 28.6 | 51.3 | 38 | 24.9
12 | 4.5 | 11 | 61.3 | 45.2 | 31 | 69.5 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 71.1 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.9 | 72.2 | 64.3 | 66.7 | 56.9 | 48.5 | 61.6 | 56.3 | 37.6 | 60.5 | 46 | 33.6
12 | 4.5 | 12 | 67.4 | 53 | 43.9 | 74.5 | 66.8 | 48.5 | 84.7 | 75.5 | 61.2 | 93.2 | 83.6 | 79.4 | 93.3 | 88.3 | 84.7 | 96.9 | 91.9 | 88.2 | 96.6 | 94.5 | 87.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 73.6 | 75.5 | 65.6 | 53.3 | 72.3 | 61.7 | 47.1 | 69.8 | 51.7 | 43.1
12 | 4.5 | 15 | 86.4 | 75.5 | 66.9 | 91.7 | 86.6 | 74.6 | 95.1 | 89.8 | 82.4 | 99.3 | 96.9 | 93.1 | 100 | 98.8 | 97.5 | 100 | 98.3 | 96.5 | 100 | 100 | 97.5 | 100 | 97.8 | 94.9 | 97.9 | 93.8 | 88.8 | 92.2 | 85.8 | 80.1 | 91.6 | 83.3 | 73 | 86.8 | 77.7 | 63.6
12 | 4.5 | 20 | 99.1 | 96.2 | 90.4 | 100 | 98.1 | 92.9 | 100 | 99.5 | 97.2 | 100 | 100 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.5 | 100 | 98.3 | 95.5 | 100 | 97.6 | 93.9 | 100 | 97 | 90.6
12 | 4.5 | 25 | 100 | 97.3 | 93.9 | 100 | 98.5 | 93.4 | 100 | 100 | 98 | 100 | 100 | 98.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.9 | 100 | 99.3 | 96.7 | 100 | 98.8 | 96.1 | 100 | 98.4 | 94.1
12 | 5 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 5 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 5 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 5 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 5 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 5 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 45.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 52 | 43.8 | 28.6 | 51.3 | 38 | 24.9
12 | 5 | 11 | 61.3 | 45.2 | 31 | 69.5 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 71.1 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.9 | 72.2 | 64.3 | 66.7 | 56.9 | 48.5 | 61.6 | 56.3 | 37.6 | 60.5 | 46 | 33.6
12 | 5 | 12 | 67.4 | 53 | 43.9 | 74.5 | 66.8 | 48.5 | 84.7 | 75.5 | 61.2 | 93.2 | 83.6 | 79.4 | 93.3 | 88.3 | 84.7 | 96.9 | 91.9 | 88.2 | 96.6 | 94.5 | 87.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 73.6 | 75.5 | 65.6 | 53.3 | 72.3 | 61.7 | 47.1 | 69.8 | 51.7 | 43.1
12 | 5 | 15 | 86.4 | 75.5 | 66.9 | 91.7 | 86.9 | 74.6 | 95.1 | 89.8 | 82.4 | 99.3 | 96.9 | 93.1 | 100 | 98.8 | 97.5 | 100 | 98.3 | 96.5 | 100 | 100 | 97.5 | 100 | 97.8 | 94.9 | 97.9 | 93.8 | 88.8 | 92.2 | 85.8 | 80.4 | 91.6 | 83.3 | 73 | 86.8 | 77.7 | 63.6
12 | 5 | 20 | 100 | 97 | 91.4 | 100 | 98.1 | 94.4 | 100 | 99.5 | 97.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.5 | 100 | 98.9 | 96.1 | 100 | 97.6 | 95.4 | 100 | 97.8 | 91.3
12 | 5 | 25 | 100 | 99.1 | 96.9 | 100 | 100 | 96.4 | 100 | 100 | 99.4 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 100 | 97.5 | 100 | 100 | 97.2
18 | 0.25 | 2
18 | 0.25 | 4 | [12 empty] | 1.6 |  |  | 2.4 |  |  | 0.1 |  |  | 2.2
18 | 0.25 | 6 | [12 empty] | 2.3 |  |  | 4 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 8 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 9 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 10 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 11 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 12 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 15 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 20 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 25 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.5 | 2
18 | 0.5 | 4 |  |  |  | 1.7 |  |  | 2.3 |  |  | 4.1 |  |  | 4.7 |  |  | 6.5 | 2.4 |  | 7.1 | 2.3 |  | 6.9 | 2.4 | 0.7 | 4.1 | 2.4 |  | 2.3 | [5 empty] | 0.9
18 | 0.5 | 6 | 2.3 |  |  | 2.5 |  |  | 6.3 |  |  | 9.7 | 2.4 | 0.4 | 9.5 | 4.7 | 2.3 | 14.6 | 10 | 2.4 | 16.5 | 9.4 | 4.6 | 15.6 | 9.5 | 4.6 | 9.7 | 4.9 |  | 2.3 |  |  | 1.8 |  |  | 2.3
18 | 0.5 | 8 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 12.6 | 7 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.3 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 9 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 10 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 11 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 12 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 15 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 20 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 25 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.75 | 2
18 | 0.75 | 4 | 0.8 |  |  | 2.7 | 1.2 |  | 3.3 |  |  | 6.4 | 2.4 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 1.4 | 7.1 | 4.7 | 0.5 | 9.2 | 4.6 | 2.3 | 7.2 | 2.4 | 0.7 | 2.3 |  |  | 2.4 |  |  | 2.3
18 | 0.75 | 6 | 4.7 | 2.3 |  | 10.2 | 5.1 |  | 13.7 | 4.7 | 2.3 | 21.1 | 9.6 | 4.7 | 18.9 | 11.4 | 4.7 | 25.9 | 17.8 | 7.9 | 26 | 16.7 | 12.4 | 28.5 | 16.4 | 9.2 | 17.2 | 12.1 | 4.9 | 7.6 | 4.2 | 1 | 4.9 | 2.4 |  | 7.1 | 2.3
18 | 0.75 | 8 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.3 | 9.3 | 2.3 | 27.1 | 17.1 | 9.4 | 28.9 | 18.8 | 13 | 36.7 | 26.1 | 12.6 | 39.1 | 28.5 | 20.6 | 37.2 | 26.1 | 18.7 | 26.4 | 19.4 | 7.9 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.4 | 4.6
18 | 0.75 | 9 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 30.9 | 21.2 | 15.5 | 39.4 | 28.9 | 14.4 | 42.7 | 30.8 | 21.4 | 38.1 | 28.5 | 18.7 | 26.8 | 19.4 | 9.4 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.4 | 4.6
18 | 0.75 | 10 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 0.75 | 11 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 0.75 | 12 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 0.75 | 15 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 0.75 | 20 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 0.75 | 25 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 1 | 2
18 | 1 | 4 | 2.3 |  |  | 5.1 | 1.7 |  | 4.7 |  |  | 7.2 | 2.5 |  | 8.6 | 2.4 |  | 9.7 | 4.9 | 2.4 | 9.5 | 6.9 | 1.6 | 9.3 | 4.7 | 2.3 | 7.3 | 4.7 | 2.4 | 2.3 | 2.3 |  | 2.4 |  |  | 3
18 | 1 | 6 | 9.3 | 4.6 |  | 14.5 | 7.6 | 2.5 | 15.9 | 9.4 | 2.3 | 24.6 | 12.2 | 9.4 | 22.4 | 14.2 | 9.1 | 31.7 | 22.8 | 14.3 | 30.5 | 21.1 | 14.7 | 30.5 | 21 | 12.7 | 21.8 | 14.3 | 10.1 | 11.6 | 5.9 | 2.3 | 9 | 4.7 | 2.4 | 10.6 | 4.7
18 | 1 | 8 | 20.8 | 7.4 | 2.3 | 22.8 | 13.2 | 5.4 | 31 | 16.5 | 9.2 | 41.1 | 25.7 | 17.7 | 43.4 | 32.3 | 23.8 | 53.3 | 38.9 | 30.1 | 54.4 | 42.7 | 30.5 | 52.3 | 40.1 | 30.8 | 36.2 | 29.6 | 19 | 22.3 | 12 | 5.2 | 16.6 | 9.7 | 4.8 | 19.7 | 9.4 | 2.3
18 | 1 | 9 | 22.4 | 9.4 | 2.3 | 22.9 | 14 | 6.9 | 33.3 | 18.8 | 10.7 | 46.8 | 29.6 | 22 | 47.4 | 38.3 | 26.6 | 58.5 | 43.5 | 35.7 | 62.1 | 48.5 | 36.8 | 57.1 | 45.2 | 34.6 | 42.7 | 34 | 21 | 26.7 | 14.1 | 7.1 | 18.4 | 9.9 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 10 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.7 | 33.4 | 21.1 | 12.9 | 46.7 | 31.9 | 22 | 48.7 | 39.7 | 27.2 | 58.6 | 46.1 | 37 | 65.1 | 50.1 | 37.5 | 59.1 | 47.6 | 35.3 | 44.2 | 34.2 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 9.9 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 11 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.6 | 33.4 | 21.1 | 12.8 | 48.4 | 31.9 | 22 | 48.7 | 39.7 | 28.1 | 58.7 | 46.3 | 37 | 65.1 | 50.1 | 38.9 | 59.1 | 47.6 | 37.7 | 44.2 | 34.3 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 9.9 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 12 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.6 | 33.4 | 21.1 | 12.8 | 48.4 | 31.9 | 22 | 48.7 | 39.7 | 28.1 | 58.7 | 46.3 | 37 | 65.7 | 50.1 | 38.9 | 59.1 | 47.6 | 37.7 | 44.2 | 34.3 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 10.1 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 15 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.6 | 33.4 | 21.1 | 12.8 | 48.4 | 31.9 | 22 | 48.7 | 39.7 | 28.1 | 58.7 | 46.3 | 37 | 65.7 | 50.1 | 40 | 59.1 | 47.6 | 37.7 | 44.2 | 34.3 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 10.1 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 20 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.6 | 33.4 | 21.1 | 12.8 | 48.4 | 31.9 | 22 | 48.7 | 39.7 | 28.1 | 58.7 | 46.3 | 37 | 65.7 | 50.1 | 40 | 59.1 | 47.6 | 37.7 | 44.2 | 34.3 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 10.1 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 25 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.6 | 33.4 | 21.1 | 12.8 | 48.4 | 31.9 | 22 | 48.7 | 39.7 | 28.1 | 58.7 | 46.3 | 37 | 65.7 | 50.1 | 40 | 59.1 | 47.6 | 37.7 | 44.2 | 34.3 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 10.1 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1.25 | 2
18 | 1.25 | 4 | 2.3 |  |  | 5.2 | 2.5 |  | 4.7 | 1.9 |  | 7.2 | 3.1 | 2.4 | 9.3 | 4.6 | 1.9 | 9.7 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 9.3 | 6.6 | 2.3 | 7.3 | 4.7 | 2.4 | 2.4 | 2.3 |  | 2.5 |  |  | 3
18 | 1.25 | 6 | 10.9 | 4.7 |  | 17.6 | 7.9 | 2.5 | 18.7 | 11.6 | 4.1 | 24.6 | 14.6 | 9.9 | 25.7 | 18.1 | 12 | 34.2 | 26.8 | 16.7 | 30.6 | 23.5 | 17.7 | 32.7 | 21.2 | 14.6 | 24.3 | 16.8 | 12 | 14.3 | 7 | 2.3 | 12.1 | 4.9 | 2.4 | 11.8 | 4.7 | 0.3
18 | 1.25 | 8 | 25.6 | 11.6 | 3 | 26.7 | 18.8 | 8.3 | 34.7 | 23.7 | 13.6 | 49.2 | 34 | 25.1 | 47.5 | 39.1 | 30.7 | 58.8 | 44.3 | 34.2 | 59 | 47.7 | 37.8 | 56.3 | 46.4 | 33.1 | 44.1 | 36.5 | 25.1 | 28 | 16.7 | 9.6 | 21.9 | 14.7 | 7.2 | 26 | 11.7 | 5.7
18 | 1.25 | 9 | 30.1 | 18.4 | 4.7 | 34 | 23.5 | 10.3 | 41.1 | 30.1 | 18.9 | 56.8 | 41.8 | 33.5 | 58.7 | 49.1 | 38.8 | 68.9 | 56 | 46.1 | 71.3 | 58.9 | 45.5 | 68.9 | 55.1 | 43.7 | 51.6 | 42.2 | 31.4 | 35.1 | 21.2 | 12.6 | 27 | 16.7 | 10.3 | 30.5 | 14.8 | 6.6
18 | 1.25 | 10 | 33.7 | 18.3 | 4.7 | 37.6 | 25 | 11.2 | 43.3 | 32.7 | 22 | 60.2 | 46.8 | 37.1 | 64.9 | 52.2 | 47.2 | 73.1 | 63.9 | 52.4 | 76.1 | 65.9 | 51.2 | 70.8 | 61.4 | 50.5 | 58.2 | 47.1 | 36.4 | 38.2 | 27.2 | 16.6 | 30.2 | 21.1 | 11.8 | 31.9 | 16.5 | 9.4
18 | 1.25 | 11 | 33.7 | 18.3 | 4.7 | 37.6 | 25.1 | 12 | 43.7 | 32.7 | 22 | 65.1 | 49.3 | 37.7 | 66 | 55.8 | 48.1 | 76.2 | 65.4 | 53.8 | 77.6 | 68 | 53.8 | 72.8 | 62.9 | 52 | 61.1 | 48.8 | 36.6 | 38.6 | 27.7 | 16.9 | 30.3 | 21 | 11.8 | 31.7 | 16.8 | 9.4
18 | 1.25 | 12 | 33.7 | 18.3 | 4.7 | 37.7 | 25.1 | 12 | 43.7 | 32.7 | 22 | 65.2 | 49.3 | 39.5 | 66 | 56.9 | 48 | 76.2 | 65.4 | 54.3 | 77.4 | 68.1 | 54 | 73 | 62.9 | 52.4 | 61.1 | 48.8 | 36.6 | 38.6 | 27.7 | 16.9 | 30.3 | 21 | 11.8 | 31.7 | 16.8 | 9.4
18 | 1.25 | 15 | 33.7 | 18.3 | 4.7 | 37.7 | 25.1 | 12 | 43.7 | 32.7 | 22 | 65.2 | 49.3 | 39.5 | 66 | 56.9 | 48 | 76.2 | 65.4 | 54.3 | 78.5 | 68.1 | 55.1 | 73 | 62.9 | 52.4 | 61.1 | 48.8 | 36.6 | 38.6 | 27.7 | 16.9 | 30.3 | 21.5 | 11.8 | 31.7 | 16.8 | 9.4
18 | 1.25 | 20 | 33.7 | 18.3 | 4.7 | 37.7 | 25.1 | 12 | 43.7 | 32.7 | 22 | 65.2 | 49.3 | 39.5 | 66 | 56.9 | 48 | 76.2 | 65.4 | 54.3 | 78.5 | 68.1 | 55.1 | 73 | 62.9 | 52.4 | 61.1 | 48.8 | 36.6 | 38.6 | 27.7 | 16.9 | 30.3 | 21.5 | 11.8 | 31.7 | 16.8 | 9.4
18 | 1.25 | 25 | 33.7 | 18.3 | 4.7 | 37.7 | 25.1 | 12 | 43.7 | 32.7 | 22 | 65.2 | 49.3 | 39.5 | 66 | 56.9 | 48 | 76.2 | 65.4 | 54.3 | 78.5 | 68.1 | 55.1 | 73 | 62.9 | 52.4 | 61.1 | 48.8 | 36.6 | 38.6 | 27.7 | 16.9 | 30.3 | 21.5 | 11.8 | 31.7 | 16.8 | 9.4
18 | 1.5 | 2
18 | 1.5 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 1.9 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.7 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 3
18 | 1.5 | 6 | 13.2 | 4.7 | 2.1 | 18.4 | 7.9 | 3.1 | 18.6 | 13.8 | 5.2 | 24.6 | 16.4 | 11.8 | 27.1 | 18.3 | 13.2 | 36.5 | 26.8 | 16.8 | 32.2 | 23.5 | 17.8 | 32.7 | 21.2 | 14.6 | 24.4 | 17.2 | 12 | 15.6 | 9.1 | 4.6 | 12.1 | 7.1 | 3.8 | 13.7 | 7 | 2.3
18 | 1.5 | 8 | 28 | 16.1 | 6.5 | 32.2 | 20.8 | 11.1 | 38.3 | 27.2 | 14.3 | 49.7 | 36.9 | 32 | 52 | 41.5 | 34 | 62.5 | 51.1 | 36.2 | 61.8 | 50.7 | 41.5 | 56.7 | 48.5 | 36.7 | 48.3 | 36.5 | 27.7 | 30.7 | 21 | 12.4 | 24.5 | 17.2 | 9.6 | 30.9 | 14.2 | 6.9
18 | 1.5 | 9 | 34.3 | 21.1 | 9.6 | 37 | 26.2 | 13.6 | 46.9 | 35.6 | 24 | 61.1 | 48.2 | 41.8 | 62 | 53.8 | 43.6 | 73.6 | 61.1 | 52.4 | 73.2 | 64 | 53.8 | 70.7 | 60.6 | 48.3 | 57.7 | 46.5 | 36.2 | 39.5 | 28.5 | 18.7 | 33.4 | 22.9 | 14.5 | 34.5 | 20 | 10.5
18 | 1.5 | 10 | 38.2 | 24.1 | 11.7 | 47.1 | 34.2 | 19.4 | 52.9 | 42.7 | 31 | 67.8 | 54.9 | 49.2 | 72.6 | 61.6 | 53.4 | 81.1 | 74.6 | 63.4 | 79.8 | 74.2 | 62.9 | 77.4 | 67.7 | 57.1 | 63.9 | 53.6 | 43.3 | 45.3 | 33.2 | 23.9 | 40.4 | 28.9 | 14.6 | 40 | 22.6 | 13.8
18 | 1.5 | 11 | 39.1 | 26.5 | 13.6 | 48.3 | 39.6 | 20.2 | 55.1 | 45.7 | 33.9 | 71.7 | 60.4 | 51.7 | 77.3 | 69 | 60.1 | 83.7 | 77.2 | 67.2 | 86.2 | 80.4 | 68.5 | 79.8 | 72.4 | 62.2 | 71 | 59.9 | 47.8 | 48.7 | 37.9 | 27.3 | 44.3 | 31.1 | 17.1 | 42.6 | 23.7 | 14.7
18 | 1.5 | 12 | 39.2 | 26.5 | 13.5 | 50.1 | 39.7 | 20.1 | 57.8 | 46.6 | 33.7 | 74.4 | 62.1 | 52.8 | 77.5 | 71.1 | 62.9 | 83.8 | 77.6 | 68.4 | 88.4 | 81.6 | 69.6 | 83.8 | 74.6 | 62.6 | 70.9 | 60.4 | 48.1 | 51.9 | 38.4 | 27.3 | 44.3 | 31.7 | 17.7 | 44.6 | 26.1 | 16.2
18 | 1.5 | 15 | 39.2 | 28.9 | 13.5 | 50.1 | 39.7 | 20.1 | 57.7 | 47.3 | 33.7 | 76.2 | 62.1 | 54.1 | 79 | 71.2 | 62.9 | 83.8 | 78.2 | 68.3 | 88.5 | 81.9 | 69.6 | 83.8 | 74.6 | 62.8 | 70.9 | 60.4 | 48.1 | 52.1 | 38.4 | 27.4 | 44.3 | 31.7 | 17.7 | 44.6 | 25.9 | 16.2
18 | 1.5 | 20 | 39.2 | 28.9 | 13.5 | 50.1 | 39.7 | 20.1 | 57.7 | 47.3 | 33.7 | 76.2 | 62.1 | 54.1 | 79 | 71.2 | 62.9 | 83.8 | 78.2 | 68.3 | 88.5 | 81.9 | 69.6 | 83.8 | 74.6 | 62.8 | 70.9 | 60.4 | 48.1 | 52.1 | 38.4 | 27.4 | 44.3 | 31.7 | 17.7 | 44.6 | 25.9 | 16.2
18 | 1.5 | 25 | 39.2 | 28.9 | 13.5 | 50.1 | 39.7 | 20.1 | 57.7 | 47.3 | 33.7 | 76.2 | 62.1 | 54.1 | 79 | 71.2 | 62.9 | 83.8 | 78.2 | 68.3 | 88.5 | 81.9 | 69.6 | 83.8 | 74.6 | 62.8 | 70.9 | 60.4 | 48.1 | 52.1 | 38.4 | 27.4 | 44.3 | 31.7 | 17.7 | 44.6 | 25.9 | 16.2
18 | 1.75 | 2
18 | 1.75 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.1
18 | 1.75 | 6 | 13.2 | 4.7 | 2.1 | 19.6 | 7.9 | 3.1 | 18.6 | 13.8 | 6.7 | 24.9 | 16.9 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 21.4 | 15.1 | 25.1 | 19.2 | 12 | 15.6 | 9.1 | 4.6 | 12.1 | 7.1 | 4.4 | 15.2 | 7.1 | 2.3
18 | 1.75 | 8 | 29.3 | 18.4 | 9.2 | 32.2 | 23.4 | 12.9 | 41 | 28.5 | 19 | 52.8 | 39.6 | 34.1 | 53.3 | 41.8 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 51.9 | 41.5 | 58.4 | 50 | 38.3 | 49.6 | 39.9 | 29.7 | 33 | 21.6 | 14 | 27.4 | 19.3 | 9.9 | 30.9 | 16.7 | 7.8
18 | 1.75 | 9 | 39.4 | 25.1 | 11.6 | 41.1 | 28.6 | 17.2 | 49.7 | 39.7 | 28.9 | 62.5 | 50.8 | 44.2 | 62.2 | 55.2 | 45.5 | 75.2 | 63.6 | 54 | 75.5 | 64.7 | 54.3 | 72.1 | 60.6 | 49.6 | 59.3 | 47.8 | 37.7 | 42.3 | 30.9 | 21.7 | 36.7 | 25.7 | 17.3 | 37.5 | 21.1 | 11.9
18 | 1.75 | 10 | 44.6 | 29.8 | 16.6 | 51.4 | 38.8 | 24.7 | 60.5 | 47.2 | 36.6 | 72.1 | 59.6 | 51.4 | 76.9 | 63.8 | 56.9 | 84.2 | 75.6 | 66.4 | 83.5 | 76.7 | 65.3 | 81.3 | 71.5 | 60.2 | 66.6 | 57.9 | 48.6 | 49.3 | 36.6 | 28.4 | 44.2 | 33.6 | 19.3 | 44.6 | 28.5 | 15.1
18 | 1.75 | 11 | 48.3 | 33.5 | 18.7 | 59 | 47.2 | 26.3 | 69.7 | 55 | 42.5 | 81.8 | 67.6 | 59.6 | 82.3 | 74.1 | 68.4 | 88.2 | 83.5 | 73.1 | 91.6 | 83.3 | 73.9 | 87 | 77 | 66.8 | 75 | 66.4 | 53.6 | 58 | 46.4 | 35.6 | 50.7 | 40.7 | 26 | 50 | 33.3 | 20.2
18 | 1.75 | 12 | 50.3 | 36.6 | 21.8 | 59.9 | 50.1 | 26.9 | 74 | 56.2 | 43.6 | 84.3 | 71.3 | 62.8 | 86.7 | 80.9 | 72.3 | 90.8 | 86 | 78.4 | 92.8 | 86.2 | 78.3 | 91.7 | 80.6 | 70.7 | 77 | 69.2 | 58.3 | 62 | 50.1 | 37.4 | 53.4 | 43.2 | 26.1 | 50.8 | 33.6 | 23.6
18 | 1.75 | 15 | 51.5 | 36.6 | 23.8 | 62.2 | 52.5 | 26.8 | 74.4 | 57.4 | 44.3 | 85.3 | 73.1 | 63.5 | 88.6 | 81.9 | 74.5 | 91 | 86.4 | 78.3 | 94.2 | 87.5 | 78.7 | 91.9 | 81.6 | 71.1 | 79.7 | 69.4 | 59.9 | 64.4 | 51.5 | 40 | 55.4 | 43.1 | 26.9 | 51.9 | 33.6 | 23.5
18 | 1.75 | 20 | 51.5 | 36.6 | 23.8 | 62.2 | 52.5 | 26.8 | 74.4 | 57.4 | 44.3 | 85.3 | 73.1 | 63.5 | 88.6 | 81.9 | 74.5 | 91 | 86.4 | 78.3 | 94 | 87.5 | 78.7 | 91.9 | 81.6 | 71.1 | 79.7 | 69.4 | 59.9 | 64.4 | 51.5 | 40 | 55.4 | 43.1 | 26.9 | 51.9 | 33.6 | 23.5
18 | 1.75 | 25 | 51.5 | 36.6 | 23.8 | 62.2 | 52.5 | 26.8 | 74.4 | 57.4 | 44.3 | 85.3 | 73.1 | 63.5 | 88.6 | 81.9 | 74.5 | 91 | 86.4 | 78.3 | 94 | 87.5 | 78.7 | 91.9 | 81.6 | 71.1 | 79.7 | 69.4 | 59.9 | 64.4 | 51.5 | 40 | 55.4 | 43.1 | 26.9 | 51.9 | 33.6 | 23.5
18 | 2 | 2
18 | 2 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 2 | 6 | 13.2 | 4.7 | 2.1 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.2 | 12 | 16.2 | 9.3 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 2 | 8 | 29.9 | 18.7 | 9.2 | 34.1 | 23.4 | 12.8 | 41.7 | 29.6 | 19.2 | 53.5 | 41.8 | 34.1 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 51.9 | 41.5 | 58.4 | 50 | 38.3 | 49.6 | 40.7 | 29.7 | 33.5 | 25.5 | 14 | 27.5 | 19.4 | 10.4 | 31.2 | 18.7 | 7.8
18 | 2 | 9 | 39.7 | 25.1 | 14.5 | 43.2 | 33.8 | 17.2 | 50.3 | 40.1 | 30.6 | 62.6 | 53.3 | 46.6 | 64.6 | 55.2 | 45.5 | 75.9 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 60.6 | 50.5 | 61.2 | 48.5 | 40.2 | 44.1 | 31.6 | 23.3 | 39.2 | 28.2 | 18.1 | 37.7 | 24.9 | 12.8
18 | 2 | 10 | 46.4 | 32.4 | 18.9 | 54.9 | 42.1 | 26 | 63.1 | 50.4 | 38.5 | 72.3 | 62.2 | 56.8 | 77 | 66.5 | 57.6 | 85.5 | 77.1 | 68.7 | 84.3 | 77.2 | 66 | 82.4 | 71.5 | 60.5 | 69.7 | 59.9 | 51.5 | 51.6 | 41.4 | 32.1 | 46.6 | 36.7 | 20.2 | 45.5 | 30.8 | 15.2
18 | 2 | 11 | 52.4 | 36.8 | 22.2 | 62.1 | 53.9 | 27.9 | 72.2 | 57.8 | 45.8 | 84.4 | 70.7 | 65 | 84.2 | 77.7 | 68.9 | 91.6 | 86 | 76.9 | 93.6 | 86.6 | 77 | 88.9 | 78.6 | 69.5 | 78.3 | 67.9 | 58.9 | 61.2 | 50 | 37.8 | 54.1 | 45.6 | 29.6 | 54.4 | 37.1 | 26.2
18 | 2 | 12 | 56.9 | 39.4 | 31.2 | 68 | 58.2 | 31.2 | 78.1 | 66.5 | 49.2 | 86.6 | 76.5 | 67.8 | 89.5 | 84.9 | 78.2 | 94.6 | 88.9 | 82.8 | 95.5 | 90.7 | 80.2 | 94.1 | 83.2 | 76.8 | 82.3 | 72.1 | 64.3 | 69.1 | 55.9 | 43.1 | 60.7 | 49.7 | 32.7 | 56.7 | 41.7 | 27.6
18 | 2 | 15 | 59.9 | 43.7 | 36.1 | 73.9 | 62.4 | 36.9 | 80.4 | 69 | 54.9 | 90.3 | 80.4 | 69.5 | 92.9 | 86.7 | 81.2 | 95 | 90.3 | 86.2 | 98.1 | 92.1 | 84.9 | 94.2 | 83.2 | 78.2 | 84.4 | 76.7 | 67.3 | 74.1 | 59.8 | 50.9 | 65.3 | 51.5 | 38.6 | 61.4 | 42.6 | 29.1
18 | 2 | 20 | 59.9 | 43.7 | 36.1 | 73.9 | 62.4 | 36.9 | 80.4 | 69 | 54.9 | 90.3 | 80.4 | 69.5 | 92.9 | 86.7 | 81.2 | 95 | 90.3 | 86.2 | 98.1 | 91.9 | 84.9 | 94.2 | 83.2 | 78.2 | 84.4 | 76.7 | 67.3 | 74.1 | 59.8 | 51 | 65.3 | 51.5 | 38.7 | 61.4 | 42.6 | 29.1
18 | 2 | 25 | 59.9 | 43.7 | 36.1 | 73.9 | 62.4 | 36.9 | 80.4 | 69 | 54.9 | 90.3 | 80.4 | 69.5 | 92.9 | 86.7 | 81.2 | 95 | 90.3 | 86.2 | 98.1 | 91.9 | 84.9 | 94.2 | 83.2 | 78.2 | 84.4 | 76.7 | 67.3 | 74.1 | 59.8 | 51 | 65.3 | 51.5 | 38.7 | 61.4 | 42.6 | 29.1
18 | 2.25 | 2
18 | 2.25 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 2.25 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 2.25 | 8 | 30.7 | 18.7 | 9.3 | 34.1 | 23.4 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.1 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50.1 | 40.7 | 29.7 | 33.5 | 25.5 | 14.3 | 28.7 | 19.4 | 10.4 | 31.2 | 19 | 8.8
18 | 2.25 | 9 | 39.7 | 26.7 | 15.2 | 43.2 | 33.8 | 18.4 | 51.8 | 40.3 | 32.7 | 62.6 | 54.2 | 46.6 | 64.6 | 56.2 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.7 | 39.2 | 28.2 | 18.1 | 37.7 | 28.2 | 14.3
18 | 2.25 | 10 | 48.1 | 32.4 | 19.5 | 54.9 | 44.6 | 26 | 63.1 | 50.4 | 38.7 | 72.9 | 64.4 | 56.9 | 77 | 66.5 | 58.9 | 86.3 | 77.1 | 68.7 | 84.3 | 77.2 | 66 | 82.6 | 74.2 | 60.5 | 70.6 | 59.9 | 51.7 | 52.4 | 41.4 | 32.3 | 48.5 | 38.2 | 20.2 | 46.4 | 33.1 | 18.7
18 | 2.25 | 11 | 55.5 | 37.6 | 24.5 | 64.4 | 54.2 | 28.9 | 73.4 | 62.8 | 47.7 | 84.4 | 72.6 | 67.7 | 84.5 | 77.8 | 69.9 | 92 | 86.1 | 78.2 | 93.6 | 86.8 | 77.7 | 90.2 | 80 | 70.6 | 78.7 | 69 | 60.2 | 62.5 | 50.1 | 39 | 56.7 | 45.6 | 31 | 55.1 | 39 | 28
18 | 2.25 | 12 | 60.8 | 45.6 | 33.9 | 70.9 | 63.1 | 36.8 | 78.8 | 69.6 | 52.9 | 89.6 | 79.4 | 73.6 | 90.6 | 85.9 | 81.2 | 95 | 89.6 | 86.1 | 95.8 | 91.9 | 82.9 | 95.8 | 84.4 | 78.8 | 83.5 | 76.7 | 68.9 | 71 | 58.9 | 45.6 | 65.8 | 53.3 | 35.4 | 62.1 | 44.1 | 33.5
18 | 2.25 | 15 | 68.7 | 53.6 | 41.8 | 80.8 | 69 | 46.7 | 87.5 | 76.2 | 61.1 | 93.3 | 87.8 | 78.7 | 94.9 | 92.3 | 88.8 | 98.2 | 93.3 | 89.6 | 99.8 | 96.1 | 90.1 | 97.7 | 89.9 | 83.9 | 90.7 | 84.2 | 73.1 | 80 | 69.2 | 61.3 | 76.1 | 60.8 | 44.5 | 72.1 | 53.4 | 40.3
18 | 2.25 | 20 | 69.3 | 53.8 | 41.8 | 80.8 | 69 | 46.7 | 87.5 | 76.1 | 61.8 | 93.3 | 87.9 | 78.7 | 95.3 | 92.3 | 88.8 | 98.2 | 93.3 | 89.6 | 99.8 | 96.1 | 90.1 | 97.7 | 89.9 | 83.9 | 90.7 | 84.2 | 73.1 | 79.9 | 69.9 | 62.6 | 76.2 | 60.8 | 45.9 | 72.1 | 53.4 | 40.3
18 | 2.25 | 25 | 69.3 | 53.8 | 41.8 | 80.8 | 69 | 46.7 | 87.5 | 76.1 | 61.8 | 93.3 | 87.9 | 78.7 | 95.3 | 92.3 | 88.8 | 98.2 | 93.3 | 89.6 | 99.8 | 96.1 | 90.1 | 97.7 | 89.9 | 83.9 | 90.7 | 84.2 | 73.1 | 79.9 | 69.9 | 62.6 | 76.2 | 60.8 | 45.9 | 72.1 | 53.4 | 40.3
18 | 2.75 | 2
18 | 2.75 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 2.75 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 2.75 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 2.75 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 40.3 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 2.75 | 10 | 48.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.3 | 73.4 | 64.7 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 78.6 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.1 | 49.9 | 38.2 | 22 | 48.7 | 33.1 | 20.9
18 | 2.75 | 11 | 57.9 | 39.4 | 25.4 | 65 | 54.2 | 31.3 | 73.4 | 62.8 | 49.9 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 86.8 | 79.4 | 90.2 | 81.3 | 70.6 | 80.4 | 69 | 61.2 | 62.5 | 53.8 | 41.2 | 57.5 | 47.2 | 31 | 57.2 | 41.9 | 30.1
18 | 2.75 | 12 | 63.9 | 49.9 | 36.1 | 71.4 | 65.2 | 41.6 | 79.6 | 71.2 | 56.1 | 90.7 | 82.8 | 76.6 | 91.9 | 87.6 | 82.6 | 95.3 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.4 | 78.8 | 86.3 | 79.3 | 70.4 | 72.2 | 61 | 48.9 | 67.7 | 55.8 | 38.6 | 65.7 | 49.6 | 37.7
18 | 2.75 | 15 | 79.9 | 64.2 | 53.6 | 87.7 | 79.7 | 61.9 | 90.7 | 83.7 | 71.2 | 96.9 | 94.2 | 87.7 | 99.3 | 97.4 | 93.8 | 100 | 96.4 | 94.1 | 100 | 98 | 95.7 | 100 | 95.3 | 91.5 | 95 | 90 | 83.3 | 86.6 | 80.1 | 72.6 | 84.4 | 74.6 | 58.2 | 80.1 | 64.8 | 53.6
18 | 2.75 | 20 | 84.6 | 68 | 56.7 | 88.7 | 80.1 | 62.1 | 93.4 | 84.8 | 72.4 | 98.6 | 94.4 | 88 | 100 | 97.7 | 94.9 | 100 | 97.2 | 94.9 | 100 | 98.3 | 95.7 | 100 | 96.6 | 92.7 | 96.1 | 91.8 | 84.9 | 90.3 | 81.5 | 73.3 | 85 | 75.4 | 61.4 | 81.4 | 68.4 | 56.6
18 | 2.75 | 25 | 84.6 | 68 | 56.7 | 88.7 | 80.1 | 62.1 | 93.4 | 84.8 | 72.4 | 98.6 | 94.4 | 88 | 100 | 97.7 | 95.3 | 100 | 97.2 | 94.9 | 100 | 98.3 | 95.7 | 100 | 96.6 | 92.7 | 96.1 | 91.8 | 84.9 | 90.3 | 81.5 | 73.3 | 85 | 75.4 | 61.4 | 81.4 | 68.4 | 56.6
18 | 3 | 2
18 | 3 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 3 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 3 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 3 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 41.9 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 3 | 10 | 49.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.3 | 73.4 | 65 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 79.2 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.4 | 49.9 | 38.2 | 22.8 | 49.2 | 33.2 | 20.9
18 | 3 | 11 | 59.3 | 40.1 | 25.4 | 65.1 | 54.2 | 32.3 | 73.4 | 62.8 | 49.9 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 86.8 | 79.4 | 90.2 | 81.3 | 70.6 | 80.4 | 69 | 61.2 | 63.7 | 53.8 | 41.2 | 57.5 | 49.2 | 32.4 | 57.9 | 41.9 | 30.1
18 | 3 | 12 | 63.9 | 49.9 | 36.1 | 71.8 | 66.1 | 41.6 | 82.8 | 72.3 | 56.1 | 90.7 | 82.4 | 77.6 | 92.2 | 88 | 82.6 | 96.3 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.4 | 78.8 | 86.3 | 79.3 | 70.6 | 72.3 | 61.3 | 49.7 | 67.7 | 58.1 | 38.6 | 65.7 | 49.6 | 37.7
18 | 3 | 15 | 81.3 | 67.3 | 57.9 | 88 | 82.1 | 64.7 | 92.9 | 84.5 | 75.8 | 97.8 | 94 | 88.5 | 99.8 | 97.8 | 95.1 | 100 | 96.7 | 94.5 | 100 | 98.5 | 96.2 | 100 | 96.8 | 92 | 96.8 | 91.3 | 85.5 | 89.2 | 80.6 | 75.1 | 85.7 | 77.6 | 62.3 | 82.5 | 68 | 54.6
18 | 3 | 20 | 87.1 | 72.4 | 61.5 | 93.6 | 85.1 | 71 | 95.7 | 88.4 | 81.5 | 100 | 95.4 | 91.2 | 100 | 100 | 97.1 | 100 | 98.2 | 96.2 | 100 | 100 | 95.9 | 100 | 97.8 | 95.3 | 97.3 | 95.1 | 88 | 92.3 | 85.5 | 79.7 | 89.3 | 81.1 | 66.9 | 85.3 | 73.8 | 64.2
18 | 3 | 25 | 87.1 | 72.4 | 61.5 | 93.6 | 85.1 | 71 | 95.7 | 88.4 | 81.5 | 100 | 95.4 | 91.2 | 100 | 100 | 97.1 | 100 | 98.2 | 96.2 | 100 | 100 | 95.9 | 100 | 97.8 | 95.3 | 97.3 | 95.1 | 88 | 92.3 | 85.5 | 79.7 | 89.3 | 81.1 | 66.9 | 85.3 | 73.8 | 64.2
18 | 3.5 | 2
18 | 3.5 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 3.5 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 3.5 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 3.5 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 41.9 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 3.5 | 10 | 49.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.3 | 73.4 | 65 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 79.2 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.4 | 49.9 | 38.2 | 22.7 | 49.2 | 33.2 | 20.9
18 | 3.5 | 11 | 59.3 | 40.1 | 25.4 | 65.1 | 54.2 | 32.3 | 73.4 | 62.8 | 50.5 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 87.2 | 79.4 | 90.2 | 81.9 | 70.6 | 80.4 | 69 | 61.2 | 63.7 | 53.8 | 41.2 | 58.2 | 49.6 | 32.4 | 57.8 | 41.9 | 30.1
18 | 3.5 | 12 | 63.9 | 49.9 | 36.1 | 72.2 | 66.1 | 41.6 | 82.8 | 73 | 56.1 | 90.7 | 82.8 | 77.6 | 92.2 | 88 | 82.6 | 96.5 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.8 | 78.8 | 86.3 | 79.3 | 70.9 | 72.3 | 61.4 | 49.7 | 67.7 | 60.1 | 40.1 | 66.8 | 49.6 | 37.7
18 | 3.5 | 15 | 82.7 | 69.2 | 58.1 | 89.9 | 84.9 | 67.7 | 93.5 | 86.3 | 77.8 | 99 | 94.9 | 89.6 | 100 | 98.1 | 95.9 | 100 | 97.6 | 95.9 | 100 | 100 | 96.4 | 100 | 97.8 | 92.8 | 97.2 | 92.2 | 86.8 | 90.3 | 81.2 | 76.9 | 88.6 | 77.8 | 67 | 85 | 69.5 | 55.8
18 | 3.5 | 20 | 92.7 | 85.8 | 73.8 | 98.1 | 92.6 | 82.4 | 99.2 | 94.9 | 87.6 | 100 | 99.4 | 95.4 | 100 | 100 | 100 | 100 | 100 | 96.6 | 100 | 100 | 99 | 100 | 100 | 97.4 | 100 | 97.4 | 93.2 | 97 | 92.2 | 86.7 | 94.7 | 90.4 | 81 | 94.3 | 85.8 | 77.3
18 | 3.5 | 25 | 92.8 | 85.8 | 74.8 | 98.2 | 92.6 | 82.4 | 99.2 | 94.9 | 87.6 | 100 | 99.4 | 95.4 | 100 | 100 | 100 | 100 | 100 | 96.6 | 100 | 100 | 99 | 100 | 100 | 97.4 | 100 | 97.4 | 93.2 | 97 | 92.2 | 86.7 | 95 | 90.4 | 81 | 94.3 | 85.8 | 77.2
18 | 4 | 2
18 | 4 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 4 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 4 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 4 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 41.9 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 4 | 10 | 49.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.4 | 73.4 | 65 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 79.2 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.4 | 49.9 | 38.2 | 22.7 | 49.2 | 33.2 | 20.9
18 | 4 | 11 | 59.3 | 40.1 | 25.4 | 65.1 | 54.2 | 32.3 | 73.4 | 62.8 | 50.5 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 87.2 | 79.4 | 90.2 | 81.9 | 70.6 | 80.4 | 69 | 61.2 | 63.7 | 53.8 | 41.2 | 58.2 | 49.6 | 32.4 | 57.8 | 41.9 | 30.1
18 | 4 | 12 | 63.9 | 49.9 | 36.1 | 72.2 | 66.1 | 41.6 | 82.8 | 73 | 56.8 | 90.7 | 82.8 | 77.6 | 92.2 | 88 | 82.6 | 96.5 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.8 | 78.8 | 86.3 | 79.3 | 70.9 | 72.3 | 61.4 | 49.7 | 67.7 | 60.1 | 42.6 | 66.8 | 49.6 | 37.7
18 | 4 | 15 | 83.1 | 70.8 | 60.3 | 90.6 | 84.9 | 70.9 | 93.8 | 86.8 | 78.7 | 99.1 | 96.7 | 91.1 | 100 | 98.4 | 96.4 | 100 | 97.8 | 95.9 | 100 | 100 | 96.6 | 100 | 98.1 | 94.1 | 97.2 | 92.2 | 87.8 | 90.3 | 82.7 | 77.4 | 89.2 | 78.5 | 68.2 | 86 | 70.7 | 57.6
18 | 4 | 20 | 97.8 | 92.5 | 84.5 | 99.6 | 95.4 | 88.5 | 100 | 97 | 93.7 | 100 | 100 | 97.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99 | 95.4 | 100 | 97.2 | 92.4 | 98.6 | 95.4 | 90.9 | 99 | 92.2 | 84.5
18 | 4 | 25 | 98 | 92.5 | 85.4 | 99.8 | 95.2 | 89.1 | 100 | 97.6 | 94.4 | 100 | 100 | 97.2 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 95.3 | 100 | 97.3 | 92.6 | 98.8 | 95.4 | 91.2 | 99 | 93.4 | 87.2
18 | 4.5 | 2
18 | 4.5 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 4.5 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 4.5 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 4.5 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 41.9 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 4.5 | 10 | 49.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.4 | 73.4 | 65 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 79.2 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.4 | 49.9 | 38.2 | 22.7 | 49.2 | 33.2 | 20.9
18 | 4.5 | 11 | 59.3 | 40.1 | 25.4 | 65.1 | 54.2 | 32.3 | 73.4 | 62.8 | 50.5 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 87.2 | 79.4 | 90.2 | 81.9 | 70.6 | 80.4 | 69 | 61.2 | 63.7 | 53.8 | 41.2 | 58.2 | 49.6 | 32.4 | 57.8 | 41.9 | 30.1
18 | 4.5 | 12 | 63.9 | 49.9 | 36.1 | 72.2 | 66.1 | 41.6 | 82.8 | 73 | 56.8 | 90.7 | 82.8 | 77.6 | 92.2 | 88 | 82.6 | 96.5 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.8 | 78.8 | 86.3 | 79.3 | 70.9 | 72.3 | 61.4 | 49.7 | 67.7 | 60.1 | 42.6 | 66.8 | 49.6 | 37.7
18 | 4.5 | 15 | 84.1 | 70.8 | 60.3 | 90.6 | 86.2 | 72.1 | 93.8 | 86.8 | 80.1 | 99.1 | 96.7 | 92.3 | 100 | 98.4 | 96.4 | 100 | 97.8 | 95.9 | 100 | 100 | 96.6 | 100 | 98.1 | 94.1 | 97.2 | 92.2 | 88.1 | 90.3 | 82.7 | 77.4 | 89.7 | 80.1 | 68.9 | 86 | 71.4 | 58.8
18 | 4.5 | 20 | 99.2 | 94.9 | 89 | 100 | 96.1 | 91.5 | 100 | 98.1 | 96.5 | 100 | 100 | 97.4 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 96.7 | 100 | 98 | 95.2 | 100 | 97.5 | 93.6 | 100 | 96.6 | 89.3
18 | 4.5 | 25 | 100 | 96.6 | 92.4 | 100 | 98.4 | 91.6 | 100 | 100 | 98 | 100 | 100 | 97.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.3 | 100 | 99.2 | 96.1 | 100 | 98.2 | 94.8 | 100 | 98 | 93.1
18 | 5 | 2
18 | 5 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 5 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 5 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 5 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 41.9 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 5 | 10 | 49.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.4 | 73.4 | 65 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 79.2 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.4 | 49.9 | 38.2 | 22.7 | 49.2 | 33.2 | 20.9
18 | 5 | 11 | 59.3 | 40.1 | 25.4 | 65.1 | 54.2 | 32.3 | 73.4 | 62.8 | 50.5 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 87.2 | 79.4 | 90.2 | 81.9 | 70.6 | 80.4 | 69 | 61.2 | 63.7 | 53.8 | 41.2 | 58.2 | 49.6 | 32.4 | 57.8 | 41.9 | 30.1
18 | 5 | 12 | 63.9 | 49.9 | 36.1 | 72.2 | 66.1 | 41.6 | 82.8 | 73 | 56.8 | 90.7 | 82.8 | 77.6 | 92.2 | 88 | 82.6 | 96.5 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.8 | 78.8 | 86.3 | 79.3 | 70.9 | 72.3 | 61.4 | 49.7 | 67.7 | 60.1 | 42.6 | 66.8 | 49.6 | 37.7
18 | 5 | 15 | 84.1 | 70.8 | 60.3 | 90.6 | 86.2 | 73.4 | 93.8 | 86.8 | 80.1 | 99.1 | 96.7 | 92.3 | 100 | 98.4 | 96.4 | 100 | 97.8 | 95.9 | 100 | 100 | 96.6 | 100 | 98.1 | 94.1 | 97.2 | 92.2 | 88.1 | 90.3 | 82.7 | 77.4 | 89.7 | 80.8 | 68.9 | 86 | 71.4 | 58.8
18 | 5 | 20 | 100 | 95.6 | 90.1 | 100 | 98.1 | 92.7 | 100 | 99.3 | 96.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98 | 100 | 98.1 | 95.6 | 100 | 97.8 | 95.3 | 100 | 97.2 | 91
18 | 5 | 25 | 100 | 99.5 | 95.3 | 100 | 100 | 95.8 | 100 | 100 | 99.4 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.2 | 100 | 100 | 97.5 | 100 | 100 | 96.3
24 | 0.25 | 2
24 | 0.25 | 4
24 | 0.25 | 6 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 8 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 9 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 10 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 11 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 12 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 15 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 20 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 25 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.5 | 2
24 | 0.5 | 4 | [9 empty] | 3.2 |  |  | 3.2 |  |  | 5.5 |  |  | 6.3 | 0.1 |  | 4.5 | 3.1 |  | 3.2
24 | 0.5 | 6 | 3 |  |  | 2.4 |  |  | 3.2 |  |  | 7.5 | 3.2 | 0.3 | 9.4 | 3.1 |  | 12.6 | 6.4 | 3.2 | 15.6 | 6.3 | 3.1 | 15.5 | 7.5 | 3.1 | 8.4 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 8 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.4 | 6.3 | 3.1 | 16.6 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 4 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 9 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 4 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 10 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 4 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 11 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 6.2 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 12 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 6.2 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 15 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 6.2 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 20 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 6.2 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 25 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 6.2 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.75 | 2
24 | 0.75 | 4 |  |  |  | 3.4 |  |  | 2.2 |  |  | 3.2 |  |  | 5.5 |  |  | 6.5 | 3.2 |  | 6.3 | 3.1 |  | 6.3 | 3.1 |  | 3.2 | 3.2 | [7 empty] | 3.1
24 | 0.75 | 6 | 5.5 |  |  | 10.1 | 3.4 |  | 12.6 | 3.1 |  | 17.7 | 6.5 | 3.2 | 18 | 9.4 | 4.7 | 22.2 | 16.1 | 6.4 | 22.1 | 14.7 | 7.2 | 21.9 | 12.5 | 7.3 | 16.1 | 9.7 | 3.2 | 7.4 | 3.1 |  | 5.1 |  |  | 6.3 | 3.1
24 | 0.75 | 8 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 24.5 | 16.1 | 7.9 | 28.4 | 15.9 | 9.3 | 35.8 | 23.5 | 12.9 | 37.1 | 26.5 | 16.8 | 36.7 | 25.3 | 12.5 | 25.8 | 16.3 | 6.5 | 11.9 | 6 | 1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 9 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 7.9 | 29.4 | 18.4 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.8 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 10 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 11 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19.1 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 12 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19.1 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 15 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19.1 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 20 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19.1 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 25 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19.1 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 1 | 2
24 | 1 | 4 |  |  |  | 3.4 |  |  | 3.2 |  |  | 6.4 | 3.2 |  | 6.3 |  |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 2.2 |  |  | 3.1
24 | 1 | 6 | 6.3 | 3.1 |  | 10.5 | 3.9 |  | 15 | 6.3 |  | 22.7 | 12.8 | 6.4 | 20.1 | 12.4 | 7.1 | 30.8 | 19.6 | 9.6 | 25.1 | 18.8 | 9.3 | 28.7 | 15.6 | 10 | 19.6 | 12.8 | 6.9 | 10.4 | 3.8 | 0.1 | 6.8 | 3.2 |  | 8.1 | 3.1
24 | 1 | 8 | 20.1 | 8.3 |  | 19.6 | 10.6 | 3.3 | 27.6 | 12.6 | 6.2 | 39.5 | 25.1 | 16.3 | 38.6 | 28.6 | 20.1 | 49.3 | 35.7 | 26.2 | 52.7 | 38 | 27.2 | 50.1 | 34.7 | 26.1 | 35.9 | 25.3 | 17.3 | 18.9 | 10.1 | 5.4 | 13.3 | 6.5 | 3.2 | 18.1 | 7.7
24 | 1 | 9 | 20.1 | 9.4 |  | 20.5 | 11.8 | 3.3 | 28.4 | 18.8 | 9.3 | 44.7 | 28.5 | 19.4 | 44.4 | 35.5 | 23.1 | 56.1 | 40.6 | 33.9 | 59.4 | 44.9 | 31 | 54.6 | 39.9 | 31.8 | 39.4 | 29.4 | 17.9 | 21.5 | 12.6 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 0.4
24 | 1 | 10 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.6 | 56.2 | 42.9 | 34.1 | 62.7 | 47.7 | 31.8 | 56.7 | 43.1 | 32.6 | 40.9 | 31.5 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1 | 11 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.7 | 56.2 | 42.9 | 34.1 | 62.6 | 47.7 | 33.4 | 56.8 | 43.1 | 34.7 | 40.9 | 31.9 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1 | 12 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.7 | 56.2 | 42.9 | 34.1 | 62.6 | 47.7 | 33.5 | 56.8 | 43.1 | 34.7 | 40.9 | 31.9 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1 | 15 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.7 | 56.2 | 42.9 | 34.1 | 62.6 | 47.7 | 33.5 | 56.8 | 43.1 | 34.7 | 40.9 | 31.9 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1 | 20 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.7 | 56.2 | 42.9 | 34.1 | 62.6 | 47.7 | 33.5 | 56.8 | 43.1 | 34.7 | 40.9 | 31.9 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1 | 25 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.7 | 56.2 | 42.9 | 34.1 | 62.6 | 47.7 | 33.5 | 56.8 | 43.1 | 34.7 | 40.9 | 31.9 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1.25 | 2
24 | 1.25 | 4 |  |  |  | 3.4 |  |  | 3.2 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 1.25 | 6 | 9.3 | 3.1 |  | 13 | 7 | 3.3 | 15.8 | 9.3 | 3.1 | 22.9 | 12.8 | 7.1 | 25.5 | 14.9 | 8.8 | 32.2 | 22.8 | 12.8 | 28.4 | 22 | 10.3 | 28.7 | 18.1 | 10 | 19.6 | 13.2 | 8.3 | 12.5 | 6.2 | 2.7 | 9.7 | 3.3 | 1.3 | 10.3 | 3.1
24 | 1.25 | 8 | 23 | 11.3 | 3.1 | 24.6 | 17.3 | 7.9 | 32.2 | 19.1 | 10.1 | 42.6 | 30 | 22.7 | 44.9 | 33.6 | 26.3 | 54 | 42.4 | 30.9 | 55.9 | 44.4 | 31.6 | 53 | 41 | 32.1 | 42.5 | 29.6 | 20.5 | 25.2 | 13.2 | 9.3 | 19.6 | 12.2 | 6.4 | 24.4 | 9.4 | 3.1
24 | 1.25 | 9 | 27 | 14.2 | 3.1 | 31.8 | 21 | 10.4 | 37.5 | 28.4 | 15.8 | 53.8 | 38.8 | 29.3 | 54.9 | 45 | 36.6 | 65.8 | 52.2 | 42.8 | 68.2 | 57.4 | 42 | 66.5 | 50.7 | 40.3 | 52.4 | 39.4 | 29.3 | 34.3 | 18.8 | 10.4 | 25.5 | 16.1 | 7.2 | 28.5 | 12.6 | 4.6
24 | 1.25 | 10 | 29.3 | 15.7 | 3.1 | 34.6 | 23.4 | 11.5 | 41.7 | 31.3 | 19 | 58.8 | 42.4 | 35.7 | 61.5 | 51.6 | 42.2 | 70.6 | 59.6 | 49.3 | 74.9 | 60.9 | 47.6 | 70 | 58.5 | 47.7 | 54.8 | 43.6 | 33 | 36.8 | 25.3 | 13.8 | 26.3 | 17.5 | 7.2 | 28.8 | 14.8 | 7.1
24 | 1.25 | 11 | 29.3 | 16.4 | 3.1 | 35.8 | 23.4 | 11.5 | 41.7 | 31.9 | 19 | 62.8 | 44.7 | 36 | 62.6 | 53.4 | 46.9 | 72.8 | 59.6 | 49.5 | 75.8 | 64.4 | 51.1 | 71.4 | 60.5 | 48.7 | 57.5 | 45.7 | 33 | 38.1 | 25.5 | 13.9 | 26.3 | 18.5 | 7.2 | 31 | 14.8 | 7.1
24 | 1.25 | 12 | 29.3 | 16.4 | 3.1 | 35.8 | 23.4 | 11.5 | 42.2 | 31.9 | 19 | 62.8 | 44.7 | 36 | 62.6 | 53.4 | 47.3 | 73.2 | 59.6 | 49.6 | 76.1 | 64.5 | 52.7 | 71.4 | 60.5 | 48.8 | 57.5 | 45.7 | 33 | 38.1 | 25.7 | 13.9 | 26.3 | 18.5 | 7.2 | 31 | 14.8 | 7.1
24 | 1.25 | 15 | 29.3 | 16.4 | 3.1 | 35.8 | 23.4 | 11.5 | 42.2 | 31.9 | 19 | 62.8 | 44.7 | 36 | 62.6 | 53.6 | 47.3 | 73.2 | 59.6 | 49.6 | 76.1 | 64.5 | 52.9 | 71.4 | 60.5 | 48.8 | 57.5 | 45.7 | 33 | 38.1 | 25.7 | 13.9 | 26.3 | 18.5 | 7.2 | 31 | 14.8 | 7.1
24 | 1.25 | 20 | 29.3 | 16.4 | 3.1 | 35.8 | 23.4 | 11.5 | 42.2 | 31.9 | 19 | 62.8 | 44.7 | 36 | 62.6 | 53.6 | 47.3 | 73.2 | 59.6 | 49.6 | 76.1 | 64.5 | 52.9 | 71.4 | 60.5 | 48.8 | 57.5 | 45.7 | 33 | 38.1 | 25.7 | 13.9 | 26.3 | 18.5 | 7.2 | 31 | 14.8 | 7.1
24 | 1.25 | 25 | 29.3 | 16.4 | 3.1 | 35.8 | 23.4 | 11.5 | 42.2 | 31.9 | 19 | 62.8 | 44.7 | 36 | 62.6 | 53.6 | 47.3 | 73.2 | 59.6 | 49.6 | 76.1 | 64.5 | 52.9 | 71.4 | 60.5 | 48.8 | 57.5 | 45.7 | 33 | 38.1 | 25.7 | 13.9 | 26.3 | 18.5 | 7.2 | 31 | 14.8 | 7.1
24 | 1.5 | 2
24 | 1.5 | 4 | 2.2 |  |  | 4.6 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.2
24 | 1.5 | 6 | 9.3 | 3.1 |  | 13.5 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 13.1 | 9.6 | 25.5 | 15.7 | 9.3 | 32.4 | 22.9 | 12.8 | 28.4 | 22 | 10.3 | 28.7 | 18.5 | 11.3 | 19.7 | 13.2 | 8.3 | 12.6 | 6.9 | 3.1 | 9.7 | 6.4 | 1.3 | 11.2 | 5.1
24 | 1.5 | 8 | 23 | 12.5 | 5.8 | 30 | 20 | 8.7 | 34.8 | 21.9 | 11.5 | 46.1 | 34.7 | 25.6 | 48.3 | 38.3 | 27.7 | 57.7 | 48.9 | 33.9 | 60.3 | 47.3 | 32.8 | 55.5 | 44.4 | 34 | 45.7 | 32.6 | 26 | 27.2 | 16.3 | 9.4 | 22.8 | 14 | 8.9 | 27.5 | 12.6 | 3.1
24 | 1.5 | 9 | 29.9 | 19.1 | 6.2 | 36.1 | 25.9 | 11.2 | 44.6 | 33.3 | 19 | 56.1 | 45.1 | 35.5 | 58.3 | 51.6 | 39.1 | 71.6 | 57.2 | 48 | 71.5 | 60.1 | 49.6 | 66.6 | 54.3 | 41.9 | 54.3 | 43.5 | 33.4 | 37.2 | 22 | 16.5 | 28.5 | 19.7 | 12 | 32.6 | 18.8 | 6.4
24 | 1.5 | 10 | 36 | 22.6 | 9.6 | 42.2 | 28.1 | 17.2 | 50.9 | 38 | 28.7 | 62.8 | 51.7 | 44.7 | 69.9 | 58.1 | 48.8 | 78.6 | 72.5 | 60.4 | 77.8 | 72.6 | 56.2 | 77.8 | 66.9 | 53.5 | 61.4 | 50.8 | 40.5 | 40.7 | 31.2 | 20 | 35.6 | 22.9 | 13.3 | 35.8 | 22 | 10.4
24 | 1.5 | 11 | 37.4 | 24.3 | 9.6 | 44.4 | 35 | 17.9 | 54 | 44 | 32.1 | 71.3 | 57.6 | 48.5 | 75 | 64.2 | 56.6 | 81.7 | 76.1 | 61.4 | 84.1 | 77.2 | 62.4 | 80.3 | 71.4 | 57.7 | 68.2 | 55.3 | 44.3 | 47.1 | 36 | 22.5 | 41.4 | 26.7 | 16.3 | 38.5 | 22.6 | 12.6
24 | 1.5 | 12 | 38.7 | 24.3 | 9.7 | 48.3 | 35 | 19.5 | 57.2 | 44.4 | 31.9 | 72.4 | 59.7 | 48.8 | 77.1 | 66.9 | 60.2 | 83.1 | 76.4 | 65.1 | 85 | 79 | 63.1 | 81.7 | 73.1 | 60.7 | 68.3 | 57.8 | 44.4 | 47.9 | 36.3 | 24.7 | 42.1 | 26.7 | 16.3 | 41.4 | 22.6 | 12.9
24 | 1.5 | 15 | 38.6 | 24.3 | 9.7 | 48.3 | 35 | 19.5 | 57.2 | 44.4 | 33 | 74.8 | 60 | 48.7 | 77.1 | 66.9 | 60.8 | 83.3 | 77.5 | 65.4 | 85 | 79.7 | 64.9 | 81.7 | 73.1 | 60.8 | 68.7 | 57.6 | 44.4 | 48 | 36.3 | 24.7 | 42.1 | 26.7 | 16.3 | 41.4 | 23.7 | 12.9
24 | 1.5 | 20 | 38.6 | 24.3 | 9.7 | 48.3 | 35 | 19.5 | 57.2 | 44.4 | 33 | 74.8 | 60 | 48.7 | 77.1 | 66.9 | 60.8 | 83.3 | 77.5 | 65.4 | 85 | 79.7 | 64.9 | 81.7 | 73.1 | 60.9 | 68.7 | 57.6 | 44.4 | 48 | 36.3 | 24.7 | 42.1 | 26.7 | 16.3 | 41.4 | 23.7 | 12.9
24 | 1.5 | 25 | 38.6 | 24.3 | 9.7 | 48.3 | 35 | 19.5 | 57.2 | 44.4 | 33 | 74.8 | 60 | 48.7 | 77.1 | 66.9 | 60.8 | 83.3 | 77.5 | 65.4 | 85 | 79.7 | 64.9 | 81.7 | 73.1 | 60.9 | 68.7 | 57.6 | 44.4 | 48 | 36.3 | 24.7 | 42.1 | 26.7 | 16.3 | 41.4 | 23.7 | 12.9
24 | 1.75 | 2
24 | 1.75 | 4 | 3.1 |  |  | 4.6 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.2
24 | 1.75 | 6 | 11.3 | 3.2 |  | 14.2 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 15.7 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 12.4 | 5.9 | 0.1
24 | 1.75 | 8 | 25.8 | 12.6 | 5.8 | 29.9 | 20.8 | 10.5 | 35 | 25.1 | 12.6 | 49 | 36.3 | 27.7 | 50.1 | 38.6 | 29.6 | 57.7 | 48.8 | 36 | 60.3 | 47.6 | 33.2 | 55.9 | 44.4 | 34 | 45.7 | 32.6 | 26 | 27.8 | 18.8 | 12.4 | 22.8 | 16.1 | 9.6 | 28.5 | 15.7 | 4
24 | 1.75 | 9 | 33.9 | 22 | 9.3 | 37.4 | 25.9 | 13.7 | 48.1 | 35.9 | 25.1 | 60 | 46 | 39.3 | 59.1 | 52.8 | 41.8 | 72.8 | 61.9 | 49.2 | 71.5 | 63.3 | 51.4 | 68 | 55.1 | 44.2 | 57.8 | 44.2 | 34.4 | 37.2 | 27.6 | 19 | 32.6 | 24.6 | 13.1 | 34.3 | 19.1 | 9.5
24 | 1.75 | 10 | 42.5 | 28.9 | 13.8 | 47.6 | 33.8 | 20.5 | 57.6 | 44 | 34.6 | 69.5 | 56 | 48.7 | 72.5 | 60.3 | 54.8 | 81.3 | 73.9 | 65.4 | 80.3 | 73.5 | 62.3 | 80 | 67.5 | 56.5 | 64.6 | 55.8 | 43.5 | 47.5 | 33.1 | 24.2 | 41 | 29.3 | 18 | 41.8 | 25.4 | 13.6
24 | 1.75 | 11 | 48 | 30.8 | 19.2 | 56.2 | 43.3 | 24 | 65.6 | 50.5 | 38.5 | 78.8 | 63.5 | 55.7 | 81.2 | 71.2 | 61.8 | 88 | 80.3 | 70.6 | 90 | 81.7 | 71.4 | 84.4 | 77 | 64.8 | 75.4 | 60.3 | 47.8 | 55.5 | 46.1 | 29.7 | 45.5 | 34.9 | 20.4 | 49.7 | 28.6 | 16.7
24 | 1.75 | 12 | 50 | 32.9 | 22.3 | 61 | 49.1 | 25.9 | 72.1 | 53.5 | 39.9 | 83.8 | 70.7 | 59 | 85.7 | 77 | 69.6 | 89.6 | 84.4 | 74.3 | 93 | 84.3 | 76.3 | 89.6 | 79 | 69.9 | 76.4 | 66 | 54.5 | 61.2 | 47.4 | 36.9 | 52.7 | 37.9 | 21.4 | 50.2 | 31.7 | 19.9
24 | 1.75 | 15 | 50 | 32.5 | 22.6 | 60.8 | 49.7 | 25.9 | 72.1 | 54.3 | 40.8 | 84.1 | 70.8 | 61.7 | 86.5 | 79.7 | 70.2 | 90.4 | 85 | 76.4 | 93.4 | 85.1 | 78.4 | 89 | 79 | 69.7 | 77.4 | 65.3 | 56.4 | 61.9 | 50 | 38.2 | 54.2 | 40.6 | 23.5 | 50.3 | 31.7 | 22.2
24 | 1.75 | 20 | 50 | 32.5 | 22.6 | 60.8 | 49.7 | 25.9 | 72.1 | 54.3 | 40.8 | 84.1 | 70.8 | 61.7 | 86.5 | 79.7 | 70.2 | 90.4 | 85 | 76.4 | 93.4 | 85.1 | 78.4 | 89 | 79 | 69.7 | 77.4 | 65.3 | 56.4 | 61.9 | 49.9 | 38.2 | 54.2 | 40.6 | 23.5 | 50.3 | 31.7 | 22.2
24 | 1.75 | 25 | 50 | 32.5 | 22.6 | 60.8 | 49.7 | 25.9 | 72.1 | 54.3 | 40.8 | 84.1 | 70.8 | 61.7 | 86.5 | 79.7 | 70.2 | 90.4 | 85 | 76.4 | 93.4 | 85.1 | 78.4 | 89 | 79 | 69.7 | 77.4 | 65.3 | 56.4 | 61.9 | 49.9 | 38.2 | 54.2 | 40.6 | 23.5 | 50.3 | 31.7 | 22.2
24 | 2 | 2
24 | 2 | 4 | 3.1 |  |  | 4.6 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 2 | 6 | 11.3 | 3.2 |  | 14.2 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 12.4 | 5.9 | 0.1
24 | 2 | 8 | 25.8 | 12.6 | 6.2 | 31.5 | 20.8 | 10.5 | 35 | 26.3 | 13.7 | 49 | 38.9 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.6 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 33.8 | 26 | 30 | 18.8 | 12.5 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.2
24 | 2 | 9 | 35.7 | 22.6 | 9.3 | 38.9 | 25.9 | 16 | 48 | 37.4 | 25.7 | 62 | 49 | 39.8 | 60.8 | 53.8 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.1 | 45.3 | 59.2 | 45.8 | 34.4 | 40.4 | 28.1 | 19.8 | 34.4 | 24.6 | 16.4 | 34.3 | 19.1 | 9.5
24 | 2 | 10 | 43 | 28.9 | 18.9 | 48 | 37.4 | 20.5 | 60 | 46.4 | 34.6 | 69.7 | 59.3 | 52.8 | 74.9 | 61.7 | 56.1 | 83 | 76.5 | 65.9 | 82.1 | 74.5 | 64.5 | 80.6 | 68 | 57.8 | 68.1 | 56.1 | 47.2 | 47.7 | 37.9 | 27.2 | 41.9 | 31 | 19.5 | 44.1 | 26.1 | 13.6
24 | 2 | 11 | 53.5 | 32.9 | 21.8 | 58 | 49.1 | 26.7 | 70.1 | 55.9 | 44.2 | 79.4 | 68.2 | 62.2 | 82.1 | 74.6 | 67 | 90.5 | 81.7 | 75.6 | 92.3 | 84.1 | 75.4 | 87.6 | 77 | 65.8 | 77.5 | 64.7 | 52.7 | 59 | 47.6 | 34.4 | 52.7 | 40.8 | 25.9 | 50.8 | 31.7 | 17.9
24 | 2 | 12 | 55.2 | 36.3 | 27.1 | 67.1 | 54.5 | 28.3 | 76.5 | 60.8 | 45.1 | 87.6 | 74 | 67.1 | 88.6 | 82.5 | 75.2 | 93.4 | 87.5 | 80.2 | 94 | 89.8 | 79.7 | 90.8 | 81.2 | 73.5 | 82.6 | 68.1 | 59.7 | 63 | 50.9 | 41.7 | 59.5 | 44.9 | 30.3 | 56.7 | 38.3 | 24.7
24 | 2 | 15 | 60.1 | 38.4 | 31 | 71.2 | 58.3 | 28.4 | 79.4 | 67.2 | 50.4 | 89 | 80.8 | 68.5 | 90.9 | 85.9 | 79.9 | 94.2 | 90 | 85.1 | 97.2 | 91.4 | 83.1 | 93 | 83.2 | 77.6 | 83.3 | 75.6 | 65.6 | 71.5 | 59.7 | 48.5 | 64.1 | 50.4 | 34.2 | 59.7 | 41.1 | 26.2
24 | 2 | 20 | 60.1 | 38.4 | 31 | 71.2 | 58.3 | 28.4 | 79.4 | 67.2 | 50.4 | 89 | 80.8 | 68.5 | 90.9 | 85.9 | 79.9 | 94.2 | 90 | 85.1 | 97.2 | 91.4 | 83.1 | 93 | 83.2 | 77.6 | 83.6 | 75.6 | 65.6 | 71.5 | 59.7 | 48.5 | 64.1 | 50.4 | 34.2 | 59.7 | 41.1 | 26.2
24 | 2 | 25 | 60.1 | 38.4 | 31 | 71.2 | 58.3 | 28.4 | 79.4 | 67.2 | 50.4 | 89 | 80.8 | 68.5 | 90.9 | 85.9 | 79.9 | 94.2 | 90 | 85.1 | 97.2 | 91.4 | 83.1 | 93 | 83.2 | 77.6 | 83.6 | 75.6 | 65.6 | 71.5 | 59.7 | 48.5 | 64.1 | 50.4 | 34.2 | 59.7 | 41.1 | 26.2
24 | 2.25 | 2
24 | 2.25 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 2.25 | 6 | 11.3 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 12.7 | 5.9 | 0.1
24 | 2.25 | 8 | 26.1 | 12.6 | 6.2 | 31.5 | 20.8 | 10.5 | 35 | 26.3 | 13.7 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.6 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.2
24 | 2.25 | 9 | 36.1 | 22.8 | 10.2 | 39 | 27.8 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.1 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.1 | 24.6 | 16.3 | 34.7 | 19.1 | 9.5
24 | 2.25 | 10 | 45 | 28.9 | 18.9 | 48 | 37.4 | 21.5 | 60 | 46.4 | 36 | 69.7 | 62.5 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.5 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 68 | 57.8 | 69.7 | 59 | 47.1 | 47.9 | 37.9 | 28.6 | 42.2 | 34.3 | 19.5 | 44.7 | 28.5 | 15.7
24 | 2.25 | 11 | 53.6 | 34.9 | 23.4 | 59.5 | 49.4 | 26.6 | 70.1 | 56 | 44.2 | 80.5 | 70.4 | 63 | 82.4 | 75.5 | 68.3 | 91.2 | 83.9 | 76.1 | 92.3 | 84.3 | 78.4 | 88.2 | 78.1 | 67.7 | 78.2 | 65.8 | 55.6 | 60 | 47.6 | 36.7 | 54 | 41.4 | 26 | 53.9 | 33.2 | 17.9
24 | 2.25 | 12 | 59.8 | 39.8 | 30.7 | 69.1 | 57 | 33.6 | 78.5 | 65.3 | 48.1 | 88.6 | 77.4 | 70.1 | 89.4 | 83.3 | 78.5 | 93.7 | 88.8 | 83.6 | 94.9 | 90.5 | 80.1 | 93.9 | 84.1 | 76.8 | 83.7 | 73.2 | 64.2 | 66.3 | 54.4 | 42.8 | 62.8 | 49.2 | 31.6 | 60.5 | 41 | 28.8
24 | 2.25 | 15 | 67.3 | 48.3 | 38.9 | 77.5 | 65.9 | 39.7 | 85.9 | 73.1 | 60.1 | 93.3 | 86.3 | 77.3 | 94.1 | 90.2 | 84.9 | 98 | 92.5 | 89.3 | 99.8 | 94.9 | 88.8 | 97.3 | 89.4 | 83 | 89.9 | 82.1 | 74.7 | 75.7 | 65.6 | 57.6 | 74.3 | 57.5 | 43.2 | 67.2 | 49.3 | 32.9
24 | 2.25 | 20 | 67.8 | 49.7 | 38.9 | 78 | 65.9 | 39.7 | 85.9 | 73.1 | 60.1 | 93.3 | 86.3 | 77.3 | 94.1 | 90.2 | 84.9 | 98 | 92.5 | 89.3 | 99.8 | 94.9 | 88.8 | 97.3 | 89.2 | 82.9 | 89.9 | 82.5 | 74.7 | 75.5 | 65.6 | 59.2 | 74.6 | 57.5 | 43.5 | 67.2 | 49.3 | 32.9
24 | 2.25 | 25 | 67.8 | 49.7 | 38.9 | 78 | 65.9 | 39.7 | 85.9 | 73.1 | 60.1 | 93.3 | 86.3 | 77.3 | 94.1 | 90.2 | 84.9 | 98 | 92.5 | 89.3 | 99.8 | 94.9 | 88.8 | 97.3 | 89.2 | 82.9 | 89.9 | 82.5 | 74.7 | 75.5 | 65.6 | 59.2 | 74.6 | 57.5 | 43.5 | 67.2 | 49.3 | 32.9
24 | 2.75 | 2
24 | 2.75 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 2.75 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 2.75 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 2.75 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 28 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 2.75 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.7
24 | 2.75 | 11 | 57.4 | 36 | 24.6 | 61.4 | 49.6 | 29.2 | 70.1 | 57.4 | 44.4 | 82.8 | 72.8 | 63.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.4 | 45.8 | 26 | 54.4 | 35.3 | 21.6
24 | 2.75 | 12 | 63.3 | 43.8 | 33 | 69.3 | 60.9 | 35.4 | 79.4 | 68.1 | 50.3 | 89.6 | 79.7 | 72.8 | 90.4 | 86.2 | 78.6 | 94.7 | 89.7 | 84 | 95.3 | 92.2 | 82.6 | 93.9 | 87.1 | 77 | 82.9 | 74.7 | 66.2 | 68.1 | 57.4 | 46.3 | 64.2 | 52.5 | 37.6 | 62.9 | 44.1 | 33
24 | 2.75 | 15 | 77.3 | 60.8 | 50 | 84.8 | 79.6 | 55.3 | 90.9 | 82.1 | 68.4 | 96.7 | 92.8 | 85.6 | 99 | 96.6 | 92.4 | 100 | 96.1 | 93.7 | 100 | 98 | 95.3 | 100 | 95 | 90.4 | 94.1 | 88.5 | 79.2 | 84.8 | 76.6 | 68.9 | 82.1 | 74.4 | 55.8 | 77.8 | 63.6 | 47.4
24 | 2.75 | 20 | 83.2 | 64.4 | 53.6 | 87.6 | 79.8 | 60 | 93.1 | 82.7 | 70 | 98.6 | 93.9 | 86.5 | 100 | 97.3 | 94 | 100 | 98.1 | 94.9 | 100 | 98 | 95.5 | 100 | 96.2 | 91.7 | 95.7 | 91.5 | 84.3 | 89.1 | 80.4 | 73.1 | 83.2 | 74.7 | 58.3 | 81.1 | 65.1 | 52.7
24 | 2.75 | 25 | 83.2 | 64.4 | 53.6 | 87.6 | 79.8 | 60 | 93.1 | 82.7 | 70 | 98.6 | 93.9 | 86.5 | 100 | 97.3 | 94 | 100 | 98.1 | 94.9 | 100 | 98 | 95.5 | 100 | 96.2 | 91.7 | 95.7 | 91.5 | 84.3 | 89.1 | 80.4 | 73.1 | 83.2 | 74.7 | 58.3 | 81.1 | 65.1 | 52.7
24 | 3 | 2
24 | 3 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 3 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 3 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 3 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 28 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 3 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.9
24 | 3 | 11 | 57.4 | 36 | 24.6 | 61.8 | 49.6 | 29.2 | 70.1 | 57.4 | 45.3 | 82.8 | 72.8 | 63.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.5 | 45.8 | 26 | 54.4 | 37.9 | 21.5
24 | 3 | 12 | 63.3 | 43.5 | 33 | 71 | 60.9 | 35.4 | 79.4 | 68.4 | 50.3 | 89.6 | 79.7 | 73.3 | 90.8 | 86.2 | 78.9 | 94.9 | 89.7 | 84 | 95.7 | 92.2 | 82.6 | 93.9 | 87.1 | 77.7 | 83 | 74.7 | 66.2 | 68.1 | 58.3 | 46.4 | 65 | 53.5 | 37.6 | 64.2 | 44.1 | 33
24 | 3 | 15 | 78.9 | 64.2 | 51.4 | 85.4 | 81.1 | 59.2 | 91.5 | 84.8 | 72.2 | 97.8 | 93.3 | 88.3 | 99.9 | 97.3 | 93.3 | 100 | 96.7 | 93.9 | 100 | 98.5 | 95.3 | 100 | 96.1 | 91.8 | 95.6 | 90.3 | 81.4 | 88.2 | 77.6 | 71.8 | 83.9 | 74.4 | 59.7 | 79.5 | 65.1 | 50.7
24 | 3 | 20 | 87 | 71 | 60 | 92.2 | 83.9 | 70.5 | 94.6 | 88.4 | 78.8 | 100 | 95.1 | 89.4 | 100 | 100 | 95.9 | 100 | 98.2 | 95.6 | 100 | 100 | 96 | 100 | 98 | 94.7 | 96.3 | 93.8 | 87.3 | 91.7 | 85.6 | 77.9 | 88.2 | 81 | 65.5 | 83.1 | 71 | 61.1
24 | 3 | 25 | 87 | 71 | 60 | 92.2 | 83.9 | 70.5 | 94.6 | 88.4 | 78.8 | 100 | 95.1 | 89.4 | 100 | 100 | 95.9 | 100 | 98.2 | 95.6 | 100 | 100 | 96 | 100 | 98 | 94.7 | 96.3 | 93.8 | 87.3 | 91.7 | 85.6 | 77.9 | 88.2 | 81 | 65.5 | 83.1 | 71 | 61.1
24 | 3.5 | 2
24 | 3.5 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 3.5 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 3.5 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 3.5 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 29.8 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 3.5 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.9
24 | 3.5 | 11 | 57.4 | 36 | 24.6 | 61.8 | 49.6 | 29.2 | 70.1 | 57.4 | 45.3 | 82.8 | 72.8 | 64.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.5 | 45.8 | 26 | 56.9 | 37.9 | 23.3
24 | 3.5 | 12 | 63.3 | 43.5 | 33 | 71 | 60.9 | 36.4 | 79.4 | 68.7 | 50.6 | 89.6 | 80.6 | 75 | 90.8 | 86.2 | 78.9 | 95.6 | 90.3 | 84 | 95.7 | 92.2 | 82.6 | 93.9 | 87.1 | 77.7 | 83 | 74.7 | 67.8 | 69.7 | 58.3 | 46.4 | 65 | 53.5 | 37.6 | 64.2 | 44.1 | 33
24 | 3.5 | 15 | 82.2 | 68.7 | 57.4 | 88.6 | 83.2 | 64.5 | 92.8 | 84.5 | 74.4 | 98.7 | 94.4 | 89.8 | 100 | 97.6 | 96 | 100 | 97.9 | 94.4 | 100 | 100 | 95.9 | 100 | 96.9 | 92.7 | 97 | 90.6 | 83.3 | 89.7 | 79.7 | 73 | 86.9 | 77.9 | 62.6 | 82 | 67.9 | 52.3
24 | 3.5 | 20 | 91.9 | 84.9 | 73 | 97.2 | 92 | 80.2 | 99.8 | 93.4 | 85.3 | 100 | 100 | 94.7 | 100 | 100 | 100 | 100 | 100 | 96.4 | 100 | 100 | 98.6 | 100 | 100 | 97.3 | 100 | 96.3 | 92.7 | 96.8 | 90.7 | 85.9 | 94.3 | 86.7 | 79.1 | 93 | 84.1 | 71.3
24 | 3.5 | 25 | 92 | 84.9 | 73 | 97.6 | 92 | 80.2 | 99.8 | 93.4 | 85.3 | 100 | 100 | 94.7 | 100 | 100 | 100 | 100 | 100 | 96.4 | 100 | 100 | 98.6 | 100 | 100 | 97.3 | 100 | 96.3 | 92.7 | 96.8 | 90.7 | 85.9 | 94.7 | 86.7 | 79.1 | 92.9 | 84.1 | 71.3
24 | 4 | 2
24 | 4 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 4 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 4 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 4 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 29.8 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 4 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.9
24 | 4 | 11 | 57.4 | 36 | 24.6 | 61.8 | 49.6 | 29.2 | 70.1 | 57.4 | 46.4 | 82.8 | 72.8 | 64.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.5 | 45.8 | 26 | 56.9 | 37.9 | 23.3
24 | 4 | 12 | 63.3 | 43.5 | 33 | 71 | 60.9 | 36.4 | 79.4 | 68.7 | 50.6 | 89.6 | 80.6 | 75 | 90.8 | 86.2 | 78.9 | 96.6 | 90.3 | 84 | 95.7 | 92.2 | 82.6 | 93.9 | 87.1 | 77.7 | 83 | 74.7 | 67.8 | 69.6 | 58.3 | 46.4 | 65 | 53.5 | 37.6 | 64.4 | 44.1 | 33
24 | 4 | 15 | 82.2 | 68.1 | 58.3 | 89.7 | 83.2 | 66.9 | 92.8 | 86.3 | 74.4 | 98.7 | 94.6 | 90.6 | 100 | 97.6 | 96 | 100 | 98.1 | 94.4 | 100 | 100 | 96 | 100 | 97.3 | 92.7 | 97 | 90.8 | 85.1 | 89.7 | 82.9 | 73.8 | 88.3 | 77.9 | 66.8 | 83.1 | 70.6 | 52.3
24 | 4 | 20 | 97 | 91.4 | 83.1 | 98.6 | 93.5 | 87.4 | 100 | 98.7 | 92.6 | 100 | 100 | 96.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.2 | 95 | 100 | 96.4 | 92.4 | 97.9 | 94.2 | 88.1 | 99 | 90.7 | 84
24 | 4 | 25 | 96.8 | 91.7 | 83.5 | 99.4 | 94 | 87.3 | 100 | 99.1 | 93 | 100 | 100 | 96.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 95.5 | 100 | 96.5 | 92.7 | 99 | 94.4 | 87.8 | 99 | 91.9 | 86.1
24 | 4.5 | 2
24 | 4.5 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 4.5 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 4.5 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 4.5 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 29.8 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 4.5 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.9
24 | 4.5 | 11 | 57.4 | 36 | 24.6 | 61.8 | 49.6 | 29.2 | 70.1 | 57.4 | 46.4 | 82.8 | 72.8 | 64.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.5 | 45.8 | 26 | 56.9 | 37.9 | 23.3
24 | 4.5 | 12 | 63.3 | 43.5 | 33 | 71 | 60.9 | 36.4 | 79.4 | 68.7 | 50.6 | 89.6 | 80.6 | 75 | 90.8 | 86.2 | 78.9 | 96.6 | 90.3 | 84 | 95.7 | 92.2 | 82.6 | 93.9 | 87.1 | 77.7 | 83 | 74.7 | 67.8 | 69.6 | 58.3 | 46.4 | 65 | 53.5 | 37.6 | 64.4 | 44.1 | 33
24 | 4.5 | 15 | 82.2 | 68.8 | 59.2 | 89.7 | 83.3 | 66.9 | 93.4 | 86.3 | 74.6 | 98.7 | 95.3 | 91.2 | 100 | 97.6 | 96 | 100 | 98.1 | 94.8 | 100 | 100 | 96 | 100 | 97.3 | 92.7 | 97 | 91.3 | 85.1 | 89.7 | 82.9 | 73.9 | 88.5 | 78.3 | 67.4 | 83.1 | 71.5 | 52.7
24 | 4.5 | 20 | 99.1 | 94.9 | 87.2 | 100 | 96.3 | 91.2 | 100 | 99.5 | 95.1 | 100 | 100 | 98.7 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 96.4 | 100 | 96.8 | 93.7 | 100 | 97.1 | 92.1 | 100 | 96.4 | 87.6
24 | 4.5 | 25 | 100 | 96.2 | 92.3 | 100 | 97 | 91.7 | 100 | 100 | 97 | 100 | 100 | 98.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.3 | 100 | 99.3 | 95.8 | 100 | 97.5 | 94.5 | 100 | 97 | 93.2
24 | 5 | 2
24 | 5 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 5 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 5 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 5 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 29.8 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 5 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.9
24 | 5 | 11 | 57.4 | 36 | 24.6 | 61.8 | 49.6 | 29.2 | 70.1 | 57.4 | 46.4 | 82.8 | 72.8 | 64.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.5 | 45.8 | 26 | 56.9 | 37.9 | 23.3
24 | 5 | 12 | 63.3 | 43.5 | 33 | 71 | 60.9 | 36.4 | 79.4 | 68.7 | 50.6 | 89.6 | 80.6 | 75 | 90.8 | 86.2 | 78.9 | 96.6 | 90.3 | 84 | 95.7 | 92.2 | 82.6 | 93.9 | 87.1 | 77.7 | 83 | 74.7 | 67.8 | 69.6 | 58.3 | 46.4 | 65 | 53.5 | 37.6 | 64.4 | 44.1 | 33
24 | 5 | 15 | 82.2 | 68.8 | 59.2 | 89.7 | 84.5 | 66.9 | 93.4 | 86.3 | 74.6 | 98.7 | 95.3 | 91.2 | 100 | 97.6 | 96 | 100 | 98.1 | 94.8 | 100 | 100 | 96 | 100 | 97.3 | 92.7 | 97 | 91.3 | 85.1 | 89.7 | 82.9 | 74.1 | 88.5 | 78.3 | 67.4 | 83.1 | 71.5 | 52.7
24 | 5 | 20 | 100 | 95.4 | 89 | 100 | 96.4 | 92.9 | 100 | 99.5 | 95.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.7 | 100 | 97.3 | 94.3 | 100 | 97.5 | 92.5 | 100 | 96.5 | 89.1
24 | 5 | 25 | 100 | 99.1 | 94.7 | 100 | 100 | 95.9 | 100 | 100 | 99.2 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98 | 100 | 100 | 96.6 | 100 | 100 | 96.7
48 | 0.25 | 2
48 | 0.25 | 4
48 | 0.25 | 6
48 | 0.25 | 8
48 | 0.25 | 9
48 | 0.25 | 10
48 | 0.25 | 11
48 | 0.25 | 12
48 | 0.25 | 15
48 | 0.25 | 20
48 | 0.25 | 25
48 | 0.5 | 2
48 | 0.5 | 4
48 | 0.5 | 6 | [9 empty] | 6.5 |  |  | 6.3 |  |  | 6.5 |  |  | 7 |  |  | 12.4 | 6.3 |  | 6.5
48 | 0.5 | 8 | [9 empty] | 6.5 |  |  | 6.5 | 2.7 |  | 11.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 9 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 10 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 11 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 12 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 15 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 20 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 25 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.75 | 2
48 | 0.75 | 4
48 | 0.75 | 6 | 2.4 |  |  | 6.9 |  |  | 6.3 |  |  | 6.6 |  |  | 7.8 | 6.3 |  | 13.1 | 6.5 |  | 12.8 | 6.3 |  | 12.8 | 6.3 |  | 9.8 | 6.5 |  | 3 | [5 empty] | 2.4
48 | 0.75 | 8 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 14.7 | 6.5 | 1.2 | 19.9 | 9 | 4.9 | 25.9 | 14.2 | 6.5 | 30.4 | 19 | 11.4 | 25.2 | 15.2 | 6.3 | 19.3 | 6.9 | 4.5 | 6.3 | [5 empty] | 6.3
48 | 0.75 | 9 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 1.2 | 20.9 | 12.8 | 6.3 | 26.4 | 15 | 8.5 | 31.9 | 19 | 12.2 | 25.2 | 16.9 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 10 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 11 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 12 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 15 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 20 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 25 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 1 | 2
48 | 1 | 4 | [21 empty] | 3.3
48 | 1 | 6 | 5.4 |  |  | 7 |  |  | 6.3 |  |  | 6.6 | 6.5 |  | 12.6 | 6.3 |  | 18.3 | 11.8 |  | 17.1 | 6.3 | 0.3 | 18.2 | 6.3 |  | 13.1 | 6.5 |  | 6.3 |  |  | 3.2 |  |  | 6.3
48 | 1 | 8 | 15.2 | 5.1 |  | 14 | 7 |  | 19.4 | 6.3 |  | 26.3 | 15.4 | 6.4 | 32 | 19 | 12.6 | 39.5 | 22.9 | 13.1 | 38.3 | 26.1 | 14.3 | 38.7 | 23.5 | 19 | 26.4 | 18.8 | 10 | 11.7 | 6.3 |  | 6.5 | 6.5 |  | 12.7 | 6.3
48 | 1 | 9 | 15.1 | 4.8 |  | 15.4 | 7 |  | 19.2 | 9.9 |  | 32.9 | 19.7 | 6.5 | 35.3 | 26.7 | 12.8 | 48.6 | 29.4 | 19.6 | 51.3 | 35.2 | 24.2 | 42.3 | 31.9 | 19.8 | 33 | 19.7 | 12.1 | 12.7 | 6.3 |  | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 10 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 32.9 | 19.7 | 6.5 | 38.2 | 27.3 | 13.2 | 49.6 | 32.4 | 21.2 | 51.2 | 35.3 | 25.4 | 44.6 | 32.3 | 25.3 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 11 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 33 | 19.7 | 6.5 | 38.2 | 29.6 | 13.5 | 49.7 | 32.4 | 21.2 | 51.2 | 38.2 | 25.9 | 44.6 | 32.4 | 25.4 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 12 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 33 | 19.7 | 6.5 | 38.2 | 29.6 | 13.5 | 49.7 | 32.4 | 21.2 | 51.2 | 38.2 | 25.9 | 44.6 | 32.4 | 25.4 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 15 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 33 | 19.7 | 6.5 | 38.2 | 29.6 | 13.5 | 49.7 | 32.4 | 21.2 | 51.2 | 38.2 | 25.9 | 44.6 | 32.4 | 25.4 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 20 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 33 | 19.7 | 6.5 | 38.2 | 29.6 | 13.5 | 49.7 | 32.4 | 21.2 | 51.2 | 38.2 | 25.9 | 44.6 | 32.4 | 25.4 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 25 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 33 | 19.7 | 6.5 | 38.2 | 29.6 | 13.5 | 49.7 | 32.4 | 21.2 | 51.2 | 38.2 | 25.9 | 44.6 | 32.4 | 25.4 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1.25 | 2
48 | 1.25 | 4 | [21 empty] | 3.3
48 | 1.25 | 6 | 6.2 |  |  | 7 |  |  | 6.3 |  |  | 12.4 | 6.5 |  | 19.1 | 6.3 |  | 19.6 | 13.1 |  | 19 | 6.5 | 2.2 | 18.3 | 6.3 |  | 13.2 | 6.5 |  | 6.3 |  |  | 6.5 |  |  | 6.3
48 | 1.25 | 8 | 17.3 | 6.3 |  | 18.5 | 7 |  | 25.4 | 12.6 |  | 31.9 | 19.7 | 6.8 | 37.2 | 21.8 | 12.8 | 43.6 | 30.7 | 17.3 | 44.4 | 31.6 | 19.1 | 42.7 | 27.3 | 19.1 | 28.8 | 25.4 | 13.1 | 14.8 | 6.5 | 0.9 | 13.1 | 6.5 |  | 12.8 | 6.3
48 | 1.25 | 9 | 21.2 | 9.7 |  | 21.7 | 12.8 | 3.7 | 30.8 | 19.1 | 7.3 | 43.2 | 26.3 | 15 | 46.1 | 34.5 | 21 | 58.5 | 39.7 | 26.6 | 54 | 44.9 | 31.9 | 56.8 | 38.3 | 28.5 | 39.9 | 32.6 | 19.7 | 25.6 | 10.1 | 6.2 | 17.3 | 6.5 | 2.1 | 19.2 | 8.3
48 | 1.25 | 10 | 22.3 | 12.1 |  | 26.8 | 14 | 3.6 | 34.6 | 22.6 | 11 | 46.4 | 32.9 | 22.9 | 52.6 | 39.4 | 27.6 | 64.1 | 49 | 35 | 63.9 | 51.6 | 39.2 | 64.1 | 46 | 38.3 | 49.1 | 33.1 | 25 | 28.4 | 17.1 | 6.4 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.25 | 11 | 22.3 | 12.1 |  | 26.7 | 14 | 3.6 | 34.6 | 25.4 | 12.5 | 54.2 | 35.7 | 25.9 | 57.4 | 40.9 | 32.5 | 64.3 | 50 | 35.1 | 63.9 | 53 | 42.9 | 64.1 | 50.8 | 42.7 | 50.8 | 36.5 | 26.1 | 31.6 | 17.9 | 6.5 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.25 | 12 | 22.3 | 12.1 |  | 26.7 | 14 | 3.5 | 36.4 | 25.4 | 12.5 | 55 | 36 | 26.2 | 57.4 | 41.4 | 32.4 | 65.8 | 50.8 | 35.1 | 64.2 | 53 | 42.9 | 64.4 | 50.8 | 42.7 | 50.8 | 36.5 | 26.1 | 31.9 | 17.7 | 6.5 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.25 | 15 | 22.3 | 12.1 |  | 26.7 | 14 | 3.5 | 36.4 | 25.4 | 12.5 | 55 | 36 | 26.2 | 57.2 | 42.5 | 32.4 | 65.8 | 50.8 | 35.1 | 64.2 | 53 | 42.9 | 64.4 | 50.8 | 42.7 | 50.8 | 36.5 | 26.1 | 31.9 | 17.6 | 6.5 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.25 | 20 | 22.3 | 12.1 |  | 26.7 | 14 | 3.5 | 36.4 | 25.4 | 12.5 | 55 | 36 | 26.2 | 57.2 | 42.5 | 32.4 | 65.8 | 50.8 | 35.1 | 64.2 | 53 | 42.9 | 64.4 | 50.8 | 42.7 | 50.8 | 36.5 | 26.1 | 31.9 | 17.6 | 6.5 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.25 | 25 | 22.3 | 12.1 |  | 26.7 | 14 | 3.5 | 36.4 | 25.4 | 12.5 | 55 | 36 | 26.2 | 57.2 | 42.5 | 32.4 | 65.8 | 50.8 | 35.1 | 64.2 | 53 | 42.9 | 64.4 | 50.8 | 42.7 | 50.8 | 36.5 | 26.1 | 31.9 | 17.6 | 6.5 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.5 | 2
48 | 1.5 | 4 | [21 empty] | 3.3
48 | 1.5 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.3 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 6.8 |  |  | 6.5 |  |  | 6.3
48 | 1.5 | 8 | 17.3 | 6.3 |  | 21.1 | 8 | 5.2 | 25.6 | 12.6 | 1.9 | 33.6 | 23.5 | 13.1 | 42.7 | 23 | 13.5 | 45.1 | 36 | 19.6 | 46.8 | 31.9 | 19.2 | 42.7 | 30.4 | 24.6 | 32.3 | 25.4 | 13.1 | 17.1 | 8.1 | 6.3 | 13.2 | 6.5 |  | 12.8 | 6.3
48 | 1.5 | 9 | 22.3 | 12.6 |  | 27.7 | 14.1 | 6.8 | 34.2 | 21.4 | 12.6 | 48.8 | 32.8 | 20.2 | 50.6 | 38.8 | 25.5 | 60.4 | 46.3 | 33.1 | 61.1 | 49.5 | 38.4 | 57.4 | 38.4 | 31.7 | 45.9 | 32.9 | 19.8 | 26.5 | 12.6 | 6.3 | 19.7 | 13.1 | 2.1 | 26.5 | 12.8
48 | 1.5 | 10 | 28.5 | 12.6 | 5.4 | 32.8 | 19 | 7 | 45 | 31.5 | 15.8 | 54.6 | 44.9 | 32.7 | 58.4 | 47.7 | 35.1 | 71.5 | 60.8 | 48.8 | 72.2 | 63.6 | 49.6 | 70 | 54.2 | 43.7 | 52.9 | 42.5 | 31.7 | 34 | 23 | 12.6 | 27.2 | 13.2 | 6.5 | 32 | 12.9 | 6.3
48 | 1.5 | 11 | 30 | 15.6 | 5.4 | 36.4 | 22.2 | 10.7 | 47 | 34.7 | 19 | 63.7 | 46.8 | 37.4 | 68.7 | 57.5 | 45.9 | 77.1 | 66.1 | 51.7 | 78.6 | 67.5 | 52 | 73.5 | 63.8 | 51.1 | 59.4 | 48.6 | 36.2 | 38.3 | 27.6 | 12.9 | 34.5 | 16.4 | 7.2 | 33.7 | 16.3 | 6.3
48 | 1.5 | 12 | 30.1 | 15.3 | 5.4 | 38.8 | 22.2 | 10.8 | 50.2 | 34.8 | 19 | 65.9 | 51.4 | 38.5 | 69.3 | 58.6 | 47.7 | 76.8 | 66.3 | 55.3 | 79.5 | 70.4 | 56.1 | 77 | 64.5 | 51.4 | 60.2 | 49.2 | 37.2 | 38.4 | 29.3 | 14.7 | 34.4 | 16.4 | 7.2 | 33.7 | 16.8 | 6.3
48 | 1.5 | 15 | 30.1 | 15.3 | 5.4 | 38.8 | 22.2 | 10.9 | 50.2 | 34.7 | 19.9 | 65.9 | 51.4 | 38.4 | 70 | 59.1 | 48.8 | 76.9 | 67.6 | 55.2 | 79.4 | 70.4 | 55.9 | 77 | 64.5 | 51.5 | 60.2 | 49.2 | 37.2 | 38.5 | 29.3 | 14.7 | 34.4 | 16.4 | 7.2 | 33.7 | 16.9 | 6.3
48 | 1.5 | 20 | 30.1 | 15.3 | 5.4 | 38.8 | 22.2 | 10.9 | 50.2 | 34.7 | 19.9 | 65.9 | 51.4 | 38.4 | 70 | 59.1 | 48.8 | 76.9 | 67.6 | 55.2 | 79.4 | 70.4 | 55.9 | 77 | 64.5 | 51.5 | 60.2 | 49.2 | 37.2 | 38.5 | 29.3 | 14.7 | 34.4 | 16.4 | 7.2 | 33.7 | 16.9 | 6.3
48 | 1.5 | 25 | 30.1 | 15.3 | 5.4 | 38.8 | 22.2 | 10.9 | 50.2 | 34.7 | 19.9 | 65.9 | 51.4 | 38.4 | 70 | 59.1 | 48.8 | 76.9 | 67.6 | 55.2 | 79.4 | 70.4 | 55.9 | 77 | 64.5 | 51.5 | 60.2 | 49.2 | 37.2 | 38.5 | 29.3 | 14.7 | 34.4 | 16.4 | 7.2 | 33.7 | 16.9 | 6.3
48 | 1.75 | 2
48 | 1.75 | 4 | [21 empty] | 3.3
48 | 1.75 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.3 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 1.75 | 8 | 18.2 | 6.3 |  | 21.1 | 12.5 | 5.2 | 25.6 | 12.8 | 4.5 | 33.6 | 23.3 | 13.1 | 42.7 | 24.5 | 15.4 | 45.1 | 36 | 20 | 46.8 | 37.4 | 21 | 42.7 | 31 | 24.6 | 32.6 | 25.4 | 13.1 | 18.6 | 11.3 | 6.3 | 13.2 | 6.5 | 0.3 | 12.8 | 8.7
48 | 1.75 | 9 | 25.4 | 12.6 | 1.7 | 29.6 | 14.1 | 6.8 | 40.4 | 25.4 | 13.6 | 52.7 | 33.1 | 21.1 | 51 | 42.5 | 25.9 | 63.2 | 49.2 | 33.1 | 62.1 | 49.5 | 38.9 | 62.4 | 41.1 | 31.9 | 46.3 | 32.9 | 21.5 | 26.5 | 15.7 | 7.5 | 24.9 | 13.1 | 6.5 | 28.4 | 12.8
48 | 1.75 | 10 | 34.5 | 19 | 6.3 | 38.3 | 23.4 | 7 | 47.5 | 37.2 | 20.5 | 60.3 | 46.1 | 33.9 | 62.7 | 51.2 | 38.7 | 75.1 | 63.1 | 52.8 | 76.3 | 66.3 | 52 | 73.5 | 61.8 | 44.7 | 56.8 | 46.3 | 32.9 | 37.3 | 25.4 | 13.3 | 29 | 19.6 | 9.4 | 32.1 | 13.4 | 6.3
48 | 1.75 | 11 | 37.4 | 23.3 | 6.4 | 47.1 | 32.3 | 14.7 | 54 | 42.9 | 26.2 | 71.8 | 52.9 | 45.9 | 75.9 | 61.8 | 50 | 83 | 73.9 | 62.7 | 83.6 | 76.1 | 58.7 | 77 | 70.6 | 54.3 | 65.3 | 52.9 | 38.2 | 48.1 | 33.3 | 19.4 | 35.1 | 21.9 | 13 | 38.1 | 19.9 | 6.3
48 | 1.75 | 12 | 41.7 | 25.4 | 12.6 | 51.3 | 35.4 | 18.7 | 65.7 | 44.6 | 32.3 | 74.6 | 63.8 | 46.2 | 80.6 | 67.5 | 57.7 | 86.4 | 80.1 | 67.1 | 89.8 | 77.8 | 65.5 | 87 | 72.8 | 62.4 | 68.6 | 59.3 | 43.9 | 49.6 | 36.8 | 25.8 | 46.3 | 25.3 | 13.1 | 43 | 20.3 | 12.6
48 | 1.75 | 15 | 41.6 | 26.2 | 12.6 | 51.9 | 39.4 | 18.7 | 65.7 | 44.9 | 32.2 | 78.6 | 63.9 | 48.2 | 82.6 | 73.4 | 60.4 | 87.1 | 80.7 | 68.2 | 90.8 | 80.2 | 65.9 | 87 | 72.8 | 62.6 | 70.9 | 58.6 | 43.9 | 51.3 | 38.2 | 28.2 | 46.3 | 26.1 | 13.1 | 42.9 | 20.4 | 12.6
48 | 1.75 | 20 | 41.6 | 26.2 | 12.6 | 51.9 | 39.4 | 18.7 | 65.7 | 44.9 | 32.2 | 78.6 | 63.9 | 48.2 | 82.6 | 73.4 | 60.4 | 87.1 | 80.7 | 68.2 | 90.6 | 80.2 | 65.9 | 87 | 72.8 | 62.6 | 70.9 | 58.6 | 43.9 | 51.3 | 38.2 | 28.2 | 46.3 | 26.1 | 13.1 | 42.9 | 20.4 | 12.6
48 | 1.75 | 25 | 41.6 | 26.2 | 12.6 | 51.9 | 39.4 | 18.7 | 65.7 | 44.9 | 32.2 | 78.6 | 63.9 | 48.2 | 82.6 | 73.4 | 60.4 | 87.1 | 80.7 | 68.2 | 90.6 | 80.2 | 65.9 | 87 | 72.8 | 62.6 | 70.9 | 58.6 | 43.9 | 51.3 | 38.2 | 28.2 | 46.3 | 26.1 | 13.1 | 42.9 | 20.4 | 12.6
48 | 2 | 2
48 | 2 | 4 | [21 empty] | 3.3
48 | 2 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 2 | 8 | 18.2 | 6.3 |  | 21.1 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 25.4 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 16.2 | 12.5
48 | 2 | 9 | 25.4 | 12.6 | 3.4 | 29.6 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 35.6 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 41 | 31.9 | 46.4 | 32.9 | 22.7 | 30.3 | 16.1 | 10.8 | 25 | 13.1 | 6.5 | 29.5 | 12.8
48 | 2 | 10 | 32.9 | 19 | 6.4 | 40.7 | 26.4 | 7.8 | 50.8 | 37.2 | 23.2 | 60.3 | 51.8 | 38.9 | 64.3 | 52.3 | 40.6 | 78.2 | 67.5 | 52.9 | 76.9 | 67.6 | 52 | 73.6 | 61.8 | 44.9 | 58.3 | 46.3 | 35.5 | 41.5 | 25.5 | 13.9 | 29.2 | 19.7 | 10.9 | 35.2 | 19.1 | 6.3
48 | 2 | 11 | 42.1 | 25.4 | 8.2 | 51.7 | 35.3 | 18 | 59.6 | 45 | 32.1 | 73.3 | 59.6 | 49.4 | 77.4 | 64.7 | 54.8 | 86.5 | 77.2 | 66.8 | 86.8 | 76.1 | 62.9 | 81.5 | 70.7 | 56.3 | 70.9 | 55.3 | 39.5 | 48.6 | 35.5 | 24.3 | 41.1 | 22.1 | 13.1 | 41.6 | 20 | 6.3
48 | 2 | 12 | 47.5 | 30.2 | 19.1 | 54.5 | 42.6 | 23.5 | 70.3 | 51.5 | 38.8 | 79.8 | 67.8 | 56.7 | 85.9 | 73.8 | 64.7 | 90.1 | 83.3 | 73.1 | 91.6 | 83.3 | 74.2 | 87.6 | 75.5 | 64.7 | 75.3 | 63.3 | 50.3 | 56.3 | 39.7 | 31.6 | 49 | 35.4 | 15.1 | 49.4 | 26.9 | 12.7
48 | 2 | 15 | 52.8 | 30.4 | 19.3 | 61.9 | 49.4 | 23.8 | 76.4 | 57.4 | 40.8 | 86.2 | 72.6 | 61 | 89.7 | 78.6 | 70.1 | 91.8 | 87.1 | 78.8 | 95.4 | 87.5 | 76.6 | 91.2 | 79.4 | 69.1 | 77.7 | 66.7 | 57.5 | 65.1 | 49.6 | 36.9 | 53.6 | 40.6 | 19.4 | 52.7 | 32 | 16.6
48 | 2 | 20 | 52.8 | 30.4 | 19.3 | 61.9 | 49.4 | 23.8 | 76.4 | 57.4 | 40.8 | 86.2 | 72.6 | 61 | 89.7 | 78.6 | 70.1 | 91.8 | 87.1 | 78.8 | 95.4 | 87.5 | 76.6 | 91.2 | 79.4 | 69.1 | 78.4 | 66.7 | 57.5 | 65.1 | 49.6 | 36.9 | 53.6 | 40.6 | 19.4 | 52.7 | 32 | 16.6
48 | 2 | 25 | 52.8 | 30.4 | 19.3 | 61.9 | 49.4 | 23.8 | 76.4 | 57.4 | 40.8 | 86.2 | 72.6 | 61 | 89.7 | 78.6 | 70.1 | 91.8 | 87.1 | 78.8 | 95.4 | 87.5 | 76.6 | 91.2 | 79.4 | 69.1 | 78.4 | 66.7 | 57.5 | 65.1 | 49.6 | 36.9 | 53.6 | 40.6 | 19.4 | 52.7 | 32 | 16.6
48 | 2.25 | 2
48 | 2.25 | 4 | [21 empty] | 3.3
48 | 2.25 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 2.25 | 8 | 20.1 | 6.3 |  | 21.1 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 2.25 | 9 | 25.4 | 12.6 | 5.9 | 29.6 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44 | 31.9 | 46.4 | 34.6 | 22.7 | 30.3 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 2.25 | 10 | 32.9 | 19 | 6.4 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 60.3 | 52.6 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 61.8 | 44.9 | 58.6 | 46.4 | 35.5 | 43.3 | 25.5 | 13.9 | 29.2 | 19.7 | 11.1 | 37.4 | 19.1 | 6.3
48 | 2.25 | 11 | 42.1 | 25.4 | 8.2 | 51.7 | 35.4 | 18.2 | 59.7 | 46.5 | 32.6 | 73.3 | 60.4 | 49.4 | 77 | 67.7 | 57.8 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 72 | 56.3 | 71.7 | 55.1 | 43.9 | 49.8 | 37.2 | 25.5 | 41.1 | 25.1 | 14.9 | 44.6 | 25.5 | 6.3
48 | 2.25 | 12 | 50.6 | 30.2 | 19.7 | 59 | 49.6 | 25.3 | 72.2 | 53.6 | 39 | 84.4 | 72.1 | 61 | 86 | 75.4 | 66.2 | 92.5 | 84.7 | 77.9 | 92.6 | 86.2 | 75.8 | 92.2 | 77.3 | 70.3 | 78.8 | 66.8 | 55.8 | 57.6 | 43.1 | 36 | 51.8 | 39.3 | 19 | 52 | 26.9 | 14.5
48 | 2.25 | 15 | 60.5 | 37.8 | 28 | 70.7 | 57 | 28.3 | 79.8 | 64.1 | 51 | 92.6 | 83.5 | 68 | 90.9 | 86.3 | 78.6 | 98 | 90.6 | 81.1 | 99.2 | 93.8 | 87.3 | 95 | 85.8 | 77.1 | 84.8 | 76.1 | 66.4 | 70.2 | 57.8 | 45 | 68.5 | 47.6 | 31.3 | 62.4 | 38.6 | 25.5
48 | 2.25 | 20 | 60.8 | 38.4 | 28.1 | 71 | 57 | 28.3 | 79.8 | 64.1 | 51 | 92.6 | 83.5 | 68 | 90.9 | 86.3 | 78.7 | 98 | 90.6 | 81.2 | 99.2 | 93.7 | 87.3 | 95 | 85.8 | 77.1 | 84.8 | 76.1 | 66.4 | 70.2 | 62.5 | 45 | 68.5 | 47.6 | 31.7 | 62.4 | 38.6 | 25.5
48 | 2.25 | 25 | 60.8 | 38.4 | 28.1 | 71 | 57 | 28.3 | 79.8 | 64.1 | 51 | 92.6 | 83.5 | 68 | 90.9 | 86.3 | 78.7 | 98 | 90.6 | 81.2 | 99.2 | 93.7 | 87.3 | 95 | 85.8 | 77.1 | 84.8 | 76.1 | 66.4 | 70.2 | 62.5 | 45 | 68.5 | 47.6 | 31.7 | 62.4 | 38.6 | 25.5
48 | 2.75 | 2
48 | 2.75 | 4 | [21 empty] | 3.3
48 | 2.75 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 2.75 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 2.75 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 2.75 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 33 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 2.75 | 11 | 44.1 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 46.5 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.2 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.6 | 29.2 | 7.9
48 | 2.75 | 12 | 54.7 | 32.7 | 22.3 | 60.3 | 49.7 | 25.3 | 74.4 | 56.3 | 38.9 | 85.8 | 73.8 | 64.2 | 86.4 | 79.7 | 66.2 | 92.9 | 84.9 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 55.8 | 61.8 | 46.2 | 36.4 | 52.6 | 40 | 22.7 | 56.8 | 33.2 | 20.1
48 | 2.75 | 15 | 69.8 | 50.4 | 42.4 | 80.3 | 74 | 44.6 | 87.1 | 77 | 58.5 | 94.2 | 89.2 | 81 | 98.3 | 94 | 88.8 | 100 | 95 | 90.7 | 100 | 96.6 | 94.1 | 100 | 92.1 | 85.8 | 91.4 | 84.3 | 73.8 | 78.9 | 70.2 | 57.9 | 77.8 | 62.9 | 44 | 70.3 | 51.1 | 31.9
48 | 2.75 | 20 | 76.2 | 52.4 | 43.3 | 85.9 | 71.1 | 50.5 | 90.9 | 76.2 | 60 | 96.5 | 91.3 | 81.2 | 100 | 95.2 | 92.3 | 100 | 96.8 | 91.8 | 100 | 97.4 | 93.1 | 100 | 93.7 | 89.8 | 93.5 | 88.2 | 78.8 | 85.3 | 73 | 63.7 | 79 | 62.8 | 47.1 | 70.8 | 56.2 | 39.7
48 | 2.75 | 25 | 76.2 | 52.4 | 43.3 | 85.9 | 71.1 | 50.5 | 90.9 | 76.2 | 60 | 96.5 | 91.3 | 81.2 | 100 | 95.2 | 92.3 | 100 | 96.8 | 91.8 | 100 | 97.4 | 93.1 | 100 | 93.7 | 89.8 | 93.5 | 88.2 | 78.8 | 85.3 | 73 | 63.7 | 79 | 62.8 | 47.1 | 70.8 | 56.2 | 39.7
48 | 3 | 2
48 | 3 | 4 | [21 empty] | 3.3
48 | 3 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 3 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 3 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 3 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 32.9 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 3 | 11 | 45.7 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 49.3 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.1 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.6 | 29.2 | 7.9
48 | 3 | 12 | 54.7 | 34.8 | 22.3 | 60.3 | 49.7 | 26.7 | 74.4 | 56.3 | 38.9 | 85.8 | 73.8 | 64.2 | 86.5 | 79.7 | 66.2 | 92.7 | 84.9 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 55.8 | 61.8 | 48.4 | 36.4 | 52.6 | 40 | 22.7 | 57.3 | 37 | 20.1
48 | 3 | 15 | 71.7 | 54 | 43.1 | 84.5 | 74.9 | 48.5 | 87.3 | 78.5 | 60.6 | 97.6 | 90 | 84.4 | 99.6 | 95.7 | 89.7 | 100 | 94.4 | 90.7 | 100 | 97.7 | 95.1 | 100 | 94.6 | 85.7 | 94 | 85.6 | 77.7 | 85.8 | 71.2 | 61.2 | 79.4 | 65.1 | 45.3 | 71.7 | 55.2 | 38.2
48 | 3 | 20 | 80.7 | 62.6 | 49.8 | 88.3 | 78.9 | 60.4 | 94.5 | 82.8 | 68.7 | 100 | 94.2 | 85.1 | 100 | 99.7 | 93.5 | 100 | 96.8 | 92.7 | 100 | 100 | 94.8 | 100 | 97.6 | 92.8 | 95.6 | 91.4 | 81.3 | 89.2 | 81.6 | 69.2 | 82.1 | 73.8 | 51.4 | 79.9 | 63.2 | 50.7
48 | 3 | 25 | 80.7 | 62.6 | 49.8 | 88.3 | 78.9 | 60.4 | 94.5 | 82.8 | 68.7 | 100 | 94.2 | 85.1 | 100 | 99.7 | 93.5 | 100 | 96.8 | 92.7 | 100 | 100 | 94.8 | 100 | 97.6 | 92.8 | 95.6 | 91.4 | 81.3 | 89.2 | 81.6 | 69.2 | 82.1 | 73.8 | 51.4 | 79.9 | 63.2 | 50.7
48 | 3.5 | 2
48 | 3.5 | 4 | [21 empty] | 3.3
48 | 3.5 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 3.5 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 3.5 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 3.5 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 32.9 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 3.5 | 11 | 45.7 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 49.3 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.1 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.8 | 29.2 | 7.9
48 | 3.5 | 12 | 54.7 | 34.9 | 22.3 | 60.3 | 49.7 | 29.3 | 74.4 | 57.5 | 40.5 | 85.8 | 74 | 65.2 | 86.5 | 79.7 | 66.2 | 93.1 | 85.7 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 57.4 | 61.8 | 48.4 | 36.4 | 52.6 | 40.6 | 22.7 | 57.3 | 37 | 20.1
48 | 3.5 | 15 | 73.6 | 59.8 | 42.9 | 85.1 | 76 | 50.9 | 90.7 | 79.6 | 61.5 | 98.7 | 91.1 | 85 | 100 | 96.1 | 90.4 | 100 | 95 | 91.5 | 100 | 98.1 | 95.3 | 100 | 95.8 | 89.6 | 95 | 85.6 | 77.9 | 88.3 | 73.9 | 63.6 | 81.2 | 71 | 51.9 | 75.9 | 57.4 | 38.6
48 | 3.5 | 20 | 86.9 | 81.5 | 61.8 | 97.1 | 89.4 | 72 | 99.8 | 90.5 | 81.9 | 100 | 100 | 91.3 | 100 | 100 | 100 | 100 | 100 | 95.6 | 100 | 100 | 98.6 | 100 | 100 | 95.8 | 100 | 94.7 | 89 | 96.2 | 87.2 | 79.8 | 92.4 | 82.9 | 71.7 | 90.3 | 77.4 | 59.3
48 | 3.5 | 25 | 86.9 | 81.6 | 61.8 | 97.1 | 89.4 | 72 | 99.8 | 90.5 | 81.9 | 100 | 100 | 91.3 | 100 | 100 | 100 | 100 | 100 | 95.6 | 100 | 100 | 98.6 | 100 | 100 | 95.8 | 100 | 94.7 | 89 | 96.2 | 89.7 | 79.7 | 93.5 | 82.9 | 71.7 | 90.3 | 77.6 | 59.3
48 | 4 | 2
48 | 4 | 4 | [21 empty] | 3.3
48 | 4 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 4 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 4 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 4 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 32.9 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 4 | 11 | 45.7 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 49.3 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.1 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.8 | 29.2 | 7.9
48 | 4 | 12 | 54.7 | 34.9 | 22.3 | 60.3 | 49.7 | 29.3 | 74.4 | 57.5 | 40.4 | 85.8 | 74 | 65.2 | 86.5 | 79.7 | 66.2 | 93.1 | 85.7 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 57.4 | 61.8 | 48.4 | 36.4 | 52.6 | 40.6 | 22.7 | 57.3 | 37 | 20.1
48 | 4 | 15 | 73.8 | 59.8 | 45 | 85.2 | 76.5 | 55 | 90.7 | 79.8 | 61.5 | 98.7 | 91.3 | 86.1 | 100 | 96.2 | 92.2 | 100 | 95.7 | 91.5 | 100 | 98.1 | 95.3 | 100 | 95.8 | 89.6 | 95 | 86 | 78.6 | 88.3 | 76.1 | 63.6 | 82.2 | 71 | 52.9 | 78.4 | 57.4 | 39.9
48 | 4 | 20 | 95.5 | 88.2 | 77.3 | 98.6 | 90.7 | 81.8 | 100 | 96.8 | 89.6 | 100 | 100 | 96 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.2 | 91.7 | 100 | 95.6 | 89.9 | 95.8 | 91.3 | 82.1 | 99 | 87.4 | 79.5
48 | 4 | 25 | 95.4 | 88.2 | 77.3 | 99.4 | 90.7 | 81.7 | 100 | 96.8 | 90.4 | 100 | 100 | 96 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 92.1 | 100 | 96.1 | 90 | 97.2 | 91.4 | 83 | 99 | 87.8 | 79.5
48 | 4.5 | 2
48 | 4.5 | 4 | [21 empty] | 3.3
48 | 4.5 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 4.5 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 4.5 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 4.5 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 32.9 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 4.5 | 11 | 45.7 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 49.3 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.1 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.8 | 29.2 | 7.9
48 | 4.5 | 12 | 54.7 | 34.9 | 22.3 | 60.3 | 49.7 | 29.3 | 74.4 | 57.5 | 40.4 | 85.8 | 74 | 65.2 | 86.5 | 79.7 | 66.2 | 93.1 | 85.7 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 57.4 | 61.8 | 48.4 | 36.4 | 52.6 | 40.6 | 22.7 | 57.3 | 37 | 20.1
48 | 4.5 | 15 | 73.8 | 59.8 | 47.1 | 85.2 | 77.8 | 55 | 90.7 | 79.8 | 65.1 | 98.7 | 91.5 | 86.3 | 100 | 96.2 | 92.2 | 100 | 96.1 | 91.8 | 100 | 98.1 | 95.3 | 100 | 95.8 | 89.6 | 95 | 86.3 | 78.6 | 88.3 | 76.3 | 64 | 82.2 | 71 | 53.2 | 78.4 | 61.6 | 40.6
48 | 4.5 | 20 | 99.1 | 91.7 | 81.6 | 100 | 94.5 | 87.3 | 100 | 98.7 | 91.9 | 100 | 100 | 98.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 94 | 100 | 96.8 | 90.7 | 100 | 94.7 | 89.5 | 100 | 94.2 | 82.5
48 | 4.5 | 25 | 100 | 94.5 | 89.5 | 100 | 96.1 | 89 | 100 | 100 | 96.5 | 100 | 100 | 97.6 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97 | 100 | 99.2 | 93.1 | 100 | 97.4 | 91.6 | 100 | 95.2 | 87.3
48 | 5 | 2
48 | 5 | 4 | [21 empty] | 3.3
48 | 5 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 5 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 5 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 5 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 32.9 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 5 | 11 | 45.7 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 49.3 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.1 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.8 | 29.2 | 7.9
48 | 5 | 12 | 54.7 | 34.9 | 22.3 | 60.3 | 49.7 | 29.3 | 74.4 | 57.5 | 40.4 | 85.8 | 74 | 65.2 | 86.5 | 79.7 | 66.2 | 93.1 | 85.7 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 57.4 | 61.8 | 48.4 | 36.4 | 52.6 | 40.6 | 22.7 | 57.3 | 37 | 20.1
48 | 5 | 15 | 73.8 | 59.8 | 47.1 | 85.2 | 77.8 | 55 | 90.9 | 79.8 | 65.1 | 98.7 | 91.5 | 86.3 | 100 | 96.2 | 92.2 | 100 | 96.1 | 91.8 | 100 | 98.1 | 95.3 | 100 | 95.8 | 89.6 | 95 | 86.3 | 78.6 | 88.3 | 76.3 | 64 | 82.2 | 71 | 53.2 | 78.4 | 61.6 | 40.6
48 | 5 | 20 | 100 | 94.1 | 82.8 | 100 | 94.7 | 87.6 | 100 | 98.7 | 93.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 96.3 | 100 | 97.3 | 91.5 | 100 | 96 | 90.5 | 100 | 95 | 82.8
48 | 5 | 25 | 100 | 99.1 | 93.9 | 100 | 100 | 93.1 | 100 | 100 | 98.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 96.9 | 100 | 100 | 94.5 | 100 | 100 | 93.5
72 | 0.25 | 2
72 | 0.25 | 4
72 | 0.25 | 6
72 | 0.25 | 8
72 | 0.25 | 9
72 | 0.25 | 10
72 | 0.25 | 11
72 | 0.25 | 12
72 | 0.25 | 15
72 | 0.25 | 20
72 | 0.25 | 25
72 | 0.5 | 2
72 | 0.5 | 4
72 | 0.5 | 6 | [21 empty] | 9.5
72 | 0.5 | 8 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 9 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 10 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 11 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 12 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 15 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 20 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 25 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.75 | 2
72 | 0.75 | 4
72 | 0.75 | 6 | [12 empty] | 6.7 |  |  | 9.3 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9
72 | 0.75 | 8 | 6.7 |  |  | 2.4 |  |  | 9.5 |  |  | 9.9 |  |  | 11.6 | 4.3 |  | 19.7 | 9.9 |  | 19.3 | 9.5 | 5.4 | 22.8 | 9.5 |  | 13.8 | 6.9 |  | 4
72 | 0.75 | 9 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 10 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 11 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 12 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 15 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 20 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 25 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 1 | 2
72 | 1 | 4
72 | 1 | 6 | 0.5 | [5 empty] | 6.7 |  |  | 9.2 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9
72 | 1 | 8 | 9.5 |  |  | 10.6 |  |  | 10.2 |  |  | 19.7 | 9.9 |  | 19.1 | 9.5 | 9.5 | 29.8 | 19.6 | 7.8 | 30.8 | 19.2 | 9.5 | 29.8 | 12.2 | 9.5 | 19.8 | 9.9 | 0.5 | 9.5 |  |  | 2.6 |  |  | 9.5
72 | 1 | 9 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.6 | 9.9 | 0.5 | 28.9 | 19.1 | 9.5 | 39.7 | 26.1 | 9.9 | 45.1 | 28.1 | 17.4 | 38.4 | 25.7 | 9.5 | 29.7 | 11.7 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 10 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 39.8 | 29.2 | 13.8 | 47.3 | 28.1 | 17.4 | 38.5 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 11 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 40.6 | 27.8 | 13.9 | 47.3 | 26.5 | 17.4 | 43.2 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 12 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 40.6 | 27.8 | 14.5 | 47.3 | 26.5 | 17.4 | 43.2 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 15 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 40.6 | 27.8 | 14.5 | 47.3 | 26.5 | 17.4 | 43.2 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 20 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 40.6 | 27.8 | 14.5 | 47.3 | 26.5 | 17.4 | 43.2 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 25 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 40.6 | 27.8 | 14.5 | 47.3 | 26.5 | 17.4 | 43.2 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1.25 | 2
72 | 1.25 | 4
72 | 1.25 | 6 | 0.5 |  |  | 3.6 |  |  | 6.7 |  |  | 9.2 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9
72 | 1.25 | 8 | 9.5 |  |  | 15.1 |  |  | 19.2 | 9.5 |  | 19.9 | 9.9 | 3.9 | 27.7 | 14.8 | 9.5 | 37.2 | 19.7 | 9.9 | 33.7 | 23.4 | 9.5 | 36.5 | 19.1 | 9.5 | 23 | 15.6 | 9.9 | 9.5 |  |  | 9.9 |  |  | 9.5
72 | 1.25 | 9 | 18.9 | 4 |  | 18 | 10.2 |  | 28.8 | 9.5 |  | 38.5 | 19.7 | 9.9 | 38.5 | 26.7 | 18.2 | 49.4 | 32.1 | 21 | 49.2 | 30.8 | 22.5 | 48.1 | 31.6 | 18.1 | 30.9 | 20.4 | 9.9 | 19 | 9.5 |  | 9.9 |  |  | 19.1
72 | 1.25 | 10 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 15.6 | 0.9 | 44.1 | 29.2 | 14.2 | 45.8 | 33.2 | 19.7 | 56.8 | 41.1 | 30.8 | 59.7 | 41.4 | 29.3 | 56.5 | 38.3 | 28.8 | 39.7 | 29.6 | 19.7 | 25.6 | 9.5 | 7.2 | 12.9 | 9.9 |  | 19.1 | 0.7
72 | 1.25 | 11 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 17.6 | 0.8 | 48.2 | 29.6 | 18.2 | 47.7 | 36.3 | 25.6 | 59.5 | 41.3 | 32.2 | 60.1 | 42.7 | 34.1 | 60.6 | 44 | 28.8 | 43.3 | 29.6 | 19.7 | 25.6 | 9.5 | 7.2 | 13 | 9.9 |  | 19.1 | 2.2
72 | 1.25 | 12 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 17.6 | 0.8 | 48.2 | 29.7 | 18.2 | 47.7 | 35.9 | 25.6 | 59.5 | 41.3 | 32.7 | 60 | 42.7 | 34.6 | 63.6 | 44 | 29.2 | 43.3 | 29.6 | 19.7 | 25.6 | 9.5 | 7.2 | 13 | 9.9 |  | 19.1 | 2.2
72 | 1.25 | 15 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 17.6 | 0.8 | 48.2 | 29.7 | 18.2 | 47.7 | 35.9 | 25.6 | 59.5 | 41.3 | 32.7 | 60 | 42.7 | 34.6 | 63.6 | 44 | 29.2 | 43.3 | 29.6 | 19.7 | 25.6 | 9.5 | 7.1 | 13 | 9.9 |  | 19.1 | 2.2
72 | 1.25 | 20 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 17.6 | 0.8 | 48.2 | 29.7 | 18.2 | 47.7 | 35.9 | 25.6 | 59.5 | 41.3 | 32.7 | 60 | 42.7 | 34.6 | 63.6 | 44 | 29.2 | 43.3 | 29.6 | 19.7 | 25.6 | 9.5 | 7.1 | 13 | 9.9 |  | 19.1 | 2.2
72 | 1.25 | 25 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 17.6 | 0.8 | 48.2 | 29.7 | 18.2 | 47.7 | 35.9 | 25.6 | 59.5 | 41.3 | 32.7 | 60 | 42.7 | 34.6 | 63.6 | 44 | 29.2 | 43.3 | 29.6 | 19.7 | 25.6 | 9.5 | 7.1 | 13 | 9.9 |  | 19.1 | 2.2
72 | 1.5 | 2
72 | 1.5 | 4
72 | 1.5 | 6 | 0.5 |  |  | 4.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 1.5 | 8 | 13.9 |  |  | 15.5 | 4.5 |  | 19.2 | 9.5 |  | 25.7 | 10.3 | 9.8 | 28.6 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 37.8 | 28.6 | 10.4 | 36.5 | 19.1 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 5.8 |  | 9.9 |  |  | 12.5
72 | 1.5 | 9 | 19.2 | 9.5 |  | 21 | 10.6 |  | 28.9 | 19.1 |  | 42.3 | 26.7 | 9.9 | 45.9 | 31.9 | 19.1 | 54.3 | 32.4 | 24.4 | 50.2 | 38.3 | 28.1 | 50.4 | 34.4 | 19.1 | 39.5 | 23.3 | 9.9 | 19.1 | 9.5 |  | 15.3 | 9.9 |  | 19.2 | 6.5
72 | 1.5 | 10 | 24.1 | 9.5 |  | 25.8 | 15.6 | 1 | 37.1 | 21.4 | 7.9 | 48.7 | 29.9 | 20.5 | 52.7 | 38 | 28.8 | 66.2 | 51.1 | 35.6 | 68.8 | 57.7 | 38.6 | 61.3 | 44.6 | 36.8 | 43.6 | 33.3 | 19.7 | 28.6 | 13.7 | 9.5 | 25.4 | 9.9 | 0.6 | 28.8 | 9.5
72 | 1.5 | 11 | 26 | 12.4 |  | 26.8 | 17.3 | 9.9 | 41 | 28.8 | 9.5 | 52.9 | 39.6 | 26.5 | 58.7 | 48 | 37.9 | 69.7 | 57.1 | 40.6 | 73.8 | 60.8 | 44.2 | 69.5 | 54.8 | 46 | 55.3 | 39.6 | 29.7 | 29.7 | 19.1 | 9.5 | 27.8 | 9.9 | 3.4 | 28.8 | 9.5 | 1
72 | 1.5 | 12 | 27.6 | 12.1 |  | 27.6 | 19.9 | 10.2 | 46.6 | 28.8 | 9.5 | 53.6 | 41.1 | 28.3 | 59.4 | 50 | 39.2 | 71.2 | 59.6 | 44.5 | 75 | 63.8 | 48 | 73.5 | 56.3 | 46.2 | 55.3 | 41.9 | 29.7 | 35.1 | 19.1 | 9.5 | 27.8 | 11.3 | 9.8 | 28.8 | 9.5 | 1
72 | 1.5 | 15 | 27.6 | 12.1 |  | 27.6 | 19.9 | 10.3 | 46.7 | 28.8 | 9.5 | 53.6 | 41.1 | 29.7 | 59.4 | 50 | 39.8 | 71.3 | 59.6 | 45.5 | 75 | 63.8 | 48.6 | 73.5 | 56.3 | 46.3 | 55.3 | 41.9 | 29.7 | 35.1 | 19.1 | 9.5 | 27.8 | 11.5 | 9.8 | 28.8 | 9.5 | 1
72 | 1.5 | 20 | 27.6 | 12.1 |  | 27.6 | 19.9 | 10.3 | 46.7 | 28.8 | 9.5 | 53.6 | 41.1 | 29.7 | 59.4 | 50 | 39.8 | 71.3 | 59.6 | 45.5 | 75 | 63.8 | 48.6 | 73.5 | 56.3 | 46.3 | 55.3 | 41.9 | 29.7 | 35.1 | 19.1 | 9.5 | 27.8 | 11.5 | 9.8 | 28.8 | 9.5 | 1
72 | 1.5 | 25 | 27.6 | 12.1 |  | 27.6 | 19.9 | 10.3 | 46.7 | 28.8 | 9.5 | 53.6 | 41.1 | 29.7 | 59.4 | 50 | 39.8 | 71.3 | 59.6 | 45.5 | 75 | 63.8 | 48.6 | 73.5 | 56.3 | 46.3 | 55.3 | 41.9 | 29.7 | 35.1 | 19.1 | 9.5 | 27.8 | 11.5 | 9.8 | 28.8 | 9.5 | 1
72 | 1.75 | 2
72 | 1.75 | 4
72 | 1.75 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 1.75 | 8 | 16.3 |  |  | 15.5 | 10.6 |  | 19.8 | 9.5 |  | 25.7 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 10.4 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 5.8 |  | 9.9 |  |  | 12.5
72 | 1.75 | 9 | 22.4 | 9.5 |  | 21 | 10.6 |  | 31.9 | 19.1 | 1.7 | 43.9 | 29.6 | 10.5 | 47.4 | 31.9 | 19.1 | 54.3 | 36.1 | 24.4 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.1 | 39.7 | 23.5 | 9.9 | 19.1 | 9.5 |  | 17.9 | 9.9 |  | 25.8 | 9.5
72 | 1.75 | 10 | 26.4 | 13 |  | 30.1 | 16.4 | 1 | 38.5 | 22 | 9.5 | 49.7 | 39.4 | 28 | 55.2 | 38.3 | 28.8 | 69.4 | 52.5 | 39.9 | 69.6 | 58.1 | 39.9 | 66.6 | 48.4 | 38.3 | 49.7 | 36.3 | 20.2 | 28.7 | 19.1 | 9.5 | 28.7 | 10 | 7.8 | 28.8 | 9.5
72 | 1.75 | 11 | 33.7 | 19.1 |  | 36.9 | 21.1 | 10.6 | 50.6 | 33.9 | 20.6 | 61.4 | 48.3 | 33.6 | 66.7 | 52.4 | 42.6 | 78.4 | 66.1 | 47.4 | 83.7 | 68.5 | 50.3 | 76.3 | 60.8 | 48.8 | 61.3 | 45.3 | 30.5 | 36.8 | 23.3 | 11.3 | 30.8 | 16.4 | 9.9 | 36.2 | 13 | 4.2
72 | 1.75 | 12 | 36 | 19.1 | 1.7 | 41.4 | 30.7 | 13 | 56.1 | 38.3 | 24 | 70.2 | 53.3 | 38.8 | 74.7 | 61.7 | 51.9 | 82.9 | 71.4 | 54.6 | 86.5 | 70.7 | 58.6 | 84 | 67.5 | 51.7 | 66.7 | 51.3 | 39.6 | 46.5 | 29.4 | 17.8 | 38.2 | 20.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 1.75 | 15 | 36.2 | 19.1 | 1.7 | 41.4 | 31.8 | 18.7 | 58.7 | 38.6 | 24.1 | 70.8 | 57.4 | 39.1 | 77.4 | 65.1 | 55.4 | 83.2 | 71.8 | 60.3 | 88.4 | 76.6 | 60.5 | 84 | 68.3 | 52 | 66.6 | 54.4 | 39.7 | 47.6 | 29.4 | 17.6 | 39 | 20.3 | 9.9 | 38.6 | 19.1 | 9.5
72 | 1.75 | 20 | 36.2 | 19.1 | 1.7 | 41.4 | 31.8 | 18.7 | 58.7 | 38.6 | 24.1 | 70.8 | 57.4 | 39.1 | 77.4 | 65.1 | 55.4 | 83.2 | 71.8 | 60.3 | 88.4 | 76.6 | 60.5 | 84 | 68.3 | 52 | 66.6 | 54.4 | 39.7 | 47.6 | 29.4 | 17.5 | 39 | 20.3 | 9.9 | 38.6 | 19.1 | 9.5
72 | 1.75 | 25 | 36.2 | 19.1 | 1.7 | 41.4 | 31.8 | 18.7 | 58.7 | 38.6 | 24.1 | 70.8 | 57.4 | 39.1 | 77.4 | 65.1 | 55.4 | 83.2 | 71.8 | 60.3 | 88.4 | 76.6 | 60.5 | 84 | 68.3 | 52 | 66.6 | 54.4 | 39.7 | 47.6 | 29.4 | 17.5 | 39 | 20.3 | 9.9 | 38.6 | 19.1 | 9.5
72 | 2 | 2
72 | 2 | 4
72 | 2 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 2 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 28.5 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 2 | 9 | 22.4 | 9.5 |  | 24 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.4 | 31.9 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 23.5 | 9.9 | 19.2 | 9.5 |  | 17.9 | 9.9 |  | 25.8 | 9.5
72 | 2 | 10 | 26.4 | 15.7 |  | 35.7 | 19.8 | 1 | 40.7 | 27.8 | 9.6 | 51.9 | 42.1 | 29.6 | 57.7 | 43.7 | 28.8 | 69.6 | 53.6 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.4 | 38.4 | 50 | 36.5 | 23.8 | 28.9 | 19.1 | 9.5 | 29 | 12.4 | 9.9 | 28.8 | 11.8 | 1
72 | 2 | 11 | 38.3 | 20.2 | 1.8 | 40.4 | 22.4 | 18.4 | 54.6 | 38.6 | 25.6 | 69 | 50.4 | 36.6 | 72.2 | 59 | 45.6 | 82.1 | 67.9 | 51.7 | 85.7 | 69.6 | 52.2 | 78.5 | 65.7 | 51.7 | 63.4 | 49.6 | 31.3 | 45.4 | 28.6 | 17.7 | 31.5 | 19.9 | 9.9 | 38.5 | 19.1 | 8
72 | 2 | 12 | 45.3 | 23.5 | 9.5 | 48.2 | 34.1 | 19.4 | 65.9 | 44 | 29.4 | 78.3 | 60.6 | 48.8 | 82.2 | 69.5 | 57.9 | 87.3 | 78.8 | 63.4 | 91.5 | 78.9 | 62.2 | 88.3 | 73.5 | 56.4 | 72.5 | 56.8 | 44.9 | 53.7 | 32.1 | 19.1 | 40.7 | 29.6 | 12.5 | 42.3 | 19.5 | 9.5
72 | 2 | 15 | 45.1 | 28.8 | 16.3 | 55.4 | 42.6 | 19.3 | 69.2 | 52.3 | 33.5 | 82.8 | 68.5 | 55.9 | 86.6 | 76.9 | 60.5 | 90.6 | 84.4 | 70 | 93.5 | 86 | 71.1 | 88.9 | 76.2 | 61.9 | 75.7 | 60.1 | 47.5 | 56.3 | 39.9 | 27.9 | 49 | 30.1 | 19.3 | 45.7 | 27.3 | 9.5
72 | 2 | 20 | 45.1 | 28.8 | 16.3 | 55.4 | 42.6 | 19.2 | 69.2 | 52.3 | 33.5 | 82.8 | 68.5 | 55.9 | 86.6 | 76.9 | 60.5 | 90.6 | 84.4 | 70 | 93.5 | 86 | 71.1 | 88.9 | 76.2 | 61.9 | 75.7 | 60.1 | 47.4 | 56.3 | 39.9 | 27.9 | 49 | 30.1 | 19.3 | 45.7 | 27.3 | 9.5
72 | 2 | 25 | 45.1 | 28.8 | 16.3 | 55.4 | 42.6 | 19.2 | 69.2 | 52.3 | 33.5 | 82.8 | 68.5 | 55.9 | 86.6 | 76.9 | 60.5 | 90.6 | 84.4 | 70 | 93.5 | 86 | 71.1 | 88.9 | 76.2 | 61.9 | 75.7 | 60.1 | 47.4 | 56.3 | 39.9 | 27.9 | 49 | 30.1 | 19.3 | 45.7 | 27.3 | 9.5
72 | 2.25 | 2
72 | 2.25 | 4
72 | 2.25 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 2.25 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 2.25 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 23.5 | 9.9 | 19.2 | 9.5 |  | 19.2 | 9.9 |  | 25.8 | 9.5
72 | 2.25 | 10 | 28.7 | 15.7 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.5 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 56.3 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.4 | 38.4 | 50 | 36.5 | 23.8 | 32.8 | 19.1 | 9.5 | 29 | 16.1 | 9.9 | 28.9 | 16.7 | 1
72 | 2.25 | 11 | 39 | 20.7 | 5.3 | 42.9 | 29.9 | 18.3 | 54.6 | 39.5 | 25.6 | 69.7 | 55.8 | 40.5 | 72.7 | 59.9 | 45.8 | 82.8 | 69.7 | 53.3 | 85.7 | 71.5 | 54.2 | 78.5 | 66.1 | 52 | 63.4 | 52.9 | 35.7 | 45.4 | 28.8 | 17.9 | 35.8 | 22.1 | 9.9 | 38.5 | 19.1 | 8.1
72 | 2.25 | 12 | 46 | 28.6 | 9.5 | 53.3 | 41.2 | 20.7 | 65.9 | 48.1 | 31.2 | 79.6 | 67.5 | 52.7 | 82.6 | 70.6 | 58.9 | 89.8 | 79.7 | 68.3 | 92.1 | 83.5 | 62.9 | 90.4 | 75.5 | 62.3 | 73.2 | 57.8 | 46.7 | 55.3 | 38.4 | 19.4 | 43.3 | 29.6 | 12.5 | 46.6 | 22.8 | 11.5
72 | 2.25 | 15 | 57.7 | 37.1 | 22 | 69.8 | 47 | 24.7 | 78.6 | 59 | 39.4 | 91.4 | 79.6 | 64.5 | 89.5 | 83.9 | 75.2 | 95.3 | 87.9 | 79.6 | 96.9 | 89.4 | 84.9 | 91.7 | 80.8 | 73.2 | 81.5 | 69.2 | 57.5 | 67 | 51.5 | 36.9 | 60.8 | 39.7 | 20.8 | 56.5 | 35.9 | 19.1
72 | 2.25 | 20 | 57.7 | 37.1 | 22 | 69.8 | 53 | 24.7 | 78.6 | 59.1 | 39.4 | 91.4 | 79.6 | 64.5 | 89.5 | 83.9 | 75.2 | 95.3 | 87.9 | 79.6 | 96.8 | 89.2 | 84.9 | 91.7 | 80.8 | 73.2 | 81.5 | 69.3 | 57.3 | 67 | 56 | 36.9 | 60.8 | 39.7 | 20.8 | 56.5 | 35.9 | 19.1
72 | 2.25 | 25 | 57.7 | 37.1 | 22 | 69.8 | 53 | 24.7 | 78.6 | 59.1 | 39.4 | 91.4 | 79.6 | 64.5 | 89.5 | 83.9 | 75.2 | 95.3 | 87.9 | 79.6 | 96.8 | 89.2 | 84.9 | 91.7 | 80.8 | 73.2 | 81.5 | 69.3 | 57.3 | 67 | 56 | 36.9 | 60.8 | 39.7 | 20.8 | 56.5 | 35.9 | 19.1
72 | 2.75 | 2
72 | 2.75 | 4
72 | 2.75 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 2.75 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 2.75 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.2 | 9.9 |  | 25.8 | 9.5
72 | 2.75 | 10 | 28.6 | 15.7 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 16.1 | 9.9 | 28.9 | 16.7 | 4.6
72 | 2.75 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 45.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 36.5 | 25.3 | 9.9 | 38.5 | 19.2 | 9.5
72 | 2.75 | 12 | 47.7 | 28.8 | 15.4 | 53.4 | 41.5 | 21.1 | 66.3 | 50 | 30.2 | 81.2 | 69.6 | 58.5 | 83 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 74.1 | 59.3 | 49.8 | 57 | 38.4 | 24.4 | 47.1 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 2.75 | 15 | 63 | 47.8 | 31.1 | 77.4 | 62.8 | 33.3 | 82 | 66.8 | 50.5 | 94.4 | 86.8 | 73.8 | 96.9 | 92.9 | 86.3 | 100 | 94.7 | 88.4 | 100 | 96.6 | 89.7 | 100 | 89.7 | 82.6 | 88.3 | 81.3 | 67 | 76 | 66 | 52.1 | 70 | 57.9 | 32.6 | 62.5 | 47.4 | 28.8
72 | 2.75 | 20 | 68.6 | 49.3 | 37.2 | 79.1 | 68.2 | 33.2 | 88.3 | 73 | 56.8 | 96.8 | 89.4 | 75.8 | 100 | 94.5 | 90.8 | 100 | 96.3 | 89.6 | 100 | 96.6 | 91.5 | 100 | 91.3 | 85 | 93.7 | 82.6 | 67.9 | 79.9 | 72 | 57.3 | 72.1 | 58.2 | 38.2 | 62.9 | 48 | 29.5
72 | 2.75 | 25 | 68.6 | 49.3 | 37.2 | 79.1 | 68.2 | 33.2 | 88.3 | 73 | 56.8 | 96.8 | 89.4 | 75.8 | 100 | 94.5 | 90.8 | 100 | 96.3 | 89.6 | 100 | 96.6 | 91.5 | 100 | 91.3 | 85 | 93.7 | 82.6 | 67.9 | 79.9 | 72 | 57.3 | 72.1 | 58.2 | 38.2 | 62.9 | 48 | 29.5
72 | 3 | 2
72 | 3 | 4
72 | 3 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 3 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 3 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.7 | 9.9 |  | 25.8 | 9.5
72 | 3 | 10 | 28.6 | 15.7 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 17.4 | 9.9 | 28.9 | 16.7 | 4.6
72 | 3 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 45.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 41 | 25.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 3 | 12 | 47.7 | 28.8 | 15.4 | 53.4 | 41.2 | 21.1 | 66.8 | 50 | 30.2 | 81.2 | 69.6 | 58.5 | 83.3 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 77.5 | 59.3 | 49.8 | 57 | 39.1 | 24.4 | 49.6 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 3 | 15 | 64.3 | 49.2 | 34.3 | 77.6 | 66.1 | 38.7 | 83.4 | 70.7 | 55.8 | 97.4 | 86.8 | 78.3 | 99.2 | 93 | 87.4 | 100 | 94.9 | 89.2 | 100 | 96.6 | 90 | 100 | 91.4 | 82.5 | 92.3 | 81.3 | 68.2 | 79.4 | 67.5 | 55.4 | 74.1 | 58.6 | 39.6 | 66.8 | 50.3 | 28.7
72 | 3 | 20 | 75.1 | 58.3 | 42.3 | 84.2 | 72.1 | 47.6 | 91 | 77.3 | 63 | 100 | 91.5 | 83.3 | 100 | 100 | 89.6 | 100 | 97.2 | 92.2 | 100 | 100 | 89.9 | 100 | 97 | 88.9 | 93.6 | 89 | 76.1 | 86 | 76.1 | 65.2 | 79.8 | 67.2 | 46.5 | 72 | 55 | 45.8
72 | 3 | 25 | 75.1 | 58.3 | 42.3 | 84.2 | 72.1 | 47.6 | 91 | 77.3 | 63 | 100 | 91.5 | 83.3 | 100 | 100 | 89.6 | 100 | 97.2 | 92.2 | 100 | 100 | 89.9 | 100 | 97 | 88.9 | 93.6 | 89 | 76.1 | 86 | 76.1 | 65.2 | 79.8 | 67.2 | 46.5 | 72 | 55 | 45.8
72 | 3.5 | 2
72 | 3.5 | 4
72 | 3.5 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 3.5 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 3.5 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.7 | 9.9 |  | 25.8 | 9.5
72 | 3.5 | 10 | 28.6 | 18.5 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 17.4 | 9.9 | 28.9 | 16.7 | 4.6
72 | 3.5 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 46.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 40.9 | 25.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 3.5 | 12 | 47.7 | 29.6 | 15.4 | 53.4 | 41.2 | 21.1 | 66.8 | 50 | 30.2 | 81.2 | 69.6 | 59.1 | 83.3 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 77.5 | 59.3 | 50.6 | 57 | 39.1 | 24.4 | 49.8 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 3.5 | 15 | 66.1 | 53.4 | 34.1 | 78 | 68.9 | 38.7 | 86.6 | 73.1 | 56.4 | 97.8 | 89.2 | 81.3 | 100 | 94 | 89.6 | 100 | 95 | 90.4 | 100 | 100 | 90.7 | 100 | 91.9 | 82.3 | 92.8 | 83.6 | 71.2 | 80 | 68.1 | 56.8 | 78.8 | 60.4 | 42.1 | 72.1 | 53.6 | 29.8
72 | 3.5 | 20 | 83.3 | 73.1 | 58.9 | 95 | 84.2 | 64.5 | 98.9 | 86.7 | 75.8 | 100 | 98.5 | 89.8 | 100 | 100 | 100 | 100 | 100 | 92.6 | 100 | 100 | 94.9 | 100 | 100 | 95.6 | 100 | 92.4 | 82.7 | 96.2 | 85.6 | 76.3 | 88.1 | 79.3 | 66.7 | 89.5 | 70.7 | 56.2
72 | 3.5 | 25 | 83.3 | 73.1 | 58.9 | 96.3 | 84.2 | 64.5 | 98.9 | 86.7 | 75.8 | 100 | 98.5 | 89.8 | 100 | 100 | 100 | 100 | 100 | 92.6 | 100 | 100 | 94.9 | 100 | 100 | 95.6 | 100 | 92.2 | 82.7 | 96.4 | 85.6 | 76.3 | 89.8 | 79.3 | 66.7 | 89.5 | 70.7 | 56.2
72 | 4 | 2
72 | 4 | 4
72 | 4 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 4 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 4 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.7 | 9.9 |  | 25.8 | 9.5
72 | 4 | 10 | 28.6 | 18.5 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 17.4 | 9.9 | 28.9 | 16.7 | 4.6
72 | 4 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 46.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 40.9 | 25.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 4 | 12 | 47.7 | 29.6 | 15.4 | 53.4 | 41.2 | 21.1 | 66.8 | 50 | 30.2 | 81.2 | 69.6 | 59.1 | 83.3 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 77.5 | 59.3 | 50.6 | 57 | 39.1 | 24.4 | 49.8 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 4 | 15 | 67.2 | 53.4 | 36.2 | 78.9 | 68.9 | 45.4 | 86.1 | 73.1 | 56.8 | 97.8 | 89.4 | 82.8 | 100 | 95.4 | 89.6 | 100 | 95.1 | 90.4 | 100 | 100 | 91.5 | 100 | 92.6 | 82.3 | 92.8 | 84.3 | 72.7 | 81.8 | 69.2 | 56.8 | 80.3 | 64 | 42.1 | 72.1 | 56.3 | 31.6
72 | 4 | 20 | 95.8 | 82.9 | 70.2 | 97.7 | 89.7 | 76 | 100 | 93.8 | 86.5 | 100 | 100 | 92.6 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.1 | 90.4 | 100 | 91.1 | 83.9 | 95.5 | 88.1 | 79.4 | 99 | 82.1 | 67.2
72 | 4 | 25 | 95.8 | 82.9 | 70.7 | 99.4 | 89.9 | 76 | 100 | 93.7 | 88.3 | 100 | 100 | 92.7 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 90.9 | 100 | 92.2 | 84 | 98 | 88.1 | 80.9 | 99 | 82.9 | 70
72 | 4.5 | 2
72 | 4.5 | 4
72 | 4.5 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 4.5 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 4.5 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.7 | 9.9 |  | 25.8 | 9.5
72 | 4.5 | 10 | 28.6 | 18.5 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 17.4 | 9.9 | 28.9 | 16.7 | 4.6
72 | 4.5 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 46.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 40.9 | 25.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 4.5 | 12 | 47.7 | 29.6 | 15.4 | 53.4 | 41.2 | 21.1 | 66.8 | 50 | 30.2 | 81.2 | 69.6 | 59.1 | 83.3 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 77.5 | 59.3 | 50.6 | 57 | 39.1 | 24.4 | 49.8 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 4.5 | 15 | 67.2 | 53.4 | 35.2 | 78.9 | 68.9 | 45.4 | 86.1 | 73.1 | 56.8 | 97.8 | 91.3 | 82.9 | 100 | 95.4 | 89.6 | 100 | 95.1 | 90.4 | 100 | 100 | 91.5 | 100 | 92.6 | 82.3 | 92.8 | 85.3 | 73 | 81.8 | 69.2 | 57.3 | 80.3 | 64 | 42.2 | 72.1 | 56.3 | 31.6
72 | 4.5 | 20 | 99.1 | 87.8 | 74.7 | 100 | 92.4 | 81 | 100 | 96.5 | 90 | 100 | 100 | 92.8 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 93.8 | 100 | 94.6 | 87 | 100 | 91 | 87.8 | 100 | 89.9 | 78.2
72 | 4.5 | 25 | 100 | 92.1 | 85.2 | 100 | 96 | 85.4 | 100 | 100 | 92.7 | 100 | 100 | 95.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.1 | 100 | 99.2 | 91.1 | 100 | 92.8 | 88.3 | 100 | 92.3 | 84.2
72 | 5 | 2
72 | 5 | 4
72 | 5 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 5 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 5 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.7 | 9.9 |  | 25.8 | 9.5
72 | 5 | 10 | 28.6 | 18.5 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 17.4 | 9.9 | 28.9 | 16.7 | 4.6
72 | 5 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 46.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 40.9 | 25.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 5 | 12 | 47.7 | 29.6 | 15.4 | 53.4 | 41.2 | 21.1 | 66.8 | 50 | 30.2 | 81.2 | 69.6 | 59.1 | 83.3 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 77.5 | 59.3 | 50.6 | 57 | 39.1 | 24.4 | 49.8 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 5 | 15 | 67.2 | 53.4 | 35.2 | 78.9 | 68.9 | 45.4 | 86.1 | 73.1 | 56.8 | 97.8 | 91.3 | 82.9 | 100 | 95.4 | 89.6 | 100 | 95.1 | 90.4 | 100 | 100 | 91.5 | 100 | 92.6 | 82.3 | 92.8 | 85.3 | 73 | 81.8 | 69.2 | 57.7 | 80.3 | 64 | 42.2 | 72.1 | 56.3 | 31.6
72 | 5 | 20 | 100 | 89.2 | 80.6 | 100 | 92.8 | 81.1 | 100 | 97.6 | 90.4 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 93.9 | 100 | 97 | 88 | 100 | 92.8 | 87.9 | 100 | 91.4 | 78.3
72 | 5 | 25 | 100 | 99.1 | 89.6 | 100 | 100 | 90.8 | 100 | 100 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 95.2 | 100 | 100 | 93.6 | 100 | 100 | 90.8

## WDT Calculation
WORKABILITY CALCULATION PART A | [7 empty] | WORKABILITY CALCULATION PART C
| PART | Limiting conditions |  |  | Total Durations (days) |  |  |  | PART | Limiting conditions |  |  | Total Durations (days)
| A | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW |  |  | C | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW
|  | 0 | 0 | 0 | 1.625 | #N/A |  |  |  | 0 | 0 | 0 | 0 | #N/A
CALCULATION |  |  |  |  | Nett days | Working days |  | CALCULATION |  |  |  |  | Nett days | Working days
Month | Month | Start | End | Persistence | in month | in month | left | Month | Month | Start | End | Persistence | in month | in month | left
1 | 1 | 0 | 1900-01-30 | #N/A | 32 | #N/A | #N/A | 1 | 1 | 0 | 1900-01-30 | #N/A | 32 | #N/A | #N/A
2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
WORKABILITY CALCULATION PART B | [7 empty] | WORKABILITY CALCULATION PART D
| PART | Limiting conditions |  |  | Total Durations (days) |  |  |  | PART | Limiting conditions |  |  | Total Durations (days)
| B | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW |  |  | D | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW
|  | 0 | 0 | 0 | 0 | #N/A |  |  |  | 0 | 0 | 0 | 0 | #N/A
CALCULATION |  |  |  |  | Nett days | Working days |  | CALCULATION |  |  |  |  | Nett days | Working days
Month |  | Start | End | Persistence | in month | in month | left | Month |  | Start | End | Persistence | in month | in month | left
1 | 1 | 0 | 1900-01-30 | #N/A | 32 | #N/A | #N/A | 1 | 1 | 0 | 1900-01-30 | #N/A | 32 | #N/A | #N/A
2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Formulas:
End = IF([Limiting conditions]+[Total Durations (days)]-1<EOMONTH([Limiting conditions],0),[Limiting conditions]+[Total Durations (days)]-1,EOMONTH([Limiting conditions],0))
End = IF([left, row above]>0,IF([Limiting conditions]+[Total Durations (days)]-1<EOMONTH([Limiting conditions],0),[Limiting conditions]+[Total Durations (days)]-1,EOMONTH([Limiting conditions],0)),[Limiting conditions])
Total Durations (days) = IFERROR(IF(G5/[Persistence]<EOMONTH([Limiting conditions],0)+1-[Limiting conditions],G5/[Persistence],EOMONTH([Limiting conditions],0)+1-[Limiting conditions]),EOMONTH([Limiting conditions],0)-[Limiting conditions]+1)
Total Durations (days) = IFERROR(IF(P5/[Persistence]<EOMONTH([Limiting conditions],0)+1-[Limiting conditions],P5/[Persistence],EOMONTH([Limiting conditions],0)+1-[Limiting conditions]),EOMONTH([Limiting conditions],0)-[Limiting conditions]+1)

## Remuneration Table (hidden)
Item | Description | Unit | Unit Rate | Quantity | Price
Mobilisation/demobilisation of vessel(s), survey equipment and personnel to site
1.1 | Mob/demob vessel Name of vessel 1 incl. vessel equipment and personnel | Lump sum | 0 | 1 | FILL UNIT RATE
1.2 | Mob/demob vessel Name of vessel 2 incl. vessel equipment and personnel | Lump sum | 0 | 0 | FILL UNIT RATE
1.3 | Mob/demob vessel Name of vessel 3 incl. vessel equipment and personnel | Lump sum | 0 | 1 | FILL UNIT RATE
1.4 | Mob/demob vessel Name of vessel 4 incl. vessel equipment and personnel | Lump sum | 0 | 0 | FILL UNIT RATE
1.5 | Mob/demob of seabed PCPT equipment and personnel | Lump sum | 0 | 1 | FILL UNIT RATE
1.6 | Mob/demob of seabed SCPT equipment and personnel | Lump sum | 0 | 1 | FILL UNIT RATE
1.7 | Mob/demob of thermal conductivity test equipment and personnel | Lump sum | 0 | 1 | FILL UNIT RATE
1.8 | Mob/demob of vibrocoring equipment and personnel | Lump sum | 0 | 1 | FILL UNIT RATE
2 | Survey Operations incl transit from and to site excluding WOW | 0 | 0 | 0 | 0
2.1 | Positioning and setting-up equipment at each location for seabed PCPT and dissipation tests | /location | 0 | 230 | FILL UNIT RATE
2.2 | Re-positioning and setting-up for any re-tests at same location (seabed PCPT and dissipation tests) | /location | 0 | 23 | FILL UNIT RATE
2.3 | Seabed PCPT performance (including any re-tests) for depths between 0-50 m | /m | 0 | 12650 | FILL UNIT RATE
Survey Operations incl transit from and to site excluding WOW
2.1 | Positioning and setting-up equipment at each location for seabed PCPT and dissipation tests | /location | 0 | 230 | FILL UNIT RATE
2.2 | Re-positioning and setting-up for any re-tests at same location (seabed PCPT and dissipation tests) | /location | 0 | 23 | FILL UNIT RATE
2.3 | Seabed PCPT performance (including any re-tests) for depths between 0-50 m | /m | 0 | 12650 | FILL UNIT RATE
2.4 | Seabed PCPT performance (including any re-tests) to a depth of between 50-60 m (amount includes bonus) | /m | 0 | 2300 | FILL UNIT RATE
2.5 | Execution of dissipation tests in seabed PCPT mode (N.B. number of tests will be limited by total time allowance) | /hour | 0 | 39 | FILL UNIT RATE
2.6 | Positioning and setting-up equipment at each location for seabed SCPT | /location | 0 | 59 | FILL UNIT RATE
2.7 | Re-positioning and setting-up for any re-tests at same location (seabed SCPT) | /location | 0 | 6 | FILL UNIT RATE
2.8 | Seabed SCPT performance excluding seismic tests (including any re-tests) for depths between 0-50 m | /m | 0 | 3250 | FILL UNIT RATE
2.9 | Seabed SCPT performance excluding seismic tests (including any re-tests) to a depth of between 50-60 m (amount includes bonus) | /m | 0 | 590 | FILL UNIT RATE
2.10 | Execution of seismic tests in seabed SCPT mode | /m | 0 | 3840 | FILL UNIT RATE
2.11 | Positioning and setting-up equipment at each location for thermal conductivity cone testing | /location | 0 | 68 | FILL UNIT RATE
2.12 | Re-positioning and setting-up for any re-tests at same location (thermal conductivity tests) | /location | 0 | 7 | FILL UNIT RATE
2.13 | Seabed in situ thermal conductivity performance (including any re-tests and any associated data) for depths between 0-6m | /m | 0 | 408 | FILL UNIT RATE
2.14 | Execution of in situ thermal conductivity tests during pause in penetration | /hour | 0 | 102 | FILL UNIT RATE
2.15 | Positioning and setting-up equipment at vibrocore location | /location | 0 | 164 | FILL UNIT RATE
2.16 | Execution of vibrocores (including any re-tests) to target depth of up to 6m | /m | 0 | 984 | FILL UNIT RATE
2.17 | Micro sitting for positioning at seabed CPT location due to unexpected high gradient of seabed frame preventing the work | /location | 0 | 23 | FILL UNIT RATE
2.18 | Port call for Name of vessel 1 during surveying PART A | /call | 0 | 0 | FILL UNIT RATE
2.19 | Port call for Name of vessel 2 during surveying PART B | /call | 0 | 1578 | FILL UNIT RATE
Lab Testing - All Soil types
3.1 | Natural Moisture content | /test | 0 | 1476 | FILL UNIT RATE
3.2 | Bulk density | /test | 0 | 1476 | FILL UNIT RATE
3.3 | Particle density | /test | 0 | 492 | FILL UNIT RATE
3.4 | Carbonate content | /test | 0 | 32.8 | FILL UNIT RATE
3.5 | Organic content (dichromate) | /test | 0 | 32.8 | FILL UNIT RATE
3.6 | Organic content (loss on ignition) | /test | 0 | 32.8 | FILL UNIT RATE
3.7 | Organic and total carbon content (Elementary analysis) | /test | 0 | 32.8 | FILL UNIT RATE
3.8 | Electrical resistivity (as input for heat capacity calculations) | /test | 0 | 68 | FILL UNIT RATE
3.9 | Pore water salinity (as input for heat capacity calculations) | /test | 0 | 68 | FILL UNIT RATE
3.10 | Microscopic photography (as input for heat capacity calculations) | /test | 0 | 68 | FILL UNIT RATE
Lab Testing - Granular Soil
3.11 | Particle size analysis (sieve) | /test | 0 | 984 | FILL UNIT RATE
3.12 | Particle size analysis (using sieve and hydrometer for fines fraction) | /test | 0 | 492 | FILL UNIT RATE
3.13 | Thermal conductivity tests on fully-saturated cohesionless samples using needle probe (ASTM D5334-14) | /test | 0 | 164 | FILL UNIT RATE
3.14 | Thermal conductivity tests on fully-saturated cohesionless samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). | /test | 0 | 20 | FILL UNIT RATE
3.15 | Shear box (set of 3 specimens with different normal stresses) | /test | 0 | 82 | FILL UNIT RATE
Lab Testing - Cohesive Soil
3.16 | Particle size analysis (using hydrometer for fines and if applicable sieve) | /test | 0 | 50 | FILL UNIT RATE
3.17 | Atterberg limits (liquid and plastic limits, cone method) | /test | 0 | 50 | FILL UNIT RATE
3.18 | Thermal conductivity tests on fully-saturated undisturbed cohesive samples using needle probe (ASTM D5334-14) | /test | 0 | 15 | FILL UNIT RATE
3.19 | Thermal conductivity tests on fully-saturated remoulded cohesive samples using needle probe (ASTM D5334-14) | /test | 0 | 15 | FILL UNIT RATE
3.20 | Thermal conductivity tests on fully-saturated undisturbed cohesive samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). | /test | 0 | 15 | FILL UNIT RATE
3.21 | Thermal conductivity tests on fully-saturated remoulded cohesive samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). | /test | 0 | 15 | FILL UNIT RATE
3.22 | Unconsolidated-undrained triaxial compression tests on undisturbed samples | /test | 0 | 50 | FILL UNIT RATE
3.23 | Unconsolidated-undrained triaxial compression tests on remoulded samples | /test | 0 | 50 | FILL UNIT RATE
Reporting
4.1 | Seabed In Situ Testing Report | Lump sum | 0 | 1 | FILL UNIT RATE
4.2 | Seabed Sampling Report (including all results from lab testing programme, except for age dating) | Lump sum | 0 | 1 | FILL UNIT RATE
4.3 | Operations Report (Lot 1) | Lump sum | 0 | 1 | FILL UNIT RATE
4.5 | Additional reporting of any seabed PCPTs in excess of base scope | /location | 0 | 10 | FILL UNIT RATE
4.6 | Additional reporting of any seabed SCPTs in excess of base scope (excluding the seismic test results) | /location | 0 | 10 | FILL UNIT RATE
4.7 | Additional reporting of any seismic tests during seabed SCPTs in excess of base scope | /test | 0 | 300 | FILL UNIT RATE
4.8 | Additional reporting of any dissipation tests in excess of base scope | /test | 0 | 10 | FILL UNIT RATE
4.9 | Additional reporting of any in situ thermal conductivity tests in excess of base scope | /location | 0 | 5 | FILL UNIT RATE
4.10 | Additional reporting of any vibrocores in excess of base scope | /location | 0 | 10 | FILL UNIT RATE
4.12 | Lab test processing/reporting and any other expenses associated with lab testing not covered by other items above | % of lab testing price | 0 | 0 | FILL UNIT RATE
Waiting on Weather
5.1 | Waiting on Weather Name of vessel 1 during surveying PART A | /day | 0 | 0 | FILL UNIT RATE
5.2 | Waiting on Weather Name of vessel 2 during surveying PART B | /day | 0 | 0 | FILL UNIT RATE
Other
6.1 | Project meetings to be held in CLIENT offices (Utrecht or The Hague) | /meeting | 0 | 15 | FILL UNIT RATE
6.2 | Additional UXO clearance measures for seabed PCPT/SCPT, in situ thermal conductivity tests, or vibrocores. | /location | 0 | 394 | FILL UNIT RATE
6.3 | Interaction with Lot 2 contractor and certification authorities (estimated 200hrs for senior level personnel) | Lump Sum | 0 | 1 | FILL UNIT RATE
6.4 | Activities related to dissemination of results (webinar and Project Site Description) | Lump Sum | 0 | 1 | FILL UNIT RATE