## Cycle times & prices
VIRTUAL CYCLE TIME & PRICE GEOTECHNICAL SURVEY - LOT 2
| Project: | IJmuiden Ver Wind Farm Zone | [8 empty] | Intermediate Target Depths (m bsf) |  |  |  |  | PCPT | SCPT | DT | TC | VC | BH | All
| Company: | Company name | [8 empty] | SB PCPT min target (for price) |  | 50 |  | Vessel 1 | [5 empty] | TRUE | TRUE
| Originator: | Originator name | [8 empty] | SB SCPT av. target (for price) |  | 50 |  | Vessel 2 | [5 empty] | FALSE | FALSE
[10 empty] | Note | BH min depth |  | 60 |  | Vessel 3 | [5 empty] | FALSE | FALSE
| I. Survey Area IJmuiden Ver and Number of Tests | [8 empty] | I.0 |  |  |  |  | Vessel 4 | [5 empty] | FALSE | FALSE
| Test type - Description |  |  |  | Target depth (m bsf) |  | Total Number | Short name |  |  | Test average duration |  |  |  | All | [5 empty] | TRUE | TRUE
| Boreholes - Type I (quasi continuous sampling followed by downhole PCPT with occasional sampling) |  |  |  | 60 - 80 |  | 95 | BH-I |  |  | Test | Duration (hrs)
| Boreholes - Type II (quasi continuous downhole SCPT) |  |  |  | 60 |  | 13 | BH-II |  |  | DT | 0.25 |  |  | Overview of activities during the different survey phases
| Boreholes - Type III (combined downhole sampling/PCPT) |  |  |  | ≥ 80 |  | 7 | BH-III |  |  | TC | 0.25 |  |  | Part A | [5 empty] | ¦BH | ¦BH¦
| Boreholes - Type IV (destructive drilling) |  |  |  | 60 |  | 10 | BH-IV | [6 empty] | Part B | [6 empty] | ¦
| PS logging (to be performed after BH completion) |  |  |  | 60 |  | 10 | PSL |  |  | Allowed factor in WOW estimation between CTR and CPY |  |  |  | Part A | [6 empty] | ¦
| Borehole Downhole density logging and Spectral gamma and downhole magnetic resonance logging |  |  |  | 60 |  | 10 | Gamma | [6 empty] | Part B | [6 empty] | ¦
[11 empty] | min | max
| II. Vessels used for which equipment & Limiting condition and required weather window |  |  |  |  | Hs (m) | Vw (m/s) | Ww (hrs) |  | II.0 | 0.75 | 1.25 |  |  | Hs | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.75 | 3 | 3.5 | 4 | 4.5 | 5
| Part A | Name of vessel 1 | [7 empty] | II.1 |  |  |  |  | Vw | 2 | 4 | 6 | 8 | 9 | 10 | 11 | 12 | 15 | 20 | 25
| Part B | Name of vessel 2 | [8 empty] | Error message if no price in remuneration section |  |  |  | Ww | 1 | 2 | 4 | 6 | 12 | 18 | 24 | 48 | 72
| Part C | Name of vessel 3
| Part D | Name of vessel 4 | [8 empty] | FILL UNIT RATE
|  | BH: Borehole | [7 empty] | II.2
Days between desired and ultimate report due date
| III. Cycle Time Geotechnical Survey (excluding weather) |  |  | Max duration (days) | Unit | Cycle | Qty | Total (days) | (end) date
| Key dates | [8 empty] | III.0 | 45 | [6 empty] | Scaling Factor | 1.95 | [7 empty] | % of push/piston sampling |  |  |  | 95%
| 1a | COMMENCEMENT DATE WORK | [6 empty] | 2020-12-03 | [8 empty] | Advanced scaling | 1.5 | [7 empty] | qty pf push/piston sampling |  |  |  | 5435
| 1b | CLIENT confirmation target coordinates and target depths of boreholes | [6 empty] | 2021-05-14 |  | Report max update/review time (days) | [6 empty] | Quantity of type of testing by borehole | [8 empty] | qty of hammer sampling |  |  |  | 286
| Preparation | [11 empty] | CTR |  | CPY |  |  |  | BH-I | BH-II | BH-III | BH-IV |  |  |  |  | qty of location with DH SCPT |  |  |  | 37
| 2a | 1st revision of project documentation (PQP, PEP) | (Max: 4 weeks) | 28 | days |  | Fill number of days |  | 2020-12-03 | III.1 |  |  | Seabed | Downhole | Seabed | Downhole |  | Sample | 58 | 12 | 5 | 2 | need to check these numbers |  |  |  | qty DH SCPT |  |  |  | 438
| 2b | Review 1st revision project documentation (PQP, PEP) |  |  | days | 14 |  |  | 2020-12-17 |  | 1 | Field | 7 | 14 | #N/A | #N/A |  | PCPT | 8 | 0 | 30 | 10 | need to check these numbers |  |  |  | qty DH PCPT |  |  |  | 1070
| 2c | 2nd revision of project documentation (PQP, PEP) | (Max: 1 week) | 7 | days |  | Fill number of days |  | 2020-12-17 |  | 2 | Interim | #N/A | 28 | #N/A | 14 |  | SCPT | 2 | 30 | 0 | 0 | need to check these numbers |  |  |  | SCPT & PCPT swap within 1 BH |  |  |  | 74
| 2d | Review 2nd revision project documentation (PQP, PEP) |  |  | days | 7 |  |  | 2020-12-24 |  | 3 | 1st draft | 35 | 49 | 21 | 21 | [10 empty] | Probability extension BH-I to 80m |  |  |  | 30%
| 2e | Finalise project documentation (incl additional revisions/review rounds) | (Max: 1 week) | 7 | days |  | Fill number of days |  | 2020-12-24 |  | 4 | 2nd draft | 14 | 14 | 14 | 7 |  | Percentage of BH with SCPT testing | [8 empty] | Probability of seabed CPT to reach 60m |  |  |  | 70%
| 2f | Review final version of project documentation (PQP, PEP) |  |  | days | 2 |  |  | 2020-12-26 |  | 5 | final | 14 | 7 | 7 | 7 |  |  | BH-I | BH-II | BH-III | BH-IV |  |  |  |  | Depth Seabed CPT if early refusal (m) |  |  |  | 25
| 2g | Minimum number of days between finalization project documentation and start mobilization | (Min: 3 days) | 3 | days | 3 |  |  | 2020-12-27 |  | 6 | cy 1st draft | #N/A | 196 | #N/A | 21 |  | SCPT (%) | 25% | 100% | 0% | 0% |  |  |  |  | % of possible additional locations |  |  |  | 15%
| 2h | Clearance of borehole locations (days after CLIENT issues target locations) | (Max: 4 weeks) | 28 | days |  | Fill number of days |  | 2021-05-14 |  | 7 | cy 2nd draft | #N/A | 21 | #N/A | 14 | [10 empty] | % of retest by locations |  |  |  | 10%
[11 empty] | 8 | cy final | #N/A | 7 | #N/A | 7 | [10 empty] | Number of VC by group |  |  |  | 5
| PART A | Survey Campaign - Name of vessel 1 - Surveying ¦BH¦ | [7 empty] | III.2
| 3a | Start of Mobilisation (earliest starting date is 1-jun-2021) |  |  |  |  | Fill Start date
| 3b | Mobilisation and transit to site | (Max: 1 week) | 7 | days |  | Fill number of days |  | 0 |  | Total quantity | [5 empty] | 50% moment | 0
| 3c | Start of survey WORK | [6 empty] | 0 | [7 empty] | days after | -44330
| 3d | Execution of BH Type 1 (quasi-continuous sampling and PCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 95 | 0 | 0 |  | 95 | 0 |  |  |  |  | weight | 98.71%
| 3e | Extension of BH Type 1 (quasi-continuous sampling and PCPT) by an additional 20 m |  |  | hrs/location |  | 28 | 0 | 0 |  | 13 | 0
| 3f | Execution of BH Type 2 (quasi continuous downhole SCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 13 | 0 | 0 |  | 7 | 0
| 3g | Execution of BH Type 3 (combined downhole sampling/PCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 7 | 0 | 0 |  | 10 | 0
| 3h | Execution of BH Type 4 (destructive drilling) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location |  | 10 | 0 | 0 |  | TRUE | 0
| 3i | Offshore Completion Date PART A Name of vessel 1 ¦ Excluding WAITING ON WEATHER | [6 empty] | 0
| 3j | Offshore Completion Date PART A Name of vessel 1 ¦ Including WAITING ON WEATHER calculated by Client |  | 30 |  |  | WAITING ON WEATHER DAYS | Fill Hs, Vw, Ww (II.1)
| 3k | Offshore Completion Date PART A Name of vessel 1 ¦ Including WAITING ON WEATHER calculated by TENDERER |  |  |  |  | WAITING ON WEATHER DAYS |  | 0 | III.3
Explanation for difference between WOW calculated by CLIENT and WOW according to TENDERER.
| 4a | Start of Mobilisation (earliest starting date is 1-jun-2021) | [6 empty] | 2021-06-01
| 4b | Mobilisation and transit to site | (Max: 1 week) | 7 | days | 7 |  |  | 2021-06-08 | [7 empty] | 50% moment | 2021-06-01
| 4c | Start of survey WORK | [6 empty] | 2021-06-08 | [7 empty] | days after | 18
| 4d | Execution of BH Type 1 (quasi-continuous sampling and PCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 24 | 0 | 0 | 2021-06-08 | [7 empty] | weight | 0%
| 4e | Extension of BH Type 1 (quasi-continuous sampling and PCPT) by an additional 20 m |  |  | hrs/location | 4 | 0 | 0 | 2021-06-08
| 4f | Execution of BH Type 2 (quasi continuous downhole SCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 22 | 0 | 0 | 2021-06-08
| 4g | Execution of BH Type 3 (combined downhole sampling/PCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 22 | 0 | 0 | 2021-06-08
| 4h | Execution of BH Type 4 (destructive drilling) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 10 | 0 | 0 | 2021-06-08
| 4i | Offshore Completion Date Name of vessel 2 ¦ Excluding WAITING ON WEATHER | [6 empty] | 2020-12-27
| 4j | Offshore Completion Date Name of vessel 2 ¦ Including WAITING ON WEATHER calculated by Client |  | 30 |  |  | WAITING ON WEATHER DAYS | Fill Hs, Vw, Ww (II.1)
| 4k | Offshore Completion Date Name of vessel 2 ¦ Including WAITING ON WEATHER calculated by TENDERER |  |  |  |  | WAITING ON WEATHER DAYS | 0 | 2020-12-27 | III.3
Explanation for difference between WOW calculated by CLIENT and WOW according to TENDERER.
| 5a | Start of Mobilisation (earliest starting date is 1-jun-2021) | [6 empty] | 2021-06-01
| 5b | Mobilisation and transit to site | (Max: 1 week) | 7 | days | 7 |  |  | 2021-06-08 | [7 empty] | 50% moment | 2021-06-01
| 5c | Start of survey WORK | [6 empty] | 2021-06-08 | [7 empty] | days after | 18
| 5d | Execution of BH Type 1 (quasi-continuous sampling and PCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 24 | 0 | 0 | 2021-06-08 | [7 empty] | weight | 0%
| 5e | Extension of BH Type 1 (quasi-continuous sampling and PCPT) by an additional 20 m |  |  | hrs/location | 4 | 0 | 0 | 2021-06-08
| 5f | Execution of BH Type 2 (quasi continuous downhole SCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 22 | 0 | 0 | 2021-06-08
| 5g | Execution of BH Type 3 (combined downhole sampling/PCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 22 | 0 | 0 | 2021-06-08
| 5h | Execution of BH Type 4 (destructive drilling) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 10 | 0 | 0 | 2021-06-08
| 5i | Offshore Completion Date Name of vessel 3 ¦ Excluding WAITING ON WEATHER | [6 empty] | 2020-12-27
| 5j | Offshore Completion Date Name of vessel 3 ¦ Including WAITING ON WEATHER calculated by Client |  | 30 |  |  | WAITING ON WEATHER DAYS | Fill Hs, Vw, Ww (II.1)
| 5k | Offshore Completion Date Name of vessel 3 ¦ Including WAITING ON WEATHER calculated by TENDERER |  |  |  |  | WAITING ON WEATHER DAYS | 0 | 2020-12-27 | III.3
Explanation for difference between WOW calculated by CLIENT and WOW according to TENDERER.
| 6a | Start of Mobilisation (earliest starting date is 1-jun-2021) | [6 empty] | 2021-06-01
| 6b | Mobilisation and transit to site | (Max: 1 week) | 7 | days | 7 |  |  | 2021-06-08 | [7 empty] | 50% moment | 2021-06-01
| 6c | Start of survey WORK | [6 empty] | 2021-06-08 | [7 empty] | days after | 18
| 6d | Execution of BH Type 1 (quasi-continuous sampling and PCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 24 | 0 | 0 | 2021-06-08 | [7 empty] | weight | 0%
| 6e | Extension of BH Type 1 (quasi-continuous sampling and PCPT) by an additional 20 m |  |  | hrs/location | 4 | 0 | 0 | 2021-06-08
| 6f | Execution of BH Type 2 (quasi continuous downhole SCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 22 | 0 | 0 | 2021-06-08
| 6g | Execution of BH Type 3 (combined downhole sampling/PCPT) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 22 | 0 | 0 | 2021-06-08
| 6h | Execution of BH Type 4 (destructive drilling) to a target depth of 60 m, incl. sailing to location and positioning at site, excl. WoW |  |  | hrs/location | 10 | 0 | 0 | 2021-06-08
| 6i | Offshore Completion Date Name of vessel 4 ¦ Excluding WAITING ON WEATHER | [6 empty] | 2020-12-27
| 6j | Offshore Completion Date Name of vessel 4 ¦ Including WAITING ON WEATHER calculated by Client |  | 30 |  |  | WAITING ON WEATHER DAYS | Fill Hs, Vw, Ww (II.1)
| 6k | Offshore Completion Date Name of vessel 4 ¦ Including WAITING ON WEATHER calculated by TENDERER |  |  |  |  | WAITING ON WEATHER DAYS | 0 | 2020-12-27 | III.3
Explanation for difference between WOW calculated by CLIENT and WOW according to TENDERER.
Data Processing and report
| 7a | OFFSHORE COMPLETION DATE for High Priority Area (50%) (including WAITING ON WEATHER) - Lot 2 (Geotechnical Boreholes) - calculated by CLIENT based on weighted average | [6 empty] | 1901-07-25
| 7b | OFFSHORE COMPLETION DATE for High Priority Area (50%) (including WAITING ON WEATHER) - Lot 2 (Geotechnical Boreholes) - provided by TENDERER | [7 empty] | III.4
| 7c | OFFSHORE COMPLETION DATE for All Geotechnical Boreholes (including WAITING ON WEATHER) - Lot 2 | [6 empty] | 0
| 7d | Delivery of 1st Version "Operations Report (Lot 2)" (days after OFFSHORE COMPLETION DATE) | (Max: 1 week) | 7 | days |  | Fill number of days |  | 0 | III.5
| 7e | CLIENT review of 1st Version "Operations Report (Lot 2)" |  |  | days | 14 |  |  | 1900-01-13
| 7f | Delivery of Final Version "Operations Report (Lot 2)" | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 0
| 7g | Delivery of 1st Version (Field Report) "Geotechnical Boreholes Report" - High Priority Area (HPA) (days after OFFSHORE COMPLETION DATE - HPA) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 0
| 7h | CLIENT review of 1st Version (Field Report) "Geotechnical Boreholes Report" - HPA |  |  | days | 21 |  |  | 1900-01-20
| 7i | Delivery of 2nd Version "Geotechnical Boreholes Report" (including partial standard lab testing results) - HPA | (Max: 18 weeks) | 126 | days |  | Fill number of days |  | 1900-01-20
| 7j | CLIENT review of 2nd Version "Geotechnical Boreholes Report" (including partial standard lab testing results) - HPA |  |  | days | 14 |  |  | 1900-02-03
| 7k | Delivery of 3rd revision "Geotechnical Boreholes Report" (including complete standard test results & Age Dating) - HPA | (Max: 6 weeks) | 42 | days |  | Fill number of days |  | 1900-02-03
| 7l | CLIENT review of 3rd revision "Geotechnical Boreholes Report" (including complete standard test results & Age Dating) - HPA |  |  | days | 14 |  |  | 1900-02-17
| 7m | Delivery of Final Version "Geotechnical Boreholes Report" - HPA | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 1900-02-17
| 7n | Delivery of 1st Version (Field Report) "Geotechnical Boreholes Report" - Low Priority Area (LPA) (days after OFFSHORE COMPLETION DATE - all) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 0
| 7o | CLIENT review of 1st Version (Field Report) "Geotechnical Boreholes Report" - LPA |  |  | days | 21 |  |  | 1900-01-20
| 7p | Delivery of 2nd Version "Geotechnical Boreholes Report" (including partial standard lab testing results) - LPA | (Max: 20 weeks) | 140 | days |  | Fill number of days |  | 1900-01-20
| 7q | CLIENT review of 2nd Version "Geotechnical Boreholes Report" (including partial standard lab testing results) - LPA |  |  | days | 14 |  |  | 1900-02-03
| 7r | Delivery of 3rd revision "Geotechnical Boreholes Report" (including complete standard test results & Age Dating) - LPA | (Max: 12 weeks) | 84 | days |  | Fill number of days |  | 1900-02-03
| 7s | CLIENT review of 3rd revision "Geotechnical Boreholes Report" (including complete standard test results & Age Dating) - LPA |  |  | days | 14 |  |  | 1900-02-17
| 7t | Delivery of Final Version "Geotechnical Boreholes Report" - LPA | (Max: 4 weeks) | 28 | days |  | Fill number of days |  | 1900-02-17
| 7u | Delivery of 1st Version "Advanced Laboratory Testing Report" (includes partial set of cyclic/dynamic tests) (days after OFFSHORE COMPLETION DATE - HPA) | (Max: 20 weeks) | 140 | days |  | Fill number of days |  | 0
| 7v | CLIENT review of 1st Version "Advanced Laboratory Testing Report" |  |  | days | 21 |  |  | 1900-01-20
| 7w | Delivery of 2nd Version "Advanced Laboratory Testing Report" (includes complete set of results for HPA & partial for LPA) | (Max: 15 weeks) | 105 | days |  | Fill number of days |  | 1900-01-20
| 7x | CLIENT review of 2nd Version "Advanced Laboratory Testing Report" |  |  | days | 14 |  |  | 1900-02-03
| 7y | Delivery of 3rd Version (Approved for Public Issue during HPA Tender) "Advanced Laboratory Testing Report" (includes complete set of results for HPA & partial for LPA) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 1900-02-03
| 7z | Delivery of 4th Version "Advanced Laboratory Testing Report" (includes complete set of results for HPA & LPA) | (Max: 40 weeks) | 280 | days |  | Fill number of days |  | 1900-02-03
| 7aa | CLIENT review of 4th Version "Advanced Laboratory Testing Report" |  |  | days | 14 |  |  | 1900-02-17
| 7ab | Delivery of Final Version "Advanced Laboratory Testing Report" | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 1900-02-17
| 7ac | Completion Date Reporting - Geotechnical Boreholes Report - HPA (7m) | [6 empty] | 1900-02-17
| 7ad | Completion Date Reporting - Geotechnical Boreholes Report - LPA (7t) | [6 empty] | 1900-02-17
| 7ae | Completion Date Reporting - Advanced Laboratory Testing Report (3rd Version for HPA Tender) (7y) | [6 empty] | 1900-02-03
| 7af | Completion Date Reporting - Advanced Laboratory Testing Report (Final Version for LPA Tender) (7ab) | [6 empty] | 1900-02-17
| TOTAL DURATION CYCLE TIME INCLUDING WEATHER - Lot 2 (HIGH PRIORITY AREA) | [6 empty] | -44119 | days
| TOTAL DURATION CYCLE TIME INCLUDING WEATHER - Lot 2 (LOW PRIORITY AREA) | [6 empty] | -44119 | days
IV. Rates Geotechnical Site Survey - Ijmuiden Ver
| ITEM |  |  |  |  | Unit Rate | Unit | Qty | Price | IV.0
| 1 | Mobilisation/demobilisation of vessel(s), survey equipment and personnel to site
| 1.1 | Mob/demob vessel Name of vessel 1 incl. vessel equipment and personnel |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.2 | Mob/demob vessel Name of vessel 2 incl. vessel equipment and personnel |  |  |  |  | Lump sum | 0 | FILL UNIT RATE
| 1.3 | Mob/demob vessel Name of vessel 3 incl. vessel equipment and personnel |  |  |  |  | Lump sum | 0 | FILL UNIT RATE
| 1.4 | Mob/demob vessel Name of vessel 4 incl. vessel equipment and personnel |  |  |  |  | Lump sum | 0 | FILL UNIT RATE
| 1.5 | Mob/demob drilling and downhole sampling/PCPT equipment and personnel |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.6 | Mob/demob downhole SCPT equipment and personnel |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.7 | Mob/demob downhole PS-logging equipment and personnel |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.8 | Mob/demob downhole density and spectral gamma logging equipment and personnel |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 2 | Survey Operations incl transit from and to site excluding WOW
| 2.1 | Positioning and setting-up on first borehole at a new location (including transiting from previous location) |  |  |  |  | /borehole | 125 | FILL UNIT RATE
| 2.2 | Re-positioning and setting-up on additional boreholes at same location |  |  |  |  | /borehole | 13 | FILL UNIT RATE
| 2.3 | Changing over between piezocone and seismic cone mid-way through a borehole |  |  |  |  | /event | 74 | FILL UNIT RATE
| 2.4 | Drilling performance (between seabed and 60m depth) |  |  |  |  | /m | 7500 | FILL UNIT RATE
| 2.5 | Drilling performance (between 60m and 80m depth) |  |  |  |  | /m | 710 | FILL UNIT RATE
| 2.6 | Drilling performance (between 80m and 100m depth) |  |  |  |  | /m | 140 | FILL UNIT RATE
| 2.7 | Execution of push sampling (including any oversampling) |  |  |  |  | /sample | 5435 | FILL UNIT RATE
| 2.8 | Execution of hammer sampling (including any oversampling) |  |  |  |  | /sample | 286 | FILL UNIT RATE
| 2.9 | Execution of downhole PCPT push (up to 3m stroke length) |  |  |  |  | /push | 1070 | FILL UNIT RATE
| 2.10 | Execution of downhole SCPT push (up to 3m stroke length) excluding seismic tests |  |  |  |  | /push | 438 | FILL UNIT RATE
| 2.11 | Execution of individual seismic test using downhole SCPT tool |  |  |  |  | /test | 438 | FILL UNIT RATE
| 2.12 | Execution of individual seismic tests using P-S logging tool |  |  |  |  | /test | 600 | FILL UNIT RATE
| 2.13 | Execution of Downhole density logging |  |  |  |  | /m | 600 | FILL UNIT RATE
| 2.14 | Execution of Spectral gamma logging |  |  |  |  | /m | 600 | FILL UNIT RATE
| 2.15 | Micro sitting for positioning at borehole location due to unexpected high gradient of seabed frame preventing the work |  |  |  |  | /location | 125 | FILL UNIT RATE
| 2.16 | Port call for Name of vessel 1 during surveying PART A |  |  |  |  | /call | 0 | FILL UNIT RATE
| 2.17 | Port call for Name of vessel 2 during surveying PART B |  |  |  |  | /call | 5 | FILL UNIT RATE
| 2.18 | Port call for Name of vessel 3 during surveying PART C |  |  |  |  | /call | 0 | FILL UNIT RATE
| 2.19 | Port call for Name of vessel 4 during surveying PART D |  |  |  |  | /call | 0 | FILL UNIT RATE
| 3 | Lab Testing
Standard Lab Testing Programme (all soil types)
| 3.1 | Particle density |  |  |  |  | /test | 878 | FILL UNIT RATE
| 3.2 | Carbonate tests |  |  |  |  | /test | 839 | FILL UNIT RATE
| 3.3 | Organic tests (dichromate) |  |  |  |  | /test | 722 | FILL UNIT RATE
| 3.4 | Organic tests (loss on ignition) |  |  |  |  | /test | 195 | FILL UNIT RATE
| 3.5 | Organic and total carbon content (Elementary analysis) |  |  |  |  | /test | 390 | FILL UNIT RATE
| 3.6 | Electrical resistivity (as input for heat capacity calculations) |  |  |  |  | /test | 108 | FILL UNIT RATE
| 3.7 | Pore water salinity (as input for heat capacity calculations) |  |  |  |  | /test | 108 | FILL UNIT RATE
| 3.8 | Microscopic photography (as input for heat capacity calculations) |  |  |  |  | /test | 108 | FILL UNIT RATE
Standard Lab Testing Programme (cohesionless soil)
| 3.9 | Binocular microscopy tests including photography (for general purpose or where batching of samples is being considered) |  |  |  |  | /test | 371 | FILL UNIT RATE
| 3.10 | Particle size analysis (sieve) |  |  |  |  | /test | 1560 | FILL UNIT RATE
| 3.11 | Particle size analysis (using sieve and hydrometer for fines fraction) |  |  |  |  | /test | 488 | FILL UNIT RATE
| 3.12 | Maximum and minimum density |  |  |  |  | /test | 449 | FILL UNIT RATE
| 3.13 | Permeability tests with permeameter |  |  |  |  | /test | 155 | FILL UNIT RATE
| 3.14 | Permeability tests in triaxial cell (using a CID test sample) |  |  |  |  | /test | 39 | FILL UNIT RATE
| 3.15 | Permeability tests in triaxial cell (as a standalone test) |  |  |  |  | /test | 117 | FILL UNIT RATE
| 3.16 | Thermal conductivity tests on fully-saturated cohesionless samples using needle probe (ASTM D5334-14) |  |  |  |  | /test | 108 | FILL UNIT RATE | IV.1
| 3.17 | Thermal conductivity tests on fully-saturated cohesionless samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). |  |  |  |  | /test | 108 | FILL UNIT RATE
| 3.18 | Isotropically consolidated drained (CID) triaxial compression tests (N.B. one "test" constitutes three individual sub-tests on three specimens at three different consolidation pressures) |  |  |  |  | /test | 507 | FILL UNIT RATE
| 3.19 | Ring shear tests (soil/soil) |  |  |  |  | /test | 166 | FILL UNIT RATE
| 3.20 | Ring shear tests (soil/steel) |  |  |  |  | /test | 229 | FILL UNIT RATE
| 3.21 | Bender element tests (as part of a CID or DSS test) |  |  |  |  | /test | 166 | FILL UNIT RATE
| 3.22 | Consolidated drained direct shear (shear box) tests (N.B. one "test" constitutes three individual sub-tests on three specimens at three different normal pressures) |  |  |  |  | /test | 283 | FILL UNIT RATE
| 3.23 | Microbially Influenced Corrosion (MIC) testing |  |  |  |  | /test | 78 | FILL UNIT RATE
Standard Lab Testing Programme (cohesive soil)
| 3.24 | Particle size analysis (using hydrometer for fines and if applicable sieve) |  |  |  |  | /test | 117 | FILL UNIT RATE
| 3.25 | Atterberg limits (liquid and plastic limits, cone method) |  |  |  |  | /test | 439 | FILL UNIT RATE
| 3.26 | Permeability tests in triaxial cell (using a CIU test sample) |  |  |  |  | /test | 39 | FILL UNIT RATE
| 3.27 | Thermal conductivity tests on fully-saturated undisturbed cohesive samples using needle probe (ASTM D5334-14) |  |  |  |  | /test | 92 | FILL UNIT RATE | IV.1
| 3.28 | Thermal conductivity tests on fully-saturated remoulded cohesive samples using needle probe (ASTM D5334-14) |  |  |  |  | /test | 12 | FILL UNIT RATE
| 3.29 | Thermal conductivity tests on fully-saturated undisturbed cohesive samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). |  |  |  |  | /test | 20 | FILL UNIT RATE
| 3.30 | Thermal conductivity tests on fully-saturated remoulded cohesive samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). |  |  |  |  | /test | 8 | FILL UNIT RATE
| 3.31 | One-dimensional consolidation (oedometer) tests up to 8 load and 4 unload stages (state whether BS or Norwegian method) |  |  |  |  | /test | 43 | FILL UNIT RATE
| 3.32 | Additional reload loops in one-dimensional consolidation (oedometer) tests |  |  |  |  | /loop | 43 | FILL UNIT RATE
| 3.33 | Constant Rate of Strain (CRS) compressibility tests (max. 4 days) |  |  |  |  | /test | 106 | FILL UNIT RATE
| 3.34 | Overdays Constant Rate of Strain (CRS) compressibility tests |  |  |  |  | /day | 621 | FILL UNIT RATE
| 3.35 | Unconsolidated undrained (UU) triaxial compression tests on undisturbed samples |  |  |  |  | /test | 20 | FILL UNIT RATE
| 3.36 | Unconsolidated undrained (UU) triaxial compression tests on remoulded samples |  |  |  |  | /test | 20 | FILL UNIT RATE
| 3.37 | Isotropically consolidated undrained triaxial compression test (CIU) (comprising saturation, consolidation and shearing, max. 4 days) |  |  |  |  | /test | 49 | FILL UNIT RATE
| 3.38 | Overdays Isotropically consolidated undrained triaxial compression test (CIU) |  |  |  |  | /day | 383 | FILL UNIT RATE
| 3.39 | Anisotropically consolidated undrained triaxial compression test (CAUc) (comprising saturation, consolidation and shearing, max. 4 days) |  |  |  |  | /test | 90 | FILL UNIT RATE
| 3.40 | Overdays anisotropically consolidated undrained triaxial compression test (CAUc) |  |  |  |  | /day | 702 | FILL UNIT RATE
| 3.41 | Anisotropically consolidated undrained triaxial extension test (CAUe) (comprising saturation, consolidation and shearing, max. 4 days) |  |  |  |  | /test | 20 | FILL UNIT RATE
| 3.42 | Overdays anisotropically consolidated undrained triaxial extension test (CAUe) |  |  |  |  | /day | 156 | FILL UNIT RATE
| 3.43 | Ring shear tests (soil/soil) |  |  |  |  | /test | 39 | FILL UNIT RATE
| 3.44 | Ring shear tests (soil/steel) |  |  |  |  | /test | 59 | FILL UNIT RATE
| 3.45 | Bender element tests (as part of the CIU, CAU or DSS test) |  |  |  |  | /test | 43 | FILL UNIT RATE
| 3.46 | Microbially Influenced Corrosion (MIC) testing |  |  |  |  | /test | 78 | FILL UNIT RATE
Standard Lab Testing Programme (Age Dating)
| 3.47 | Palynology analysis |  |  |  |  | /sample | 449 | FILL UNIT RATE
| 3.48 | Analysis of Algae |  |  |  |  | /sample | 371 | FILL UNIT RATE
| 3.49 | Analysis of Fungi |  |  |  |  | /sample | 371 | FILL UNIT RATE
| 3.50 | Analysis of Spores |  |  |  |  | /sample | 371 | FILL UNIT RATE
| 3.51 | Nanno- or micro-fossil analysis including Dinoflagellate Cysts and Foraminifera |  |  |  |  | /sample | 371 | FILL UNIT RATE
| 3.52 | Carbon dating analysis |  |  |  |  | /sample | 20 | FILL UNIT RATE
| 3.53 | Mollucs |  |  |  |  | /sample | 20 | FILL UNIT RATE
| 3.54 | Diatoms |  |  |  |  | /sample | 20 | FILL UNIT RATE
Advanced Lab Testing Programme (Cyclic and dynamic tests)
| 3.55 | Cyclic direct simple shear tests (CSS) with pre-shearing (including three test stages as per SoW; cohesionless soils; under "drained" or "undrained" conditions) |  |  |  |  | /test | 197 | FILL UNIT RATE
| 3.56 | Cyclic direct simple shear tests (CSS) without pre-shearing (including two test stages as per SoW; cohesionless or cohesive soils; under "drained" or "undrained" conditions) |  |  |  |  | /test | 108 | FILL UNIT RATE
| 3.57 | CSS extra loading stage (up to 1500 load cycles; cohesionless or cohesive soils; under "drained" or "undrained" conditions) |  |  |  |  | /stage | 23 | FILL UNIT RATE
| 3.58 | Post cyclic static testing to failure if cyclic CSS test failure does not occur |  |  |  |  | /test | 122 | FILL UNIT RATE
| 3.59 | Cyclic triaxial compression tests (CTX) (including three test stages as per SoW; cohesionless or cohesive soils; under "drained" or "undrained" conditions) |  |  |  |  | /test | 90 | FILL UNIT RATE
| 3.60 | CTX extra loading stage (up to 1500 load cycles; cohesionless or cohesive soils; under "drained" or "undrained" conditions) |  |  |  |  | /stage | 12 | FILL UNIT RATE
| 3.61 | Post cyclic static testing to failure if cyclic CTX test failure does not occur |  |  |  |  | /test | 45 | FILL UNIT RATE
| 3.62 | Resonant column (RC) test (including initial loading and repeat loading as per SoW; cohesionless and cohesive samples; under "drained" or "undrained" conditions) |  |  |  |  | /test | 18 | FILL UNIT RATE
| 3.63 | RC extra loading stage (cohesionless and cohesive samples; under "drained" or "undrained" conditions) |  |  |  |  | /stage | 9 | FILL UNIT RATE
Advanced Lab Testing Programme (Classification and static reference tests)
| 3.64 | Particle size distribution analyses (sieve) (for batch samples) |  |  |  |  | /test | 15 | FILL UNIT RATE
| 3.65 | Microscopic photography (for batch samples) |  |  |  |  | /test | 15 | FILL UNIT RATE
| 3.66 | Direct simple shear test, constant volume or constant stress (N.B. only one specimen tested under one set of conditions) |  |  |  |  | /test | 32 | FILL UNIT RATE
| 3.67 | Isotropically consolidated drained (CID) triaxial compression tests (N.B. only one specimen tested under one consolidation pressure) |  |  |  |  | /test | 9 | FILL UNIT RATE
| 3.68 | (An)isotropically consolidated undrained triaxial compression test (CIUc/CAUc) (comprising saturation, consolidation and shearing, max. 4 days) |  |  |  |  | /test | 44 | FILL UNIT RATE
| 3.69 | Overdays (an)isotropically consolidated undrained triaxial compression test (CAUc) |  |  |  |  | /day | 86 | FILL UNIT RATE
| 3.70 | Anisotropically consolidated undrained triaxial extension test (CAUe) (comprising saturation, consolidation and shearing, max. 4 days) |  |  |  |  | /test | 3 | FILL UNIT RATE
| 3.71 | Overdays anisotropically consolidated undrained triaxial extension test (CAUe) |  |  |  |  | /day | 6 | FILL UNIT RATE
| 4 | Reporting
| 4.1 | Geotechnical Boreholes Report for HPA (including all results from in situ testing, standard laboratory testing programme, Age Dating analysis and MIC assessment) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 4.2 | Geotechnical Boreholes Report for LPA (including all results from in situ testing, standard laboratory testing programme, Age Dating analysis and MIC assessment) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 4.3 | Operations Report (Lot 2) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 4.4 | Advanced Laboratory Testing Report (including all classification, static, cyclic and dynamic test results from Advanced Lab Testing programme for HPA & LPA) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 4.5 | Additional reporting associated with numbers of boreholes in excess of base scope |  |  |  |  | /location | 5 | FILL UNIT RATE
| 4.6 | Additional reporting associated with each downhole SCPT seismic test in excess of base scope |  |  |  |  | /test | 10 | FILL UNIT RATE
| 4.7 | Additional reporting associated with each seismic test undertaken using P-S logging tool in excess of base scope |  |  |  |  | /test | 10 | FILL UNIT RATE
| 4.8 | Additional reporting associated with downhole spectral gamma logging in excess of base scope |  |  |  |  | /metre | 10 | FILL UNIT RATE
| 4.9 | Additional reporting associated with downhole density logging in excess of base scope |  |  |  |  | /metre | 10 | FILL UNIT RATE
| 4.10 | Lab test processing/reporting and any other expenses associated with lab testing not covered by other items above. |  |  |  |  | % of total lab testing price |  | FILL UNIT RATE
| 5 | Waiting on Weather | [7 empty] | IV.2
| 5.1 | Waiting on Weather Name of vessel 1 during surveying PART A |  |  |  |  | /day | 0 | FILL UNIT RATE
| 5.2 | Waiting on Weather Name of vessel 2 during surveying PART B |  |  |  |  | /day | 0 | FILL UNIT RATE
| 5.3 | Waiting on Weather Name of vessel 3 during surveying PART C |  |  |  |  | /day | 0 | FILL UNIT RATE
| 5.4 | Waiting on Weather Name of vessel 4 during surveying PART D |  |  |  |  | /day | 0 | FILL UNIT RATE
| 6 | Other
| 6.1 | Project meetings to be held in CLIENT offices (Utrecht or The Hague) |  |  |  |  | /meeting | 15 | FILL UNIT RATE
| 6.2 | Additional UXO clearance measures for borehole locations |  |  |  |  | /location | 125 | FILL UNIT RATE
| 6.3 | Interaction with Lot 1 contractor and certification authorities (estimated 200hrs for senior level personnel) |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE
| 6.4 | Activities related to dissemination of results (webinar and Project Site Description) |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE | IV.3
V. INPUT FOR ASSESSMENT OF THE OFFER
| INPUT FOR ASSESSMENT OF THE PRICE CRITERION - Fixed prices/rates | [8 empty] | V.0
Weighing
| Option 1/3 | Total cost for executing the survey excluding WAITING ON WEATHER / risk sharing | Survey works |  |  |  | 0 | 50% |  | V.1
|  |  | Expected costs for WOW for Vessel 1 |  |  |  | FILL UNIT RATE
|  |  | Expected costs for WOW for Vessel 2 |  |  |  | 0
|  |  | Expected costs for WOW for Vessel 3 |  |  |  | 0
|  |  | Expected costs for WOW for Vessel 4 |  |  |  | 0
|  |  | Webinar Activities |  |  |  | FILL UNIT RATE
| Option 2 | Total cost for executing the survey including WAITING ON WEATHER | Survey works |  |  |  | 0 | 50% |  | V.2
Allowance for WOW for Vessel 1
Allowance for WOW for Vessel 2
Allowance for WOW for Vessel 3
Allowance for WOW for Vessel 4
|  |  | Webinar Activities |  |  |  | FILL UNIT RATE
| TOTAL VIRTUAL PRICE for assessment | [6 empty] | 0 |  | V.3
|  |  | Max. number of points that can be awarded |  |  |  |  | 20
|  |  | Minimum Price (determined by CLIENT) |  |  |  |  | 15000000
|  |  | Maximum Price (determined by CLIENT) |  |  |  |  | 25000000
|  |  | Points gained for the TOTAL PRICE proposed: |  |  |  |  | 0 | Points
| INPUT FOR ASSESSMENT OF THE COMPLETION DATE / CYCLE TIME CRITERION (Ability to finalize the offshore campaign at the preferred end date as set by CLIENT): | [8 empty] | V.4
|  |  | Earliest MOBILIZATION DATE set by CLIENT |  |  |  |  | 2021-06-01
|  |  | Desired OFFSHORE COMPLETION DATE for High Priority Area set by CLIENT (incl. WOW) |  |  |  |  | 2021-08-14
| Key Completion Dates |  | Ultimate OFFSHORE COMPLETION DATE for High Priority Area set by CLIENT (incl. WOW) |  |  |  |  | 2021-09-28
[7 empty] | OFFSHORE COMPLETION DATE High Priority Area determined by input TENDERER | 0 |  | V.5
[7 empty] | Desired date for DELIVERY OF FINAL GEOTECHNICAL BOREHOLE REPORT for High Priority Area (7m) set by CLIENT (incl. WOW) | 2022-02-01
[7 empty] | Desired date for DELIVERY OF ALL FINAL REPORTS for High Priority Area (7y, 7m) set by CLIENT (incl. WOW) | 2022-04-17
[7 empty] | Ultimate date for DELIVERY OF FINAL REPORTS for HPA, set by CLIENT (incl. WOW) | 2022-06-01
[7 empty] | DELIVERY OF FINAL REPORTS for High Priority Area determined by input TENDERER | 1900-02-17 |  | V.5
[7 empty] | TOTAL difference DELIVERY OF FINAL REPORTS for High Priority Area from desired date (for assessment) | -44619 | days
|  |  | Max. number of points that can be awarded |  |  |  |  | 12
[5 empty] | Points for the TOTAL CYCLE TIME proposed: |  |  | 12 | Points
| TOTAL POINTS GAINED BY TENDERER | [6 empty] | 12 | Points
VI. NOTES
| I.0 | IN CASE A CELL IN THIS ANNEX 4b IS COLORED RED AS SHOWN IN THIS CELL THE PROPOSAL IS NOT VALID.
| I.0 | TENDERER to check verify whether: - The checkboxes for the boreholes have been checked once; - The project documentation is finalized 3 days before the first mobilisation date as set by TENDERER; - The planned MOBILISATION date is not before the earliest MOBILISATION date (1-jun-2021) - The planned OFFSHORE COMPLETION DATE (incl. WAITING ON WEATHER) is not later than the ultimate date set by CLIENT; - The planned completion date for the final report is not later than the ultimate date set by CLIENT; - The TOTAL VIRTUAL PRICE is within the range set by CLIENT; - Cycle times are within ranges allowed by CLIENT
| I.0 | All numbers indicated in green are starting points set by CLIENT.
| I.0 | All numbers indicated in blue (yellow cells) are to be provided by TENDERER and will form part of the PRICING SCHEDULE / CONTRACT PRICE as included in Annex 6 - Contract Section IV (Remuneration), and/or KEY DATES as included in Annex 6 - Contract Section VI (Scope of Work). All quantities will be used for assessment purposes and will also be the basis for determining the final CONTRACT PRICE and KEY DATES for these activities to be carried out under the CONTRACT. IN CASE THE BLUE TEXT TURNS RED, THIS MEANS THAT TENDERER ENTERED A VALUE OUTSIDE THE ALLOWABLE RANGES. This colour coding is for convenience only; the TENDERER is responsible for ensuring that the correct values are submitted by the TENDERER.
| II.0 | TENDERER shall specify the vessels with which the survey shall be carried out and indicate which equipment is operated from which vessel. TENDERER may carry out the surveys with 1,2,3 or 4 vessels. In case TENDERER intends to carry out the survey in separate passes with one vessel, TENDERER shall specify the same vessel for different parts (as limitation might be different). In case the different parts are carried out with two vessels TENDERER shall specify the vessel used for each part. The PCPT ¦ SCPT ¦ DT ¦ TC ¦ VC ¦ BH check boxes must at least be checked once indicating which survey equipment will be used on which vessel during each Part. The combination of survey equipment items to run from one vessel shall be compliant with the Annex 6 - Contract Section VI (Scope of Work) At CONTRACT award, the values specified in this Annex 4 shall be taken over in Annex 6 - Contract Section IV (Remuneration)
| II.1 | TENDERER to provide limiting operational conditions and minimum required weather window to perform the survey for the vessels proposed. These data are input for adverse weather determination as specified in Annex 6 - Contract Section VII (Quality requirements & Administrative instructions) - chapter 8 TENDERER shall specify for each Part the limiting operational conditions of the vessel including equipment for the execution of the survey works. In case the same vessel is used for different Parts, different limiting operational conditions may be specified as a result of the different survey equipment used for each Part.
| II.2 | The workability % is automatically determined through extracting the workability at the specified limiting conditions from the persistence tables in tab [U10-wave]. TENDERER shall specify the number of WAITING ON WEATHER days to be included and if this deviates from the calculated value, an explanation should be provided. The maximum amount of WAITING ON WEATHER ALLOWANCE DAYS is 30. These days will be taken over as the WAITING ON WEATHER ALLOWANCE DAYS in Annex 6 - Contract Section IV (Remuneration)
| III.0 | TENDERER shall specify the cycle times for executing the works. Based upon these cycle times, the key dates are determined. At CONTRACT award these dates will be taken over in Annex 6 - Contract Section VI (Scope of Work) / Table 1 Please note that Liquidated Damages become applicable in case TENDERER fails to meet Key Dates as per Annex 6 - Contract Section III (Conditions of Contract)- Clause 42!
| III.1 | TENDERER to provide the number of days required for preparing & updating after review 1 & 2 of project documentation. Dates 2a-g are generated automatically based on these cycle times. Finalization of project documentation must be 3 days before the actual commencement of the offshore work (project documentation to comply with requirements as stated in Annex 6).
| III.2 | In case the finalization date of the project documentation is later than 3 days before the start of the mobilization, this cell is coloured red. This means that the time allowed for preparation is not sufficient in relation to the planned mobilisation date and as such the proposal not valid!
| III.3 | The latest of the dates 3k, 4k, 5k and 6k is the OFFSHORE COMPLETION DATE (including WAITING IN WEATHER) and are compared to the desired offshore completion date for assessment.
The number of WAITING ON WEATHER DAYS is automatically determined in tab [WDT Calculation] based upon the end of mobilisation (incl. transit to site), limiting conditions and cycle times given by TENDERER and the persistence percentages given in tab [U10-wave]. The automatic calculation of WAITING ON WEATHER is for information only. The TENDERER shall specify the number of WAITING ON WEATHER DAYS, accounting more detailed limits than specified in this Annex 4. If there is a significant difference (>25%) between the automatically-calculated and TENDERER-calculated WAITING ON WEATHER days, TENDERER shall explain the reason for this difference. The explanation will be used in the evaluation of the vessel and equipment according to Annex 3. The number of WAITING ON WEATHER days shall be input for WAITING ON WEATHER ALLOWANCE DAYS dependent on the chosen weather downtime option and weather down time principles as specified in Annex 6 - Contract Section IV (Remuneration) and Annex 6 - Contract Section VII (Quality requirements & Administrative instructions).
| III.4 | IN CASE THE OFFSHORE COMPLETION DATE FOR THE HPA IS LATER THAN 28/9/2021 THIS CELL IS COLORED RED. THIS MEANS THAT THE OFFSHORE COMPLETION DATE IS LATER THAN THE ULTIMATE DUE DATE AND AS SUCH THE PROPOSAL NOT VALID!
| III.5 | Please note that CLIENT has set a maximum duration after the OFFSHORE COMPLETION DATE for delivery of the reports.
| IV.0 | At Contract award, all rates specified in this Annex 4b shall be taken over in the PRICING SCHEDULE in Annex 6 - Contract Section IV (Remuneration). See sheet [Remuneration Table] for the table and its format as will be used in Annex 6 - Contract Section IV (Remuneration)
| IV.1 | Thermal conductivity tests to include specific heat capacity. Tests include duplicate tests on two separate specimens from one sample and testing at five different densities.
| IV.2 | The automatically generated number of WAITING ON WEATHER days shall be input for adverse weather determinations as the WAITING ON WEATHER ALLOWANCE DAYS in case "Option 2: Lump sum including weather scenario" and "Option 3: Lump sum including risk sharing mechanism on weather downtime" is chosen. At Contract award the values specified in this Annex 4b shall be taken over in Annex 6 - Contract Section IV (Remuneration)
| IV.3 | Lump sum for Activities related to dissemination of results (webinar and Project Site Description) shall be paid upon completion of the webinar and PSD, in accordance with Annex 6 - Contract Section IV (Remuneration).
| V.0 | The number of points that can be awarded is determined through linear interpolation between the minimum and maximum price. IN CASE THE TOTAL VIRTUAL PRICE OFFERED IS HIGHER THAN THE MAXIMUM PRICE THEN THE PROPOSAL IS NOT VALID!
| V.1 | The cost for WAITING ON WEATHER are calculated automatically based upon the automatically generated number of WAITING ON WEATHER DAYS and the standby rates for the vessel(s) as specified by TENDERER under items 5.1 and 5.2. The cost determined here are used determining the TOTAL VIRTUAL PRICE as explained in the Tender Document section 5.2.6
| V.2 | TENDERER shall specify the allowance for WAITING ON WEATHER in case "Option 2: Lumpsum including weather" is chosen. This WAITING ON WEATHER ALLOWANCE shall cover all WEATHER DOWNTIME that could be encountered during the execution of the works. At Contract award the values specified in this Annex 4b shall be taken over in Annex 6 - Contract Section IV (Remuneration)
| V.3 | The TOTAL VIRTUAL PRICE is determined by averaging the weather down time scenarios. Weather downtime options and weather down time principles are specified in Annex 6 - Section IV (Remuneration) and Annex 6 - Section VII (Quality requirements & Administrative instructions). IN CASE THE TOTAL VIRTUAL PRICE OFFERED IS HIGHER THAN THE MAXIMUM PRICE THAN THE PROPOSAL IS NOT VALID!
| V.4 | The TENDERER gains points when able to complete the works and deliver the final report close to or before the date desired by CLIENT. The number of points that is awarded is determined through linear interpolation between the minimum and maximum number of days. In case the completion date is later than the Ultimate date set by CLIENT the proposal will be rejected! The weather downtime days as specified by the TENDERER are included in the calculation of the OFFSHORE COMPLETION DATES.
| V.5 | IN CASE THIS DATE IS LATER THAN IS LATER THAN THE ULTIMATE DUE DATE SET BY THE CLINET THIS CELL IS COLORED RED. THIS MEANS THE PROPOSAL NOT VALID!
Formulas:
Total (days) = [Total (days), row above]+45
BH
BH
BH
BH
BH
Note on AA29: [Opmerkingenthread] U kunt deze opmerkingenthread lezen in uw versie van Excel. Eventuele wijzigingen aan de thread gaan echter verloren als het bestand wordt geopend in een nieuwere versie van Excel. Meer informatie: https://go.microsoft.com/fwlink/?linkid=870924 Opmerking: increase to 50?

## Key dates
in green, bold and underlined key date for which contractor is liable for liquidated damages in case of failure to complete these dates
|  |  |  | Survey type | Dates
No. | Description | Date |  |  | Start Mob | Start work
1a | COMMENCEMENT DATE WORK | 2020-12-03 | A | DH | 0 | 0
2e | Project documentation final | 2020-12-24 | B |  | 2021-06-01 | 2021-06-08
3a | Start of Mobilisation - Lot 2 | 0 | C |  | 2021-06-01 | 2021-06-08
3c | Start of survey WORK - Lot 2 | 0 | D |  | 2021-06-01 | 2021-06-08
7b | OFFSHORE COMPLETION DATE for High Priority Area (50%) (including WAITING ON WEATHER) - Lot 2 (Geotechnical Boreholes) | 0 | SB | SB | 0 | 0
7c | OFFSHORE COMPLETION DATE for All Geotechnical Boreholes (including WAITING ON WEATHER) - Lot 2* | 0 | DH | DH | 0 | 0
7d | 1st Version "Operations Report (Lot 2) | 0
7f | Final Version "Operations Report (Lot 2) | 0
7g | 1st Version (Field Report) "Geotechnical Boreholes Report" - High Priority Area (HPA)* | 0
7i | 2nd Version "Geotechnical Boreholes Report" (including partial standard lab testing results) - HPA* | 1900-01-20
7k | 3rd revision "Geotechnical Boreholes Report" (including complete standard test results & Age Dating) - HPA* | 1900-02-03
7m | Completion Date Reporting - Geotechnical Boreholes Report - HPA* | 1900-02-17
7t | Completion Date Reporting - Geotechnical Boreholes Report - LPA* | 1900-02-17
7u | 1st Version "Advanced Laboratory Testing Report" (includes partial set of cyclic/dynamic tests)* | 0
7w | 2nd Version "Advanced Laboratory Testing Report" (includes complete set of results for HPA & partial for LPA)* | 1900-01-20
7y | 3rd Version (HPA Tender) "Advanced Laboratory Testing Report" (includes complete set of results for HPA & partial for LPA)* | 1900-02-03
7z | Delivery of 4th Version "Advanced Laboratory Testing Report" (includes complete set of results for HPA & LPA)* | 1900-02-03
Formulas:
Start Mob = MINIFS(I4:[Start Mob, row above],H4:H7,"SB")
Start work = MINIFS(J4:[Start work, row above],H4:H7,"SB")

## U10-wave
Weather window (%) |  | Month | January |  |  | February |  |  | March |  |  | April |  |  | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December
|  | Quantile | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80%
duration (h) | Hm0 (m) < | U10 (m/s) < | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12
1 | 0.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0.8 | 0 | 0 | 1.4 | 0.3 | 0 | 0.8 | 0.4 | 0 | 1.2 | 0.3 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 0 | 3.2 | 0.4 | 0 | 5.1 | 1.1 | 0 | 3 | 1.3 | 0 | 5.2 | 1.6 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 6.9 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1.1 | 0 | 7 | 1.5 | 0 | 3.5 | 2.2 | 0 | 5.8 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.5 | 2 | 0.1 | 0 | 0 | 0.6 | 0.1 | 0 | 0.9 | 0.1 | 0 | 2.3 | 1 | 0.3 | 3.2 | 1.1 | 0.3 | 4.4 | 2.5 | 0.5 | 4.5 | 2.2 | 0.8 | 3.6 | 1.5 | 0.9 | 2.4 | 1 | 0.1 | 0.8 | 0 | 0 | 0.4 | 0 | 0 | 0.7 | 0.1 | 0
1 | 0.5 | 4 | 2 | 0.1 | 0 | 3.3 | 2.2 | 0 | 6 | 1.5 | 0 | 9.3 | 4.3 | 1.9 | 10.7 | 4.4 | 2.3 | 14 | 9.2 | 3.5 | 14.1 | 9 | 5.3 | 15.2 | 8.6 | 5.5 | 9.6 | 5 | 1.9 | 3.4 | 1.5 | 0 | 2.5 | 0.4 | 0 | 3 | 0.8 | 0
1 | 0.5 | 6 | 4.3 | 0.4 | 0 | 6 | 2.8 | 0 | 9.1 | 2.8 | 0.5 | 16.6 | 8.5 | 4.7 | 18.3 | 10.3 | 6.1 | 22.5 | 15.7 | 6.8 | 28.1 | 18.3 | 9 | 24.9 | 16 | 8.7 | 17 | 9 | 2.8 | 5.4 | 2.3 | 0.2 | 3.1 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 8 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.5 | 9 | 5.2 | 21.5 | 12.9 | 6.7 | 25.8 | 17.8 | 8 | 31.3 | 20.7 | 10.3 | 26.6 | 17.3 | 9.3 | 18.2 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 9 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 10 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 11 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 12 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 15 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 20 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.5 | 25 | 4.4 | 0.4 | 0 | 6.2 | 3 | 0 | 10.1 | 3.1 | 0.6 | 17.6 | 9 | 5.2 | 22 | 12.9 | 6.8 | 25.9 | 17.8 | 8.1 | 31.3 | 21 | 10.5 | 26.8 | 17.3 | 9.3 | 18.3 | 9.6 | 3.1 | 5.8 | 2.3 | 0.2 | 3.2 | 0.6 | 0 | 4.1 | 1.6 | 0
1 | 0.75 | 2 | 0.5 | 0.1 | 0 | 2 | 0.4 | 0 | 2.2 | 0.8 | 0.1 | 3.9 | 1.8 | 1.2 | 4.1 | 1.9 | 0.9 | 5.5 | 3.2 | 1.6 | 5.1 | 3 | 1.5 | 4.3 | 3 | 1.5 | 3.1 | 2.2 | 0.7 | 1.2 | 0.5 |  | 0.9 | 0.3 | 0 | 1.1 | 0.4 | 0
1 | 0.75 | 4 | 4.6 | 1.3 | 0.1 | 8.1 | 4.3 | 0.4 | 9.4 | 4.4 | 1.8 | 15.6 | 8.5 | 5.6 | 15.3 | 9.3 | 5.8 | 20.7 | 15.3 | 8.6 | 19.7 | 13.8 | 10.2 | 21 | 14.8 | 8.1 | 15 | 10.1 | 5.7 | 7.1 | 3.2 | 1 | 4.7 | 2.5 | 0.6 | 6 | 2.6 | 0.8
1 | 0.75 | 6 | 11.3 | 4.3 | 0.7 | 14.8 | 8.9 | 2 | 20.8 | 10.3 | 5.9 | 28.8 | 17.4 | 13.5 | 30.6 | 21.9 | 15.6 | 38.4 | 27.8 | 16.9 | 38 | 30.6 | 22.8 | 39.3 | 28.1 | 19.2 | 28.3 | 20.6 | 11.4 | 14.5 | 7.8 | 3.6 | 11.3 | 5.6 | 1.8 | 12.4 | 6.3 | 1.5
1 | 0.75 | 8 | 17.1 | 6 | 0.7 | 18.2 | 11.4 | 2.9 | 26.9 | 13.3 | 8.6 | 36.3 | 23.3 | 16.4 | 37.3 | 30.1 | 20.9 | 46.2 | 37.5 | 23.8 | 51.3 | 38.7 | 29.8 | 47.1 | 38.2 | 27 | 35.9 | 27.6 | 14 | 18.8 | 10.8 | 5.6 | 13.1 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 9 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.7 | 24.2 | 16.8 | 39.7 | 30.6 | 23.6 | 47.5 | 38.1 | 24.8 | 52.8 | 41.1 | 30.7 | 48.7 | 39.5 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.8 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 10 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.2 | 23.9 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.8 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 11 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.3 | 24 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.9 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 12 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.3 | 24 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.9 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 15 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.3 | 24 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.9 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 20 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.3 | 24 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.9 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 0.75 | 25 | 17.1 | 6.2 | 0.7 | 18.3 | 11.4 | 2.9 | 27 | 13.7 | 8.9 | 37.8 | 24.4 | 17 | 40.2 | 31.3 | 24 | 47.5 | 38.1 | 24.9 | 53 | 41.1 | 30.7 | 49.1 | 40.1 | 27.5 | 36.3 | 27.8 | 14.3 | 18.8 | 10.9 | 5.7 | 13.2 | 7.4 | 2 | 14.1 | 7.9 | 1.8
1 | 1 | 2 | 1.3 | 0.3 |  | 2.2 | 0.6 | 0.1 | 2.9 | 1.3 | 0.3 | 4.3 | 2.5 | 1.5 | 4.5 | 2.3 | 1.1 | 6 | 3.9 | 2 | 6 | 3.6 | 1.8 | 5.1 | 3.4 | 1.7 | 3.6 | 2.5 | 1.1 | 1.7 | 0.8 | 0.4 | 1.6 | 0.4 |  | 1.4 | 0.7 | 0.1
1 | 1 | 4 | 6.2 | 2.7 | 0.9 | 10.6 | 5.7 | 2 | 12.6 | 6.9 | 2.5 | 18.2 | 11.7 | 8 | 17.2 | 13 | 7.8 | 23.7 | 17.9 | 11.9 | 23 | 17.1 | 11.7 | 23.4 | 16.9 | 11.3 | 16.4 | 11.3 | 7.6 | 10.1 | 5.1 | 2.9 | 7.2 | 3.9 | 1.7 | 7.3 | 3.6 | 1.2
1 | 1 | 6 | 17.4 | 9 | 2.4 | 20.2 | 14.7 | 5.5 | 27.6 | 16.3 | 9 | 37.2 | 25.4 | 19.7 | 37.4 | 29 | 22.1 | 46.8 | 36.3 | 27.9 | 46.3 | 36.7 | 28.3 | 45.1 | 33.6 | 27.1 | 35.2 | 28.2 | 19.1 | 22.3 | 12.5 | 7.2 | 16.4 | 9.2 | 5.3 | 18.6 | 8.7 | 3.7
1 | 1 | 8 | 26.4 | 13.8 | 3.5 | 30.4 | 20.2 | 10.5 | 37.7 | 26.2 | 16.3 | 52.8 | 38.8 | 29.9 | 53.1 | 46.1 | 36.1 | 63.1 | 53.1 | 42.9 | 66.8 | 56.2 | 42.1 | 62.8 | 51.7 | 42.3 | 48.3 | 41.1 | 29.8 | 30.5 | 19.8 | 10.8 | 25.3 | 15.3 | 7.7 | 26.2 | 12.5 | 6.2
1 | 1 | 9 | 27 | 15.1 | 3.8 | 31.6 | 21.3 | 10.8 | 40.4 | 29.3 | 18.5 | 55.5 | 40.6 | 32.2 | 58.6 | 48.9 | 38.4 | 66.5 | 55.8 | 46.7 | 71.1 | 61.3 | 46.8 | 67.8 | 54.8 | 45.4 | 52.1 | 43.6 | 31.7 | 32.5 | 22.7 | 12.1 | 26.7 | 16.3 | 7.8 | 27.6 | 12.8 | 6.6
1 | 1 | 10 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.8 | 40.9 | 29.7 | 19.1 | 56.3 | 41.7 | 32.7 | 60.5 | 50.9 | 40 | 67.2 | 57.1 | 48.5 | 72.1 | 62.9 | 48.4 | 68.7 | 56 | 46.7 | 53.4 | 45.1 | 32.4 | 32.9 | 23.8 | 12.6 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1 | 11 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.9 | 40.9 | 30 | 19.1 | 56.5 | 41.8 | 32.9 | 60.6 | 51.1 | 40.3 | 67.3 | 57.1 | 48.6 | 72.3 | 62.9 | 48.5 | 69.2 | 56.3 | 46.9 | 53.6 | 45.4 | 32.4 | 32.9 | 23.8 | 12.7 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1 | 12 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.9 | 40.9 | 30 | 19.1 | 56.5 | 41.8 | 33 | 60.6 | 51.2 | 40.3 | 67.3 | 57.1 | 48.8 | 72.3 | 63 | 48.5 | 69.2 | 56.5 | 46.9 | 53.6 | 45.4 | 32.4 | 32.9 | 23.8 | 12.7 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1 | 15 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.9 | 40.9 | 30 | 19.1 | 56.5 | 41.8 | 33 | 60.6 | 51.3 | 40.3 | 67.3 | 57.1 | 48.8 | 72.3 | 63 | 48.5 | 69.2 | 56.5 | 46.9 | 53.6 | 45.4 | 32.4 | 32.9 | 23.8 | 12.7 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1 | 20 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.9 | 40.9 | 30 | 19.1 | 56.5 | 41.8 | 33 | 60.6 | 51.3 | 40.3 | 67.3 | 57.1 | 48.8 | 72.3 | 63 | 48.5 | 69.2 | 56.5 | 46.9 | 53.6 | 45.4 | 32.4 | 32.9 | 23.8 | 12.7 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1 | 25 | 27.2 | 15.6 | 3.8 | 31.7 | 21.3 | 10.9 | 40.9 | 30 | 19.1 | 56.5 | 41.8 | 33 | 60.6 | 51.3 | 40.3 | 67.3 | 57.1 | 48.8 | 72.3 | 63 | 48.5 | 69.2 | 56.5 | 46.9 | 53.6 | 45.4 | 32.4 | 32.9 | 23.8 | 12.7 | 27.2 | 16.3 | 7.9 | 27.6 | 13 | 6.7
1 | 1.25 | 2 | 1.3 | 0.5 |  | 2.5 | 1 | 0.1 | 3 | 1.5 | 0.4 | 4.3 | 2.8 | 1.8 | 4.5 | 3.4 | 1.3 | 6 | 4.2 | 2.1 | 6 | 3.6 | 1.8 | 5.7 | 3.4 | 1.7 | 3.9 | 2.5 | 1.3 | 2.2 | 1.1 | 0.5 | 1.7 | 0.6 | 0.3 | 1.8 | 0.8 | 0.2
1 | 1.25 | 4 | 6.7 | 3.6 | 1.7 | 12.3 | 7.9 | 2.9 | 14.3 | 8.6 | 3.9 | 19.6 | 12.5 | 9.6 | 18.9 | 14.1 | 9.3 | 25.3 | 20 | 12.9 | 23.9 | 17.6 | 12.1 | 25.5 | 17.3 | 11.7 | 18 | 12.2 | 8.2 | 11.4 | 6 | 3.8 | 8.5 | 5 | 2.8 | 9.5 | 4.3 | 2.2
1 | 1.25 | 6 | 23.2 | 10.2 | 5.8 | 25.4 | 17.7 | 7.2 | 29 | 20.7 | 12.6 | 40.1 | 28.6 | 23.3 | 40 | 32.1 | 25.8 | 50.7 | 41.3 | 31.9 | 48.5 | 39.8 | 31 | 46.3 | 36.2 | 30.6 | 38.3 | 30.6 | 20.5 | 25.8 | 16.1 | 11 | 21.1 | 12.9 | 7.9 | 22.9 | 12 | 5.5
1 | 1.25 | 8 | 35.6 | 21.5 | 10.2 | 37.5 | 28.6 | 13.3 | 48.2 | 34.7 | 23.2 | 59.8 | 47.4 | 40.2 | 59.4 | 53.9 | 46.3 | 72.1 | 61.4 | 50.6 | 72.7 | 64.8 | 51.1 | 70.1 | 59.5 | 50.1 | 57.5 | 48.6 | 36.7 | 38.1 | 27.7 | 19.8 | 34 | 23.5 | 13.6 | 34.9 | 19.8 | 12.4
1 | 1.25 | 9 | 37.8 | 24.5 | 11.2 | 42.7 | 32.4 | 16.2 | 52.1 | 42.3 | 28.2 | 66.3 | 54.3 | 45.4 | 69.4 | 60.6 | 53.8 | 78.4 | 68.6 | 58.2 | 79.8 | 73.3 | 58.2 | 75.5 | 67.7 | 56.7 | 64.3 | 52.9 | 40.7 | 43.2 | 33.5 | 22.3 | 38.1 | 28.1 | 15.9 | 37.3 | 23 | 15
1 | 1.25 | 10 | 39.8 | 24.7 | 12.1 | 46.2 | 33.5 | 17 | 55.2 | 43.4 | 29.3 | 70.4 | 56.8 | 46.9 | 74.6 | 64.8 | 58.2 | 81.2 | 73.2 | 61.5 | 84.2 | 77.4 | 60.8 | 79 | 69.9 | 59.8 | 66.6 | 57.2 | 43.3 | 45.5 | 35.9 | 23.7 | 39.6 | 29 | 16.6 | 38.1 | 23.8 | 15.9
1 | 1.25 | 11 | 40.1 | 25 | 12.2 | 46.6 | 33.9 | 17.8 | 55.9 | 44.5 | 29.4 | 72.2 | 58.1 | 47.8 | 75.7 | 66.4 | 60.4 | 81.5 | 74.6 | 62.6 | 85.3 | 78.6 | 62.6 | 79.7 | 71.8 | 61.3 | 67 | 58.8 | 44.1 | 45.9 | 36.7 | 24 | 39.8 | 29.4 | 16.6 | 38.5 | 23.8 | 16
1 | 1.25 | 12 | 40.1 | 25 | 12.2 | 46.8 | 33.9 | 17.9 | 56.3 | 44.8 | 29.5 | 72.2 | 58.3 | 47.9 | 75.8 | 66.4 | 60.7 | 81.5 | 74.7 | 63.2 | 85.3 | 78.8 | 63.2 | 79.9 | 71.8 | 61.6 | 67.2 | 58.8 | 44.1 | 46 | 36.8 | 24 | 39.8 | 29.4 | 16.6 | 38.5 | 23.8 | 16
1 | 1.25 | 15 | 40.2 | 25 | 12.2 | 46.8 | 33.9 | 18 | 56.3 | 44.8 | 29.5 | 72.2 | 58.3 | 47.9 | 75.8 | 66.4 | 60.8 | 81.5 | 74.7 | 63.2 | 85.3 | 78.9 | 63.5 | 79.9 | 71.8 | 61.6 | 67.2 | 58.8 | 44.1 | 46 | 36.8 | 24 | 39.9 | 29.4 | 16.6 | 38.5 | 23.8 | 16
1 | 1.25 | 20 | 40.3 | 25 | 12.2 | 46.8 | 33.9 | 18 | 56.3 | 44.8 | 29.5 | 72.2 | 58.3 | 47.9 | 75.8 | 66.4 | 60.8 | 81.5 | 74.7 | 63.2 | 85.3 | 78.9 | 63.5 | 79.9 | 71.8 | 61.6 | 67.2 | 58.9 | 44.1 | 46 | 36.8 | 24 | 39.9 | 29.4 | 16.6 | 38.5 | 23.8 | 16
1 | 1.25 | 25 | 40.3 | 25 | 12.2 | 46.8 | 33.9 | 18 | 56.3 | 44.8 | 29.5 | 72.2 | 58.3 | 47.9 | 75.8 | 66.4 | 60.8 | 81.5 | 74.7 | 63.2 | 85.3 | 78.9 | 63.5 | 79.9 | 71.8 | 61.6 | 67.2 | 58.9 | 44.1 | 46 | 36.8 | 24 | 39.9 | 29.4 | 16.6 | 38.5 | 23.8 | 16
1 | 1.5 | 2 | 1.4 | 0.7 | 0.1 | 3.2 | 1.1 | 0.3 | 3.1 | 1.5 | 0.4 | 4.6 | 2.8 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 3.9 | 2.5 | 1.3 | 2.2 | 1.1 | 0.5 | 1.8 | 0.8 | 0.3 | 2.2 | 0.8 | 0.3
1 | 1.5 | 4 | 8.4 | 3.9 | 2.2 | 13.3 | 8.2 | 3.3 | 14.5 | 9 | 4.5 | 19.6 | 13.9 | 10.6 | 19.1 | 14.8 | 9.6 | 25.4 | 20.7 | 13.4 | 23.9 | 17.7 | 12.5 | 25.7 | 17.3 | 12.1 | 18.3 | 12.5 | 8.9 | 11.5 | 7 | 3.9 | 9.4 | 5.6 | 3.5 | 11.5 | 5.2 | 2.9
1 | 1.5 | 6 | 25.1 | 12.5 | 6.7 | 27.5 | 18.8 | 8.8 | 31 | 23 | 14.7 | 40.9 | 30.7 | 27.2 | 40.6 | 33.3 | 26.9 | 51.4 | 41.9 | 32.7 | 50.1 | 40.5 | 31.8 | 49.2 | 39 | 32 | 39.7 | 31.7 | 22 | 27.2 | 19.1 | 12.5 | 22 | 16 | 9.3 | 24.5 | 14.4 | 7.1
1 | 1.5 | 8 | 39.8 | 26.2 | 14.4 | 42.3 | 33.3 | 17.9 | 49.9 | 37.9 | 28.5 | 63 | 51 | 44.8 | 63.8 | 57.3 | 48.6 | 75 | 65.1 | 55.2 | 75.1 | 67.3 | 56.6 | 72.1 | 63.2 | 51.7 | 61.2 | 51.5 | 42.8 | 43.1 | 32.4 | 23.5 | 39.6 | 29.2 | 19.3 | 38.6 | 24.6 | 15.5
1 | 1.5 | 9 | 43.9 | 32.3 | 17.4 | 52.1 | 41.2 | 22.5 | 61.9 | 48 | 37.1 | 71 | 59.6 | 53.1 | 74.5 | 66.1 | 58.8 | 83 | 75.4 | 65.8 | 82.5 | 76.7 | 66.5 | 79.6 | 71.4 | 61.3 | 67.9 | 60 | 49.9 | 49.5 | 39.9 | 29.8 | 45.7 | 35.6 | 23.4 | 43.5 | 29 | 19.5
1 | 1.5 | 10 | 47.2 | 34.8 | 20.4 | 59.1 | 46.3 | 26.8 | 67.9 | 53.2 | 42 | 77.8 | 65.8 | 56.8 | 81 | 72.8 | 67.4 | 87.8 | 81.7 | 71.3 | 89.2 | 83.5 | 72.7 | 85.8 | 77.4 | 67.4 | 75.8 | 65.1 | 54.9 | 57.4 | 45.2 | 34.8 | 52.8 | 38.2 | 26.3 | 47.6 | 32.5 | 23.1
1 | 1.5 | 11 | 49.2 | 36 | 21.5 | 60.7 | 48.2 | 27.6 | 71.1 | 54.7 | 44 | 81.6 | 70 | 60.4 | 84 | 78.1 | 69.9 | 89.5 | 84 | 74.7 | 92.3 | 86.2 | 75.8 | 87.5 | 79.6 | 70.6 | 77.9 | 67.8 | 57.3 | 61 | 48.7 | 36.8 | 55.7 | 39.3 | 27.3 | 50.2 | 34.1 | 23.5
1 | 1.5 | 12 | 49.5 | 36.3 | 22.1 | 60.9 | 49 | 27.9 | 72.1 | 55.1 | 44.3 | 82.4 | 71.8 | 61.3 | 84.6 | 79.3 | 71.3 | 90 | 84.2 | 75.8 | 93.3 | 86.6 | 76.1 | 88 | 79.7 | 71.2 | 78.1 | 68.9 | 57.8 | 62 | 49.6 | 37.3 | 56 | 39.9 | 28.1 | 50.7 | 34.9 | 23.7
1 | 1.5 | 15 | 49.6 | 36.6 | 22.2 | 61 | 49 | 28 | 72.1 | 55.5 | 44.4 | 82.7 | 71.9 | 61.3 | 85.1 | 79.3 | 71.6 | 90 | 84.3 | 75.8 | 93.4 | 87.1 | 76.1 | 88.1 | 79.8 | 71.7 | 78.3 | 68.9 | 57.8 | 62.1 | 49.9 | 37.3 | 56.2 | 39.9 | 28.1 | 50.8 | 35.1 | 23.7
1 | 1.5 | 20 | 49.6 | 36.6 | 22.2 | 61 | 49 | 28 | 72.1 | 55.5 | 44.4 | 82.7 | 71.9 | 61.3 | 85.1 | 79.3 | 71.6 | 90 | 84.3 | 75.8 | 93.4 | 87.1 | 76.1 | 88.1 | 79.8 | 71.7 | 78.3 | 68.9 | 57.8 | 62.1 | 49.9 | 37.3 | 56.2 | 39.9 | 28.1 | 50.8 | 35.1 | 23.7
1 | 1.5 | 25 | 49.6 | 36.6 | 22.2 | 61 | 49 | 28 | 72.1 | 55.5 | 44.4 | 82.7 | 71.9 | 61.3 | 85.1 | 79.3 | 71.6 | 90 | 84.3 | 75.8 | 93.4 | 87.1 | 76.1 | 88.1 | 79.8 | 71.7 | 78.3 | 68.9 | 57.8 | 62.1 | 49.9 | 37.3 | 56.2 | 39.9 | 28.1 | 50.8 | 35.1 | 23.7
1 | 1.75 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.5 | 4.6 | 2.8 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4 | 2.8 | 1.3 | 2.3 | 1.2 | 0.5 | 1.9 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 1.75 | 4 | 8.8 | 4 | 2.5 | 13.8 | 8.6 | 3.9 | 14.7 | 9.1 | 6.1 | 19.6 | 14.4 | 10.9 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.3 | 11.6 | 7.3 | 4.2 | 9.8 | 6 | 3.5 | 12.3 | 5.6 | 2.9
1 | 1.75 | 6 | 25.8 | 13.8 | 7.7 | 28.7 | 20.5 | 11.2 | 31.1 | 23.9 | 17 | 42.5 | 32.2 | 27.3 | 40.8 | 34.3 | 27 | 51.6 | 42.5 | 33 | 50.1 | 40.5 | 32.3 | 49.3 | 39.1 | 32.1 | 39.9 | 32.1 | 22.6 | 27.4 | 19.5 | 12.8 | 23.2 | 17.5 | 10.5 | 25.2 | 15.3 | 7.4
1 | 1.75 | 8 | 42.3 | 28.9 | 16.2 | 45.6 | 36.6 | 21.5 | 51.7 | 41 | 34.8 | 64.3 | 53.5 | 47.6 | 64.6 | 59 | 49.5 | 76.3 | 65.6 | 57.6 | 75.6 | 67.6 | 58.4 | 72.4 | 63.8 | 52.7 | 63.4 | 53.3 | 45.4 | 45.3 | 33.7 | 25.9 | 42.4 | 32.4 | 20.5 | 40.3 | 27.7 | 17.8
1 | 1.75 | 9 | 49.9 | 34.8 | 21.3 | 56.4 | 46 | 27 | 66.4 | 50.7 | 41.9 | 72.3 | 63.2 | 57.8 | 76.2 | 67.9 | 61.1 | 85.4 | 76.9 | 68.1 | 83.6 | 78.6 | 68.9 | 82.2 | 72.3 | 62.9 | 71.6 | 63.5 | 54.5 | 52.6 | 41.7 | 34.7 | 49.5 | 39.3 | 27.6 | 48.3 | 32.5 | 22.9
1 | 1.75 | 10 | 53.8 | 40.6 | 28.2 | 65.6 | 52.2 | 31.2 | 73.9 | 59.7 | 46.4 | 82.6 | 72.9 | 64.4 | 84.4 | 75.8 | 71.4 | 90.8 | 85.3 | 76.3 | 90.8 | 85.3 | 77.4 | 89.2 | 78.5 | 71.3 | 78.3 | 68.5 | 59.8 | 61.1 | 49.7 | 41.8 | 57.3 | 45.1 | 32.8 | 55.5 | 39.1 | 28.9
1 | 1.75 | 11 | 57.7 | 43.5 | 33.6 | 68.6 | 57.9 | 34.4 | 77.4 | 65.9 | 51 | 87.5 | 77.8 | 69 | 88.7 | 82.8 | 77.9 | 93.6 | 88.8 | 81.5 | 95.8 | 89.5 | 81.3 | 91.5 | 83.9 | 76.6 | 82.2 | 74.6 | 64.6 | 69.3 | 57 | 47.1 | 62.4 | 49.4 | 35.3 | 58.6 | 42.6 | 30.6
1 | 1.75 | 12 | 59.4 | 45 | 36.6 | 71 | 60.1 | 36.4 | 79.9 | 67.2 | 54.4 | 87.8 | 80 | 70.1 | 90.8 | 85.9 | 81.7 | 94.5 | 89.6 | 84.2 | 96.6 | 91.1 | 82.6 | 93.4 | 85.1 | 79.3 | 83.8 | 76.3 | 66.6 | 72.9 | 59.5 | 49.8 | 64.8 | 50.1 | 37 | 61.3 | 43.4 | 31.4
1 | 1.75 | 15 | 60.3 | 45.6 | 37.1 | 71.8 | 61.2 | 37.8 | 81 | 67.7 | 56.4 | 88.7 | 80.4 | 70.7 | 91.4 | 87 | 82.9 | 94.7 | 90 | 84.6 | 96.8 | 91.7 | 83.1 | 93.5 | 85.3 | 79.8 | 84.4 | 77.1 | 67.3 | 74.2 | 60.2 | 51.8 | 65.7 | 50.1 | 38.3 | 61.8 | 44.1 | 31.8
1 | 1.75 | 20 | 60.4 | 45.6 | 37.1 | 71.8 | 61.2 | 37.8 | 81 | 67.7 | 56.4 | 88.7 | 80.4 | 70.7 | 91.4 | 87 | 82.9 | 94.7 | 90 | 84.6 | 96.8 | 91.7 | 83.1 | 93.5 | 85.3 | 79.9 | 84.4 | 77.1 | 67.3 | 74.2 | 60.2 | 51.8 | 65.8 | 50.1 | 38.3 | 61.8 | 44.1 | 31.8
1 | 1.75 | 25 | 60.4 | 45.6 | 37.1 | 71.8 | 61.2 | 37.8 | 81 | 67.7 | 56.4 | 88.7 | 80.4 | 70.7 | 91.4 | 87 | 82.9 | 94.7 | 90 | 84.6 | 96.8 | 91.7 | 83.1 | 93.5 | 85.3 | 79.9 | 84.4 | 77.1 | 67.3 | 74.2 | 60.2 | 51.8 | 65.8 | 50.1 | 38.3 | 61.8 | 44.1 | 31.8
1 | 2 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.3 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 2 | 4 | 9.2 | 4 | 2.6 | 13.8 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.4 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.3 | 11.7 | 7.4 | 4.6 | 9.8 | 6 | 3.9 | 12.6 | 5.6 | 2.9
1 | 2 | 6 | 26 | 14 | 8.4 | 29.2 | 20.8 | 11.3 | 31.3 | 23.9 | 17.3 | 43.2 | 32.9 | 27.4 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.6 | 49.3 | 39.1 | 32.1 | 40.1 | 32.1 | 23.1 | 27.5 | 20 | 12.8 | 23.3 | 17.8 | 10.7 | 26 | 15.9 | 8.1
1 | 2 | 8 | 43.5 | 29.3 | 17.4 | 48.1 | 37.4 | 22.3 | 53.5 | 42.1 | 35.7 | 64.3 | 56.1 | 48.8 | 65.1 | 59.1 | 51.1 | 76.4 | 66 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64 | 52.9 | 64 | 54.2 | 45.9 | 46.2 | 34.3 | 28.2 | 43.6 | 32.5 | 21.3 | 42.1 | 28.4 | 19.4
1 | 2 | 9 | 53.1 | 37.6 | 23.1 | 57.3 | 48.2 | 27.9 | 67.5 | 53.5 | 44 | 72.6 | 65.3 | 60.1 | 77.3 | 68.8 | 62.1 | 86.3 | 77.8 | 69.6 | 83.9 | 78.9 | 70.4 | 83.5 | 73.4 | 63.6 | 73.9 | 64.9 | 56.3 | 54.1 | 42.3 | 36.4 | 52.3 | 41.3 | 29.9 | 51.2 | 35.6 | 25
1 | 2 | 10 | 57.4 | 43.3 | 31.7 | 66.9 | 56.1 | 33.4 | 75.6 | 62.1 | 50.2 | 83.9 | 75 | 67.4 | 84.6 | 78.2 | 74 | 92.1 | 86.5 | 79.2 | 91.5 | 86.4 | 79.9 | 90.5 | 81.5 | 72.8 | 80.3 | 71 | 62.7 | 62.7 | 52.2 | 44.9 | 59.7 | 48.2 | 36.6 | 58 | 42.6 | 32.6
1 | 2 | 11 | 62.2 | 49.6 | 39.2 | 73.1 | 63.4 | 39.2 | 80.1 | 69.8 | 57.2 | 89.3 | 81.3 | 72.7 | 90.7 | 85.8 | 81.4 | 95.2 | 90.6 | 84.8 | 96.2 | 91.8 | 84 | 93.8 | 85.8 | 78.8 | 84.4 | 77.6 | 69.2 | 71.5 | 61.3 | 51.7 | 67.4 | 56.8 | 42.4 | 63.2 | 46.9 | 36.5
1 | 2 | 12 | 66.5 | 53.6 | 43.6 | 76.9 | 67.7 | 44.8 | 84.1 | 74.5 | 60.3 | 91.7 | 85.6 | 76.1 | 93.1 | 89.8 | 86.6 | 96.3 | 92.6 | 88.9 | 98.3 | 95.2 | 87.6 | 96.9 | 88.2 | 83 | 87.1 | 81.3 | 72.8 | 76 | 64.8 | 56.7 | 71.9 | 59.9 | 44.9 | 67.8 | 49.3 | 38.5
1 | 2 | 15 | 69.7 | 55.6 | 45.3 | 81.2 | 71.4 | 48.1 | 86 | 76.9 | 64.7 | 93.4 | 87.1 | 78.2 | 94.8 | 91.1 | 88.7 | 97 | 93.6 | 89.9 | 99.2 | 96.4 | 90.2 | 97.4 | 89.5 | 84.8 | 89.1 | 83.9 | 75.1 | 79.2 | 69.8 | 62.4 | 77.2 | 63.5 | 48.1 | 71 | 53.2 | 40
1 | 2 | 20 | 69.9 | 55.8 | 45.4 | 81.3 | 71.4 | 48.1 | 86 | 76.9 | 64.7 | 93.4 | 87.1 | 78.2 | 94.8 | 91.1 | 88.8 | 97 | 93.6 | 89.9 | 99.2 | 96.4 | 90.2 | 97.4 | 89.5 | 85 | 89.1 | 83.9 | 75.1 | 79.2 | 69.8 | 62.6 | 77.2 | 63.6 | 48.1 | 71 | 53.2 | 40.1
1 | 2 | 25 | 69.9 | 55.8 | 45.4 | 81.3 | 71.4 | 48.1 | 86 | 76.9 | 64.7 | 93.4 | 87.1 | 78.2 | 94.8 | 91.1 | 88.8 | 97 | 93.6 | 89.9 | 99.2 | 96.4 | 90.2 | 97.4 | 89.5 | 85 | 89.1 | 83.9 | 75.1 | 79.2 | 69.8 | 62.6 | 77.2 | 63.6 | 48.1 | 71 | 53.2 | 40.1
1 | 2.25 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 2.25 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 3.9 | 13.1 | 5.8 | 3
1 | 2.25 | 6 | 26 | 14 | 8.9 | 29.3 | 20.8 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.6 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.1 | 23.3 | 18.1 | 11.2 | 27 | 16.1 | 8.3
1 | 2.25 | 8 | 44.1 | 29.4 | 17.7 | 49.2 | 37.6 | 23.1 | 53.6 | 42.7 | 35.9 | 64.4 | 56.4 | 49 | 65.1 | 59.1 | 51.1 | 76.8 | 66.3 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.4 | 52.9 | 64.1 | 54.2 | 45.9 | 46.5 | 34.7 | 28.8 | 43.9 | 32.9 | 22 | 43.3 | 28.4 | 20.2
1 | 2.25 | 9 | 53.3 | 37.6 | 23.9 | 57.8 | 48.8 | 29.4 | 67.7 | 54.6 | 45 | 73.6 | 65.8 | 60.6 | 77.6 | 69 | 62.6 | 86.6 | 77.8 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 73.9 | 63.8 | 74 | 65 | 56.6 | 55 | 43.3 | 36.9 | 53.5 | 42.6 | 31.1 | 53 | 37.4 | 25.7
1 | 2.25 | 10 | 59.1 | 43.3 | 32.6 | 67.1 | 57.1 | 36.4 | 76 | 63.8 | 51.5 | 84.6 | 75.1 | 69.4 | 85.2 | 78.8 | 74.2 | 92.5 | 86.8 | 79.6 | 91.5 | 87 | 80.6 | 90.9 | 83.7 | 73.4 | 80.6 | 71.4 | 64.1 | 64.7 | 53.6 | 46 | 61.1 | 51.7 | 38.2 | 59.6 | 44.8 | 33.6
1 | 2.25 | 11 | 66.6 | 51.2 | 41.6 | 74.3 | 64.2 | 43.2 | 81.2 | 71.5 | 59.8 | 90 | 82.1 | 76.2 | 91.2 | 86.2 | 82.6 | 96 | 91.1 | 86 | 96.4 | 92.5 | 86.6 | 94.8 | 87.6 | 80.2 | 86.8 | 78.6 | 71.3 | 73 | 63.2 | 53.6 | 70.5 | 60.4 | 45.9 | 65.9 | 49.9 | 42.1
1 | 2.25 | 12 | 70.8 | 58.1 | 47.9 | 80.2 | 71.4 | 51.5 | 86.6 | 77.4 | 63.8 | 93.8 | 87.4 | 80.2 | 94.5 | 91.5 | 88.5 | 98.1 | 94.3 | 91 | 98.5 | 95.7 | 90.6 | 97.8 | 91.5 | 85.9 | 90.2 | 84.6 | 76 | 78.7 | 69.6 | 60.5 | 75.9 | 65.8 | 49.6 | 72.7 | 54.7 | 47.1
1 | 2.25 | 15 | 77.4 | 63 | 52.8 | 85.5 | 77.1 | 57.8 | 91.2 | 82.4 | 70.4 | 96.5 | 92.6 | 85.2 | 97 | 95.4 | 92.6 | 99.5 | 96.3 | 93.7 | 99.9 | 97.8 | 94.7 | 98.4 | 93.8 | 89.2 | 93.7 | 88.3 | 81.3 | 85.1 | 77.4 | 71.9 | 82.2 | 70.8 | 56.4 | 77.6 | 63.6 | 52
1 | 2.25 | 20 | 77.4 | 63.4 | 52.8 | 85.7 | 77.2 | 57.9 | 91.5 | 82.5 | 70.5 | 96.5 | 92.6 | 85.2 | 97 | 95.4 | 92.6 | 99.5 | 96.3 | 93.8 | 99.9 | 97.8 | 94.7 | 98.4 | 94 | 89.4 | 93.7 | 88.8 | 81.4 | 85.3 | 77.6 | 72 | 82.9 | 70.8 | 57.5 | 77.7 | 63.8 | 52.4
1 | 2.25 | 25 | 77.4 | 63.4 | 52.8 | 85.7 | 77.2 | 57.9 | 91.5 | 82.5 | 70.5 | 96.5 | 92.6 | 85.2 | 97 | 95.4 | 92.6 | 99.5 | 96.3 | 93.8 | 99.9 | 97.8 | 94.7 | 98.4 | 94 | 89.4 | 93.7 | 88.8 | 81.4 | 85.3 | 77.6 | 72 | 82.9 | 70.8 | 57.5 | 77.7 | 63.8 | 52.4
1 | 2.75 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 2.75 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 2.75 | 6 | 26 | 14 | 8.9 | 29.3 | 21.3 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.3 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 2.75 | 8 | 44.4 | 29.6 | 17.9 | 50.1 | 39.8 | 23.9 | 53.6 | 42.7 | 36 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.5 | 44.5 | 28.4 | 20.6
1 | 2.75 | 9 | 53.7 | 37.8 | 24.4 | 58 | 49.6 | 30.2 | 67.7 | 55.4 | 45.4 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.7 | 44.8 | 38.1 | 53.7 | 44.7 | 32.3 | 54.9 | 37.8 | 26.7
1 | 2.75 | 10 | 60.6 | 44.1 | 33.4 | 67.3 | 58.6 | 38.2 | 76.3 | 65.1 | 53.9 | 85.1 | 75.7 | 71.1 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 64.9 | 66.4 | 54.7 | 47.1 | 61.7 | 55 | 39 | 61.1 | 45.7 | 35.1
1 | 2.75 | 11 | 68.6 | 53.9 | 43.3 | 75.2 | 66.7 | 45.2 | 82.1 | 74.1 | 62.1 | 91.5 | 83.5 | 78.1 | 91.6 | 88 | 83.5 | 96.1 | 91.7 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 73.7 | 73.7 | 65.3 | 55.2 | 72.3 | 62.2 | 48.8 | 69.2 | 53.5 | 43.7
1 | 2.75 | 12 | 74 | 61.7 | 51.6 | 81.4 | 76.2 | 55.4 | 88.8 | 81.2 | 67.5 | 94.8 | 88.8 | 83.2 | 95.6 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.1 | 91.8 | 97.8 | 93.4 | 87.3 | 91.9 | 86.3 | 78.7 | 80 | 71.8 | 62.7 | 79.7 | 69.3 | 53.7 | 75.2 | 60.2 | 51.2
1 | 2.75 | 15 | 86.7 | 74.5 | 64.7 | 91.4 | 85.8 | 72.2 | 95.3 | 88.4 | 80.7 | 98.9 | 96 | 92.3 | 99.7 | 98.8 | 96.7 | 100 | 98.2 | 96.5 | 100 | 99.1 | 96.7 | 100 | 98 | 94.4 | 97.2 | 94.9 | 89.1 | 91.8 | 85.1 | 80.6 | 90.1 | 82.9 | 69.5 | 86.5 | 74.1 | 66.3
1 | 2.75 | 20 | 89.1 | 76.7 | 65.9 | 92.9 | 86.5 | 73.6 | 96.1 | 89.4 | 81.3 | 99.2 | 96.3 | 92.8 | 100 | 99.1 | 97.1 | 100 | 98.5 | 96.6 | 100 | 99.2 | 96.7 | 100 | 98 | 95.8 | 97.6 | 96.1 | 89.9 | 92.6 | 87.2 | 81.9 | 90.9 | 83.6 | 72.8 | 87.1 | 76.5 | 69.1
1 | 2.75 | 25 | 89.1 | 76.7 | 65.9 | 92.9 | 86.5 | 73.6 | 96.1 | 89.4 | 81.3 | 99.2 | 96.3 | 92.8 | 100 | 99.1 | 97.1 | 100 | 98.5 | 96.6 | 100 | 99.2 | 96.7 | 100 | 98 | 95.8 | 97.6 | 96.1 | 89.9 | 92.6 | 87.2 | 81.9 | 90.9 | 83.6 | 72.8 | 87.1 | 76.5 | 69.1
1 | 3 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 3 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 3 | 6 | 26 | 14 | 8.9 | 29.3 | 21.4 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.4 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 3 | 8 | 44.4 | 29.6 | 17.9 | 50.2 | 40 | 24 | 53.6 | 42.7 | 36 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.6 | 44.7 | 28.4 | 20.6
1 | 3 | 9 | 53.9 | 37.8 | 24.4 | 58 | 49.9 | 30.3 | 67.7 | 55.5 | 45.6 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.8 | 45 | 38.1 | 53.7 | 44.7 | 32.4 | 54.9 | 37.9 | 26.8
1 | 3 | 10 | 60.8 | 44.2 | 33.4 | 67.3 | 58.8 | 38.5 | 76.3 | 65.2 | 54 | 85.1 | 75.7 | 71.2 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 65.1 | 66.5 | 55.2 | 47.3 | 61.7 | 55.7 | 39.3 | 61.3 | 46.1 | 35.3
1 | 3 | 11 | 68.8 | 53.9 | 43.5 | 75.5 | 66.7 | 45.6 | 82.2 | 74.5 | 62.5 | 91.7 | 83.5 | 78.2 | 91.6 | 88 | 83.6 | 96.1 | 91.8 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 74.1 | 73.9 | 66.4 | 55.4 | 72.4 | 62.2 | 49.3 | 69.5 | 54.3 | 44.1
1 | 3 | 12 | 74.2 | 61.8 | 52.6 | 81.5 | 76.3 | 56.1 | 89.3 | 81.6 | 68.7 | 94.9 | 89.3 | 83.8 | 95.8 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.2 | 91.8 | 97.8 | 93.5 | 87.3 | 92 | 86.4 | 80.1 | 80.9 | 72.2 | 63.1 | 80.4 | 71.1 | 55.1 | 76.4 | 60.9 | 51.8
1 | 3 | 15 | 88.3 | 79.3 | 68.6 | 92.9 | 88.2 | 76.7 | 96.6 | 91 | 85.3 | 99.3 | 97.2 | 93.8 | 99.9 | 99.1 | 98.3 | 100 | 98.9 | 97 | 100 | 99.6 | 97.4 | 100 | 98.8 | 95.6 | 98.1 | 95.4 | 90.6 | 93.6 | 87.6 | 82.7 | 91.3 | 85.3 | 73.7 | 88.2 | 78.4 | 69.5
1 | 3 | 20 | 92.4 | 82.1 | 70.2 | 95.5 | 90.7 | 79.9 | 97.9 | 92.9 | 86.7 | 100 | 97.9 | 94.6 | 100 | 100 | 98.6 | 100 | 99.3 | 97.2 | 100 | 100 | 98.4 | 100 | 99.2 | 97.2 | 98.9 | 96.9 | 92.2 | 95.2 | 90.1 | 85.9 | 93.2 | 87.8 | 78.8 | 90.6 | 82.4 | 75.4
1 | 3 | 25 | 92.4 | 82.1 | 70.2 | 95.5 | 90.7 | 79.9 | 97.9 | 92.9 | 86.7 | 100 | 97.9 | 94.6 | 100 | 100 | 98.6 | 100 | 99.3 | 97.2 | 100 | 100 | 98.4 | 100 | 99.2 | 97.2 | 98.9 | 96.9 | 92.2 | 95.2 | 90.1 | 85.9 | 93.2 | 87.8 | 78.8 | 90.6 | 82.4 | 75.4
1 | 3.5 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 3.5 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 3.5 | 6 | 26 | 14 | 8.9 | 29.3 | 21.4 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.4 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 3.5 | 8 | 44.4 | 29.6 | 17.9 | 50.2 | 40 | 24 | 53.6 | 42.7 | 36.1 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.6 | 44.7 | 28.4 | 20.6
1 | 3.5 | 9 | 53.9 | 37.8 | 24.4 | 58 | 49.9 | 30.3 | 67.7 | 55.5 | 45.7 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.8 | 45 | 38.1 | 53.7 | 44.7 | 32.4 | 54.9 | 37.9 | 26.9
1 | 3.5 | 10 | 61.2 | 44.2 | 33.7 | 67.3 | 58.8 | 38.7 | 76.3 | 65.3 | 54 | 85.1 | 75.7 | 71.2 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 65.1 | 66.5 | 55.6 | 47.3 | 61.7 | 55.7 | 39.5 | 61.3 | 46.2 | 35.6
1 | 3.5 | 11 | 68.8 | 54 | 43.5 | 75.5 | 66.7 | 46 | 82.2 | 74.5 | 62.8 | 91.8 | 83.5 | 78.3 | 91.6 | 88 | 83.6 | 96.3 | 91.8 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 74.3 | 74.1 | 66.5 | 55.7 | 72.4 | 62.8 | 49.4 | 69.8 | 54.6 | 44.2
1 | 3.5 | 12 | 74.2 | 61.8 | 53 | 81.9 | 76.6 | 56.5 | 89.3 | 82 | 70.1 | 95 | 89.6 | 84.2 | 95.8 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.2 | 91.9 | 97.8 | 93.5 | 87.3 | 92.1 | 86.5 | 81 | 81 | 72.2 | 63.3 | 80.6 | 72.2 | 57.3 | 76.5 | 61.4 | 52.2
1 | 3.5 | 15 | 89.6 | 81.9 | 75 | 94.2 | 90.2 | 80.7 | 97.1 | 92.1 | 87.8 | 99.4 | 97.9 | 94.5 | 100 | 99.5 | 98.6 | 100 | 99.2 | 97.4 | 100 | 100 | 98.3 | 100 | 99.1 | 96.6 | 99 | 95.8 | 92.3 | 94.1 | 89.2 | 84.6 | 93.8 | 86.8 | 78.2 | 90.1 | 81.9 | 71.7
1 | 3.5 | 20 | 96.1 | 91.3 | 84.8 | 98.8 | 94.3 | 88.6 | 99.9 | 97.6 | 93.5 | 100 | 100 | 97.1 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.6 | 96 | 98.9 | 95.6 | 92.5 | 97.4 | 93.9 | 88.6 | 96.6 | 91.4 | 84.5
1 | 3.5 | 25 | 96.1 | 91.4 | 84.8 | 99 | 94.3 | 88.6 | 99.9 | 97.6 | 93.5 | 100 | 100 | 97.1 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.6 | 96 | 98.9 | 95.6 | 92.6 | 97.4 | 93.9 | 88.6 | 96.6 | 91.4 | 84.7
1 | 4 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 4 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 4 | 6 | 26 | 14 | 8.9 | 29.3 | 21.4 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.4 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 4 | 8 | 44.4 | 29.6 | 17.9 | 50.2 | 40 | 24 | 53.6 | 42.7 | 36.1 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.6 | 44.7 | 28.4 | 20.6
1 | 4 | 9 | 53.9 | 37.8 | 24.4 | 58 | 49.9 | 30.3 | 67.7 | 55.5 | 45.7 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.8 | 45 | 38.1 | 53.7 | 44.7 | 32.4 | 54.9 | 37.9 | 26.9
1 | 4 | 10 | 61.3 | 44.2 | 33.7 | 67.3 | 58.8 | 38.7 | 76.3 | 65.3 | 54 | 85.1 | 75.7 | 71.2 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 65.1 | 66.5 | 55.6 | 47.3 | 61.7 | 55.7 | 39.5 | 61.3 | 46.2 | 35.7
1 | 4 | 11 | 68.8 | 54.2 | 43.5 | 75.5 | 66.7 | 46 | 82.2 | 74.5 | 62.8 | 91.8 | 83.5 | 78.3 | 91.6 | 88 | 83.6 | 96.3 | 91.8 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 74.3 | 74.1 | 66.5 | 55.8 | 72.4 | 62.8 | 49.4 | 69.8 | 54.6 | 44.2
1 | 4 | 12 | 74.2 | 61.8 | 53 | 82.2 | 76.6 | 56.7 | 89.3 | 82 | 70.3 | 95 | 89.6 | 84.2 | 95.8 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.2 | 91.9 | 97.8 | 93.5 | 87.3 | 92.1 | 86.5 | 81 | 81 | 72.2 | 63.5 | 80.8 | 72.4 | 57.8 | 76.5 | 61.4 | 52.2
1 | 4 | 15 | 91 | 82.4 | 76.2 | 95.2 | 91.1 | 83 | 97.1 | 93.1 | 87.8 | 99.4 | 98.6 | 95.1 | 100 | 99.5 | 98.6 | 100 | 99.3 | 98.1 | 100 | 100 | 98.5 | 100 | 99.1 | 97 | 99 | 96.4 | 93 | 94.6 | 89.7 | 85.1 | 94.8 | 87.5 | 80.9 | 91.5 | 83.6 | 72.6
1 | 4 | 20 | 99 | 96 | 91.2 | 99.7 | 97.8 | 92.8 | 100 | 99.2 | 97 | 100 | 100 | 98.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.7 | 97.6 | 100 | 98 | 95.6 | 99.6 | 97.2 | 94.5 | 99.4 | 96 | 91.9
1 | 4 | 25 | 99 | 96.2 | 91.6 | 99.9 | 97.9 | 93.3 | 100 | 99.6 | 97.2 | 100 | 100 | 98.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.8 | 100 | 98.1 | 95.7 | 99.7 | 97.4 | 95.2 | 99.7 | 96.1 | 92.4
1 | 4.5 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 4.5 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 4.5 | 6 | 26 | 14 | 8.9 | 29.3 | 21.4 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.4 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 4.5 | 8 | 44.4 | 29.6 | 17.9 | 50.2 | 40 | 24 | 53.6 | 42.7 | 36.1 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.6 | 44.7 | 28.4 | 20.6
1 | 4.5 | 9 | 53.9 | 37.8 | 24.4 | 58 | 49.9 | 30.3 | 67.7 | 55.5 | 45.7 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.8 | 45 | 38.1 | 53.7 | 44.7 | 32.4 | 54.9 | 37.9 | 26.9
1 | 4.5 | 10 | 61.3 | 44.2 | 33.7 | 67.3 | 58.8 | 38.7 | 76.3 | 65.3 | 54 | 85.1 | 75.7 | 71.2 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 65.1 | 66.5 | 55.6 | 47.3 | 61.7 | 55.7 | 39.5 | 61.3 | 46.2 | 35.7
1 | 4.5 | 11 | 68.8 | 54.2 | 43.5 | 75.5 | 66.7 | 46 | 82.2 | 74.5 | 62.8 | 91.8 | 83.5 | 78.3 | 91.6 | 88 | 83.6 | 96.3 | 91.8 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 74.3 | 74.1 | 66.5 | 55.8 | 72.4 | 62.8 | 49.4 | 69.8 | 54.6 | 44.2
1 | 4.5 | 12 | 74.2 | 61.8 | 53 | 82.2 | 76.6 | 56.7 | 89.3 | 82 | 70.3 | 95 | 89.6 | 84.2 | 95.8 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.2 | 91.9 | 97.8 | 93.5 | 87.3 | 92.1 | 86.5 | 81 | 81 | 72.2 | 63.5 | 80.8 | 72.4 | 57.8 | 76.5 | 61.4 | 52.2
1 | 4.5 | 15 | 91.5 | 82.4 | 76.2 | 95.3 | 91.1 | 83 | 97.1 | 93.5 | 88.3 | 99.4 | 98.6 | 95.4 | 100 | 99.5 | 98.6 | 100 | 99.3 | 98.1 | 100 | 100 | 98.5 | 100 | 99.1 | 97 | 99 | 96.4 | 93.1 | 94.7 | 89.7 | 85.4 | 94.9 | 88.3 | 81.4 | 91.7 | 83.9 | 73
1 | 4.5 | 20 | 99.8 | 97.7 | 94 | 100 | 98.8 | 94.8 | 100 | 100 | 98.7 | 100 | 100 | 99.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 99.3 | 97.4 | 100 | 98.6 | 96.5 | 100 | 98.4 | 94.7
1 | 4.5 | 25 | 100 | 98.3 | 95.5 | 100 | 99.3 | 95.7 | 100 | 100 | 99 | 100 | 100 | 99.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.3 | 100 | 99.6 | 98.1 | 100 | 99.2 | 97.7 | 100 | 99.1 | 96.3
1 | 5 | 2 | 1.5 | 0.8 | 0.2 | 3.3 | 1.1 | 0.6 | 3.1 | 1.5 | 0.6 | 4.6 | 3.1 | 2.1 | 4.8 | 3.4 | 1.3 | 6 | 4.2 | 2.2 | 6 | 3.6 | 1.9 | 6 | 3.4 | 1.9 | 4.1 | 2.8 | 1.3 | 2.5 | 1.2 | 0.6 | 2 | 0.8 | 0.3 | 2.4 | 1.2 | 0.3
1 | 5 | 4 | 9.2 | 4 | 2.9 | 14.1 | 8.6 | 4.5 | 14.7 | 9.1 | 6.1 | 19.6 | 14.6 | 11 | 19.1 | 15.3 | 9.6 | 25.4 | 20.7 | 13.5 | 23.9 | 17.7 | 12.5 | 26 | 17.3 | 12.1 | 18.3 | 13.1 | 9.6 | 12.1 | 7.5 | 4.6 | 9.8 | 6 | 4 | 13.1 | 6.2 | 3
1 | 5 | 6 | 26 | 14 | 8.9 | 29.3 | 21.4 | 12 | 31.3 | 23.9 | 17.3 | 43.3 | 33.8 | 27.5 | 40.8 | 34.4 | 28.1 | 51.6 | 42.6 | 33 | 50.1 | 40.5 | 32.7 | 49.3 | 39.1 | 32.1 | 40.3 | 32.1 | 23.1 | 27.5 | 20.2 | 13.4 | 23.5 | 18.1 | 11.5 | 27.9 | 16.1 | 8.6
1 | 5 | 8 | 44.4 | 29.6 | 17.9 | 50.2 | 40 | 24 | 53.6 | 42.7 | 36.1 | 64.4 | 56.9 | 49.1 | 65.1 | 59.1 | 51.1 | 76.8 | 66.4 | 57.9 | 75.8 | 67.6 | 58.8 | 72.4 | 64.9 | 52.9 | 64.1 | 54.2 | 45.9 | 46.6 | 34.7 | 28.8 | 44.2 | 32.9 | 22.6 | 44.7 | 28.4 | 20.6
1 | 5 | 9 | 53.9 | 37.8 | 24.4 | 58 | 49.9 | 30.3 | 67.7 | 55.5 | 45.7 | 74.8 | 66.7 | 61.3 | 77.6 | 69 | 62.9 | 86.6 | 77.9 | 69.6 | 83.9 | 78.9 | 70.7 | 83.5 | 74.3 | 63.9 | 74 | 65 | 56.6 | 55.8 | 45 | 38.1 | 53.7 | 44.7 | 32.4 | 54.9 | 37.9 | 26.9
1 | 5 | 10 | 61.3 | 44.2 | 33.7 | 67.3 | 58.8 | 38.7 | 76.3 | 65.3 | 54 | 85.1 | 75.7 | 71.2 | 86.1 | 78.8 | 74.5 | 92.6 | 87.1 | 79.6 | 91.5 | 87 | 81.1 | 91.3 | 84 | 73.6 | 80.9 | 71.4 | 65.1 | 66.5 | 55.6 | 47.3 | 61.7 | 55.7 | 39.5 | 61.3 | 46.2 | 35.7
1 | 5 | 11 | 68.8 | 54.2 | 43.5 | 75.5 | 66.7 | 46 | 82.2 | 74.5 | 62.8 | 91.8 | 83.5 | 78.3 | 91.6 | 88 | 83.6 | 96.3 | 91.8 | 86.1 | 96.5 | 93.1 | 88 | 94.9 | 88.8 | 81 | 87.6 | 78.9 | 74.3 | 74.1 | 66.5 | 55.8 | 72.4 | 62.8 | 49.4 | 69.8 | 54.6 | 44.2
1 | 5 | 12 | 74.2 | 61.8 | 53 | 82.2 | 76.6 | 56.7 | 89.3 | 82 | 70.3 | 95 | 89.6 | 84.2 | 95.8 | 92.9 | 90.4 | 98.6 | 95 | 92.4 | 98.6 | 96.2 | 91.9 | 97.8 | 93.5 | 87.3 | 92.1 | 86.5 | 81 | 81 | 72.2 | 63.5 | 80.8 | 72.4 | 57.8 | 76.5 | 61.4 | 52.2
1 | 5 | 15 | 91.5 | 82.4 | 76.2 | 95.3 | 91.2 | 83 | 97.1 | 93.5 | 88.4 | 99.4 | 98.6 | 95.4 | 100 | 99.5 | 98.6 | 100 | 99.3 | 98.1 | 100 | 100 | 98.5 | 100 | 99.1 | 97 | 99 | 96.4 | 93.1 | 94.7 | 89.7 | 85.5 | 94.9 | 88.3 | 81.4 | 91.7 | 84.5 | 73
1 | 5 | 20 | 100 | 98 | 95.1 | 100 | 99.3 | 96.1 | 100 | 100 | 98.7 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.3 | 100 | 99.7 | 98.3 | 100 | 98.9 | 97.4 | 100 | 99.1 | 95.6
1 | 5 | 25 | 100 | 99.7 | 98.2 | 100 | 100 | 98 | 100 | 100 | 99.7 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.4 | 100 | 100 | 98.8 | 100 | 100 | 98.2
2 | 0.25 | 2 | [9 empty] | 0.3 |  |  | 0.7 |  |  | 1.2 | 0.1 |  | 0.7 | 0.4 |  | 1.1
2 | 0.25 | 4 | [9 empty] | 1.5 |  |  | 3 | 0.4 |  | 4.7 | 1 |  | 2.8 | 1.2 |  | 4.7 | 1.5 |  | 0.9
2 | 0.25 | 6 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.6 | 1.3 |  | 3.4 | 1.9 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 8 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 9 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 10 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 11 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 12 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 15 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 20 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.25 | 25 | [9 empty] | 2 |  |  | 3.9 | 0.8 |  | 6.8 | 1.3 |  | 3.4 | 2.2 |  | 5.5 | 2.4 |  | 1
2 | 0.5 | 2 | 0.2 |  |  | 0.4 |  |  | 0.9 | 0.3 |  | 2.2 | 1 | 0.2 | 2.5 | 0.8 |  | 4 | 1.8 | 0.3 | 4.3 | 1.6 | 0.8 | 3.1 | 1.3 | 0.7 | 2.1 | 0.8 |  | 0.6 |  |  | 0.3 |  |  | 0.6 | 0.1
2 | 0.5 | 4 | 1.9 | 0.1 |  | 2.9 | 2.2 |  | 5.7 | 1.5 |  | 8.9 | 4.3 | 1.5 | 10.4 | 4.2 | 1.7 | 13.5 | 9 | 3.3 | 13.7 | 8.2 | 4.6 | 14.3 | 8.3 | 5.3 | 9 | 4.9 | 1.8 | 3.3 | 1.5 |  | 2.4 | 0.4 |  | 3 | 0.7
2 | 0.5 | 6 | 4.3 | 0.4 |  | 5.9 | 2.7 |  | 8.7 | 2.8 | 0.4 | 16.3 | 8.2 | 4.7 | 17.6 | 10.1 | 5.7 | 22.1 | 15 | 6.5 | 26.9 | 17.6 | 8.5 | 23.8 | 15.3 | 8.2 | 16.3 | 8.9 | 2.7 | 5.2 | 2.2 | 0.1 | 2.9 | 0.7 |  | 4 | 1.6
2 | 0.5 | 8 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.2 | 8.5 | 5.2 | 20.7 | 12.6 | 6.6 | 25.4 | 17.6 | 7.4 | 30.4 | 20.2 | 10.2 | 26 | 16.7 | 9 | 17.7 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 9 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.2 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 10 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 11 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 12 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 15 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 20 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.5 | 25 | 4.3 | 0.4 |  | 6 | 2.8 |  | 10 | 3.1 | 0.5 | 17.5 | 8.5 | 5.2 | 21.1 | 12.6 | 6.6 | 25.6 | 17.6 | 7.6 | 30.4 | 20.3 | 10.4 | 26.3 | 16.7 | 9 | 17.8 | 9.6 | 3 | 5.5 | 2.3 | 0.1 | 3.2 | 0.7 |  | 4 | 1.6
2 | 0.75 | 2 | 0.4 |  |  | 1.7 | 0.3 |  | 1.8 | 0.5 |  | 3.4 | 1.7 | 0.9 | 3.5 | 1.6 | 0.7 | 5 | 2.8 | 1.5 | 4.8 | 2.7 | 1.3 | 4.1 | 2.4 | 1.1 | 2.8 | 1.9 | 0.6 | 1.2 | 0.5 |  | 0.8 | 0.1 |  | 1.1 | 0.3
2 | 0.75 | 4 | 4.4 | 1.1 | 0.1 | 8 | 4.2 | 0.4 | 9.2 | 4.3 | 1.9 | 15.1 | 7.8 | 5.3 | 14.5 | 8.6 | 5.2 | 19.5 | 14.4 | 8.2 | 18.7 | 13.2 | 9.3 | 19.4 | 13.8 | 7.7 | 14.4 | 9.3 | 5.2 | 6.7 | 3.1 | 0.9 | 4.7 | 2.5 | 0.5 | 5.3 | 2.3 | 0.7
2 | 0.75 | 6 | 11.1 | 4.3 | 0.6 | 14.5 | 8.5 | 1.8 | 20.2 | 10.1 | 5.9 | 28.3 | 16.8 | 13 | 29.7 | 21.2 | 15.2 | 37.6 | 26.8 | 16.2 | 37.2 | 29.3 | 22.3 | 38.2 | 26.9 | 18.5 | 27.5 | 19.9 | 11 | 14.2 | 7.3 | 3.6 | 10.9 | 5 | 1.8 | 11.9 | 5.9 | 1.4
2 | 0.75 | 8 | 16.8 | 6 | 0.6 | 17.6 | 11.4 | 2.8 | 26.4 | 12.8 | 8.1 | 35.5 | 22.8 | 15.8 | 37 | 29.3 | 20.6 | 45.5 | 36.9 | 23.7 | 50.7 | 38.2 | 29.5 | 46.3 | 37.6 | 26.9 | 35.2 | 27.1 | 13.9 | 18.4 | 10.3 | 5.6 | 12.7 | 7.2 | 2 | 13.5 | 7.7 | 1.7
2 | 0.75 | 9 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 23.5 | 16.2 | 39.2 | 30.1 | 23.3 | 46.9 | 37.5 | 24.5 | 52.2 | 40.5 | 30.3 | 48.1 | 39.2 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.3 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 10 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.5 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.3 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 11 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.9 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.6 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 12 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.9 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.6 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 15 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.9 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.6 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 20 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.9 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.6 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 0.75 | 25 | 16.8 | 6 | 0.6 | 17.8 | 11.4 | 2.8 | 26.5 | 13.4 | 8.4 | 36.5 | 24 | 16.3 | 39.4 | 30.9 | 23.7 | 47 | 37.5 | 24.6 | 52.3 | 40.5 | 30.3 | 48.6 | 39.4 | 27.3 | 35.9 | 27.1 | 14.2 | 18.4 | 10.6 | 5.6 | 12.8 | 7.2 | 2 | 13.6 | 7.7 | 1.7
2 | 1 | 2 | 1.1 | 0.3 |  | 2.1 | 0.6 |  | 2.5 | 1.1 |  | 3.7 | 2.2 | 1.3 | 4 | 2 | 0.9 | 5.5 | 3.2 | 1.9 | 5.9 | 3.1 | 1.6 | 4.7 | 2.7 | 1.3 | 3.2 | 2.2 | 0.9 | 1.7 | 0.7 | 0.4 | 1.5 | 0.4 |  | 1.3 | 0.5
2 | 1 | 4 | 5.9 | 2.4 | 0.7 | 10.4 | 5.6 | 2 | 12.2 | 6.7 | 2.5 | 17.5 | 11.3 | 7.3 | 16.9 | 12.1 | 7.1 | 23 | 17.1 | 10.9 | 21.8 | 15.6 | 10.5 | 22 | 15.3 | 10.8 | 15.4 | 10.6 | 7.1 | 9.8 | 4.7 | 2.7 | 6.7 | 3.3 | 1.5 | 6.4 | 3.4 | 0.9
2 | 1 | 6 | 16.9 | 8.6 | 2.3 | 20.1 | 14.3 | 5.5 | 26.9 | 15.9 | 8.6 | 35.6 | 24.6 | 19.3 | 36.2 | 28.2 | 20.8 | 45.7 | 35 | 26.6 | 45.1 | 35.5 | 27.4 | 44 | 32.3 | 25.8 | 33.8 | 27.5 | 18.2 | 21.7 | 11.8 | 6.9 | 15.8 | 8.9 | 5 | 18.2 | 8.3 | 3.7
2 | 1 | 8 | 26.2 | 13.6 | 3.5 | 30 | 19.8 | 10.3 | 36.9 | 24.7 | 15.9 | 52.5 | 37.4 | 29.5 | 52.3 | 45 | 35.4 | 62.3 | 52.2 | 42.1 | 65.9 | 55.5 | 40.8 | 61.5 | 50.8 | 41.8 | 47.5 | 40.4 | 29.5 | 29.8 | 19.5 | 10.6 | 24.3 | 14.9 | 7.5 | 25.9 | 12.4 | 6
2 | 1 | 9 | 26.6 | 15.1 | 3.7 | 31.1 | 21 | 10.8 | 39.9 | 28.4 | 18.1 | 55.1 | 40 | 31.5 | 57.8 | 48.3 | 38.2 | 65.9 | 55.3 | 45.9 | 71 | 60.1 | 45.4 | 66.8 | 53.9 | 44.9 | 51.7 | 43.1 | 31.2 | 32.2 | 22.2 | 11.8 | 26 | 16 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 10 | 26.8 | 14.7 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.4 | 18.7 | 55.8 | 41.3 | 32.1 | 60.1 | 50.4 | 39.6 | 66.6 | 56.7 | 47.7 | 71.8 | 61.7 | 47.6 | 68.3 | 55 | 45.9 | 52.8 | 44.4 | 31.9 | 32.4 | 23.5 | 12.3 | 26.2 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 11 | 26.8 | 14.7 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.9 | 18.7 | 56.1 | 41.3 | 32.4 | 60.2 | 50.7 | 40 | 66.7 | 56.7 | 47.8 | 72.1 | 62.1 | 47.9 | 68.7 | 55.5 | 46.3 | 53 | 44.7 | 31.9 | 32.4 | 23.8 | 12.3 | 26.3 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 12 | 26.8 | 14.7 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.9 | 18.7 | 56.1 | 41.3 | 32.6 | 60.2 | 50.5 | 40 | 66.7 | 56.7 | 48 | 72.1 | 62.1 | 47.9 | 68.7 | 55.5 | 46.5 | 53 | 44.7 | 31.9 | 32.4 | 23.8 | 12.3 | 26.3 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 15 | 26.8 | 14.9 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.9 | 18.7 | 56.1 | 41.3 | 32.6 | 60.2 | 50.8 | 40 | 66.7 | 56.7 | 48 | 72.1 | 62.1 | 47.9 | 68.7 | 55.5 | 46.5 | 53 | 44.7 | 31.9 | 32.4 | 23.8 | 12.3 | 26.3 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 20 | 26.8 | 14.9 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.9 | 18.7 | 56.1 | 41.3 | 32.6 | 60.2 | 50.8 | 40 | 66.7 | 56.7 | 48 | 72.1 | 62.1 | 47.9 | 68.7 | 55.5 | 46.5 | 53 | 44.7 | 31.9 | 32.4 | 23.8 | 12.3 | 26.3 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1 | 25 | 26.8 | 14.9 | 3.8 | 31.2 | 21 | 10.8 | 40.3 | 28.9 | 18.7 | 56.1 | 41.3 | 32.6 | 60.2 | 50.8 | 40 | 66.7 | 56.7 | 48 | 72.1 | 62.1 | 47.9 | 68.7 | 55.5 | 46.5 | 53 | 44.7 | 31.9 | 32.4 | 23.8 | 12.3 | 26.3 | 16.1 | 7.7 | 27.5 | 12.6 | 6.5
2 | 1.25 | 2 | 1.2 | 0.5 |  | 2.3 | 0.9 | 0.1 | 2.6 | 1.2 | 0.3 | 3.8 | 2.5 | 1.5 | 4 | 2.8 | 1.1 | 5.9 | 3.3 | 1.9 | 5.9 | 3.5 | 1.6 | 5.2 | 2.7 | 1.5 | 3.5 | 2.2 | 1.2 | 1.9 | 0.8 | 0.4 | 1.5 | 0.7 | 0.1 | 1.7 | 0.7 | 0.2
2 | 1.25 | 4 | 6.4 | 3.1 | 1.6 | 11.6 | 7.6 | 2.9 | 13.8 | 7.9 | 3.5 | 18.7 | 11.9 | 9.2 | 17.7 | 13.7 | 8.8 | 23.7 | 19 | 12.4 | 22.8 | 16.3 | 11.1 | 23.7 | 16 | 11.4 | 16.9 | 11.4 | 7.6 | 10.5 | 5.6 | 3.6 | 8 | 4.6 | 2.5 | 8.5 | 3.9 | 1.7
2 | 1.25 | 6 | 22.1 | 9.7 | 5.7 | 24.6 | 16.8 | 7 | 28.2 | 19.8 | 12.1 | 38 | 27.9 | 22.4 | 38.9 | 30.9 | 25 | 49.7 | 40.6 | 30.7 | 47 | 38.6 | 29.3 | 45.3 | 34.9 | 29.6 | 37 | 29.7 | 19.2 | 24.9 | 15.1 | 10.5 | 20.4 | 12.6 | 7.7 | 21.8 | 11.8 | 5.4
2 | 1.25 | 8 | 34.8 | 21 | 9.7 | 36.8 | 28.1 | 12.7 | 47.5 | 34.8 | 22.8 | 58.9 | 46.1 | 39.4 | 58.4 | 53.2 | 45.3 | 71.3 | 60.8 | 49.2 | 72 | 63.6 | 50.3 | 69.2 | 58.2 | 49.3 | 56.3 | 47.2 | 36.3 | 36.5 | 26.7 | 19.1 | 32.9 | 23.1 | 13 | 35.2 | 18.8 | 11.9
2 | 1.25 | 9 | 37.1 | 23.8 | 10.7 | 42.2 | 30.8 | 15.7 | 51.3 | 41.9 | 27.5 | 65.3 | 52.8 | 44.8 | 68.8 | 60.1 | 52.8 | 77.7 | 67.5 | 57.6 | 78.9 | 72.4 | 56.8 | 75 | 66.8 | 55.9 | 63.9 | 52.1 | 40.3 | 42.8 | 32.8 | 21.8 | 37.5 | 27.4 | 15.2 | 36.9 | 22.6 | 14.5
2 | 1.25 | 10 | 38.9 | 24.1 | 11.6 | 45.4 | 33.2 | 16.8 | 54.7 | 43.1 | 28.8 | 70.1 | 56.1 | 46.4 | 74 | 64 | 57.3 | 80.8 | 72.4 | 60.6 | 83.2 | 76.6 | 60.3 | 78.3 | 69.4 | 59 | 65.9 | 56.3 | 42.8 | 45.4 | 34.9 | 23.1 | 39.1 | 28.6 | 16 | 37.8 | 23.4 | 15.6
2 | 1.25 | 11 | 39.2 | 24.6 | 11.8 | 45.8 | 33.5 | 17.2 | 55.2 | 44.1 | 28.8 | 72.1 | 57.4 | 47 | 75.1 | 66.1 | 59.5 | 81.2 | 74 | 61.6 | 84.8 | 77.8 | 61.8 | 79.2 | 71.2 | 60.9 | 66.4 | 58.3 | 43.5 | 45.5 | 36.3 | 23.5 | 39.4 | 29.3 | 16 | 38 | 23.4 | 15.7
2 | 1.25 | 12 | 39.2 | 24.6 | 11.8 | 45.9 | 33.5 | 17.2 | 55.6 | 44.4 | 28.9 | 72.1 | 57.9 | 47.3 | 75.1 | 66.1 | 59.8 | 81.2 | 74 | 62.4 | 84.8 | 78.1 | 62.6 | 79.3 | 71.5 | 61.1 | 66.8 | 58.3 | 43.6 | 45.5 | 36.6 | 23.5 | 39.4 | 29.3 | 16 | 38 | 23.4 | 15.7
2 | 1.25 | 15 | 39.4 | 24.6 | 11.8 | 45.9 | 33.5 | 17.4 | 55.6 | 44.4 | 28.9 | 72.1 | 57.9 | 47.3 | 75.2 | 66.1 | 59.9 | 81.2 | 74 | 62.4 | 84.8 | 78.1 | 62.9 | 79.3 | 71.5 | 61.1 | 66.8 | 58.3 | 43.6 | 45.5 | 36.6 | 23.5 | 39.4 | 29.3 | 16 | 38 | 23.4 | 15.7
2 | 1.25 | 20 | 39.4 | 24.6 | 11.8 | 45.9 | 33.5 | 17.4 | 55.6 | 44.4 | 28.9 | 72.1 | 57.9 | 47.3 | 75.2 | 66.1 | 59.9 | 81.2 | 74 | 62.4 | 84.8 | 78.1 | 62.9 | 79.3 | 71.5 | 61.1 | 66.8 | 58.6 | 43.6 | 45.5 | 36.6 | 23.5 | 39.4 | 29.3 | 16 | 38 | 23.4 | 15.7
2 | 1.25 | 25 | 39.4 | 24.6 | 11.8 | 45.9 | 33.5 | 17.4 | 55.6 | 44.4 | 28.9 | 72.1 | 57.9 | 47.3 | 75.2 | 66.1 | 59.9 | 81.2 | 74 | 62.4 | 84.8 | 78.1 | 62.9 | 79.3 | 71.5 | 61.1 | 66.8 | 58.6 | 43.6 | 45.5 | 36.6 | 23.5 | 39.4 | 29.3 | 16 | 38 | 23.4 | 15.7
2 | 1.5 | 2 | 1.3 | 0.5 |  | 2.7 | 0.7 | 0.3 | 2.7 | 1.3 | 0.3 | 3.9 | 2.5 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.6 | 2.2 | 1.3 | 2 | 0.8 | 0.4 | 1.5 | 0.7 | 0.1 | 1.9 | 0.9 | 0.3
2 | 1.5 | 4 | 7.9 | 3.6 | 1.9 | 12.5 | 7.7 | 3.3 | 13.8 | 8.3 | 4.1 | 18.7 | 12.9 | 9.9 | 17.9 | 14.1 | 9.2 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.3 | 23.9 | 16.1 | 11.6 | 17.5 | 11.9 | 8.2 | 10.8 | 6.3 | 3.9 | 8.9 | 5 | 3.1 | 10.5 | 4.4 | 2.5
2 | 1.5 | 6 | 24 | 12.1 | 6.4 | 26.7 | 17.7 | 8.7 | 29.8 | 21.8 | 14.4 | 38.5 | 29.4 | 25.6 | 39.4 | 32.3 | 25.6 | 50.4 | 41.1 | 31.4 | 49.1 | 39.4 | 30 | 47.7 | 37.9 | 30.8 | 38.2 | 30.7 | 21.2 | 26.4 | 18 | 11.8 | 20.8 | 15.1 | 8.9 | 23.9 | 14.2 | 6.8
2 | 1.5 | 8 | 39 | 24.9 | 13.6 | 42.1 | 32.7 | 17.2 | 49.1 | 38 | 27.7 | 62.2 | 50 | 44 | 62.4 | 56.7 | 47.8 | 74.1 | 64.7 | 53.9 | 74.6 | 66.3 | 55.5 | 70.8 | 61.8 | 50.9 | 60 | 50.4 | 41.6 | 42.6 | 31.2 | 23 | 38.4 | 27.9 | 18.7 | 38 | 23.4 | 15.1
2 | 1.5 | 9 | 43.1 | 31.6 | 16.9 | 51.1 | 40.4 | 21.3 | 60.9 | 47.2 | 35.9 | 70.3 | 58.8 | 52.2 | 73.7 | 65.3 | 57.3 | 82.5 | 74 | 64.7 | 81.6 | 76.2 | 65.2 | 79.2 | 70.6 | 60.4 | 67.3 | 59.6 | 49.2 | 48.1 | 39.1 | 29 | 44.9 | 34.7 | 22.6 | 43 | 28.4 | 18.5
2 | 1.5 | 10 | 46.7 | 33.9 | 19.8 | 58.4 | 44.9 | 26.4 | 66.6 | 52.3 | 41.5 | 76.8 | 65.1 | 56.2 | 80.9 | 72.4 | 66.7 | 87.2 | 81.7 | 70.9 | 88.7 | 82.9 | 72 | 85.2 | 76.6 | 66.7 | 74.6 | 63.6 | 54.3 | 56.9 | 44.4 | 34 | 52.4 | 37.8 | 25.3 | 47.2 | 31.6 | 22.5
2 | 1.5 | 11 | 48.5 | 34.9 | 21 | 59.8 | 47.3 | 26.7 | 70.9 | 53.9 | 43.3 | 80.9 | 69.2 | 59.9 | 83.5 | 77.6 | 69.2 | 89.2 | 83.6 | 74.2 | 92.1 | 86.2 | 75.3 | 87.1 | 79.4 | 69.9 | 77.2 | 67.1 | 56.9 | 60.1 | 48.5 | 36.2 | 54.7 | 39 | 26.7 | 50.2 | 33.9 | 23.1
2 | 1.5 | 12 | 48.8 | 35.2 | 21.8 | 60.3 | 48.5 | 27.4 | 71.4 | 54.7 | 43.5 | 82 | 70.8 | 60.7 | 83.9 | 78.8 | 70.8 | 89.7 | 84 | 75.3 | 93.1 | 86.4 | 75.5 | 87.6 | 79.6 | 70.7 | 77.6 | 68.5 | 57.2 | 61.3 | 49.5 | 36.9 | 55.2 | 39.3 | 27.5 | 50.4 | 34 | 23.4
2 | 1.5 | 15 | 48.9 | 35.8 | 21.8 | 60.3 | 48.5 | 27.2 | 71.5 | 54.7 | 43.9 | 82.3 | 70.8 | 60.8 | 84.5 | 78.8 | 71 | 89.7 | 84.2 | 75.2 | 93.2 | 86.8 | 75.5 | 87.6 | 79.6 | 71.2 | 77.8 | 68.5 | 57.2 | 61.5 | 49.6 | 36.9 | 55.5 | 39.3 | 27.6 | 50.5 | 34 | 23.4
2 | 1.5 | 20 | 49 | 35.8 | 21.8 | 60.3 | 48.5 | 27.2 | 71.5 | 54.7 | 43.9 | 82.3 | 70.8 | 60.8 | 84.5 | 78.8 | 71 | 89.7 | 84.2 | 75.2 | 93.3 | 86.8 | 75.5 | 87.6 | 79.6 | 71.2 | 77.8 | 68.5 | 57.2 | 61.5 | 49.6 | 36.9 | 55.5 | 39.3 | 27.6 | 50.5 | 34 | 23.4
2 | 1.5 | 25 | 49 | 35.8 | 21.8 | 60.3 | 48.5 | 27.2 | 71.5 | 54.7 | 43.9 | 82.3 | 70.8 | 60.8 | 84.5 | 78.8 | 71 | 89.7 | 84.2 | 75.2 | 93.3 | 86.8 | 75.5 | 87.6 | 79.6 | 71.2 | 77.8 | 68.5 | 57.2 | 61.5 | 49.6 | 36.9 | 55.5 | 39.3 | 27.6 | 50.5 | 34 | 23.4
2 | 1.75 | 2 | 1.3 | 0.7 | 0.1 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.5 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.4 | 1.8 | 0.8 | 0.1 | 2.2 | 1.1 | 0.3
2 | 1.75 | 4 | 8.4 | 3.8 | 2 | 13.1 | 8.2 | 3.5 | 14.1 | 8.5 | 5.6 | 18.7 | 13.2 | 10.1 | 18 | 14.5 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.2 | 16.1 | 11.6 | 17.5 | 12.5 | 8.6 | 10.8 | 6.5 | 4.1 | 9.3 | 5.4 | 3.2 | 11 | 5.4 | 2.6
2 | 1.75 | 6 | 24.6 | 13.3 | 7.7 | 27.9 | 19.8 | 10.8 | 30 | 22.7 | 16.6 | 41.5 | 31.1 | 26.2 | 39.6 | 33.3 | 26.5 | 50.6 | 41.7 | 31.7 | 49.1 | 39.4 | 30.4 | 47.8 | 38.2 | 31 | 38.7 | 31.5 | 21.8 | 26.7 | 18.8 | 12 | 22.3 | 16.4 | 9.9 | 24.5 | 14.9 | 7
2 | 1.75 | 8 | 41.5 | 27.4 | 15.5 | 45.2 | 35.6 | 20.8 | 50.6 | 40.3 | 33.4 | 63.9 | 52.9 | 46.7 | 63.5 | 58.5 | 48.6 | 75.4 | 65.1 | 56.1 | 75.2 | 66.8 | 56.7 | 70.8 | 62.8 | 51.4 | 62.7 | 52.4 | 44.1 | 44.7 | 32.8 | 25.1 | 41.1 | 31 | 19.2 | 39.5 | 26.3 | 17.3
2 | 1.75 | 9 | 48.9 | 34.5 | 20.4 | 55.6 | 45.4 | 26.3 | 64.9 | 49.6 | 40.5 | 71.8 | 62.4 | 57 | 75 | 66.8 | 59.9 | 85.1 | 76.4 | 67.5 | 82.7 | 77.6 | 67.8 | 81.1 | 71.8 | 62.1 | 71.3 | 62.4 | 53.6 | 51.9 | 41.1 | 33.7 | 48.4 | 38.2 | 27.1 | 46.9 | 32 | 21.9
2 | 1.75 | 10 | 53 | 39.4 | 27.2 | 64.7 | 51.3 | 31 | 73.3 | 58.1 | 45.2 | 82 | 72.1 | 63.5 | 83.9 | 75.3 | 70 | 90.3 | 84.7 | 75.8 | 90.1 | 84.7 | 76.4 | 88.5 | 77.7 | 70.3 | 77 | 68.1 | 58.7 | 60.1 | 48.5 | 40.9 | 56.6 | 44.3 | 32 | 55 | 38.3 | 27.4
2 | 1.75 | 11 | 57.3 | 43.3 | 32.8 | 67.9 | 57.3 | 33.3 | 77.1 | 65.5 | 50.6 | 87.3 | 76.9 | 68.5 | 88.1 | 82.5 | 77.2 | 93.4 | 88.5 | 80.9 | 95.4 | 89.1 | 81.1 | 90.8 | 83.6 | 76 | 81.7 | 74 | 64.2 | 68.4 | 56 | 46.1 | 61.8 | 48.5 | 34.9 | 58 | 41.9 | 30
2 | 1.75 | 12 | 59 | 44.5 | 35.8 | 70 | 59.5 | 35.6 | 79.3 | 66.3 | 53.6 | 87.7 | 79.3 | 69.6 | 90.6 | 85.2 | 80.8 | 94.3 | 89.3 | 83.8 | 96.4 | 91 | 82.3 | 93 | 84.8 | 78.5 | 83.6 | 75.6 | 66.1 | 72.8 | 58.6 | 49 | 63.8 | 49.6 | 36.6 | 60.9 | 42.9 | 30.9
2 | 1.75 | 15 | 59.8 | 45.4 | 36.5 | 70.8 | 60.7 | 36.7 | 80.4 | 67.1 | 55.8 | 88.3 | 79.7 | 70 | 91.2 | 86.6 | 82.3 | 94.7 | 89.7 | 84.4 | 96.4 | 91.5 | 82.6 | 93.3 | 85.2 | 79.5 | 84.3 | 76.5 | 66.9 | 74 | 59.9 | 51.1 | 65.1 | 49.7 | 37.8 | 61.5 | 43.1 | 31.2
2 | 1.75 | 20 | 59.8 | 45.4 | 36.5 | 70.8 | 60.7 | 36.7 | 80.4 | 67.1 | 55.8 | 88.3 | 79.7 | 70 | 91.2 | 86.6 | 82.3 | 94.7 | 89.7 | 84.4 | 96.4 | 91.5 | 82.6 | 93.3 | 85.2 | 79.5 | 84.3 | 76.5 | 66.9 | 74 | 59.9 | 51.1 | 65.1 | 49.7 | 37.8 | 61.5 | 43.1 | 31.2
2 | 1.75 | 25 | 59.8 | 45.4 | 36.5 | 70.8 | 60.7 | 36.7 | 80.4 | 67.1 | 55.8 | 88.3 | 79.7 | 70 | 91.2 | 86.6 | 82.3 | 94.7 | 89.7 | 84.4 | 96.4 | 91.5 | 82.6 | 93.3 | 85.2 | 79.5 | 84.3 | 76.5 | 66.9 | 74 | 59.9 | 51.1 | 65.1 | 49.7 | 37.8 | 61.5 | 43.1 | 31.2
2 | 2 | 2 | 1.4 | 0.7 | 0.1 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 2 | 4 | 8.9 | 3.8 | 2.2 | 13.5 | 8.2 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 8.6 | 11 | 6.9 | 4.2 | 9.3 | 5.6 | 3.6 | 11.8 | 5.4 | 2.6
2 | 2 | 6 | 24.9 | 13.6 | 8.3 | 28.1 | 19.8 | 10.8 | 30.1 | 22.8 | 16.9 | 41.6 | 31.7 | 26.7 | 39.7 | 33.3 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31 | 47.8 | 38.2 | 31 | 38.7 | 31.5 | 21.8 | 26.8 | 19.4 | 12 | 22.4 | 17.1 | 10.3 | 25.2 | 15.2 | 7.9
2 | 2 | 8 | 42.5 | 28.2 | 16.8 | 47.7 | 36.4 | 21.4 | 52.2 | 41.4 | 34.6 | 64 | 55 | 47.4 | 63.8 | 58.5 | 49.9 | 75.5 | 65.7 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.1 | 44.4 | 45.1 | 33.1 | 27.2 | 42.3 | 31.5 | 20.8 | 41 | 26.7 | 18.5
2 | 2 | 9 | 52.4 | 36.3 | 21.9 | 56.6 | 47.5 | 27.5 | 65.9 | 52 | 42.9 | 71.9 | 64.6 | 59.1 | 76.2 | 67.6 | 60.9 | 85.7 | 76.9 | 68.5 | 83.1 | 77.8 | 69.5 | 82.3 | 72.4 | 63.1 | 73 | 63.8 | 54.9 | 53.5 | 41.5 | 35.4 | 50.8 | 40 | 29.1 | 49.8 | 35.3 | 23.9
2 | 2 | 10 | 56.7 | 43 | 30.3 | 65.5 | 54.9 | 32.9 | 75.3 | 62 | 49.1 | 82.9 | 73.8 | 66.7 | 84.3 | 77.7 | 73 | 91.4 | 85.8 | 78.4 | 90.8 | 85.8 | 79.2 | 89.7 | 80.5 | 72.2 | 79.8 | 69.6 | 61.3 | 61.5 | 51.5 | 43.8 | 58.5 | 47.6 | 35.5 | 57.9 | 41.7 | 31
2 | 2 | 11 | 61.8 | 48.7 | 38.2 | 72.3 | 62.2 | 38.6 | 79.3 | 68.7 | 56.3 | 89.2 | 79.7 | 72 | 90.1 | 84.4 | 80.8 | 95 | 90.6 | 84.1 | 95.9 | 91.5 | 83.5 | 93.2 | 85.1 | 77.9 | 84.2 | 77.1 | 68.4 | 70.7 | 60.5 | 50.4 | 66.4 | 55.7 | 41.6 | 62.6 | 46.1 | 36
2 | 2 | 12 | 65.6 | 52.8 | 43 | 76.4 | 67.4 | 44 | 83.6 | 73.7 | 59.5 | 91.1 | 84.9 | 75.8 | 92.9 | 89.5 | 85.8 | 96.1 | 92.4 | 88.5 | 98.3 | 94.6 | 87 | 96.6 | 87.6 | 82.2 | 86.7 | 80.6 | 72.2 | 74.9 | 64 | 55.8 | 71.1 | 59.3 | 44.3 | 66.6 | 48.8 | 37.9
2 | 2 | 15 | 69.3 | 55.1 | 45.1 | 80.9 | 71.1 | 46.7 | 85.6 | 76.2 | 64 | 93.4 | 86.8 | 77.6 | 94.6 | 91 | 88.3 | 96.9 | 93.5 | 89.7 | 99.1 | 96.2 | 89.9 | 97.4 | 89 | 84.2 | 88.6 | 83.3 | 74.7 | 78.8 | 69.4 | 61.7 | 76.5 | 62.2 | 47.4 | 70.1 | 51.9 | 39.2
2 | 2 | 20 | 69.6 | 55.1 | 45.3 | 80.9 | 71.1 | 46.7 | 85.6 | 76.2 | 64 | 93.4 | 86.8 | 77.6 | 94.6 | 91 | 88.3 | 96.9 | 93.5 | 89.7 | 99.1 | 96.2 | 89.9 | 97.4 | 89 | 84.6 | 88.6 | 83.3 | 74.7 | 78.8 | 69.4 | 61.9 | 76.5 | 62.5 | 47.4 | 70.1 | 52 | 39.2
2 | 2 | 25 | 69.6 | 55.1 | 45.3 | 80.9 | 71.1 | 46.7 | 85.6 | 76.2 | 64 | 93.4 | 86.8 | 77.6 | 94.6 | 91 | 88.3 | 96.9 | 93.5 | 89.7 | 99.1 | 96.2 | 89.9 | 97.4 | 89 | 84.6 | 88.6 | 83.3 | 74.7 | 78.8 | 69.4 | 61.9 | 76.5 | 62.5 | 47.4 | 70.1 | 52 | 39.2
2 | 2.25 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 2.25 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.6 | 12.2 | 5.4 | 2.7
2 | 2.25 | 6 | 24.9 | 13.6 | 8.5 | 28.2 | 19.8 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.2 | 22.4 | 16.9 | 10.9 | 26.3 | 15.5 | 8.1
2 | 2.25 | 8 | 43.1 | 28.9 | 17.2 | 48.7 | 36.6 | 22.2 | 52.2 | 41.7 | 34.9 | 64 | 55.3 | 47.6 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34 | 27.7 | 42.7 | 31.8 | 21.1 | 42.3 | 26.7 | 19
2 | 2.25 | 9 | 52.5 | 36.7 | 22.8 | 57.2 | 47.8 | 28.7 | 65.9 | 53.2 | 43.4 | 72.8 | 65.3 | 59.6 | 76.6 | 67.6 | 61.7 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.1 | 63.3 | 73.1 | 63.9 | 55.1 | 54.3 | 42.9 | 35.6 | 52.1 | 41.7 | 30.1 | 51.5 | 36.7 | 24.6
2 | 2.25 | 10 | 58.6 | 43 | 31.4 | 65.9 | 56.1 | 35.3 | 75.7 | 62.6 | 50 | 83.5 | 74.2 | 68.4 | 84.5 | 78.2 | 73 | 91.8 | 86.1 | 78.6 | 90.8 | 86.3 | 79.9 | 90.1 | 83.2 | 72.6 | 80 | 69.9 | 63.3 | 63.4 | 53.1 | 45.4 | 60.1 | 51.3 | 36.8 | 59.2 | 43.7 | 32
2 | 2.25 | 11 | 65.9 | 50.7 | 40.6 | 73.6 | 63.4 | 42.3 | 80.2 | 71 | 59.1 | 89.8 | 80.8 | 75.5 | 90.6 | 85.8 | 82.2 | 95.9 | 90.8 | 85.3 | 96.2 | 91.8 | 85.9 | 94.2 | 86.8 | 79.3 | 86.8 | 77.6 | 70.5 | 72.2 | 62.1 | 52.2 | 69.4 | 59.2 | 44.7 | 64.9 | 49.1 | 40.9
2 | 2.25 | 12 | 69.7 | 57 | 46.9 | 79.2 | 70.5 | 51 | 86.2 | 76.7 | 62.7 | 93.6 | 86.5 | 80 | 94.4 | 91.3 | 87.7 | 98 | 94.2 | 90.6 | 98.3 | 95.3 | 89.9 | 97.5 | 91.1 | 85.5 | 89.9 | 84 | 75.4 | 77.9 | 68.7 | 59.3 | 75.3 | 65 | 48.7 | 71.9 | 53.5 | 46.2
2 | 2.25 | 15 | 77 | 62.5 | 52 | 85 | 76.5 | 56.9 | 90.8 | 81.9 | 69.6 | 96.4 | 92.5 | 84.7 | 96.8 | 95.3 | 92.4 | 99.4 | 96 | 93.5 | 99.9 | 97.6 | 94.5 | 98.3 | 93.4 | 88.8 | 93.5 | 88.2 | 81 | 84.5 | 76.9 | 71.5 | 82 | 70.4 | 55.2 | 77.2 | 63 | 50.9
2 | 2.25 | 20 | 76.9 | 62.9 | 52 | 85.3 | 77.1 | 56.9 | 91.1 | 82 | 69.8 | 96.4 | 92.5 | 84.7 | 96.9 | 95.3 | 92.4 | 99.4 | 96.1 | 93.7 | 99.9 | 97.6 | 94.6 | 98.3 | 93.7 | 89.1 | 93.6 | 88.5 | 81.2 | 84.7 | 77.2 | 71.5 | 82.6 | 70.6 | 56.3 | 77.3 | 63.3 | 51.4
2 | 2.25 | 25 | 76.9 | 62.9 | 52 | 85.3 | 77.1 | 56.9 | 91.1 | 82 | 69.8 | 96.4 | 92.5 | 84.7 | 96.9 | 95.3 | 92.4 | 99.4 | 96.1 | 93.7 | 99.9 | 97.6 | 94.6 | 98.3 | 93.7 | 89.1 | 93.6 | 88.5 | 81.2 | 84.7 | 77.2 | 71.5 | 82.6 | 70.6 | 56.3 | 77.3 | 63.3 | 51.4
2 | 2.75 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 2.75 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 2.75 | 6 | 24.9 | 13.6 | 8.5 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 2.75 | 8 | 43.3 | 28.9 | 17.4 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.4 | 27 | 19.3
2 | 2.75 | 9 | 52.7 | 36.6 | 23.2 | 57.3 | 48.6 | 29.7 | 65.9 | 53.2 | 43.9 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.6 | 36.5 | 53.1 | 43.3 | 31 | 53.9 | 37 | 25.5
2 | 2.75 | 10 | 60 | 43.3 | 32.3 | 65.9 | 57.4 | 37.5 | 76 | 63.8 | 52.2 | 84 | 74.7 | 70.5 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.2 | 65.7 | 53.9 | 46.3 | 61.1 | 53.3 | 37.7 | 60.9 | 44.1 | 33.5
2 | 2.75 | 11 | 67.1 | 52.8 | 42 | 74.5 | 65.5 | 44.2 | 80.8 | 73.4 | 61 | 90.8 | 83.2 | 77.4 | 91 | 87.8 | 82.9 | 96 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.6 | 80 | 87.5 | 78.3 | 72.8 | 73.1 | 64.5 | 54 | 71.2 | 60.8 | 47.5 | 68.4 | 52.8 | 42.9
2 | 2.75 | 12 | 73.1 | 60.2 | 50.8 | 80.1 | 75.3 | 54.4 | 88.3 | 80.5 | 66.4 | 94.5 | 87.9 | 82.9 | 95.3 | 92.1 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96 | 91.3 | 97.5 | 93 | 86.6 | 91.3 | 85.8 | 77.8 | 79.4 | 71.1 | 61.4 | 79.3 | 69 | 52.5 | 73.7 | 58.6 | 50.5
2 | 2.75 | 15 | 86.1 | 73.5 | 64.1 | 91.1 | 85.6 | 71.3 | 95 | 88.4 | 80.2 | 98.8 | 96 | 91.9 | 99.7 | 98.5 | 96.6 | 100 | 98.2 | 96.4 | 100 | 99.1 | 96.7 | 100 | 97.7 | 94.2 | 97.1 | 94.6 | 88.5 | 91.5 | 84.5 | 80.3 | 89.8 | 82.4 | 68.7 | 86.1 | 73.4 | 65.3
2 | 2.75 | 20 | 88.8 | 75.9 | 65.3 | 92.7 | 86.1 | 72.9 | 95.8 | 89.2 | 80.7 | 99.1 | 96.1 | 92.5 | 100 | 98.9 | 96.8 | 100 | 98.3 | 96.5 | 100 | 99.1 | 96.7 | 100 | 98 | 95.5 | 97.4 | 95.8 | 89.9 | 92.1 | 86.7 | 81.4 | 90.7 | 83.2 | 72.3 | 86.9 | 75.8 | 68.5
2 | 2.75 | 25 | 88.8 | 75.9 | 65.3 | 92.7 | 86.1 | 72.9 | 95.8 | 89.2 | 80.7 | 99.1 | 96.1 | 92.5 | 100 | 98.9 | 96.9 | 100 | 98.3 | 96.5 | 100 | 99.1 | 96.7 | 100 | 98 | 95.5 | 97.4 | 95.8 | 89.9 | 92.1 | 86.7 | 81.4 | 90.7 | 83.2 | 72.3 | 86.9 | 75.8 | 68.5
2 | 3 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 3 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 3 | 6 | 24.9 | 13.6 | 8.6 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 3 | 8 | 43.3 | 28.9 | 17.6 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.5 | 27 | 19.4
2 | 3 | 9 | 52.9 | 36.6 | 23.2 | 57.3 | 48.6 | 29.8 | 65.9 | 53.2 | 44.1 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.9 | 36.5 | 53.1 | 43.3 | 31 | 54 | 37.2 | 25.6
2 | 3 | 10 | 60.2 | 43.3 | 32.3 | 65.9 | 57.7 | 37.6 | 76 | 63.8 | 52.4 | 84 | 74.7 | 70.7 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.3 | 65.7 | 54.2 | 46.5 | 61.1 | 54.6 | 38.1 | 61 | 44.6 | 33.5
2 | 3 | 11 | 67.5 | 53.1 | 42 | 74.5 | 65.5 | 44.7 | 81 | 73.5 | 61.4 | 91 | 83.2 | 77.5 | 91 | 87.8 | 83 | 96 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.6 | 80 | 87.5 | 78.3 | 73 | 73.1 | 65.5 | 54.2 | 71.2 | 60.8 | 48.3 | 68.7 | 53.4 | 43.4
2 | 3 | 12 | 73.3 | 60.3 | 51.7 | 80.3 | 75.3 | 55.4 | 88.9 | 80.8 | 67.5 | 94.7 | 88.3 | 83.7 | 95.7 | 92.3 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96.2 | 91.4 | 97.5 | 93 | 86.8 | 91.5 | 86 | 79.4 | 80.3 | 71.4 | 61.8 | 79.7 | 70.4 | 53.9 | 75.1 | 60.1 | 50.6
2 | 3 | 15 | 87.5 | 78.2 | 67.7 | 92.8 | 87.8 | 76 | 96.3 | 90.6 | 84.7 | 99.2 | 97.2 | 93.5 | 99.9 | 98.9 | 98 | 100 | 98.9 | 96.9 | 100 | 99.6 | 97.3 | 100 | 98.7 | 95.4 | 97.9 | 95.1 | 90.5 | 93.1 | 87.1 | 81.9 | 91.1 | 85 | 73.2 | 87.8 | 78.1 | 68.5
2 | 3 | 20 | 92.3 | 81.6 | 69.7 | 95.5 | 90.5 | 79.2 | 97.8 | 92.9 | 86.3 | 100 | 97.8 | 94.5 | 100 | 100 | 98.5 | 100 | 99.2 | 97 | 100 | 100 | 98.4 | 100 | 99.2 | 97.1 | 98.8 | 96.8 | 92 | 95 | 89.8 | 85.5 | 92.9 | 87.5 | 78.2 | 90.4 | 82 | 75
2 | 3 | 25 | 92.3 | 81.6 | 69.7 | 95.5 | 90.5 | 79.2 | 97.8 | 92.9 | 86.3 | 100 | 97.8 | 94.5 | 100 | 100 | 98.5 | 100 | 99.2 | 97 | 100 | 100 | 98.4 | 100 | 99.2 | 97.1 | 98.8 | 96.9 | 92 | 95 | 89.8 | 85.5 | 92.9 | 87.5 | 78.2 | 90.4 | 82 | 75
2 | 3.5 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 3.5 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 3.5 | 6 | 24.9 | 13.6 | 8.6 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 3.5 | 8 | 43.3 | 28.9 | 17.6 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.5 | 27 | 19.4
2 | 3.5 | 9 | 52.9 | 36.6 | 23.2 | 57.3 | 48.6 | 29.8 | 65.9 | 53.2 | 44.6 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.9 | 36.5 | 53.1 | 43.3 | 31 | 54 | 37.2 | 25.6
2 | 3.5 | 10 | 60.5 | 43.3 | 32.7 | 65.9 | 57.7 | 38 | 76 | 64.1 | 52.4 | 84 | 74.7 | 70.7 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.3 | 65.7 | 54.4 | 46.5 | 61.1 | 54.6 | 38.2 | 61 | 44.6 | 33.8
2 | 3.5 | 11 | 67.5 | 53.2 | 42.2 | 74.5 | 65.5 | 44.9 | 81 | 73.8 | 61.9 | 91 | 83.2 | 77.5 | 91 | 87.8 | 83 | 96.3 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.9 | 80 | 87.5 | 78.3 | 73.5 | 73.1 | 65.6 | 54.3 | 71.2 | 61.8 | 48.2 | 69 | 53.6 | 43.5
2 | 3.5 | 12 | 73.3 | 60.3 | 52.2 | 81.3 | 75.3 | 55.8 | 88.9 | 81.5 | 69 | 94.7 | 88.9 | 84.1 | 95.7 | 92.3 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96.2 | 91.4 | 97.5 | 93 | 86.8 | 91.6 | 86.3 | 80.3 | 80.3 | 71.4 | 62 | 79.8 | 71.8 | 56 | 75.9 | 60.3 | 51
2 | 3.5 | 15 | 89.1 | 81.3 | 73.7 | 93.9 | 90.1 | 79.7 | 96.9 | 91.8 | 87.4 | 99.4 | 97.8 | 94.4 | 100 | 99.3 | 98.5 | 100 | 99 | 97.2 | 100 | 100 | 98.3 | 100 | 98.9 | 96.4 | 98.9 | 95.6 | 92.1 | 93.9 | 89 | 83.9 | 93.7 | 86.3 | 77.5 | 89.9 | 80.8 | 70.5
2 | 3.5 | 20 | 95.9 | 91.1 | 84.1 | 98.6 | 94 | 88.4 | 99.8 | 97.3 | 93.5 | 100 | 100 | 97.1 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.5 | 95.9 | 98.8 | 95.6 | 92 | 97.1 | 93.2 | 88 | 96.3 | 90.7 | 84.2
2 | 3.5 | 25 | 96 | 91.1 | 84.1 | 98.8 | 94 | 88.4 | 99.8 | 97.3 | 93.5 | 100 | 100 | 97.1 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.5 | 95.9 | 98.8 | 95.6 | 92.1 | 97.2 | 93.2 | 88 | 96.3 | 90.7 | 84.2
2 | 4 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 4 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 4 | 6 | 24.9 | 13.6 | 8.6 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 4 | 8 | 43.3 | 28.9 | 17.6 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.5 | 27 | 19.4
2 | 4 | 9 | 52.9 | 36.6 | 23.2 | 57.3 | 48.6 | 29.8 | 65.9 | 53.2 | 44.6 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.9 | 36.5 | 53.1 | 43.3 | 31 | 54 | 37.2 | 25.6
2 | 4 | 10 | 60.7 | 43.3 | 32.9 | 65.9 | 57.7 | 38 | 76 | 64.1 | 52.4 | 84 | 74.7 | 70.7 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.3 | 65.7 | 54.4 | 46.5 | 61.1 | 54.6 | 38.2 | 61 | 44.6 | 33.9
2 | 4 | 11 | 67.5 | 53.2 | 42.2 | 74.5 | 65.5 | 44.9 | 81 | 73.8 | 61.9 | 91 | 83.2 | 77.5 | 91 | 87.8 | 83 | 96.3 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.9 | 80 | 87.5 | 78.3 | 73.5 | 73.1 | 65.6 | 54.5 | 71.2 | 61.8 | 48.2 | 69 | 53.6 | 43.5
2 | 4 | 12 | 73.4 | 60.3 | 52.2 | 81.5 | 75.3 | 55.9 | 88.9 | 81.5 | 69.4 | 94.7 | 88.9 | 84.1 | 95.7 | 92.3 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96.2 | 91.4 | 97.5 | 93 | 86.8 | 91.6 | 86.3 | 80.3 | 80.3 | 71.4 | 62.2 | 79.9 | 71.9 | 56.7 | 75.9 | 60.3 | 51
2 | 4 | 15 | 90.6 | 81.5 | 75 | 94.6 | 90.9 | 81.9 | 97.1 | 92.6 | 87.4 | 99.4 | 98.3 | 94.9 | 100 | 99.5 | 98.5 | 100 | 99.2 | 98 | 100 | 100 | 98.5 | 100 | 98.9 | 96.9 | 98.9 | 96 | 92.7 | 94.1 | 89.4 | 84.6 | 94.5 | 87.2 | 80.3 | 90.9 | 82.5 | 71.7
2 | 4 | 20 | 99 | 95.7 | 90.8 | 99.6 | 97.8 | 92.4 | 100 | 99.2 | 96.9 | 100 | 100 | 98.2 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.7 | 97.6 | 100 | 98 | 95.6 | 99.5 | 97.1 | 94.2 | 99.3 | 95.4 | 91.3
2 | 4 | 25 | 98.9 | 96 | 91.1 | 99.8 | 97.8 | 92.9 | 100 | 99.6 | 97.2 | 100 | 100 | 98.2 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.6 | 100 | 98.1 | 95.6 | 99.5 | 97.2 | 95 | 99.6 | 95.8 | 92.2
2 | 4.5 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 4.5 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 4.5 | 6 | 24.9 | 13.6 | 8.6 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 4.5 | 8 | 43.3 | 28.9 | 17.6 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.5 | 27 | 19.4
2 | 4.5 | 9 | 52.9 | 36.6 | 23.2 | 57.3 | 48.6 | 29.8 | 65.9 | 53.2 | 44.6 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.9 | 36.5 | 53.1 | 43.3 | 31 | 54 | 37.2 | 25.6
2 | 4.5 | 10 | 60.7 | 43.3 | 32.9 | 65.9 | 57.7 | 38 | 76 | 64.1 | 52.4 | 84 | 74.7 | 70.7 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.3 | 65.7 | 54.4 | 46.5 | 61.1 | 54.6 | 38.2 | 61 | 44.6 | 33.9
2 | 4.5 | 11 | 67.5 | 53.2 | 42.2 | 74.5 | 65.5 | 44.9 | 81 | 73.8 | 61.9 | 91 | 83.2 | 77.5 | 91 | 87.8 | 83 | 96.3 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.9 | 80 | 87.5 | 78.3 | 73.5 | 73.1 | 65.6 | 54.5 | 71.2 | 61.8 | 48.2 | 69 | 53.6 | 43.5
2 | 4.5 | 12 | 73.4 | 60.3 | 52.2 | 81.5 | 75.3 | 55.9 | 88.9 | 81.5 | 69.4 | 94.7 | 88.9 | 84.1 | 95.7 | 92.3 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96.2 | 91.4 | 97.5 | 93 | 86.8 | 91.6 | 86.3 | 80.3 | 80.3 | 71.4 | 62.2 | 79.9 | 71.9 | 56.7 | 75.9 | 60.3 | 51
2 | 4.5 | 15 | 91 | 81.7 | 75 | 94.6 | 90.9 | 81.9 | 97.1 | 93 | 87.8 | 99.4 | 98.6 | 95.3 | 100 | 99.5 | 98.5 | 100 | 99.2 | 98.1 | 100 | 100 | 98.5 | 100 | 98.9 | 96.9 | 98.9 | 96 | 92.8 | 94.2 | 89.4 | 84.9 | 94.6 | 87.8 | 80.7 | 91.3 | 83.2 | 71.9
2 | 4.5 | 20 | 99.8 | 97.3 | 93.4 | 100 | 98.5 | 94.7 | 100 | 100 | 98.4 | 100 | 100 | 99.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.4 | 100 | 99.1 | 97.1 | 100 | 98.5 | 96.5 | 100 | 98.1 | 94.7
2 | 4.5 | 25 | 100 | 98.3 | 95.2 | 100 | 99.1 | 95.7 | 100 | 100 | 98.8 | 100 | 100 | 99.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.2 | 100 | 99.6 | 98 | 100 | 99.2 | 97.7 | 100 | 99.1 | 96.3
2 | 5 | 2 | 1.5 | 0.7 | 0.2 | 2.8 | 0.9 | 0.4 | 2.7 | 1.3 | 0.4 | 3.9 | 2.6 | 1.6 | 4.2 | 2.8 | 1.1 | 5.9 | 3.5 | 2.1 | 5.9 | 3.5 | 1.7 | 5.4 | 2.7 | 1.6 | 3.7 | 2.2 | 1.4 | 2.2 | 0.9 | 0.5 | 1.9 | 0.8 | 0.1 | 2.3 | 1.1 | 0.3
2 | 5 | 4 | 8.8 | 3.9 | 2.5 | 13.7 | 8.3 | 3.9 | 14.1 | 8.5 | 5.6 | 18.7 | 13.5 | 10.5 | 18 | 14.8 | 9.3 | 23.8 | 19.7 | 12.6 | 23.2 | 16.5 | 11.4 | 24.3 | 16.1 | 11.6 | 17.5 | 12.5 | 9.1 | 11.3 | 7.1 | 4.3 | 9.3 | 5.6 | 3.8 | 12.2 | 5.4 | 2.7
2 | 5 | 6 | 24.9 | 13.6 | 8.6 | 28.2 | 20.4 | 11.1 | 30.1 | 22.8 | 16.9 | 41.6 | 31.8 | 26.7 | 39.7 | 33.5 | 27.6 | 50.6 | 41.9 | 31.7 | 49.1 | 39.4 | 31.1 | 47.8 | 38.2 | 31 | 38.9 | 31.5 | 21.8 | 26.8 | 19.8 | 12.4 | 22.5 | 16.9 | 11.2 | 27 | 15.5 | 8.4
2 | 5 | 8 | 43.3 | 28.9 | 17.6 | 48.8 | 39.1 | 23 | 52.2 | 41.9 | 34.9 | 64 | 55.8 | 47.7 | 63.9 | 58.5 | 49.9 | 76 | 66 | 56.3 | 75.3 | 66.8 | 57.6 | 70.8 | 63 | 51.7 | 63.2 | 53.2 | 44.4 | 45.5 | 34.3 | 27.7 | 43.3 | 31.9 | 21.8 | 43.5 | 27 | 19.4
2 | 5 | 9 | 52.9 | 36.6 | 23.2 | 57.3 | 48.6 | 29.8 | 65.9 | 53.2 | 44.6 | 73.8 | 65.6 | 60.4 | 76.6 | 67.6 | 61.8 | 86 | 76.9 | 68.5 | 83.1 | 77.8 | 69.9 | 82.3 | 73.5 | 63.3 | 73.1 | 63.9 | 55.1 | 54.8 | 44.9 | 36.5 | 53.1 | 43.3 | 31 | 54 | 37.2 | 25.6
2 | 5 | 10 | 60.7 | 43.3 | 32.9 | 65.9 | 57.7 | 38 | 76 | 64.1 | 52.4 | 84 | 74.7 | 70.7 | 85.5 | 78.2 | 73.3 | 91.9 | 86.4 | 78.6 | 90.8 | 86.3 | 80.3 | 90.6 | 83.3 | 72.8 | 80.3 | 69.9 | 64.3 | 65.7 | 54.4 | 46.5 | 61.1 | 54.6 | 38.2 | 61 | 44.6 | 33.9
2 | 5 | 11 | 67.5 | 53.2 | 42.2 | 74.5 | 65.5 | 44.9 | 81 | 73.8 | 61.9 | 91 | 83.2 | 77.5 | 91 | 87.8 | 83 | 96.3 | 91.3 | 85.6 | 96.2 | 92.7 | 87 | 94.4 | 87.9 | 80 | 87.5 | 78.3 | 73.5 | 73.1 | 65.6 | 54.5 | 71.2 | 61.8 | 48.2 | 69 | 53.6 | 43.5
2 | 5 | 12 | 73.4 | 60.3 | 52.2 | 81.5 | 75.3 | 55.9 | 88.9 | 81.5 | 69.4 | 94.7 | 88.9 | 84.1 | 95.7 | 92.3 | 89.4 | 98.6 | 94.9 | 92.1 | 98.5 | 96.2 | 91.4 | 97.5 | 93 | 86.8 | 91.6 | 86.3 | 80.3 | 80.3 | 71.4 | 62.2 | 79.9 | 71.9 | 56.7 | 75.9 | 60.3 | 51
2 | 5 | 15 | 91 | 81.7 | 75 | 94.6 | 90.9 | 81.9 | 97.1 | 93 | 87.9 | 99.4 | 98.6 | 95.3 | 100 | 99.5 | 98.5 | 100 | 99.2 | 98.1 | 100 | 100 | 98.5 | 100 | 98.9 | 96.9 | 98.9 | 96 | 92.8 | 94.2 | 89.4 | 85 | 94.6 | 87.8 | 80.7 | 91.3 | 83.6 | 71.9
2 | 5 | 20 | 100 | 97.8 | 94.9 | 100 | 99.3 | 95.7 | 100 | 100 | 98.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.3 | 100 | 99.6 | 98.2 | 100 | 98.8 | 97.1 | 100 | 98.9 | 95.2
2 | 5 | 25 | 100 | 99.7 | 98 | 100 | 100 | 97.9 | 100 | 100 | 99.6 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.4 | 100 | 100 | 98.6 | 100 | 100 | 98.2
4 | 0.25 | 2 | [12 empty] | 0.5 |  |  | 1 |  |  | 0.5 |  |  | 0.9
4 | 0.25 | 4 | [9 empty] | 1.5 |  |  | 2.9 | 0.4 |  | 4.3 | 1 |  | 2.5 | 0.9 |  | 4.2 | 1.5 |  | 0.8
4 | 0.25 | 6 | [9 empty] | 1.5 |  |  | 3.6 | 0.5 |  | 6.2 | 1 |  | 2.8 | 1.3 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 8 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 9 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 10 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 11 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 12 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 15 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 20 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.25 | 25 | [9 empty] | 1.5 |  |  | 3.6 | 0.8 |  | 6.4 | 1 |  | 2.8 | 1.7 |  | 4.6 | 2.2 |  | 1
4 | 0.5 | 2 |  |  |  | 0.4 |  |  | 0.5 |  |  | 1.8 | 0.4 |  | 2.4 | 0.5 |  | 3 | 1.3 |  | 3.5 | 1.2 | 0.4 | 2.3 | 0.9 | 0.1 | 1.5 | 0.6 |  | 0.5 | [5 empty] | 0.3
4 | 0.5 | 4 | 1.6 |  |  | 2.7 | 1.8 |  | 4.7 | 0.9 |  | 8.3 | 3.8 | 1.1 | 9.8 | 3.4 | 1.1 | 12.2 | 7.8 | 2.6 | 12.3 | 7.1 | 4.2 | 13.2 | 7.3 | 4.1 | 8.1 | 4.4 | 1.4 | 3.1 | 1.5 |  | 2 | 0.4 |  | 2.7 | 0.5
4 | 0.5 | 6 | 4 | 0.4 |  | 5.1 | 2.7 |  | 8.4 | 2.3 | 0.4 | 15.2 | 7.9 | 4.3 | 15.5 | 9.5 | 5 | 20.6 | 13.9 | 6 | 25.7 | 16.3 | 7.9 | 21.3 | 14.8 | 8.2 | 15.3 | 7.9 | 2.2 | 4.7 | 1.9 | 0.1 | 2.6 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 8 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 16.5 | 7.9 | 4.5 | 19.6 | 11.7 | 6 | 23.8 | 16.5 | 6.7 | 29.2 | 19.1 | 9.4 | 25 | 16 | 8.4 | 16.9 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 9 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 10 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 11 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 12 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 15 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 20 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.5 | 25 | 4 | 0.4 |  | 5.4 | 2.7 |  | 9.7 | 2.8 | 0.4 | 17 | 7.9 | 4.5 | 20 | 12 | 6 | 23.9 | 16.5 | 7 | 29.2 | 19.5 | 9.8 | 25.4 | 16 | 8.4 | 17.1 | 8.8 | 2.7 | 5.2 | 2 | 0.1 | 3.2 | 0.4 |  | 3.6 | 1.3
4 | 0.75 | 2 | 0.5 |  |  | 1 |  |  | 1.6 | 0.5 |  | 2.8 | 1.3 | 0.4 | 2.8 | 1.2 | 0.4 | 4 | 1.9 | 1 | 4.1 | 2 | 0.8 | 3.4 | 1.3 | 0.4 | 2.2 | 1.1 | 0.4 | 0.5 | 0.4 |  | 0.6 |  |  | 0.5
4 | 0.75 | 4 | 4 | 0.9 |  | 7.1 | 3.7 | 0.1 | 8.4 | 3.5 | 0.8 | 13.4 | 6.9 | 4.3 | 13.1 | 7.7 | 4.2 | 17.7 | 12.6 | 6 | 16.5 | 11.8 | 7.1 | 17.3 | 12.2 | 6.6 | 12.5 | 7.9 | 4.6 | 5.6 | 2.6 | 0.7 | 3.6 | 1.9 | 0.1 | 4.7 | 2 | 0.4
4 | 0.75 | 6 | 10.1 | 3.6 | 0.6 | 14 | 7.9 | 1.6 | 18.8 | 8.6 | 5.6 | 27.7 | 16 | 11.9 | 27.7 | 19.4 | 14.1 | 35.9 | 24.2 | 14.7 | 35.5 | 28.2 | 20.4 | 36 | 25.8 | 17.2 | 26.1 | 18.6 | 10.6 | 13.8 | 6.3 | 3.2 | 10 | 4.2 | 1.5 | 11.3 | 5.4 | 1.3
4 | 0.75 | 8 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 12 | 7.7 | 34.6 | 22.1 | 14.9 | 36 | 28.2 | 19.3 | 44.1 | 34.6 | 22.7 | 48.6 | 37 | 28.1 | 45.4 | 36.8 | 26.5 | 33.9 | 25.4 | 12.9 | 17.4 | 9.5 | 5.1 | 11.9 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 9 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 22.6 | 15.3 | 37.9 | 29.2 | 22 | 45.8 | 36.3 | 23.7 | 50.2 | 39.2 | 29.3 | 46.7 | 37.8 | 26.8 | 34.5 | 25.4 | 13.3 | 17.4 | 9.9 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 10 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.4 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.9 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 11 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.7 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.8 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 12 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.7 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.8 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 15 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.7 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.8 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 20 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.7 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.8 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 0.75 | 25 | 16.2 | 5.5 | 0.6 | 16.7 | 10.8 | 2.3 | 25.8 | 13 | 7.9 | 35.2 | 23.1 | 15.3 | 38.4 | 29.7 | 23.1 | 45.9 | 36.3 | 23.7 | 50.6 | 39.2 | 29.3 | 47.2 | 37.8 | 26.8 | 34.5 | 25.4 | 13.4 | 17.4 | 9.8 | 5.1 | 12.1 | 6.5 | 1.9 | 12.8 | 7.7 | 1.5
4 | 1 | 2 | 0.9 |  |  | 1.6 |  |  | 1.7 | 0.8 |  | 3 | 1.5 | 0.6 | 3.2 | 1.3 | 0.5 | 4.2 | 2.2 | 1.1 | 4.4 | 2.3 | 1 | 3.8 | 1.7 | 0.7 | 2.5 | 1.5 | 0.6 | 0.9 | 0.4 |  | 1 |  |  | 1.2 | 0.4
4 | 1 | 4 | 5.5 | 2 | 0.1 | 9.4 | 4.2 | 1.6 | 10.4 | 5.9 | 1.6 | 15.7 | 9.6 | 6.4 | 14.7 | 11.3 | 5.9 | 20.6 | 14.9 | 9.3 | 19.6 | 13.4 | 8.2 | 19.2 | 13.4 | 9 | 13.6 | 9.4 | 6.3 | 8 | 4 | 2.3 | 6.2 | 2.9 | 1 | 5.9 | 3 | 0.9
4 | 1 | 6 | 15.6 | 7.8 | 2 | 18.8 | 12.6 | 5 | 26 | 15.3 | 7.6 | 33.7 | 23.3 | 17.7 | 33.5 | 26.7 | 18.7 | 44 | 32.5 | 24.2 | 42.6 | 33.3 | 25.1 | 41.9 | 30.4 | 24.1 | 31.8 | 25.6 | 16.7 | 20.4 | 10.3 | 6.2 | 14.5 | 8.2 | 4.8 | 17.3 | 7.8 | 3.1
4 | 1 | 8 | 25.6 | 12.9 | 3.2 | 28.8 | 19 | 10.1 | 36 | 23.4 | 14 | 51.7 | 35.6 | 28.2 | 50.7 | 43.3 | 33.8 | 60.8 | 50.6 | 40.6 | 64.7 | 54 | 39.1 | 59.4 | 49.9 | 41 | 45.4 | 38.5 | 28.3 | 28.5 | 17.6 | 10.1 | 23.5 | 14.3 | 7.3 | 25.7 | 12.1 | 5.9
4 | 1 | 9 | 25.9 | 13.4 | 3.2 | 29.6 | 20.4 | 10.5 | 38.8 | 27.6 | 17.3 | 54 | 38.6 | 30.4 | 56.1 | 47.2 | 36.5 | 64.6 | 53.8 | 44.9 | 70.1 | 58.7 | 43.9 | 64.9 | 52.6 | 44 | 50.8 | 41.4 | 30.7 | 30.9 | 20.7 | 11.3 | 25.1 | 15.6 | 7.6 | 26.9 | 12.1 | 6
4 | 1 | 10 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.6 | 54.5 | 40.3 | 31.4 | 59.2 | 49.7 | 37.7 | 65.7 | 56 | 46.4 | 71.1 | 60.3 | 46 | 66.9 | 53.2 | 44.9 | 52.3 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1 | 11 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.8 | 54.8 | 40.3 | 31.7 | 59.4 | 50.3 | 38.2 | 65.8 | 56.1 | 46.5 | 71.4 | 60.1 | 46.6 | 67.2 | 53.8 | 45.2 | 52.5 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1 | 12 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.8 | 54.8 | 40.3 | 31.7 | 59.4 | 50.3 | 38.2 | 65.8 | 56.1 | 46.9 | 71.4 | 60.1 | 46.6 | 67.2 | 53.8 | 45.6 | 52.5 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1 | 15 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.8 | 54.8 | 40.3 | 31.7 | 59.4 | 50.5 | 38.2 | 65.8 | 56.4 | 46.9 | 71.4 | 60.1 | 46.6 | 67.2 | 53.8 | 45.6 | 52.5 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1 | 20 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.8 | 54.8 | 40.3 | 31.7 | 59.4 | 50.5 | 38.2 | 65.8 | 56.4 | 46.9 | 71.4 | 60.1 | 46.6 | 67.2 | 53.8 | 45.6 | 52.5 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1 | 25 | 25.9 | 14 | 3.5 | 29.7 | 20.4 | 10.5 | 39 | 28.2 | 17.8 | 54.8 | 40.3 | 31.7 | 59.4 | 50.5 | 38.2 | 65.8 | 56.4 | 46.9 | 71.4 | 60.1 | 46.6 | 67.2 | 53.8 | 45.6 | 52.5 | 42.5 | 31.5 | 31.3 | 21.9 | 11.3 | 25.3 | 15.6 | 7.6 | 26.9 | 12.4 | 6
4 | 1.25 | 2 | 0.9 |  |  | 1.9 | 0.4 |  | 1.7 | 0.8 |  | 3 | 1.8 | 0.9 | 3.2 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.3 | 1.7 | 0.7 | 2.5 | 1.5 | 0.6 | 1.4 | 0.5 |  | 1.3 | 0.4 |  | 1.3 | 0.4
4 | 1.25 | 4 | 6 | 2.8 | 1.1 | 10.8 | 6.4 | 2.4 | 12.3 | 6.7 | 2.9 | 16.3 | 10.3 | 7.8 | 15.9 | 11.8 | 7.3 | 20.9 | 16.5 | 10.3 | 20.1 | 15.1 | 8.6 | 21.3 | 14 | 9.1 | 15.4 | 10.3 | 6.7 | 9 | 4.8 | 2.7 | 7.1 | 3.9 | 1.7 | 7.6 | 3.5 | 1.3
4 | 1.25 | 6 | 20.2 | 8.6 | 5.1 | 22.6 | 15.3 | 6.3 | 26.9 | 18 | 11.1 | 36.1 | 26.3 | 20.8 | 36.4 | 28.5 | 22.3 | 47.7 | 39.2 | 27.8 | 44.9 | 36.8 | 27.2 | 43.3 | 32.7 | 27.2 | 34.4 | 27.8 | 17.7 | 23 | 14.5 | 9.1 | 18.5 | 11.7 | 6.9 | 20.4 | 10.3 | 5
4 | 1.25 | 8 | 34.2 | 19.8 | 9.1 | 34.7 | 26.8 | 12.3 | 45.5 | 32.1 | 21.6 | 57.8 | 45 | 38.1 | 57 | 51.3 | 42.7 | 69.8 | 58.8 | 46.5 | 69.9 | 61.3 | 46.8 | 66.7 | 56.7 | 46.9 | 54.2 | 45.4 | 34.9 | 34.1 | 24.6 | 17.9 | 31.5 | 21.7 | 11.8 | 33.7 | 17.9 | 10.9
4 | 1.25 | 9 | 35.8 | 22.8 | 10.1 | 40.5 | 29.2 | 15 | 49.9 | 40.1 | 26.3 | 63.7 | 50.4 | 43.2 | 66.5 | 59.3 | 50.7 | 76.6 | 66 | 55.4 | 76.4 | 70.7 | 55.3 | 73.7 | 65.9 | 54.5 | 62 | 51.3 | 39.2 | 41.5 | 31.7 | 21.1 | 36.9 | 25.7 | 13.9 | 36 | 21.2 | 13.9
4 | 1.25 | 10 | 38.3 | 23.3 | 11.3 | 43.8 | 32.3 | 15.7 | 52.5 | 42.3 | 27.5 | 68.7 | 55 | 45.3 | 72.9 | 62 | 55.4 | 79.8 | 71.3 | 58.9 | 82.1 | 75.4 | 58.7 | 76.9 | 68.5 | 58.4 | 65.4 | 55.1 | 42.2 | 44.8 | 33.2 | 22.2 | 38.3 | 27.1 | 14.5 | 37.2 | 22.2 | 15
4 | 1.25 | 11 | 38.2 | 23.8 | 11.3 | 45 | 32.3 | 16.5 | 53.7 | 43 | 27.5 | 70.9 | 56.5 | 45.7 | 73.9 | 64 | 57.7 | 80.8 | 73.5 | 60.2 | 84.1 | 76.6 | 60.2 | 78.3 | 70.7 | 59.9 | 65.8 | 57.4 | 42.7 | 45.1 | 34.9 | 22.7 | 38.7 | 28.3 | 14.9 | 37.1 | 22.7 | 15
4 | 1.25 | 12 | 38.2 | 23.8 | 11.3 | 45.1 | 32.3 | 16.5 | 53.8 | 43 | 27.6 | 70.9 | 56.8 | 45.7 | 73.9 | 64.5 | 58 | 80.8 | 73.5 | 60.9 | 84.1 | 77.3 | 60.7 | 78.5 | 70.7 | 60 | 66.5 | 57.4 | 42.7 | 45.1 | 34.9 | 22.7 | 38.7 | 28.3 | 15.1 | 37.1 | 22.7 | 15
4 | 1.25 | 15 | 38.5 | 23.8 | 11.3 | 45.1 | 32.3 | 16.5 | 53.8 | 43 | 27.6 | 70.9 | 56.8 | 45.7 | 74.3 | 64.5 | 58 | 80.8 | 73.5 | 60.9 | 84.1 | 77.3 | 61.2 | 78.5 | 70.7 | 60.1 | 66.5 | 57.4 | 42.7 | 45.1 | 34.9 | 22.7 | 38.8 | 28.3 | 15.1 | 37.1 | 22.7 | 15
4 | 1.25 | 20 | 38.4 | 23.8 | 11.3 | 45.1 | 32.3 | 16.5 | 53.8 | 43 | 27.6 | 70.9 | 56.8 | 45.7 | 74.3 | 64.5 | 58 | 80.8 | 73.5 | 60.9 | 84.1 | 77.3 | 61.2 | 78.5 | 70.7 | 60.1 | 66.5 | 57.5 | 42.7 | 45.1 | 34.9 | 22.7 | 38.8 | 28.3 | 15.1 | 37.1 | 22.7 | 15
4 | 1.25 | 25 | 38.4 | 23.8 | 11.3 | 45.1 | 32.3 | 16.5 | 53.8 | 43 | 27.6 | 70.9 | 56.8 | 45.7 | 74.3 | 64.5 | 58 | 80.8 | 73.5 | 60.9 | 84.1 | 77.3 | 61.2 | 78.5 | 70.7 | 60.1 | 66.5 | 57.5 | 42.7 | 45.1 | 34.9 | 22.7 | 38.8 | 28.3 | 15.1 | 37.1 | 22.7 | 15
4 | 1.5 | 2 | 0.9 | 0.4 |  | 2.2 | 0.4 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 1.7 | 0.7 | 2.5 | 1.5 | 0.8 | 1.4 | 0.5 | 0.4 | 1.3 | 0.4 |  | 1.4 | 0.4
4 | 1.5 | 4 | 7.5 | 3.4 | 1.3 | 11.5 | 6.4 | 2.8 | 12.4 | 7.3 | 3.5 | 16.4 | 11.4 | 8.6 | 16.3 | 12.6 | 7.7 | 21.3 | 18.1 | 10.7 | 20.1 | 15.1 | 8.8 | 21.4 | 14 | 9.7 | 16.2 | 10.6 | 7.3 | 9.3 | 5.4 | 3 | 8.2 | 4.6 | 2.5 | 9.6 | 4.3 | 1.8
4 | 1.5 | 6 | 22.1 | 10.6 | 5.8 | 24.8 | 16.1 | 7.8 | 27.9 | 18.8 | 12.8 | 36.4 | 27.8 | 23.5 | 36.7 | 29.8 | 23.5 | 48.8 | 39.7 | 28.6 | 46.9 | 37.4 | 27.7 | 44.2 | 35.6 | 28.6 | 36 | 28.8 | 18.9 | 24.6 | 17.6 | 10.8 | 19 | 13.9 | 7.9 | 22.2 | 13.2 | 5.9
4 | 1.5 | 8 | 37.4 | 23.1 | 12.7 | 40.6 | 31.3 | 15.9 | 47.5 | 35.8 | 25.3 | 61.5 | 48.1 | 42.1 | 60.5 | 55 | 46 | 72.6 | 62.1 | 51.4 | 73.3 | 64 | 53 | 68.1 | 60.6 | 48.9 | 57.8 | 48.9 | 39.7 | 41.2 | 29.6 | 21.6 | 35.8 | 26.5 | 17.5 | 37.5 | 22.2 | 13.8
4 | 1.5 | 9 | 40.9 | 30.5 | 15.4 | 48.6 | 39.2 | 20.1 | 58.8 | 44.9 | 33.6 | 69.5 | 57.4 | 51 | 72.3 | 63.8 | 55.3 | 81.3 | 72.1 | 62.6 | 79.5 | 73.9 | 63.9 | 78.5 | 68.3 | 58.7 | 66.1 | 57.8 | 47 | 47.3 | 36.8 | 27.5 | 44 | 33.1 | 20.9 | 42.2 | 26.5 | 17.1
4 | 1.5 | 10 | 45.4 | 32.3 | 18.5 | 56.2 | 42.7 | 25.4 | 63.4 | 50.7 | 40.4 | 75.3 | 63.2 | 54.8 | 80 | 71.4 | 64.4 | 86.1 | 80.8 | 70.3 | 87.7 | 81.9 | 70.9 | 84.1 | 75.4 | 65.4 | 72.6 | 62.9 | 52.6 | 55.2 | 42.7 | 32.8 | 50.5 | 36.4 | 23.9 | 46.9 | 30.5 | 21.1
4 | 1.5 | 11 | 47.6 | 34.1 | 20.3 | 57.7 | 46.4 | 26.1 | 70 | 52.6 | 42.1 | 80 | 67.6 | 58.3 | 82.9 | 76.2 | 68.4 | 88.7 | 82.8 | 72.7 | 91.5 | 85.6 | 74.7 | 86.7 | 78.2 | 69 | 75.6 | 66 | 55.6 | 58.6 | 46.8 | 35.4 | 52.8 | 36.9 | 25.6 | 48.9 | 32.5 | 22.5
4 | 1.5 | 12 | 47.8 | 34.1 | 21.1 | 58.5 | 47 | 26.5 | 69.9 | 53.1 | 42.4 | 81.2 | 70.3 | 59.8 | 83.1 | 78.1 | 69.6 | 89.2 | 83.1 | 74.2 | 92.8 | 85.9 | 74.9 | 87.1 | 79 | 69.7 | 75.9 | 67.4 | 56.2 | 59.5 | 47.7 | 35.9 | 53.7 | 37.1 | 26.4 | 48.9 | 32.7 | 23
4 | 1.5 | 15 | 47.8 | 34.1 | 21.2 | 58.5 | 47.6 | 26.5 | 69.9 | 53.1 | 42.6 | 81.7 | 70.3 | 59.8 | 83.4 | 78.1 | 69.6 | 89.2 | 83.6 | 74.1 | 92.8 | 86.4 | 74.9 | 87.3 | 79 | 69.9 | 75.9 | 67.4 | 56.2 | 59.5 | 48 | 35.9 | 54.4 | 37.1 | 26.4 | 49 | 33.1 | 23
4 | 1.5 | 20 | 48 | 34.1 | 21.2 | 58.5 | 47.6 | 26.5 | 69.9 | 53.1 | 42.6 | 81.7 | 70.3 | 59.8 | 83.4 | 78.1 | 69.6 | 89.2 | 83.6 | 74.1 | 92.8 | 86.4 | 74.9 | 87.3 | 79 | 69.9 | 75.9 | 67.4 | 56.2 | 59.5 | 48 | 35.9 | 54.4 | 37.1 | 26.4 | 49 | 33.1 | 23
4 | 1.5 | 25 | 48 | 34.1 | 21.2 | 58.5 | 47.6 | 26.5 | 69.9 | 53.1 | 42.6 | 81.7 | 70.3 | 59.8 | 83.4 | 78.1 | 69.6 | 89.2 | 83.6 | 74.1 | 92.8 | 86.4 | 74.9 | 87.3 | 79 | 69.9 | 75.9 | 67.4 | 56.2 | 59.5 | 48 | 35.9 | 54.4 | 37.1 | 26.4 | 49 | 33.1 | 23
4 | 1.75 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 1.75 | 4 | 7.8 | 3.4 | 1.6 | 11.8 | 6.8 | 3.2 | 12.5 | 7.3 | 4.1 | 16.4 | 11.8 | 8.6 | 16.3 | 13 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.4 | 3.4 | 8.3 | 4.7 | 2.5 | 9.7 | 4.6 | 2
4 | 1.75 | 6 | 22.9 | 11.8 | 6.6 | 25.8 | 17.9 | 8.8 | 28.1 | 20.3 | 15.4 | 38.8 | 29.2 | 24 | 37.2 | 30.8 | 24.2 | 48.8 | 39.7 | 29 | 46.9 | 37.6 | 28.3 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 24.8 | 17.6 | 11.2 | 20.8 | 14.9 | 8.7 | 22.6 | 13.7 | 6.2
4 | 1.75 | 8 | 39.5 | 25.7 | 14.6 | 43 | 34.1 | 19.4 | 48.5 | 38.3 | 30.4 | 63.3 | 50.6 | 44.9 | 61.8 | 55.9 | 46.7 | 73.5 | 63.2 | 53.9 | 73.4 | 64.5 | 54.2 | 68.1 | 61.3 | 49.7 | 60.4 | 50.4 | 41.7 | 43.4 | 31.3 | 23.9 | 38.5 | 29.3 | 18.2 | 38.2 | 24.7 | 16.5
4 | 1.75 | 9 | 47.1 | 33.1 | 19.1 | 54.2 | 42.1 | 24.7 | 62.2 | 46.8 | 38.9 | 71.3 | 60.7 | 55.5 | 73.2 | 65.7 | 57.9 | 83.3 | 75.3 | 65.6 | 80.9 | 75.5 | 66.6 | 80.3 | 70.2 | 60.3 | 70.3 | 60.3 | 51.4 | 50.9 | 39.4 | 31.8 | 46.3 | 36.3 | 25.9 | 44.6 | 30.6 | 20.4
4 | 1.75 | 10 | 51.4 | 37.9 | 25.4 | 62.4 | 50.6 | 29.4 | 71.7 | 56.3 | 44.1 | 81 | 70.1 | 62.3 | 82.9 | 73.3 | 68.2 | 89.4 | 83.5 | 75 | 89 | 83.5 | 75.1 | 87.5 | 76.5 | 68.1 | 75.2 | 66.8 | 57.6 | 58.1 | 46.9 | 38.3 | 54.8 | 42.5 | 30.3 | 53.3 | 36.6 | 25.7
4 | 1.75 | 11 | 55.9 | 42.1 | 31.8 | 67 | 56.6 | 31.7 | 76.3 | 64 | 49.1 | 86.7 | 75.6 | 67.5 | 87 | 81.2 | 75.5 | 92.6 | 87.4 | 80.1 | 95.1 | 88.4 | 80.4 | 89.7 | 83.1 | 74.6 | 80.9 | 72.5 | 62.4 | 67.1 | 54.3 | 44.3 | 60.2 | 47.4 | 33 | 57.1 | 40.1 | 29
4 | 1.75 | 12 | 58 | 43.1 | 34.6 | 69.1 | 58.3 | 33.9 | 78.8 | 64.7 | 51.7 | 87.1 | 78.3 | 68.6 | 89.9 | 84.7 | 79.3 | 94 | 88.9 | 82.6 | 95.8 | 89.5 | 82.1 | 92.6 | 83.9 | 77 | 82.1 | 74.4 | 65.3 | 72.1 | 57.5 | 47.8 | 62.1 | 49 | 35.1 | 59.7 | 40.9 | 29.1
4 | 1.75 | 15 | 58.3 | 44 | 35.1 | 69.4 | 59.8 | 35.2 | 79.9 | 66 | 54.8 | 87.5 | 78.6 | 69 | 90.6 | 86 | 81.1 | 94.5 | 89.4 | 83.6 | 96 | 90.2 | 82.3 | 93.1 | 84.4 | 78.7 | 83.2 | 75.8 | 65.6 | 73.5 | 59.1 | 49.2 | 63.6 | 49.4 | 36.6 | 60 | 42.1 | 29.5
4 | 1.75 | 20 | 58.3 | 44 | 35.1 | 69.4 | 59.8 | 35.2 | 79.9 | 66 | 54.8 | 87.5 | 78.6 | 69 | 90.6 | 86 | 81.1 | 94.5 | 89.4 | 83.6 | 96 | 90.2 | 82.3 | 93.1 | 84.4 | 78.7 | 83.2 | 75.8 | 65.6 | 73.5 | 59.1 | 49.2 | 63.6 | 49.4 | 36.6 | 60 | 42.1 | 29.5
4 | 1.75 | 25 | 58.3 | 44 | 35.1 | 69.4 | 59.8 | 35.2 | 79.9 | 66 | 54.8 | 87.5 | 78.6 | 69 | 90.6 | 86 | 81.1 | 94.5 | 89.4 | 83.6 | 96 | 90.2 | 82.3 | 93.1 | 84.4 | 78.7 | 83.2 | 75.8 | 65.6 | 73.5 | 59.1 | 49.2 | 63.6 | 49.4 | 36.6 | 60 | 42.1 | 29.5
4 | 2 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 2 | 4 | 7.9 | 3.4 | 1.6 | 12.1 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.8 | 3.4 | 8.3 | 4.7 | 2.6 | 10.6 | 4.6 | 2
4 | 2 | 6 | 23.1 | 12 | 6.7 | 25.9 | 18 | 8.9 | 28.4 | 20.3 | 15.4 | 39 | 29.2 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 24.8 | 18.3 | 11.2 | 20.8 | 15.7 | 9.2 | 23.5 | 13.7 | 6.8
4 | 2 | 8 | 40.1 | 26.1 | 15.6 | 44.9 | 34.6 | 20.2 | 50.2 | 39.2 | 31.6 | 63.3 | 53.1 | 45.1 | 62.1 | 56.5 | 47.6 | 73.6 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.3 | 49.9 | 61.1 | 50.8 | 42.4 | 44 | 31.9 | 25.3 | 40.2 | 29.4 | 19 | 39.1 | 25.1 | 17.5
4 | 2 | 9 | 50.9 | 34.7 | 20.6 | 54.9 | 45.5 | 25.9 | 63.4 | 48.9 | 41.2 | 71.3 | 62.8 | 57.4 | 74.6 | 65.7 | 58.4 | 84.4 | 76 | 66.2 | 81.4 | 76.6 | 68.1 | 80.9 | 71.2 | 60.5 | 71.4 | 61.7 | 53.6 | 52.7 | 40.1 | 33 | 48.5 | 38.3 | 26.7 | 47.1 | 33.1 | 22.5
4 | 2 | 10 | 55.7 | 41.8 | 27.3 | 63.3 | 54 | 31.8 | 73.7 | 59.9 | 46.9 | 82.1 | 72.2 | 64.9 | 83.4 | 75.9 | 71.3 | 90.3 | 84.6 | 77.3 | 89.7 | 84.5 | 78 | 88.5 | 78.9 | 70 | 78.1 | 68.2 | 59.6 | 59.1 | 50.5 | 42.3 | 57.9 | 46.1 | 33.6 | 56.8 | 39.4 | 29.1
4 | 2 | 11 | 60 | 47.2 | 35.6 | 71.2 | 61.3 | 37.1 | 78.1 | 66.9 | 54.6 | 88.9 | 78.5 | 70.9 | 89.6 | 83.7 | 79.6 | 94.3 | 90 | 83.2 | 95.6 | 90.5 | 82.9 | 92.7 | 84.5 | 76.6 | 83.8 | 75.1 | 66.6 | 69 | 58.2 | 48.7 | 64.3 | 53.9 | 40.3 | 61.4 | 44.8 | 34.5
4 | 2 | 12 | 63.9 | 51.5 | 41 | 74.4 | 66.4 | 41.9 | 83.3 | 72.2 | 57.8 | 90.9 | 83.6 | 74.9 | 92.5 | 88.7 | 84.6 | 95.7 | 91.9 | 87.7 | 97.7 | 94.1 | 85.1 | 96.4 | 87.2 | 81.4 | 86.1 | 79 | 70.7 | 74.4 | 63.4 | 53.9 | 68.8 | 58.2 | 42.6 | 65.5 | 46.9 | 36.6
4 | 2 | 15 | 67.4 | 53.5 | 44.2 | 79.9 | 70.3 | 44.6 | 84.6 | 74.9 | 62.7 | 92.7 | 86.1 | 76.9 | 94.3 | 90.3 | 87.3 | 96.9 | 92.8 | 89.3 | 98.9 | 95.8 | 89.2 | 96.9 | 87.9 | 83.7 | 88.2 | 82.6 | 73.7 | 77.6 | 68.3 | 60.5 | 74.9 | 59.6 | 46.1 | 68.8 | 50.9 | 38.1
4 | 2 | 20 | 67.8 | 53.5 | 44.6 | 79.9 | 70.3 | 44.6 | 84.6 | 74.9 | 62.7 | 92.8 | 86.1 | 76.9 | 94.3 | 90.3 | 87.4 | 96.9 | 92.8 | 89.3 | 98.9 | 95.8 | 89.2 | 96.9 | 87.9 | 83.8 | 88.2 | 82.6 | 73.7 | 77.8 | 68.3 | 60.6 | 74.9 | 59.6 | 46.1 | 68.8 | 50.9 | 38.1
4 | 2 | 25 | 67.8 | 53.5 | 44.6 | 79.9 | 70.3 | 44.6 | 84.6 | 74.9 | 62.7 | 92.8 | 86.1 | 76.9 | 94.3 | 90.3 | 87.4 | 96.9 | 92.8 | 89.3 | 98.9 | 95.8 | 89.2 | 96.9 | 87.9 | 83.8 | 88.2 | 82.6 | 73.7 | 77.8 | 68.3 | 60.6 | 74.9 | 59.6 | 46.1 | 68.8 | 50.9 | 38.1
4 | 2.25 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 2.25 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 4.7 | 2.2
4 | 2.25 | 6 | 23.5 | 12 | 7.3 | 26.3 | 18.6 | 9.5 | 28.4 | 20.4 | 15.4 | 39 | 29.3 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 9.7 | 24.3 | 13.7 | 7
4 | 2.25 | 8 | 40.5 | 26.5 | 15.8 | 46.4 | 35.2 | 21 | 50.2 | 39.7 | 31.8 | 63.3 | 53.6 | 45.1 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.3 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.1 | 40.9 | 30 | 19.3 | 40.2 | 25.7 | 17.8
4 | 2.25 | 9 | 50.9 | 34.7 | 21.5 | 55.5 | 46.1 | 26.7 | 63.3 | 50.1 | 41.2 | 71.3 | 63.5 | 57.7 | 74.9 | 66.3 | 58.7 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.2 | 60.5 | 71.8 | 61.7 | 53.6 | 52.6 | 40.6 | 33.9 | 50.2 | 39.3 | 28.3 | 49.5 | 34.1 | 22.5
4 | 2.25 | 10 | 56.9 | 41.9 | 28.6 | 64.4 | 55.2 | 33.3 | 74.2 | 61 | 48.1 | 82.2 | 72.6 | 67 | 83.7 | 76.3 | 71.3 | 90.9 | 84.7 | 77.8 | 89.7 | 84.8 | 78.8 | 89.2 | 81.9 | 70.5 | 78.1 | 68.6 | 62.3 | 60.8 | 52 | 43.5 | 58.3 | 48.6 | 35.1 | 57.4 | 41.5 | 29.5
4 | 2.25 | 11 | 64.5 | 48.9 | 37.9 | 72.7 | 62.2 | 40.3 | 78.8 | 69 | 57.3 | 89.3 | 79.4 | 74.3 | 90 | 84.7 | 81 | 95.1 | 90.6 | 84.4 | 95.7 | 90.5 | 84.4 | 93.5 | 86 | 77.9 | 85.7 | 76 | 68.9 | 71 | 61.2 | 50.6 | 67.6 | 56.8 | 42.2 | 63.3 | 47.3 | 38.9
4 | 2.25 | 12 | 68.6 | 55.5 | 45.1 | 77.6 | 70.1 | 48.7 | 84.7 | 75.5 | 61.3 | 93.3 | 86.3 | 78.6 | 94 | 90.6 | 86.7 | 97.6 | 93.2 | 89.8 | 97.9 | 94.9 | 88.3 | 97.4 | 90.1 | 84.5 | 89.4 | 83.2 | 74.4 | 76.5 | 67.2 | 57.3 | 73.9 | 63.2 | 47.1 | 69.7 | 52.7 | 45.3
4 | 2.25 | 15 | 75.9 | 60.8 | 50.7 | 84.5 | 75.1 | 55.1 | 90.1 | 80.8 | 68.6 | 96.4 | 91.7 | 83.5 | 96.5 | 95 | 91.8 | 99.3 | 95.4 | 93.1 | 99.9 | 97.4 | 94 | 98.2 | 93.1 | 88.1 | 93.3 | 87.8 | 80.3 | 83.6 | 75.8 | 69.6 | 81.4 | 68.5 | 53.7 | 76.5 | 62.2 | 49.3
4 | 2.25 | 20 | 75.9 | 61.2 | 50.7 | 84.9 | 75.7 | 55.1 | 90.3 | 81.2 | 68.8 | 96.4 | 91.7 | 83.5 | 96.6 | 95 | 91.8 | 99.3 | 95.4 | 93.1 | 99.9 | 97.4 | 94 | 98.2 | 93.1 | 88.4 | 93.3 | 88.2 | 80.4 | 83.8 | 76.5 | 69.7 | 81.8 | 68.5 | 55.1 | 76.5 | 62.8 | 50.1
4 | 2.25 | 25 | 75.9 | 61.2 | 50.7 | 84.9 | 75.7 | 55.1 | 90.3 | 81.2 | 68.8 | 96.4 | 91.7 | 83.5 | 96.6 | 95 | 91.8 | 99.3 | 95.4 | 93.1 | 99.9 | 97.4 | 94 | 98.2 | 93.1 | 88.4 | 93.3 | 88.2 | 80.4 | 83.8 | 76.5 | 69.7 | 81.8 | 68.5 | 55.1 | 76.5 | 62.8 | 50.1
4 | 2.75 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 2.75 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 2.75 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 2.75 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 20 | 41.5 | 26.2 | 18.1
4 | 2.75 | 9 | 50.9 | 34.8 | 21.7 | 55.6 | 46.7 | 27.4 | 63.3 | 50.5 | 41.6 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.2 | 34.5 | 50.4 | 41.3 | 29.3 | 51.4 | 34.7 | 23.7
4 | 2.75 | 10 | 58.4 | 41.9 | 29.3 | 64.4 | 56 | 36 | 74.6 | 62.1 | 49.8 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.9 | 50.3 | 35.9 | 59.2 | 42.1 | 31
4 | 2.75 | 11 | 65.7 | 51.2 | 38.5 | 73.3 | 63.4 | 42.3 | 79.3 | 71.4 | 58.6 | 89.5 | 82.5 | 75.7 | 90.5 | 86.6 | 82.1 | 95.3 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 86.6 | 78.5 | 86.6 | 76.3 | 71.3 | 71.8 | 62.6 | 52.6 | 69.2 | 59.9 | 45.6 | 66.1 | 51.3 | 40.4
4 | 2.75 | 12 | 71.8 | 58.6 | 49.5 | 79 | 73.7 | 52.2 | 86.7 | 78.2 | 65 | 93.9 | 86.8 | 82.1 | 95 | 91.4 | 87.8 | 98.3 | 93.6 | 91.4 | 98.2 | 95.7 | 90 | 97.4 | 91.8 | 85.7 | 90.9 | 84.7 | 76.3 | 78.5 | 70 | 59.3 | 77.6 | 67.1 | 50.2 | 72.6 | 57.3 | 49.2
4 | 2.75 | 15 | 85.2 | 73.1 | 62.7 | 90.2 | 83.9 | 70 | 94.3 | 87.8 | 79.2 | 98.8 | 95.4 | 91.1 | 99.6 | 98.4 | 96.3 | 100 | 98.2 | 96.3 | 100 | 98.8 | 96.4 | 100 | 97.4 | 94 | 96.5 | 93.5 | 88.1 | 91.3 | 83.9 | 78.9 | 88.7 | 81.4 | 67.7 | 85.5 | 73 | 63
4 | 2.75 | 20 | 88.9 | 74.6 | 64.3 | 92.3 | 85.8 | 72.1 | 95.8 | 88.7 | 80 | 99 | 96 | 91.8 | 100 | 98.9 | 96.7 | 100 | 98.1 | 96.3 | 100 | 99.1 | 96.4 | 100 | 98 | 95 | 97.4 | 95.3 | 89.7 | 91.7 | 85.9 | 80 | 90.2 | 82.2 | 70.9 | 85.8 | 74.6 | 66.8
4 | 2.75 | 25 | 88.9 | 74.6 | 64.3 | 92.3 | 85.8 | 72.1 | 95.8 | 88.7 | 80 | 99 | 96 | 91.8 | 100 | 98.9 | 96.7 | 100 | 98.1 | 96.3 | 100 | 99.1 | 96.4 | 100 | 98 | 95 | 97.4 | 95.3 | 89.7 | 91.7 | 85.9 | 80 | 90.2 | 82.2 | 70.9 | 85.8 | 74.6 | 66.8
4 | 3 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 3 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 3 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 3 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 19.9 | 41.5 | 26.2 | 18.1
4 | 3 | 9 | 51 | 34.8 | 21.7 | 55.6 | 47.3 | 27.4 | 63.3 | 50.5 | 41.6 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.5 | 34.5 | 50.4 | 41.3 | 29.3 | 51.4 | 35.2 | 23.7
4 | 3 | 10 | 58.6 | 41.9 | 29.3 | 64.4 | 56.5 | 36.2 | 74.6 | 62.1 | 50 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.8 | 51.9 | 36.2 | 59.6 | 42.9 | 31
4 | 3 | 11 | 65.8 | 51.2 | 38.8 | 73.3 | 63.4 | 42.5 | 79.8 | 71.4 | 59 | 89.9 | 82.5 | 76 | 90.5 | 86.6 | 82.1 | 95.3 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 87 | 78.5 | 86.6 | 76.3 | 71.3 | 71.8 | 62.9 | 52.6 | 69.2 | 59.9 | 45.9 | 66.8 | 51.3 | 40.8
4 | 3 | 12 | 72.5 | 60.1 | 50.4 | 79 | 73.7 | 53.1 | 87.8 | 79.3 | 66.1 | 94.3 | 87.1 | 83.1 | 95.4 | 91.4 | 88.1 | 98.3 | 93.6 | 91.5 | 98.2 | 96.1 | 90.4 | 97.4 | 92.1 | 85.7 | 90.9 | 84.7 | 78.3 | 78.5 | 70.6 | 60 | 77.8 | 68.8 | 52 | 73.5 | 58.1 | 49.2
4 | 3 | 15 | 87 | 76.2 | 66.4 | 91.8 | 87.2 | 74.6 | 96.1 | 89.9 | 83.3 | 99 | 96.5 | 92.6 | 99.9 | 98.8 | 97.8 | 100 | 98.6 | 96.7 | 100 | 99.3 | 96.9 | 100 | 98.3 | 95.3 | 97.7 | 94.4 | 90.1 | 92.8 | 86.2 | 81.2 | 90.5 | 84.2 | 72 | 86.9 | 76.7 | 66.6
4 | 3 | 20 | 91.6 | 80.6 | 69 | 95.1 | 90.2 | 78.2 | 97.5 | 92.9 | 85.4 | 100 | 97.5 | 94.1 | 100 | 100 | 98.4 | 100 | 99 | 96.8 | 100 | 100 | 98.2 | 100 | 99.1 | 96.8 | 98.6 | 96.5 | 91.3 | 94.4 | 89.5 | 84.5 | 92.6 | 86.9 | 76.8 | 89.9 | 81 | 73.6
4 | 3 | 25 | 91.6 | 80.6 | 69 | 95.1 | 90.2 | 78.2 | 97.5 | 92.9 | 85.4 | 100 | 97.5 | 94.1 | 100 | 100 | 98.4 | 100 | 99 | 96.8 | 100 | 100 | 98.2 | 100 | 99.1 | 96.8 | 98.6 | 96.5 | 91.3 | 94.4 | 89.5 | 84.5 | 92.6 | 86.9 | 76.8 | 89.9 | 81 | 73.6
4 | 3.5 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 3.5 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 3.5 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 3.5 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 19.9 | 41.5 | 26.2 | 18.1
4 | 3.5 | 9 | 51 | 34.8 | 21.7 | 55.6 | 47.3 | 27.4 | 63.3 | 50.5 | 41.7 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.5 | 34.5 | 50.4 | 41.3 | 29.4 | 51.4 | 35.2 | 23.8
4 | 3.5 | 10 | 58.9 | 41.9 | 29.9 | 64.4 | 56.5 | 36.4 | 74.6 | 62.1 | 50.5 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.8 | 51.9 | 36.3 | 59.6 | 42.9 | 31.2
4 | 3.5 | 11 | 65.8 | 51.2 | 39.2 | 73.3 | 63.4 | 42.6 | 79.8 | 71.4 | 59.5 | 89.9 | 82.5 | 76.3 | 90.5 | 86.6 | 82.1 | 95.7 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 87 | 78.5 | 86.6 | 76.3 | 71.4 | 71.8 | 62.9 | 53 | 69.2 | 59.9 | 45.9 | 67.2 | 51.9 | 41
4 | 3.5 | 12 | 72.5 | 60.1 | 50.8 | 79.8 | 73.7 | 53.7 | 87.8 | 79.7 | 67.5 | 94.3 | 87.9 | 83.5 | 95.4 | 91.4 | 88.1 | 98.3 | 94.2 | 91.5 | 98.2 | 96.1 | 90.4 | 97.4 | 92.1 | 85.7 | 91.1 | 85.3 | 79.6 | 78.5 | 70.6 | 60 | 77.9 | 69.3 | 53.8 | 74.4 | 59.1 | 49.4
4 | 3.5 | 15 | 88.4 | 79.8 | 72 | 93.3 | 89.3 | 78.4 | 96.4 | 91.3 | 85.8 | 99.4 | 97.8 | 94 | 100 | 99.2 | 98.2 | 100 | 98.8 | 97.1 | 100 | 100 | 98 | 100 | 98.5 | 96.2 | 98.7 | 95 | 91.6 | 93.4 | 87.9 | 82.9 | 93.1 | 85.3 | 76.2 | 88.5 | 78.9 | 69.1
4 | 3.5 | 20 | 95.4 | 90.3 | 82.7 | 98.5 | 93.9 | 87.5 | 99.8 | 97 | 92.9 | 100 | 100 | 96.8 | 100 | 100 | 100 | 100 | 100 | 98.4 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.2 | 95.5 | 98.6 | 94.9 | 91.2 | 97 | 92.6 | 87.1 | 96.1 | 90.1 | 83.2
4 | 3.5 | 25 | 95.5 | 90.7 | 82.7 | 98.8 | 93.9 | 87.5 | 99.8 | 97 | 92.9 | 100 | 100 | 96.8 | 100 | 100 | 100 | 100 | 100 | 98.4 | 100 | 100 | 99.5 | 100 | 100 | 98.6 | 100 | 98.2 | 95.5 | 98.6 | 94.9 | 91.2 | 97.2 | 92.6 | 87.1 | 96.1 | 90.1 | 83.5
4 | 4 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 4 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 4 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 4 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 19.9 | 41.5 | 26.2 | 18.1
4 | 4 | 9 | 51 | 34.8 | 21.7 | 55.6 | 47.3 | 27.4 | 63.3 | 50.5 | 41.7 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.5 | 34.5 | 50.4 | 41.3 | 29.4 | 51.4 | 35.2 | 23.8
4 | 4 | 10 | 58.9 | 41.9 | 29.9 | 64.4 | 56.5 | 36.4 | 74.6 | 62.1 | 50.5 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.8 | 51.9 | 36.3 | 59.6 | 42.9 | 31.2
4 | 4 | 11 | 66 | 51.2 | 39.2 | 73.3 | 63.4 | 42.6 | 79.8 | 71.4 | 59.6 | 89.9 | 82.5 | 76.3 | 90.5 | 86.6 | 82.1 | 95.7 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 87 | 78.5 | 86.6 | 76.3 | 71.4 | 71.8 | 62.9 | 53 | 69.2 | 59.9 | 45.9 | 67.2 | 51.9 | 41
4 | 4 | 12 | 72.7 | 60.1 | 50.8 | 79.8 | 73.7 | 53.9 | 87.8 | 79.7 | 67.5 | 94.3 | 87.9 | 83.5 | 95.4 | 91.4 | 88.1 | 98.3 | 94.2 | 91.5 | 98.2 | 96.1 | 90.4 | 97.4 | 92.1 | 85.7 | 91.1 | 85.3 | 79.6 | 78.5 | 70.6 | 60.3 | 78.1 | 69.3 | 54.3 | 74.4 | 59.1 | 49.4
4 | 4 | 15 | 89.5 | 80.4 | 73.2 | 93.9 | 89.9 | 79.7 | 96.4 | 92.2 | 86.4 | 99.4 | 98.1 | 94.4 | 100 | 99.3 | 98.2 | 100 | 98.9 | 97.6 | 100 | 100 | 98.2 | 100 | 98.7 | 96.5 | 98.7 | 95.6 | 92.2 | 93.5 | 88.7 | 84 | 93.9 | 86.1 | 78 | 90 | 81.2 | 70.1
4 | 4 | 20 | 98.5 | 95.4 | 90 | 99.4 | 97.5 | 92.2 | 100 | 99.2 | 96.5 | 100 | 100 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.7 | 97.4 | 100 | 97.8 | 95.1 | 99.3 | 96.8 | 93.5 | 99.1 | 94.9 | 90.4
4 | 4 | 25 | 98.5 | 95.7 | 90.2 | 99.8 | 97.3 | 92.5 | 100 | 99.3 | 96.8 | 100 | 100 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.4 | 100 | 98.1 | 95.2 | 99.3 | 96.9 | 94.2 | 99.3 | 95.2 | 91.4
4 | 4.5 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 4.5 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 4.5 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 4.5 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 19.9 | 41.5 | 26.2 | 18.1
4 | 4.5 | 9 | 51 | 34.8 | 21.7 | 55.6 | 47.3 | 27.4 | 63.3 | 50.5 | 41.7 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.5 | 34.5 | 50.4 | 41.3 | 29.4 | 51.4 | 35.2 | 23.8
4 | 4.5 | 10 | 58.9 | 41.9 | 29.9 | 64.4 | 56.5 | 36.4 | 74.6 | 62.1 | 50.5 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.8 | 51.9 | 36.3 | 59.6 | 42.9 | 31.2
4 | 4.5 | 11 | 66 | 51.2 | 39.2 | 73.3 | 63.4 | 42.6 | 79.8 | 71.4 | 59.6 | 89.9 | 82.5 | 76.3 | 90.5 | 86.6 | 82.1 | 95.7 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 87 | 78.5 | 86.6 | 76.3 | 71.4 | 71.8 | 62.9 | 53 | 69.2 | 59.9 | 45.9 | 67.2 | 51.9 | 41
4 | 4.5 | 12 | 72.7 | 60.1 | 50.8 | 79.8 | 73.7 | 53.9 | 87.8 | 79.7 | 67.5 | 94.3 | 87.9 | 83.5 | 95.4 | 91.4 | 88.1 | 98.3 | 94.2 | 91.5 | 98.2 | 96.1 | 90.4 | 97.4 | 92.1 | 85.7 | 91.1 | 85.3 | 79.6 | 78.5 | 70.6 | 60.3 | 78.1 | 69.3 | 54.3 | 74.4 | 59.1 | 49.4
4 | 4.5 | 15 | 89.9 | 80.4 | 73.2 | 93.9 | 89.9 | 79.7 | 96.4 | 92.2 | 86.8 | 99.4 | 98.3 | 94.8 | 100 | 99.3 | 98.2 | 100 | 98.9 | 97.8 | 100 | 100 | 98.2 | 100 | 98.7 | 96.5 | 98.7 | 95.7 | 92.2 | 93.7 | 88.7 | 84.2 | 94 | 86.7 | 78.6 | 90.5 | 82 | 70.5
4 | 4.5 | 20 | 99.8 | 97.3 | 93 | 100 | 98.5 | 94.4 | 100 | 100 | 98.3 | 100 | 100 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.4 | 100 | 98.8 | 96.5 | 100 | 98.3 | 96 | 100 | 97.6 | 93.9
4 | 4.5 | 25 | 100 | 98 | 94.8 | 100 | 99 | 95.1 | 100 | 100 | 98.8 | 100 | 100 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.2 | 100 | 99.6 | 97.8 | 100 | 98.9 | 97.1 | 100 | 98.8 | 95.7
4 | 5 | 2 | 0.9 | 0.4 |  | 2.2 | 0.6 |  | 1.9 | 0.9 |  | 3.1 | 1.9 | 1 | 3.3 | 1.9 | 0.9 | 4.4 | 2.5 | 1.3 | 4.4 | 2.3 | 1 | 4.6 | 2.2 | 0.7 | 2.8 | 1.5 | 0.9 | 1.7 | 0.5 | 0.4 | 1.4 | 0.4 |  | 1.5 | 0.4
4 | 5 | 4 | 7.9 | 3.4 | 1.7 | 12.2 | 6.8 | 3.2 | 12.5 | 7.3 | 4.3 | 16.4 | 11.8 | 8.6 | 16.3 | 13.2 | 7.9 | 21.4 | 18.1 | 10.7 | 20.1 | 15.1 | 8.9 | 21.7 | 14 | 9.7 | 16.2 | 10.8 | 7.6 | 9.7 | 5.9 | 3.4 | 8.3 | 4.7 | 2.6 | 11.1 | 5 | 2.2
4 | 5 | 6 | 23.6 | 12.5 | 7.3 | 26.2 | 18.6 | 9.5 | 28.4 | 21 | 15.4 | 39 | 29.9 | 24.5 | 37.2 | 31.2 | 25.2 | 48.8 | 40.3 | 29 | 46.9 | 37.6 | 28.8 | 44.4 | 35.6 | 28.7 | 36.5 | 29.3 | 19.9 | 25 | 19.4 | 11.3 | 20.8 | 15.7 | 10.5 | 25.2 | 13.7 | 7
4 | 5 | 8 | 41.1 | 26.5 | 15.8 | 46.4 | 36.9 | 21.5 | 50.2 | 40.7 | 31.8 | 63.3 | 54.2 | 45.5 | 62.5 | 56.5 | 47.6 | 73.8 | 63.8 | 53.9 | 73.8 | 64.5 | 54.2 | 68.1 | 61.6 | 49.9 | 61.1 | 50.8 | 42.4 | 44.4 | 31.9 | 26.3 | 41 | 30 | 19.9 | 41.5 | 26.2 | 18.1
4 | 5 | 9 | 51 | 34.8 | 21.7 | 55.6 | 47.3 | 27.4 | 63.3 | 50.5 | 41.7 | 72.6 | 63.8 | 58.3 | 74.9 | 66.3 | 59 | 84.8 | 76 | 66.2 | 81.4 | 76.6 | 68.2 | 80.9 | 71.8 | 60.5 | 71.8 | 61.8 | 53.6 | 53.4 | 42.5 | 34.5 | 50.4 | 41.3 | 29.4 | 51.4 | 35.2 | 23.8
4 | 5 | 10 | 58.9 | 41.9 | 29.9 | 64.4 | 56.5 | 36.4 | 74.6 | 62.1 | 50.5 | 82.5 | 73.2 | 68.8 | 84.5 | 76.3 | 71.4 | 91 | 85.1 | 77.8 | 89.7 | 85.2 | 78.9 | 89.6 | 82.7 | 70.5 | 78.7 | 69.2 | 62.9 | 63.3 | 52.7 | 43.8 | 58.8 | 51.9 | 36.3 | 59.6 | 42.9 | 31.2
4 | 5 | 11 | 66 | 51.2 | 39.2 | 73.3 | 63.4 | 42.6 | 79.8 | 71.4 | 59.6 | 89.9 | 82.5 | 76.3 | 90.5 | 86.6 | 82.1 | 95.7 | 90.7 | 84.7 | 95.8 | 91.9 | 85.2 | 93.5 | 87 | 78.5 | 86.6 | 76.3 | 71.4 | 71.8 | 62.9 | 53 | 69.2 | 59.9 | 45.9 | 67.2 | 51.9 | 41
4 | 5 | 12 | 72.7 | 60.1 | 50.8 | 79.8 | 73.7 | 53.9 | 87.8 | 79.7 | 67.5 | 94.3 | 87.9 | 83.5 | 95.4 | 91.4 | 88.1 | 98.3 | 94.2 | 91.5 | 98.2 | 96.1 | 90.4 | 97.4 | 92.1 | 85.7 | 91.1 | 85.3 | 79.6 | 78.5 | 70.6 | 60.3 | 78.1 | 69.3 | 54.3 | 74.4 | 59.1 | 49.4
4 | 5 | 15 | 89.9 | 80.4 | 73.2 | 93.9 | 90.3 | 79.7 | 96.4 | 92.2 | 86.8 | 99.4 | 98.3 | 94.8 | 100 | 99.3 | 98.2 | 100 | 98.9 | 97.8 | 100 | 100 | 98.2 | 100 | 98.7 | 96.5 | 98.7 | 95.7 | 92.2 | 93.7 | 88.7 | 84.6 | 94 | 86.9 | 78.6 | 90.5 | 82 | 70.5
4 | 5 | 20 | 100 | 97.4 | 94.1 | 100 | 99 | 95.4 | 100 | 100 | 98.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.2 | 100 | 99.5 | 97.7 | 100 | 98.8 | 96.8 | 100 | 98.4 | 94.4
4 | 5 | 25 | 100 | 99.5 | 97.6 | 100 | 100 | 97.3 | 100 | 100 | 99.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.1 | 100 | 100 | 98.3 | 100 | 100 | 98.1
6 | 0.25 | 2 | [12 empty] | 0.8 |  |  | 0.8 | [5 empty] | 0.7
6 | 0.25 | 4 | [9 empty] | 1.2 |  |  | 2.8 |  |  | 3.2 | 0.8 |  | 2.3 | 0.7 |  | 3.7 | 0.7 |  | 0.7
6 | 0.25 | 6 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 5.8 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 8 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 9 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 10 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 11 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 12 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 15 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 20 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.25 | 25 | [9 empty] | 1.5 |  |  | 3.3 | 0.7 |  | 6.1 | 0.7 |  | 3 | 1.3 |  | 4.9 | 1.5 |  | 0.7
6 | 0.5 | 2 | [6 empty] | 0.5 |  |  | 1.5 |  |  | 1.5 | 0.7 |  | 2.8 | 0.7 |  | 2.2 | 0.7 |  | 2.2 | 0.7 |  | 1.4
6 | 0.5 | 4 | 0.7 |  |  | 2.5 | 1.6 |  | 4.2 | 0.8 |  | 7.1 | 3.8 | 1 | 8.8 | 3.5 | 0.7 | 11 | 6.9 | 2.2 | 11.4 | 6 | 3.8 | 12.2 | 6.9 | 3.9 | 7.1 | 3.8 | 1.4 | 2.8 | 1.3 |  | 1.5 |  |  | 2.2 | 0.5
6 | 0.5 | 6 | 4 |  |  | 5.3 | 2.4 |  | 7.4 | 2.2 |  | 13.6 | 6.4 | 3.7 | 14.6 | 9.1 | 4.5 | 19.8 | 13.8 | 5 | 23.8 | 15.6 | 7.2 | 21.3 | 14.2 | 7.5 | 14.2 | 6.9 | 2 | 4.8 | 1.5 |  | 2.4 |  |  | 3.1 | 1.3
6 | 0.5 | 8 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 18.8 | 10.8 | 5.7 | 23.2 | 14.6 | 6.2 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 9 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 10 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 11 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 12 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 15 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 20 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.5 | 25 | 4 |  |  | 5.4 | 2.4 |  | 8.6 | 2.6 |  | 16 | 7.9 | 4.2 | 19.4 | 11.7 | 5.7 | 23.1 | 14.6 | 6.8 | 28.4 | 18.5 | 9.1 | 23.3 | 16 | 7.8 | 16.2 | 7.8 | 2.1 | 5 | 2.2 |  | 2.8 | 0.6 |  | 3.1 | 1.3
6 | 0.75 | 2 |  |  |  | 0.9 |  |  | 0.8 |  |  | 1.5 | 0.8 |  | 2.2 | 0.7 |  | 3.1 | 1.4 |  | 2.8 | 1.3 |  | 2.2 | 0.8 | 0.7 | 1.5 | 0.8 |  | 0.7 |  |  | 0.5 |  |  | 0.8
6 | 0.75 | 4 | 2.7 | 0.7 |  | 5.9 | 3.3 |  | 7.7 | 3 | 1 | 12.3 | 6 | 3.9 | 12.2 | 6.6 | 2.8 | 15.5 | 11.5 | 6.7 | 14.7 | 9.9 | 6.7 | 16.4 | 10.1 | 5.2 | 12.4 | 7.2 | 4 | 4.4 | 2.3 | 0.2 | 3.1 | 1.9 |  | 4.3 | 1.5 | 0.2
6 | 0.75 | 6 | 9.7 | 3.8 | 0.2 | 13.1 | 7.4 | 1.6 | 18.3 | 6.9 | 4.9 | 27.2 | 15 | 10.5 | 27.3 | 18 | 13.2 | 34.7 | 24 | 13.6 | 34.4 | 25.1 | 19.1 | 35.7 | 22.6 | 14.6 | 24 | 17.9 | 9.8 | 12.8 | 5.8 | 2.9 | 8.9 | 4 | 1 | 10.7 | 5.1 | 1.3
6 | 0.75 | 8 | 15.7 | 5.2 | 0.2 | 16.7 | 10.3 | 2.5 | 25.2 | 11.4 | 7.5 | 33.1 | 20.8 | 13.6 | 35.1 | 27.3 | 18.8 | 42.6 | 33.3 | 20.9 | 48.1 | 36.2 | 27.2 | 44.2 | 35.5 | 24.9 | 32.7 | 24.2 | 12.4 | 15.9 | 8.6 | 4.8 | 11.5 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 9 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.1 | 7.6 | 33.1 | 21.7 | 13.6 | 37 | 28.4 | 20.7 | 44.9 | 34.6 | 22.3 | 49.5 | 38.4 | 29.3 | 45.6 | 37 | 25.6 | 33.5 | 24.2 | 12.4 | 15.9 | 9.1 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 10 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.2 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.1 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 11 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.3 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.3 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 12 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.3 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.3 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 15 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.3 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.3 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 20 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.3 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.3 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 0.75 | 25 | 15.7 | 5.2 | 0.2 | 16.6 | 10.3 | 2.5 | 25.2 | 12.2 | 7.6 | 33.1 | 22.1 | 13.9 | 37.8 | 29.3 | 21.3 | 44.9 | 34.6 | 22.6 | 49.5 | 38.4 | 29.5 | 46.3 | 37.4 | 25.6 | 33.5 | 24.2 | 12.5 | 15.9 | 9.3 | 4.8 | 11.7 | 5.4 | 1.5 | 12.3 | 6.9 | 1.5
6 | 1 | 2 | 0.8 |  |  | 1.6 |  |  | 1.5 |  |  | 2 | 0.8 | 0.7 | 2.2 | 0.8 |  | 3 | 1.4 | 0.7 | 3 | 1.7 |  | 2.7 | 0.8 | 0.7 | 2.2 | 1.4 |  | 0.8 |  |  | 0.8 |  |  | 0.8
6 | 1 | 4 | 4.5 | 1.5 |  | 8.6 | 3.9 | 1.6 | 9.8 | 4.4 | 1.5 | 13.4 | 8.2 | 5.9 | 13 | 8.9 | 5.1 | 18.2 | 13.9 | 8.4 | 17.7 | 12.1 | 7.9 | 17.5 | 12 | 7.5 | 13 | 8.8 | 5.3 | 6.8 | 3.6 | 2.2 | 5.2 | 2.4 | 0.7 | 4.3 | 2.8 | 0.7
6 | 1 | 6 | 14.3 | 7 | 1.6 | 18.1 | 10.9 | 4.2 | 24.3 | 14.1 | 7.2 | 31.1 | 21.1 | 15.8 | 31.5 | 23.8 | 17.2 | 40.5 | 31.7 | 22.3 | 41.1 | 32.3 | 23.7 | 40.1 | 28.6 | 22.3 | 30.7 | 24.7 | 14.4 | 18.9 | 9.7 | 5.5 | 12.9 | 7.2 | 4.9 | 15.5 | 7.7 | 2.9
6 | 1 | 8 | 24.9 | 12.1 | 3 | 27.8 | 17.7 | 9.7 | 35.6 | 23 | 14.3 | 49.7 | 33.9 | 27 | 48.6 | 42.7 | 32.5 | 59.1 | 48.3 | 39.5 | 62 | 51.5 | 37.2 | 58.6 | 48.8 | 39.1 | 45.2 | 37.6 | 27.7 | 27.8 | 16.7 | 9.2 | 22.2 | 13.5 | 6.7 | 23.4 | 10.9 | 5.1
6 | 1 | 9 | 25.7 | 13.3 | 3 | 28.7 | 20.4 | 10.1 | 37.4 | 24.7 | 15.5 | 54 | 38.9 | 28.7 | 55 | 45.4 | 33.9 | 62.9 | 52.8 | 43.2 | 69.1 | 56.9 | 42.9 | 63.8 | 50.8 | 42.7 | 49.8 | 40.3 | 28.9 | 29.6 | 19.4 | 10.4 | 24 | 14.7 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 10 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 26.2 | 16.8 | 54.5 | 38.8 | 29 | 56.9 | 46.9 | 36.1 | 64.3 | 54 | 45.1 | 70.3 | 58.2 | 44.6 | 65.3 | 52.4 | 44.1 | 50.4 | 41.9 | 29.8 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 11 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 27 | 16.7 | 54.5 | 38.8 | 29 | 56.9 | 47.6 | 36.4 | 64.4 | 54.3 | 45.1 | 70.5 | 59 | 45.7 | 65.6 | 52.4 | 44.6 | 50.4 | 41.9 | 29.9 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 12 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 27 | 16.7 | 54.5 | 38.8 | 29 | 56.9 | 47.6 | 36.4 | 64.4 | 54.3 | 45.1 | 70.6 | 59 | 45.9 | 65.6 | 52.4 | 44.6 | 50.4 | 41.9 | 29.9 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 15 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 27 | 16.7 | 54.5 | 38.8 | 29 | 56.9 | 47.6 | 36.4 | 64.4 | 54.3 | 45.1 | 70.6 | 59 | 45.9 | 65.6 | 52.4 | 44.6 | 50.4 | 41.9 | 29.9 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 20 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 27 | 16.7 | 54.5 | 38.8 | 29 | 56.9 | 47.6 | 36.4 | 64.4 | 54.3 | 45.1 | 70.6 | 59 | 45.9 | 65.6 | 52.4 | 44.6 | 50.4 | 41.9 | 29.9 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1 | 25 | 25.7 | 13 | 3 | 28.7 | 20.4 | 10.2 | 37.9 | 27 | 16.7 | 54.5 | 38.8 | 29 | 56.9 | 47.6 | 36.4 | 64.4 | 54.3 | 45.1 | 70.6 | 59 | 45.9 | 65.6 | 52.4 | 44.6 | 50.4 | 41.9 | 29.9 | 30 | 19.8 | 11.6 | 24.5 | 14.9 | 6.7 | 25.2 | 11.7 | 6
6 | 1.25 | 2 | 0.8 |  |  | 1.6 |  |  | 1.5 |  |  | 2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.3 | 0.7 | 2.2 | 1.4 |  | 1.2 |  |  | 0.8 |  |  | 1.3
6 | 1.25 | 4 | 5.7 | 2 | 0.7 | 9.6 | 5.5 | 2.4 | 11.2 | 5.9 | 2.2 | 14.8 | 9.2 | 6.6 | 13.9 | 9.8 | 6 | 18.4 | 15.4 | 8.6 | 18.4 | 12.8 | 7.9 | 19 | 13 | 8 | 14.6 | 9.3 | 5.4 | 8.3 | 4.3 | 2.2 | 6.2 | 3.1 | 1.5 | 6.1 | 3 | 0.7
6 | 1.25 | 6 | 19.2 | 7.7 | 3.9 | 22 | 13.4 | 5.3 | 25.5 | 16.5 | 9.8 | 33.6 | 23.6 | 18.4 | 34.3 | 26.6 | 21.6 | 45.3 | 35.7 | 26.3 | 43.4 | 34.4 | 25.2 | 41.2 | 30.4 | 24 | 33 | 27.4 | 16.5 | 20.8 | 12.8 | 8.2 | 17.3 | 10.3 | 6.4 | 18.7 | 9.8 | 3.8
6 | 1.25 | 8 | 32 | 18.5 | 7.9 | 33 | 26.3 | 11.6 | 44.1 | 31 | 19.9 | 55.1 | 42.5 | 35.5 | 55.5 | 49.5 | 40.9 | 68.6 | 57.4 | 45.9 | 68 | 59.4 | 45.4 | 65 | 55.2 | 46.2 | 53.4 | 43.3 | 34.6 | 34.8 | 23.3 | 16.7 | 30.1 | 20 | 11.4 | 32.8 | 17.3 | 9.8
6 | 1.25 | 9 | 34.6 | 21.8 | 9.5 | 40.1 | 28.9 | 13.5 | 48 | 37.9 | 24.2 | 62.4 | 49 | 41.6 | 65.3 | 57 | 49.4 | 75.4 | 64.3 | 54.4 | 75.4 | 68.4 | 53.7 | 72.7 | 64 | 52.5 | 60.4 | 49.7 | 38 | 41.1 | 29.3 | 20.2 | 35.2 | 24.2 | 14.3 | 34.6 | 20.6 | 12.2
6 | 1.25 | 10 | 37 | 22 | 10.5 | 43 | 31.3 | 15 | 51.7 | 41.4 | 25.9 | 68.2 | 53.2 | 43.8 | 71.2 | 61.2 | 53.7 | 78.2 | 69.7 | 58.3 | 81.3 | 74.2 | 58.4 | 76.1 | 67.6 | 56.5 | 64.3 | 54.3 | 40 | 43.4 | 32.9 | 21.6 | 37.3 | 26.1 | 14.4 | 35.6 | 21.2 | 14.2
6 | 1.25 | 11 | 37.6 | 23.5 | 10.5 | 43.6 | 31.3 | 16 | 51.6 | 42.1 | 25.9 | 70.4 | 55.6 | 44.6 | 73 | 63.8 | 56.3 | 79.3 | 71.5 | 59.7 | 82.9 | 75.7 | 59.3 | 76.6 | 68.8 | 58.5 | 64.9 | 56.3 | 41.4 | 43.6 | 33.5 | 22.3 | 37.8 | 26.1 | 14.3 | 35.6 | 21.1 | 14.7
6 | 1.25 | 12 | 37.6 | 23.5 | 10.5 | 43.6 | 31.3 | 16 | 52.7 | 42.3 | 25.9 | 70.4 | 55.6 | 44.8 | 73 | 63.8 | 56.5 | 79.4 | 71.5 | 59.9 | 82.9 | 75.7 | 59.7 | 77.1 | 69.6 | 58.9 | 64.9 | 56.3 | 41.4 | 43.6 | 33.5 | 22.3 | 38.1 | 26.1 | 14.3 | 35.6 | 21.1 | 14.7
6 | 1.25 | 15 | 37.6 | 23.5 | 10.5 | 43.6 | 31.3 | 16 | 52.7 | 42.3 | 25.9 | 70.4 | 55.6 | 44.8 | 72.9 | 63.8 | 56.5 | 79.4 | 71.5 | 59.9 | 82.9 | 75.7 | 60.1 | 77.1 | 69.6 | 58.9 | 64.9 | 56.3 | 41.4 | 43.6 | 33.5 | 22.3 | 38.1 | 26.1 | 14.3 | 35.6 | 21.1 | 14.7
6 | 1.25 | 20 | 37.6 | 23.5 | 10.5 | 43.6 | 31.3 | 16 | 52.7 | 42.3 | 25.9 | 70.4 | 55.6 | 44.8 | 72.9 | 63.8 | 56.5 | 79.4 | 71.5 | 59.9 | 82.9 | 75.7 | 60.1 | 77.1 | 69.6 | 58.9 | 64.9 | 56.3 | 41.4 | 43.6 | 33.5 | 22.3 | 38.1 | 26.1 | 14.3 | 35.6 | 21.1 | 14.7
6 | 1.25 | 25 | 37.6 | 23.5 | 10.5 | 43.6 | 31.3 | 16 | 52.7 | 42.3 | 25.9 | 70.4 | 55.6 | 44.8 | 72.9 | 63.8 | 56.5 | 79.4 | 71.5 | 59.9 | 82.9 | 75.7 | 60.1 | 77.1 | 69.6 | 58.9 | 64.9 | 56.3 | 41.4 | 43.6 | 33.5 | 22.3 | 38.1 | 26.1 | 14.3 | 35.6 | 21.1 | 14.7
6 | 1.5 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 |  |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.3 | 0.7 | 2.2 | 1.4 |  | 1.2 |  |  | 0.8 |  |  | 1.5
6 | 1.5 | 4 | 7.2 | 2.3 | 1.3 | 10.4 | 5.5 | 2.4 | 12 | 6.5 | 2.6 | 14.9 | 9.7 | 7.4 | 14.4 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8 | 19.3 | 13 | 8 | 15.1 | 9.6 | 5.8 | 8.8 | 4.4 | 2.5 | 6.3 | 3.2 | 1.5 | 7.9 | 3 | 1.3
6 | 1.5 | 6 | 21.3 | 9 | 5.1 | 23.2 | 13.4 | 6.7 | 26.7 | 18.1 | 10.6 | 35.2 | 25.1 | 20.4 | 35.2 | 27.7 | 22.4 | 45.8 | 35.7 | 27.6 | 45 | 34.8 | 25.8 | 42.7 | 31.7 | 25.1 | 33.3 | 27.8 | 16.6 | 22.1 | 15.7 | 9.1 | 18.1 | 13.3 | 7.9 | 19.9 | 11.8 | 4.7
6 | 1.5 | 8 | 35 | 21.5 | 11.4 | 39.6 | 29.8 | 15.1 | 45.4 | 33.9 | 23.7 | 59.9 | 46.3 | 40.9 | 59.8 | 52.4 | 44 | 71.3 | 60 | 49.9 | 70 | 61.4 | 50.4 | 66 | 58.6 | 47.5 | 56.2 | 45.8 | 37.9 | 39.5 | 27.6 | 20.3 | 34 | 24.9 | 15.7 | 35.9 | 20.6 | 12.6
6 | 1.5 | 9 | 40.9 | 28.6 | 14.9 | 46.8 | 37.5 | 19.9 | 56.7 | 44.4 | 32.7 | 67.2 | 54.9 | 49.8 | 70 | 62.2 | 53.4 | 79.5 | 70.8 | 61.9 | 77.9 | 73.5 | 61.2 | 76.8 | 66.7 | 56.6 | 64.7 | 56.7 | 46 | 46 | 35.1 | 25.7 | 42.3 | 31.7 | 19.3 | 40.8 | 25.3 | 17.1
6 | 1.5 | 10 | 45.3 | 31.2 | 17.2 | 55.5 | 40.9 | 23.9 | 62.7 | 50.3 | 38.8 | 74.3 | 61.4 | 54.5 | 78.1 | 69.2 | 62.4 | 84.9 | 79.6 | 69.1 | 85.9 | 81 | 70.2 | 83.6 | 73.7 | 63.8 | 71.4 | 61.4 | 50.7 | 52.9 | 39.8 | 31.9 | 48.9 | 36.3 | 23.2 | 44.9 | 29.8 | 20.1
6 | 1.5 | 11 | 46.4 | 32.5 | 18.8 | 57.7 | 44.5 | 24.2 | 67.1 | 52.3 | 40.8 | 78.1 | 66.7 | 57.5 | 82.2 | 74.5 | 67 | 87.9 | 81.9 | 71.4 | 90.3 | 84.8 | 73.2 | 85.8 | 78.5 | 68.1 | 74.7 | 65.7 | 54.1 | 56.5 | 45.4 | 33.6 | 52.5 | 36.9 | 23.9 | 47.4 | 31.2 | 21.5
6 | 1.5 | 12 | 46.8 | 33.3 | 19 | 58.2 | 45.5 | 24.3 | 67.8 | 52.3 | 41 | 79.1 | 67.6 | 58.5 | 82.4 | 76.2 | 68.9 | 88.7 | 82.1 | 73.2 | 91.8 | 85.5 | 73.4 | 86.6 | 78.5 | 69.4 | 75.7 | 66.5 | 54 | 57.5 | 46.6 | 34.3 | 52.8 | 37.1 | 24.3 | 48.5 | 31.6 | 22.3
6 | 1.5 | 15 | 47 | 34.1 | 19.1 | 58.3 | 45.5 | 24.3 | 67.8 | 52.7 | 41.5 | 79.8 | 67.6 | 58.6 | 82.4 | 76.7 | 68.9 | 88.7 | 82.2 | 73.2 | 92 | 85.6 | 73.4 | 86.8 | 78.5 | 70.2 | 75.6 | 67.4 | 54 | 58.3 | 46.5 | 34.3 | 52.7 | 37.1 | 24.5 | 48.4 | 32.8 | 22.3
6 | 1.5 | 20 | 47 | 34.1 | 19.1 | 58.3 | 45.5 | 24.3 | 67.8 | 52.7 | 41.5 | 79.8 | 67.6 | 58.6 | 82.4 | 76.7 | 68.9 | 88.7 | 82.2 | 73.2 | 92 | 85.6 | 73.4 | 86.8 | 78.5 | 70.2 | 75.6 | 67.4 | 54 | 58.3 | 46.5 | 34.3 | 52.7 | 37.1 | 24.5 | 48.4 | 32.8 | 22.3
6 | 1.5 | 25 | 47 | 34.1 | 19.1 | 58.3 | 45.5 | 24.3 | 67.8 | 52.7 | 41.5 | 79.8 | 67.6 | 58.6 | 82.4 | 76.7 | 68.9 | 88.7 | 82.2 | 73.2 | 92 | 85.6 | 73.4 | 86.8 | 78.5 | 70.2 | 75.6 | 67.4 | 54 | 58.3 | 46.5 | 34.3 | 52.7 | 37.1 | 24.5 | 48.4 | 32.8 | 22.3
6 | 1.75 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 1.75 | 4 | 7.2 | 2.3 | 1.4 | 10.6 | 5.8 | 2.4 | 12.4 | 6.6 | 3.2 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.3 | 9 | 4.6 | 3.5 | 7 | 3.8 | 1.7 | 8.3 | 3.6 | 1.4
6 | 1.75 | 6 | 21.8 | 10.6 | 5.7 | 23.5 | 14.9 | 8.5 | 27 | 19 | 12.7 | 36.2 | 27.1 | 21.8 | 35.2 | 28.9 | 23 | 45.8 | 37.1 | 27.6 | 45 | 34.8 | 25.8 | 43 | 32.5 | 25.2 | 33.8 | 28.8 | 17.4 | 22.5 | 17.2 | 9.4 | 18.8 | 14 | 8.8 | 20.4 | 13.3 | 5.1
6 | 1.75 | 8 | 37.1 | 24.2 | 13.9 | 41.3 | 32.1 | 18.8 | 47.4 | 37.2 | 27.4 | 60.9 | 48.3 | 42.3 | 60.6 | 53.2 | 45.4 | 71.3 | 61.8 | 52.5 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 47.7 | 58.4 | 47.4 | 38.9 | 42.1 | 30.1 | 22.3 | 37.2 | 26.5 | 16.5 | 36.2 | 23.4 | 13.6
6 | 1.75 | 9 | 46.3 | 32.5 | 17.4 | 52.3 | 40 | 23.8 | 59.9 | 46.2 | 36.6 | 69.4 | 59 | 54.1 | 72 | 64.5 | 55.4 | 82.6 | 72.6 | 64.2 | 80 | 74.7 | 63.4 | 77.4 | 68.3 | 57.9 | 68.5 | 58.1 | 49.7 | 49.8 | 37.4 | 30.1 | 45.8 | 33.5 | 23.6 | 43.4 | 28.5 | 18.7
6 | 1.75 | 10 | 51.2 | 35.9 | 23.2 | 60.2 | 48.4 | 29.5 | 70.1 | 55.2 | 42.7 | 78.7 | 67.6 | 61.1 | 81.7 | 73 | 66.4 | 87.8 | 82.1 | 73.6 | 87.9 | 82.9 | 74 | 86.8 | 75.7 | 67.6 | 73.6 | 65.6 | 56.7 | 55.5 | 45.3 | 35.8 | 52.6 | 41 | 29.5 | 51.3 | 35.3 | 23.7
6 | 1.75 | 11 | 55.3 | 41.7 | 29.5 | 65.9 | 54 | 31.2 | 75.3 | 61.2 | 47.9 | 86.3 | 74.3 | 66.4 | 86.3 | 79.2 | 74.2 | 92.2 | 87.6 | 78 | 94.4 | 87.9 | 79.7 | 90 | 82.1 | 73.5 | 79.3 | 71.3 | 62.5 | 65.2 | 53.8 | 42.3 | 58.1 | 46 | 33.2 | 56.5 | 39.8 | 28.6
6 | 1.75 | 12 | 56.9 | 42.5 | 32.9 | 67.6 | 57.1 | 34.2 | 78.1 | 64.7 | 51 | 86.4 | 76.3 | 67.8 | 89.4 | 84 | 77.8 | 93.8 | 88.3 | 81.2 | 95.6 | 89.2 | 81.2 | 92.2 | 84.1 | 76.4 | 81.4 | 74.2 | 64.7 | 71 | 56.6 | 46.1 | 61.5 | 47.9 | 34 | 58.8 | 39.7 | 29.6
6 | 1.75 | 15 | 57.6 | 42.5 | 33.8 | 68.8 | 58 | 34.6 | 78.3 | 65.6 | 53.1 | 86.9 | 76.7 | 68.4 | 89.9 | 85.8 | 79.7 | 94 | 88.3 | 82.3 | 95.8 | 90.2 | 81.8 | 92.2 | 84.1 | 77.6 | 83 | 74.6 | 65.3 | 73.4 | 57.5 | 47.8 | 62.8 | 47.8 | 36 | 59.2 | 41.1 | 29.6
6 | 1.75 | 20 | 57.8 | 42.5 | 33.8 | 68.8 | 58 | 34.6 | 78.3 | 65.6 | 53.1 | 86.9 | 76.7 | 68.4 | 89.9 | 85.8 | 79.7 | 94 | 88.3 | 82.3 | 95.8 | 90.2 | 81.8 | 92.2 | 84.1 | 77.6 | 83 | 74.6 | 65.3 | 73.4 | 57.5 | 47.8 | 62.8 | 47.8 | 36 | 59.2 | 41.1 | 29.6
6 | 1.75 | 25 | 57.8 | 42.5 | 33.8 | 68.8 | 58 | 34.6 | 78.3 | 65.6 | 53.1 | 86.9 | 76.7 | 68.4 | 89.9 | 85.8 | 79.7 | 94 | 88.3 | 82.3 | 95.8 | 90.2 | 81.8 | 92.2 | 84.1 | 77.6 | 83 | 74.6 | 65.3 | 73.4 | 57.5 | 47.8 | 62.8 | 47.8 | 36 | 59.2 | 41.1 | 29.6
6 | 2 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 2 | 4 | 7.2 | 2.3 | 1.4 | 10.9 | 5.8 | 2.4 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.4 | 9.2 | 5 | 3.5 | 7 | 4.3 | 1.7 | 8.8 | 3.8 | 1.4
6 | 2 | 6 | 21.8 | 10.6 | 6.1 | 24 | 15 | 9 | 27 | 19.2 | 12.7 | 36.2 | 27.2 | 22.6 | 35.2 | 29 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 34.8 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.7 | 9.9 | 18.8 | 14 | 9.4 | 21.3 | 13.8 | 5.3
6 | 2 | 8 | 38.1 | 25 | 15.3 | 43.1 | 33 | 19.8 | 49 | 38.3 | 28.7 | 60.9 | 50.7 | 43.8 | 60.8 | 53.5 | 45.4 | 71.3 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.4 | 48.1 | 39.2 | 42.6 | 30.9 | 23.2 | 37.8 | 28.1 | 17.3 | 37.8 | 24.2 | 14.9
6 | 2 | 9 | 49.4 | 32.7 | 19.2 | 54.2 | 41.5 | 24.7 | 60.5 | 47.3 | 38.9 | 70.4 | 60.8 | 55.4 | 72.7 | 64.9 | 56.4 | 83.4 | 73.5 | 65.4 | 80.2 | 75 | 64.8 | 79.1 | 69.4 | 58.8 | 69.6 | 60.3 | 50.9 | 50.9 | 37.4 | 31 | 48.1 | 36.5 | 25.3 | 46 | 31.5 | 20.6
6 | 2 | 10 | 54.8 | 39 | 26.5 | 61.7 | 52.5 | 29.9 | 70.8 | 58.7 | 45.7 | 79.9 | 71.3 | 64.2 | 81.9 | 75.5 | 68.5 | 89.5 | 83.6 | 76.9 | 88.5 | 83.9 | 76.1 | 87.5 | 77.6 | 68.6 | 77.8 | 66.4 | 59.2 | 58 | 49.3 | 39.7 | 55.6 | 44.2 | 32.7 | 54.9 | 37.8 | 27.2
6 | 2 | 11 | 59.7 | 43.5 | 34.4 | 70.1 | 60 | 34.1 | 76.9 | 66.1 | 52.9 | 87.5 | 76.8 | 69 | 88.2 | 82.4 | 78.2 | 94.3 | 89.2 | 82 | 95.7 | 89.9 | 82.2 | 92.1 | 83.7 | 75.4 | 82.3 | 74.2 | 65.4 | 67.4 | 57.8 | 46.9 | 63.5 | 51.3 | 38.1 | 60.1 | 43.4 | 33.3
6 | 2 | 12 | 64.3 | 48.1 | 40.3 | 73.2 | 65.1 | 41 | 81.8 | 70.8 | 55.5 | 89.9 | 81.9 | 72.8 | 92.4 | 88.4 | 83.3 | 95.7 | 91.4 | 87.7 | 97.7 | 93.3 | 85 | 94.9 | 87.2 | 80.3 | 85.3 | 79.2 | 70.5 | 73.3 | 61 | 52.4 | 68.6 | 57.1 | 40.5 | 63.3 | 46.6 | 34.8
6 | 2 | 15 | 66.5 | 51.9 | 43.5 | 79.5 | 69 | 44.3 | 84.1 | 74.1 | 61.1 | 92.1 | 85.6 | 74.9 | 94.2 | 90.1 | 87.1 | 96.6 | 92.8 | 88.7 | 98.8 | 95.4 | 88.8 | 96.7 | 87.9 | 82.7 | 87.3 | 81.9 | 72.2 | 77.5 | 67.3 | 58.6 | 73.1 | 59.6 | 45.3 | 68.1 | 50 | 35.5
6 | 2 | 20 | 66.5 | 51.9 | 43.5 | 79.5 | 69 | 44.3 | 84.1 | 74.1 | 61.1 | 92.1 | 85.6 | 74.9 | 94.2 | 90.1 | 87.2 | 96.6 | 92.8 | 88.7 | 98.8 | 95.4 | 88.8 | 96.7 | 87.9 | 82.7 | 87.3 | 81.9 | 72.2 | 77.5 | 67.5 | 58.7 | 73.1 | 59.6 | 45.3 | 68.1 | 50 | 35.5
6 | 2 | 25 | 66.5 | 51.9 | 43.5 | 79.5 | 69 | 44.3 | 84.1 | 74.1 | 61.1 | 92.1 | 85.6 | 74.9 | 94.2 | 90.1 | 87.2 | 96.6 | 92.8 | 88.7 | 98.8 | 95.4 | 88.8 | 96.7 | 87.9 | 82.7 | 87.3 | 81.9 | 72.2 | 77.5 | 67.5 | 58.7 | 73.1 | 59.6 | 45.3 | 68.1 | 50 | 35.5
6 | 2.25 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 2.25 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 1.7 | 9.9 | 3.8 | 1.4
6 | 2.25 | 6 | 21.7 | 10.6 | 6.6 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.3 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 21.6 | 13.8 | 5.9
6 | 2.25 | 8 | 39.1 | 25.8 | 16 | 44.4 | 33.9 | 20 | 49 | 39.4 | 29.5 | 60.9 | 51.3 | 43.8 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.3 | 28.9 | 17.6 | 38.4 | 24.2 | 16.5
6 | 2.25 | 9 | 49.4 | 32.7 | 19.9 | 54.2 | 42.4 | 25.5 | 60.8 | 48.1 | 39.1 | 70.4 | 62.1 | 55.7 | 72.7 | 64.8 | 57 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.8 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 51.9 | 39.2 | 31.7 | 48.7 | 36.5 | 26.9 | 47.2 | 33.3 | 21.8
6 | 2.25 | 10 | 56.2 | 40.2 | 26.9 | 62.5 | 54.3 | 32.9 | 71.7 | 58.7 | 46.9 | 80.7 | 72.1 | 65.9 | 82.5 | 75.7 | 68.7 | 90.2 | 83.8 | 77.2 | 88.5 | 84 | 76.7 | 88 | 80.2 | 69.4 | 77.8 | 67.2 | 60.8 | 59.2 | 50.7 | 41.5 | 56.1 | 46.8 | 33.4 | 55.9 | 41 | 28.6
6 | 2.25 | 11 | 62.2 | 46.8 | 36.2 | 72.1 | 60.3 | 37.3 | 77.8 | 68.3 | 56.3 | 87.9 | 77.9 | 72.3 | 89.8 | 83.2 | 79.5 | 94.8 | 89.6 | 82.8 | 95.7 | 90.3 | 83.1 | 93 | 85.1 | 76.7 | 84.8 | 74.6 | 67 | 68.4 | 59 | 49.2 | 66 | 54.4 | 41.3 | 62.2 | 46.2 | 36.6
6 | 2.25 | 12 | 67.8 | 53.2 | 43.3 | 75.8 | 67.6 | 47.8 | 84 | 74.7 | 59.4 | 92.4 | 85 | 77.5 | 93.1 | 89.1 | 85.3 | 97.6 | 92.2 | 88.7 | 97.6 | 94.5 | 88.3 | 97 | 89.5 | 83.7 | 88.4 | 81.9 | 72.9 | 75.2 | 65.5 | 56.4 | 73.2 | 62.1 | 44.4 | 69.7 | 50 | 41.8
6 | 2.25 | 15 | 75.5 | 60.1 | 49.2 | 83.1 | 74.3 | 54.3 | 90.1 | 81 | 67.4 | 95.9 | 91.9 | 82.9 | 96.2 | 94.4 | 91.3 | 99 | 95.1 | 92.6 | 99.8 | 97.2 | 93.3 | 98.2 | 92.6 | 87.6 | 92.6 | 87.1 | 79.8 | 82.7 | 75.8 | 69.1 | 80.1 | 68.1 | 52.4 | 75.6 | 61.2 | 47.8
6 | 2.25 | 20 | 75.8 | 60.2 | 49.2 | 83.8 | 75.1 | 54.3 | 90.4 | 80.9 | 67.6 | 96 | 91.9 | 82.9 | 96.2 | 94.4 | 91.3 | 99 | 95.3 | 92.6 | 99.8 | 97.2 | 93.3 | 98.2 | 92.5 | 88 | 92.5 | 87.1 | 79.8 | 82.8 | 75.8 | 69.2 | 80.9 | 67.9 | 53 | 75.6 | 61.8 | 48.4
6 | 2.25 | 25 | 75.8 | 60.2 | 49.2 | 83.8 | 75.1 | 54.3 | 90.4 | 80.9 | 67.6 | 96 | 91.9 | 82.9 | 96.2 | 94.4 | 91.3 | 99 | 95.3 | 92.6 | 99.8 | 97.2 | 93.3 | 98.2 | 92.5 | 88 | 92.5 | 87.1 | 79.8 | 82.8 | 75.8 | 69.2 | 80.9 | 67.9 | 53 | 75.6 | 61.8 | 48.4
6 | 2.75 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 2.75 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 2.75 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 2.75 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.5 | 49 | 39.2 | 29.5 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 2.75 | 9 | 49.4 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.1 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.5 | 40.1 | 32.5 | 48.8 | 39.4 | 27.4 | 49 | 33.3 | 22.2
6 | 2.75 | 10 | 57.9 | 40.2 | 27.9 | 62.7 | 55.4 | 34 | 71.7 | 59.8 | 48.6 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.3 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 60.8 | 62 | 51.7 | 42.4 | 57.2 | 48.8 | 34 | 57.2 | 41.8 | 29.3
6 | 2.75 | 11 | 63.9 | 49.3 | 37.5 | 72.4 | 61.1 | 39 | 78.4 | 69.8 | 57.2 | 88.2 | 80.7 | 74.9 | 90.5 | 84.9 | 79.9 | 94.9 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 68.9 | 71 | 60.6 | 50.6 | 67.6 | 57.6 | 42.6 | 65 | 48.8 | 39
6 | 2.75 | 12 | 70.7 | 57.1 | 46.6 | 77.2 | 72.5 | 50 | 85.7 | 78.1 | 62.4 | 93.9 | 86.5 | 81.1 | 94.5 | 90.7 | 87.1 | 97.9 | 93.6 | 89.9 | 97.9 | 95.6 | 89.1 | 97 | 91.4 | 84.7 | 89.5 | 83.3 | 75.6 | 77.3 | 69 | 57.6 | 75.3 | 66.8 | 48.8 | 71.2 | 55.6 | 46.7
6 | 2.75 | 15 | 84.4 | 72 | 61.8 | 89.5 | 83.3 | 68 | 93.9 | 87.2 | 77.5 | 98.5 | 95.1 | 91 | 99.6 | 98.3 | 96.2 | 100 | 97.9 | 96.2 | 100 | 98.7 | 96.2 | 100 | 96.9 | 93.8 | 96.5 | 93.8 | 86.9 | 90.2 | 82.4 | 78.1 | 88.1 | 80 | 65.6 | 83.9 | 70.4 | 61.5
6 | 2.75 | 20 | 87.6 | 73.7 | 63.2 | 91.6 | 84.6 | 69.5 | 94.9 | 88.3 | 77.9 | 99 | 96 | 91.5 | 100 | 98.5 | 96.3 | 100 | 98.1 | 96.2 | 100 | 98.9 | 96.3 | 100 | 97.4 | 94.4 | 96.9 | 94.9 | 88.5 | 91.3 | 84.7 | 79.8 | 89.9 | 81.3 | 69.7 | 86 | 73 | 66
6 | 2.75 | 25 | 87.6 | 73.7 | 63.2 | 91.6 | 84.6 | 69.5 | 94.9 | 88.3 | 77.9 | 99 | 96 | 91.5 | 100 | 98.5 | 96.8 | 100 | 98.1 | 96.2 | 100 | 98.9 | 96.3 | 100 | 97.4 | 94.4 | 96.9 | 94.9 | 88.5 | 91.3 | 84.7 | 79.8 | 89.9 | 81.3 | 69.7 | 86 | 73 | 66
6 | 3 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 3 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 3 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 3 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.4 | 49 | 39.2 | 30 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 3 | 9 | 49.5 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.1 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.8 | 40.1 | 32.5 | 48.8 | 39.4 | 27.6 | 49 | 33.3 | 22.4
6 | 3 | 10 | 58.1 | 40.2 | 27.9 | 62.7 | 55.4 | 34.2 | 71.7 | 59.8 | 48.9 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.4 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 61 | 62 | 51.7 | 43 | 57.9 | 49.6 | 34.2 | 58.3 | 41.8 | 29.8
6 | 3 | 11 | 64.6 | 49.3 | 37.4 | 72.4 | 61.1 | 39.9 | 78.4 | 69.8 | 57.4 | 88.2 | 80.7 | 75 | 90.5 | 84.9 | 79.9 | 95.2 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 69.3 | 71 | 61.7 | 50.6 | 67.6 | 57.8 | 44 | 65.3 | 50.7 | 39
6 | 3 | 12 | 71.3 | 57.7 | 46.7 | 77.2 | 72.8 | 51.4 | 86.9 | 78.9 | 63.2 | 93.9 | 86.5 | 81.4 | 94.7 | 90.7 | 88.1 | 97.9 | 93.6 | 90 | 97.9 | 95.6 | 89.6 | 97 | 91.4 | 84.7 | 89.5 | 84 | 76.7 | 77.5 | 69.2 | 58.4 | 75.3 | 66.9 | 50.1 | 72.5 | 57.3 | 46.7
6 | 3 | 15 | 85.5 | 75.9 | 65.8 | 91.4 | 86.6 | 72.9 | 94.8 | 89 | 82.2 | 99 | 96.4 | 91.9 | 99.9 | 98.8 | 97.4 | 100 | 98.3 | 96.4 | 100 | 99.3 | 96.9 | 100 | 98.1 | 94.8 | 97.5 | 93.9 | 90.2 | 91.9 | 85.1 | 79.8 | 89.6 | 81.8 | 70.4 | 85.7 | 75.3 | 64.3
6 | 3 | 20 | 90.8 | 79.4 | 67.6 | 95.1 | 89.1 | 76.9 | 97.1 | 91.5 | 85.1 | 100 | 97.2 | 93.6 | 100 | 100 | 98 | 100 | 99 | 97 | 100 | 100 | 97.9 | 100 | 98.8 | 96.7 | 98.3 | 96.3 | 91.3 | 94.1 | 89.4 | 84 | 92.2 | 87.5 | 76.2 | 88.5 | 79.2 | 71.2
6 | 3 | 25 | 90.8 | 79.4 | 67.6 | 95.1 | 89.1 | 76.9 | 97.1 | 91.5 | 85.1 | 100 | 97.2 | 93.6 | 100 | 100 | 98 | 100 | 99 | 97 | 100 | 100 | 97.9 | 100 | 98.8 | 96.7 | 98.3 | 96.3 | 91.3 | 94.1 | 89.4 | 84 | 92.2 | 87.5 | 76.2 | 88.5 | 79.2 | 71.2
6 | 3.5 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 3.5 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 3.5 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 3.5 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.4 | 49 | 39.2 | 30 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 3.5 | 9 | 49.5 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.7 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.8 | 40.1 | 32.5 | 48.8 | 39.4 | 27.6 | 49 | 33.3 | 22.4
6 | 3.5 | 10 | 58.1 | 40.2 | 27.9 | 62.7 | 55.4 | 34.2 | 71.7 | 59.8 | 49.1 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.4 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 61 | 62 | 51.7 | 43 | 57.9 | 50.6 | 34.2 | 58.3 | 41.8 | 29.8
6 | 3.5 | 11 | 64.7 | 49.3 | 37.4 | 72.4 | 61.1 | 40 | 78.4 | 69.9 | 57.4 | 88.2 | 80.7 | 75 | 90.5 | 84.9 | 79.9 | 95.2 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 69.3 | 71.1 | 62.1 | 51.4 | 67.6 | 58.6 | 44 | 65.6 | 50.5 | 39.4
6 | 3.5 | 12 | 71.3 | 57.8 | 46.7 | 77.4 | 72.8 | 51.9 | 86.9 | 79.6 | 65.5 | 93.9 | 86.5 | 81.5 | 94.7 | 90.7 | 88.1 | 97.9 | 93.6 | 90 | 97.9 | 95.6 | 89.6 | 97 | 91.4 | 84.7 | 89.7 | 84 | 77.6 | 77.5 | 69.8 | 58.4 | 75.3 | 67.8 | 51.8 | 73.5 | 57.7 | 47.1
6 | 3.5 | 15 | 87.5 | 78.9 | 69.1 | 92.7 | 88.2 | 77.2 | 95.8 | 90.1 | 84.3 | 99.3 | 97.5 | 93.8 | 100 | 99.1 | 98.4 | 100 | 98.3 | 97.1 | 100 | 100 | 98 | 100 | 98.5 | 95.1 | 98.4 | 94.6 | 91.4 | 92.8 | 87 | 81.2 | 92.4 | 83.6 | 75.2 | 88.1 | 77.8 | 67.6
6 | 3.5 | 20 | 95.6 | 89.8 | 81.6 | 98.5 | 92.8 | 86.2 | 99.8 | 96.8 | 92.1 | 100 | 100 | 96.6 | 100 | 100 | 100 | 100 | 100 | 98.1 | 100 | 100 | 99.3 | 100 | 100 | 98.5 | 100 | 97.9 | 95.1 | 98.1 | 94.5 | 90.2 | 96.8 | 92.4 | 86.6 | 96 | 89 | 81.9
6 | 3.5 | 25 | 95.7 | 90.1 | 81.6 | 98.5 | 92.8 | 86.2 | 99.8 | 96.8 | 92.1 | 100 | 100 | 96.6 | 100 | 100 | 100 | 100 | 100 | 98.1 | 100 | 100 | 99.3 | 100 | 100 | 98.4 | 100 | 97.9 | 95.1 | 98.1 | 94.5 | 90.2 | 96.9 | 92.4 | 86.6 | 96 | 89 | 82.2
6 | 4 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 4 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 4 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 4 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.4 | 49 | 39.2 | 30 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 4 | 9 | 49.5 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.7 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.8 | 40.1 | 32.5 | 48.8 | 39.4 | 27.6 | 49 | 33.3 | 22.4
6 | 4 | 10 | 58.1 | 40.2 | 27.9 | 62.7 | 55.4 | 34.2 | 71.7 | 59.8 | 49.1 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.4 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 61 | 62 | 51.7 | 43 | 57.9 | 50.6 | 34.2 | 58.3 | 41.8 | 29.8
6 | 4 | 11 | 64.8 | 49.3 | 37.4 | 72.4 | 61.1 | 40 | 78.4 | 69.9 | 57.4 | 88.2 | 80.7 | 75 | 90.5 | 84.9 | 79.9 | 95.2 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 69.3 | 71.1 | 62.1 | 51.4 | 67.6 | 58.6 | 44 | 65.6 | 50.5 | 39.4
6 | 4 | 12 | 71.3 | 57.8 | 46.7 | 77.4 | 72.8 | 51.9 | 86.9 | 79.6 | 65.6 | 93.9 | 86.5 | 81.5 | 94.7 | 90.7 | 88.1 | 97.9 | 93.6 | 90 | 97.9 | 95.6 | 89.6 | 97 | 91.4 | 84.7 | 89.7 | 84 | 77.6 | 77.5 | 69.8 | 58.4 | 75.3 | 67.8 | 52.9 | 73.5 | 57.7 | 47.1
6 | 4 | 15 | 88.5 | 79 | 70.4 | 93.1 | 88.8 | 78.2 | 96.1 | 90.7 | 84.4 | 99.3 | 97.8 | 94.1 | 100 | 99.2 | 98.4 | 100 | 98.9 | 97.1 | 100 | 100 | 98.3 | 100 | 98.7 | 95.7 | 98.4 | 94.9 | 91.8 | 93 | 87.8 | 82.3 | 93.3 | 85.1 | 76.8 | 89.1 | 80.8 | 68.3
6 | 4 | 20 | 98.3 | 95 | 89.4 | 99.6 | 96.9 | 90.9 | 100 | 98.7 | 96.3 | 100 | 100 | 98.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.7 | 97 | 100 | 97.6 | 95 | 99.5 | 96.7 | 93.2 | 99.1 | 94.6 | 89.6
6 | 4 | 25 | 98.3 | 94.9 | 89.6 | 99.8 | 97 | 91.1 | 100 | 99.1 | 96.4 | 100 | 100 | 98.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.2 | 100 | 97.6 | 95.2 | 99.5 | 96.8 | 94.1 | 99.2 | 94.9 | 91.7
6 | 4.5 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 4.5 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 4.5 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 4.5 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.4 | 49 | 39.2 | 30 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 4.5 | 9 | 49.5 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.7 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.8 | 40.1 | 32.5 | 48.8 | 39.4 | 27.6 | 49 | 33.3 | 22.4
6 | 4.5 | 10 | 58.1 | 40.2 | 27.9 | 62.7 | 55.4 | 34.2 | 71.7 | 59.8 | 49.1 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.4 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 61 | 62 | 51.7 | 43 | 57.9 | 50.6 | 34.2 | 58.3 | 41.8 | 29.8
6 | 4.5 | 11 | 64.8 | 49.3 | 37.4 | 72.4 | 61.1 | 40 | 78.4 | 69.9 | 57.4 | 88.2 | 80.7 | 75 | 90.5 | 84.9 | 79.9 | 95.2 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 69.3 | 71.1 | 62.1 | 51.4 | 67.6 | 58.6 | 44 | 65.6 | 50.5 | 39.4
6 | 4.5 | 12 | 71.3 | 57.8 | 46.7 | 77.4 | 72.8 | 51.9 | 86.9 | 79.6 | 65.6 | 93.9 | 86.5 | 81.5 | 94.7 | 90.7 | 88.1 | 97.9 | 93.6 | 90 | 97.9 | 95.6 | 89.6 | 97 | 91.4 | 84.7 | 89.7 | 84 | 77.6 | 77.5 | 69.8 | 58.4 | 75.3 | 67.8 | 52.9 | 73.5 | 57.7 | 47.1
6 | 4.5 | 15 | 89.1 | 79 | 70.4 | 93.1 | 89 | 78.2 | 96.1 | 91.1 | 84.5 | 99.3 | 98.2 | 94.6 | 100 | 99.2 | 98.4 | 100 | 98.9 | 97.7 | 100 | 100 | 98.3 | 100 | 98.7 | 95.7 | 98.4 | 95 | 91.8 | 93 | 87.8 | 82.5 | 93.3 | 85.7 | 77.3 | 89.1 | 80.8 | 68.4
6 | 4.5 | 20 | 99.5 | 96.9 | 92.4 | 100 | 98.1 | 94.1 | 100 | 99.5 | 98 | 100 | 100 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.9 | 100 | 98.8 | 96.5 | 100 | 98.5 | 95.5 | 100 | 97.8 | 93.3
6 | 4.5 | 25 | 100 | 97.8 | 94.3 | 100 | 98.9 | 94.9 | 100 | 100 | 98.4 | 100 | 100 | 98.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99 | 100 | 99.3 | 97.4 | 100 | 99 | 97 | 100 | 98.8 | 95.3
6 | 5 | 2 | 0.8 |  |  | 1.6 |  |  | 1.9 | 0.7 |  | 2.2 | 1.4 | 0.7 | 2.2 | 1.3 | 0.7 | 3 | 1.5 | 0.7 | 3 | 1.7 | 0.2 | 3.6 | 1.5 | 0.7 | 2.2 | 1.4 |  | 1.4 |  |  | 0.8 |  |  | 1.5 | 0.7
6 | 5 | 4 | 7.2 | 2.3 | 1.5 | 10.9 | 6.4 | 2.6 | 12.4 | 6.6 | 3.8 | 14.9 | 10 | 7.4 | 14.5 | 11.2 | 6.1 | 18.5 | 15.4 | 9.3 | 18.4 | 12.8 | 8.4 | 19.6 | 13 | 8 | 15.1 | 9.6 | 6.8 | 9.2 | 5.1 | 3.5 | 7 | 4.3 | 2.1 | 9.9 | 3.8 | 1.6
6 | 5 | 6 | 21.9 | 10.6 | 6.7 | 24 | 15.6 | 9.1 | 27 | 19.8 | 12.7 | 36.2 | 27.9 | 22.7 | 35.2 | 29.2 | 23.9 | 45.8 | 37.1 | 27.6 | 45 | 35.3 | 25.8 | 43 | 32.5 | 25.2 | 34 | 28.8 | 17.8 | 22.5 | 17.9 | 9.9 | 18.8 | 14 | 9.4 | 22 | 13.8 | 6.5
6 | 5 | 8 | 39.9 | 25.8 | 16 | 44.4 | 33.9 | 21.4 | 49 | 39.2 | 30 | 60.9 | 51.3 | 44 | 60.8 | 53.5 | 45.4 | 71.5 | 62.2 | 52.6 | 70.6 | 62.8 | 51.3 | 66.6 | 59.9 | 48.2 | 58.5 | 48.5 | 39.2 | 42.6 | 30.9 | 23.2 | 38.9 | 28.9 | 17.9 | 38.7 | 24.2 | 17
6 | 5 | 9 | 49.5 | 32.7 | 20.2 | 54.8 | 44 | 26.4 | 60.7 | 48.1 | 39.7 | 70.6 | 62.1 | 56.8 | 73.4 | 64.8 | 57.1 | 83.6 | 73.5 | 65.5 | 80.2 | 75 | 64.9 | 79.1 | 69.4 | 59 | 69.9 | 60.6 | 51.1 | 52.8 | 40.1 | 32.5 | 48.8 | 39.4 | 27.6 | 49 | 33.3 | 22.4
6 | 5 | 10 | 58.1 | 40.2 | 27.9 | 62.7 | 55.4 | 34.2 | 71.7 | 59.8 | 49.1 | 80.8 | 72.5 | 67.2 | 82.6 | 75.7 | 69.8 | 90.2 | 84.4 | 77.2 | 88.5 | 84 | 76.9 | 88 | 81.3 | 69.4 | 78.2 | 67.2 | 61 | 62 | 51.7 | 43 | 57.9 | 50.6 | 34.2 | 58.3 | 41.8 | 29.8
6 | 5 | 11 | 64.8 | 49.3 | 37.4 | 72.4 | 61.1 | 40 | 78.4 | 69.9 | 57.4 | 88.2 | 80.7 | 75 | 90.5 | 84.9 | 79.9 | 95.2 | 90.3 | 82.9 | 95.7 | 91.3 | 83.7 | 93 | 86.2 | 77.4 | 86.1 | 75 | 69.3 | 71.1 | 62.1 | 51.4 | 67.6 | 58.6 | 44 | 65.6 | 50.5 | 39.4
6 | 5 | 12 | 71.3 | 57.8 | 46.7 | 77.4 | 72.8 | 51.9 | 86.9 | 79.6 | 65.6 | 93.9 | 86.5 | 81.5 | 94.7 | 90.7 | 88.1 | 97.9 | 93.6 | 90 | 97.9 | 95.6 | 89.6 | 97 | 91.4 | 84.7 | 89.7 | 84 | 77.6 | 77.5 | 69.8 | 58.4 | 75.3 | 67.8 | 52.9 | 73.5 | 57.7 | 47.1
6 | 5 | 15 | 89.1 | 79 | 70.4 | 93.1 | 89.1 | 78.2 | 96.1 | 91.1 | 84.5 | 99.3 | 98.2 | 94.6 | 100 | 99.2 | 98.4 | 100 | 98.9 | 97.7 | 100 | 100 | 98.3 | 100 | 98.7 | 95.7 | 98.4 | 95 | 91.8 | 93 | 87.8 | 82.5 | 93.3 | 85.7 | 77.3 | 89.1 | 80.8 | 68.4
6 | 5 | 20 | 100 | 97.2 | 93.4 | 100 | 99 | 95.5 | 100 | 99.5 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.8 | 100 | 99.2 | 97.1 | 100 | 98.5 | 96.6 | 100 | 98.7 | 94
6 | 5 | 25 | 100 | 99.7 | 97.7 | 100 | 100 | 97.8 | 100 | 100 | 99.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99 | 100 | 100 | 98.2 | 100 | 100 | 97.9
12 | 0.25 | 2
12 | 0.25 | 4 | [12 empty] | 1.6 |  |  | 2.6 |  |  | 1.5 |  |  | 2.9
12 | 0.25 | 6 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 4.3 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 8 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 9 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 10 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 11 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 12 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 15 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 20 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.25 | 25 | [9 empty] | 1.1 |  |  | 2.6 |  |  | 5.6 |  |  | 1.5 |  |  | 3.1 | 1.5
12 | 0.5 | 2 | [15 empty] | 1.5
12 | 0.5 | 4 |  |  |  | 1.6 |  |  | 2.6 |  |  | 5.8 | 1.7 |  | 6.6 | 1.5 |  | 8.1 | 4.6 | 1.5 | 7.8 | 3.4 | 1.5 | 9.1 | 4.7 | 1.5 | 5.8 | 3.1 |  | 1.6 |  |  | 1.5 |  |  | 1.5
12 | 0.5 | 6 | 4 |  |  | 3.4 | 1.6 |  | 5.7 | 1.5 |  | 11.1 | 4.9 | 1.8 | 12.1 | 6 | 3.1 | 16.1 | 11.3 | 3.2 | 20.1 | 12.4 | 5.9 | 16.8 | 11 | 6.1 | 11.2 | 5.6 | 1.5 | 3.1 | 1.5 |  | 1.6 |  |  | 3.1
12 | 0.5 | 8 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16 | 9.3 | 4.5 | 19.5 | 13.1 | 4.9 | 26 | 15.5 | 7.7 | 20.4 | 12.5 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 9 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 12.5 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 10 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 11 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 12 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 15 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 20 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.5 | 25 | 4 |  |  | 5 | 1.6 |  | 7.1 | 1.6 |  | 14 | 6.4 | 3.2 | 16.4 | 9.5 | 4.6 | 19.5 | 13.1 | 4.9 | 26 | 15.7 | 7.7 | 20.4 | 14 | 6.7 | 13.8 | 6.4 | 1.5 | 4.1 | 1.5 |  | 2.6 |  |  | 3.1
12 | 0.75 | 2 | [15 empty] | 1.5 |  |  | 1.5 |  |  | 1
12 | 0.75 | 4 | 1.6 |  |  | 4.4 | 1.6 |  | 6 | 1.5 |  | 7.9 | 3.3 | 2.1 | 8.2 | 3.1 |  | 11.3 | 7.9 | 3.1 | 10.9 | 7.5 | 3 | 12.3 | 7.5 | 3.5 | 9 | 4.7 | 1.5 | 3.1 | 1.5 |  | 3.1 | 1.5 |  | 3.1 | 1.5
12 | 0.75 | 6 | 8.8 | 3 |  | 11.4 | 5.1 | 1.6 | 16.3 | 4.7 | 3 | 23.5 | 11.9 | 7.7 | 24.6 | 14.1 | 8.5 | 29.7 | 19.6 | 11.1 | 29.9 | 20.6 | 15.2 | 30.4 | 19 | 12.3 | 21 | 16.1 | 8.1 | 10.3 | 4.7 | 1.7 | 6.2 | 3.2 |  | 8.8 | 4.6 | 1.3
12 | 0.75 | 8 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 9.3 | 4.6 | 30.4 | 17.9 | 11.4 | 31.8 | 22.7 | 16.8 | 40.7 | 30.3 | 19.2 | 42.7 | 33.9 | 23.2 | 41.1 | 30.8 | 21.5 | 30.5 | 21 | 11.2 | 13.5 | 6.3 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 9 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 34.4 | 25.9 | 17.6 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.2 | 14 | 6.9 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 10 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.9 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 11 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.6 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 12 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.6 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 15 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.6 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 20 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.6 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 0.75 | 25 | 14.2 | 3.8 |  | 15.3 | 8.5 | 1.6 | 23.7 | 10.8 | 4.6 | 29.8 | 19.4 | 11.4 | 35.1 | 26.2 | 17.8 | 42.2 | 31.1 | 19.6 | 44.4 | 33.9 | 26.4 | 43.8 | 32.7 | 21.5 | 31.1 | 22.6 | 11.3 | 14 | 6.6 | 3.6 | 9.7 | 4.7 | 1.5 | 11 | 6.2 | 1.5
12 | 1 | 2 | [9 empty] | 1.1 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5
12 | 1 | 4 | 2.9 | 0.8 |  | 6.7 | 3.3 | 0.5 | 7.4 | 3 |  | 10.7 | 6.1 | 3.1 | 9.3 | 4.6 | 1.5 | 14.1 | 9.4 | 4.7 | 12.4 | 7.8 | 3.1 | 13.2 | 7.7 | 4.6 | 9.6 | 6.3 | 3.1 | 3.1 | 1.5 |  | 4.3 | 1.5 |  | 3.1 | 1.5
12 | 1 | 6 | 10.8 | 5.4 | 1.5 | 15.6 | 8.6 | 3.2 | 18.8 | 11 | 4.5 | 26.4 | 16.8 | 11.8 | 27.9 | 18.3 | 13.3 | 37.4 | 28.2 | 16.7 | 35.8 | 25.1 | 18.3 | 36.3 | 23.1 | 17.4 | 25.8 | 20.8 | 12.6 | 14.8 | 7.7 | 3.1 | 11.1 | 6.3 | 3.2 | 12 | 4.7 | 1.5
12 | 1 | 8 | 21.4 | 10.9 | 1.5 | 24 | 15.9 | 6.2 | 32.9 | 19.2 | 11.4 | 45.4 | 30.6 | 23.1 | 45.4 | 36.7 | 27.4 | 54.3 | 42.6 | 33.9 | 59.1 | 47.3 | 33.2 | 57.3 | 45.2 | 36.2 | 40.2 | 31.7 | 26 | 25.4 | 13.8 | 6.7 | 19.8 | 10.8 | 5 | 21.7 | 10.6 | 4.5
12 | 1 | 9 | 23 | 12.5 | 1.5 | 25.3 | 17.4 | 8.5 | 33.6 | 21.9 | 12.6 | 51.2 | 34.6 | 25.8 | 49.5 | 41.8 | 29.2 | 60.1 | 48.2 | 39.8 | 64.6 | 53 | 38.7 | 59.7 | 47.8 | 39.5 | 45.6 | 35.7 | 27.5 | 26.7 | 16.3 | 8.3 | 21 | 11.5 | 5.6 | 23.4 | 11 | 4.6
12 | 1 | 10 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.3 | 12.9 | 52.5 | 35.1 | 26.7 | 52 | 44.1 | 32 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 39.6 | 62 | 49.6 | 40.9 | 47.5 | 37.4 | 28.3 | 27.9 | 17.1 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1 | 11 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.8 | 12.9 | 52.6 | 35.1 | 26.8 | 52 | 44.5 | 32.5 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 41.3 | 62.2 | 49.6 | 41.1 | 47.5 | 37.4 | 28.3 | 27.9 | 17.2 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1 | 12 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.8 | 12.9 | 52.6 | 35.1 | 26.8 | 52 | 44.5 | 32.5 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 41.9 | 62.2 | 49.6 | 41.1 | 47.5 | 37.4 | 28.3 | 27.9 | 17.2 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1 | 15 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.8 | 12.9 | 52.6 | 35.1 | 26.8 | 52 | 44.5 | 32.5 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 42.4 | 62.2 | 49.6 | 41.1 | 47.5 | 37.4 | 28.3 | 27.9 | 17.2 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1 | 20 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.8 | 12.9 | 52.6 | 35.1 | 26.8 | 52 | 44.5 | 32.5 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 42.4 | 62.2 | 49.6 | 41.1 | 47.5 | 37.4 | 28.3 | 27.9 | 17.2 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1 | 25 | 23 | 12.5 | 1.9 | 26.7 | 17.6 | 8.5 | 35 | 23.8 | 12.9 | 52.6 | 35.1 | 26.8 | 52 | 44.5 | 32.5 | 61.6 | 51.7 | 41.1 | 67.4 | 53.9 | 42.4 | 62.2 | 49.6 | 41.1 | 47.5 | 37.4 | 28.3 | 27.9 | 17.2 | 8.3 | 21.4 | 11.5 | 5.6 | 23.4 | 11 | 4.5
12 | 1.25 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5
12 | 1.25 | 4 | 4 | 1.5 |  | 6.8 | 3.3 | 0.5 | 7.7 | 3.1 |  | 10.7 | 6.3 | 3.2 | 10.7 | 6 | 3 | 14.4 | 11 | 5.1 | 13.4 | 9.1 | 3.1 | 13.8 | 9 | 4.6 | 11.1 | 6.4 | 3.1 | 6.3 | 3 |  | 4.7 | 1.5 |  | 4.5 | 1.6
12 | 1.25 | 6 | 16.6 | 6 | 2.9 | 17.7 | 8.8 | 4.9 | 21.4 | 12.6 | 5.2 | 28.6 | 19.3 | 14.5 | 31 | 21.4 | 16.3 | 39.7 | 31.4 | 20.6 | 39 | 29.2 | 20.9 | 37 | 26.5 | 18.3 | 27.1 | 22.4 | 12.8 | 16.8 | 10.8 | 4.6 | 12.9 | 8.1 | 4.7 | 12.6 | 7.7 | 3
12 | 1.25 | 8 | 30.2 | 15.5 | 5.3 | 30.2 | 22.3 | 11 | 39.9 | 27.6 | 15.9 | 52.8 | 37.8 | 30.9 | 51.3 | 42.9 | 36.3 | 63.5 | 52.1 | 38 | 63.2 | 52.2 | 39.7 | 61 | 50.1 | 42.1 | 49 | 37.5 | 29 | 31.9 | 18.5 | 13.1 | 24.9 | 17.6 | 8.1 | 29.3 | 14.1 | 6.6
12 | 1.25 | 9 | 33.4 | 19.5 | 6.7 | 35.7 | 26.2 | 12.7 | 42.4 | 34.3 | 20.6 | 58.7 | 45.7 | 36.2 | 60.9 | 52.4 | 44.9 | 71.7 | 60.6 | 50.3 | 72.6 | 64 | 50.5 | 70.2 | 58.6 | 48.3 | 57.2 | 46.4 | 34.5 | 39 | 24.7 | 17.2 | 31.8 | 20.7 | 11.5 | 32.1 | 17.6 | 8.6
12 | 1.25 | 10 | 36.2 | 20 | 8 | 40.2 | 28.1 | 13.2 | 47.6 | 37.8 | 22.7 | 63.6 | 49.4 | 41.7 | 67.2 | 58.1 | 50 | 75.7 | 66 | 55.2 | 77.9 | 70.3 | 56.6 | 73 | 62.9 | 53.3 | 61.2 | 50.3 | 37.2 | 40.5 | 28.9 | 18.8 | 33.9 | 22.5 | 11.5 | 33.7 | 19.5 | 12.7
12 | 1.25 | 11 | 36.2 | 20 | 8 | 40.9 | 28.1 | 13.3 | 47.6 | 39.5 | 22.7 | 67.7 | 51 | 41.9 | 69.2 | 58.7 | 53.3 | 77.8 | 67.4 | 57.1 | 79.8 | 72.7 | 57.1 | 74.6 | 66.1 | 55.4 | 63 | 51.1 | 38.5 | 40.8 | 30.4 | 19.1 | 34.4 | 23.9 | 11.5 | 34 | 19.5 | 12.6
12 | 1.25 | 12 | 36.2 | 20 | 8 | 40.8 | 28.1 | 13.3 | 48.2 | 39.5 | 22.7 | 67.7 | 51 | 41.9 | 70 | 59.1 | 53.3 | 77.8 | 67.6 | 57.2 | 79.7 | 72.8 | 57.4 | 74.6 | 66.5 | 55.5 | 63 | 51.1 | 38.5 | 41.1 | 30.5 | 19.1 | 34.7 | 23.9 | 11.5 | 34 | 19.5 | 12.6
12 | 1.25 | 15 | 36.2 | 20 | 8 | 40.8 | 28.1 | 13.3 | 49.2 | 39.5 | 22.7 | 67.7 | 51 | 41.9 | 69.8 | 59.1 | 53.4 | 77.8 | 67.6 | 57.2 | 79.7 | 72.8 | 57.8 | 74.6 | 66.5 | 55.5 | 63 | 51.1 | 38.5 | 41.1 | 30.5 | 19.1 | 34.7 | 23.9 | 11.5 | 34 | 19.5 | 12.6
12 | 1.25 | 20 | 36.2 | 20 | 8 | 40.8 | 28.1 | 13.3 | 49.2 | 39.5 | 22.7 | 67.7 | 51 | 41.9 | 69.8 | 59.1 | 53.4 | 77.8 | 67.6 | 57.2 | 79.7 | 72.8 | 57.8 | 74.6 | 66.5 | 55.5 | 63 | 51.1 | 38.5 | 41.1 | 30.5 | 19.1 | 34.7 | 23.9 | 11.5 | 34 | 19.5 | 12.6
12 | 1.25 | 25 | 36.2 | 20 | 8 | 40.8 | 28.1 | 13.3 | 49.2 | 39.5 | 22.7 | 67.7 | 51 | 41.9 | 69.8 | 59.1 | 53.4 | 77.8 | 67.6 | 57.2 | 79.7 | 72.8 | 57.8 | 74.6 | 66.5 | 55.5 | 63 | 51.1 | 38.5 | 41.1 | 30.5 | 19.1 | 34.7 | 23.9 | 11.5 | 34 | 19.5 | 12.6
12 | 1.5 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5
12 | 1.5 | 4 | 5.6 | 1.5 |  | 7.9 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.3 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 13.8 | 9.1 | 4.6 | 11.1 | 6.4 | 3.1 | 7.1 | 3 | 1.5 | 4.7 | 1.5 |  | 7 | 1.6
12 | 1.5 | 6 | 18 | 7.7 | 2.9 | 19.3 | 10.3 | 4.9 | 23.2 | 13.8 | 7.6 | 29.9 | 20.6 | 16.2 | 31 | 23.8 | 17.1 | 40.6 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 37.4 | 26.6 | 18.7 | 28 | 23.8 | 12.8 | 18.3 | 12 | 5.6 | 14.4 | 9.6 | 5.2 | 13.9 | 9.3 | 3.1
12 | 1.5 | 8 | 31.6 | 17.6 | 9.1 | 37.1 | 24 | 13.1 | 42.1 | 29.6 | 19.5 | 56.9 | 41 | 34.8 | 54.3 | 46.2 | 38.8 | 67.7 | 54.9 | 43.8 | 64.7 | 55.6 | 43.4 | 62.6 | 53.8 | 43.5 | 52.3 | 40.4 | 31.6 | 36.4 | 21.8 | 17.2 | 29.6 | 21 | 12 | 31.9 | 17.2 | 9.6
12 | 1.5 | 9 | 36.7 | 24.6 | 10.8 | 41.4 | 31.5 | 16.3 | 51.2 | 37.8 | 26.8 | 63.8 | 51 | 44.5 | 65 | 58.3 | 48.6 | 77.1 | 64.9 | 56.8 | 75.8 | 69.5 | 56.9 | 72.4 | 63.7 | 51.2 | 61.9 | 50.6 | 40.3 | 43.8 | 30.6 | 21.9 | 36.9 | 27.4 | 17.3 | 38.9 | 23.7 | 13.2
12 | 1.5 | 10 | 40.8 | 28.2 | 14.9 | 49.8 | 38.5 | 21.9 | 56.7 | 45.3 | 35.2 | 70.6 | 57.8 | 51 | 73.9 | 65.9 | 57.3 | 83.1 | 77.1 | 67.6 | 82.5 | 78.1 | 66 | 81.3 | 70.7 | 59.4 | 66.3 | 59.2 | 47.1 | 48.7 | 36.2 | 26.6 | 44.1 | 29.3 | 19.4 | 41.2 | 27.4 | 16.4
12 | 1.5 | 11 | 43.6 | 30.6 | 16.2 | 53.5 | 40.5 | 21.9 | 61.2 | 49.7 | 36.6 | 76.4 | 63.1 | 53.8 | 79.9 | 71.4 | 63.2 | 86.4 | 80.7 | 67.5 | 88.8 | 82.4 | 69.9 | 84.3 | 76.1 | 64.6 | 71.6 | 61.8 | 50 | 52.4 | 41.8 | 29 | 48.3 | 32.8 | 21.9 | 45 | 28.6 | 18.2
12 | 1.5 | 12 | 44.8 | 30.6 | 17.2 | 54.1 | 42.1 | 22.4 | 61.9 | 49.6 | 36.6 | 77 | 63.6 | 55.9 | 80.5 | 73.1 | 65.8 | 86.9 | 81.1 | 69.9 | 90.2 | 83.3 | 70.9 | 84.6 | 76.1 | 66.4 | 71.6 | 63.9 | 49.8 | 53.7 | 42.3 | 29.6 | 49.8 | 32.8 | 21.6 | 45.3 | 28.6 | 18.7
12 | 1.5 | 15 | 44.8 | 30.6 | 17.2 | 54.1 | 42.1 | 22.4 | 61.9 | 49.6 | 36.6 | 78.2 | 63.5 | 55.8 | 80.5 | 73.1 | 65.8 | 86.9 | 81.3 | 69.8 | 90.2 | 83.3 | 70.9 | 85.4 | 76.1 | 66.4 | 71.6 | 63.8 | 49.8 | 53.7 | 42.3 | 30.4 | 49.7 | 32.8 | 22.2 | 45.3 | 28.8 | 18.7
12 | 1.5 | 20 | 44.8 | 30.6 | 17.2 | 54.1 | 42.1 | 22.4 | 61.9 | 49.6 | 36.6 | 78.2 | 63.5 | 55.8 | 80.5 | 73.1 | 65.8 | 86.9 | 81.3 | 69.8 | 90.2 | 83.3 | 70.9 | 85.4 | 76.1 | 66.4 | 71.6 | 63.8 | 49.8 | 53.7 | 42.3 | 30.4 | 49.7 | 32.8 | 22.2 | 45.3 | 28.8 | 18.7
12 | 1.5 | 25 | 44.8 | 30.6 | 17.2 | 54.1 | 42.1 | 22.4 | 61.9 | 49.6 | 36.6 | 78.2 | 63.5 | 55.8 | 80.5 | 73.1 | 65.8 | 86.9 | 81.3 | 69.8 | 90.2 | 83.3 | 70.9 | 85.4 | 76.1 | 66.4 | 71.6 | 63.8 | 49.8 | 53.7 | 42.3 | 30.4 | 49.7 | 32.8 | 22.2 | 45.3 | 28.8 | 18.7
12 | 1.75 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5
12 | 1.75 | 4 | 5.7 | 1.5 |  | 7.9 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.1 | 7.1 | 3 | 1.5 | 4.7 | 1.5 |  | 7.4 | 3
12 | 1.75 | 6 | 18.6 | 7.7 | 3 | 19.3 | 11.9 | 4.9 | 23.2 | 15.3 | 7.9 | 31.2 | 21.5 | 17.3 | 31 | 24.5 | 17.1 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 26.6 | 19.3 | 28.1 | 23.8 | 13.2 | 18.6 | 12.5 | 6.5 | 15.4 | 11.1 | 6.3 | 15.9 | 10.8 | 3.7
12 | 1.75 | 8 | 34 | 19.1 | 10.6 | 39 | 28.2 | 14.8 | 42.8 | 32.4 | 20.8 | 57.7 | 44 | 36.7 | 55.3 | 48 | 39.4 | 67.7 | 56.5 | 45.5 | 65.7 | 57.8 | 43.4 | 62.6 | 53.6 | 43.5 | 53.4 | 41.8 | 33.2 | 36.9 | 24.2 | 19.6 | 31.5 | 23.2 | 12.6 | 33 | 20 | 11.3
12 | 1.75 | 9 | 43.1 | 26.6 | 15.1 | 47.4 | 35.6 | 20 | 54 | 40.9 | 32 | 66.8 | 54.9 | 48.5 | 66.8 | 61.4 | 50.5 | 79 | 68.1 | 60 | 76.3 | 71.1 | 59.1 | 73 | 63.7 | 53.3 | 65.1 | 52.9 | 44.3 | 46.1 | 34 | 24.9 | 41.8 | 29.7 | 19.6 | 40.8 | 26.2 | 14.9
12 | 1.75 | 10 | 47.3 | 32.4 | 20.1 | 57.2 | 41.8 | 26.8 | 66.9 | 52 | 40.2 | 74.6 | 63.3 | 58.3 | 78.6 | 69.5 | 63 | 84.7 | 79.7 | 71.4 | 86 | 79.2 | 71.1 | 82.9 | 72.7 | 63.2 | 69.3 | 61.7 | 53.6 | 54.3 | 41.4 | 30.2 | 47.6 | 37.4 | 25 | 46.6 | 31.6 | 20.3
12 | 1.75 | 11 | 51.5 | 37.8 | 26.9 | 62.8 | 50.6 | 28.9 | 73.4 | 57.4 | 44.6 | 84.2 | 71.7 | 63.2 | 84.4 | 76.2 | 70 | 90.1 | 84.9 | 74.9 | 92.6 | 86 | 78 | 87.8 | 79.6 | 70.5 | 77.4 | 68.2 | 57.8 | 61.4 | 50.4 | 38.3 | 53.7 | 42.8 | 28.6 | 54.2 | 34.8 | 25.9
12 | 1.75 | 12 | 53.2 | 40.1 | 28.5 | 65.3 | 54.8 | 30.3 | 76.4 | 59 | 48.6 | 85.2 | 74.9 | 65.3 | 87.9 | 81.6 | 73.2 | 92 | 86.7 | 79 | 93.8 | 87.4 | 80.5 | 91.6 | 81 | 72.8 | 79 | 70.4 | 61 | 67.1 | 52.2 | 41.7 | 57.5 | 45.6 | 28.6 | 55.5 | 36.4 | 26
12 | 1.75 | 15 | 54.5 | 40.1 | 29.8 | 65.4 | 56 | 30.3 | 77.2 | 59.1 | 50.5 | 85.7 | 75.7 | 66.9 | 88.9 | 83.3 | 75.9 | 93 | 87.9 | 80.4 | 95.1 | 87.8 | 81.2 | 91.6 | 82.8 | 74 | 80.7 | 71.4 | 63 | 67.7 | 54.4 | 43.4 | 59 | 45.4 | 31.2 | 56.3 | 36.4 | 26
12 | 1.75 | 20 | 54.5 | 40.1 | 29.8 | 65.4 | 56 | 30.3 | 77.2 | 59.1 | 50.5 | 85.7 | 75.7 | 66.9 | 88.9 | 83.3 | 75.9 | 93 | 87.9 | 80.4 | 95.1 | 87.8 | 81.2 | 91.6 | 82.8 | 74 | 80.7 | 71.4 | 63 | 67.7 | 54.4 | 43.4 | 59 | 45.4 | 31.2 | 56.3 | 36.4 | 26
12 | 1.75 | 25 | 54.5 | 40.1 | 29.8 | 65.4 | 56 | 30.3 | 77.2 | 59.1 | 50.5 | 85.7 | 75.7 | 66.9 | 88.9 | 83.3 | 75.9 | 93 | 87.9 | 80.4 | 95.1 | 87.8 | 81.2 | 91.6 | 82.8 | 74 | 80.7 | 71.4 | 63 | 67.7 | 54.4 | 43.4 | 59 | 45.4 | 31.2 | 56.3 | 36.4 | 26
12 | 2 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 2 | 4 | 5.7 | 1.5 |  | 7.9 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.1 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.4 | 3
12 | 2 | 6 | 18.6 | 7.7 | 3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.1 | 6.3 | 17.8 | 10.8 | 3.7
12 | 2 | 8 | 35 | 19.5 | 12.6 | 39.8 | 28.3 | 17.2 | 43.6 | 33.2 | 22.3 | 57.7 | 45.8 | 36.7 | 56.6 | 48 | 40.6 | 67.7 | 56.9 | 45.5 | 66.2 | 57.8 | 44.3 | 62.6 | 53.6 | 43.5 | 53.9 | 42.2 | 33.2 | 38.3 | 26.5 | 19.6 | 32 | 24.3 | 13.7 | 33.5 | 20.4 | 11.5
12 | 2 | 9 | 44.5 | 27.8 | 15.2 | 48 | 37.5 | 20.7 | 55.4 | 42.5 | 33.1 | 67.7 | 56.5 | 50.4 | 68.4 | 62.2 | 52.1 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 59.7 | 73.9 | 65.1 | 53.4 | 66.5 | 55 | 44.8 | 46.7 | 34 | 25.4 | 43.6 | 32.4 | 20.9 | 41.3 | 27.6 | 16.5
12 | 2 | 10 | 50.9 | 35.9 | 22.3 | 57.5 | 47 | 27.4 | 66.9 | 53.5 | 40.8 | 76.1 | 66.9 | 60.5 | 78.9 | 72.3 | 63.8 | 86.4 | 81.3 | 72.9 | 87.6 | 79.7 | 73 | 83.8 | 75.8 | 64.3 | 73.1 | 63.1 | 55 | 54.4 | 44.2 | 34.7 | 51 | 39.4 | 27.9 | 49.4 | 32.1 | 22.4
12 | 2 | 11 | 56.3 | 39.7 | 28.8 | 65.9 | 55.5 | 30.7 | 74.7 | 62 | 49.7 | 85.9 | 73.9 | 66.3 | 86.6 | 79.4 | 74.7 | 92.1 | 87.1 | 79 | 94.2 | 88 | 81.2 | 91 | 81.5 | 72.1 | 79.8 | 70.3 | 59.5 | 63.1 | 53.8 | 41.2 | 59 | 48.1 | 35.3 | 55.9 | 38.7 | 29.2
12 | 2 | 12 | 61.4 | 44.5 | 34.3 | 71.5 | 61.6 | 34.6 | 79.9 | 67.5 | 51.4 | 89.7 | 80 | 69.7 | 91 | 85.3 | 80.1 | 95.1 | 89.9 | 85.3 | 96.3 | 91.8 | 82.2 | 93.9 | 84.8 | 77.2 | 84.1 | 74.4 | 66.1 | 70.7 | 59.1 | 49 | 64.9 | 54.7 | 36.7 | 61.6 | 42.9 | 31.8
12 | 2 | 15 | 63.5 | 47.2 | 37.8 | 75.9 | 65.5 | 39.6 | 82.2 | 70.6 | 58.5 | 90.7 | 83.6 | 72.1 | 93.2 | 88.8 | 84.3 | 95.8 | 92.1 | 87 | 98.4 | 94.6 | 86.7 | 95.6 | 86.8 | 81.9 | 85.8 | 80.3 | 69 | 75.7 | 63.7 | 54.8 | 68.6 | 56.7 | 41.1 | 64.1 | 45.7 | 32.7
12 | 2 | 20 | 63.5 | 47.2 | 37.8 | 75.9 | 65.5 | 39.6 | 82.2 | 70.6 | 58.5 | 90.7 | 83.6 | 72.1 | 93.2 | 88.8 | 84.3 | 95.8 | 92.1 | 87 | 98.4 | 94.6 | 86.7 | 95.6 | 86.8 | 81.9 | 86 | 80.3 | 69 | 75.7 | 63.7 | 54.9 | 68.6 | 56.7 | 41.1 | 64.1 | 46.1 | 32.7
12 | 2 | 25 | 63.5 | 47.2 | 37.8 | 75.9 | 65.5 | 39.6 | 82.2 | 70.6 | 58.5 | 90.7 | 83.6 | 72.1 | 93.2 | 88.8 | 84.3 | 95.8 | 92.1 | 87 | 98.4 | 94.6 | 86.7 | 95.6 | 86.8 | 81.9 | 86 | 80.3 | 69 | 75.7 | 63.7 | 54.9 | 68.6 | 56.7 | 41.1 | 64.1 | 46.1 | 32.7
12 | 2.25 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 2.25 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 2.25 | 6 | 18.5 | 7.7 | 3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.3 | 10.8 | 4.1
12 | 2.25 | 8 | 35.6 | 20.3 | 13.3 | 40.1 | 29.5 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.7 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 57.8 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.9
12 | 2.25 | 9 | 44.5 | 29 | 16.6 | 49.2 | 37.9 | 21.5 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.4 | 68.7 | 62.2 | 52.3 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 59.7 | 73.9 | 65.1 | 53.7 | 66.8 | 55.6 | 44.8 | 46.7 | 34 | 26.6 | 43.8 | 33.1 | 22.4 | 43.3 | 27.6 | 17.5
12 | 2.25 | 10 | 51.2 | 35.9 | 22.7 | 58.7 | 48.2 | 28.2 | 68.3 | 55.8 | 42.9 | 76.1 | 68.1 | 61.7 | 78.9 | 72.3 | 64.7 | 87 | 81.5 | 74.4 | 87.6 | 80.5 | 73 | 84.3 | 75.7 | 64.4 | 73.3 | 63.2 | 56.1 | 56.1 | 44.5 | 36.6 | 51.3 | 41.7 | 28.4 | 49.7 | 36.4 | 24.9
12 | 2.25 | 11 | 57.9 | 42.7 | 29.1 | 67.8 | 55.7 | 32.6 | 75.9 | 65.3 | 52.1 | 86.1 | 74.9 | 68.6 | 87.3 | 80 | 75.5 | 92.5 | 87.9 | 80.6 | 94.2 | 88 | 81.6 | 91.5 | 82.5 | 73.2 | 82.6 | 70.7 | 63.1 | 64.9 | 55.2 | 44.5 | 59.2 | 49 | 36.7 | 58.1 | 41.9 | 30.7
12 | 2.25 | 12 | 64.5 | 48.1 | 37.6 | 72.6 | 64.7 | 43 | 81.2 | 70.4 | 56 | 91.5 | 82.5 | 73.8 | 91.2 | 87 | 82.9 | 96.2 | 91.3 | 86.8 | 96.3 | 93.8 | 84 | 96.2 | 87.2 | 81.1 | 86.5 | 79 | 69.1 | 72.9 | 60.8 | 51.7 | 69.2 | 56.7 | 38.8 | 64.4 | 46.8 | 37.5
12 | 2.25 | 15 | 72.1 | 57 | 45.1 | 80.7 | 71 | 50.3 | 88.5 | 78.6 | 64.6 | 95.6 | 89.4 | 80.5 | 95.7 | 92.9 | 89.6 | 98.8 | 94.2 | 91.4 | 99.8 | 96.5 | 91.6 | 97.7 | 91.5 | 85.5 | 91 | 85.7 | 78.7 | 80.5 | 72 | 64 | 78.7 | 64 | 48 | 73.4 | 57.3 | 43.2
12 | 2.25 | 20 | 72.5 | 57.5 | 45.1 | 81.4 | 72 | 50.3 | 89.2 | 78.5 | 64.6 | 95.6 | 89.4 | 80.5 | 95.7 | 92.9 | 89.6 | 98.8 | 94.2 | 91.4 | 99.8 | 96.4 | 91.6 | 97.7 | 91.5 | 85.9 | 90.9 | 85.8 | 78.7 | 80.3 | 72 | 64 | 78.7 | 64 | 48.8 | 73.4 | 57.3 | 44.4
12 | 2.25 | 25 | 72.5 | 57.5 | 45.1 | 81.4 | 72 | 50.3 | 89.2 | 78.5 | 64.6 | 95.6 | 89.4 | 80.5 | 95.7 | 92.9 | 89.6 | 98.8 | 94.2 | 91.4 | 99.8 | 96.4 | 91.6 | 97.7 | 91.5 | 85.9 | 90.9 | 85.8 | 78.7 | 80.3 | 72 | 64 | 78.7 | 64 | 48.8 | 73.4 | 57.3 | 44.4
12 | 2.75 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 2.75 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 2.75 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 2.75 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 2.75 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 2.75 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 44.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 51.5 | 42.6 | 28.6 | 51.3 | 38 | 24.9
12 | 2.75 | 11 | 59.8 | 44.6 | 30.8 | 69 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 70.6 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.7 | 72.2 | 64.3 | 66.7 | 56.9 | 47.4 | 61.6 | 55.6 | 37.6 | 59.2 | 45 | 32.4
12 | 2.75 | 12 | 66.7 | 51.2 | 43.9 | 74.5 | 66.8 | 47.5 | 84.1 | 73.9 | 58 | 93.2 | 83.6 | 77.9 | 92.7 | 88.3 | 84.1 | 96.4 | 91.5 | 88.2 | 96.6 | 94.5 | 86.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 72.7 | 74.8 | 65.1 | 53.1 | 72.3 | 61.3 | 43.6 | 68.1 | 51.7 | 42.7
12 | 2.75 | 15 | 81.6 | 67.3 | 56.7 | 87.9 | 81.7 | 64.2 | 92.1 | 85.6 | 74.2 | 97.8 | 94.3 | 89.3 | 99.2 | 97.7 | 95.1 | 100 | 97.4 | 95.3 | 100 | 98.1 | 95.8 | 100 | 96.6 | 92.1 | 95.8 | 91.3 | 85.7 | 89.1 | 80 | 74.5 | 86.1 | 77.6 | 61.7 | 82.1 | 68 | 57.1
12 | 2.75 | 20 | 86.9 | 71.1 | 60.7 | 89.7 | 83 | 65.6 | 94.4 | 88.3 | 76.4 | 98.6 | 95.3 | 89.4 | 100 | 98 | 95.5 | 100 | 98.1 | 95.6 | 100 | 98.7 | 96.1 | 100 | 96.9 | 93.6 | 96.5 | 93.2 | 88.5 | 90.5 | 82 | 76.5 | 88 | 77.9 | 65 | 83.3 | 69.8 | 61.9
12 | 2.75 | 25 | 86.9 | 71.1 | 60.7 | 89.7 | 83 | 65.6 | 94.4 | 88.3 | 76.4 | 98.6 | 95.3 | 89.4 | 100 | 98 | 95.5 | 100 | 98.1 | 95.6 | 100 | 98.7 | 96.1 | 100 | 96.9 | 93.6 | 96.5 | 93.2 | 88.5 | 90.5 | 82 | 76.5 | 88 | 77.9 | 65 | 83.3 | 69.8 | 61.9
12 | 3 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 3 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 3 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 3 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 3 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 3 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 44.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 52 | 43.8 | 28.6 | 51.3 | 38 | 24.9
12 | 3 | 11 | 61.3 | 45.2 | 30.8 | 69 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 71.1 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.9 | 72.2 | 64.3 | 66.7 | 56.9 | 47.4 | 61.6 | 56.3 | 37.6 | 60.1 | 46 | 32.4
12 | 3 | 12 | 67.4 | 53 | 43.9 | 74.5 | 66.8 | 48 | 84.7 | 75.5 | 58 | 93.2 | 83.6 | 78.1 | 93.3 | 88.3 | 84.7 | 96.6 | 91.9 | 88.2 | 96.6 | 94.5 | 87.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 73.5 | 74.8 | 65.6 | 53.3 | 72.3 | 61.7 | 44.5 | 69.5 | 51.7 | 42.7
12 | 3 | 15 | 83.5 | 71.2 | 61.3 | 89.8 | 85.1 | 69.4 | 94.2 | 87.4 | 78.4 | 99 | 94.9 | 90.4 | 99.9 | 98.5 | 96.6 | 100 | 98.1 | 95.5 | 100 | 98.9 | 96.5 | 100 | 97.6 | 93.6 | 96.9 | 92.2 | 88.5 | 90.5 | 82 | 76.5 | 88.6 | 77.6 | 66.7 | 83.8 | 73.3 | 60.9
12 | 3 | 20 | 89.9 | 75.8 | 65.2 | 94.4 | 87.4 | 73.5 | 96.2 | 90.7 | 82 | 100 | 96.7 | 92.5 | 100 | 100 | 97.4 | 100 | 98.3 | 96.5 | 100 | 100 | 97 | 100 | 98.3 | 95.9 | 97.6 | 95.4 | 89.1 | 93.8 | 87.2 | 81.9 | 91.5 | 84.4 | 72.5 | 85.9 | 76.6 | 68.1
12 | 3 | 25 | 89.9 | 75.8 | 65.2 | 94.4 | 87.4 | 73.5 | 96.2 | 90.7 | 82 | 100 | 96.7 | 92.5 | 100 | 100 | 97.4 | 100 | 98.3 | 96.5 | 100 | 100 | 97 | 100 | 98.3 | 95.9 | 97.6 | 95.4 | 89.1 | 93.8 | 87.2 | 81.9 | 91.5 | 84.4 | 72.5 | 85.9 | 76.6 | 68.1
12 | 3.5 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 3.5 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 3.5 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 3.5 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 3.5 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 3.5 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 44.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 52 | 43.8 | 28.6 | 51.3 | 38 | 24.9
12 | 3.5 | 11 | 61.3 | 45.2 | 31 | 69.5 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 71.1 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.9 | 72.2 | 64.3 | 66.7 | 56.9 | 48.5 | 61.6 | 56.3 | 37.6 | 60.5 | 46 | 33.5
12 | 3.5 | 12 | 67.4 | 53 | 43.9 | 74.5 | 66.8 | 48.5 | 84.7 | 75.5 | 60.3 | 93.2 | 83.6 | 79.4 | 93.3 | 88.3 | 84.7 | 96.9 | 91.9 | 88.2 | 96.6 | 94.5 | 87.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 73.6 | 75.5 | 65.6 | 53.3 | 72.3 | 61.7 | 45.9 | 69.5 | 51.7 | 43.1
12 | 3.5 | 15 | 86.2 | 75.1 | 64.3 | 90.1 | 86.3 | 71.8 | 94.5 | 89.1 | 81.8 | 99.3 | 96.4 | 92.2 | 100 | 98.8 | 97.5 | 100 | 98.2 | 96.1 | 100 | 100 | 97.3 | 100 | 97.8 | 94.9 | 97.9 | 92.9 | 88.8 | 92 | 84.5 | 78.8 | 90.3 | 81.1 | 71 | 85.2 | 74.9 | 63.5
12 | 3.5 | 20 | 93.2 | 88.2 | 78.5 | 98.2 | 92.7 | 84.3 | 99.8 | 95.2 | 90 | 100 | 100 | 95.6 | 100 | 100 | 100 | 100 | 100 | 97.6 | 100 | 100 | 99.1 | 100 | 100 | 98.2 | 100 | 97.9 | 93.4 | 97.8 | 93.3 | 88.3 | 96.1 | 90.8 | 84.1 | 95.1 | 87.4 | 79.4
12 | 3.5 | 25 | 93.3 | 88.8 | 78.5 | 98.5 | 92.7 | 84.3 | 99.8 | 95.2 | 90 | 100 | 100 | 95.6 | 100 | 100 | 100 | 100 | 100 | 97.6 | 100 | 100 | 99.1 | 100 | 100 | 98.2 | 100 | 97.9 | 93.4 | 97.8 | 93.3 | 88.3 | 96.5 | 90.8 | 84.1 | 95 | 87.4 | 79.7
12 | 4 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 4 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 4 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 4 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 4 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 4 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 45.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 52 | 43.8 | 28.6 | 51.3 | 38 | 24.9
12 | 4 | 11 | 61.3 | 45.2 | 31 | 69.5 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 71.1 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.9 | 72.2 | 64.3 | 66.7 | 56.9 | 48.5 | 61.6 | 56.3 | 37.6 | 60.5 | 46 | 33.6
12 | 4 | 12 | 67.4 | 53 | 43.9 | 74.5 | 66.8 | 48.5 | 84.7 | 75.5 | 61.2 | 93.2 | 83.6 | 79.4 | 93.3 | 88.3 | 84.7 | 96.9 | 91.9 | 88.2 | 96.6 | 94.5 | 87.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 73.6 | 75.5 | 65.6 | 53.3 | 72.3 | 61.7 | 47.1 | 69.8 | 51.7 | 43.1
12 | 4 | 15 | 86.4 | 75.5 | 66.9 | 91.7 | 86.3 | 74.6 | 95 | 89.8 | 81.8 | 99.3 | 96.7 | 92.8 | 100 | 98.8 | 97.5 | 100 | 98.3 | 96.4 | 100 | 100 | 97.5 | 100 | 97.8 | 94.9 | 97.9 | 93.3 | 88.8 | 92 | 85.8 | 79.4 | 91.1 | 81.1 | 72.5 | 86.4 | 75.3 | 63.6
12 | 4 | 20 | 97.6 | 93.5 | 87.4 | 99.2 | 95.5 | 89.9 | 100 | 98.7 | 95.7 | 100 | 100 | 97.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99.7 | 96.8 | 100 | 96.8 | 94 | 98.8 | 95.8 | 91.8 | 99.1 | 93.7 | 87.6
12 | 4 | 25 | 97.7 | 93.4 | 87.5 | 99.8 | 96.1 | 90.1 | 100 | 99.1 | 95.8 | 100 | 100 | 97.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 96.8 | 100 | 96.8 | 94 | 99 | 96 | 91.9 | 99 | 94 | 89.2
12 | 4.5 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 4.5 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 4.5 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 4.5 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 4.5 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 4.5 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 45.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 52 | 43.8 | 28.6 | 51.3 | 38 | 24.9
12 | 4.5 | 11 | 61.3 | 45.2 | 31 | 69.5 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 71.1 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.9 | 72.2 | 64.3 | 66.7 | 56.9 | 48.5 | 61.6 | 56.3 | 37.6 | 60.5 | 46 | 33.6
12 | 4.5 | 12 | 67.4 | 53 | 43.9 | 74.5 | 66.8 | 48.5 | 84.7 | 75.5 | 61.2 | 93.2 | 83.6 | 79.4 | 93.3 | 88.3 | 84.7 | 96.9 | 91.9 | 88.2 | 96.6 | 94.5 | 87.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 73.6 | 75.5 | 65.6 | 53.3 | 72.3 | 61.7 | 47.1 | 69.8 | 51.7 | 43.1
12 | 4.5 | 15 | 86.4 | 75.5 | 66.9 | 91.7 | 86.6 | 74.6 | 95.1 | 89.8 | 82.4 | 99.3 | 96.9 | 93.1 | 100 | 98.8 | 97.5 | 100 | 98.3 | 96.5 | 100 | 100 | 97.5 | 100 | 97.8 | 94.9 | 97.9 | 93.8 | 88.8 | 92.2 | 85.8 | 80.1 | 91.6 | 83.3 | 73 | 86.8 | 77.7 | 63.6
12 | 4.5 | 20 | 99.1 | 96.2 | 90.4 | 100 | 98.1 | 92.9 | 100 | 99.5 | 97.2 | 100 | 100 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.5 | 100 | 98.3 | 95.5 | 100 | 97.6 | 93.9 | 100 | 97 | 90.6
12 | 4.5 | 25 | 100 | 97.3 | 93.9 | 100 | 98.5 | 93.4 | 100 | 100 | 98 | 100 | 100 | 98.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.9 | 100 | 99.3 | 96.7 | 100 | 98.8 | 96.1 | 100 | 98.4 | 94.1
12 | 5 | 2 | [9 empty] | 1.5 |  |  | 1 |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 | [11 empty] | 1
12 | 5 | 4 | 5.7 | 1.5 |  | 8.1 | 3.3 | 1.6 | 7.9 | 3.1 | 1.5 | 10.7 | 6.4 | 3.3 | 11.1 | 6.7 | 3.1 | 14.4 | 11 | 6.1 | 13.4 | 9.1 | 3.5 | 14.7 | 9.1 | 4.6 | 11.1 | 6.4 | 3.2 | 7.6 | 3 | 1.5 | 4.7 | 1.5 |  | 7.6 | 3
12 | 5 | 6 | 19.2 | 7.7 | 3.3 | 21.4 | 11.9 | 4.9 | 23.2 | 15.3 | 8.1 | 31.2 | 21.5 | 17.3 | 31 | 24.6 | 17.4 | 40.5 | 31.4 | 21 | 39.3 | 29.4 | 20.9 | 38 | 28.1 | 19.3 | 29 | 23.8 | 13.2 | 18.6 | 14 | 6.4 | 15.4 | 11.3 | 6.3 | 18.7 | 10.8 | 4.1
12 | 5 | 8 | 35.6 | 21.9 | 13.7 | 40.2 | 29.6 | 17.1 | 43.6 | 33.2 | 23.2 | 57.7 | 47.1 | 36.8 | 56.8 | 48 | 40.7 | 67.7 | 56.9 | 45.5 | 66.2 | 58.2 | 44.8 | 62.6 | 53.6 | 43.5 | 53.9 | 42.5 | 33.2 | 38.3 | 26.5 | 20.2 | 33.2 | 24.7 | 14.8 | 34.4 | 21.1 | 12.8
12 | 5 | 9 | 44.5 | 29 | 17.2 | 49.8 | 37.9 | 21.7 | 55.8 | 42.5 | 33.1 | 68.3 | 57.6 | 50.6 | 68.7 | 62.2 | 53 | 79.3 | 68.3 | 61.3 | 76.9 | 71.1 | 60.8 | 73.9 | 65.2 | 53.7 | 66.8 | 55.7 | 44.8 | 46.7 | 36.2 | 27.7 | 44.4 | 34 | 22.4 | 44.2 | 27.7 | 17.5
12 | 5 | 10 | 53.2 | 36.3 | 22.7 | 59.2 | 49.1 | 29.4 | 68.3 | 55.8 | 45.4 | 76.3 | 69.3 | 63.5 | 79.1 | 72.3 | 64.7 | 87 | 81.8 | 74.4 | 87.6 | 80.8 | 73 | 84.8 | 78.5 | 64.4 | 74 | 63.2 | 56.1 | 57.8 | 47.2 | 37.7 | 52 | 43.8 | 28.6 | 51.3 | 38 | 24.9
12 | 5 | 11 | 61.3 | 45.2 | 31 | 69.5 | 57.9 | 33.2 | 75.9 | 66.7 | 52.9 | 86.3 | 77.1 | 71.1 | 88 | 81.9 | 75.8 | 92.5 | 88.5 | 80.6 | 94.2 | 88.7 | 81.7 | 91.5 | 83.9 | 73.7 | 83.9 | 72.2 | 64.3 | 66.7 | 56.9 | 48.5 | 61.6 | 56.3 | 37.6 | 60.5 | 46 | 33.6
12 | 5 | 12 | 67.4 | 53 | 43.9 | 74.5 | 66.8 | 48.5 | 84.7 | 75.5 | 61.2 | 93.2 | 83.6 | 79.4 | 93.3 | 88.3 | 84.7 | 96.9 | 91.9 | 88.2 | 96.6 | 94.5 | 87.4 | 96.2 | 89.8 | 81.3 | 87.2 | 79.6 | 73.6 | 75.5 | 65.6 | 53.3 | 72.3 | 61.7 | 47.1 | 69.8 | 51.7 | 43.1
12 | 5 | 15 | 86.4 | 75.5 | 66.9 | 91.7 | 86.9 | 74.6 | 95.1 | 89.8 | 82.4 | 99.3 | 96.9 | 93.1 | 100 | 98.8 | 97.5 | 100 | 98.3 | 96.5 | 100 | 100 | 97.5 | 100 | 97.8 | 94.9 | 97.9 | 93.8 | 88.8 | 92.2 | 85.8 | 80.4 | 91.6 | 83.3 | 73 | 86.8 | 77.7 | 63.6
12 | 5 | 20 | 100 | 97 | 91.4 | 100 | 98.1 | 94.4 | 100 | 99.5 | 97.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.5 | 100 | 98.9 | 96.1 | 100 | 97.6 | 95.4 | 100 | 97.8 | 91.3
12 | 5 | 25 | 100 | 99.1 | 96.9 | 100 | 100 | 96.4 | 100 | 100 | 99.4 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.6 | 100 | 100 | 97.5 | 100 | 100 | 97.2
18 | 0.25 | 2
18 | 0.25 | 4 | [12 empty] | 1.6 |  |  | 2.4 |  |  | 0.1 |  |  | 2.2
18 | 0.25 | 6 | [12 empty] | 2.3 |  |  | 4 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 8 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 9 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 10 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 11 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 12 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 15 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 20 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.25 | 25 | [12 empty] | 2.3 |  |  | 4.3 |  |  | 2.3 |  |  | 2.4
18 | 0.5 | 2
18 | 0.5 | 4 |  |  |  | 1.7 |  |  | 2.3 |  |  | 4.1 |  |  | 4.7 |  |  | 6.5 | 2.4 |  | 7.1 | 2.3 |  | 6.9 | 2.4 | 0.7 | 4.1 | 2.4 |  | 2.3 | [5 empty] | 0.9
18 | 0.5 | 6 | 2.3 |  |  | 2.5 |  |  | 6.3 |  |  | 9.7 | 2.4 | 0.4 | 9.5 | 4.7 | 2.3 | 14.6 | 10 | 2.4 | 16.5 | 9.4 | 4.6 | 15.6 | 9.5 | 4.6 | 9.7 | 4.9 |  | 2.3 |  |  | 1.8 |  |  | 2.3
18 | 0.5 | 8 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 12.6 | 7 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.3 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 9 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 10 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 11 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 12 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 15 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 20 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.5 | 25 | 2.3 |  |  | 2.5 | 2.4 |  | 6.3 |  |  | 12.2 | 4.9 | 2.4 | 13.2 | 9.1 | 2.3 | 17.3 | 11.9 | 4.8 | 21 | 14 | 6.9 | 20.5 | 11.7 | 4.6 | 11.4 | 4.9 |  | 2.4 |  |  | 2.4 |  |  | 2.3
18 | 0.75 | 2
18 | 0.75 | 4 | 0.8 |  |  | 2.7 | 1.2 |  | 3.3 |  |  | 6.4 | 2.4 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 1.4 | 7.1 | 4.7 | 0.5 | 9.2 | 4.6 | 2.3 | 7.2 | 2.4 | 0.7 | 2.3 |  |  | 2.4 |  |  | 2.3
18 | 0.75 | 6 | 4.7 | 2.3 |  | 10.2 | 5.1 |  | 13.7 | 4.7 | 2.3 | 21.1 | 9.6 | 4.7 | 18.9 | 11.4 | 4.7 | 25.9 | 17.8 | 7.9 | 26 | 16.7 | 12.4 | 28.5 | 16.4 | 9.2 | 17.2 | 12.1 | 4.9 | 7.6 | 4.2 | 1 | 4.9 | 2.4 |  | 7.1 | 2.3
18 | 0.75 | 8 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.3 | 9.3 | 2.3 | 27.1 | 17.1 | 9.4 | 28.9 | 18.8 | 13 | 36.7 | 26.1 | 12.6 | 39.1 | 28.5 | 20.6 | 37.2 | 26.1 | 18.7 | 26.4 | 19.4 | 7.9 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.4 | 4.6
18 | 0.75 | 9 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 30.9 | 21.2 | 15.5 | 39.4 | 28.9 | 14.4 | 42.7 | 30.8 | 21.4 | 38.1 | 28.5 | 18.7 | 26.8 | 19.4 | 9.4 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.4 | 4.6
18 | 0.75 | 10 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 0.75 | 11 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 0.75 | 12 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 0.75 | 15 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 0.75 | 20 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 0.75 | 25 | 11.8 | 2.3 |  | 12.8 | 7.5 |  | 22.4 | 9.3 | 3 | 27.3 | 17.1 | 9.4 | 32.3 | 21.2 | 16.3 | 39.4 | 28.9 | 14.6 | 42.7 | 30.8 | 21.4 | 39.4 | 28.5 | 19.5 | 26.8 | 19.4 | 9.6 | 12.4 | 6.9 | 2.3 | 7.3 | 2.4 |  | 8.3 | 4.6
18 | 1 | 2
18 | 1 | 4 | 2.3 |  |  | 5.1 | 1.7 |  | 4.7 |  |  | 7.2 | 2.5 |  | 8.6 | 2.4 |  | 9.7 | 4.9 | 2.4 | 9.5 | 6.9 | 1.6 | 9.3 | 4.7 | 2.3 | 7.3 | 4.7 | 2.4 | 2.3 | 2.3 |  | 2.4 |  |  | 3
18 | 1 | 6 | 9.3 | 4.6 |  | 14.5 | 7.6 | 2.5 | 15.9 | 9.4 | 2.3 | 24.6 | 12.2 | 9.4 | 22.4 | 14.2 | 9.1 | 31.7 | 22.8 | 14.3 | 30.5 | 21.1 | 14.7 | 30.5 | 21 | 12.7 | 21.8 | 14.3 | 10.1 | 11.6 | 5.9 | 2.3 | 9 | 4.7 | 2.4 | 10.6 | 4.7
18 | 1 | 8 | 20.8 | 7.4 | 2.3 | 22.8 | 13.2 | 5.4 | 31 | 16.5 | 9.2 | 41.1 | 25.7 | 17.7 | 43.4 | 32.3 | 23.8 | 53.3 | 38.9 | 30.1 | 54.4 | 42.7 | 30.5 | 52.3 | 40.1 | 30.8 | 36.2 | 29.6 | 19 | 22.3 | 12 | 5.2 | 16.6 | 9.7 | 4.8 | 19.7 | 9.4 | 2.3
18 | 1 | 9 | 22.4 | 9.4 | 2.3 | 22.9 | 14 | 6.9 | 33.3 | 18.8 | 10.7 | 46.8 | 29.6 | 22 | 47.4 | 38.3 | 26.6 | 58.5 | 43.5 | 35.7 | 62.1 | 48.5 | 36.8 | 57.1 | 45.2 | 34.6 | 42.7 | 34 | 21 | 26.7 | 14.1 | 7.1 | 18.4 | 9.9 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 10 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.7 | 33.4 | 21.1 | 12.9 | 46.7 | 31.9 | 22 | 48.7 | 39.7 | 27.2 | 58.6 | 46.1 | 37 | 65.1 | 50.1 | 37.5 | 59.1 | 47.6 | 35.3 | 44.2 | 34.2 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 9.9 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 11 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.6 | 33.4 | 21.1 | 12.8 | 48.4 | 31.9 | 22 | 48.7 | 39.7 | 28.1 | 58.7 | 46.3 | 37 | 65.1 | 50.1 | 38.9 | 59.1 | 47.6 | 37.7 | 44.2 | 34.3 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 9.9 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 12 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.6 | 33.4 | 21.1 | 12.8 | 48.4 | 31.9 | 22 | 48.7 | 39.7 | 28.1 | 58.7 | 46.3 | 37 | 65.7 | 50.1 | 38.9 | 59.1 | 47.6 | 37.7 | 44.2 | 34.3 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 10.1 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 15 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.6 | 33.4 | 21.1 | 12.8 | 48.4 | 31.9 | 22 | 48.7 | 39.7 | 28.1 | 58.7 | 46.3 | 37 | 65.7 | 50.1 | 40 | 59.1 | 47.6 | 37.7 | 44.2 | 34.3 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 10.1 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 20 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.6 | 33.4 | 21.1 | 12.8 | 48.4 | 31.9 | 22 | 48.7 | 39.7 | 28.1 | 58.7 | 46.3 | 37 | 65.7 | 50.1 | 40 | 59.1 | 47.6 | 37.7 | 44.2 | 34.3 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 10.1 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1 | 25 | 22.4 | 9.4 | 2.3 | 23.4 | 15.5 | 7.6 | 33.4 | 21.1 | 12.8 | 48.4 | 31.9 | 22 | 48.7 | 39.7 | 28.1 | 58.7 | 46.3 | 37 | 65.7 | 50.1 | 40 | 59.1 | 47.6 | 37.7 | 44.2 | 34.3 | 22.6 | 26.6 | 16.4 | 7.6 | 19.1 | 10.1 | 4.8 | 21.5 | 9.4 | 2.7
18 | 1.25 | 2
18 | 1.25 | 4 | 2.3 |  |  | 5.2 | 2.5 |  | 4.7 | 1.9 |  | 7.2 | 3.1 | 2.4 | 9.3 | 4.6 | 1.9 | 9.7 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 9.3 | 6.6 | 2.3 | 7.3 | 4.7 | 2.4 | 2.4 | 2.3 |  | 2.5 |  |  | 3
18 | 1.25 | 6 | 10.9 | 4.7 |  | 17.6 | 7.9 | 2.5 | 18.7 | 11.6 | 4.1 | 24.6 | 14.6 | 9.9 | 25.7 | 18.1 | 12 | 34.2 | 26.8 | 16.7 | 30.6 | 23.5 | 17.7 | 32.7 | 21.2 | 14.6 | 24.3 | 16.8 | 12 | 14.3 | 7 | 2.3 | 12.1 | 4.9 | 2.4 | 11.8 | 4.7 | 0.3
18 | 1.25 | 8 | 25.6 | 11.6 | 3 | 26.7 | 18.8 | 8.3 | 34.7 | 23.7 | 13.6 | 49.2 | 34 | 25.1 | 47.5 | 39.1 | 30.7 | 58.8 | 44.3 | 34.2 | 59 | 47.7 | 37.8 | 56.3 | 46.4 | 33.1 | 44.1 | 36.5 | 25.1 | 28 | 16.7 | 9.6 | 21.9 | 14.7 | 7.2 | 26 | 11.7 | 5.7
18 | 1.25 | 9 | 30.1 | 18.4 | 4.7 | 34 | 23.5 | 10.3 | 41.1 | 30.1 | 18.9 | 56.8 | 41.8 | 33.5 | 58.7 | 49.1 | 38.8 | 68.9 | 56 | 46.1 | 71.3 | 58.9 | 45.5 | 68.9 | 55.1 | 43.7 | 51.6 | 42.2 | 31.4 | 35.1 | 21.2 | 12.6 | 27 | 16.7 | 10.3 | 30.5 | 14.8 | 6.6
18 | 1.25 | 10 | 33.7 | 18.3 | 4.7 | 37.6 | 25 | 11.2 | 43.3 | 32.7 | 22 | 60.2 | 46.8 | 37.1 | 64.9 | 52.2 | 47.2 | 73.1 | 63.9 | 52.4 | 76.1 | 65.9 | 51.2 | 70.8 | 61.4 | 50.5 | 58.2 | 47.1 | 36.4 | 38.2 | 27.2 | 16.6 | 30.2 | 21.1 | 11.8 | 31.9 | 16.5 | 9.4
18 | 1.25 | 11 | 33.7 | 18.3 | 4.7 | 37.6 | 25.1 | 12 | 43.7 | 32.7 | 22 | 65.1 | 49.3 | 37.7 | 66 | 55.8 | 48.1 | 76.2 | 65.4 | 53.8 | 77.6 | 68 | 53.8 | 72.8 | 62.9 | 52 | 61.1 | 48.8 | 36.6 | 38.6 | 27.7 | 16.9 | 30.3 | 21 | 11.8 | 31.7 | 16.8 | 9.4
18 | 1.25 | 12 | 33.7 | 18.3 | 4.7 | 37.7 | 25.1 | 12 | 43.7 | 32.7 | 22 | 65.2 | 49.3 | 39.5 | 66 | 56.9 | 48 | 76.2 | 65.4 | 54.3 | 77.4 | 68.1 | 54 | 73 | 62.9 | 52.4 | 61.1 | 48.8 | 36.6 | 38.6 | 27.7 | 16.9 | 30.3 | 21 | 11.8 | 31.7 | 16.8 | 9.4
18 | 1.25 | 15 | 33.7 | 18.3 | 4.7 | 37.7 | 25.1 | 12 | 43.7 | 32.7 | 22 | 65.2 | 49.3 | 39.5 | 66 | 56.9 | 48 | 76.2 | 65.4 | 54.3 | 78.5 | 68.1 | 55.1 | 73 | 62.9 | 52.4 | 61.1 | 48.8 | 36.6 | 38.6 | 27.7 | 16.9 | 30.3 | 21.5 | 11.8 | 31.7 | 16.8 | 9.4
18 | 1.25 | 20 | 33.7 | 18.3 | 4.7 | 37.7 | 25.1 | 12 | 43.7 | 32.7 | 22 | 65.2 | 49.3 | 39.5 | 66 | 56.9 | 48 | 76.2 | 65.4 | 54.3 | 78.5 | 68.1 | 55.1 | 73 | 62.9 | 52.4 | 61.1 | 48.8 | 36.6 | 38.6 | 27.7 | 16.9 | 30.3 | 21.5 | 11.8 | 31.7 | 16.8 | 9.4
18 | 1.25 | 25 | 33.7 | 18.3 | 4.7 | 37.7 | 25.1 | 12 | 43.7 | 32.7 | 22 | 65.2 | 49.3 | 39.5 | 66 | 56.9 | 48 | 76.2 | 65.4 | 54.3 | 78.5 | 68.1 | 55.1 | 73 | 62.9 | 52.4 | 61.1 | 48.8 | 36.6 | 38.6 | 27.7 | 16.9 | 30.3 | 21.5 | 11.8 | 31.7 | 16.8 | 9.4
18 | 1.5 | 2
18 | 1.5 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 1.9 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.7 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 3
18 | 1.5 | 6 | 13.2 | 4.7 | 2.1 | 18.4 | 7.9 | 3.1 | 18.6 | 13.8 | 5.2 | 24.6 | 16.4 | 11.8 | 27.1 | 18.3 | 13.2 | 36.5 | 26.8 | 16.8 | 32.2 | 23.5 | 17.8 | 32.7 | 21.2 | 14.6 | 24.4 | 17.2 | 12 | 15.6 | 9.1 | 4.6 | 12.1 | 7.1 | 3.8 | 13.7 | 7 | 2.3
18 | 1.5 | 8 | 28 | 16.1 | 6.5 | 32.2 | 20.8 | 11.1 | 38.3 | 27.2 | 14.3 | 49.7 | 36.9 | 32 | 52 | 41.5 | 34 | 62.5 | 51.1 | 36.2 | 61.8 | 50.7 | 41.5 | 56.7 | 48.5 | 36.7 | 48.3 | 36.5 | 27.7 | 30.7 | 21 | 12.4 | 24.5 | 17.2 | 9.6 | 30.9 | 14.2 | 6.9
18 | 1.5 | 9 | 34.3 | 21.1 | 9.6 | 37 | 26.2 | 13.6 | 46.9 | 35.6 | 24 | 61.1 | 48.2 | 41.8 | 62 | 53.8 | 43.6 | 73.6 | 61.1 | 52.4 | 73.2 | 64 | 53.8 | 70.7 | 60.6 | 48.3 | 57.7 | 46.5 | 36.2 | 39.5 | 28.5 | 18.7 | 33.4 | 22.9 | 14.5 | 34.5 | 20 | 10.5
18 | 1.5 | 10 | 38.2 | 24.1 | 11.7 | 47.1 | 34.2 | 19.4 | 52.9 | 42.7 | 31 | 67.8 | 54.9 | 49.2 | 72.6 | 61.6 | 53.4 | 81.1 | 74.6 | 63.4 | 79.8 | 74.2 | 62.9 | 77.4 | 67.7 | 57.1 | 63.9 | 53.6 | 43.3 | 45.3 | 33.2 | 23.9 | 40.4 | 28.9 | 14.6 | 40 | 22.6 | 13.8
18 | 1.5 | 11 | 39.1 | 26.5 | 13.6 | 48.3 | 39.6 | 20.2 | 55.1 | 45.7 | 33.9 | 71.7 | 60.4 | 51.7 | 77.3 | 69 | 60.1 | 83.7 | 77.2 | 67.2 | 86.2 | 80.4 | 68.5 | 79.8 | 72.4 | 62.2 | 71 | 59.9 | 47.8 | 48.7 | 37.9 | 27.3 | 44.3 | 31.1 | 17.1 | 42.6 | 23.7 | 14.7
18 | 1.5 | 12 | 39.2 | 26.5 | 13.5 | 50.1 | 39.7 | 20.1 | 57.8 | 46.6 | 33.7 | 74.4 | 62.1 | 52.8 | 77.5 | 71.1 | 62.9 | 83.8 | 77.6 | 68.4 | 88.4 | 81.6 | 69.6 | 83.8 | 74.6 | 62.6 | 70.9 | 60.4 | 48.1 | 51.9 | 38.4 | 27.3 | 44.3 | 31.7 | 17.7 | 44.6 | 26.1 | 16.2
18 | 1.5 | 15 | 39.2 | 28.9 | 13.5 | 50.1 | 39.7 | 20.1 | 57.7 | 47.3 | 33.7 | 76.2 | 62.1 | 54.1 | 79 | 71.2 | 62.9 | 83.8 | 78.2 | 68.3 | 88.5 | 81.9 | 69.6 | 83.8 | 74.6 | 62.8 | 70.9 | 60.4 | 48.1 | 52.1 | 38.4 | 27.4 | 44.3 | 31.7 | 17.7 | 44.6 | 25.9 | 16.2
18 | 1.5 | 20 | 39.2 | 28.9 | 13.5 | 50.1 | 39.7 | 20.1 | 57.7 | 47.3 | 33.7 | 76.2 | 62.1 | 54.1 | 79 | 71.2 | 62.9 | 83.8 | 78.2 | 68.3 | 88.5 | 81.9 | 69.6 | 83.8 | 74.6 | 62.8 | 70.9 | 60.4 | 48.1 | 52.1 | 38.4 | 27.4 | 44.3 | 31.7 | 17.7 | 44.6 | 25.9 | 16.2
18 | 1.5 | 25 | 39.2 | 28.9 | 13.5 | 50.1 | 39.7 | 20.1 | 57.7 | 47.3 | 33.7 | 76.2 | 62.1 | 54.1 | 79 | 71.2 | 62.9 | 83.8 | 78.2 | 68.3 | 88.5 | 81.9 | 69.6 | 83.8 | 74.6 | 62.8 | 70.9 | 60.4 | 48.1 | 52.1 | 38.4 | 27.4 | 44.3 | 31.7 | 17.7 | 44.6 | 25.9 | 16.2
18 | 1.75 | 2
18 | 1.75 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.1
18 | 1.75 | 6 | 13.2 | 4.7 | 2.1 | 19.6 | 7.9 | 3.1 | 18.6 | 13.8 | 6.7 | 24.9 | 16.9 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 21.4 | 15.1 | 25.1 | 19.2 | 12 | 15.6 | 9.1 | 4.6 | 12.1 | 7.1 | 4.4 | 15.2 | 7.1 | 2.3
18 | 1.75 | 8 | 29.3 | 18.4 | 9.2 | 32.2 | 23.4 | 12.9 | 41 | 28.5 | 19 | 52.8 | 39.6 | 34.1 | 53.3 | 41.8 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 51.9 | 41.5 | 58.4 | 50 | 38.3 | 49.6 | 39.9 | 29.7 | 33 | 21.6 | 14 | 27.4 | 19.3 | 9.9 | 30.9 | 16.7 | 7.8
18 | 1.75 | 9 | 39.4 | 25.1 | 11.6 | 41.1 | 28.6 | 17.2 | 49.7 | 39.7 | 28.9 | 62.5 | 50.8 | 44.2 | 62.2 | 55.2 | 45.5 | 75.2 | 63.6 | 54 | 75.5 | 64.7 | 54.3 | 72.1 | 60.6 | 49.6 | 59.3 | 47.8 | 37.7 | 42.3 | 30.9 | 21.7 | 36.7 | 25.7 | 17.3 | 37.5 | 21.1 | 11.9
18 | 1.75 | 10 | 44.6 | 29.8 | 16.6 | 51.4 | 38.8 | 24.7 | 60.5 | 47.2 | 36.6 | 72.1 | 59.6 | 51.4 | 76.9 | 63.8 | 56.9 | 84.2 | 75.6 | 66.4 | 83.5 | 76.7 | 65.3 | 81.3 | 71.5 | 60.2 | 66.6 | 57.9 | 48.6 | 49.3 | 36.6 | 28.4 | 44.2 | 33.6 | 19.3 | 44.6 | 28.5 | 15.1
18 | 1.75 | 11 | 48.3 | 33.5 | 18.7 | 59 | 47.2 | 26.3 | 69.7 | 55 | 42.5 | 81.8 | 67.6 | 59.6 | 82.3 | 74.1 | 68.4 | 88.2 | 83.5 | 73.1 | 91.6 | 83.3 | 73.9 | 87 | 77 | 66.8 | 75 | 66.4 | 53.6 | 58 | 46.4 | 35.6 | 50.7 | 40.7 | 26 | 50 | 33.3 | 20.2
18 | 1.75 | 12 | 50.3 | 36.6 | 21.8 | 59.9 | 50.1 | 26.9 | 74 | 56.2 | 43.6 | 84.3 | 71.3 | 62.8 | 86.7 | 80.9 | 72.3 | 90.8 | 86 | 78.4 | 92.8 | 86.2 | 78.3 | 91.7 | 80.6 | 70.7 | 77 | 69.2 | 58.3 | 62 | 50.1 | 37.4 | 53.4 | 43.2 | 26.1 | 50.8 | 33.6 | 23.6
18 | 1.75 | 15 | 51.5 | 36.6 | 23.8 | 62.2 | 52.5 | 26.8 | 74.4 | 57.4 | 44.3 | 85.3 | 73.1 | 63.5 | 88.6 | 81.9 | 74.5 | 91 | 86.4 | 78.3 | 94.2 | 87.5 | 78.7 | 91.9 | 81.6 | 71.1 | 79.7 | 69.4 | 59.9 | 64.4 | 51.5 | 40 | 55.4 | 43.1 | 26.9 | 51.9 | 33.6 | 23.5
18 | 1.75 | 20 | 51.5 | 36.6 | 23.8 | 62.2 | 52.5 | 26.8 | 74.4 | 57.4 | 44.3 | 85.3 | 73.1 | 63.5 | 88.6 | 81.9 | 74.5 | 91 | 86.4 | 78.3 | 94 | 87.5 | 78.7 | 91.9 | 81.6 | 71.1 | 79.7 | 69.4 | 59.9 | 64.4 | 51.5 | 40 | 55.4 | 43.1 | 26.9 | 51.9 | 33.6 | 23.5
18 | 1.75 | 25 | 51.5 | 36.6 | 23.8 | 62.2 | 52.5 | 26.8 | 74.4 | 57.4 | 44.3 | 85.3 | 73.1 | 63.5 | 88.6 | 81.9 | 74.5 | 91 | 86.4 | 78.3 | 94 | 87.5 | 78.7 | 91.9 | 81.6 | 71.1 | 79.7 | 69.4 | 59.9 | 64.4 | 51.5 | 40 | 55.4 | 43.1 | 26.9 | 51.9 | 33.6 | 23.5
18 | 2 | 2
18 | 2 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 2 | 6 | 13.2 | 4.7 | 2.1 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.2 | 12 | 16.2 | 9.3 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 2 | 8 | 29.9 | 18.7 | 9.2 | 34.1 | 23.4 | 12.8 | 41.7 | 29.6 | 19.2 | 53.5 | 41.8 | 34.1 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 51.9 | 41.5 | 58.4 | 50 | 38.3 | 49.6 | 40.7 | 29.7 | 33.5 | 25.5 | 14 | 27.5 | 19.4 | 10.4 | 31.2 | 18.7 | 7.8
18 | 2 | 9 | 39.7 | 25.1 | 14.5 | 43.2 | 33.8 | 17.2 | 50.3 | 40.1 | 30.6 | 62.6 | 53.3 | 46.6 | 64.6 | 55.2 | 45.5 | 75.9 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 60.6 | 50.5 | 61.2 | 48.5 | 40.2 | 44.1 | 31.6 | 23.3 | 39.2 | 28.2 | 18.1 | 37.7 | 24.9 | 12.8
18 | 2 | 10 | 46.4 | 32.4 | 18.9 | 54.9 | 42.1 | 26 | 63.1 | 50.4 | 38.5 | 72.3 | 62.2 | 56.8 | 77 | 66.5 | 57.6 | 85.5 | 77.1 | 68.7 | 84.3 | 77.2 | 66 | 82.4 | 71.5 | 60.5 | 69.7 | 59.9 | 51.5 | 51.6 | 41.4 | 32.1 | 46.6 | 36.7 | 20.2 | 45.5 | 30.8 | 15.2
18 | 2 | 11 | 52.4 | 36.8 | 22.2 | 62.1 | 53.9 | 27.9 | 72.2 | 57.8 | 45.8 | 84.4 | 70.7 | 65 | 84.2 | 77.7 | 68.9 | 91.6 | 86 | 76.9 | 93.6 | 86.6 | 77 | 88.9 | 78.6 | 69.5 | 78.3 | 67.9 | 58.9 | 61.2 | 50 | 37.8 | 54.1 | 45.6 | 29.6 | 54.4 | 37.1 | 26.2
18 | 2 | 12 | 56.9 | 39.4 | 31.2 | 68 | 58.2 | 31.2 | 78.1 | 66.5 | 49.2 | 86.6 | 76.5 | 67.8 | 89.5 | 84.9 | 78.2 | 94.6 | 88.9 | 82.8 | 95.5 | 90.7 | 80.2 | 94.1 | 83.2 | 76.8 | 82.3 | 72.1 | 64.3 | 69.1 | 55.9 | 43.1 | 60.7 | 49.7 | 32.7 | 56.7 | 41.7 | 27.6
18 | 2 | 15 | 59.9 | 43.7 | 36.1 | 73.9 | 62.4 | 36.9 | 80.4 | 69 | 54.9 | 90.3 | 80.4 | 69.5 | 92.9 | 86.7 | 81.2 | 95 | 90.3 | 86.2 | 98.1 | 92.1 | 84.9 | 94.2 | 83.2 | 78.2 | 84.4 | 76.7 | 67.3 | 74.1 | 59.8 | 50.9 | 65.3 | 51.5 | 38.6 | 61.4 | 42.6 | 29.1
18 | 2 | 20 | 59.9 | 43.7 | 36.1 | 73.9 | 62.4 | 36.9 | 80.4 | 69 | 54.9 | 90.3 | 80.4 | 69.5 | 92.9 | 86.7 | 81.2 | 95 | 90.3 | 86.2 | 98.1 | 91.9 | 84.9 | 94.2 | 83.2 | 78.2 | 84.4 | 76.7 | 67.3 | 74.1 | 59.8 | 51 | 65.3 | 51.5 | 38.7 | 61.4 | 42.6 | 29.1
18 | 2 | 25 | 59.9 | 43.7 | 36.1 | 73.9 | 62.4 | 36.9 | 80.4 | 69 | 54.9 | 90.3 | 80.4 | 69.5 | 92.9 | 86.7 | 81.2 | 95 | 90.3 | 86.2 | 98.1 | 91.9 | 84.9 | 94.2 | 83.2 | 78.2 | 84.4 | 76.7 | 67.3 | 74.1 | 59.8 | 51 | 65.3 | 51.5 | 38.7 | 61.4 | 42.6 | 29.1
18 | 2.25 | 2
18 | 2.25 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 2.25 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 2.25 | 8 | 30.7 | 18.7 | 9.3 | 34.1 | 23.4 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.1 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50.1 | 40.7 | 29.7 | 33.5 | 25.5 | 14.3 | 28.7 | 19.4 | 10.4 | 31.2 | 19 | 8.8
18 | 2.25 | 9 | 39.7 | 26.7 | 15.2 | 43.2 | 33.8 | 18.4 | 51.8 | 40.3 | 32.7 | 62.6 | 54.2 | 46.6 | 64.6 | 56.2 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.7 | 39.2 | 28.2 | 18.1 | 37.7 | 28.2 | 14.3
18 | 2.25 | 10 | 48.1 | 32.4 | 19.5 | 54.9 | 44.6 | 26 | 63.1 | 50.4 | 38.7 | 72.9 | 64.4 | 56.9 | 77 | 66.5 | 58.9 | 86.3 | 77.1 | 68.7 | 84.3 | 77.2 | 66 | 82.6 | 74.2 | 60.5 | 70.6 | 59.9 | 51.7 | 52.4 | 41.4 | 32.3 | 48.5 | 38.2 | 20.2 | 46.4 | 33.1 | 18.7
18 | 2.25 | 11 | 55.5 | 37.6 | 24.5 | 64.4 | 54.2 | 28.9 | 73.4 | 62.8 | 47.7 | 84.4 | 72.6 | 67.7 | 84.5 | 77.8 | 69.9 | 92 | 86.1 | 78.2 | 93.6 | 86.8 | 77.7 | 90.2 | 80 | 70.6 | 78.7 | 69 | 60.2 | 62.5 | 50.1 | 39 | 56.7 | 45.6 | 31 | 55.1 | 39 | 28
18 | 2.25 | 12 | 60.8 | 45.6 | 33.9 | 70.9 | 63.1 | 36.8 | 78.8 | 69.6 | 52.9 | 89.6 | 79.4 | 73.6 | 90.6 | 85.9 | 81.2 | 95 | 89.6 | 86.1 | 95.8 | 91.9 | 82.9 | 95.8 | 84.4 | 78.8 | 83.5 | 76.7 | 68.9 | 71 | 58.9 | 45.6 | 65.8 | 53.3 | 35.4 | 62.1 | 44.1 | 33.5
18 | 2.25 | 15 | 68.7 | 53.6 | 41.8 | 80.8 | 69 | 46.7 | 87.5 | 76.2 | 61.1 | 93.3 | 87.8 | 78.7 | 94.9 | 92.3 | 88.8 | 98.2 | 93.3 | 89.6 | 99.8 | 96.1 | 90.1 | 97.7 | 89.9 | 83.9 | 90.7 | 84.2 | 73.1 | 80 | 69.2 | 61.3 | 76.1 | 60.8 | 44.5 | 72.1 | 53.4 | 40.3
18 | 2.25 | 20 | 69.3 | 53.8 | 41.8 | 80.8 | 69 | 46.7 | 87.5 | 76.1 | 61.8 | 93.3 | 87.9 | 78.7 | 95.3 | 92.3 | 88.8 | 98.2 | 93.3 | 89.6 | 99.8 | 96.1 | 90.1 | 97.7 | 89.9 | 83.9 | 90.7 | 84.2 | 73.1 | 79.9 | 69.9 | 62.6 | 76.2 | 60.8 | 45.9 | 72.1 | 53.4 | 40.3
18 | 2.25 | 25 | 69.3 | 53.8 | 41.8 | 80.8 | 69 | 46.7 | 87.5 | 76.1 | 61.8 | 93.3 | 87.9 | 78.7 | 95.3 | 92.3 | 88.8 | 98.2 | 93.3 | 89.6 | 99.8 | 96.1 | 90.1 | 97.7 | 89.9 | 83.9 | 90.7 | 84.2 | 73.1 | 79.9 | 69.9 | 62.6 | 76.2 | 60.8 | 45.9 | 72.1 | 53.4 | 40.3
18 | 2.75 | 2
18 | 2.75 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 2.75 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 2.75 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 2.75 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 40.3 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 2.75 | 10 | 48.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.3 | 73.4 | 64.7 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 78.6 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.1 | 49.9 | 38.2 | 22 | 48.7 | 33.1 | 20.9
18 | 2.75 | 11 | 57.9 | 39.4 | 25.4 | 65 | 54.2 | 31.3 | 73.4 | 62.8 | 49.9 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 86.8 | 79.4 | 90.2 | 81.3 | 70.6 | 80.4 | 69 | 61.2 | 62.5 | 53.8 | 41.2 | 57.5 | 47.2 | 31 | 57.2 | 41.9 | 30.1
18 | 2.75 | 12 | 63.9 | 49.9 | 36.1 | 71.4 | 65.2 | 41.6 | 79.6 | 71.2 | 56.1 | 90.7 | 82.8 | 76.6 | 91.9 | 87.6 | 82.6 | 95.3 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.4 | 78.8 | 86.3 | 79.3 | 70.4 | 72.2 | 61 | 48.9 | 67.7 | 55.8 | 38.6 | 65.7 | 49.6 | 37.7
18 | 2.75 | 15 | 79.9 | 64.2 | 53.6 | 87.7 | 79.7 | 61.9 | 90.7 | 83.7 | 71.2 | 96.9 | 94.2 | 87.7 | 99.3 | 97.4 | 93.8 | 100 | 96.4 | 94.1 | 100 | 98 | 95.7 | 100 | 95.3 | 91.5 | 95 | 90 | 83.3 | 86.6 | 80.1 | 72.6 | 84.4 | 74.6 | 58.2 | 80.1 | 64.8 | 53.6
18 | 2.75 | 20 | 84.6 | 68 | 56.7 | 88.7 | 80.1 | 62.1 | 93.4 | 84.8 | 72.4 | 98.6 | 94.4 | 88 | 100 | 97.7 | 94.9 | 100 | 97.2 | 94.9 | 100 | 98.3 | 95.7 | 100 | 96.6 | 92.7 | 96.1 | 91.8 | 84.9 | 90.3 | 81.5 | 73.3 | 85 | 75.4 | 61.4 | 81.4 | 68.4 | 56.6
18 | 2.75 | 25 | 84.6 | 68 | 56.7 | 88.7 | 80.1 | 62.1 | 93.4 | 84.8 | 72.4 | 98.6 | 94.4 | 88 | 100 | 97.7 | 95.3 | 100 | 97.2 | 94.9 | 100 | 98.3 | 95.7 | 100 | 96.6 | 92.7 | 96.1 | 91.8 | 84.9 | 90.3 | 81.5 | 73.3 | 85 | 75.4 | 61.4 | 81.4 | 68.4 | 56.6
18 | 3 | 2
18 | 3 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 3 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 3 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 3 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 41.9 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 3 | 10 | 49.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.3 | 73.4 | 65 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 79.2 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.4 | 49.9 | 38.2 | 22.8 | 49.2 | 33.2 | 20.9
18 | 3 | 11 | 59.3 | 40.1 | 25.4 | 65.1 | 54.2 | 32.3 | 73.4 | 62.8 | 49.9 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 86.8 | 79.4 | 90.2 | 81.3 | 70.6 | 80.4 | 69 | 61.2 | 63.7 | 53.8 | 41.2 | 57.5 | 49.2 | 32.4 | 57.9 | 41.9 | 30.1
18 | 3 | 12 | 63.9 | 49.9 | 36.1 | 71.8 | 66.1 | 41.6 | 82.8 | 72.3 | 56.1 | 90.7 | 82.4 | 77.6 | 92.2 | 88 | 82.6 | 96.3 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.4 | 78.8 | 86.3 | 79.3 | 70.6 | 72.3 | 61.3 | 49.7 | 67.7 | 58.1 | 38.6 | 65.7 | 49.6 | 37.7
18 | 3 | 15 | 81.3 | 67.3 | 57.9 | 88 | 82.1 | 64.7 | 92.9 | 84.5 | 75.8 | 97.8 | 94 | 88.5 | 99.8 | 97.8 | 95.1 | 100 | 96.7 | 94.5 | 100 | 98.5 | 96.2 | 100 | 96.8 | 92 | 96.8 | 91.3 | 85.5 | 89.2 | 80.6 | 75.1 | 85.7 | 77.6 | 62.3 | 82.5 | 68 | 54.6
18 | 3 | 20 | 87.1 | 72.4 | 61.5 | 93.6 | 85.1 | 71 | 95.7 | 88.4 | 81.5 | 100 | 95.4 | 91.2 | 100 | 100 | 97.1 | 100 | 98.2 | 96.2 | 100 | 100 | 95.9 | 100 | 97.8 | 95.3 | 97.3 | 95.1 | 88 | 92.3 | 85.5 | 79.7 | 89.3 | 81.1 | 66.9 | 85.3 | 73.8 | 64.2
18 | 3 | 25 | 87.1 | 72.4 | 61.5 | 93.6 | 85.1 | 71 | 95.7 | 88.4 | 81.5 | 100 | 95.4 | 91.2 | 100 | 100 | 97.1 | 100 | 98.2 | 96.2 | 100 | 100 | 95.9 | 100 | 97.8 | 95.3 | 97.3 | 95.1 | 88 | 92.3 | 85.5 | 79.7 | 89.3 | 81.1 | 66.9 | 85.3 | 73.8 | 64.2
18 | 3.5 | 2
18 | 3.5 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 3.5 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 3.5 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 3.5 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 41.9 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 3.5 | 10 | 49.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.3 | 73.4 | 65 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 79.2 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.4 | 49.9 | 38.2 | 22.7 | 49.2 | 33.2 | 20.9
18 | 3.5 | 11 | 59.3 | 40.1 | 25.4 | 65.1 | 54.2 | 32.3 | 73.4 | 62.8 | 50.5 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 87.2 | 79.4 | 90.2 | 81.9 | 70.6 | 80.4 | 69 | 61.2 | 63.7 | 53.8 | 41.2 | 58.2 | 49.6 | 32.4 | 57.8 | 41.9 | 30.1
18 | 3.5 | 12 | 63.9 | 49.9 | 36.1 | 72.2 | 66.1 | 41.6 | 82.8 | 73 | 56.1 | 90.7 | 82.8 | 77.6 | 92.2 | 88 | 82.6 | 96.5 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.8 | 78.8 | 86.3 | 79.3 | 70.9 | 72.3 | 61.4 | 49.7 | 67.7 | 60.1 | 40.1 | 66.8 | 49.6 | 37.7
18 | 3.5 | 15 | 82.7 | 69.2 | 58.1 | 89.9 | 84.9 | 67.7 | 93.5 | 86.3 | 77.8 | 99 | 94.9 | 89.6 | 100 | 98.1 | 95.9 | 100 | 97.6 | 95.9 | 100 | 100 | 96.4 | 100 | 97.8 | 92.8 | 97.2 | 92.2 | 86.8 | 90.3 | 81.2 | 76.9 | 88.6 | 77.8 | 67 | 85 | 69.5 | 55.8
18 | 3.5 | 20 | 92.7 | 85.8 | 73.8 | 98.1 | 92.6 | 82.4 | 99.2 | 94.9 | 87.6 | 100 | 99.4 | 95.4 | 100 | 100 | 100 | 100 | 100 | 96.6 | 100 | 100 | 99 | 100 | 100 | 97.4 | 100 | 97.4 | 93.2 | 97 | 92.2 | 86.7 | 94.7 | 90.4 | 81 | 94.3 | 85.8 | 77.3
18 | 3.5 | 25 | 92.8 | 85.8 | 74.8 | 98.2 | 92.6 | 82.4 | 99.2 | 94.9 | 87.6 | 100 | 99.4 | 95.4 | 100 | 100 | 100 | 100 | 100 | 96.6 | 100 | 100 | 99 | 100 | 100 | 97.4 | 100 | 97.4 | 93.2 | 97 | 92.2 | 86.7 | 95 | 90.4 | 81 | 94.3 | 85.8 | 77.2
18 | 4 | 2
18 | 4 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 4 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 4 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 4 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 41.9 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 4 | 10 | 49.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.4 | 73.4 | 65 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 79.2 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.4 | 49.9 | 38.2 | 22.7 | 49.2 | 33.2 | 20.9
18 | 4 | 11 | 59.3 | 40.1 | 25.4 | 65.1 | 54.2 | 32.3 | 73.4 | 62.8 | 50.5 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 87.2 | 79.4 | 90.2 | 81.9 | 70.6 | 80.4 | 69 | 61.2 | 63.7 | 53.8 | 41.2 | 58.2 | 49.6 | 32.4 | 57.8 | 41.9 | 30.1
18 | 4 | 12 | 63.9 | 49.9 | 36.1 | 72.2 | 66.1 | 41.6 | 82.8 | 73 | 56.8 | 90.7 | 82.8 | 77.6 | 92.2 | 88 | 82.6 | 96.5 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.8 | 78.8 | 86.3 | 79.3 | 70.9 | 72.3 | 61.4 | 49.7 | 67.7 | 60.1 | 42.6 | 66.8 | 49.6 | 37.7
18 | 4 | 15 | 83.1 | 70.8 | 60.3 | 90.6 | 84.9 | 70.9 | 93.8 | 86.8 | 78.7 | 99.1 | 96.7 | 91.1 | 100 | 98.4 | 96.4 | 100 | 97.8 | 95.9 | 100 | 100 | 96.6 | 100 | 98.1 | 94.1 | 97.2 | 92.2 | 87.8 | 90.3 | 82.7 | 77.4 | 89.2 | 78.5 | 68.2 | 86 | 70.7 | 57.6
18 | 4 | 20 | 97.8 | 92.5 | 84.5 | 99.6 | 95.4 | 88.5 | 100 | 97 | 93.7 | 100 | 100 | 97.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 99 | 95.4 | 100 | 97.2 | 92.4 | 98.6 | 95.4 | 90.9 | 99 | 92.2 | 84.5
18 | 4 | 25 | 98 | 92.5 | 85.4 | 99.8 | 95.2 | 89.1 | 100 | 97.6 | 94.4 | 100 | 100 | 97.2 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 95.3 | 100 | 97.3 | 92.6 | 98.8 | 95.4 | 91.2 | 99 | 93.4 | 87.2
18 | 4.5 | 2
18 | 4.5 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 4.5 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 4.5 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 4.5 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 41.9 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 4.5 | 10 | 49.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.4 | 73.4 | 65 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 79.2 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.4 | 49.9 | 38.2 | 22.7 | 49.2 | 33.2 | 20.9
18 | 4.5 | 11 | 59.3 | 40.1 | 25.4 | 65.1 | 54.2 | 32.3 | 73.4 | 62.8 | 50.5 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 87.2 | 79.4 | 90.2 | 81.9 | 70.6 | 80.4 | 69 | 61.2 | 63.7 | 53.8 | 41.2 | 58.2 | 49.6 | 32.4 | 57.8 | 41.9 | 30.1
18 | 4.5 | 12 | 63.9 | 49.9 | 36.1 | 72.2 | 66.1 | 41.6 | 82.8 | 73 | 56.8 | 90.7 | 82.8 | 77.6 | 92.2 | 88 | 82.6 | 96.5 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.8 | 78.8 | 86.3 | 79.3 | 70.9 | 72.3 | 61.4 | 49.7 | 67.7 | 60.1 | 42.6 | 66.8 | 49.6 | 37.7
18 | 4.5 | 15 | 84.1 | 70.8 | 60.3 | 90.6 | 86.2 | 72.1 | 93.8 | 86.8 | 80.1 | 99.1 | 96.7 | 92.3 | 100 | 98.4 | 96.4 | 100 | 97.8 | 95.9 | 100 | 100 | 96.6 | 100 | 98.1 | 94.1 | 97.2 | 92.2 | 88.1 | 90.3 | 82.7 | 77.4 | 89.7 | 80.1 | 68.9 | 86 | 71.4 | 58.8
18 | 4.5 | 20 | 99.2 | 94.9 | 89 | 100 | 96.1 | 91.5 | 100 | 98.1 | 96.5 | 100 | 100 | 97.4 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 96.7 | 100 | 98 | 95.2 | 100 | 97.5 | 93.6 | 100 | 96.6 | 89.3
18 | 4.5 | 25 | 100 | 96.6 | 92.4 | 100 | 98.4 | 91.6 | 100 | 100 | 98 | 100 | 100 | 97.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.3 | 100 | 99.2 | 96.1 | 100 | 98.2 | 94.8 | 100 | 98 | 93.1
18 | 5 | 2
18 | 5 | 4 | 4.6 |  |  | 6.7 | 2.5 |  | 6.3 | 2.3 |  | 7.2 | 4.7 | 2.4 | 9.3 | 4.6 | 2.3 | 10.9 | 7.1 | 2.4 | 9.5 | 6.9 | 1.6 | 11.6 | 6.6 | 2.3 | 9.6 | 4.9 | 2.4 | 4.7 | 2.3 |  | 2.5 |  |  | 4.3 | 1.9
18 | 5 | 6 | 13.7 | 4.7 | 2.3 | 19.7 | 7.9 | 4.4 | 19.2 | 13.8 | 6.7 | 24.9 | 17.1 | 12.7 | 27.1 | 18.4 | 14.4 | 36.5 | 26.8 | 17 | 32.2 | 23.5 | 17.8 | 32.7 | 23.3 | 15.1 | 25.1 | 19.6 | 12 | 16.2 | 9.4 | 4.6 | 12.1 | 7.2 | 4.4 | 15.6 | 7.1 | 2.3
18 | 5 | 8 | 31.3 | 18.7 | 9.4 | 34.1 | 23.5 | 13.6 | 41.6 | 29.6 | 19.2 | 54.3 | 42.6 | 34.2 | 53.7 | 42.1 | 34.8 | 62.5 | 51.1 | 37.7 | 63.6 | 52.3 | 41.5 | 58.4 | 50 | 38.3 | 50 | 40.7 | 29.7 | 33.4 | 25.5 | 14.3 | 28.7 | 19.4 | 10.5 | 31.2 | 19 | 8.8
18 | 5 | 9 | 39.7 | 26.7 | 15.7 | 43.2 | 33.8 | 18.4 | 51.8 | 41.9 | 32.7 | 62.6 | 54.2 | 47.1 | 64.6 | 56.3 | 45.5 | 76.8 | 64.2 | 54 | 75.5 | 64.8 | 56 | 72.3 | 62 | 50.5 | 61.2 | 51 | 40.2 | 44.9 | 32.1 | 23.6 | 39.2 | 28.8 | 19.3 | 38.4 | 28.6 | 14.3
18 | 5 | 10 | 49.6 | 32.4 | 19.6 | 54.9 | 44.9 | 26.8 | 64.5 | 50.8 | 39.4 | 73.4 | 65 | 58.8 | 77 | 66.5 | 58.9 | 86.3 | 79.2 | 68.7 | 84.3 | 77.2 | 66.1 | 82.6 | 75 | 61.5 | 70.6 | 59.9 | 51.7 | 52.7 | 44.9 | 33.4 | 49.9 | 38.2 | 22.7 | 49.2 | 33.2 | 20.9
18 | 5 | 11 | 59.3 | 40.1 | 25.4 | 65.1 | 54.2 | 32.3 | 73.4 | 62.8 | 50.5 | 85.2 | 73.1 | 69.9 | 85.6 | 79.6 | 73.2 | 92 | 86.9 | 78.2 | 93.6 | 87.2 | 79.4 | 90.2 | 81.9 | 70.6 | 80.4 | 69 | 61.2 | 63.7 | 53.8 | 41.2 | 58.2 | 49.6 | 32.4 | 57.8 | 41.9 | 30.1
18 | 5 | 12 | 63.9 | 49.9 | 36.1 | 72.2 | 66.1 | 41.6 | 82.8 | 73 | 56.8 | 90.7 | 82.8 | 77.6 | 92.2 | 88 | 82.6 | 96.5 | 91.1 | 86.3 | 96.4 | 93 | 84.7 | 95.8 | 87.8 | 78.8 | 86.3 | 79.3 | 70.9 | 72.3 | 61.4 | 49.7 | 67.7 | 60.1 | 42.6 | 66.8 | 49.6 | 37.7
18 | 5 | 15 | 84.1 | 70.8 | 60.3 | 90.6 | 86.2 | 73.4 | 93.8 | 86.8 | 80.1 | 99.1 | 96.7 | 92.3 | 100 | 98.4 | 96.4 | 100 | 97.8 | 95.9 | 100 | 100 | 96.6 | 100 | 98.1 | 94.1 | 97.2 | 92.2 | 88.1 | 90.3 | 82.7 | 77.4 | 89.7 | 80.8 | 68.9 | 86 | 71.4 | 58.8
18 | 5 | 20 | 100 | 95.6 | 90.1 | 100 | 98.1 | 92.7 | 100 | 99.3 | 96.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98 | 100 | 98.1 | 95.6 | 100 | 97.8 | 95.3 | 100 | 97.2 | 91
18 | 5 | 25 | 100 | 99.5 | 95.3 | 100 | 100 | 95.8 | 100 | 100 | 99.4 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.2 | 100 | 100 | 97.5 | 100 | 100 | 96.3
24 | 0.25 | 2
24 | 0.25 | 4
24 | 0.25 | 6 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 8 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 9 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 10 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 11 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 12 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 15 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 20 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.25 | 25 | [12 empty] | 2.2 |  |  | 3.2 | [5 empty] | 3
24 | 0.5 | 2
24 | 0.5 | 4 | [9 empty] | 3.2 |  |  | 3.2 |  |  | 5.5 |  |  | 6.3 | 0.1 |  | 4.5 | 3.1 |  | 3.2
24 | 0.5 | 6 | 3 |  |  | 2.4 |  |  | 3.2 |  |  | 7.5 | 3.2 | 0.3 | 9.4 | 3.1 |  | 12.6 | 6.4 | 3.2 | 15.6 | 6.3 | 3.1 | 15.5 | 7.5 | 3.1 | 8.4 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 8 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.4 | 6.3 | 3.1 | 16.6 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 4 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 9 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 4 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 10 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 4 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 11 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 6.2 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 12 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 6.2 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 15 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 6.2 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 20 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 6.2 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.5 | 25 | 3 |  |  | 3.4 |  |  | 3.1 |  |  | 9.8 | 3.2 | 1.3 | 11.9 | 6.3 | 3.1 | 18.7 | 9.9 | 3.2 | 16.1 | 9.5 | 5.5 | 18.5 | 9.4 | 6.2 | 9.7 | 3.2 |  | 3.1 | [5 empty] | 3.1
24 | 0.75 | 2
24 | 0.75 | 4 |  |  |  | 3.4 |  |  | 2.2 |  |  | 3.2 |  |  | 5.5 |  |  | 6.5 | 3.2 |  | 6.3 | 3.1 |  | 6.3 | 3.1 |  | 3.2 | 3.2 | [7 empty] | 3.1
24 | 0.75 | 6 | 5.5 |  |  | 10.1 | 3.4 |  | 12.6 | 3.1 |  | 17.7 | 6.5 | 3.2 | 18 | 9.4 | 4.7 | 22.2 | 16.1 | 6.4 | 22.1 | 14.7 | 7.2 | 21.9 | 12.5 | 7.3 | 16.1 | 9.7 | 3.2 | 7.4 | 3.1 |  | 5.1 |  |  | 6.3 | 3.1
24 | 0.75 | 8 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 24.5 | 16.1 | 7.9 | 28.4 | 15.9 | 9.3 | 35.8 | 23.5 | 12.9 | 37.1 | 26.5 | 16.8 | 36.7 | 25.3 | 12.5 | 25.8 | 16.3 | 6.5 | 11.9 | 6 | 1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 9 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 7.9 | 29.4 | 18.4 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.8 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 10 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 11 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19.1 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 12 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19.1 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 15 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19.1 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 20 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19.1 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 0.75 | 25 | 12.6 |  |  | 12.7 | 6.8 |  | 19 | 6.2 | 3.1 | 23.5 | 16.3 | 9.3 | 29.5 | 19.1 | 9.4 | 35.9 | 24 | 13.4 | 38.2 | 27 | 19.7 | 36.7 | 25.4 | 13.5 | 25.8 | 16.9 | 6.5 | 11.9 | 6.2 | 3.1 | 6.5 | 3.2 |  | 6.3 | 3.1
24 | 1 | 2
24 | 1 | 4 |  |  |  | 3.4 |  |  | 3.2 |  |  | 6.4 | 3.2 |  | 6.3 |  |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 2.2 |  |  | 3.1
24 | 1 | 6 | 6.3 | 3.1 |  | 10.5 | 3.9 |  | 15 | 6.3 |  | 22.7 | 12.8 | 6.4 | 20.1 | 12.4 | 7.1 | 30.8 | 19.6 | 9.6 | 25.1 | 18.8 | 9.3 | 28.7 | 15.6 | 10 | 19.6 | 12.8 | 6.9 | 10.4 | 3.8 | 0.1 | 6.8 | 3.2 |  | 8.1 | 3.1
24 | 1 | 8 | 20.1 | 8.3 |  | 19.6 | 10.6 | 3.3 | 27.6 | 12.6 | 6.2 | 39.5 | 25.1 | 16.3 | 38.6 | 28.6 | 20.1 | 49.3 | 35.7 | 26.2 | 52.7 | 38 | 27.2 | 50.1 | 34.7 | 26.1 | 35.9 | 25.3 | 17.3 | 18.9 | 10.1 | 5.4 | 13.3 | 6.5 | 3.2 | 18.1 | 7.7
24 | 1 | 9 | 20.1 | 9.4 |  | 20.5 | 11.8 | 3.3 | 28.4 | 18.8 | 9.3 | 44.7 | 28.5 | 19.4 | 44.4 | 35.5 | 23.1 | 56.1 | 40.6 | 33.9 | 59.4 | 44.9 | 31 | 54.6 | 39.9 | 31.8 | 39.4 | 29.4 | 17.9 | 21.5 | 12.6 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 0.4
24 | 1 | 10 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.6 | 56.2 | 42.9 | 34.1 | 62.7 | 47.7 | 31.8 | 56.7 | 43.1 | 32.6 | 40.9 | 31.5 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1 | 11 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.7 | 56.2 | 42.9 | 34.1 | 62.6 | 47.7 | 33.4 | 56.8 | 43.1 | 34.7 | 40.9 | 31.9 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1 | 12 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.7 | 56.2 | 42.9 | 34.1 | 62.6 | 47.7 | 33.5 | 56.8 | 43.1 | 34.7 | 40.9 | 31.9 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1 | 15 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.7 | 56.2 | 42.9 | 34.1 | 62.6 | 47.7 | 33.5 | 56.8 | 43.1 | 34.7 | 40.9 | 31.9 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1 | 20 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.7 | 56.2 | 42.9 | 34.1 | 62.6 | 47.7 | 33.5 | 56.8 | 43.1 | 34.7 | 40.9 | 31.9 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1 | 25 | 20.8 | 9.4 |  | 20.8 | 14.1 | 4.2 | 31 | 18.7 | 9.4 | 45.3 | 30.8 | 19.4 | 47.3 | 39 | 25.7 | 56.2 | 42.9 | 34.1 | 62.6 | 47.7 | 33.5 | 56.8 | 43.1 | 34.7 | 40.9 | 31.9 | 20.1 | 21.9 | 13 | 6.3 | 15.4 | 6.5 | 3.2 | 19.2 | 9.4 | 1.9
24 | 1.25 | 2
24 | 1.25 | 4 |  |  |  | 3.4 |  |  | 3.2 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 1.25 | 6 | 9.3 | 3.1 |  | 13 | 7 | 3.3 | 15.8 | 9.3 | 3.1 | 22.9 | 12.8 | 7.1 | 25.5 | 14.9 | 8.8 | 32.2 | 22.8 | 12.8 | 28.4 | 22 | 10.3 | 28.7 | 18.1 | 10 | 19.6 | 13.2 | 8.3 | 12.5 | 6.2 | 2.7 | 9.7 | 3.3 | 1.3 | 10.3 | 3.1
24 | 1.25 | 8 | 23 | 11.3 | 3.1 | 24.6 | 17.3 | 7.9 | 32.2 | 19.1 | 10.1 | 42.6 | 30 | 22.7 | 44.9 | 33.6 | 26.3 | 54 | 42.4 | 30.9 | 55.9 | 44.4 | 31.6 | 53 | 41 | 32.1 | 42.5 | 29.6 | 20.5 | 25.2 | 13.2 | 9.3 | 19.6 | 12.2 | 6.4 | 24.4 | 9.4 | 3.1
24 | 1.25 | 9 | 27 | 14.2 | 3.1 | 31.8 | 21 | 10.4 | 37.5 | 28.4 | 15.8 | 53.8 | 38.8 | 29.3 | 54.9 | 45 | 36.6 | 65.8 | 52.2 | 42.8 | 68.2 | 57.4 | 42 | 66.5 | 50.7 | 40.3 | 52.4 | 39.4 | 29.3 | 34.3 | 18.8 | 10.4 | 25.5 | 16.1 | 7.2 | 28.5 | 12.6 | 4.6
24 | 1.25 | 10 | 29.3 | 15.7 | 3.1 | 34.6 | 23.4 | 11.5 | 41.7 | 31.3 | 19 | 58.8 | 42.4 | 35.7 | 61.5 | 51.6 | 42.2 | 70.6 | 59.6 | 49.3 | 74.9 | 60.9 | 47.6 | 70 | 58.5 | 47.7 | 54.8 | 43.6 | 33 | 36.8 | 25.3 | 13.8 | 26.3 | 17.5 | 7.2 | 28.8 | 14.8 | 7.1
24 | 1.25 | 11 | 29.3 | 16.4 | 3.1 | 35.8 | 23.4 | 11.5 | 41.7 | 31.9 | 19 | 62.8 | 44.7 | 36 | 62.6 | 53.4 | 46.9 | 72.8 | 59.6 | 49.5 | 75.8 | 64.4 | 51.1 | 71.4 | 60.5 | 48.7 | 57.5 | 45.7 | 33 | 38.1 | 25.5 | 13.9 | 26.3 | 18.5 | 7.2 | 31 | 14.8 | 7.1
24 | 1.25 | 12 | 29.3 | 16.4 | 3.1 | 35.8 | 23.4 | 11.5 | 42.2 | 31.9 | 19 | 62.8 | 44.7 | 36 | 62.6 | 53.4 | 47.3 | 73.2 | 59.6 | 49.6 | 76.1 | 64.5 | 52.7 | 71.4 | 60.5 | 48.8 | 57.5 | 45.7 | 33 | 38.1 | 25.7 | 13.9 | 26.3 | 18.5 | 7.2 | 31 | 14.8 | 7.1
24 | 1.25 | 15 | 29.3 | 16.4 | 3.1 | 35.8 | 23.4 | 11.5 | 42.2 | 31.9 | 19 | 62.8 | 44.7 | 36 | 62.6 | 53.6 | 47.3 | 73.2 | 59.6 | 49.6 | 76.1 | 64.5 | 52.9 | 71.4 | 60.5 | 48.8 | 57.5 | 45.7 | 33 | 38.1 | 25.7 | 13.9 | 26.3 | 18.5 | 7.2 | 31 | 14.8 | 7.1
24 | 1.25 | 20 | 29.3 | 16.4 | 3.1 | 35.8 | 23.4 | 11.5 | 42.2 | 31.9 | 19 | 62.8 | 44.7 | 36 | 62.6 | 53.6 | 47.3 | 73.2 | 59.6 | 49.6 | 76.1 | 64.5 | 52.9 | 71.4 | 60.5 | 48.8 | 57.5 | 45.7 | 33 | 38.1 | 25.7 | 13.9 | 26.3 | 18.5 | 7.2 | 31 | 14.8 | 7.1
24 | 1.25 | 25 | 29.3 | 16.4 | 3.1 | 35.8 | 23.4 | 11.5 | 42.2 | 31.9 | 19 | 62.8 | 44.7 | 36 | 62.6 | 53.6 | 47.3 | 73.2 | 59.6 | 49.6 | 76.1 | 64.5 | 52.9 | 71.4 | 60.5 | 48.8 | 57.5 | 45.7 | 33 | 38.1 | 25.7 | 13.9 | 26.3 | 18.5 | 7.2 | 31 | 14.8 | 7.1
24 | 1.5 | 2
24 | 1.5 | 4 | 2.2 |  |  | 4.6 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.2
24 | 1.5 | 6 | 9.3 | 3.1 |  | 13.5 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 13.1 | 9.6 | 25.5 | 15.7 | 9.3 | 32.4 | 22.9 | 12.8 | 28.4 | 22 | 10.3 | 28.7 | 18.5 | 11.3 | 19.7 | 13.2 | 8.3 | 12.6 | 6.9 | 3.1 | 9.7 | 6.4 | 1.3 | 11.2 | 5.1
24 | 1.5 | 8 | 23 | 12.5 | 5.8 | 30 | 20 | 8.7 | 34.8 | 21.9 | 11.5 | 46.1 | 34.7 | 25.6 | 48.3 | 38.3 | 27.7 | 57.7 | 48.9 | 33.9 | 60.3 | 47.3 | 32.8 | 55.5 | 44.4 | 34 | 45.7 | 32.6 | 26 | 27.2 | 16.3 | 9.4 | 22.8 | 14 | 8.9 | 27.5 | 12.6 | 3.1
24 | 1.5 | 9 | 29.9 | 19.1 | 6.2 | 36.1 | 25.9 | 11.2 | 44.6 | 33.3 | 19 | 56.1 | 45.1 | 35.5 | 58.3 | 51.6 | 39.1 | 71.6 | 57.2 | 48 | 71.5 | 60.1 | 49.6 | 66.6 | 54.3 | 41.9 | 54.3 | 43.5 | 33.4 | 37.2 | 22 | 16.5 | 28.5 | 19.7 | 12 | 32.6 | 18.8 | 6.4
24 | 1.5 | 10 | 36 | 22.6 | 9.6 | 42.2 | 28.1 | 17.2 | 50.9 | 38 | 28.7 | 62.8 | 51.7 | 44.7 | 69.9 | 58.1 | 48.8 | 78.6 | 72.5 | 60.4 | 77.8 | 72.6 | 56.2 | 77.8 | 66.9 | 53.5 | 61.4 | 50.8 | 40.5 | 40.7 | 31.2 | 20 | 35.6 | 22.9 | 13.3 | 35.8 | 22 | 10.4
24 | 1.5 | 11 | 37.4 | 24.3 | 9.6 | 44.4 | 35 | 17.9 | 54 | 44 | 32.1 | 71.3 | 57.6 | 48.5 | 75 | 64.2 | 56.6 | 81.7 | 76.1 | 61.4 | 84.1 | 77.2 | 62.4 | 80.3 | 71.4 | 57.7 | 68.2 | 55.3 | 44.3 | 47.1 | 36 | 22.5 | 41.4 | 26.7 | 16.3 | 38.5 | 22.6 | 12.6
24 | 1.5 | 12 | 38.7 | 24.3 | 9.7 | 48.3 | 35 | 19.5 | 57.2 | 44.4 | 31.9 | 72.4 | 59.7 | 48.8 | 77.1 | 66.9 | 60.2 | 83.1 | 76.4 | 65.1 | 85 | 79 | 63.1 | 81.7 | 73.1 | 60.7 | 68.3 | 57.8 | 44.4 | 47.9 | 36.3 | 24.7 | 42.1 | 26.7 | 16.3 | 41.4 | 22.6 | 12.9
24 | 1.5 | 15 | 38.6 | 24.3 | 9.7 | 48.3 | 35 | 19.5 | 57.2 | 44.4 | 33 | 74.8 | 60 | 48.7 | 77.1 | 66.9 | 60.8 | 83.3 | 77.5 | 65.4 | 85 | 79.7 | 64.9 | 81.7 | 73.1 | 60.8 | 68.7 | 57.6 | 44.4 | 48 | 36.3 | 24.7 | 42.1 | 26.7 | 16.3 | 41.4 | 23.7 | 12.9
24 | 1.5 | 20 | 38.6 | 24.3 | 9.7 | 48.3 | 35 | 19.5 | 57.2 | 44.4 | 33 | 74.8 | 60 | 48.7 | 77.1 | 66.9 | 60.8 | 83.3 | 77.5 | 65.4 | 85 | 79.7 | 64.9 | 81.7 | 73.1 | 60.9 | 68.7 | 57.6 | 44.4 | 48 | 36.3 | 24.7 | 42.1 | 26.7 | 16.3 | 41.4 | 23.7 | 12.9
24 | 1.5 | 25 | 38.6 | 24.3 | 9.7 | 48.3 | 35 | 19.5 | 57.2 | 44.4 | 33 | 74.8 | 60 | 48.7 | 77.1 | 66.9 | 60.8 | 83.3 | 77.5 | 65.4 | 85 | 79.7 | 64.9 | 81.7 | 73.1 | 60.9 | 68.7 | 57.6 | 44.4 | 48 | 36.3 | 24.7 | 42.1 | 26.7 | 16.3 | 41.4 | 23.7 | 12.9
24 | 1.75 | 2
24 | 1.75 | 4 | 3.1 |  |  | 4.6 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.2
24 | 1.75 | 6 | 11.3 | 3.2 |  | 14.2 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 15.7 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 12.4 | 5.9 | 0.1
24 | 1.75 | 8 | 25.8 | 12.6 | 5.8 | 29.9 | 20.8 | 10.5 | 35 | 25.1 | 12.6 | 49 | 36.3 | 27.7 | 50.1 | 38.6 | 29.6 | 57.7 | 48.8 | 36 | 60.3 | 47.6 | 33.2 | 55.9 | 44.4 | 34 | 45.7 | 32.6 | 26 | 27.8 | 18.8 | 12.4 | 22.8 | 16.1 | 9.6 | 28.5 | 15.7 | 4
24 | 1.75 | 9 | 33.9 | 22 | 9.3 | 37.4 | 25.9 | 13.7 | 48.1 | 35.9 | 25.1 | 60 | 46 | 39.3 | 59.1 | 52.8 | 41.8 | 72.8 | 61.9 | 49.2 | 71.5 | 63.3 | 51.4 | 68 | 55.1 | 44.2 | 57.8 | 44.2 | 34.4 | 37.2 | 27.6 | 19 | 32.6 | 24.6 | 13.1 | 34.3 | 19.1 | 9.5
24 | 1.75 | 10 | 42.5 | 28.9 | 13.8 | 47.6 | 33.8 | 20.5 | 57.6 | 44 | 34.6 | 69.5 | 56 | 48.7 | 72.5 | 60.3 | 54.8 | 81.3 | 73.9 | 65.4 | 80.3 | 73.5 | 62.3 | 80 | 67.5 | 56.5 | 64.6 | 55.8 | 43.5 | 47.5 | 33.1 | 24.2 | 41 | 29.3 | 18 | 41.8 | 25.4 | 13.6
24 | 1.75 | 11 | 48 | 30.8 | 19.2 | 56.2 | 43.3 | 24 | 65.6 | 50.5 | 38.5 | 78.8 | 63.5 | 55.7 | 81.2 | 71.2 | 61.8 | 88 | 80.3 | 70.6 | 90 | 81.7 | 71.4 | 84.4 | 77 | 64.8 | 75.4 | 60.3 | 47.8 | 55.5 | 46.1 | 29.7 | 45.5 | 34.9 | 20.4 | 49.7 | 28.6 | 16.7
24 | 1.75 | 12 | 50 | 32.9 | 22.3 | 61 | 49.1 | 25.9 | 72.1 | 53.5 | 39.9 | 83.8 | 70.7 | 59 | 85.7 | 77 | 69.6 | 89.6 | 84.4 | 74.3 | 93 | 84.3 | 76.3 | 89.6 | 79 | 69.9 | 76.4 | 66 | 54.5 | 61.2 | 47.4 | 36.9 | 52.7 | 37.9 | 21.4 | 50.2 | 31.7 | 19.9
24 | 1.75 | 15 | 50 | 32.5 | 22.6 | 60.8 | 49.7 | 25.9 | 72.1 | 54.3 | 40.8 | 84.1 | 70.8 | 61.7 | 86.5 | 79.7 | 70.2 | 90.4 | 85 | 76.4 | 93.4 | 85.1 | 78.4 | 89 | 79 | 69.7 | 77.4 | 65.3 | 56.4 | 61.9 | 50 | 38.2 | 54.2 | 40.6 | 23.5 | 50.3 | 31.7 | 22.2
24 | 1.75 | 20 | 50 | 32.5 | 22.6 | 60.8 | 49.7 | 25.9 | 72.1 | 54.3 | 40.8 | 84.1 | 70.8 | 61.7 | 86.5 | 79.7 | 70.2 | 90.4 | 85 | 76.4 | 93.4 | 85.1 | 78.4 | 89 | 79 | 69.7 | 77.4 | 65.3 | 56.4 | 61.9 | 49.9 | 38.2 | 54.2 | 40.6 | 23.5 | 50.3 | 31.7 | 22.2
24 | 1.75 | 25 | 50 | 32.5 | 22.6 | 60.8 | 49.7 | 25.9 | 72.1 | 54.3 | 40.8 | 84.1 | 70.8 | 61.7 | 86.5 | 79.7 | 70.2 | 90.4 | 85 | 76.4 | 93.4 | 85.1 | 78.4 | 89 | 79 | 69.7 | 77.4 | 65.3 | 56.4 | 61.9 | 49.9 | 38.2 | 54.2 | 40.6 | 23.5 | 50.3 | 31.7 | 22.2
24 | 2 | 2
24 | 2 | 4 | 3.1 |  |  | 4.6 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 2 | 6 | 11.3 | 3.2 |  | 14.2 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 12.4 | 5.9 | 0.1
24 | 2 | 8 | 25.8 | 12.6 | 6.2 | 31.5 | 20.8 | 10.5 | 35 | 26.3 | 13.7 | 49 | 38.9 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.6 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 33.8 | 26 | 30 | 18.8 | 12.5 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.2
24 | 2 | 9 | 35.7 | 22.6 | 9.3 | 38.9 | 25.9 | 16 | 48 | 37.4 | 25.7 | 62 | 49 | 39.8 | 60.8 | 53.8 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.1 | 45.3 | 59.2 | 45.8 | 34.4 | 40.4 | 28.1 | 19.8 | 34.4 | 24.6 | 16.4 | 34.3 | 19.1 | 9.5
24 | 2 | 10 | 43 | 28.9 | 18.9 | 48 | 37.4 | 20.5 | 60 | 46.4 | 34.6 | 69.7 | 59.3 | 52.8 | 74.9 | 61.7 | 56.1 | 83 | 76.5 | 65.9 | 82.1 | 74.5 | 64.5 | 80.6 | 68 | 57.8 | 68.1 | 56.1 | 47.2 | 47.7 | 37.9 | 27.2 | 41.9 | 31 | 19.5 | 44.1 | 26.1 | 13.6
24 | 2 | 11 | 53.5 | 32.9 | 21.8 | 58 | 49.1 | 26.7 | 70.1 | 55.9 | 44.2 | 79.4 | 68.2 | 62.2 | 82.1 | 74.6 | 67 | 90.5 | 81.7 | 75.6 | 92.3 | 84.1 | 75.4 | 87.6 | 77 | 65.8 | 77.5 | 64.7 | 52.7 | 59 | 47.6 | 34.4 | 52.7 | 40.8 | 25.9 | 50.8 | 31.7 | 17.9
24 | 2 | 12 | 55.2 | 36.3 | 27.1 | 67.1 | 54.5 | 28.3 | 76.5 | 60.8 | 45.1 | 87.6 | 74 | 67.1 | 88.6 | 82.5 | 75.2 | 93.4 | 87.5 | 80.2 | 94 | 89.8 | 79.7 | 90.8 | 81.2 | 73.5 | 82.6 | 68.1 | 59.7 | 63 | 50.9 | 41.7 | 59.5 | 44.9 | 30.3 | 56.7 | 38.3 | 24.7
24 | 2 | 15 | 60.1 | 38.4 | 31 | 71.2 | 58.3 | 28.4 | 79.4 | 67.2 | 50.4 | 89 | 80.8 | 68.5 | 90.9 | 85.9 | 79.9 | 94.2 | 90 | 85.1 | 97.2 | 91.4 | 83.1 | 93 | 83.2 | 77.6 | 83.3 | 75.6 | 65.6 | 71.5 | 59.7 | 48.5 | 64.1 | 50.4 | 34.2 | 59.7 | 41.1 | 26.2
24 | 2 | 20 | 60.1 | 38.4 | 31 | 71.2 | 58.3 | 28.4 | 79.4 | 67.2 | 50.4 | 89 | 80.8 | 68.5 | 90.9 | 85.9 | 79.9 | 94.2 | 90 | 85.1 | 97.2 | 91.4 | 83.1 | 93 | 83.2 | 77.6 | 83.6 | 75.6 | 65.6 | 71.5 | 59.7 | 48.5 | 64.1 | 50.4 | 34.2 | 59.7 | 41.1 | 26.2
24 | 2 | 25 | 60.1 | 38.4 | 31 | 71.2 | 58.3 | 28.4 | 79.4 | 67.2 | 50.4 | 89 | 80.8 | 68.5 | 90.9 | 85.9 | 79.9 | 94.2 | 90 | 85.1 | 97.2 | 91.4 | 83.1 | 93 | 83.2 | 77.6 | 83.6 | 75.6 | 65.6 | 71.5 | 59.7 | 48.5 | 64.1 | 50.4 | 34.2 | 59.7 | 41.1 | 26.2
24 | 2.25 | 2
24 | 2.25 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 2.25 | 6 | 11.3 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 12.7 | 5.9 | 0.1
24 | 2.25 | 8 | 26.1 | 12.6 | 6.2 | 31.5 | 20.8 | 10.5 | 35 | 26.3 | 13.7 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.6 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.2
24 | 2.25 | 9 | 36.1 | 22.8 | 10.2 | 39 | 27.8 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.1 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.1 | 24.6 | 16.3 | 34.7 | 19.1 | 9.5
24 | 2.25 | 10 | 45 | 28.9 | 18.9 | 48 | 37.4 | 21.5 | 60 | 46.4 | 36 | 69.7 | 62.5 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.5 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 68 | 57.8 | 69.7 | 59 | 47.1 | 47.9 | 37.9 | 28.6 | 42.2 | 34.3 | 19.5 | 44.7 | 28.5 | 15.7
24 | 2.25 | 11 | 53.6 | 34.9 | 23.4 | 59.5 | 49.4 | 26.6 | 70.1 | 56 | 44.2 | 80.5 | 70.4 | 63 | 82.4 | 75.5 | 68.3 | 91.2 | 83.9 | 76.1 | 92.3 | 84.3 | 78.4 | 88.2 | 78.1 | 67.7 | 78.2 | 65.8 | 55.6 | 60 | 47.6 | 36.7 | 54 | 41.4 | 26 | 53.9 | 33.2 | 17.9
24 | 2.25 | 12 | 59.8 | 39.8 | 30.7 | 69.1 | 57 | 33.6 | 78.5 | 65.3 | 48.1 | 88.6 | 77.4 | 70.1 | 89.4 | 83.3 | 78.5 | 93.7 | 88.8 | 83.6 | 94.9 | 90.5 | 80.1 | 93.9 | 84.1 | 76.8 | 83.7 | 73.2 | 64.2 | 66.3 | 54.4 | 42.8 | 62.8 | 49.2 | 31.6 | 60.5 | 41 | 28.8
24 | 2.25 | 15 | 67.3 | 48.3 | 38.9 | 77.5 | 65.9 | 39.7 | 85.9 | 73.1 | 60.1 | 93.3 | 86.3 | 77.3 | 94.1 | 90.2 | 84.9 | 98 | 92.5 | 89.3 | 99.8 | 94.9 | 88.8 | 97.3 | 89.4 | 83 | 89.9 | 82.1 | 74.7 | 75.7 | 65.6 | 57.6 | 74.3 | 57.5 | 43.2 | 67.2 | 49.3 | 32.9
24 | 2.25 | 20 | 67.8 | 49.7 | 38.9 | 78 | 65.9 | 39.7 | 85.9 | 73.1 | 60.1 | 93.3 | 86.3 | 77.3 | 94.1 | 90.2 | 84.9 | 98 | 92.5 | 89.3 | 99.8 | 94.9 | 88.8 | 97.3 | 89.2 | 82.9 | 89.9 | 82.5 | 74.7 | 75.5 | 65.6 | 59.2 | 74.6 | 57.5 | 43.5 | 67.2 | 49.3 | 32.9
24 | 2.25 | 25 | 67.8 | 49.7 | 38.9 | 78 | 65.9 | 39.7 | 85.9 | 73.1 | 60.1 | 93.3 | 86.3 | 77.3 | 94.1 | 90.2 | 84.9 | 98 | 92.5 | 89.3 | 99.8 | 94.9 | 88.8 | 97.3 | 89.2 | 82.9 | 89.9 | 82.5 | 74.7 | 75.5 | 65.6 | 59.2 | 74.6 | 57.5 | 43.5 | 67.2 | 49.3 | 32.9
24 | 2.75 | 2
24 | 2.75 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 2.75 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 2.75 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 2.75 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 28 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 2.75 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.7
24 | 2.75 | 11 | 57.4 | 36 | 24.6 | 61.4 | 49.6 | 29.2 | 70.1 | 57.4 | 44.4 | 82.8 | 72.8 | 63.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.4 | 45.8 | 26 | 54.4 | 35.3 | 21.6
24 | 2.75 | 12 | 63.3 | 43.8 | 33 | 69.3 | 60.9 | 35.4 | 79.4 | 68.1 | 50.3 | 89.6 | 79.7 | 72.8 | 90.4 | 86.2 | 78.6 | 94.7 | 89.7 | 84 | 95.3 | 92.2 | 82.6 | 93.9 | 87.1 | 77 | 82.9 | 74.7 | 66.2 | 68.1 | 57.4 | 46.3 | 64.2 | 52.5 | 37.6 | 62.9 | 44.1 | 33
24 | 2.75 | 15 | 77.3 | 60.8 | 50 | 84.8 | 79.6 | 55.3 | 90.9 | 82.1 | 68.4 | 96.7 | 92.8 | 85.6 | 99 | 96.6 | 92.4 | 100 | 96.1 | 93.7 | 100 | 98 | 95.3 | 100 | 95 | 90.4 | 94.1 | 88.5 | 79.2 | 84.8 | 76.6 | 68.9 | 82.1 | 74.4 | 55.8 | 77.8 | 63.6 | 47.4
24 | 2.75 | 20 | 83.2 | 64.4 | 53.6 | 87.6 | 79.8 | 60 | 93.1 | 82.7 | 70 | 98.6 | 93.9 | 86.5 | 100 | 97.3 | 94 | 100 | 98.1 | 94.9 | 100 | 98 | 95.5 | 100 | 96.2 | 91.7 | 95.7 | 91.5 | 84.3 | 89.1 | 80.4 | 73.1 | 83.2 | 74.7 | 58.3 | 81.1 | 65.1 | 52.7
24 | 2.75 | 25 | 83.2 | 64.4 | 53.6 | 87.6 | 79.8 | 60 | 93.1 | 82.7 | 70 | 98.6 | 93.9 | 86.5 | 100 | 97.3 | 94 | 100 | 98.1 | 94.9 | 100 | 98 | 95.5 | 100 | 96.2 | 91.7 | 95.7 | 91.5 | 84.3 | 89.1 | 80.4 | 73.1 | 83.2 | 74.7 | 58.3 | 81.1 | 65.1 | 52.7
24 | 3 | 2
24 | 3 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 3 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 3 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 3 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 28 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 3 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.9
24 | 3 | 11 | 57.4 | 36 | 24.6 | 61.8 | 49.6 | 29.2 | 70.1 | 57.4 | 45.3 | 82.8 | 72.8 | 63.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.5 | 45.8 | 26 | 54.4 | 37.9 | 21.5
24 | 3 | 12 | 63.3 | 43.5 | 33 | 71 | 60.9 | 35.4 | 79.4 | 68.4 | 50.3 | 89.6 | 79.7 | 73.3 | 90.8 | 86.2 | 78.9 | 94.9 | 89.7 | 84 | 95.7 | 92.2 | 82.6 | 93.9 | 87.1 | 77.7 | 83 | 74.7 | 66.2 | 68.1 | 58.3 | 46.4 | 65 | 53.5 | 37.6 | 64.2 | 44.1 | 33
24 | 3 | 15 | 78.9 | 64.2 | 51.4 | 85.4 | 81.1 | 59.2 | 91.5 | 84.8 | 72.2 | 97.8 | 93.3 | 88.3 | 99.9 | 97.3 | 93.3 | 100 | 96.7 | 93.9 | 100 | 98.5 | 95.3 | 100 | 96.1 | 91.8 | 95.6 | 90.3 | 81.4 | 88.2 | 77.6 | 71.8 | 83.9 | 74.4 | 59.7 | 79.5 | 65.1 | 50.7
24 | 3 | 20 | 87 | 71 | 60 | 92.2 | 83.9 | 70.5 | 94.6 | 88.4 | 78.8 | 100 | 95.1 | 89.4 | 100 | 100 | 95.9 | 100 | 98.2 | 95.6 | 100 | 100 | 96 | 100 | 98 | 94.7 | 96.3 | 93.8 | 87.3 | 91.7 | 85.6 | 77.9 | 88.2 | 81 | 65.5 | 83.1 | 71 | 61.1
24 | 3 | 25 | 87 | 71 | 60 | 92.2 | 83.9 | 70.5 | 94.6 | 88.4 | 78.8 | 100 | 95.1 | 89.4 | 100 | 100 | 95.9 | 100 | 98.2 | 95.6 | 100 | 100 | 96 | 100 | 98 | 94.7 | 96.3 | 93.8 | 87.3 | 91.7 | 85.6 | 77.9 | 88.2 | 81 | 65.5 | 83.1 | 71 | 61.1
24 | 3.5 | 2
24 | 3.5 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 3.5 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 3.5 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 3.5 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 29.8 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 3.5 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.9
24 | 3.5 | 11 | 57.4 | 36 | 24.6 | 61.8 | 49.6 | 29.2 | 70.1 | 57.4 | 45.3 | 82.8 | 72.8 | 64.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.5 | 45.8 | 26 | 56.9 | 37.9 | 23.3
24 | 3.5 | 12 | 63.3 | 43.5 | 33 | 71 | 60.9 | 36.4 | 79.4 | 68.7 | 50.6 | 89.6 | 80.6 | 75 | 90.8 | 86.2 | 78.9 | 95.6 | 90.3 | 84 | 95.7 | 92.2 | 82.6 | 93.9 | 87.1 | 77.7 | 83 | 74.7 | 67.8 | 69.7 | 58.3 | 46.4 | 65 | 53.5 | 37.6 | 64.2 | 44.1 | 33
24 | 3.5 | 15 | 82.2 | 68.7 | 57.4 | 88.6 | 83.2 | 64.5 | 92.8 | 84.5 | 74.4 | 98.7 | 94.4 | 89.8 | 100 | 97.6 | 96 | 100 | 97.9 | 94.4 | 100 | 100 | 95.9 | 100 | 96.9 | 92.7 | 97 | 90.6 | 83.3 | 89.7 | 79.7 | 73 | 86.9 | 77.9 | 62.6 | 82 | 67.9 | 52.3
24 | 3.5 | 20 | 91.9 | 84.9 | 73 | 97.2 | 92 | 80.2 | 99.8 | 93.4 | 85.3 | 100 | 100 | 94.7 | 100 | 100 | 100 | 100 | 100 | 96.4 | 100 | 100 | 98.6 | 100 | 100 | 97.3 | 100 | 96.3 | 92.7 | 96.8 | 90.7 | 85.9 | 94.3 | 86.7 | 79.1 | 93 | 84.1 | 71.3
24 | 3.5 | 25 | 92 | 84.9 | 73 | 97.6 | 92 | 80.2 | 99.8 | 93.4 | 85.3 | 100 | 100 | 94.7 | 100 | 100 | 100 | 100 | 100 | 96.4 | 100 | 100 | 98.6 | 100 | 100 | 97.3 | 100 | 96.3 | 92.7 | 96.8 | 90.7 | 85.9 | 94.7 | 86.7 | 79.1 | 92.9 | 84.1 | 71.3
24 | 4 | 2
24 | 4 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 4 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 4 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 4 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 29.8 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 4 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.9
24 | 4 | 11 | 57.4 | 36 | 24.6 | 61.8 | 49.6 | 29.2 | 70.1 | 57.4 | 46.4 | 82.8 | 72.8 | 64.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.5 | 45.8 | 26 | 56.9 | 37.9 | 23.3
24 | 4 | 12 | 63.3 | 43.5 | 33 | 71 | 60.9 | 36.4 | 79.4 | 68.7 | 50.6 | 89.6 | 80.6 | 75 | 90.8 | 86.2 | 78.9 | 96.6 | 90.3 | 84 | 95.7 | 92.2 | 82.6 | 93.9 | 87.1 | 77.7 | 83 | 74.7 | 67.8 | 69.6 | 58.3 | 46.4 | 65 | 53.5 | 37.6 | 64.4 | 44.1 | 33
24 | 4 | 15 | 82.2 | 68.1 | 58.3 | 89.7 | 83.2 | 66.9 | 92.8 | 86.3 | 74.4 | 98.7 | 94.6 | 90.6 | 100 | 97.6 | 96 | 100 | 98.1 | 94.4 | 100 | 100 | 96 | 100 | 97.3 | 92.7 | 97 | 90.8 | 85.1 | 89.7 | 82.9 | 73.8 | 88.3 | 77.9 | 66.8 | 83.1 | 70.6 | 52.3
24 | 4 | 20 | 97 | 91.4 | 83.1 | 98.6 | 93.5 | 87.4 | 100 | 98.7 | 92.6 | 100 | 100 | 96.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.2 | 95 | 100 | 96.4 | 92.4 | 97.9 | 94.2 | 88.1 | 99 | 90.7 | 84
24 | 4 | 25 | 96.8 | 91.7 | 83.5 | 99.4 | 94 | 87.3 | 100 | 99.1 | 93 | 100 | 100 | 96.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 95.5 | 100 | 96.5 | 92.7 | 99 | 94.4 | 87.8 | 99 | 91.9 | 86.1
24 | 4.5 | 2
24 | 4.5 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 4.5 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 4.5 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 4.5 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 29.8 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 4.5 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.9
24 | 4.5 | 11 | 57.4 | 36 | 24.6 | 61.8 | 49.6 | 29.2 | 70.1 | 57.4 | 46.4 | 82.8 | 72.8 | 64.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.5 | 45.8 | 26 | 56.9 | 37.9 | 23.3
24 | 4.5 | 12 | 63.3 | 43.5 | 33 | 71 | 60.9 | 36.4 | 79.4 | 68.7 | 50.6 | 89.6 | 80.6 | 75 | 90.8 | 86.2 | 78.9 | 96.6 | 90.3 | 84 | 95.7 | 92.2 | 82.6 | 93.9 | 87.1 | 77.7 | 83 | 74.7 | 67.8 | 69.6 | 58.3 | 46.4 | 65 | 53.5 | 37.6 | 64.4 | 44.1 | 33
24 | 4.5 | 15 | 82.2 | 68.8 | 59.2 | 89.7 | 83.3 | 66.9 | 93.4 | 86.3 | 74.6 | 98.7 | 95.3 | 91.2 | 100 | 97.6 | 96 | 100 | 98.1 | 94.8 | 100 | 100 | 96 | 100 | 97.3 | 92.7 | 97 | 91.3 | 85.1 | 89.7 | 82.9 | 73.9 | 88.5 | 78.3 | 67.4 | 83.1 | 71.5 | 52.7
24 | 4.5 | 20 | 99.1 | 94.9 | 87.2 | 100 | 96.3 | 91.2 | 100 | 99.5 | 95.1 | 100 | 100 | 98.7 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 96.4 | 100 | 96.8 | 93.7 | 100 | 97.1 | 92.1 | 100 | 96.4 | 87.6
24 | 4.5 | 25 | 100 | 96.2 | 92.3 | 100 | 97 | 91.7 | 100 | 100 | 97 | 100 | 100 | 98.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.3 | 100 | 99.3 | 95.8 | 100 | 97.5 | 94.5 | 100 | 97 | 93.2
24 | 5 | 2
24 | 5 | 4 | 3.1 |  |  | 4.9 |  |  | 3.4 |  |  | 6.4 | 3.2 |  | 6.3 | 3.1 |  | 6.5 | 3.2 |  | 8.9 | 3.1 |  | 8.4 | 3.1 |  | 6.4 | 3.2 |  | 3.1 |  |  | 3.2 |  |  | 3.1
24 | 5 | 6 | 11.5 | 3.2 |  | 16.1 | 7 | 3.3 | 18.1 | 9.4 | 3.1 | 23.2 | 14 | 9.7 | 25.5 | 16 | 9.3 | 32.4 | 22.9 | 12.8 | 30.6 | 22 | 10.3 | 28.8 | 18.5 | 11.4 | 20.3 | 16 | 8.3 | 13.8 | 6.9 | 3.1 | 9.7 | 6.4 | 3.2 | 14.4 | 5.9 | 0.1
24 | 5 | 8 | 25.9 | 13 | 6.2 | 31.9 | 21 | 10.5 | 35 | 26.3 | 15.4 | 49 | 39.4 | 27.7 | 50.1 | 38.6 | 29.7 | 58 | 48.8 | 36.8 | 60.3 | 47.7 | 33.7 | 55.9 | 44.4 | 34 | 45.7 | 35.4 | 26 | 30 | 18.8 | 12.7 | 24.7 | 16.1 | 9.6 | 30.6 | 15.7 | 6.7
24 | 5 | 9 | 36.1 | 22.8 | 12.1 | 41.2 | 29.8 | 16.6 | 48 | 37.4 | 25.7 | 62 | 50 | 39.8 | 62.2 | 54.4 | 44.1 | 74.2 | 62.1 | 50.5 | 71.5 | 64.1 | 52.4 | 68 | 55.9 | 45.4 | 59.2 | 46 | 36.1 | 40.4 | 29.4 | 20.8 | 35.7 | 24.6 | 16.7 | 34.9 | 19.1 | 9.5
24 | 5 | 10 | 46.2 | 30.8 | 19 | 48 | 38.7 | 21.5 | 60 | 46.4 | 36 | 69.7 | 63.3 | 53.8 | 74.9 | 61.7 | 57.2 | 83 | 76.7 | 66.2 | 82.1 | 74.5 | 64.5 | 81 | 71.2 | 57.8 | 69.7 | 59.2 | 47.1 | 50.1 | 37.9 | 29.4 | 42.2 | 35.7 | 19.5 | 44.7 | 28.8 | 15.9
24 | 5 | 11 | 57.4 | 36 | 24.6 | 61.8 | 49.6 | 29.2 | 70.1 | 57.4 | 46.4 | 82.8 | 72.8 | 64.8 | 82.6 | 76.3 | 68.3 | 91.2 | 85.1 | 76.3 | 92.3 | 84.5 | 78.4 | 88.2 | 80.2 | 68.3 | 78.2 | 67.1 | 56.8 | 60.8 | 49.1 | 40.8 | 54.5 | 45.8 | 26 | 56.9 | 37.9 | 23.3
24 | 5 | 12 | 63.3 | 43.5 | 33 | 71 | 60.9 | 36.4 | 79.4 | 68.7 | 50.6 | 89.6 | 80.6 | 75 | 90.8 | 86.2 | 78.9 | 96.6 | 90.3 | 84 | 95.7 | 92.2 | 82.6 | 93.9 | 87.1 | 77.7 | 83 | 74.7 | 67.8 | 69.6 | 58.3 | 46.4 | 65 | 53.5 | 37.6 | 64.4 | 44.1 | 33
24 | 5 | 15 | 82.2 | 68.8 | 59.2 | 89.7 | 84.5 | 66.9 | 93.4 | 86.3 | 74.6 | 98.7 | 95.3 | 91.2 | 100 | 97.6 | 96 | 100 | 98.1 | 94.8 | 100 | 100 | 96 | 100 | 97.3 | 92.7 | 97 | 91.3 | 85.1 | 89.7 | 82.9 | 74.1 | 88.5 | 78.3 | 67.4 | 83.1 | 71.5 | 52.7
24 | 5 | 20 | 100 | 95.4 | 89 | 100 | 96.4 | 92.9 | 100 | 99.5 | 95.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.7 | 100 | 97.3 | 94.3 | 100 | 97.5 | 92.5 | 100 | 96.5 | 89.1
24 | 5 | 25 | 100 | 99.1 | 94.7 | 100 | 100 | 95.9 | 100 | 100 | 99.2 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98 | 100 | 100 | 96.6 | 100 | 100 | 96.7
48 | 0.25 | 2
48 | 0.25 | 4
48 | 0.25 | 6
48 | 0.25 | 8
48 | 0.25 | 9
48 | 0.25 | 10
48 | 0.25 | 11
48 | 0.25 | 12
48 | 0.25 | 15
48 | 0.25 | 20
48 | 0.25 | 25
48 | 0.5 | 2
48 | 0.5 | 4
48 | 0.5 | 6 | [9 empty] | 6.5 |  |  | 6.3 |  |  | 6.5 |  |  | 7 |  |  | 12.4 | 6.3 |  | 6.5
48 | 0.5 | 8 | [9 empty] | 6.5 |  |  | 6.5 | 2.7 |  | 11.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 9 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 10 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 11 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 12 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 15 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 20 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.5 | 25 | [9 empty] | 6.5 |  |  | 7.7 | 6.3 |  | 13.1 | 4.4 |  | 10.2 | 6.3 |  | 14.6 | 6.3 |  | 6.5
48 | 0.75 | 2
48 | 0.75 | 4
48 | 0.75 | 6 | 2.4 |  |  | 6.9 |  |  | 6.3 |  |  | 6.6 |  |  | 7.8 | 6.3 |  | 13.1 | 6.5 |  | 12.8 | 6.3 |  | 12.8 | 6.3 |  | 9.8 | 6.5 |  | 3 | [5 empty] | 2.4
48 | 0.75 | 8 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 14.7 | 6.5 | 1.2 | 19.9 | 9 | 4.9 | 25.9 | 14.2 | 6.5 | 30.4 | 19 | 11.4 | 25.2 | 15.2 | 6.3 | 19.3 | 6.9 | 4.5 | 6.3 | [5 empty] | 6.3
48 | 0.75 | 9 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 1.2 | 20.9 | 12.8 | 6.3 | 26.4 | 15 | 8.5 | 31.9 | 19 | 12.2 | 25.2 | 16.9 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 10 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 11 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 12 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 15 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 20 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 0.75 | 25 | 6.3 |  |  | 7 |  |  | 12.6 |  |  | 19 | 6.5 | 4.8 | 22.2 | 12.8 | 6.3 | 26.4 | 17.5 | 8.5 | 31.9 | 19 | 12.6 | 25.2 | 18.5 | 6.3 | 19.7 | 9.9 | 4.5 | 6.3 |  |  | 1.2 |  |  | 6.3
48 | 1 | 2
48 | 1 | 4 | [21 empty] | 3.3
48 | 1 | 6 | 5.4 |  |  | 7 |  |  | 6.3 |  |  | 6.6 | 6.5 |  | 12.6 | 6.3 |  | 18.3 | 11.8 |  | 17.1 | 6.3 | 0.3 | 18.2 | 6.3 |  | 13.1 | 6.5 |  | 6.3 |  |  | 3.2 |  |  | 6.3
48 | 1 | 8 | 15.2 | 5.1 |  | 14 | 7 |  | 19.4 | 6.3 |  | 26.3 | 15.4 | 6.4 | 32 | 19 | 12.6 | 39.5 | 22.9 | 13.1 | 38.3 | 26.1 | 14.3 | 38.7 | 23.5 | 19 | 26.4 | 18.8 | 10 | 11.7 | 6.3 |  | 6.5 | 6.5 |  | 12.7 | 6.3
48 | 1 | 9 | 15.1 | 4.8 |  | 15.4 | 7 |  | 19.2 | 9.9 |  | 32.9 | 19.7 | 6.5 | 35.3 | 26.7 | 12.8 | 48.6 | 29.4 | 19.6 | 51.3 | 35.2 | 24.2 | 42.3 | 31.9 | 19.8 | 33 | 19.7 | 12.1 | 12.7 | 6.3 |  | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 10 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 32.9 | 19.7 | 6.5 | 38.2 | 27.3 | 13.2 | 49.6 | 32.4 | 21.2 | 51.2 | 35.3 | 25.4 | 44.6 | 32.3 | 25.3 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 11 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 33 | 19.7 | 6.5 | 38.2 | 29.6 | 13.5 | 49.7 | 32.4 | 21.2 | 51.2 | 38.2 | 25.9 | 44.6 | 32.4 | 25.4 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 12 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 33 | 19.7 | 6.5 | 38.2 | 29.6 | 13.5 | 49.7 | 32.4 | 21.2 | 51.2 | 38.2 | 25.9 | 44.6 | 32.4 | 25.4 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 15 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 33 | 19.7 | 6.5 | 38.2 | 29.6 | 13.5 | 49.7 | 32.4 | 21.2 | 51.2 | 38.2 | 25.9 | 44.6 | 32.4 | 25.4 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 20 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 33 | 19.7 | 6.5 | 38.2 | 29.6 | 13.5 | 49.7 | 32.4 | 21.2 | 51.2 | 38.2 | 25.9 | 44.6 | 32.4 | 25.4 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1 | 25 | 15.1 | 4.8 |  | 15.4 | 7 |  | 23.9 | 10.5 |  | 33 | 19.7 | 6.5 | 38.2 | 29.6 | 13.5 | 49.7 | 32.4 | 21.2 | 51.2 | 38.2 | 25.9 | 44.6 | 32.4 | 25.4 | 33.1 | 19.7 | 12.1 | 12.7 | 6.3 | 1.9 | 6.8 | 6.5 |  | 12.7 | 6.3
48 | 1.25 | 2
48 | 1.25 | 4 | [21 empty] | 3.3
48 | 1.25 | 6 | 6.2 |  |  | 7 |  |  | 6.3 |  |  | 12.4 | 6.5 |  | 19.1 | 6.3 |  | 19.6 | 13.1 |  | 19 | 6.5 | 2.2 | 18.3 | 6.3 |  | 13.2 | 6.5 |  | 6.3 |  |  | 6.5 |  |  | 6.3
48 | 1.25 | 8 | 17.3 | 6.3 |  | 18.5 | 7 |  | 25.4 | 12.6 |  | 31.9 | 19.7 | 6.8 | 37.2 | 21.8 | 12.8 | 43.6 | 30.7 | 17.3 | 44.4 | 31.6 | 19.1 | 42.7 | 27.3 | 19.1 | 28.8 | 25.4 | 13.1 | 14.8 | 6.5 | 0.9 | 13.1 | 6.5 |  | 12.8 | 6.3
48 | 1.25 | 9 | 21.2 | 9.7 |  | 21.7 | 12.8 | 3.7 | 30.8 | 19.1 | 7.3 | 43.2 | 26.3 | 15 | 46.1 | 34.5 | 21 | 58.5 | 39.7 | 26.6 | 54 | 44.9 | 31.9 | 56.8 | 38.3 | 28.5 | 39.9 | 32.6 | 19.7 | 25.6 | 10.1 | 6.2 | 17.3 | 6.5 | 2.1 | 19.2 | 8.3
48 | 1.25 | 10 | 22.3 | 12.1 |  | 26.8 | 14 | 3.6 | 34.6 | 22.6 | 11 | 46.4 | 32.9 | 22.9 | 52.6 | 39.4 | 27.6 | 64.1 | 49 | 35 | 63.9 | 51.6 | 39.2 | 64.1 | 46 | 38.3 | 49.1 | 33.1 | 25 | 28.4 | 17.1 | 6.4 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.25 | 11 | 22.3 | 12.1 |  | 26.7 | 14 | 3.6 | 34.6 | 25.4 | 12.5 | 54.2 | 35.7 | 25.9 | 57.4 | 40.9 | 32.5 | 64.3 | 50 | 35.1 | 63.9 | 53 | 42.9 | 64.1 | 50.8 | 42.7 | 50.8 | 36.5 | 26.1 | 31.6 | 17.9 | 6.5 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.25 | 12 | 22.3 | 12.1 |  | 26.7 | 14 | 3.5 | 36.4 | 25.4 | 12.5 | 55 | 36 | 26.2 | 57.4 | 41.4 | 32.4 | 65.8 | 50.8 | 35.1 | 64.2 | 53 | 42.9 | 64.4 | 50.8 | 42.7 | 50.8 | 36.5 | 26.1 | 31.9 | 17.7 | 6.5 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.25 | 15 | 22.3 | 12.1 |  | 26.7 | 14 | 3.5 | 36.4 | 25.4 | 12.5 | 55 | 36 | 26.2 | 57.2 | 42.5 | 32.4 | 65.8 | 50.8 | 35.1 | 64.2 | 53 | 42.9 | 64.4 | 50.8 | 42.7 | 50.8 | 36.5 | 26.1 | 31.9 | 17.6 | 6.5 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.25 | 20 | 22.3 | 12.1 |  | 26.7 | 14 | 3.5 | 36.4 | 25.4 | 12.5 | 55 | 36 | 26.2 | 57.2 | 42.5 | 32.4 | 65.8 | 50.8 | 35.1 | 64.2 | 53 | 42.9 | 64.4 | 50.8 | 42.7 | 50.8 | 36.5 | 26.1 | 31.9 | 17.6 | 6.5 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.25 | 25 | 22.3 | 12.1 |  | 26.7 | 14 | 3.5 | 36.4 | 25.4 | 12.5 | 55 | 36 | 26.2 | 57.2 | 42.5 | 32.4 | 65.8 | 50.8 | 35.1 | 64.2 | 53 | 42.9 | 64.4 | 50.8 | 42.7 | 50.8 | 36.5 | 26.1 | 31.9 | 17.6 | 6.5 | 19.6 | 9.4 | 3.6 | 19.2 | 8.5 | 4.5
48 | 1.5 | 2
48 | 1.5 | 4 | [21 empty] | 3.3
48 | 1.5 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.3 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 6.8 |  |  | 6.5 |  |  | 6.3
48 | 1.5 | 8 | 17.3 | 6.3 |  | 21.1 | 8 | 5.2 | 25.6 | 12.6 | 1.9 | 33.6 | 23.5 | 13.1 | 42.7 | 23 | 13.5 | 45.1 | 36 | 19.6 | 46.8 | 31.9 | 19.2 | 42.7 | 30.4 | 24.6 | 32.3 | 25.4 | 13.1 | 17.1 | 8.1 | 6.3 | 13.2 | 6.5 |  | 12.8 | 6.3
48 | 1.5 | 9 | 22.3 | 12.6 |  | 27.7 | 14.1 | 6.8 | 34.2 | 21.4 | 12.6 | 48.8 | 32.8 | 20.2 | 50.6 | 38.8 | 25.5 | 60.4 | 46.3 | 33.1 | 61.1 | 49.5 | 38.4 | 57.4 | 38.4 | 31.7 | 45.9 | 32.9 | 19.8 | 26.5 | 12.6 | 6.3 | 19.7 | 13.1 | 2.1 | 26.5 | 12.8
48 | 1.5 | 10 | 28.5 | 12.6 | 5.4 | 32.8 | 19 | 7 | 45 | 31.5 | 15.8 | 54.6 | 44.9 | 32.7 | 58.4 | 47.7 | 35.1 | 71.5 | 60.8 | 48.8 | 72.2 | 63.6 | 49.6 | 70 | 54.2 | 43.7 | 52.9 | 42.5 | 31.7 | 34 | 23 | 12.6 | 27.2 | 13.2 | 6.5 | 32 | 12.9 | 6.3
48 | 1.5 | 11 | 30 | 15.6 | 5.4 | 36.4 | 22.2 | 10.7 | 47 | 34.7 | 19 | 63.7 | 46.8 | 37.4 | 68.7 | 57.5 | 45.9 | 77.1 | 66.1 | 51.7 | 78.6 | 67.5 | 52 | 73.5 | 63.8 | 51.1 | 59.4 | 48.6 | 36.2 | 38.3 | 27.6 | 12.9 | 34.5 | 16.4 | 7.2 | 33.7 | 16.3 | 6.3
48 | 1.5 | 12 | 30.1 | 15.3 | 5.4 | 38.8 | 22.2 | 10.8 | 50.2 | 34.8 | 19 | 65.9 | 51.4 | 38.5 | 69.3 | 58.6 | 47.7 | 76.8 | 66.3 | 55.3 | 79.5 | 70.4 | 56.1 | 77 | 64.5 | 51.4 | 60.2 | 49.2 | 37.2 | 38.4 | 29.3 | 14.7 | 34.4 | 16.4 | 7.2 | 33.7 | 16.8 | 6.3
48 | 1.5 | 15 | 30.1 | 15.3 | 5.4 | 38.8 | 22.2 | 10.9 | 50.2 | 34.7 | 19.9 | 65.9 | 51.4 | 38.4 | 70 | 59.1 | 48.8 | 76.9 | 67.6 | 55.2 | 79.4 | 70.4 | 55.9 | 77 | 64.5 | 51.5 | 60.2 | 49.2 | 37.2 | 38.5 | 29.3 | 14.7 | 34.4 | 16.4 | 7.2 | 33.7 | 16.9 | 6.3
48 | 1.5 | 20 | 30.1 | 15.3 | 5.4 | 38.8 | 22.2 | 10.9 | 50.2 | 34.7 | 19.9 | 65.9 | 51.4 | 38.4 | 70 | 59.1 | 48.8 | 76.9 | 67.6 | 55.2 | 79.4 | 70.4 | 55.9 | 77 | 64.5 | 51.5 | 60.2 | 49.2 | 37.2 | 38.5 | 29.3 | 14.7 | 34.4 | 16.4 | 7.2 | 33.7 | 16.9 | 6.3
48 | 1.5 | 25 | 30.1 | 15.3 | 5.4 | 38.8 | 22.2 | 10.9 | 50.2 | 34.7 | 19.9 | 65.9 | 51.4 | 38.4 | 70 | 59.1 | 48.8 | 76.9 | 67.6 | 55.2 | 79.4 | 70.4 | 55.9 | 77 | 64.5 | 51.5 | 60.2 | 49.2 | 37.2 | 38.5 | 29.3 | 14.7 | 34.4 | 16.4 | 7.2 | 33.7 | 16.9 | 6.3
48 | 1.75 | 2
48 | 1.75 | 4 | [21 empty] | 3.3
48 | 1.75 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.3 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 1.75 | 8 | 18.2 | 6.3 |  | 21.1 | 12.5 | 5.2 | 25.6 | 12.8 | 4.5 | 33.6 | 23.3 | 13.1 | 42.7 | 24.5 | 15.4 | 45.1 | 36 | 20 | 46.8 | 37.4 | 21 | 42.7 | 31 | 24.6 | 32.6 | 25.4 | 13.1 | 18.6 | 11.3 | 6.3 | 13.2 | 6.5 | 0.3 | 12.8 | 8.7
48 | 1.75 | 9 | 25.4 | 12.6 | 1.7 | 29.6 | 14.1 | 6.8 | 40.4 | 25.4 | 13.6 | 52.7 | 33.1 | 21.1 | 51 | 42.5 | 25.9 | 63.2 | 49.2 | 33.1 | 62.1 | 49.5 | 38.9 | 62.4 | 41.1 | 31.9 | 46.3 | 32.9 | 21.5 | 26.5 | 15.7 | 7.5 | 24.9 | 13.1 | 6.5 | 28.4 | 12.8
48 | 1.75 | 10 | 34.5 | 19 | 6.3 | 38.3 | 23.4 | 7 | 47.5 | 37.2 | 20.5 | 60.3 | 46.1 | 33.9 | 62.7 | 51.2 | 38.7 | 75.1 | 63.1 | 52.8 | 76.3 | 66.3 | 52 | 73.5 | 61.8 | 44.7 | 56.8 | 46.3 | 32.9 | 37.3 | 25.4 | 13.3 | 29 | 19.6 | 9.4 | 32.1 | 13.4 | 6.3
48 | 1.75 | 11 | 37.4 | 23.3 | 6.4 | 47.1 | 32.3 | 14.7 | 54 | 42.9 | 26.2 | 71.8 | 52.9 | 45.9 | 75.9 | 61.8 | 50 | 83 | 73.9 | 62.7 | 83.6 | 76.1 | 58.7 | 77 | 70.6 | 54.3 | 65.3 | 52.9 | 38.2 | 48.1 | 33.3 | 19.4 | 35.1 | 21.9 | 13 | 38.1 | 19.9 | 6.3
48 | 1.75 | 12 | 41.7 | 25.4 | 12.6 | 51.3 | 35.4 | 18.7 | 65.7 | 44.6 | 32.3 | 74.6 | 63.8 | 46.2 | 80.6 | 67.5 | 57.7 | 86.4 | 80.1 | 67.1 | 89.8 | 77.8 | 65.5 | 87 | 72.8 | 62.4 | 68.6 | 59.3 | 43.9 | 49.6 | 36.8 | 25.8 | 46.3 | 25.3 | 13.1 | 43 | 20.3 | 12.6
48 | 1.75 | 15 | 41.6 | 26.2 | 12.6 | 51.9 | 39.4 | 18.7 | 65.7 | 44.9 | 32.2 | 78.6 | 63.9 | 48.2 | 82.6 | 73.4 | 60.4 | 87.1 | 80.7 | 68.2 | 90.8 | 80.2 | 65.9 | 87 | 72.8 | 62.6 | 70.9 | 58.6 | 43.9 | 51.3 | 38.2 | 28.2 | 46.3 | 26.1 | 13.1 | 42.9 | 20.4 | 12.6
48 | 1.75 | 20 | 41.6 | 26.2 | 12.6 | 51.9 | 39.4 | 18.7 | 65.7 | 44.9 | 32.2 | 78.6 | 63.9 | 48.2 | 82.6 | 73.4 | 60.4 | 87.1 | 80.7 | 68.2 | 90.6 | 80.2 | 65.9 | 87 | 72.8 | 62.6 | 70.9 | 58.6 | 43.9 | 51.3 | 38.2 | 28.2 | 46.3 | 26.1 | 13.1 | 42.9 | 20.4 | 12.6
48 | 1.75 | 25 | 41.6 | 26.2 | 12.6 | 51.9 | 39.4 | 18.7 | 65.7 | 44.9 | 32.2 | 78.6 | 63.9 | 48.2 | 82.6 | 73.4 | 60.4 | 87.1 | 80.7 | 68.2 | 90.6 | 80.2 | 65.9 | 87 | 72.8 | 62.6 | 70.9 | 58.6 | 43.9 | 51.3 | 38.2 | 28.2 | 46.3 | 26.1 | 13.1 | 42.9 | 20.4 | 12.6
48 | 2 | 2
48 | 2 | 4 | [21 empty] | 3.3
48 | 2 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 2 | 8 | 18.2 | 6.3 |  | 21.1 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 25.4 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 16.2 | 12.5
48 | 2 | 9 | 25.4 | 12.6 | 3.4 | 29.6 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 35.6 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 41 | 31.9 | 46.4 | 32.9 | 22.7 | 30.3 | 16.1 | 10.8 | 25 | 13.1 | 6.5 | 29.5 | 12.8
48 | 2 | 10 | 32.9 | 19 | 6.4 | 40.7 | 26.4 | 7.8 | 50.8 | 37.2 | 23.2 | 60.3 | 51.8 | 38.9 | 64.3 | 52.3 | 40.6 | 78.2 | 67.5 | 52.9 | 76.9 | 67.6 | 52 | 73.6 | 61.8 | 44.9 | 58.3 | 46.3 | 35.5 | 41.5 | 25.5 | 13.9 | 29.2 | 19.7 | 10.9 | 35.2 | 19.1 | 6.3
48 | 2 | 11 | 42.1 | 25.4 | 8.2 | 51.7 | 35.3 | 18 | 59.6 | 45 | 32.1 | 73.3 | 59.6 | 49.4 | 77.4 | 64.7 | 54.8 | 86.5 | 77.2 | 66.8 | 86.8 | 76.1 | 62.9 | 81.5 | 70.7 | 56.3 | 70.9 | 55.3 | 39.5 | 48.6 | 35.5 | 24.3 | 41.1 | 22.1 | 13.1 | 41.6 | 20 | 6.3
48 | 2 | 12 | 47.5 | 30.2 | 19.1 | 54.5 | 42.6 | 23.5 | 70.3 | 51.5 | 38.8 | 79.8 | 67.8 | 56.7 | 85.9 | 73.8 | 64.7 | 90.1 | 83.3 | 73.1 | 91.6 | 83.3 | 74.2 | 87.6 | 75.5 | 64.7 | 75.3 | 63.3 | 50.3 | 56.3 | 39.7 | 31.6 | 49 | 35.4 | 15.1 | 49.4 | 26.9 | 12.7
48 | 2 | 15 | 52.8 | 30.4 | 19.3 | 61.9 | 49.4 | 23.8 | 76.4 | 57.4 | 40.8 | 86.2 | 72.6 | 61 | 89.7 | 78.6 | 70.1 | 91.8 | 87.1 | 78.8 | 95.4 | 87.5 | 76.6 | 91.2 | 79.4 | 69.1 | 77.7 | 66.7 | 57.5 | 65.1 | 49.6 | 36.9 | 53.6 | 40.6 | 19.4 | 52.7 | 32 | 16.6
48 | 2 | 20 | 52.8 | 30.4 | 19.3 | 61.9 | 49.4 | 23.8 | 76.4 | 57.4 | 40.8 | 86.2 | 72.6 | 61 | 89.7 | 78.6 | 70.1 | 91.8 | 87.1 | 78.8 | 95.4 | 87.5 | 76.6 | 91.2 | 79.4 | 69.1 | 78.4 | 66.7 | 57.5 | 65.1 | 49.6 | 36.9 | 53.6 | 40.6 | 19.4 | 52.7 | 32 | 16.6
48 | 2 | 25 | 52.8 | 30.4 | 19.3 | 61.9 | 49.4 | 23.8 | 76.4 | 57.4 | 40.8 | 86.2 | 72.6 | 61 | 89.7 | 78.6 | 70.1 | 91.8 | 87.1 | 78.8 | 95.4 | 87.5 | 76.6 | 91.2 | 79.4 | 69.1 | 78.4 | 66.7 | 57.5 | 65.1 | 49.6 | 36.9 | 53.6 | 40.6 | 19.4 | 52.7 | 32 | 16.6
48 | 2.25 | 2
48 | 2.25 | 4 | [21 empty] | 3.3
48 | 2.25 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 2.25 | 8 | 20.1 | 6.3 |  | 21.1 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 2.25 | 9 | 25.4 | 12.6 | 5.9 | 29.6 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44 | 31.9 | 46.4 | 34.6 | 22.7 | 30.3 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 2.25 | 10 | 32.9 | 19 | 6.4 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 60.3 | 52.6 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 61.8 | 44.9 | 58.6 | 46.4 | 35.5 | 43.3 | 25.5 | 13.9 | 29.2 | 19.7 | 11.1 | 37.4 | 19.1 | 6.3
48 | 2.25 | 11 | 42.1 | 25.4 | 8.2 | 51.7 | 35.4 | 18.2 | 59.7 | 46.5 | 32.6 | 73.3 | 60.4 | 49.4 | 77 | 67.7 | 57.8 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 72 | 56.3 | 71.7 | 55.1 | 43.9 | 49.8 | 37.2 | 25.5 | 41.1 | 25.1 | 14.9 | 44.6 | 25.5 | 6.3
48 | 2.25 | 12 | 50.6 | 30.2 | 19.7 | 59 | 49.6 | 25.3 | 72.2 | 53.6 | 39 | 84.4 | 72.1 | 61 | 86 | 75.4 | 66.2 | 92.5 | 84.7 | 77.9 | 92.6 | 86.2 | 75.8 | 92.2 | 77.3 | 70.3 | 78.8 | 66.8 | 55.8 | 57.6 | 43.1 | 36 | 51.8 | 39.3 | 19 | 52 | 26.9 | 14.5
48 | 2.25 | 15 | 60.5 | 37.8 | 28 | 70.7 | 57 | 28.3 | 79.8 | 64.1 | 51 | 92.6 | 83.5 | 68 | 90.9 | 86.3 | 78.6 | 98 | 90.6 | 81.1 | 99.2 | 93.8 | 87.3 | 95 | 85.8 | 77.1 | 84.8 | 76.1 | 66.4 | 70.2 | 57.8 | 45 | 68.5 | 47.6 | 31.3 | 62.4 | 38.6 | 25.5
48 | 2.25 | 20 | 60.8 | 38.4 | 28.1 | 71 | 57 | 28.3 | 79.8 | 64.1 | 51 | 92.6 | 83.5 | 68 | 90.9 | 86.3 | 78.7 | 98 | 90.6 | 81.2 | 99.2 | 93.7 | 87.3 | 95 | 85.8 | 77.1 | 84.8 | 76.1 | 66.4 | 70.2 | 62.5 | 45 | 68.5 | 47.6 | 31.7 | 62.4 | 38.6 | 25.5
48 | 2.25 | 25 | 60.8 | 38.4 | 28.1 | 71 | 57 | 28.3 | 79.8 | 64.1 | 51 | 92.6 | 83.5 | 68 | 90.9 | 86.3 | 78.7 | 98 | 90.6 | 81.2 | 99.2 | 93.7 | 87.3 | 95 | 85.8 | 77.1 | 84.8 | 76.1 | 66.4 | 70.2 | 62.5 | 45 | 68.5 | 47.6 | 31.7 | 62.4 | 38.6 | 25.5
48 | 2.75 | 2
48 | 2.75 | 4 | [21 empty] | 3.3
48 | 2.75 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 2.75 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 2.75 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 2.75 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 33 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 2.75 | 11 | 44.1 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 46.5 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.2 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.6 | 29.2 | 7.9
48 | 2.75 | 12 | 54.7 | 32.7 | 22.3 | 60.3 | 49.7 | 25.3 | 74.4 | 56.3 | 38.9 | 85.8 | 73.8 | 64.2 | 86.4 | 79.7 | 66.2 | 92.9 | 84.9 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 55.8 | 61.8 | 46.2 | 36.4 | 52.6 | 40 | 22.7 | 56.8 | 33.2 | 20.1
48 | 2.75 | 15 | 69.8 | 50.4 | 42.4 | 80.3 | 74 | 44.6 | 87.1 | 77 | 58.5 | 94.2 | 89.2 | 81 | 98.3 | 94 | 88.8 | 100 | 95 | 90.7 | 100 | 96.6 | 94.1 | 100 | 92.1 | 85.8 | 91.4 | 84.3 | 73.8 | 78.9 | 70.2 | 57.9 | 77.8 | 62.9 | 44 | 70.3 | 51.1 | 31.9
48 | 2.75 | 20 | 76.2 | 52.4 | 43.3 | 85.9 | 71.1 | 50.5 | 90.9 | 76.2 | 60 | 96.5 | 91.3 | 81.2 | 100 | 95.2 | 92.3 | 100 | 96.8 | 91.8 | 100 | 97.4 | 93.1 | 100 | 93.7 | 89.8 | 93.5 | 88.2 | 78.8 | 85.3 | 73 | 63.7 | 79 | 62.8 | 47.1 | 70.8 | 56.2 | 39.7
48 | 2.75 | 25 | 76.2 | 52.4 | 43.3 | 85.9 | 71.1 | 50.5 | 90.9 | 76.2 | 60 | 96.5 | 91.3 | 81.2 | 100 | 95.2 | 92.3 | 100 | 96.8 | 91.8 | 100 | 97.4 | 93.1 | 100 | 93.7 | 89.8 | 93.5 | 88.2 | 78.8 | 85.3 | 73 | 63.7 | 79 | 62.8 | 47.1 | 70.8 | 56.2 | 39.7
48 | 3 | 2
48 | 3 | 4 | [21 empty] | 3.3
48 | 3 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 3 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 3 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 3 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 32.9 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 3 | 11 | 45.7 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 49.3 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.1 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.6 | 29.2 | 7.9
48 | 3 | 12 | 54.7 | 34.8 | 22.3 | 60.3 | 49.7 | 26.7 | 74.4 | 56.3 | 38.9 | 85.8 | 73.8 | 64.2 | 86.5 | 79.7 | 66.2 | 92.7 | 84.9 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 55.8 | 61.8 | 48.4 | 36.4 | 52.6 | 40 | 22.7 | 57.3 | 37 | 20.1
48 | 3 | 15 | 71.7 | 54 | 43.1 | 84.5 | 74.9 | 48.5 | 87.3 | 78.5 | 60.6 | 97.6 | 90 | 84.4 | 99.6 | 95.7 | 89.7 | 100 | 94.4 | 90.7 | 100 | 97.7 | 95.1 | 100 | 94.6 | 85.7 | 94 | 85.6 | 77.7 | 85.8 | 71.2 | 61.2 | 79.4 | 65.1 | 45.3 | 71.7 | 55.2 | 38.2
48 | 3 | 20 | 80.7 | 62.6 | 49.8 | 88.3 | 78.9 | 60.4 | 94.5 | 82.8 | 68.7 | 100 | 94.2 | 85.1 | 100 | 99.7 | 93.5 | 100 | 96.8 | 92.7 | 100 | 100 | 94.8 | 100 | 97.6 | 92.8 | 95.6 | 91.4 | 81.3 | 89.2 | 81.6 | 69.2 | 82.1 | 73.8 | 51.4 | 79.9 | 63.2 | 50.7
48 | 3 | 25 | 80.7 | 62.6 | 49.8 | 88.3 | 78.9 | 60.4 | 94.5 | 82.8 | 68.7 | 100 | 94.2 | 85.1 | 100 | 99.7 | 93.5 | 100 | 96.8 | 92.7 | 100 | 100 | 94.8 | 100 | 97.6 | 92.8 | 95.6 | 91.4 | 81.3 | 89.2 | 81.6 | 69.2 | 82.1 | 73.8 | 51.4 | 79.9 | 63.2 | 50.7
48 | 3.5 | 2
48 | 3.5 | 4 | [21 empty] | 3.3
48 | 3.5 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 3.5 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 3.5 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 3.5 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 32.9 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 3.5 | 11 | 45.7 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 49.3 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.1 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.8 | 29.2 | 7.9
48 | 3.5 | 12 | 54.7 | 34.9 | 22.3 | 60.3 | 49.7 | 29.3 | 74.4 | 57.5 | 40.5 | 85.8 | 74 | 65.2 | 86.5 | 79.7 | 66.2 | 93.1 | 85.7 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 57.4 | 61.8 | 48.4 | 36.4 | 52.6 | 40.6 | 22.7 | 57.3 | 37 | 20.1
48 | 3.5 | 15 | 73.6 | 59.8 | 42.9 | 85.1 | 76 | 50.9 | 90.7 | 79.6 | 61.5 | 98.7 | 91.1 | 85 | 100 | 96.1 | 90.4 | 100 | 95 | 91.5 | 100 | 98.1 | 95.3 | 100 | 95.8 | 89.6 | 95 | 85.6 | 77.9 | 88.3 | 73.9 | 63.6 | 81.2 | 71 | 51.9 | 75.9 | 57.4 | 38.6
48 | 3.5 | 20 | 86.9 | 81.5 | 61.8 | 97.1 | 89.4 | 72 | 99.8 | 90.5 | 81.9 | 100 | 100 | 91.3 | 100 | 100 | 100 | 100 | 100 | 95.6 | 100 | 100 | 98.6 | 100 | 100 | 95.8 | 100 | 94.7 | 89 | 96.2 | 87.2 | 79.8 | 92.4 | 82.9 | 71.7 | 90.3 | 77.4 | 59.3
48 | 3.5 | 25 | 86.9 | 81.6 | 61.8 | 97.1 | 89.4 | 72 | 99.8 | 90.5 | 81.9 | 100 | 100 | 91.3 | 100 | 100 | 100 | 100 | 100 | 95.6 | 100 | 100 | 98.6 | 100 | 100 | 95.8 | 100 | 94.7 | 89 | 96.2 | 89.7 | 79.7 | 93.5 | 82.9 | 71.7 | 90.3 | 77.6 | 59.3
48 | 4 | 2
48 | 4 | 4 | [21 empty] | 3.3
48 | 4 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 4 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 4 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 4 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 32.9 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 4 | 11 | 45.7 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 49.3 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.1 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.8 | 29.2 | 7.9
48 | 4 | 12 | 54.7 | 34.9 | 22.3 | 60.3 | 49.7 | 29.3 | 74.4 | 57.5 | 40.4 | 85.8 | 74 | 65.2 | 86.5 | 79.7 | 66.2 | 93.1 | 85.7 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 57.4 | 61.8 | 48.4 | 36.4 | 52.6 | 40.6 | 22.7 | 57.3 | 37 | 20.1
48 | 4 | 15 | 73.8 | 59.8 | 45 | 85.2 | 76.5 | 55 | 90.7 | 79.8 | 61.5 | 98.7 | 91.3 | 86.1 | 100 | 96.2 | 92.2 | 100 | 95.7 | 91.5 | 100 | 98.1 | 95.3 | 100 | 95.8 | 89.6 | 95 | 86 | 78.6 | 88.3 | 76.1 | 63.6 | 82.2 | 71 | 52.9 | 78.4 | 57.4 | 39.9
48 | 4 | 20 | 95.5 | 88.2 | 77.3 | 98.6 | 90.7 | 81.8 | 100 | 96.8 | 89.6 | 100 | 100 | 96 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.2 | 91.7 | 100 | 95.6 | 89.9 | 95.8 | 91.3 | 82.1 | 99 | 87.4 | 79.5
48 | 4 | 25 | 95.4 | 88.2 | 77.3 | 99.4 | 90.7 | 81.7 | 100 | 96.8 | 90.4 | 100 | 100 | 96 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 92.1 | 100 | 96.1 | 90 | 97.2 | 91.4 | 83 | 99 | 87.8 | 79.5
48 | 4.5 | 2
48 | 4.5 | 4 | [21 empty] | 3.3
48 | 4.5 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 4.5 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 4.5 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 4.5 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 32.9 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 4.5 | 11 | 45.7 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 49.3 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.1 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.8 | 29.2 | 7.9
48 | 4.5 | 12 | 54.7 | 34.9 | 22.3 | 60.3 | 49.7 | 29.3 | 74.4 | 57.5 | 40.4 | 85.8 | 74 | 65.2 | 86.5 | 79.7 | 66.2 | 93.1 | 85.7 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 57.4 | 61.8 | 48.4 | 36.4 | 52.6 | 40.6 | 22.7 | 57.3 | 37 | 20.1
48 | 4.5 | 15 | 73.8 | 59.8 | 47.1 | 85.2 | 77.8 | 55 | 90.7 | 79.8 | 65.1 | 98.7 | 91.5 | 86.3 | 100 | 96.2 | 92.2 | 100 | 96.1 | 91.8 | 100 | 98.1 | 95.3 | 100 | 95.8 | 89.6 | 95 | 86.3 | 78.6 | 88.3 | 76.3 | 64 | 82.2 | 71 | 53.2 | 78.4 | 61.6 | 40.6
48 | 4.5 | 20 | 99.1 | 91.7 | 81.6 | 100 | 94.5 | 87.3 | 100 | 98.7 | 91.9 | 100 | 100 | 98.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 94 | 100 | 96.8 | 90.7 | 100 | 94.7 | 89.5 | 100 | 94.2 | 82.5
48 | 4.5 | 25 | 100 | 94.5 | 89.5 | 100 | 96.1 | 89 | 100 | 100 | 96.5 | 100 | 100 | 97.6 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97 | 100 | 99.2 | 93.1 | 100 | 97.4 | 91.6 | 100 | 95.2 | 87.3
48 | 5 | 2
48 | 5 | 4 | [21 empty] | 3.3
48 | 5 | 6 | 6.3 |  |  | 7.3 | 1.6 |  | 10.7 |  |  | 13.1 | 6.5 |  | 19.1 | 6.5 |  | 19.6 | 13.1 |  | 19.1 | 6.5 | 5.5 | 19.1 | 6.3 |  | 13.2 | 6.5 |  | 8 |  |  | 6.5 |  |  | 6.3
48 | 5 | 8 | 20.1 | 6.3 |  | 22.7 | 12.5 | 5.2 | 25.7 | 12.8 | 6.3 | 33.6 | 25.4 | 13.3 | 42.7 | 24.9 | 19 | 45.1 | 36 | 20 | 46.8 | 38 | 21 | 42.7 | 31 | 24.6 | 32.6 | 26.1 | 13.1 | 19 | 11.3 | 6.3 | 14.2 | 6.5 | 0.3 | 18.4 | 12.5
48 | 5 | 9 | 25.4 | 12.6 | 5.9 | 30.9 | 15.9 | 7 | 40.4 | 25.4 | 14.5 | 52.9 | 38.1 | 23.3 | 51.3 | 42.5 | 27.6 | 65.7 | 49.2 | 33.9 | 62.1 | 50.7 | 38.9 | 62.4 | 44.5 | 31.9 | 46.4 | 34.6 | 22.7 | 31.7 | 16.1 | 12.4 | 25 | 13.1 | 6.5 | 31.2 | 12.8
48 | 5 | 10 | 35.2 | 19 | 9.2 | 41.2 | 28.1 | 13.6 | 50.8 | 37.2 | 25.3 | 64.2 | 54.2 | 39.2 | 64.5 | 52.3 | 40.6 | 78.2 | 67.5 | 53.1 | 76.9 | 67.6 | 52 | 74 | 63.8 | 45.7 | 58.6 | 47.9 | 35.5 | 43.3 | 25.5 | 17.2 | 32.9 | 21.5 | 11.1 | 37.4 | 19.1 | 6.3
48 | 5 | 11 | 45.7 | 26.3 | 12.6 | 51.7 | 36.9 | 18.2 | 59.7 | 49.3 | 32.6 | 74.1 | 66.1 | 52.1 | 77.9 | 68.4 | 57.9 | 86.8 | 79.6 | 66.8 | 86.8 | 76.2 | 67 | 81.5 | 75.1 | 56.3 | 71.7 | 57.1 | 44.2 | 49.8 | 38.3 | 30.1 | 41.2 | 28.3 | 16.7 | 44.8 | 29.2 | 7.9
48 | 5 | 12 | 54.7 | 34.9 | 22.3 | 60.3 | 49.7 | 29.3 | 74.4 | 57.5 | 40.4 | 85.8 | 74 | 65.2 | 86.5 | 79.7 | 66.2 | 93.1 | 85.7 | 78.6 | 93.6 | 87.1 | 77.7 | 93.2 | 79.6 | 70.3 | 81 | 70 | 57.4 | 61.8 | 48.4 | 36.4 | 52.6 | 40.6 | 22.7 | 57.3 | 37 | 20.1
48 | 5 | 15 | 73.8 | 59.8 | 47.1 | 85.2 | 77.8 | 55 | 90.9 | 79.8 | 65.1 | 98.7 | 91.5 | 86.3 | 100 | 96.2 | 92.2 | 100 | 96.1 | 91.8 | 100 | 98.1 | 95.3 | 100 | 95.8 | 89.6 | 95 | 86.3 | 78.6 | 88.3 | 76.3 | 64 | 82.2 | 71 | 53.2 | 78.4 | 61.6 | 40.6
48 | 5 | 20 | 100 | 94.1 | 82.8 | 100 | 94.7 | 87.6 | 100 | 98.7 | 93.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 96.3 | 100 | 97.3 | 91.5 | 100 | 96 | 90.5 | 100 | 95 | 82.8
48 | 5 | 25 | 100 | 99.1 | 93.9 | 100 | 100 | 93.1 | 100 | 100 | 98.3 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 96.9 | 100 | 100 | 94.5 | 100 | 100 | 93.5
72 | 0.25 | 2
72 | 0.25 | 4
72 | 0.25 | 6
72 | 0.25 | 8
72 | 0.25 | 9
72 | 0.25 | 10
72 | 0.25 | 11
72 | 0.25 | 12
72 | 0.25 | 15
72 | 0.25 | 20
72 | 0.25 | 25
72 | 0.5 | 2
72 | 0.5 | 4
72 | 0.5 | 6 | [21 empty] | 9.5
72 | 0.5 | 8 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 9 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 10 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 11 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 12 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 15 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 20 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.5 | 25 | [12 empty] | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5
72 | 0.75 | 2
72 | 0.75 | 4
72 | 0.75 | 6 | [12 empty] | 6.7 |  |  | 9.3 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9
72 | 0.75 | 8 | 6.7 |  |  | 2.4 |  |  | 9.5 |  |  | 9.9 |  |  | 11.6 | 4.3 |  | 19.7 | 9.9 |  | 19.3 | 9.5 | 5.4 | 22.8 | 9.5 |  | 13.8 | 6.9 |  | 4
72 | 0.75 | 9 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 10 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 11 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 12 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 15 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 20 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 0.75 | 25 | 6.7 |  |  | 2.3 |  |  | 9.5 |  |  | 9.9 |  |  | 18.5 | 9.5 |  | 19.9 | 9.9 |  | 22.6 | 9.5 | 6.3 | 27 | 9.5 |  | 17.9 | 8.9 |  | 4.2
72 | 1 | 2
72 | 1 | 4
72 | 1 | 6 | 0.5 | [5 empty] | 6.7 |  |  | 9.2 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9
72 | 1 | 8 | 9.5 |  |  | 10.6 |  |  | 10.2 |  |  | 19.7 | 9.9 |  | 19.1 | 9.5 | 9.5 | 29.8 | 19.6 | 7.8 | 30.8 | 19.2 | 9.5 | 29.8 | 12.2 | 9.5 | 19.8 | 9.9 | 0.5 | 9.5 |  |  | 2.6 |  |  | 9.5
72 | 1 | 9 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.6 | 9.9 | 0.5 | 28.9 | 19.1 | 9.5 | 39.7 | 26.1 | 9.9 | 45.1 | 28.1 | 17.4 | 38.4 | 25.7 | 9.5 | 29.7 | 11.7 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 10 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 39.8 | 29.2 | 13.8 | 47.3 | 28.1 | 17.4 | 38.5 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 11 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 40.6 | 27.8 | 13.9 | 47.3 | 26.5 | 17.4 | 43.2 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 12 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 40.6 | 27.8 | 14.5 | 47.3 | 26.5 | 17.4 | 43.2 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 15 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 40.6 | 27.8 | 14.5 | 47.3 | 26.5 | 17.4 | 43.2 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 20 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 40.6 | 27.8 | 14.5 | 47.3 | 26.5 | 17.4 | 43.2 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1 | 25 | 9.5 |  |  | 12.9 |  |  | 16.3 | 9.5 |  | 29.7 | 11.5 | 9.9 | 29.8 | 23.3 | 9.5 | 40.6 | 27.8 | 14.5 | 47.3 | 26.5 | 17.4 | 43.2 | 28.8 | 9.5 | 29.7 | 15.6 | 9.9 | 9.5 |  |  | 8 |  |  | 9.5
72 | 1.25 | 2
72 | 1.25 | 4
72 | 1.25 | 6 | 0.5 |  |  | 3.6 |  |  | 6.7 |  |  | 9.2 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9
72 | 1.25 | 8 | 9.5 |  |  | 15.1 |  |  | 19.2 | 9.5 |  | 19.9 | 9.9 | 3.9 | 27.7 | 14.8 | 9.5 | 37.2 | 19.7 | 9.9 | 33.7 | 23.4 | 9.5 | 36.5 | 19.1 | 9.5 | 23 | 15.6 | 9.9 | 9.5 |  |  | 9.9 |  |  | 9.5
72 | 1.25 | 9 | 18.9 | 4 |  | 18 | 10.2 |  | 28.8 | 9.5 |  | 38.5 | 19.7 | 9.9 | 38.5 | 26.7 | 18.2 | 49.4 | 32.1 | 21 | 49.2 | 30.8 | 22.5 | 48.1 | 31.6 | 18.1 | 30.9 | 20.4 | 9.9 | 19 | 9.5 |  | 9.9 |  |  | 19.1
72 | 1.25 | 10 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 15.6 | 0.9 | 44.1 | 29.2 | 14.2 | 45.8 | 33.2 | 19.7 | 56.8 | 41.1 | 30.8 | 59.7 | 41.4 | 29.3 | 56.5 | 38.3 | 28.8 | 39.7 | 29.6 | 19.7 | 25.6 | 9.5 | 7.2 | 12.9 | 9.9 |  | 19.1 | 0.7
72 | 1.25 | 11 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 17.6 | 0.8 | 48.2 | 29.6 | 18.2 | 47.7 | 36.3 | 25.6 | 59.5 | 41.3 | 32.2 | 60.1 | 42.7 | 34.1 | 60.6 | 44 | 28.8 | 43.3 | 29.6 | 19.7 | 25.6 | 9.5 | 7.2 | 13 | 9.9 |  | 19.1 | 2.2
72 | 1.25 | 12 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 17.6 | 0.8 | 48.2 | 29.7 | 18.2 | 47.7 | 35.9 | 25.6 | 59.5 | 41.3 | 32.7 | 60 | 42.7 | 34.6 | 63.6 | 44 | 29.2 | 43.3 | 29.6 | 19.7 | 25.6 | 9.5 | 7.2 | 13 | 9.9 |  | 19.1 | 2.2
72 | 1.25 | 15 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 17.6 | 0.8 | 48.2 | 29.7 | 18.2 | 47.7 | 35.9 | 25.6 | 59.5 | 41.3 | 32.7 | 60 | 42.7 | 34.6 | 63.6 | 44 | 29.2 | 43.3 | 29.6 | 19.7 | 25.6 | 9.5 | 7.1 | 13 | 9.9 |  | 19.1 | 2.2
72 | 1.25 | 20 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 17.6 | 0.8 | 48.2 | 29.7 | 18.2 | 47.7 | 35.9 | 25.6 | 59.5 | 41.3 | 32.7 | 60 | 42.7 | 34.6 | 63.6 | 44 | 29.2 | 43.3 | 29.6 | 19.7 | 25.6 | 9.5 | 7.1 | 13 | 9.9 |  | 19.1 | 2.2
72 | 1.25 | 25 | 19.2 | 4 |  | 19 | 10.6 |  | 31.4 | 17.6 | 0.8 | 48.2 | 29.7 | 18.2 | 47.7 | 35.9 | 25.6 | 59.5 | 41.3 | 32.7 | 60 | 42.7 | 34.6 | 63.6 | 44 | 29.2 | 43.3 | 29.6 | 19.7 | 25.6 | 9.5 | 7.1 | 13 | 9.9 |  | 19.1 | 2.2
72 | 1.5 | 2
72 | 1.5 | 4
72 | 1.5 | 6 | 0.5 |  |  | 4.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 1.5 | 8 | 13.9 |  |  | 15.5 | 4.5 |  | 19.2 | 9.5 |  | 25.7 | 10.3 | 9.8 | 28.6 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 37.8 | 28.6 | 10.4 | 36.5 | 19.1 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 5.8 |  | 9.9 |  |  | 12.5
72 | 1.5 | 9 | 19.2 | 9.5 |  | 21 | 10.6 |  | 28.9 | 19.1 |  | 42.3 | 26.7 | 9.9 | 45.9 | 31.9 | 19.1 | 54.3 | 32.4 | 24.4 | 50.2 | 38.3 | 28.1 | 50.4 | 34.4 | 19.1 | 39.5 | 23.3 | 9.9 | 19.1 | 9.5 |  | 15.3 | 9.9 |  | 19.2 | 6.5
72 | 1.5 | 10 | 24.1 | 9.5 |  | 25.8 | 15.6 | 1 | 37.1 | 21.4 | 7.9 | 48.7 | 29.9 | 20.5 | 52.7 | 38 | 28.8 | 66.2 | 51.1 | 35.6 | 68.8 | 57.7 | 38.6 | 61.3 | 44.6 | 36.8 | 43.6 | 33.3 | 19.7 | 28.6 | 13.7 | 9.5 | 25.4 | 9.9 | 0.6 | 28.8 | 9.5
72 | 1.5 | 11 | 26 | 12.4 |  | 26.8 | 17.3 | 9.9 | 41 | 28.8 | 9.5 | 52.9 | 39.6 | 26.5 | 58.7 | 48 | 37.9 | 69.7 | 57.1 | 40.6 | 73.8 | 60.8 | 44.2 | 69.5 | 54.8 | 46 | 55.3 | 39.6 | 29.7 | 29.7 | 19.1 | 9.5 | 27.8 | 9.9 | 3.4 | 28.8 | 9.5 | 1
72 | 1.5 | 12 | 27.6 | 12.1 |  | 27.6 | 19.9 | 10.2 | 46.6 | 28.8 | 9.5 | 53.6 | 41.1 | 28.3 | 59.4 | 50 | 39.2 | 71.2 | 59.6 | 44.5 | 75 | 63.8 | 48 | 73.5 | 56.3 | 46.2 | 55.3 | 41.9 | 29.7 | 35.1 | 19.1 | 9.5 | 27.8 | 11.3 | 9.8 | 28.8 | 9.5 | 1
72 | 1.5 | 15 | 27.6 | 12.1 |  | 27.6 | 19.9 | 10.3 | 46.7 | 28.8 | 9.5 | 53.6 | 41.1 | 29.7 | 59.4 | 50 | 39.8 | 71.3 | 59.6 | 45.5 | 75 | 63.8 | 48.6 | 73.5 | 56.3 | 46.3 | 55.3 | 41.9 | 29.7 | 35.1 | 19.1 | 9.5 | 27.8 | 11.5 | 9.8 | 28.8 | 9.5 | 1
72 | 1.5 | 20 | 27.6 | 12.1 |  | 27.6 | 19.9 | 10.3 | 46.7 | 28.8 | 9.5 | 53.6 | 41.1 | 29.7 | 59.4 | 50 | 39.8 | 71.3 | 59.6 | 45.5 | 75 | 63.8 | 48.6 | 73.5 | 56.3 | 46.3 | 55.3 | 41.9 | 29.7 | 35.1 | 19.1 | 9.5 | 27.8 | 11.5 | 9.8 | 28.8 | 9.5 | 1
72 | 1.5 | 25 | 27.6 | 12.1 |  | 27.6 | 19.9 | 10.3 | 46.7 | 28.8 | 9.5 | 53.6 | 41.1 | 29.7 | 59.4 | 50 | 39.8 | 71.3 | 59.6 | 45.5 | 75 | 63.8 | 48.6 | 73.5 | 56.3 | 46.3 | 55.3 | 41.9 | 29.7 | 35.1 | 19.1 | 9.5 | 27.8 | 11.5 | 9.8 | 28.8 | 9.5 | 1
72 | 1.75 | 2
72 | 1.75 | 4
72 | 1.75 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 1.75 | 8 | 16.3 |  |  | 15.5 | 10.6 |  | 19.8 | 9.5 |  | 25.7 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 10.4 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 5.8 |  | 9.9 |  |  | 12.5
72 | 1.75 | 9 | 22.4 | 9.5 |  | 21 | 10.6 |  | 31.9 | 19.1 | 1.7 | 43.9 | 29.6 | 10.5 | 47.4 | 31.9 | 19.1 | 54.3 | 36.1 | 24.4 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.1 | 39.7 | 23.5 | 9.9 | 19.1 | 9.5 |  | 17.9 | 9.9 |  | 25.8 | 9.5
72 | 1.75 | 10 | 26.4 | 13 |  | 30.1 | 16.4 | 1 | 38.5 | 22 | 9.5 | 49.7 | 39.4 | 28 | 55.2 | 38.3 | 28.8 | 69.4 | 52.5 | 39.9 | 69.6 | 58.1 | 39.9 | 66.6 | 48.4 | 38.3 | 49.7 | 36.3 | 20.2 | 28.7 | 19.1 | 9.5 | 28.7 | 10 | 7.8 | 28.8 | 9.5
72 | 1.75 | 11 | 33.7 | 19.1 |  | 36.9 | 21.1 | 10.6 | 50.6 | 33.9 | 20.6 | 61.4 | 48.3 | 33.6 | 66.7 | 52.4 | 42.6 | 78.4 | 66.1 | 47.4 | 83.7 | 68.5 | 50.3 | 76.3 | 60.8 | 48.8 | 61.3 | 45.3 | 30.5 | 36.8 | 23.3 | 11.3 | 30.8 | 16.4 | 9.9 | 36.2 | 13 | 4.2
72 | 1.75 | 12 | 36 | 19.1 | 1.7 | 41.4 | 30.7 | 13 | 56.1 | 38.3 | 24 | 70.2 | 53.3 | 38.8 | 74.7 | 61.7 | 51.9 | 82.9 | 71.4 | 54.6 | 86.5 | 70.7 | 58.6 | 84 | 67.5 | 51.7 | 66.7 | 51.3 | 39.6 | 46.5 | 29.4 | 17.8 | 38.2 | 20.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 1.75 | 15 | 36.2 | 19.1 | 1.7 | 41.4 | 31.8 | 18.7 | 58.7 | 38.6 | 24.1 | 70.8 | 57.4 | 39.1 | 77.4 | 65.1 | 55.4 | 83.2 | 71.8 | 60.3 | 88.4 | 76.6 | 60.5 | 84 | 68.3 | 52 | 66.6 | 54.4 | 39.7 | 47.6 | 29.4 | 17.6 | 39 | 20.3 | 9.9 | 38.6 | 19.1 | 9.5
72 | 1.75 | 20 | 36.2 | 19.1 | 1.7 | 41.4 | 31.8 | 18.7 | 58.7 | 38.6 | 24.1 | 70.8 | 57.4 | 39.1 | 77.4 | 65.1 | 55.4 | 83.2 | 71.8 | 60.3 | 88.4 | 76.6 | 60.5 | 84 | 68.3 | 52 | 66.6 | 54.4 | 39.7 | 47.6 | 29.4 | 17.5 | 39 | 20.3 | 9.9 | 38.6 | 19.1 | 9.5
72 | 1.75 | 25 | 36.2 | 19.1 | 1.7 | 41.4 | 31.8 | 18.7 | 58.7 | 38.6 | 24.1 | 70.8 | 57.4 | 39.1 | 77.4 | 65.1 | 55.4 | 83.2 | 71.8 | 60.3 | 88.4 | 76.6 | 60.5 | 84 | 68.3 | 52 | 66.6 | 54.4 | 39.7 | 47.6 | 29.4 | 17.5 | 39 | 20.3 | 9.9 | 38.6 | 19.1 | 9.5
72 | 2 | 2
72 | 2 | 4
72 | 2 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 2 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 28.5 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 2 | 9 | 22.4 | 9.5 |  | 24 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.4 | 31.9 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 23.5 | 9.9 | 19.2 | 9.5 |  | 17.9 | 9.9 |  | 25.8 | 9.5
72 | 2 | 10 | 26.4 | 15.7 |  | 35.7 | 19.8 | 1 | 40.7 | 27.8 | 9.6 | 51.9 | 42.1 | 29.6 | 57.7 | 43.7 | 28.8 | 69.6 | 53.6 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.4 | 38.4 | 50 | 36.5 | 23.8 | 28.9 | 19.1 | 9.5 | 29 | 12.4 | 9.9 | 28.8 | 11.8 | 1
72 | 2 | 11 | 38.3 | 20.2 | 1.8 | 40.4 | 22.4 | 18.4 | 54.6 | 38.6 | 25.6 | 69 | 50.4 | 36.6 | 72.2 | 59 | 45.6 | 82.1 | 67.9 | 51.7 | 85.7 | 69.6 | 52.2 | 78.5 | 65.7 | 51.7 | 63.4 | 49.6 | 31.3 | 45.4 | 28.6 | 17.7 | 31.5 | 19.9 | 9.9 | 38.5 | 19.1 | 8
72 | 2 | 12 | 45.3 | 23.5 | 9.5 | 48.2 | 34.1 | 19.4 | 65.9 | 44 | 29.4 | 78.3 | 60.6 | 48.8 | 82.2 | 69.5 | 57.9 | 87.3 | 78.8 | 63.4 | 91.5 | 78.9 | 62.2 | 88.3 | 73.5 | 56.4 | 72.5 | 56.8 | 44.9 | 53.7 | 32.1 | 19.1 | 40.7 | 29.6 | 12.5 | 42.3 | 19.5 | 9.5
72 | 2 | 15 | 45.1 | 28.8 | 16.3 | 55.4 | 42.6 | 19.3 | 69.2 | 52.3 | 33.5 | 82.8 | 68.5 | 55.9 | 86.6 | 76.9 | 60.5 | 90.6 | 84.4 | 70 | 93.5 | 86 | 71.1 | 88.9 | 76.2 | 61.9 | 75.7 | 60.1 | 47.5 | 56.3 | 39.9 | 27.9 | 49 | 30.1 | 19.3 | 45.7 | 27.3 | 9.5
72 | 2 | 20 | 45.1 | 28.8 | 16.3 | 55.4 | 42.6 | 19.2 | 69.2 | 52.3 | 33.5 | 82.8 | 68.5 | 55.9 | 86.6 | 76.9 | 60.5 | 90.6 | 84.4 | 70 | 93.5 | 86 | 71.1 | 88.9 | 76.2 | 61.9 | 75.7 | 60.1 | 47.4 | 56.3 | 39.9 | 27.9 | 49 | 30.1 | 19.3 | 45.7 | 27.3 | 9.5
72 | 2 | 25 | 45.1 | 28.8 | 16.3 | 55.4 | 42.6 | 19.2 | 69.2 | 52.3 | 33.5 | 82.8 | 68.5 | 55.9 | 86.6 | 76.9 | 60.5 | 90.6 | 84.4 | 70 | 93.5 | 86 | 71.1 | 88.9 | 76.2 | 61.9 | 75.7 | 60.1 | 47.4 | 56.3 | 39.9 | 27.9 | 49 | 30.1 | 19.3 | 45.7 | 27.3 | 9.5
72 | 2.25 | 2
72 | 2.25 | 4
72 | 2.25 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 2.25 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 2.25 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 23.5 | 9.9 | 19.2 | 9.5 |  | 19.2 | 9.9 |  | 25.8 | 9.5
72 | 2.25 | 10 | 28.7 | 15.7 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.5 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 56.3 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.4 | 38.4 | 50 | 36.5 | 23.8 | 32.8 | 19.1 | 9.5 | 29 | 16.1 | 9.9 | 28.9 | 16.7 | 1
72 | 2.25 | 11 | 39 | 20.7 | 5.3 | 42.9 | 29.9 | 18.3 | 54.6 | 39.5 | 25.6 | 69.7 | 55.8 | 40.5 | 72.7 | 59.9 | 45.8 | 82.8 | 69.7 | 53.3 | 85.7 | 71.5 | 54.2 | 78.5 | 66.1 | 52 | 63.4 | 52.9 | 35.7 | 45.4 | 28.8 | 17.9 | 35.8 | 22.1 | 9.9 | 38.5 | 19.1 | 8.1
72 | 2.25 | 12 | 46 | 28.6 | 9.5 | 53.3 | 41.2 | 20.7 | 65.9 | 48.1 | 31.2 | 79.6 | 67.5 | 52.7 | 82.6 | 70.6 | 58.9 | 89.8 | 79.7 | 68.3 | 92.1 | 83.5 | 62.9 | 90.4 | 75.5 | 62.3 | 73.2 | 57.8 | 46.7 | 55.3 | 38.4 | 19.4 | 43.3 | 29.6 | 12.5 | 46.6 | 22.8 | 11.5
72 | 2.25 | 15 | 57.7 | 37.1 | 22 | 69.8 | 47 | 24.7 | 78.6 | 59 | 39.4 | 91.4 | 79.6 | 64.5 | 89.5 | 83.9 | 75.2 | 95.3 | 87.9 | 79.6 | 96.9 | 89.4 | 84.9 | 91.7 | 80.8 | 73.2 | 81.5 | 69.2 | 57.5 | 67 | 51.5 | 36.9 | 60.8 | 39.7 | 20.8 | 56.5 | 35.9 | 19.1
72 | 2.25 | 20 | 57.7 | 37.1 | 22 | 69.8 | 53 | 24.7 | 78.6 | 59.1 | 39.4 | 91.4 | 79.6 | 64.5 | 89.5 | 83.9 | 75.2 | 95.3 | 87.9 | 79.6 | 96.8 | 89.2 | 84.9 | 91.7 | 80.8 | 73.2 | 81.5 | 69.3 | 57.3 | 67 | 56 | 36.9 | 60.8 | 39.7 | 20.8 | 56.5 | 35.9 | 19.1
72 | 2.25 | 25 | 57.7 | 37.1 | 22 | 69.8 | 53 | 24.7 | 78.6 | 59.1 | 39.4 | 91.4 | 79.6 | 64.5 | 89.5 | 83.9 | 75.2 | 95.3 | 87.9 | 79.6 | 96.8 | 89.2 | 84.9 | 91.7 | 80.8 | 73.2 | 81.5 | 69.3 | 57.3 | 67 | 56 | 36.9 | 60.8 | 39.7 | 20.8 | 56.5 | 35.9 | 19.1
72 | 2.75 | 2
72 | 2.75 | 4
72 | 2.75 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 2.75 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 2.75 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.2 | 9.9 |  | 25.8 | 9.5
72 | 2.75 | 10 | 28.6 | 15.7 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 16.1 | 9.9 | 28.9 | 16.7 | 4.6
72 | 2.75 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 45.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 36.5 | 25.3 | 9.9 | 38.5 | 19.2 | 9.5
72 | 2.75 | 12 | 47.7 | 28.8 | 15.4 | 53.4 | 41.5 | 21.1 | 66.3 | 50 | 30.2 | 81.2 | 69.6 | 58.5 | 83 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 74.1 | 59.3 | 49.8 | 57 | 38.4 | 24.4 | 47.1 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 2.75 | 15 | 63 | 47.8 | 31.1 | 77.4 | 62.8 | 33.3 | 82 | 66.8 | 50.5 | 94.4 | 86.8 | 73.8 | 96.9 | 92.9 | 86.3 | 100 | 94.7 | 88.4 | 100 | 96.6 | 89.7 | 100 | 89.7 | 82.6 | 88.3 | 81.3 | 67 | 76 | 66 | 52.1 | 70 | 57.9 | 32.6 | 62.5 | 47.4 | 28.8
72 | 2.75 | 20 | 68.6 | 49.3 | 37.2 | 79.1 | 68.2 | 33.2 | 88.3 | 73 | 56.8 | 96.8 | 89.4 | 75.8 | 100 | 94.5 | 90.8 | 100 | 96.3 | 89.6 | 100 | 96.6 | 91.5 | 100 | 91.3 | 85 | 93.7 | 82.6 | 67.9 | 79.9 | 72 | 57.3 | 72.1 | 58.2 | 38.2 | 62.9 | 48 | 29.5
72 | 2.75 | 25 | 68.6 | 49.3 | 37.2 | 79.1 | 68.2 | 33.2 | 88.3 | 73 | 56.8 | 96.8 | 89.4 | 75.8 | 100 | 94.5 | 90.8 | 100 | 96.3 | 89.6 | 100 | 96.6 | 91.5 | 100 | 91.3 | 85 | 93.7 | 82.6 | 67.9 | 79.9 | 72 | 57.3 | 72.1 | 58.2 | 38.2 | 62.9 | 48 | 29.5
72 | 3 | 2
72 | 3 | 4
72 | 3 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 3 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 3 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.7 | 9.9 |  | 25.8 | 9.5
72 | 3 | 10 | 28.6 | 15.7 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 17.4 | 9.9 | 28.9 | 16.7 | 4.6
72 | 3 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 45.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 41 | 25.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 3 | 12 | 47.7 | 28.8 | 15.4 | 53.4 | 41.2 | 21.1 | 66.8 | 50 | 30.2 | 81.2 | 69.6 | 58.5 | 83.3 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 77.5 | 59.3 | 49.8 | 57 | 39.1 | 24.4 | 49.6 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 3 | 15 | 64.3 | 49.2 | 34.3 | 77.6 | 66.1 | 38.7 | 83.4 | 70.7 | 55.8 | 97.4 | 86.8 | 78.3 | 99.2 | 93 | 87.4 | 100 | 94.9 | 89.2 | 100 | 96.6 | 90 | 100 | 91.4 | 82.5 | 92.3 | 81.3 | 68.2 | 79.4 | 67.5 | 55.4 | 74.1 | 58.6 | 39.6 | 66.8 | 50.3 | 28.7
72 | 3 | 20 | 75.1 | 58.3 | 42.3 | 84.2 | 72.1 | 47.6 | 91 | 77.3 | 63 | 100 | 91.5 | 83.3 | 100 | 100 | 89.6 | 100 | 97.2 | 92.2 | 100 | 100 | 89.9 | 100 | 97 | 88.9 | 93.6 | 89 | 76.1 | 86 | 76.1 | 65.2 | 79.8 | 67.2 | 46.5 | 72 | 55 | 45.8
72 | 3 | 25 | 75.1 | 58.3 | 42.3 | 84.2 | 72.1 | 47.6 | 91 | 77.3 | 63 | 100 | 91.5 | 83.3 | 100 | 100 | 89.6 | 100 | 97.2 | 92.2 | 100 | 100 | 89.9 | 100 | 97 | 88.9 | 93.6 | 89 | 76.1 | 86 | 76.1 | 65.2 | 79.8 | 67.2 | 46.5 | 72 | 55 | 45.8
72 | 3.5 | 2
72 | 3.5 | 4
72 | 3.5 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 3.5 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 3.5 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.7 | 9.9 |  | 25.8 | 9.5
72 | 3.5 | 10 | 28.6 | 18.5 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 17.4 | 9.9 | 28.9 | 16.7 | 4.6
72 | 3.5 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 46.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 40.9 | 25.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 3.5 | 12 | 47.7 | 29.6 | 15.4 | 53.4 | 41.2 | 21.1 | 66.8 | 50 | 30.2 | 81.2 | 69.6 | 59.1 | 83.3 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 77.5 | 59.3 | 50.6 | 57 | 39.1 | 24.4 | 49.8 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 3.5 | 15 | 66.1 | 53.4 | 34.1 | 78 | 68.9 | 38.7 | 86.6 | 73.1 | 56.4 | 97.8 | 89.2 | 81.3 | 100 | 94 | 89.6 | 100 | 95 | 90.4 | 100 | 100 | 90.7 | 100 | 91.9 | 82.3 | 92.8 | 83.6 | 71.2 | 80 | 68.1 | 56.8 | 78.8 | 60.4 | 42.1 | 72.1 | 53.6 | 29.8
72 | 3.5 | 20 | 83.3 | 73.1 | 58.9 | 95 | 84.2 | 64.5 | 98.9 | 86.7 | 75.8 | 100 | 98.5 | 89.8 | 100 | 100 | 100 | 100 | 100 | 92.6 | 100 | 100 | 94.9 | 100 | 100 | 95.6 | 100 | 92.4 | 82.7 | 96.2 | 85.6 | 76.3 | 88.1 | 79.3 | 66.7 | 89.5 | 70.7 | 56.2
72 | 3.5 | 25 | 83.3 | 73.1 | 58.9 | 96.3 | 84.2 | 64.5 | 98.9 | 86.7 | 75.8 | 100 | 98.5 | 89.8 | 100 | 100 | 100 | 100 | 100 | 92.6 | 100 | 100 | 94.9 | 100 | 100 | 95.6 | 100 | 92.2 | 82.7 | 96.4 | 85.6 | 76.3 | 89.8 | 79.3 | 66.7 | 89.5 | 70.7 | 56.2
72 | 4 | 2
72 | 4 | 4
72 | 4 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 4 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 4 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.7 | 9.9 |  | 25.8 | 9.5
72 | 4 | 10 | 28.6 | 18.5 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 17.4 | 9.9 | 28.9 | 16.7 | 4.6
72 | 4 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 46.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 40.9 | 25.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 4 | 12 | 47.7 | 29.6 | 15.4 | 53.4 | 41.2 | 21.1 | 66.8 | 50 | 30.2 | 81.2 | 69.6 | 59.1 | 83.3 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 77.5 | 59.3 | 50.6 | 57 | 39.1 | 24.4 | 49.8 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 4 | 15 | 67.2 | 53.4 | 36.2 | 78.9 | 68.9 | 45.4 | 86.1 | 73.1 | 56.8 | 97.8 | 89.4 | 82.8 | 100 | 95.4 | 89.6 | 100 | 95.1 | 90.4 | 100 | 100 | 91.5 | 100 | 92.6 | 82.3 | 92.8 | 84.3 | 72.7 | 81.8 | 69.2 | 56.8 | 80.3 | 64 | 42.1 | 72.1 | 56.3 | 31.6
72 | 4 | 20 | 95.8 | 82.9 | 70.2 | 97.7 | 89.7 | 76 | 100 | 93.8 | 86.5 | 100 | 100 | 92.6 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98.1 | 90.4 | 100 | 91.1 | 83.9 | 95.5 | 88.1 | 79.4 | 99 | 82.1 | 67.2
72 | 4 | 25 | 95.8 | 82.9 | 70.7 | 99.4 | 89.9 | 76 | 100 | 93.7 | 88.3 | 100 | 100 | 92.7 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 90.9 | 100 | 92.2 | 84 | 98 | 88.1 | 80.9 | 99 | 82.9 | 70
72 | 4.5 | 2
72 | 4.5 | 4
72 | 4.5 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 4.5 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 4.5 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.7 | 9.9 |  | 25.8 | 9.5
72 | 4.5 | 10 | 28.6 | 18.5 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 17.4 | 9.9 | 28.9 | 16.7 | 4.6
72 | 4.5 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 46.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 40.9 | 25.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 4.5 | 12 | 47.7 | 29.6 | 15.4 | 53.4 | 41.2 | 21.1 | 66.8 | 50 | 30.2 | 81.2 | 69.6 | 59.1 | 83.3 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 77.5 | 59.3 | 50.6 | 57 | 39.1 | 24.4 | 49.8 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 4.5 | 15 | 67.2 | 53.4 | 35.2 | 78.9 | 68.9 | 45.4 | 86.1 | 73.1 | 56.8 | 97.8 | 91.3 | 82.9 | 100 | 95.4 | 89.6 | 100 | 95.1 | 90.4 | 100 | 100 | 91.5 | 100 | 92.6 | 82.3 | 92.8 | 85.3 | 73 | 81.8 | 69.2 | 57.3 | 80.3 | 64 | 42.2 | 72.1 | 56.3 | 31.6
72 | 4.5 | 20 | 99.1 | 87.8 | 74.7 | 100 | 92.4 | 81 | 100 | 96.5 | 90 | 100 | 100 | 92.8 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 93.8 | 100 | 94.6 | 87 | 100 | 91 | 87.8 | 100 | 89.9 | 78.2
72 | 4.5 | 25 | 100 | 92.1 | 85.2 | 100 | 96 | 85.4 | 100 | 100 | 92.7 | 100 | 100 | 95.1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 97.1 | 100 | 99.2 | 91.1 | 100 | 92.8 | 88.3 | 100 | 92.3 | 84.2
72 | 5 | 2
72 | 5 | 4
72 | 5 | 6 | 0.5 |  |  | 8.4 |  |  | 6.7 |  |  | 9.9 |  |  | 9.5 |  |  | 9.9 |  |  | 9.5 |  |  | 9.5 |  |  | 9.9 |  |  | 2.6
72 | 5 | 8 | 16.3 |  |  | 15.9 | 10.6 |  | 19.8 | 9.5 |  | 29.6 | 18.5 | 9.9 | 28.7 | 18.7 | 9.5 | 39.6 | 19.9 | 9.9 | 38.2 | 28.8 | 13.5 | 36.5 | 19.2 | 9.5 | 29.6 | 19.3 | 9.9 | 11.5 | 6 |  | 9.9 |  |  | 12.5
72 | 5 | 9 | 22.4 | 9.5 |  | 26.1 | 10.6 |  | 31.9 | 19.1 | 1.2 | 48.5 | 29.6 | 14.1 | 47.9 | 32.1 | 19.1 | 56.4 | 36.1 | 26.6 | 50.2 | 40.1 | 28.6 | 53.6 | 35.9 | 19.2 | 39.7 | 24.7 | 9.9 | 19.2 | 9.5 |  | 19.7 | 9.9 |  | 25.8 | 9.5
72 | 5 | 10 | 28.6 | 18.5 |  | 35.7 | 19.8 | 1 | 41.9 | 27.8 | 9.6 | 53.9 | 45.3 | 29.8 | 57.8 | 44.9 | 28.8 | 69.7 | 59.4 | 39.9 | 69.6 | 58.5 | 42.2 | 67.4 | 48.7 | 39 | 50 | 39.6 | 23.8 | 33.4 | 19.1 | 9.5 | 29 | 17.4 | 9.9 | 28.9 | 16.7 | 4.6
72 | 5 | 11 | 39.3 | 20.7 | 5.3 | 44.5 | 29.9 | 18.3 | 57.2 | 39.5 | 25.6 | 69.7 | 57.1 | 46.3 | 72.7 | 60.1 | 45.8 | 82.8 | 73.3 | 53.8 | 85.7 | 71.6 | 54.2 | 80.9 | 67.5 | 53 | 63.4 | 52.9 | 37 | 46.3 | 28.8 | 18.8 | 40.9 | 25.3 | 9.9 | 38.5 | 19.1 | 9.5
72 | 5 | 12 | 47.7 | 29.6 | 15.4 | 53.4 | 41.2 | 21.1 | 66.8 | 50 | 30.2 | 81.2 | 69.6 | 59.1 | 83.3 | 75.5 | 61.7 | 91 | 81.4 | 69.5 | 92.6 | 83.5 | 69.9 | 90.4 | 78.1 | 62.8 | 77.5 | 59.3 | 50.6 | 57 | 39.1 | 24.4 | 49.8 | 32.4 | 12.5 | 47.9 | 28.8 | 12.4
72 | 5 | 15 | 67.2 | 53.4 | 35.2 | 78.9 | 68.9 | 45.4 | 86.1 | 73.1 | 56.8 | 97.8 | 91.3 | 82.9 | 100 | 95.4 | 89.6 | 100 | 95.1 | 90.4 | 100 | 100 | 91.5 | 100 | 92.6 | 82.3 | 92.8 | 85.3 | 73 | 81.8 | 69.2 | 57.7 | 80.3 | 64 | 42.2 | 72.1 | 56.3 | 31.6
72 | 5 | 20 | 100 | 89.2 | 80.6 | 100 | 92.8 | 81.1 | 100 | 97.6 | 90.4 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 93.9 | 100 | 97 | 88 | 100 | 92.8 | 87.9 | 100 | 91.4 | 78.3
72 | 5 | 25 | 100 | 99.1 | 89.6 | 100 | 100 | 90.8 | 100 | 100 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 95.2 | 100 | 100 | 93.6 | 100 | 100 | 90.8

## WDT Calculation
WORKABILITY CALCULATION PART A | [7 empty] | WORKABILITY CALCULATION PART C
| PART | Limiting conditions |  |  | Total Durations (days) |  |  |  | PART | Limiting conditions |  |  | Total Durations (days)
| A | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW |  |  | C | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW
|  | 0 | 0 | 0 | 0 | #N/A |  |  |  | 0 | 0 | 0 | 0 | #N/A
CALCULATION |  |  |  |  | Nett days | Working days |  | CALCULATION |  |  |  |  | Nett days | Working days
Month | Month | Start | End | Persistence | in month | in month | left | Month | Month | Start | End | Persistence | in month | in month | left
1 | 1 | 0 | 1900-01-30 | #N/A | 32 | #N/A | #N/A | 1 | 1 | 0 | 1900-01-30 | #N/A | 32 | #N/A | #N/A
2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
WORKABILITY CALCULATION PART B | [7 empty] | WORKABILITY CALCULATION PART D
| PART | Limiting conditions |  |  | Total Durations (days) |  |  |  | PART | Limiting conditions |  |  | Total Durations (days)
| B | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW |  |  | D | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW
|  | 0 | 0 | 0 | 0 | #N/A |  |  |  | 0 | 0 | 0 | 0 | #N/A
CALCULATION |  |  |  |  | Nett days | Working days |  | CALCULATION |  |  |  |  | Nett days | Working days
Month |  | Start | End | Persistence | in month | in month | left | Month |  | Start | End | Persistence | in month | in month | left
1 | 6 | 2021-06-08 | 2021-06-30 | #N/A | 23 | #N/A | #N/A | 1 | 6 | 2021-06-08 | 2021-06-30 | #N/A | 23 | #N/A | #N/A
2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Formulas:
End = IF([Limiting conditions]+[Total Durations (days)]-1<EOMONTH([Limiting conditions],0),[Limiting conditions]+[Total Durations (days)]-1,EOMONTH([Limiting conditions],0))
End = IF([left, row above]>0,IF([Limiting conditions]+[Total Durations (days)]-1<EOMONTH([Limiting conditions],0),[Limiting conditions]+[Total Durations (days)]-1,EOMONTH([Limiting conditions],0)),[Limiting conditions])
Total Durations (days) = IFERROR(IF(G5/[Persistence]<EOMONTH([Limiting conditions],0)+1-[Limiting conditions],G5/[Persistence],EOMONTH([Limiting conditions],0)+1-[Limiting conditions]),EOMONTH([Limiting conditions],0)-[Limiting conditions]+1)
Total Durations (days) = IFERROR(IF(P5/[Persistence]<EOMONTH([Limiting conditions],0)+1-[Limiting conditions],P5/[Persistence],EOMONTH([Limiting conditions],0)+1-[Limiting conditions]),EOMONTH([Limiting conditions],0)-[Limiting conditions]+1)

## Remuneration Table (hidden)
Item | Description | Unit | Unit Rate | Quantity | Price
Mobilisation/demobilisation of vessel(s), survey equipment and personnel to site
1.1 | Mob/demob vessel Name of vessel 1 incl. vessel equipment and personnel | Lump sum | 0 | 1 | FILL UNIT RATE
1.2 | Mob/demob vessel Name of vessel 2 incl. vessel equipment and personnel | Lump sum | 0 | 0 | FILL UNIT RATE
1.3 | Mob/demob vessel Name of vessel 3 incl. vessel equipment and personnel | Lump sum | 0 | 0 | FILL UNIT RATE
1.4 | Mob/demob vessel Name of vessel 4 incl. vessel equipment and personnel | Lump sum | 0 | 0 | FILL UNIT RATE
1.5 | Mob/demob drilling and downhole sampling/PCPT equipment and personnel | Lump sum | 0 | 1 | FILL UNIT RATE
1.6 | Mob/demob downhole SCPT equipment and personnel | Lump sum | 0 | 1 | FILL UNIT RATE
1.7 | Mob/demob downhole PS-logging equipment and personnel | Lump sum | 0 | 1 | FILL UNIT RATE
1.8 | Mob/demob downhole density and spectral gamma logging equipment and personnel | Lump sum | 0 | 1 | FILL UNIT RATE
Survey Operations incl transit from and to site excluding WOW
2.1 | Positioning and setting-up on first borehole at a new location (including transiting from previous location) | /borehole | 0 | 125 | FILL UNIT RATE
2.2 | Re-positioning and setting-up on additional boreholes at same location | /borehole | 0 | 13 | FILL UNIT RATE
2.3 | Changing over between piezocone and seismic cone mid-way through a borehole | /event | 0 | 74 | FILL UNIT RATE
2.4 | Drilling performance (between seabed and 60m depth) | /m | 0 | 7500 | FILL UNIT RATE
2.5 | Drilling performance (between 60m and 80m depth) | /m | 0 | 710 | FILL UNIT RATE
2.6 | Drilling performance (between 80m and 100m depth) | /m | 0 | 140 | FILL UNIT RATE
2.7 | Execution of push sampling (including any oversampling) | /sample | 0 | 5435 | FILL UNIT RATE
2.8 | Execution of hammer sampling (including any oversampling) | /sample | 0 | 286 | FILL UNIT RATE
2.9 | Execution of downhole PCPT push (up to 3m stroke length) | /push | 0 | 1070 | FILL UNIT RATE
2.10 | Execution of downhole SCPT push (up to 3m stroke length) excluding seismic tests | /push | 0 | 438 | FILL UNIT RATE
2.11 | Execution of individual seismic test using downhole SCPT tool | /test | 0 | 438 | FILL UNIT RATE
2.12 | Execution of individual seismic tests using P-S logging tool | /test | 0 | 600 | FILL UNIT RATE
2.13 | Execution of Downhole density logging | /m | 0 | 600 | FILL UNIT RATE
2.14 | Execution of Spectral gamma logging | /m | 0 | 600 | FILL UNIT RATE
2.15 | Micro sitting for positioning at borehole location due to unexpected high gradient of seabed frame preventing the work | /location | 0 | 125 | FILL UNIT RATE
2.16 | Port call for Name of vessel 1 during surveying PART A | /call | 0 | 0 | FILL UNIT RATE
2.17 | Port call for Name of vessel 2 during surveying PART B | /call | 0 | 5 | FILL UNIT RATE
2.18 | Port call for Name of vessel 3 during surveying PART C | /call | 0 | 0 | FILL UNIT RATE
2.19 | Port call for Name of vessel 4 during surveying PART D | /call | 0 | 0 | FILL UNIT RATE
Lab Testing - Standard Lab Testing Programme (all soil types)
3.1 | Particle density | /test | 0 | 878 | FILL UNIT RATE
3.2 | Carbonate tests | /test | 0 | 839 | FILL UNIT RATE
3.3 | Organic tests (dichromate) | /test | 0 | 722 | FILL UNIT RATE
3.4 | Organic tests (loss on ignition) | /test | 0 | 195 | FILL UNIT RATE
3.5 | Organic and total carbon content (Elementary analysis) | /test | 0 | 390 | FILL UNIT RATE
3.6 | Electrical resistivity (as input for heat capacity calculations) | /test | 0 | 108 | FILL UNIT RATE
3.7 | Pore water salinity (as input for heat capacity calculations) | /test | 0 | 108 | FILL UNIT RATE
3.8 | Microscopic photography (as input for heat capacity calculations) | /test | 0 | 108 | FILL UNIT RATE
Lab Testing - Standard Lab Testing Programme (cohesionless soil)
3.9 | Binocular microscopy tests including photography (for general purpose or where batching of samples is being considered) | /test | 0 | 371 | FILL UNIT RATE
3.10 | Particle size analysis (sieve) | /test | 0 | 1560 | FILL UNIT RATE
3.11 | Particle size analysis (using sieve and hydrometer for fines fraction) | /test | 0 | 488 | FILL UNIT RATE
3.12 | Maximum and minimum density | /test | 0 | 449 | FILL UNIT RATE
3.13 | Permeability tests with permeameter | /test | 0 | 155 | FILL UNIT RATE
3.14 | Permeability tests in triaxial cell (using a CID test sample) | /test | 0 | 39 | FILL UNIT RATE
3.15 | Permeability tests in triaxial cell (as a standalone test) | /test | 0 | 117 | FILL UNIT RATE
3.16 | Thermal conductivity tests on fully-saturated cohesionless samples using needle probe (ASTM D5334-14) | /test | 0 | 108 | FILL UNIT RATE
3.17 | Thermal conductivity tests on fully-saturated cohesionless samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). | /test | 0 | 108 | FILL UNIT RATE
3.18 | Isotropically consolidated drained (CID) triaxial compression tests (N.B. one "test" constitutes three individual sub-tests on three specimens at three different consolidation pressures) | /test | 0 | 507 | FILL UNIT RATE
3.19 | Ring shear tests (soil/soil) | /test | 0 | 166 | FILL UNIT RATE
3.20 | Ring shear tests (soil/steel) | /test | 0 | 229 | FILL UNIT RATE
3.21 | Bender element tests (as part of a CID or DSS test) | /test | 0 | 166 | FILL UNIT RATE
3.22 | Consolidated drained direct shear (shear box) tests (N.B. one "test" constitutes three individual sub-tests on three specimens at three different normal pressures) | /test | 0 | 283 | FILL UNIT RATE
3.23 | Microbially Influenced Corrosion (MIC) testing | /test | 0 | 78 | FILL UNIT RATE
Lab Testing - Standard Lab Testing Programme (cohesive soil)
3.24 | Particle size analysis (using hydrometer for fines and if applicable sieve) | /test | 0 | 117 | FILL UNIT RATE
3.25 | Atterberg limits (liquid and plastic limits, cone method) | /test | 0 | 439 | FILL UNIT RATE
3.26 | Permeability tests in triaxial cell (using a CIU test sample) | /test | 0 | 39 | FILL UNIT RATE
3.27 | Thermal conductivity tests on fully-saturated undisturbed cohesive samples using needle probe (ASTM D5334-14) | /test | 0 | 92 | FILL UNIT RATE
3.28 | Thermal conductivity tests on fully-saturated remoulded cohesive samples using needle probe (ASTM D5334-14) | /test | 0 | 12 | FILL UNIT RATE
3.29 | Thermal conductivity tests on fully-saturated undisturbed cohesive samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). | /test | 0 | 20 | FILL UNIT RATE
3.30 | Thermal conductivity tests on fully-saturated remoulded cohesive samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). | /test | 0 | 8 | FILL UNIT RATE
3.31 | One-dimensional consolidation (oedometer) tests up to 8 load and 4 unload stages (state whether BS or Norwegian method) | /test | 0 | 43 | FILL UNIT RATE
3.32 | Additional reload loops in one-dimensional consolidation (oedometer) tests | /loop | 0 | 43 | FILL UNIT RATE
3.33 | Constant Rate of Strain (CRS) compressibility tests (max. 4 days) | /test | 0 | 106 | FILL UNIT RATE
3.34 | Overdays Constant Rate of Strain (CRS) compressibility tests | /day | 0 | 621 | FILL UNIT RATE
3.35 | Unconsolidated undrained (UU) triaxial compression tests on undisturbed samples | /test | 0 | 20 | FILL UNIT RATE
3.36 | Unconsolidated undrained (UU) triaxial compression tests on remoulded samples | /test | 0 | 20 | FILL UNIT RATE
3.37 | Isotropically consolidated undrained triaxial compression test (CIU) (comprising saturation, consolidation and shearing, max. 4 days) | /test | 0 | 49 | FILL UNIT RATE
3.38 | Overdays Isotropically consolidated undrained triaxial compression test (CIU) | /day | 0 | 383 | FILL UNIT RATE
3.39 | Anisotropically consolidated undrained triaxial compression test (CAUc) (comprising saturation, consolidation and shearing, max. 4 days) | /test | 0 | 90 | FILL UNIT RATE
3.40 | Overdays anisotropically consolidated undrained triaxial compression test (CAUc) | /day | 0 | 702 | FILL UNIT RATE
3.41 | Anisotropically consolidated undrained triaxial extension test (CAUe) (comprising saturation, consolidation and shearing, max. 4 days) | /test | 0 | 20 | FILL UNIT RATE
3.42 | Overdays anisotropically consolidated undrained triaxial extension test (CAUe) | /day | 0 | 156 | FILL UNIT RATE
3.43 | Ring shear tests (soil/soil) | /test | 0 | 39 | FILL UNIT RATE
3.44 | Ring shear tests (soil/steel) | /test | 0 | 59 | FILL UNIT RATE
3.45 | Bender element tests (as part of the CIU, CAU or DSS test) | /test | 0 | 43 | FILL UNIT RATE
3.46 | Microbially Influenced Corrosion (MIC) testing | /test | 0 | 78 | FILL UNIT RATE
Lab Testing - Standard Lab Testing Programme (Age Dating)
3.47 | Palynology analysis | /sample | 0 | 449 | FILL UNIT RATE
3.48 | Analysis of Algae | /sample | 0 | 371 | FILL UNIT RATE
3.49 | Analysis of Fungi | /sample | 0 | 371 | FILL UNIT RATE
3.50 | Analysis of Spores | /sample | 0 | 371 | FILL UNIT RATE
3.51 | Nanno- or micro-fossil analysis including Dinoflagellate Cysts and Foraminifera | /sample | 0 | 371 | FILL UNIT RATE
3.52 | Carbon dating analysis | /sample | 0 | 20 | FILL UNIT RATE
Lab Testing - Advanced Lab Testing Programme (Cyclic and dynamic tests)
3.55 | Cyclic direct simple shear tests (CSS) with pre-shearing (including three test stages as per SoW; cohesionless soils; under "drained" or "undrained" conditions) | /test | 0 | 197 | FILL UNIT RATE
3.56 | Cyclic direct simple shear tests (CSS) without pre-shearing (including two test stages as per SoW; cohesionless or cohesive soils; under "drained" or "undrained" conditions) | /test | 0 | 108 | FILL UNIT RATE
3.57 | CSS extra loading stage (up to 1500 load cycles; cohesionless or cohesive soils; under "drained" or "undrained" conditions) | /stage | 0 | 23 | FILL UNIT RATE
3.58 | Post cyclic static testing to failure if cyclic CSS test failure does not occur | /test | 0 | 122 | FILL UNIT RATE
3.59 | Cyclic triaxial compression tests (CTX) (including three test stages as per SoW; cohesionless or cohesive soils; under "drained" or "undrained" conditions) | /test | 0 | 90 | FILL UNIT RATE
3.60 | CTX extra loading stage (up to 1500 load cycles; cohesionless or cohesive soils; under "drained" or "undrained" conditions) | /stage | 0 | 12 | FILL UNIT RATE
3.61 | Post cyclic static testing to failure if cyclic CTX test failure does not occur | /test | 0 | 45 | FILL UNIT RATE
3.62 | Resonant column (RC) test (including initial loading and repeat loading as per SoW; cohesionless and cohesive samples; under "drained" or "undrained" conditions) | /test | 0 | 18 | FILL UNIT RATE
3.63 | RC extra loading stage (cohesionless and cohesive samples; under "drained" or "undrained" conditions) | /stage | 0 | 9 | FILL UNIT RATE
- Advanced Lab Testing Programme (Classification and static reference tests)
3.64 | Particle size distribution analyses (sieve) (for batch samples) | /test | 0 | 15 | FILL UNIT RATE
3.65 | Microscopic photography (for batch samples) | /test | 0 | 15 | FILL UNIT RATE
3.66 | Direct simple shear test, constant volume or constant stress (N.B. only one specimen tested under one set of conditions) | /test | 0 | 32 | FILL UNIT RATE
3.67 | Isotropically consolidated drained (CID) triaxial compression tests (N.B. only one specimen tested under one consolidation pressure) | /test | 0 | 9 | FILL UNIT RATE
3.68 | (An)isotropically consolidated undrained triaxial compression test (CIUc/CAUc) (comprising saturation, consolidation and shearing, max. 4 days) | /test | 0 | 44 | FILL UNIT RATE
3.69 | Overdays (an)isotropically consolidated undrained triaxial compression test (CAUc) | /day | 0 | 86 | FILL UNIT RATE
3.70 | Anisotropically consolidated undrained triaxial extension test (CAUe) (comprising saturation, consolidation and shearing, max. 4 days) | /test | 0 | 3 | FILL UNIT RATE
3.71 | Overdays anisotropically consolidated undrained triaxial extension test (CAUe) | /day | 0 | 6 | FILL UNIT RATE
Reporting
4.1 | Geotechnical Boreholes Report for HPA (including all results from in situ testing, standard laboratory testing programme, Age Dating analysis and MIC assessment) | Lump sum | 0 | 1 | FILL UNIT RATE
4.2 | Geotechnical Boreholes Report for LPA (including all results from in situ testing, standard laboratory testing programme, Age Dating analysis and MIC assessment) | Lump sum | 0 | 1 | FILL UNIT RATE
4.3 | Operations Report (Lot 2) | Lump sum | 0 | 1 | FILL UNIT RATE
4.4 | Advanced Laboratory Testing Report (including all classification, static, cyclic and dynamic test results from Advanced Lab Testing programme for HPA & LPA) | Lump sum | 0 | 1 | FILL UNIT RATE
4.5 | Additional reporting associated with numbers of boreholes in excess of base scope | /location | 0 | 5 | FILL UNIT RATE
4.6 | Additional reporting associated with each downhole SCPT seismic test in excess of base scope | /test | 0 | 10 | FILL UNIT RATE
4.7 | Additional reporting associated with each seismic test undertaken using P-S logging tool in excess of base scope | /test | 0 | 10 | FILL UNIT RATE
4.8 | Additional reporting associated with downhole spectral gamma logging in excess of base scope | /metre | 0 | 10 | FILL UNIT RATE
4.9 | Additional reporting associated with downhole density logging in excess of base scope | /metre | 0 | 10 | FILL UNIT RATE
4.10 | Lab test processing/reporting and any other expenses associated with lab testing not covered by other items above. | % of total lab testing price | 0 | 0 | FILL UNIT RATE
Waiting on Weather
5.1 | Waiting on Weather Name of vessel 1 during surveying PART A | /day | 0 | 0 | FILL UNIT RATE
5.2 | Waiting on Weather Name of vessel 2 during surveying PART B | /day | 0 | 0 | FILL UNIT RATE
5.3 | Waiting on Weather Name of vessel 3 during surveying PART C | /day | 0 | 0 | FILL UNIT RATE
5.4 | Waiting on Weather Name of vessel 4 during surveying PART D | /day | 0 | 0 | FILL UNIT RATE
Other
6.1 | Project meetings to be held in CLIENT offices (Utrecht or The Hague) | /meeting | 0 | 15 | FILL UNIT RATE
6.2 | Additional UXO clearance measures for borehole locations | /location | 0 | 125 | FILL UNIT RATE
6.3 | Interaction with Lot 1 contractor and certification authorities (estimated 200hrs for senior level personnel) | Lump Sum | 0 | 1 | FILL UNIT RATE
6.4 | Activities related to dissemination of results (webinar and Project Site Description) | Lump Sum | 0 | 1 | FILL UNIT RATE