| August 18, 2021 |  |
| --- | --- |
| Headline |  |
| Steam Turbine outage 2022 Rotterdam Capelle |  |
| Subheading |  |
| Note of Information #1 |  |
| Continuous text |  |

Dear Tenderers,

Hereby we would like to make one announcement for the tender Steam Turbine outage 2022 Rotterdam Capelle.

- See new time schedule in attachment below

Yours sincerely,

Tender Team

New Time schedule for this tender

| Item | Original date | New date | Hour |
| --- | --- | --- | --- |
| Publication of tender | 27.07.2021 |  |  |
| Deadline request for site visit | 10.08.2021 | 20.08.2021 | 16:00 A.M. CET |
| Site Visit | 11.08.2021 or 12.08.2021 | 11.08. – 25.08.2021 |  |
| Closure round 1 of questions / request for information | 17.08.2021 | 27.08.2021 | 17:30 P.M. CET |
| Publication of answers round 1 | 20.08.2021 | 03.09.2021 |  |
| Closure round 2 of questions / request for information | 25.08.2021 | 08.09.2021 | 17:30 P.M. CET |
| Publication of answers round 2 | 30.08.2021 | 13.09.2021 |  |
| Deadline for submission | 10.09.2021 | 24.09.2021 | 12:00 P.M. CET |
| Review of submissions | 13.09.2021- 27.09.2021 | 24.09.2021- 08.10.2021 |  |
| Interviews with top 3 tenderers | 28.09.2021- 08.10.2021 | 11.10.2021- 15.10.2021 |  |
| Announcement of preliminary winning tenderer | latest by 19.10.2021 | latest by 26.10.2021 |  |
| End of Alcatel period | latest by 09.11.2021 | latest by 16.11.2021 |  |
| Starting date of contract | latest by 16.11.2021 | latest by 23.11.2021 |  |
| Outage RoCa ST - Start Major Inspection | 16.05.2022 |  |  |
| End Major Inspection | 06.07.2022 |  |  |
| End of commissioning | 08.07.2022 |  |  |