## Risk analysis project name
Risk analysis | RISMANMETHODIEK © |  |  |  |  | Consequence probability |  |  | Consequence time |  | Consequence quality |  | Consequence costs |  | Risk score |  |  |  |  | Type of measure
Project number |  |  | 2021-36 |  |  | 0 | Risk passed |  | 0 | No consequences | 0 | Does not exist | 0 | 0 | [5 empty] | Reduce
Project name |  |  | Tender traction power components |  |  | 1 | Improbable | 0 – 5 % | 1 | 0 up to and including 1 w | 1 | Detail adjustment | 1 | 2500 | small |  |  |  |  | Repression
Component |  |  | Risk analysis |  |  | 2 | Possible | 5 – 10 % | 2 | 1 up to and including 4 w | 2 | Minor adjustment | 2 | 5000 | [5 empty] | Correction
Drawn up by |  |  | Name tenderer |  |  | 3 | Average | 10 – 25 % | 3 | 4 up to and including 12 w | 3 | Partial adjustment | 3 | 15000 | [5 empty] | Accept
Date drawn up | [5 empty] | 4 | Probable | 25 – 50 % | 4 | 12 up to and including 26 w | 4 | Comprehensive adjustment | 4 | 25000 | [5 empty] | Manipulation
Version / Status | [5 empty] | 5 | Almost certain | 50 – 100 % | 5 | > 26 w | 5 | Full adjustment | 5 | 50000
Undesirable top event |  | Money | [12 empty] | Large
Step 1: Description of the risks | [5 empty] | Step 2: Determine the size of the risk | [9 empty] | Owner |  |  |  | Step 3: Controlling the measures | [5 empty] | Planning | Various
Component | Risk number | Type of risk | Undesirable event | Cause | Consequence | Probability (0-5) |  |  | Consequence time (0-5) |  | Consequence quality (0-5) |  | Consequence costs (0-5) |  | Score (KxG) | Client | Engineering firm | Contractor | Stakeholder | Type of measure | Control measures | Action | When | residual risk | Status control measure | day-month-year | Comment risks
probability x consequence
Note on L2: Aanpassen indien gewenst: dagen - weken - maanden
Note on P2: Hoogte van de risicokosten aanpassen aan het werk (realisatie)
Note on X3: het voorkomen dat iets gebeurt of het verminderen van de kans dat het gebeurt;
Note on X4: het beperken van de schade wanneer een bedreiging optreedt;
Note on X5: het instellen van maatregelen die worden geactiveerd zodra iets is gebeurd om het effect hiervan (deels) terug te draaien
Note on X6: geen maatregelen, men accepteert de kans en het mogelijke gevolg van een bedreiging;
Note on X7: het wijzigen van parameters in de berekening om tot een gewenst resultaat te komen.
Note on K8: Indien de kans groter of gelijk aan 50 is, dient het niet als risico gezien te worden, maar dient het onderdeel van het werk te zijn.

## Input (hidden)
1 - Initiatieffase | Financieel | Tijd
2 - Offerte contractfase | Juridisch | Geld
3 - Gunning contractfase | Maatschappelijk/Sociaal | Kwaliteit
4 - Schetsontwerp | Organisatorisch
5 - Voorlopig ontwerp | Politiek/Bestuurlijk
6 - Definitief ontwerp | Ruimtelijk/Planologisch
7 - Besteksontwerp | Inhoudelijk/Technisch
8 - Uitvoeringsontwerp | …
9 - Contractfase
10 - Aanbestedingsfase
11 - Gunningsfase
12 - Uitvoeringsfase
…

## Risman explanation
What does the RISMAN method involve (Source: CROW)
The RISMAN method is a risk management method.
This method was originally developed for projects.
This RISMAN method is also suitable for organisations and programmes.
The remainder of this document will mainly address risk management for projects.
The purpose of risk management in case of projects
Risk management in case of a project has several purposes:
* Identification and mentioning risks opens the risks to a project to debate.
The various risks “inside the heads” of the project team members become visible to everyone so that the same
image can arise within the project team concerning the (main) risks to the project.
This creates a strong risk awareness within the project organisation, which makes it possible to make deliberate choices with
respect to risk control. The introduction of risk management within a project means that risks are
inventoried and discussed on a regular basis with fixed intervals. The risks within the project are kept “top of mind” and there is
continuous attention for controlling these risks.
* Risks are handled proactively instead of reactively
Indicating and implementing the control measures and before risks actually materialise makes it possible to handle risks in a proactive manner
instead of waiting for the risk to materialise and only then take action to limit the consequences.
* Handling risks in a conscious manner and considering the control measures instead of “associative”, intuitively.
Carrying out a risk analysis means that risks and control measures are inventoried in a structured manner rather than in a random manner.
This will create a more complete image of the risks to a project and the probability of “project blindness” is reduced.
What is risk management in case of projects?
Risk management can be seen as a cyclical process that consists of several steps
(see figure 2).
Step 1: performance of an integral risk analysis
A first step is to provide insight into the status at a certain moment.
This takes place by conducting an integral risks analysis.
The RISMAN method considers the project from the following perspectives, so that an integral image is obtained:
* political/administrative
* financial/economic
* legal
* technical
* organisational
* geographic/spatial
* social.
The result of the risk analysis is a list of risks sorted by the extent of the risk to the project
indicating the possible measures to reduce the probability that the risk materialises or to reduce the consequences of the
risk. We refer in this connection to “control measures”.
The risk analysis forms the basis of risk management and must be repeated at certain moments, namely:
1. at the moment major changes occur in the environment during the project
2. at the start of every new project phase.
Stap 2: determine control measures
The risk analysis presented several possible control measures for the main risks.
The project leadership (project manager, MT) decides which of these measures are actually implemented.
This takes place on the basis of on the one hand the expected impact of the control measures and on the other
the costs or effort required by the control measure. It is also determine who will actually implement
the control measure or who is responsible for implementation.
The result is a list that includes successively:
1. the risk
2. the control measures determined
3. the person responsible.
Stap 3: implementation of control measures
The responsible persons subsequently ensure that the measures are actually implemented.
Stap 4: evaluation of control measures
It must be reviewed on a regular basis whether the control measures were implemented and whether the control measures had the desired effect.
This can take place on a monthly basis during project consultation or management consultation.
Stap 5: updating the risk analysis
The list of risks that was generated originally by the risks analysis has to be updated following the evaluation
of the control measures. This means that it is assessed which risks can be removed from the list because they are no longer current as a result
of the measures implemented or as a result of the passage of time. Possible new risks are also inventoried and added to the list.
The project employees and project leadership provide input for this purpose. They are able to identify the risks on the basis of the planning, assessment and the
quality requirements that have been determined. Control measures for the new risks are inventoried as well during this consultation.
Starting points of risk management in case of projects
The main starting points in the organisation of risk management are:
1. Risk management must be in line with existing procedures.
Risk management must be in line with the existing procedure within the project as much as possible.
Reports concerning risks and the control measures implemented will therefore have to take place at the same level and at the same time
as the reporting on the related control aspects, such as in the progress reports.
The identification of new risks and the conception and monitoring of control measures must take place during all project consultations.
2. Risk management follows control.
This means that the responsibility for a risk lies where the responsibility for the work to which risk may
relate lies. In other words, every project leader or project team member is responsible for identifying
and implementing measures that are part of his responsibility.
Risk management becomes the responsibility of each project team member. The starting point that the project team members are made personally responsible
for performance of risk management is important to the successful implementation
of risk management. This means that risk management cannot be outsourced in full to an external party.
An external party can provide assistance in this connection. Risk management should become a part of team meetings that recurs on a regular basis.
Employees must recognise its usefulness and become enthusiastic about it: it must become “alive” within the project.

## Checklist
You check all possible risks using the list below and this how you obtain a complete overview of
what may be waiting for you during your project.
The legal perspective
o No/insufficient insight into all legal requirements and possible changes thereto in the area of:
• safety
• environment (EIA guidelines/evaluation of EIA)/planological adjustment (obligation to compensate any loss of nature conservation areas)
• noise
• land acquisition and expropriations
• tender procedure
• exemptions and permits
• proceedings concerning zoning plans and regional plans
o Possibility of claims:
• contractor claims as a result of implementing errors are not covered sufficiently by the contract documents
• claims from the municipality as a result of a failure to comply with arrangements made or damage to the environment
• claims from local residents as a result of damage to houses or business premises
• claims from other interested parties
o Errors on the part of the contractor relating to regulations preparation
o Errors on the part of the contractor relating to regulations implementation
The organisational perspective
o Changes to the Schedule of Requirements as a result of:
• uncertainty concerning the starting points
• changes to the project definition
o Lack of project procedures
• change procedure Schedule of Requirements, planning, estimate
• delivery/acceptance procedures
• AO procedures
• tender plan/procedure
• award procedure
o Uncertainty concerning the requirements of the client, manager, municipalities, provinces and suchlike
o Failure to make arrangements with parties involved (in time)
o The lack of sound internal and external communication; communication plan
o Lack of a quality plan
o Uncertainty about project boundaries
o No/insufficient coordination between subprojects (internal)
o No/insufficient account taken of projects in the vicinity
o Lack of the required manpower at any time:
o problems setting up and structuring the project organisation
o key persons becoming unavailable
o changes to the project name
o Failure to order materials in time
o Incorrectness and incompleteness of the estimate
o Incompleteness and carelessness in the formulation of contract documents.
The technical perspective
o Incorrect assessment of techniques, construction methods or phasing and tools
o Change to the assumptions of the design and (structural) drawings
o Extra or additional work when connecting a new work to an existing work for the purpose of realising sound coherence
o Application of new, innovative materials, implementation methods
o Design changes during implementation
o Collapse during construction
o Incorrect assessment of the quantity of material required
o Disappointing performance on the part of the contractor/designer:
• unavailability of essential equipment
• late deliveries of materials
• construction errors
• complexity performance by contractor underestimated
• strikes
The spatial perspective
o Presence of obstacles or foundation remains
o Archaeological discoveries
• possibility of excavations by the municipal archaeological service
o Presence of cables and pipes
• incompleteness inventory
• no cooperation from the owners of cables and pipes
o Special climate circumstances (long periods of frost, damage as a result of storms)
o More or heavier pollution of the location
• quality of the investigation
• insufficient insight into the remediation measures to be implemented
o Disappointing soil quality
• soil mechanical instability
• disappointing bearing strength
• unexpected occurrence of subsidence
o No or insufficient assessment of compensatory environmental measures
o Insufficient account taken of fauna measures
o Costs related to ground water protection areas
o Accessibility of the construction site
• roads leading in and out (relationship with other projects, resistance from the environment)
• insufficient space at the construction site
o Additional necessary auxiliary works and facilities for traffic and safety
o Creation of facilities or implementation of measures for road traffic and shipping
The financial perspective
o The price increase of materials is higher than expected
o Rate changes
o Bankruptcy
• contractor/supplier
• client
o Availability financing at any time
• lack of prefinancing options
• underspending
o Claims not paid in time
o No/no sound provision of financial information
o Deviation assumed depreciation
o Deviation assumed taxation
o Deviation assumed exchange rates
The social perspective
o Lack of sound communication with the environment, information and public comment procedures
o Additional noise-cancelling measures during implementation
o Measures to mitigate damage
o Damage resulting from work on the property of third parties
o Insufficient estimation of facilities or measures for road traffic and shipping
o Delaying blockades/actions by local residents
o Strikes
The political perspective
o Failure to obtain permits and approvals under public law or a failure to do so in time
o No/insufficient insight into all required permits
o Lack of agreement with the municipality/municipalities, provinces, water authorities and suchlike
o No/insufficient insight into the requirements imposed by the municipality concerning
o the method of implementation
• architectural design
• finishing/repair or adjustment infrastructure in the environment
o Problems adjusting the regional plans, zoning plans
o Problems involving expropriations