## Cycle times & prices
VIRTUAL CYCLE TIME & PRICE INTEGRATED GROUND MODEL
| Project: | IJmuiden Ver Wind Farm Sites V-VI: Integrated Ground Model |  | Hide column
| Company: | Company name | [8 empty] | Error message if no price in remuneration section
| Originator: | Originator name
[10 empty] | Note | FILL UNIT RATE
| I. Cycle Time Ground Model |  |  | max duration (days) | Unit | Cycle |  |  | (end) date | I.0
| Key dates | [9 empty] | Days between desired and ultimate report due date
| 1a | COMMENCEMENT DATE WORK | [6 empty] | 2022-06-16
| 1b | GP Phase: Provision of Geophysical Field Report | [6 empty] | 2022-07-31 |  | 59
| 1c | GP Phase: Provision of first draft Geophysical report and digital data | [6 empty] | 2022-08-31 | I.1
| 1d | GP Phase: Provision of Final Geophysical report and digital data | [6 empty] | 2022-10-31
| 1e | GP Phase: Provision of first draft Seabed Sampling Report, including lab results | [6 empty] | 2022-09-15
| 1f | GP Phase: Provision of final Seabed Sampling Report, including lab results | [6 empty] | 2022-12-01
| 1g | GT Phase: Provision of Field Report In Situ Test Report (Seabed phase) | [6 empty] | 2023-04-06
| 1h | GT Phase: Provision of Final In Situ Test Report (Seabed phase) | [6 empty] | 2023-05-08
| 1i | GT Phase: Provision of draft Seabed Sampling Report (Seabed phase), including onshore laboratory tests | [6 empty] | 2023-06-12
| 1j | GT Phase: Provision of Final Seabed Sampling Report (Seabed phase) | [6 empty] | 2023-06-28
| 1k | GT Phase: Provision of interim BH Locations Report, excluding onshore laboratory test results | [6 empty] | 2023-10-17
| 1l | GT Phase: Provision of first draft BH Locations Report, including onshore laboratory test results | [6 empty] | 2024-02-02
| 1m | GT Phase: Provision of final BH Locations Report | [6 empty] | 2024-02-27
| 1n | GT Phase: Provision of final Advanced Laboratory Test Results Report, including cyclic and dynamic laboratory testing. | [6 empty] | 2024-06-27
Preparation
| 2a | Provision of 1st revision of project documentation (days after project award) (SoW 2.2.1) | (max 8 weeks) | 56 | days |  | Fill number of days |  | 2022-06-16
| 2b | Client review 1st revision project documentation |  |  | days | 7 |  |  | 2022-06-23
| 2c | Provision of 2nd revision of project documentation (after receipt final geophysical report) (SoW 2.2.1) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2022-10-31
| 2d | Client review 2nd revision project documentation |  |  | days | 7 |  |  | 2022-11-07
| 2e | Finalise project documentation (incl additional revisions/review rounds) (after receipt final seabed sampling report GP) (SoW 2.2.1) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2022-12-01
| 2f | Review final version of project documentation |  |  | days | 2 |  |  | 2022-12-03
| 2g | Provision of Laboratory Testing Strategy Plan (days after provision of geophysical data) (SoW 2.2.4) | (Max: 8 weeks) | 56 | days |  | Fill number of days |  | 2022-10-31
| 2h | Review of Laboratory Testing Strategy Plan |  |  | days | 14 |  |  | 2022-11-14
| 2i | Provision of Final Laboratory Testing Strategy Plan (SoW 2.2.4) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2022-11-14
| 2j | Proposal VC/CPT investigation locations based on available geophysical data (days after provision of geophysical data) (SoW 2.2.5) | (Max: 4 weeks) | 28 | days |  | Fill number of days |  | 2022-10-31
| 2k | Proposal BH/CPT locations based on available geophysical data (days after provision of final geophysical data) (SoW 2.2.5) | (Max: 8 weeks) | 56 | days |  | Fill number of days |  | 2022-10-31
| 2l | Delivery of Geological Ground Model Report Template, GGM (days after provision of geophysical data) | (Max: 6 weeks) | 42 | days |  | Fill number of days |  | 2022-08-31 | I.2
| 2m | Delivery of Geotechnical Interpretation Report Template, GIR (days after provision of final laboratory testing strategy plan) | (Max: 6 weeks) | 42 | days |  | Fill number of days |  | 2022-11-14 | I.2
| 2n | Delivery of example of IGM database format (days after contract award) | (Max: 26 weeks) | 182 | days |  | Fill number of days |  | 2022-06-16 | I.2
Data processing and reporting
| 3a | Delivery of Draft Report Geological Ground Model (after reception of final geophysical report) (SoW 2.2.9) | (Max: 24 weeks) | 168 | days |  | Fill number of days |  | 2022-10-31 | I.3
| 3b | CLIENT review of Draft Report Geological Ground Model |  |  | days | 21 |  |  | 2022-11-21
| 3c | Delivery of 2nd revision Draft Report Geological Ground Model) (SoW 2.2.14) | (Max: 4 weeks) | 28 | days |  | Fill number of days |  | 2022-11-21
| 3d | CLIENT review of 2nd revision Draft Report Geological Ground Model |  |  | days | 14 |  |  | 2022-12-05
| 3e | Delivery of 3rd revision Draft Report Geological Ground Model) (SoW 22.2.14) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2022-12-05
| 3f | CLIENT review of 3rd revision Draft Report Geological Ground Model |  |  | days | 7 |  |  | 2022-12-12
| 3g | Final Report Geological Ground Model) (SoW 2.2.14) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2022-12-12
| 3h | CLIENT review of Final Report Geological Ground Model |  |  | days | 7 |  |  | 2022-12-19
| 3i | Delivery of 1st revision Draft Report Geotechnical Interpretation Report (after reception of final BH Locations report and data) (SoW 2.2.16) | (Max: 4 weeks) | 28 | days |  | Fill number of days |  | 2024-02-27
| 3j | CLIENT review of 1st revision Draft Geotechnical Interpretation Report |  |  | days | 21 |  |  | 2024-03-19
| 3k | Delivery of 2nd revision Draft Geotechnical Interpretation Report (after reception of final Advanced Lab Report and data) ) (SoW 2.2.19) | (Max: 6 weeks) | 42 | days |  | Fill number of days |  | 2024-06-27
| 3l | CLIENT review of 2nd revision Draft Geotechnical Interpretation Report |  |  | days | 14 |  |  | 2024-07-11
| 3m | Final Report Geotechnical Interpretation Report (SoW 2.2.19) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2024-07-11
| 3n | CLIENT review of Final Geotechnical Interpretation Report |  |  | days | 7 |  |  | 2024-07-18
| 3o | Delivery of 1st revision Draft Report Integrated Ground Model (after reception of final BH Locations Report and data) (SoW 2.2.18) | (Max: 8 weeks) | 56 | days |  | Fill number of days |  | 2024-02-27
| 3p | CLIENT review of 1st revision Draft Report Integrated Ground Model |  |  | days | 21 |  |  | 2024-03-19
| 3q | Delivery of 2nd revision Draft Report Integrated Ground Model (after reception of final Advanced Laboratory Report and data) ) (SoW 2.2.19) | (Max: 8 weeks) | 56 | days |  | Fill number of days |  | 2024-06-27
| 3r | CLIENT review of 2nd revision Draft Report Integrated Ground Model |  |  | days | 14 |  |  | 2024-07-11
| 3s | Delivery of 3rd revision Draft Report Integrated Ground Model (SoW 2.2.19) | (Max: 4 weeks) | 28 | days |  | Fill number of days |  | 2024-07-11
| 3t | CLIENT review of 3rd revision Draft Report Integrated Ground Model |  |  | days | 7 |  |  | 2024-07-18
| 3u | Final Report Integrated Ground Model (SoW 2.2.19) | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2024-07-18
| 3v | CLIENT review of Final Report Integrated Ground Model |  |  | days | 7 |  |  | 2024-07-25
| TOTAL DURATION CYCLE TIME | [6 empty] | 770 | days
II. Rates
| ITEM |  |  |  |  | Unit Rate | Unit | Qty | Price | II.0
| 1 | Reporting
| 1.1 | Project Execution Plan |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.2 | Reprocessing of seismic data |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.3 | Velocity picking |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.4 | Reinterpretation of PGM |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.5 | Laboratory Test Strategy |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.6 | Geological Ground Model Report (GGM) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.7 | Geotechnical Interpretation Report (GIR) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.8 | Prediction of CPTs based on seismic data |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.9 | Integrated Ground Model Report (IGM) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 2 | Other
| 2.1 | Project meetings to be held in CLIENT offices (Utrecht or The Hague) |  |  |  |  | /meeting | 5 | FILL UNIT RATE
| 2.2 | Online meetings and workshops | [6 empty] | 0
| 2.2.1 | Bi-weekly Work Progress Meetings (RVO-Contractor) |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE
| 2.2.2 | Four-weekly Joint Progress Meetings (RVO-Contractor-GT Contractor) |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE
| 2.2.3 | Expert/ specialist meetings |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE
| 2.2.4 | Workshops |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE
| 2.3 | Activities related to dissemination of results (webinar and Project Site Description) |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE | II.1
| 2.4 | Hourly rate for Project Manager |  |  |  |  | hr | 0 | FILL UNIT RATE
| 2.5 | Hourly rate for Senior Specialist |  |  |  |  | hr | 0 | FILL UNIT RATE
| 2.6 | Hourly rate for Medior Specialist |  |  |  |  | hr | 0 | FILL UNIT RATE
III. INPUT FOR ASSESSMENT OF THE OFFER
INPUT FOR ASSESSMENT OF THE PRICE CRITERION - Fixed prices/rates
| Costs |  | Reporting works |  |  |  |  | 0
|  |  | Webinar Activities |  |  |  |  | FILL UNIT RATE
| TOTAL PRICE for assessment | [6 empty] | 0 |  | III.0
|  |  | Max. number of points that can be awarded |  |  |  |  | 20
|  |  | Minimum Price (determined by CLIENT) |  |  |  |  | 700000
|  |  | Maximum Price (determined by CLIENT) |  |  |  |  | 1600000
|  |  | Points gained for the TOTAL PRICE proposed: |  |  |  |  | 0 | Points | III.0
| INPUT FOR ASSESSMENT OF THE COMPLETION DATE / CYCLE TIME CRITERION (Ability to finalize the offshore campaign at the preferred end date as set by CLIENT): | [8 empty] | III.1
| Key Completion dates |  | Desired date for Delivery of Final Report (3h,3n, 3v), set by CLIENT |  |  |  |  | 2024-09-02
|  |  | Ultimate date for Delivery of Final Reports set by CLIENT |  |  |  |  | 2024-10-31
|  |  |  | Date determined by input TENDERER |  |  |  | 2024-07-25 |  | III.2
|  |  | TOTAL difference from desired date (for assessment) |  |  |  |  | -39 | days
|  |  | Max. number of points that can be awarded |  |  |  |  | 5
|  |  | Points for the TOTAL CYCLE TIME proposed: |  |  |  |  | 5 | Points
| TOTAL POINTS GAINED BY TENDERER | [6 empty] | 5 | Points
VI. NOTES
| I.0 | IN CASE A CELL IN THIS ANNEX 4 IS COLORED RED AS SHOWN IN THIS CELL THE PROPOSAL IS NOT VALID.
| I.0 | All numbers indicated in green are starting points set by CLIENT.
| I.0 | All numbers indicated in blue (yellow cells) are to be provided by TENDERER and will form part of the PRICING SCHEDULE / CONTRACT PRICE as included in Annex 6 - Contract Section IV (Remuneration), and/or KEY DATES as included in Annex 6 - Contract Section VI (Scope of Work). All quantities will be used for assessment purposes and will also be the basis for determining the final CONTRACT PRICE and KEY DATES for these activities to be carried out under the CONTRACT. IN CASE THE BLUE TEXT TURNS RED, THIS MEANS THAT TENDERER ENTERED A VALUE OUTSIDE THE ALLOWABLE RANGES. This colour coding is for convenience only; the TENDERER is responsible for ensuring that the correct values are submitted by the TENDERER.
| I.0 | TENDERER shall specify the cycle times for executing the works. Based upon these cycle times, the key dates are determined. At Contract award these dates will be taken over in Annex 6 - Contract Section VI (Scope of Work) Please note that Liquidated Damages become applicable in case TENDERER fails to meet Key Dates as per Annex 6 - Contract Section III (Conditions of Contract)- Clause 42!
| I.1 | In case of a delay of the delivery of the data and reports from the geophysical and geotechnical contractor(s) as indicated in 1b to 1n (during execution phase of the contract), the dates for data processing and reporting (3a-3v) will be shifted accordingly.
| I.2 | TENDERER to provide dates for issue of report template based on the key dates indicated.
| I.3 | TENDERER to provide the number of days required for preparing & updating of the reports. Key dates 3a-3v are generated automatically based on these cycle times. Please note CLIENT as set maximum durations for delivery of the reports
| II.0 | At Contract award, all rates specified in this Annex 4 shall be taken over in the PRICING SCHEDULE in Annex 6 - Contract Section IV (Remuneration). See sheet [Remuneration Table] for the table and its format as will be used in Annex 6 - Contract Section IV (Remuneration).
| II.1 | Lump sum for Activities related to dissemination of results (webinar and Project Site Description) shall be paid upon completion of the webinar and PSD, in accordance with Annex 6 - Contract Section IV (Remuneration).
| III.0 | The number of points that can be awarded is determined through linear interpolation between the minimum and maximum price. IN CASE THE TOTAL VIRTUAL PRICE OFFERED IS HIGHER THAN THE MAXIMUM PRICE THEN THE PROPOSAL IS NOT VALID!
| III.1 | The TENDERER gains points when able to deliver the final report close to or before the date desired by CLIENT. The number of points that is awarded is determined through linear interpolation between the minimum and maximum number of days. In case the completion date is later than the Ultimate date set by CLIENT the proposal will be rejected! The weather downtime days as specified by the TENDERER under items 3k and 4k are included in the calculation of the OFFSHORE COMPLETION DATE (5a).
| III.2 | IN CASE THIS DATE IS LATER THAN THE ULTIMATE DUE DATE SET BY THE CLIENT THIS CELL IS COLORED RED. THIS MEANS THE PROPOSAL NOT VALID!

## Key dates
in green, bold and underlined key date for which contractor is liable for liquidated damages in case of failure to complete these dates
No. | Description | Date
1a | COMMENCEMENT DATE CONTRACT | 2022-06-16
2e | Project documentation final | 2022-12-01
2l | Geological Ground Model Report Template | 2022-08-31
2i | Provision of Final Laboratory Stratey Plan | 2022-11-14
2j | Proposal VC/CPT Investigation Locations | 2022-10-31
2k | Proposal BH/CPT Investigation Locations | 2022-10-31
3a | Draft Report - Geological Ground Model* | 2022-10-31
3g | Final Report - Geological Ground Model* | 2022-12-12
2m | Geotechnical Interpretation Report Template | 2022-11-14
3i | Draft Report - Geotechnical Interpretation Report | 2024-02-27
3m | Final Report - Geotechnical Interpretation Report | 2024-07-11
2n | Example of IGM Database format | 2022-06-16
3o | Draft Report - Integrated Ground Model* | 2024-02-27
3u | Final Report Integrated Ground Model* | 2024-07-18

## Remuneration Table
Item | Description | Unit | Unit Rate | Quantity | Price
Reporting
1.1 | Project Execution Plan | Lump sum | 0 | 1 | FILL UNIT RATE
1.2 | Reprocessing of seismic data | Lump sum | 0 | 1 | FILL UNIT RATE
1.3 | Velocity picking | Lump sum | 0 | 1 | FILL UNIT RATE
1.4 | Reinterpretation of PGM | Lump sum | 0 | 1 | FILL UNIT RATE
1.5 | Laboratory Test Strategy | Lump sum | 0 | 1 | FILL UNIT RATE
1.6 | Geological Ground Model Report (GGM) | Lump sum | 0 | 1 | FILL UNIT RATE
1.7 | Geotechnical Interpretation Report (GIR) | Lump sum | 0 | 1 | FILL UNIT RATE
1.8 | Prediction of CPTs based on seismic data | Lump sum | 0 | 1 | FILL UNIT RATE
1.9 | Integrated Ground Model Report (IGM) | Lump sum | 0 | 1 | FILL UNIT RATE
Other
2.1 | Project meetings to be held in CLIENT offices (Utrecht or The Hague) | /meeting | 0 | 5 | FILL UNIT RATE
2.2 | Online meetings and workshops |  |  |  | 0
2.2.1 | Bi-weekly Work Progress Meetings (RVO-Contractor) | Lump Sum | 0 | 1 | FILL UNIT RATE
2.2.2 | Four-weekly Joint Progress Meetings (RVO-Contractor-GT Contractor) | Lump Sum | 0 | 1 | FILL UNIT RATE
2.2.3 | Expert/ specialist meetings | Lump Sum | 0 | 1 | FILL UNIT RATE
2.2.4 | Workshops | Lump Sum | 0 | 1 | FILL UNIT RATE
2.3 | Activities related to dissemination of results (webinar and Project Site Description) | Lump Sum | 0 | 1 | FILL UNIT RATE
2.4 | Hourly rate for Project Manager | hr | 0 | 0 | FILL UNIT RATE
2.5 | Hourly rate for Senior Specialist | hr | 0 | 0 | FILL UNIT RATE
2.6 | Hourly rate for Medior Specialist | hr | 0 | 0 | FILL UNIT RATE