Terms of Reference (ToR)

‘Strengthening the capacity

of 14 regional referral

hospitals in Uganda’

D2B19UG02

Content

1	BACKGROUND	3

1.1	Introduction	3

1.2	Project Context	3

1.2.1	General context	3

1.2.2	Problem analysis	5

1.2.3	Pre-feasilbility study	6

1.2.4	Priority fields of recipient government	9

2	PROJECT DEFINITION	9

2.1	Project scope	9

2.2	Project objectives	10

2.3	Assumptions	10

2.4	General risks	11

3	SERVICES	14

3.1	Objectives	14

3.2	Phases and deliverables	15

3.3	Phase 1: Inception	18

3.4	Phase 2: Reassessment of project definition, costs and baseline situation (update pre-feasibility study)	19

3.5	Phase 3: Feasibility and detailed project plan	24

3.6	Phase 4: DRIVE Intake Form	27

3.7	Phase 5: Preparation of procurement documents	27

4	PROJECT BUDGET	28

5	PROJECT DURATION	28

6	PROJECT ORGANIZATION AND STRUCTURE	29

6.1	Project Steering Committee	29

6.2	Project Management Unit	29

6.3	Roles and responsibilities project stakeholders	30

7	CONSULTANT TEAM PROFILE	31

7.1	Qualification requirements firms	31

7.2	Qualification requirements staffing	31

Annexes	35

- BACKGROUND

  - Introduction

The Ugandan Ministry of Health (MOH) wishes to cooperate with the Netherlands Enterprise Agency (RVO) with the aim to Strengthening the Capacity of 14 Regional Referral Hospitals (RRH) in Uganda. To this end, various activities need to be carried out, amongst others the studies as described in this Terms of Reference (TOR) document.

These TOR provide the detailed activities to be carried out by a Consultant who is to be selected through an open competitive bidding procedure, managed and financed by RVO through the Develop2Build (D2B) program, in cooperation with the Ugandan MOH.

Through D2B the Ministry of Foreign Affairs of The Netherlands provides support to foreign governments eligible for support in developing relevant infrastructure with positive effects on people, the environment and society. D2B focuses on infrastructure in the sectors of water, food security, climate and sexual and reproductive health and rights (SRHR). The projects must contribute to the development of the private sector, improving people’s ability to provide for themselves.

D2B supports projects in least developed countries and the Dutch development cooperation partner countries and focuses on the development, procurement and implementation readiness of infrastructure projects that ensure technical, social, environmental, financial and economical sustainability.

  - Project Context

    - General context

The main objective of this project is to strengthen the capacity of 14 RRHs in Uganda, which are fully owned by the Ugandan Ministry of Health (MOH). These hospitals suffer from a lack of resources and assets, disfunctional equipment and shortage of skilled staff which render these hospitals unable to provide the standard and/or volume of care required. Due to this, local communities do not trust the care provided at the nearest RRH. For that reason people seek healthcare services at higher levels (National Referral Hospitals) resulting in an overstressed use of these facilities.

Public health services in Uganda are delivered through four hub categories: Health Centres (subdivided in HC I, HC II, HC III and HC IV), General Hospitals (GH), Regional Referral Hospitals (RRH) and National Referral Hospitals (NRH) or Specialized Hospitals (SH). The range of health services delivered varies with the level of care. RRHs function as the first line of referral for the GH or the HCs if a GH is not available and/or able to provide the required health care services, and offer more advanced and relatively more specialized medical services than the HCs and GHs (see table 1).

Health Centers

The HC I health centers have no physical structure, but consist of a team of people, the Village Health Team (VHT), a team that functions as a link between the health centres and communities. The HC II provides only outpatient care and community outreach services. An enrolled comprehensive nurse is the key person between the VHTs and the HC IIs. The HC II provides the first level of interaction between the formal health sector and the communities. The HC III provides basic promotive, preventive and curative care and provides support supervision of the community and the HC IIs under its jurisdiction. There are provisions for laboratory services for diagnosis and maternal care. HC III are the first referral point at sub-county level. Patients from HC IIIs are reffered to HC IVs at county level. HC IVs, run by a medical doctor, are providing surgical services in addition to all the services provided at HC III. They are also intended to provide blood transfusion services and comprehensive emergency obstetric care.

| Level of Health Unit | Level | Health system supervision | Target population | Services provided |
| --- | --- | --- | --- | --- |
| - Health Centre I | Village | Village Health Team | 1,000 | Community based preventive and promotive health services |
| - Health Centre II | Parish | Local Council | 5,000 | Preventive, promotive, outpatient curative health services, outreach care and emergency deliveries |
| - Health Centre III | Sub-county | Local Council | 20,000 | Preventive, promotive, outpatient curative, maternity, inpatient health services and laboratory. |
| - Health Centre IV | County | Health Sub-District Team | 100,000 | Preventive, promotive, outpatient curative, maternity, inpatient health services, emergency surgery, blood transfusion and laboratory services |
| - General Hospital | District | District Health Office | 500,000 | In addition to services offered at HC IV other general services are provided. They also provide in- service training, consultation and research to community-based health care programmes. |
| - Regional Referral Hospital | District | Ministry of Health | 2,000,000 | In addition to services offered at the General Hospitals, specialist services are offered, such as Psychiatry, Ear Nose Throat, Ophthalmology, Dentistry, Radiology, Intensive Care, Pathology, higher level surgery and medical services. Also function as teaching hospitals in some areas. |
| - National Referral Hospital | National | Ministry of Health | 45,000,000 | Provision of comprehensive specialist services. In addition they are involved in teaching and research. |

Table 1: Summary of public health services delivery in Uganda

General Hospitals

GHs are the first level of secondary care available and provide general hospital services to inpatients and outpatients. On average, a GH has around 130 beds, a 24-hour emergency service and a minor operating theatre. In some circumstances primary health care services are rendered where there is no alternative source of this care within a reasonable distance. GHs receive referrals from the dispensaries and HCs IV in its counties.

Regional Referral Hospitals

RRHs function as the first line of referral for the GHs (or HCs IV if a GH is not available) and offer more advanced and relatively more specialized medical services than hospitals at general level. Larger than GHs, RRHs employ more staff, including specialists in various fields, and cover a catchment area of several districts, serving several millions of inhabitants. RRHs refer patients to NRHs which are at the top of the referral system in Uganda.

National Referral/ Specialized Hospitals

NRHs offer tertiary and specialy healthcare services and form as such the top of the referral system in Uganda. The services provided include various fields and specialties such as cardiology, oncology, neurology, paediatrics, nephrology, psychiatry, obstetrics, gynaecology and orthopaedics. All NRHs are located in the capital Kampala. There are three NRHs: Kiruddu National Referral Hospital, Kawempe National Referral Hospital and Butabika National Referral Mental Hospital in the capital. The Mulago Specialized Women’s Hospital is a newly opened hospital with specialized Obstetrics and Gynaecology services. As such, for these services, it also functions as a NRH. An upgraded Mulago Super Specialized Hospital is yet to be opened for highly specialized healthcare services as well.

Health Care Referral System

Referral can be defined as any process in which health care providers at lower levels of the health system, who lack the skills, the facilities, or both to manage a given clinical condition, seek the assistance of providers who are better equipped or specially trained, to take over responsibility for managing a clinical condition of a patient. Referral thus takes place from a lower level of care, to an increasingly higher level (see figure 1).

Figure 1: Uganda’s Health Care Referral system

For a referral system to work, there should be a marked distinction in the type and level of services offered by healthcare facilities at different levels. The referral system is consistent with the pyramidal shape of the healthcare system. The bottom represents many healthcare facilities at primary level who deliver basic healthcare services, from which a patient, if necessary, moves up along different levels of care to finally reach the top, which consists of a much smaller number of tertiary and specialized hospitals who have access to highly trained staff and the most advanced medical equipment. A functional referral system corresponds to a geographical division where primary healthcare facilities (HC) in a certain district refer to the GH. All GHs in a certain region refer to the RRH in that region. RRHs in their turn refer to the NRHs.

- Problem analysis

The healthcare referral system in Uganda is faced with several challenges. One of the main reasons for the referral system not to function properly is the unavailability or inadequacy of services and resources (e.g. skilled staff and equipment) at lower levels of care. This encourages patients to enter the health system at a higher level of care, provided by the RRHs and the NRHs in Uganda, than strictly necessary. These level 6 and 7 hospitals provide specialized health care services but are often overcrowded due to health services delivered to patients who should have been attended to at a lower level within the referral system (Table 1: Level of Health Unit 1 to 5). The Kawempe and Kiruddu NRHs in Kampala are examples of overcrowded level 7 hospitals.

The fact that the referral system is not working properly also leads to cost increases because many people are treated at higher costs than necessary when looking at the level of care required. Thus, one of the basic premises to strengthen the referral system is to offer the right level of qualitative  health care to patients at the lowest possible level to allow hospitals higher in the referral system to focus on more advanced and specialized services.

The second main reason is that many hospitals in Uganda are located in isolated regions, from where referral might exist as a theoretical concept, but practically it is not considered a realistic option for patients who lack the financial means or time (in terms of progress in their medical condition) to travel to the nearest referral facility. For these hospitals it is even more important to be able to offer at least the range and quality of diagnostic and treatment services they are supposed to within the referral system. These hospitals should treat as many patients and conditions independently instead of having to advise them to seek for care at a more advanced and distant facility, knowing the patient is likely to go home and not receive any care at all. The biggest challenge is to provide the right health care services at the right levels of healthcare.

This project thus focuses on the RRHs, providing access to well-functioning, state-of-the-art and sustainable medical equipment with supporting infrastructure and adequately trained staff. It is expected that this will enable them to better fulfil their role in the referral system and ultimately improve patient care and health outcomes.

- Pre-feasilbility study

AMPC International Health Consultants (AMPC) performed the AMPC Assessment v2.0 I August 2019 (Annex 1) of the 14 RRHs in Uganda. Several fact-finding missions have been conducted to assess the equipment needs of the RRHs. In March 2019, the latest inventory and assessment was performed of all major equipment present at selected departments – maternity, newborn, diagnostic, accident & emergency, intensive care and surgical – in all fourteen project RRHs. To the AMPC Assessment v2.0 I August 2019 four annexes were attached and these can also be found as annexes to this TOR: Site Visit Report (Annex 2), Equipment List per Hospital (Annex 3), Capacity Building Plan (Annex 4) and Power Infrastructure Requirements (Annex 5).

Description of project area

The 14 RRHs that are proposed to be part of the project are located throughout Uganda (see figure 2). The target population per RRH is around 2 million.

Figure 2: Map showing the locations of the 14 Regional Referral Hospitals

Equipment and infrastructure needs assessment

During the site visits of AMPC, the following data and information was gathered:

- Information on the status of the major equipment at the main departments in the 14 RRHs;

- Information about the infrastructure that supports this equipment;

- Information about the available Human Resources in the 14 RRHs;

- Mapping of the main challenges that the 14 RRHs are facing.

An inventory was done of all major equipment that were present during the visits at selected departments. Neither instruments nor patient wards were part of the assessment. The following departments were included in this assessment:

- Radiology (Imaging);

- Accident & Emergency (A&E);

- Main Operating Theatres (OTs);

- Central Sterilization Services Departments (CSSD)

- Recovery

- ICU;

- Maternity;

- Obstetric OTs/ Delivery Rooms

- NICU

- Maintenance workshop.

In all RRHs that were assessed outside the capital Kampala, the laboratories appeared to be in a rather good state. The number and type of equipment present as well as the maintenance status of the equipment were good. The reason for this is an ongoing countrywide project aiming at strengthening the capacity of the laboratories funded by USAID/ Sustain. Since this project is still ongoing, it was decided to exclude the laboratories from both the report and the scope of the project.

Description of the equipment

In all RRHs assessed, the medical equipment was generally in a “poor” condition across all of the departments visited. This means that equipment was either partly broken (varying from a switch that is not working to an ultrasound transducer having problems with its crystals), or that the equipment was not working at all.

Furthermore, there is a gap in the “completeness” and “adequacy” of equipment per department (e.g. the most suitable type of equipment(s) in the required quantity for the health care services to be provided). It needs to be (re)-established by the Consultant what constitutes this gap of equipment per department, and what not, in order to determine what equipment per department needs to be replaced through the intervention proposed by this project. Per the AMPC assessment 2019, the equipment in use was unlikely to remain functional for more than 2-3 years even if maintenance plans were put in place, due to end of life or damage already done to components.

Description of the infrastructure

Over the last few years, there have been significant investments by the Japanese funding agency, Japan International Cooperation Agency (JICA), into the upgrading of various buildings and infrastructure (power/water/medical gas) at the RRHs, which since then are considered to be in very good condition and of good quality. However, the majority of buildings which have not been upgraded are in a very poor and dilapidated state and are in urgent need of highly needed renovations.

A stable power supply is of critical importance at all hospitals. Almost all RRHs have a maximum available power supply of 200KVA with only Mbarara having three 500KVA transformers on site and a new main distribution panel. Where JICA have built new buildings/departments they have included a new transformer and distribution board for these buildings, but this does not extend to the rest of the hospital, nor does it have the capacity to be extended to other buildings on the site.

For any equipment upgrades to be successful, upgraded power supplies will be required at each hospital including main switch gear, voltage regulators and stabilizers. Without this upgrade, any new equipment would not be able to function effectively. Electrical power quality is already significantly hindering the reliability and availability of much of the equipment currently present in the RRHs. For example, some CSSD departments have been upgraded recently with new vacuum steam sterilizers but are unable to run due to lack of power.

Human resources status

As in all other African countries, Uganda suffers from an overall shortage of health workers. In addition, it was noticed that in the RRHs the number of trained specialized nurses is not enough. This results in a significant challenge to provide A&E, ICU and NICU services.

Many hospitals have no ICU or even HDU department available at all and even in the few that had ICUs, most are not in use due to a lack of trained ICU nurses and other support staff. All hospitals expressed the need for a fully functional ICU, but confirmed that they did not have sufficient suitably trained staff to run the units. In many neonatal ICUs there are on average 10 - 15 babies per nurse versus the recommended 1 nurse to 4 babies ratio for adequate NICU care at any given time. As such, this negatively influences the clinical outcomes and ability to deliver a full NICU service significantly.

Surgeons were a contrast to this trend as there appeared to be sufficient surgeons available. However, they were hindered by a lack of equipment with some hospitals even sending their surgeons to other hospitals as there were no longer the facilities available for them to continue performing procedures safely at the respective hospitals.

Furthermore, skilled technical staff needed to perform preventive and corrective maintenance of medical equipment are not present, either in number and/or level of training, in the assessed hospitals. The pre-feasibility study did not address the availability and skills of management and supporting staff at the RRHs

- Priority fields of recipient government

The proposed project is also complementary to past, currently ongoing and possibly other future projects related to the RRHs, in order to avoid any duplication. Among the RRHs currently, the only project improving the infrastructure and equipment availability is the East African Public Health Laboratory Networking Project (EAPHLNP) which does not overlap with the proposed project. Of course, it should be investigated if there are other initiatives and/or projects being developed, implemented or finalized that are of influence on the RRHs.

The proposed project is aligned with the Health Sector’s strategic objective I and IV to contribute to production of a healthy human capital for wealth creation through provision of equitable, safe and sustainable health services. In particular, the upgraded healthcare services at the RRHs will reduce referrals both nationally and internationally eventually availing better free-to-access healthcare services.

- PROJECT DEFINITION

  - Project scope

The project scope is currently defined as the improvement of the 14 RRHs in Uganda. This will strengthen the health care referral system.

During the studies described in this TOR the exact project definition will be defined. At current, the documents provided (See annexes 1 to 5) identify the following project components:

- Delivery and installation of medical equipment;

- Improvement of physical infrastructure to ensure proper functioning of the new high-end

medical equipment;

- Capacity building and transfer of specific knowledge to ensure the sustainability of implemented

improvements;

- Maintenance of all installed equipment for 5 years.

Within the scope of the current project, the referral system will be improved mainly in the areas of maternal and neonatal care, surgery, diagnostic imaging and emergency care. In practical terms this means, for example, that regional level maternity departments should be able to spend more time on high-risk pregnancies and deliveries with major complications. In the same way, better diagnostic imaging equipment installed in RRHs (such as digital x-ray, PACS) will increase regional diagnostic capacity and relieve the pressure on the two NRH. To strengthen their position in the referral system even more, the RRHs should be able to offer high-end diagnostic services like CT examinations, breast diagnosis and even MRI scans. Therefore, the diagnostics package of the project has been enhanced with high-end diagnostic imaging equipment such as CT scanners, Mammography equipment and MRI scanners.

Table 2: List of the 14 Regional Referral Hospitals that will be strengthened

  - Project objectives

Overall objective

The overall objective of the project is to reduce general, mother and child morbidity and mortality rates in Uganda. This will be achieved by increasing the quality and quantity of healthcare services through strengthening the Ugandan regional referral health care system.

Specific objective

The specific objective of the D2B Studies is to develop an integrated project plan and a set of procurement documents required for the eventual sustainable implementation of an infrastructure project aimed at strengthening 14 RRHs in Uganda.

  - Assumptions

The following assumptions have been made as preconditions for the successful execution of the D2B studies:

- The COVID-19 situation in and outside Uganda, regional security circumstances and the

elections aftermath should not prevent teams of local and, where appropriate and necessary,

international experts from working on the ground;

- A continuous and structured consultation is established between the Consultant, RVO, the

Project Management Unit, the Project Steering Committee, the Government of Uganda and other project stakeholders in order to facilitate information exchange, task execution, review of results and orientation of the studies;

- Study resources can be mobilised in an efficient and timely manner;

- The review and validation of the interim and final reports shall take place within a reasonable

period of time to ensure that the D2B studies can be delivered within the expected time frame;

- The scope and solution proposed in the D2B studies, which can deviate if required and

necessary from the project scope currently known (See Annexes 1 – 5), is known to the project stakeholders;

- The experts that will carry out the Environmental and Social Impact Assessment as part of the

D2B Studies need to be formally registered and certified by the Government of Uganda National Environmental Management Authority (NEMA). International experts that are not registered can only participate in the execution of the ESIA as part of a team led by a registered and certified expert (see also section 7.2). This requirement does not apply to local and/or international experts carrying out project briefs.

An assessment of the potential risks and their mitigation measures related to the implementation of the D2B studies and infrastructure project is provided in the next section.

  - General risks

An assessment of the probability and impact of expected risks, including proposed mitigation measures is provided in the table below. The Consultant is expected to take these risks into account in its proposal and to add, if needed, any other relevant risks.

| Type of risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Time risk: delays during project development, for instance during review of the studies | Medium | Medium | - All parties involved (amongst others MOH, RVO and the Consultant) need to respect and meet the agreed upon timelines. A dedicated project team has to be set up within MOH. - RVO will build in go/no go decisions in the assignment. |
| Political risks: elections in February 2021. Is this project still a priority for the next government? Will a budget be available for the implementation of this project? | Medium | High | - Budget for the project needs to be included in the FY2020/21 and beyond. - MOFPED should guarantee the availability of the supplemental budget to complete the project post the 2021 elections. |

| Financing risks: lack of budget for the required capital and operational expenditures by MOH / MOFPED. | High | High | - If the Government of Uganda is not able to sustainably secure the substantial required capital and operational budget, then the realization of the intended goals and impact of the project are at risk. It should be reviewed and established how the required residual financing by MOH / MOFPED can be secured up front through cooperation with (an)other donor(s)/ financier(s), as this is necessary to secure financial and operational feasibility and sustainability of the project. - Apart from the above, MOFPED is expected to confirm its long term financial commitment to the project in the Grant Arrangement and/or in a separate commitment letter. |
| --- | --- | --- | --- |
| Institutional risks: does MOH have the capacity to review the studies and become the project owner after completion of the studies? Does MOH have the institutional capacity to organize the tender for construction? | Medium to High | High | - A dedicated project team with the right skills and decision-making mandate has to be set up within MOH. - If needed, RVO could provide technical assistance to MOH during the procurement procedure required to select the eventual winning Turn-Key bidder and the winning Independent Supervisor. |
| Construction risks: the implementation of this project could be delayed and/or could suffer cost overruns. | Medium | High | - MOFPED should guarantee to cover any cost overruns during the implementation phase. - The Employer and Contractor(s) should guarantee project completion in accordance with the contractually agreed terms and conditions, including the contract price. |
| Operational risks: do the staff of the RRHs have enough skills and knowledge to use the equipment? How to ensure a sustainable transfer of knowledge? Do the hospitals have enough skilled staff at all levels (management, health care providers, technicians, supporting staff etc.)? | High | High | - The project scope includes a training component. The feasibility study should further study the gap in human resources and recommend measures to ensure that here is sufficient staff available in the RRHs and that the staff is sufficiently skilled to use the equipment. - Secured and (continued) availlability of the required skilled staff at all levels in the run up to and as of the moment of handover and start of operations per RRH and throughout the lifecycle of the project (implementation and operations and maintenance phases) and beyond. - Apart from getting the right staff at all levels trained and available at the required moments per RRH, this staff needs to be retained during the lifecycle of the project to keep the facility up and running. It needs to become clear how this is secured long term. |
| Maintenance risks: how can we ensure proper life cycle maintenance of the equipment? | Medium | High | - 5 years maintenance is included in the project scope for implementation (1-year warranty and 4 years maintenance after installation). - Capacity building of MOH Biomedical Engineers to be able to independently service and repair the medical equipment also post the project duration. - Guarantee by the equipment suppliers of availability of spares for the supplied equipment for the duration of their life cycle that will be enforced by a requirement of local presence for easy access of after sales services when needed. - Use of a project supplied inventory management system that tracks medical equipment performance, service and repairs. |
| Social risks - Occupational Health and Safety during construction - Health and safety community - Land issues for expansion | High | Medium | - Inclusive consultation of stakeholders proportional to the project including the Minstry of Gender, Labour and Social Development - Mitigation and management of identified impacts through implementation of the Environmental and Social Management System (ESMS), ESMP and related specific management plans (e.g. OHS plan, HR-plan, local recruiment plan, stakeholder engagement plan, traffic). - Residual impacts including those outside the sphere of influence should be clearly identified during the scoping phase (Phase II) to inform the go/no go decision. |
| Environmental risks - Unsustainable collection and disposal of waste during construction and operations & maintenance phase | High | Medium | - Inclusive consultation of stakeholders proportional to the project. - Mitigation and management of identified impacts through implementation of the Environmental and Social Management System (ESMS), ESMP and related specific management plans (e.g. OHS plan, HR-plan, local recruiment plan, stakeholder engagement plan, traffic) - Alignment and compliance with the National Environment (Waste Management) Regulations 2020 and IFC PS as well as safeguarding the guidelines from the Ugandan Atomic Energy Council. - Residual impacts including those outside the sphere of influence should be clearly identified during the scoping phase (Phase II) to inform the go/no go decision. |

| COVID-19 risks - Delays and restrictions for execution of the D2B studies - Risks of spreading catching the virus during study phase or implementation of the project |  |  | - A methodology for the safe execution of the studies will be developed by the Consultant as part of Implementation Strategy that will be prepared for the bid of the tender. This methodology should take into consideration local and international restrictive measures. This should include a periodic review to adapt to changing cicrumstances. - Identification of potential COVID-19 risks for workers and the community should be identified as a part of the ESIA process. Mitigation and management of identified impacts through implementation of the ESMS, ESMP and related specific management plans (e.g. OHS plan, stakeholder engagement plan, EHS) - Alignment and compliance with MOH Guidelines on preventive measures against the coronavirus (https://www.health.go.ug/covid/) and the IFC Performance Standards and IFC’s interim advice on how to handle COVID-19-risks (see next point) - IFC’s interim advice on how to handle COVID-19-risks during various project phases should be consulted: - For Interim Advice for IFC Clients on Preventing and Managing Health Risks of COVID-19 in the Workplace - Interim Advice for IFC Clients on Supporting Workers in the Context of COVID-19 - Interim Advice for IFC Clients on Safe Stakeholder Engagement in the Context of COVID-19 - Interim Advice for IFC Clients on Developing a COVID-19 Emergency Preparedness and Response Plan (EPRP) |
| --- | --- | --- | --- |

- SERVICES

  - Objectives

The D2B studies refer to the full list of tasks and services requested under these TOR. The objective of these studies is to provide the Ugandan MOH with a detailed project and procurement plan for the implementation of an infrastructure project to strengthen 14 RRHs and which can potentially benefit from DRIVE co-financing if all DRIVE relevant requirements are met. For and during the development of the D2B studies it is therefore required that the DRIVE Policy Rules and Criteria (https://english.rvo.nl/subsidies-programmes/development-related-infrastructure-investment-vehicle-drive) and Intake Form (Annex 6) are applied and adhered to.

  - Phases and deliverables

The assignment for the Consultant is set-up in five phases. Each phase consists of specific tasks and deliverables, which are presented in the table below. At the end of each phase the Consultant will have meetings with the Project Steering Committee (SC) and RVO to discuss and get approval of deliverables (SC1 – SC5). After that, RVO will be requested for a go/no go decision in consultation with the MOH of Uganda before moving into the next phase. More detailed information on the project organisation can be found in Section 6.

Phase 1 is the kick-off of the project, which should result in an inception report including a detailed description of tasks, deliverables and timetable for the implementation of the D2B studies. The objective of Phase 2 is a reassessment of the project scope and definition, which should result in an update of the pre-feasibility study (Annex 1). At the end of Phase 2, RVO, after consultation with the MOH, will take a go/no go decision which is required to allow the Consultant to move forward with  Phase 3, Feasibility and detailed project plan. By the end of phase 3 RVO wants to be able to determine if the terms and conditions set by the DRIVE Policy Rules are expected to be sufficiently met, and as a result would give reason for the Consultant to start with Phase 4, DRIVE Intake Form. The Consultant will be required to prepare in full the DRIVE Intake forms and provide all necessary annexes which the MOH is expected to put forward to RVO for formal assessment by the Assessment Committee DRIVE. The Consultant is also tasked to prepare the procurement documentation for the Contract to deliver capital goods, works and related services (Turn Key Contract) and for the Independent Supervision contract in Phase 5. Of course, draft procurement documents for the aforementioned two contracts can already be shared with the assistance of the Consultant by the MOH of Uganda as part of Phase 4.  The finalization of the procurement documents can only start after the go/no go decision for Phase 4.

Environmental and social deliverables

Establishing what is needed to ensure that the Project is in full compliance with the IFC Performance Standards (IFC PS) and the Ugandan ESIA regulations is an essential deliverable. For the overall Project and per individual project site it needs to be determined what environmental and social assessment(s) is (are) required that will ensure in content, outline, proportionality and form that the applicable national and international environmental and social standards will be met.

According to Ugandan regulations two project categories may apply to the project: those that require a project brief and those that require a full-scale ESIA. The IFC categorisation works with the A/B/C environmental and social categories of the IFC1. The IFC categories are:

- Category A: a project is classified as Category A if it has the potential to have significant adverse environmental and/or social impacts, which are diverse, irreversible and/or unprecedented. These impacts may affect an area broader than the sites or facilities subject to physical works. The consequences may be irreversible or unique. For category A projects a full-scale ESIA is mandatory.

- Category B: a project is classified as Category B if its potential environmental and/or social impacts are less adverse than those of Category A projects. Typically, these impacts are few in number, are site-specific, few of them (if any) are irreversible, and mitigation measures are more readily available. For Category B projects a full-scale ESIA is required.

- Category C: a project is classified as Category C if it has minimal or no potentially adverse environmental and/or social impact. For Category C projects a limited ESIA is required in which potential adverse impacts are identified, prevented or mitigated and should be described in an impact analysis and should include a detailed ESMP.

Based on the preliminary screening (see Annex 7) provided by both the Netherlands Commission for Environmental Assessment (NCEA) and by NEMA it is expected that for most RRHs a limited ESIA (=project brief according to Ugandan ESIA regulations) would suffice, instead of a full-scale ESIA. The list of requirements to be covered through either the one or the other can thus differ.

It is necessary to ensure appropriate compliance on ESIA requirements for the Project with the Ugandan ESIA Regulations as well as the IFC PS. This means that it needs to be determined as early as possible what the required depth and scope of the required ESIA overall and per project location should be, taking into consideration the inherent qualified impacts and risks. That can also provide an explanation of the differences between individual project sites on for example the effort(s) needed to gather the necessary site inspection and baseline information, to conduct a suitable stakeholder consultation etc.

Furthermore, it might even be the case that for some project sites it is established that the environmental and social impacts and risks are minimal or even non-existent, warranting the conclusion that for these project sites an impact assessment is not required but would require as a minimum topics of resource efficiency and waste management to be addressed in the screening report and integrated in the project plan.

The aforementioned exemplifies the importance of the screening phase wherein the Consultant is required to clearly justify the overall project and project site specific requirements for the ESIA in content, scope and depth, because it is important that both NEMA together with the competent authority as well as RVO can assess the appropriateness of the proposed level of assessment whilst making sure that the required approval and/or statement of no objection procedures take place in a timely manner. For example, projects for which a full-scale ESIA is mandatory go through a more elaborate procedure, involving the development of a scoping study and Terms of Reference (ToR), compared to projects that require a limited ESIA (or project brief) or none at all.

In Phase 1 the Consultant will be asked to report on how all environmental and social requirements will be delivered on. After receiving the required approvals and statement of no objections for Phase 1, the Consultant will work, amongst others, towards the presentation of a summary document highlighting the overall results of the ESIA Process as well as the overall and site specific characteristics, profile, impacts and managements thereof (see Phase 3). Obviously, this will be an important part of the Turk Key solution for the project.

Like already mentioned above, NEMA and RVO and the other project stakeholders will cooperate to assure mutual acceptance and approval of any required and necessary action to achieve full compliance with the national ESIA requirements and with the IFC PS. With regard to the environmental and social deliverables it is important to note that in case of differences on the ESIA requirements, categorisation and scope between national ESIA requirements (NEMA) and the IFC PS (RVO) the most strict requirements will apply.

Table with phases, tasks, deliverables and Go/No Go decisions

| Phase | Task | Deliverables |
| --- | --- | --- |
| Phase 1: Inception (SC1) | 1.1 | Inception report |
|  | 1.2 | Environmental and social screening and approach |
| Go/No Go decision by RVO (after consultation of the SC), prior to start of Phase 2 |  |  |
| Phase 2: Reassessment of project definition, costs and baseline situation (update pre-feasibility study) (SC2) | 2.1 | Theory of Change |
|  | 2.2 | Institutional and stakeholder analysis |
|  | 2.3 | Reassessment hospital equipment and infrastructure needs |
|  | 2.4 | Reassessment capacity building plan and human resources planning |
|  | 2.5 | Environmental and social scoping |
|  | 2.6 | Preliminary cost-benefit analysis |
|  | 2.7 | Preliminary assessment continuous secured and sustainable residual financing options for the capital and operational expenses budget and the fiscal framework |
|  | 2.8 | Preliminary assessment of procurement options |
|  | 2.9 | Reassessment of project risks |
|  | 2.10 | Reassessment of project definition and baseline situation |
| Go/no go decision by RVO (after consultation of the SC), prior to start of Phase 3 |  |  |
| Phase 3: Feasibility and detailed project plan (SC3) | 3.1 | Finalisation of the Environmental and Social Impact Assessment for the Project and all project locations, including the Environmental and Social Action Plan and Environmental and Social Management Plan |
|  | 3.2 | Detailed cost-benefit analysis |
|  | 3.3 | Continuous secured and sustainable residual financing options for the capital and operational expenses budget |
|  | 3.4 | Detailed medical and non-medical equipment specificatione |
|  | 3.5 | Detailed technical specifications for power infrastructure |
|  | 3.6 | Detailed organisational plan |
|  | 3.7 | Detailed capacity building plan |
|  | 3.8 | Detailed operations and maintenance plan |
|  | 3.9 | Detailed procurement plan |
|  | 3.10 | Detailed financing plan |
| Go/no go decision by RVO (after consultation of the SC), prior to start of Phase 3 |  |  |
| Phase 4e: DRIVE Intake Form (SC4) | 4.1 | Preparation and finalization of a full DRIVE Intake Form with all required addenda formally to be submitted by MOH |
| Go/no go decision by RVO (Assessment Committee DRIVE) based on the submitted DRIVE Intake Form with all required addenda prior to start of Phase 5 |  |  |
| Phase 5: Procurement documents (SC5) | 5.1 | Tender documents for the Independent Supervision Contract |
|  | 5.2 | Tender documents for the DRIVE Transaction Contract |
| Go/no go decision by RVO prior to signing of the DRIVE Grant Arrangement |  |  |

The detailed description of each phase and deliverable is provided in the following sections.

  - Phase 1: Inception

| Phase 1: Inception |  |
| --- | --- |
| Task | Deliverable |
| 1.1 | Inception report - Review available documentation - Reassessment of how this project fits in the overall national health sector policy of Uganda and identify important health system gaps. - Reassessment of past, current and future projects related to the project scope to avoid duplication and excess of investments - Identify and familiarize with relevant stakeholders - Update and refine the tasks, methodology and deliverables developed in the proposal submitted by selected Consultant - Update and refine the planning, coordination and management of the D2B studies developed in the proposal submitted by the selected Consultant - Reassessment of the project risks and mitigation measures as developed in the proposal submitted by the selected Consultant |
| 1.2 | - Enviromental and social screening and approach - It should be determined what the project category is in accordance with the national Ugandan ESIA requirements and the IFC PS. The Consultant should provide clear arguments for the categorization and provide a thorough understanding of the project, its location(s) etc. and an overview of the existing environmental and social setting per project location. Categorisation should be done site-specific meaning each RRH should be categorized seperately. - Based on the categorisation, it should be determined by the Consultant what the impact assessment requirements per site are (i.e. limited ESIA/project brief vs. full-scale ESIA, other). If, in case of “other”, an impact assessment is not considered necessary for a project site this should be clearly justified in the screening report whilst, as a minimum, resource efficiency and waste management should be addressed and integrated in the project plan appropriately. - NEMA, MOH and RVO will review this information to determine whether their respective environmental and social safeguards are met. In case of differences in the project impact categorisation the strictest requirements will apply. RVO will also use the information in the screening document as part of the go/no go decision of Phase I. - The Consultant should develop a general standarized research and impact evaluation methodology to determine how for all RRHs the assessment and mitigation and management of impacts will be done. This methodology should be in compliance with both Ugandan requirements and the requirements set by the IFC PS per project site and for the Project overall. This includes working with a standarized list of contents and (set of) template(s) for an effective execution and review. The impact assessment should contain general and site-specific information of which the level of detail and scope will depend to a large degree on the severity and scale of impact. The methodology and list of content will be reviewed and approved by RVO. This is not a formal part of the ESIA screenig process but a separate deliverable for RVO to ensure consistency among the various impact assessments. More information: - The Netherlands Commission for Environmental Assessment (NCEA) has made a preliminary assessment of the project and applicable regulations based on the pre-feasibility study. The complete assessment by NCEA can be found in Annex 7. - NEMA has performed a preliminary screening of the various RRHs based on the pre-feasibility study. Based on this preliminary screening it is estimated that 9 RRHs will require a project brief and 5 RRHs wil require an ESIA according to Uganda requirements. The assessment of what type of ESIA is actually needed requires verification by NEMA during Phase I. - When it comes down to preparing an offer for the tender for the D2B Studies the interested Consultants should, from a budgeting perspective, pay attention to: - the estimation based on the preliminary screening by NEMA - the differences in levels of ESIA’s to be performed vs the required effort and cost per project location and overall - the possibility that based on the actual assessment the ESIA’s required per project location might differ from the preliminary estimation as presented above. |
| SC1 | - A (digital) kick-off meeting with the SC at the start of the inception phase to discuss and clarify the definition of the D2B studies (as specified in the TOR and in the proposal of the contracted Consultant). This meeting will result in an agreement on the tasks, deliverables, planning, coordination and management of the D2B studies. - A meeting with the SC at the end of Phase 1 to discuss and get approval on the inception report and the E&S screening conclusions before the go/no go decision by RVO to move into the next phase. |
| RVO | Go/no go decision by RVO (after consultation with the SC), prior to the start of Phase 2 |

  - Phase 2: Reassessment of project definition, costs and baseline situation (update pre-feasibility study)

| Phase 2: Reassessment of project definition, costs and baseline situation (update pre-feasibility study) |  |
| --- | --- |
| Task | Deliverable |
| 2.1 | - Theory of Change (ToC) - The Consultant has to develop a Theory of Change (ToC), a comprehensive description and illustration of how and why a desired change is expected to happen in the particular context. The ToC ought to map out or fill in what has been described as the “missing middle” between what the project does (its activities or interventions) and how these lead to desired goal(s) achievement. - The ToC needs to consist of a report clearly stating, but not limited to, the following: - Description of the effects and the desired impact (the ultimate outcome) that the project will have on the local community (using economic, socio-cultural, institutional, environmental, technological and other indicators). - Description of the inputs and activities of the project. - Description of the pathways through which the project (inputs and activities) contributes to the desired results/impact (logical step approach contributing to the project objectives). - Description of the outputs and outcomes (which may include immediate and intermediate outcomes) of the project. Ideally, these pathways will be based on existing evidence/literature, and/or assumptions will be made explicit. - The ToC needs to be delivered as a visualisation including the project inputs, activities, outputs, outcomes and impact, followed by a short explanation/narrative. - Also, a brief description of the Sustainable Development Goals (SDG’s) the project contributes to has to be incorporated. - The ToC needs to be developed by the Consultant in collaboration with all relevant stakeholders to ensure political, institutional, social, environmental and financial sustainability of the project solution. - A first draft monitoring & evaluation plan and matrix. |
| 2.2 | Institutional and stakeholder analysis - Identify and describe the key authorities and stakeholders that are relevant for this project at national, regional and local level. - Assess the institutional capacity of authorities and stakeholders involved. - Assess how these institutions and stakeholders interact formally (and maybe informally). - Assess the strength and weaknesses of the identified key authorities and stakeholders. - The assessment should take the following dimensions into account: political, institutional, social, environmental, cultural and financial. - Assess the formal and actual (land) ownership of each RRH and project site. - Assess how to realize local “buy in”, acceptance and ownership of national plans owned and planned for by MOH. - Assess the parties formally responsible for the fiscal and budgetary planning from national, regional and local perspective and explain if, how and to what extent this responsibility is assumed at any of these levels, and how the timely coordination, allocation and management of sufficient operational and capital expenses budget in the right denominations will be supportive to the overall sustainability of the project solution. |
| 2.3 | - Reassessment hospital equipment and infrastructure needs - A reassessment of the up to date and actual hospital equipment and infrastructure needs of the 14 RRHs as presented in the pre-feasibility study. - Neither instruments nor patient wards and laboratories were part of the pre-feasibility study. An additional assessment is needed to determine the status of instruments, patient wards and laboratories and to what extent they affect the current problem or might become a problem in the future. Which solution should at least be part of the project scope or not, and if not inside the project scope how will MOH manage potential future problems outside of project scope? What would be the investment and operational costs of this solution and how will these costs be managed sustainably? - It should be assessed whether the current status of patient information systems are of any importance to the problem(s) for which the project is expected to provide a solution and/or to the strengthening the project solution itself. Is there any existing system, and if so, is it suitable for future purposes or not? If not, which solution should at least be part of the project scope? What would be the investment and operational costs of this solution? - The assessment should also include an analysis of peripheral power supply. What party purchases the power supply which is used by the RRHs? Who supplies the power? Who owns and manages the grid through which the power is supplied? What is the current state of power supply? Is it trustworthy and dependable allowing the current facilities to run the health care services as required? What should the power supply infrastructure look like in order to be able to run the current facilities? How does that compare to what would be needed when the project solution gets implemented per location? What part(y(ies) should take ownership of that power supply solution for the future RRHs, in order to ensure that the future project solution and health care facilities can operate without hinderance and in an environmentally sustainable and acceptable manner? What type of agreements should come about between what parties to ensure delivery of the necessary energy to each RRH? What are currently the costs of energy to the off taker, and what will the cost be in the future? How does MOH sustainably budget for these operational expenses, and what is the current budget and how is it expected to develop in the future ? - The Consultant should conduct field visits to all hospitals for this purpose. This also allows the Consultant to take into account per project location what other project initiatives have already been implemented, are currently being implemented or are expected and committed to be implemented in the near future, in order to get a clear understanding of what infrastructural needs as captured in the AMPC assessment of 2019 have already been catered for and what not, thus resulting in a customized and updated project solution. Also, this avoids overlap with other projects and/or contracts that have already been implemented, are currently implemented and/or will soon be implemented for the project locations for example supported by other International Financial Institutions (e.g. WB ICU Project) and/or other stakeholders. |
| 2.4 | Reassessment capacity building plan and human resources planning As part of the pre-feasilibility study a training and capacity building program has been developed to ensure the effectiveness and sustainability of the project. The capacity building plan should be reassessed and include: - A reassessment of the actual status and the current and future need for qualified (additional) human resources (HR) at each RRHs, and how this is included in, aligned with and supported by the strategic HR planning of the MOH. - The reassessment should identify the HR gaps at all staff levels (medical, technical, management, support) at each RRH and measures that will be taken by MOH to ensure required qualified staff will remain and become available per RRH during and on time in support of the sustainable operation of the project solution during project duration and beyond. - Reassess if there are any possibilities for synergies on capacity building and human resources planning with existing training and capacity building programs from the MOH and Ministry of Education, with or without support of other donors. - Formal and actual ownership and acceptance of the capacity building and human resources planning at national and regional level. - Establish an understanding of (donor) partners that are now and in the near future supporting the MOH with Strategic Multi-Year Human Resources Planning and Budgetting and their possible involvement already with this potential future project. - Reassess the capacity building and human resources plan and in what manner these are managed, planned for and financially secured in a sustainable manner during project duration and beyond at a national or regional level. - Determine to what extent the Capacity Building and Human Resources Plan can or cannot be considered part of the project scope. |
| 2.5 | - ESIA scoping - For the sites that require a full-scale ESIA: - Conduct an ESIA scoping per RRH according to the National Environment (Environmental and Social Assessment) Regulations, 20202 and the IFC performance standards3 and assess if there are any fundamental or insuperable environmental and/or social impacts. - Scoping is a process which determines the potentially adverse impacts that are likely to be significant and consequently should be the main focus of the ESIA. Consequently, scoping identifies data already available and existing data gaps. The scoping process determines the appropriate spatial and temporal scopes for the assessment, which alternatives to study and suggests suitable survey and research methodologies. The ESIA scoping allows to discuss the implications with all affected stakeholders (and not just the technical experts), enhancing local ownership of choices and support for the project. - The Scoping report will include at least: - The methodology to be used to undertake the ESIA study including the proposed method for evaluating identified potential impacts and proposed mitigation measures. - Review of existing information on environmental and social baseline conditions. - Specification of the various intervention alternatives and provide justification for proposed alternative. - Determine Area of Influence. The area likely to be affected either directly or indirectly by project operations, including ancillaries and associated activities. - Policy, legal, and institutional framework including a gap analysis between the host countries law and the IFC Performance Standards that are triggered and propose ways to overcome identified gaps. Determine local ESIA procedures including requirements and timeline. - Identification of the main negative and positive impacts in the various phases of the project, specific attention will be given to: - Environmental and social characteristics of the hospital areas (geography, surface, flora and fauna, nearby communities and uses). - Affordability and accessibility to health care (focus on lower income groups, women and other vulnerable groups) - Land governance and land use issues: determine whether any involuntary physical and/or economic displacement (according the definition and scope of local requirement as well as IFC Performance Standard 5 is foreseen. It should be specified whether a Resettlement Policy Framework/Resettlement Action Plan should be developed as part of the ESIA in Phase 3. - Current waste management practices and capacity and production of solid and liquid waste and smell and propose ways of managing those. - Main health & safety risks/impacts for the adjacent communities during construction phase per project site - Ways and quantities of water utilisation, location of project elements that produce clean and waste water vis-à-vis surface water - Current energy demand per RRH site, how this is provided for and by what means and what the future expected energy demand will be and what options are proposed to provide for this energy demand in a sustainable manner. - The level of effort needed to fully understand the risks, impacts and options for mitigating these. The results of the scoping process should determine what needs to be included in the environmental and social impact assessment, which could include separate studies and/or management plans including some preliminary costing of required mitigation measures; - Develop a tentative Stakeholder Engagement Plan (SEP) that shall be applicable throughout the project cycle including the planning stage and provide effective and inclusive engagement with project affected parties with a specific focus on vulnerable groups. - Carry out initial site visits, including formal and informal discussions/meetings with local communities, government agencies and other key stakeholders in the project affected area. - The result of this phase is a scoping study and a ToR for the ESIA (task 3.1) for each separate RRH. RVO will request a technical expert group from the Netherlands Commission for Environmental Assessment (NCEA) to review a draft version of the Scoping report and ToR for the ESIA. The consultant is expected to incorporate 6-8 weeks for the review of the RVO and NCEA and develop a final version of the Scoping report and ToR for the ESIA for formal approval by NEMA. The review process by NEMA is expected to take 2-3 weeks and can run parallel with the approval proces of RVO. - For the sites that require a limited ESIA (project brief): - There is no formal scoping phase required for a limited ESIA. However for RVO to have a clear idea of the progress and direction in which the work is headed as well as ensuring that relevant issues are identified timely and where possible included in the scope of the project the following items are asked of the Consultant in this phase: - Develop a template for the limited ESIA: to ensure both the requirements of RVO as well as NEMA are met, a template should be prepared that will be used for the development of all project briefs. - Provide an overview of the level of effort needed to fully understand the risks and impacts related to the project. - A detailed overview of the steps and activities taken so far per site and those that will be taken in the coming phases. This should include results of initial site visits and formal and informal discussions/meetings with local communities, government agencies and other key stakeholders in the project affected area. - Identification of the main negative and positive impacts in the various phases of the project. - Current waste management practices and capacity and production of solid and liquid waste and smell and propose ways of managing those. - Affordability and accessibility to health care (focus on lower income groups, women and other vulnerable groups). - Current energy demand per RRH site, how this is provided for and by what means and what the future expected energy demand will be and what options are proposed to provide for this energy demand in a sustainable manner. - Develop a tentative Stakeholder Engagement Plan (SEP) that shall be applicable throughout the project cycle including the planning stage and provides effective and inclusive engagement with project affected parties with a specific focus on vulnerable groups. - RVO expects this document to be reviewed within the same timeframe as the scoping reports for the ESIA (6-8 weeks). |
| 2.6 | Preliminary cost-benefit analysis Based on the pre-feasibility assessment, the total costs for strengthening the 14 RRHs have been estimated at approximately 55 million euros, for all equipment, construction, capacity building and maintenance costs. This budget will need to be revisited, studied and scrutinized based on the reassessment of the pre-feasilbity study and its potential impact on the project scope. The preliminary cost-benefit analysis will be confirmed in the detailed cost-benefit analysis (task 3.2). The preliminary financial analysis at hospital level should include: - A costing of the project investment for the entire project - A calculation of both the capital, operating cost and revenue implications for each of the RRHs during the implementation and operations & maintenance phase of the project. The costs and revenue estimates can be based on standard/benchmark figures - The financial implications for MOH to bear the costs of operation and maintenance - A calculation of relevant financial ratios - The preliminary cost-benefit analysis at aggregate project level should include: - An assessment of the commercial viability for the entire project - An assessment of the financial sustainability for the entire project - An assessment of the economic viability by calculating the economic and internal rate of return (eIRR) |
| 2.7 | Preliminary assessement continuous sustainable residual financing options for the capital and operational expenses budget and the fiscal framework The identification of sustainable modes and sources of financing and funding necessary to secure the non-grant covered capital and operational expenditures related to the project, is essential in order to look for options to safeguard project continuity. The preferred sources of financing are commercial as long as these together with a possible DRIVE contribution can be considered in compliance with the concessionality requirements applicable to Uganda. Other sources are those available at International Financial Institutions (e.g. World Bank, ADB, EIB, EU, etc.), or other interested bilateral donors, based on the results of the financial and economic analysis of the project. The preliminary assessment should include: - A review of the Medium Term Expenditure Framework - A review of the fiscal framework to understand if the project is tax exempt or not and to what extent costs can be publicly sourced - An analysis of what part of the Project operational and capital expenditure can be sustainably financed through donors/financiers (e.g. DRIVE) and possibly by the Government of Ugada /MOH. - An analysis of the sustainable financial ability of the MOH to bear the total costs for strengthening the 14 RRHs at the right moment in the right currency during implementation and operations and maintenance phases and as a result of the Project Contract and Contract for Independent Supervision. |
| 2.8 | Preliminary assessment of procurement options The Consultant will be responsible for the preparation of the procurement documentation for the Contract to deliver capital goods, works and related services (Turn Key Contract) and for the Independent Supervision contract. The MOH of Uganda will be responsible for the public procurement of the contracts. The preliminary assessment should provide an assessment of: - The procurement options for the Turn Key Contract and Independent Supervision Contract. - What project components are expected to be included in the Turn Key Contract which bidding companies will eventually be asked to bid for and what is not expected to be included and thus is required to be managed in parallel but separately by MOH Uganda . - The technical procurement capacity at the MOH, and the required technical procurement assistance provided in a timely manner through RVO throughout all the required phases of the international competivite bidding process up to the evaluation of bids, selection of winning bidder and contract negotiations and closure. - Planning of the procurement procedure for both the Independent Supervision Contract and the Turn Key Contract |
| 2.9 | Reassessment of project risks - Update of the projects risks and appropriate mitigation measures as identified in the Inception Report and ESIA Scoping Report and/or Project Brief by the Consultant. |
| 2.10 | Reassessment of project definition and baseline situation - Redefine the project definition as presented in the pre-feasibility study by using inputs from the previous deliverables. - Given the aforementioned deliverables conducted in Phase 2 a baseline study should include the Key Project Indicators (KPI’s) and their established quantified initial baseline values, knowing these should be in line with the proposal of the established Theory of Change (ref 2.1) and the DRIVE relevant M&E requirements, and should be captured in a monitoring, evaluation and reporting matrix. - Provide recommendations for the next phases of the D2B studies to ensure that DRIVE criteria are being met. |
| SC2 | A meeting with the SC at the end of Phase 2 to discuss and get approval of the deliverables before the go/no go decision by RVO to move into the next phase. |
| RVO | Go/no go decision by RVO (after consultation with the SC), prior to the start of Phase 3 |

  - Phase 3: Feasibility and detailed project plan

| Phase 3: Feasibility and detailed project plan |  |
| --- | --- |
| Task | Deliverable |
| 3.1 | Finalisation of the Environmental and Social Impact Assessment for the Project and all project locations, including the Environmental and Social Action Plan and Environmental and Social Management Plan In this phase, based on the E&S screening (see task 1.2) and depending on what was decided in Phase 1, the ESIA Terms of Reference (ToR) which were discussed, developed and accepted by NEMA and RVO (see task 2.5), the full-scale or limited ESIA will be drafted and finalised. The ESIA should be fully consistent and compliant with both the Ugandan ESIA regulations and the IFC PS. It is expected to be developed following the principles of good international industry practices as outlined in the World Bank Environmental Health and Safety Guidelines (general and sector specific). An ESIA in line with the IFC PS and the Ugandan ESIA regulations requires amongst others baseline studies, impact prediction and evaluation, proposals for mitigation. The ESIA process also requires stakeholder consultations. The environmental and social management and monitoring plan (ESMMP) together with specified sub-plans should be worked out in the ESIA. The IFC PS cover eight areas that should be addressed in the ESIA: - Assessment and management of environmental and social risks and impacts; - Labour and social conditions; - Resource efficiency and pollution prevention; - Community health, safety and security; - Biodiversity conservation and sustainable management of living natural resources; - Land acquisition and involuntary resettlement; - Indigenous people; - Cultural heritage. The ESMP should include: - Stakeholder Engagement Plan for the construction and operation phase of the project, including a Community Engagement Plan; - Emergency response and action plan - Waste Management Plan, including liquid (like wastewater) and solid discharges and discharges by air, being either hazardous and non hazardous. - Other management plans that are deemed necessary for the mitigation and management of impacts (e.g. resettlement). This will be decided based on the results of the scoping study. To ensure equal and fair treatment and to maximize positive impacts, special attention should be given to gender in all project phases (data collection, impact assessment, monitoring and evaluation, design, construction, operational and maintenance). Gender should be considered where relevant in plans and policies concerning amongst others job opportunities and enhancement (including local recruiment), training of staff, access to health care, OHS and stakeholder and community engagement. For more information on content requirements refer to Annex 8 (based on IFC PS) and the National Environment (Environmental and Social assessment) Regulations 2020 (specifically Part V), Schedule 2 and Article 6 (project brief) and Articles 12-18 (full-scale ESIA). The Netherlands Commission for Environmental Assessment (NCEA) has screened the project proposal and described which IFC PS could be triggered by this project: IFC PS 1: Assessment and management of Environmental and Social Risks and Impacts: triggered This PS applies to all projects. It requires that project proponents identify and assess environmental and social impacts, and then anticipate, avoid, minimize or compensate impacts as needed to improve their social and environmental performance. Where a project requires an ESIA according to the local requirements (which may be the case of some of the RRHs), this ESIA process can be utilized to comply with IFC PS 1. IFC PS 2: Labor and Working Conditions: triggered An approximation of the workforce that will be mobilized in project implementation needs to be made, including identification and management of any issues regarding the treatment, health and safety of workers (for instance in relation to the supply of equipment, construction material or management of project waste). In addition, occupational health and safety issues may be at stake, such as hazards affecting health care providers, cleaning and maintenance personnel, and workers involved in waste management handling, treatment, and disposal. IFC PS 3: Resource Efficiency and Pollution Prevention: triggered Because the project involves the use of resources and energy for rehabilitation and operation. In addition: during construction activities, waste will be produced (but limited). A specific point of attention is the (hazardous) hospital waste that may be produced using the new equipment. IFC PS 4: Community Health, Safety and Security: unlikely to be triggered In some RRHs safety and health risks and nuisance for different users of the area may occur, where construction of new buildings is foreseen. Also some noise, dust, safety (heavy traffic) issues may occur during the delivery of the equipment. In the operational phase no impact is expected. Moreover, the project aims to achieve a decrease in mortality rates and improvement of the health care system. IFC PS 5: Land Acquisition and Involuntary Resettlement: unlikely to be triggered The available information is insufficient to determine whether land acquisition is needed and involuntary resettlement could happen in the case of construction of new buildings/departments. Therefore, it is important to identify if any economical or physical resettlement could be required (or desirable from safety point of view). The following IFC PS are not triggered, as activities take place in an urban setting in or near to already existing RHHs: IFC PS 6: Biodiversity Conservation and Sustainable Management of Living Natural Resources: not triggered IFC PS 7: Indigenous peoples: not triggered IFC PS 8: Cultural heritage: not triggered A draft of the ESIA should first be submitted for review to both MOH and NEMA and to RVO. RVO will review the draft version of the ESIA in partnership with the NCEA. The Consultant should take into account approximately 4 weeks to allow the NCEA to conduct its review. Based on the input from both MOH and RVO/NCEA the Consultant will be asked to draft a final ESIA. That final draft ESIA upon receipt by MOH will be submitted to NEMA for final review and approval. The consultant is expected to facilitate this process and make adjustments to the final draft ESIA when required for the purposes of NEMA and RVO. NEMA will determine whether the ESIA and/or limited ESIA (project brief) is in full accordance with the Ugandan ESIA procedures. Furthermore, NEMA will be enabled to determine whether it will be possible to provide a (conditional) environmental approval for the project overall and per identified project site specific and what ESIA procedural steps are (still) required and expected to be followed to reach that stage. Approval by the NEMA will take up to 30 days for a project brief. For ESIA the approval period is maximum six months depending on the quality of the document, complexity of the project and the need for organizing and holding public hearings. A separate deliverable is a summary document to be developed for RVO highlighting the overall results of all of the performed impact assessments done as part of the assignment including the general and site-specific characteristics, profile, impacts and management thereof. |
| 3.2 | - Detailed cost-benefit analysis - Update and refining of the preliminary cost-benefit analysis (deliverable 2.6) based on additional information acquired in the feasibility phase including the ESIA. |
| 3.3 | - Continuous secured and sustainable residual financing options for the capital and operational expenses budget Update and refining of the preliminary assessment of continuous secured and sustainable residual financing options (deliverable 2.7) based on additional information acquired in the feasibility phase including the ESIA. |
| 3.4. | Detailed medical and non-medical equipment specifications - An overview of all medical and non-medical equipment required for each RRHs based on the updated needs assessment and available budget |
| 3.5 | Detailed technical specifications for power infrastructure - An overview of all technical specifications for the power infrastructure at each RRH, including: - Hydro-sanitary system - Electrical installations - Special systems - Air conditioning and mechanical ventilation - Medical gas or steam network - Technical specifications |
| 3.6 | Detailed organisational plan The organisational plan is of vital importance for the implementation of the project. The Consultant will have to elaborate in this document on: - A project management and supervision plan - A stakeholder engagement plan (if captured in the ESIA please reference to it) - A monitoring and evaluation plan and matrix (KPI’s, SDGs, Climate Markers, etc) - Recommendation for the operations & maintenance phase after the end of the project (tenor) to ensure long term sustainability |
| 3.7 | - Detailed capacity building plan and human resources plan - A detailed elaboration of the reassessed capacity building and human resources plan (deliverable 2.4) including additional information from the feasibility studies. |
| 3.8 | Detailed operations and maintenance plan - An inventory of the requirements for the organisation, personnel, equipment, infrastructure, maintenance and reinvestments during and after the end of the project - Recommendations regarding maintenance clauses that should be included in contracts with equipment suppliers, taking into consideration the potential stimulation of private sector development in a sustainable, viable and safe manner for health services. |
| 3.9 | Detailed procurement plan Update of the preliminary assessment of procurement options (deliverable 2.8), which should specify for the Contract for the delivery of capital goods, works and related services and the Independent Supervision Contract: - The procurement method (open competitive bidding procedure, restricted bidding procedure) - The type of contract for the delivery of capital goods, works and related services (specified according to FIDIC or equivalent standards) - The applicable national and international procurement requirements - The planning of a tender procedure for the required technical procurement assistance contract prior to the start of procurement procedure preparations for the independent supervision contract and the contract for the delivery of capital goods, works and related services. - For the Timing of the tender for each contract it is required to secure the timely involvement of a contracted independent supervisor. That means that the procurement procedure for the independent supervisor contract should be finalized prior to the start or finalization of the procurement procedure for the contract for the delivery of capital goods, works and related services, as this will ensure that the independent supervisor can deliver in a timely manner on the tasks set in his contract. |
| 3.10 | Detailed continuous sustainable residual financing plan - Update of the continuous sustainable residual financing options (deliverable 3.3) presenting the most viable and sustainable option for financing the non-grant covered part of the project in order to safeguard continuity. |
| SC3 | - A meeting with the SC at the end of Phase 3 to discuss and get approval of the deliverables |
| RVO | - Go/no go decision by RVO (after consultation with the SC), prior to the start of Phase 4 |

  - Phase 4: DRIVE Intake Form

| Phase 4: DRIVE Intake Form |  |
| --- | --- |
| Task | Deliverable |
| 4.1 | DRIVE Intake Form The Consultant will be required to prepare in full the DRIVE Intake Forms and provide all necessary annexes including first draft procurement documents for the Contract for the delivery of capital goods, works and related services and Independent Supervision Contract, which the MOH of Uganda is expected to submit to RVO for a formal Intake assessment by the Assessment Committee DRIVE. |
| SC4 | A meeting with the SC at the end of Phase 5 to discuss and get approval of the deliverables |
| RVO | Go/no go decision by RVO (Assessment Committee DRIVE) based on the submitted DRIVE Intake Form with all required addenda prior to the start of Phase 5 |

  - Phase 5: Preparation of procurement documents

| Phase 5: Preparation of procurement documents |  |
| --- | --- |
| Task | Deliverable |
| 5.1 | Tender documents for Independent Supervision Contract The tender documents for the Independent Supervision should: - Be developed in collaboration with the Project Management Unit. - Be drawn up in accordance with the detailed procurement plan (see deliverable 3.9) - Ensure compatibility with all applicable (inter)national standards and regulations including IFC PS and World Bank’s EHS Guidelines - At least include (non-exhaustive list): - Tendering processs: - Instruction to tenderers - Qualification and evaluation criteria - Procurement forms - Requirements: - Terms of Reference specifying the scope of the services requested - Technical specifications - Contractual conditions and contract form - All other relevant information, such as a list of all studies carried out up to the date of publication. |
| 5.2 | Tender documents for the Contract for the delivery of capital goods, works and related services The tender documents for Contract for the delivery of capital goods, works and related service (Turn Key Contract) should: - Be developed in collaboration with the Project Management Unit. - Drawn up in accordance with the detailed procurement plan (see deliverable 3.9) - Ensure compatibility with all applicable (inter)national standards and regulations including IFC PS and World Bank’s EHS Guidelines - At least include (non-exhaustive list): - Tendering processs: - Instruction to tenderers - Qualification and evaluation criteria - Procurement forms - Requirements: - Terms of Reference specifying the scope of the project solution requested - Technical specifications - Contractual conditions and contract form - All other relevant information, such as a list of all studies carried out up to the date of publication. |
| SC5 | A meeting with the SC at the end of Phase 5 to discuss and get approval of the deliverables |
| RVO | Go/no go decision by RVO prior to signing of the DRIVE Grant Arrangement |

- PROJECT BUDGET

In its capacity as Tendering Authority, RVO has estimated a total contract value of EUR. 650,000 (excl. VAT) for the project. From this estimation no rights can be derived.

- PROJECT DURATION

The total duration for the execution by the selected Consultant of the D2B studies is estimated at 12 months and this is presented in the third column in the table below. This does not include per phase the estimated time needed by RVO to come to a Go/No Go decision, which obviously is required for the D2B studies to move into the next phase. The time needed by RVO per Go/No Go decision is indicated in the fourth column.

| Phase | Estimated start date per Phase (1st of the month) | Estimated time per Phase (Consultant) | Estimated time per Phase to reach Go/No Go (RVO) |
| --- | --- | --- | --- |
| Phase 1: Inception | October 2021 | 1 month |  |
| Go/no go decision RVO | November 2021 |  | 1 month |
| Phase 2: Reassessment of project definition and baseline situation (update pre-feasibility study) | December 2021 | 3 months |  |
| Go/no go decision RVO | March 2022 |  | 1 month |
| Phase 3: Feasibilty and detailed project plan | April 2022 | 5 months |  |
| Go/no go decision RVO | September 2022 |  | 2 months |
| Phase 4: Drive Intake Form | November 2022 | 1 month |  |
| Go/no go decision RVO | December 2022 |  | 2 months |
| Phase 5: Procurement documents | February2023 | 2 months |  |
| Go/no go decision RVO | April 2023 |  | 1 month |
| Total duration D2B studies (estimation) | 19 months | 12 months | 7 months |

Each bidding Consultant is requested to include a detailed time planning in the proposal taking into account the consultants estimated required time per phase and the estimated time needed by RVO towards a go/no go decision at the end of each phase.

- PROJECT ORGANIZATION AND STRUCTURE

The Ministry of Health (MOH) will play an active role during the definition and the execution of the project, with an overall goal of reducing mortality rates in general and more specifically mother and child morbidity and mortality rates. The project will be jointly developed by MOH and RVO. MOH will set up a Project Steering Committee and a Project Management Unit.

  - Project Steering Committee

The Project Steering Committee will be responsible for taking important project-related decisions, supervising the overall implementation of the project and ensuring timely delivery of the project. The Project Steering Committee consists of the following members:

- Dr Diana Kanzira Atwine, Permanent Secretary of the Ministry of Health

- Eng George Otim, Commisioner Health Services – Health infrastructure Division

- Dr Henry Mwebesa, Director Planning

- Ms Doreen Kakyo, MOH Project Manager for the DRIVE Project

- Representatives from the Regional Referral Hospitals

- Chairperson NACME (National Advisory Committee on Medical Equipment)

- Representative from MOFPED (Ministry of Finance Planning and Economic Development)

- Representative from NEMA (National Environmental Management Authority)

  - Project Management Unit

The Project Management Unit is responsible for the day to day project management and coordination of the project, including monitoring the progress, liaising with stakeholders, assessing the project deliverables and providing input and feedback to RVO. The Project Management Unit reports to the Project Steering Committee. The Project Management Unit consists of the following members:

- Ms Doreen Kakyo Mpuuga, MOH Project Manager

- Mr Owen Tumuhimbise, Biomedical Engineer

- Mr Jacob Nsubuga, Civil Engineer

- Ms Beatrice Nalubega, Electrical Engineer

  - Roles and responsibilities project stakeholders

| Organisation | Roles and responsibilities |
| --- | --- |
| Netherlands Enterprise Agency (RVO), Develop2Build (D2B) | - Draft and sign the Terms of Reference for the D2B studies - Draft and sign the D2B Grant Arrangement - Organize an ICB tender for the consultancy assignment - Inform MOH about the award decision - Sign the contract with the Consultant - Share the D2B studies with MOH - Jointly review the D2B studies with MOH - Accept the D2B studies in consultation with MOH - Decide on important project-related issues (See also Project Steering Committee) - Take a Go / No Go decision before the D2B studies can move into the next phase - Receive finalized DRIVE Intake from MOH with all annexes - Pay the Consultant directly upon acceptance of payment request by RVO as a result per phase of each Go/No Go decision |
| Ministry of Health (MOH) | - Provide feedback, approve and sign the Terms of Reference - Provide feedback, approve and sign the D2B Grant Arrangement - Constitute a Project Steering Committee and Project Management Unit - Actively engage in looking for co-financing opportunities for the implementation and operations phases - Review the D2B studies and deliverables and provide feedback to RVO - Submit the DRIVE Intake with all annexes supported by the Consultant - Responsible for coordination between local stakeholders - Ensuring the project's inclusion in the national monitoring and evaluation programme - Support planning and monitoring activities in close collaboration with the Consultant and RVO's D2B team |
| Ministry of Finance Planning and Economic Development (MOFPED) | - Participate in the Project Steering Committee - Formal communication in representation of the Government - Actively engage in looking for co-financing opportunities for the implementation and operations phase |
| Project Steering Committee | - Decide on important project-related issues (See also RVO) - Supervise overall project implementation - Ensure timely delivery of the project - Presents the D2B studies, tasks and deliverables per Phase for a Go / No Go decision to RVO |
| Project Management Unit | - Responsible for coordination amongst local stakeholders - Review the draft studies and deliverables |
| Contractor (Consultant of the studies) | - Conduct the D2B studies according to the TOR - Submit the D2B studies for review and acceptance to RVO - Submit invoices and payment requests to RVO |
| National Environmental Management Auhtority (NEMA) in Uganda | - Review the E(S)IA project brief in consultation with the relevant lead agencies - Review the E(S)IA Scoping - Review the E(S)IA Terms of Reference - Review the full-fledged final ESIA in consultation with relevant lead agencies - Issues the necessary environmental certification for the project |
| Netherlands Commission for Environmental Assessment (NCEA) | - Reviews the scoping report - Reviews the ESIA Terms of Reference to ensure that the ESIA process is in line with Ugandan ESIA regulations - Reviews the ESIA Terms of Reference to ensure that the ESIA is in line with the IFC Performance Standards/WB EHS Guidelines - Reviews the ESIA |
| Representative from the National Advisory Committee on Medical Equipment (NACME) | - NACME is the MOH medical equipment regulatory body. It is included to ensure the medical equipment scoped is compliant with national requirements and needs. - Participate in the Project Steering Committee |
| Representatives of the RRHs | - Participate in the Project Steering Committee |
| Any other identified party that can improve the impact of the project | - To be identified/investigated by the Consultant in the Inception Phase (e.g. strategic HR support) |

- CONSULTANT TEAM PROFILE

  - Qualification requirements firms

The Consultant should include a mix of international and local experts. Participation in tendering is open on equal terms to consultancy firms, either individually or in association (with other consultancy firms, experts or NGO’s). It should be clearly indicated which organisation is the lead applicant/service provider and ultimately responsible for task delivery, (financial) reporting, invoicing etc..

Firms will be qualified based on the following criteria:

  - Qualification requirements staffing

The Consultant consists of a team of (senior) experts, led by an experienced Team Leader who is considered to be a senior expert him/herself. The Team Leader is part of and manages and leads a core team that further consists of senior experts. This core team should at least consist of and will each be evaluated on the following criteria:

| Required profile | Evaluation criteria |
| --- | --- |
| Team leader | - A university degree in public health, or equivalent. - At least 8 years of experience in carrying out feasibility studies for the development and management of health infrastructures. - Proven experience of at least 8 years in project management in sub-Saharan Africa, preferably in Uganda or Eastern Africa. - Proven experience of at least 8 years in project management with Government stakeholders and donor agencies. - Proven experience of at least 8 years in project management with multidisciplinary team. - Proven track record of at least 8 years with and access to International Financial Institutions, Commercial Banks and Export Credit. - At least 7 years of experience in developing and implementing monitoring and evaluation plans and matrices for Government and donor agency supported projects. - Proficiency in spoken and written English. |
| Economic and financial expert | - A university degree in business administration, (health) economics, or equivalent. - At least 7 years of experience in financial modelling (cash flow modelling) and cost-benefit analysis. - Proven experience in health infrastructure projects in sub-Saharan Africa, preferably in Uganda or Eastern Africa. - Proven track record of at least 7 years with and access to International Financial Institutions, Commercial Banks and Export Credit Agencies - Proficiency in spoken and written English. |
| Medical equipment, after sales and maintenance expert | - A university degree in civil or biomedical engineering. - At least 8 years of experience developing and implementing medical equipment projects in Sub-Saharan Africa, preferably Uganda or Eastern Africa. - Proficiency in spoken and written English. |
| Environmental and social impact assessment expert | - A university degree in environmental engineering or equivalent. - At least 7 years of proven experience in managing and conducting ESIA and ESM(M)P in accordance with the IFC PS or equivalent in developing countries. - At least 7 years of experience with Government and donor agency supported public infrastructure development projects. - Proven experience in conducting ESIA and ESM(M)P in Uganda and/or other Eastern Africa countries. - At least 7 years of experience in developing and implementing monitoring and evaluation plans and matrices for Government and donor agency supported projects. - Expert, Ugandan and/or foreign, should be registered with and certified by NEMA as an Environmental Practitioner. Foreign experts neither registered nor certified can participate as a member of a team led by a proven registered and certified expert. - Proficiency in spoken and written English. |
| Procurement Specialist | - A university degree in economics, business administration or equivalent. - At least 8 years of experience in preparing tender documents under the standard contract conditions of FIDIC, the World Bank, or equivalent. - Able to take into account Uganda’s national regulations for public procurement. - Proficiency in spoken and written English. |
| Human resources for health expert | - A university degree in public health or equivalent. - At least 7 years of experience in human resources planning and management. - Experience in supporting policy makers in Sub-Saharan Africa, preferable Uganda or Eastern Africa. - Proven experience of at least 7 years with Government stakeholders and donor agencies. - Proficiency in spoken and written English. |

The core team will be complemented by additional experts.

| Required profile | Evaluation criteria |
| --- | --- |
| Civil engineer | - A university degree in civil engineering - At least 7 years experience in hospital infrastructure, design studies and cost estimation - Proven experience in projects in sub-Saharan Africa - Proficiency in spoken and written English |
| Electrical engineer | - A university degree in electrical engineering - At least 7 years experience with the design and maintenance of hospital electronic networks in the Sub-Saharan Africa according to national requirements - Proficiency in spoken and written English |
| Heating, ventilation and air conditioning engineer | - A university degree in electrical engineering - At least 7 years experience in designing hospital HVAC systems in Sub-Saharan Africa according to national requirements - Proficiency in spoken and written English |
| WASH expert | - A university degree in civil engineering - At least 7 years experience with water, sanitation, hygiene, health care waste management and cleaning in health facilities - Proficiency in spoken and written English |

The evaluation of the capacity and experience of the proposed core and additional experts will be based on the review of their CVs. CVs should specify in particular their experience in similar assignments over a minimum of 7 years, including the following information:

- Contracting Authority/client for the assignment

- Project area/country

- Duration (from month/year to month/year)

- Number of expert-months for the assigment

- Contract value

- Main activities

- Objectives of the assignment

Please use the format indicated in Annex 8 to present this information. It should be noted that a person may be appointed for more than one position as an expert, if he or she meets all the required qualifications and experience and can provide the services within the time frame.

It should also be noted that a (relatively) compact and well-balanced team with the required qualifications and experience could be evaluated positively in terms of the efficient use of project resources.

The combination of international and local consultants in the team is encouraged, in order to better take into account the local context and the legislation and regulations in force in Uganda and avoid if possible difficulties due to international travel restrictions. In addition to the experts mentioned above, the Consultant must provide adequate full-time or part-time qualified and experienced support staff to meet the requirements of this assignment. The CVs of these support staff should not be included in the offer. The costs for such support staff shall be included in the offer submitted.

In Uganda there is an accreditation system. This system requires minimum standards and criteria for qualification of practitioners working in Uganda on Environmental Impact Assessments (EIA), Environmental Audits (EA) and/or the coordination around conducting an EIA and/or EA respectively. Local practitioners should be registered and certified with NEMA. Foreign practitioners can apply for certification on assignment-basis. They should:

- Show evidence of a valid certification and/or accreditation and proof of competent qualifications

to practice obtained outside of Uganda

- Show that he or she has gained relevant experience of not less than five years in conducting

environmental impact studies and/or audits in the relevant area or areas of competence

- Include at least one Environmental Practitioner registered in Uganda on his or her team

- Provide at least two abstracts of previous environmental impact studies or environmental audits

conducted in the last three years

- Provide a curriculum vitae and at least three referees

- Pay the fee for certification of a Foreign Environmental Practitioner (800,000 UGX)

The approval timelines for the registration and certification of foreign practitioners may provide challenges for practitioners not yet registered and certified by NEMA. Unregistered practitioners can still participate as a contributing expert in the execution of the E(S)IA but only as part of a team of experts led by a registered consultants. It is not necessary to be a certified or registered Environmental Practitioner in the case of preparation or submission of a project brief to the Authority or to a lead agency. More information can be found here:

- National Environment Regulations (Conduct and Certification of Environmental Practitioners),

2003: http://extwprlegs1.fao.org/docs/pdf/uga40873.pdf

- List of registered and certified environmental practitioners in Uganda (2019):

https://nema.go.ug/sites/all/themes/nema/docs/List%20of%20Environmental%20Practitioners%20-Final-pdf.pdf

Annexes

| Annex 1 | AMPC assessment v2.0 ¦ August 2019 |
| --- | --- |
| Annex 2 | Site Visit Report |
| Annex 3 | Equipment List per Hospital |
| Annex 4 | Capacity Building Plan |
| Annex 5 | Power Infrastructure Requirements |
| Annex 6 | DRIVE Intake Form |
| Annex 7 | Screening RVO D2B on E(S)IA requirements & IFC PS |
| Annex 8 | ESIA requirements |

Let’s get in touch. Together we build the sustainable markets of tomorrow.

Invest International

Malietoren | Bezuidenhoutseweg 12

2594 AV The Hague

The Netherlands

procurement@investinternational.nl

+31(0)631675906

investinternational.nl