Soil Investigations Wind Farm Zones

Annex 6 - Section IIIa Remuneration

Geotechnical Survey – Lot 1

Nederwiek Wind Farm Zone

Colophon

| Project name | Geotechnical Survey Nederwiek Wind Farm |
| --- | --- |
| Project number | WOZ2230070/WOZ2230071 |
| Version | Final |
| File name | NWN_20230324_GT_Annex 6 Section IIIa Remuneration_F01.docx |
| Project manager | M. Vrolijk |
| Annex(es) |  |
| Author | M. Vrolijk |
| Reviewed | U. Gerdes |
| Approved | P. Lebbink |

Contents

1	Introduction	4

2	Rates, prices and percentages	5

3	Payment Schedule	8

4	Pricing Schedule	9

5	Bonus and Malus	11

# Introduction

## Remuneration document

This document details the CONTRACT PRICE as part of the CONTRACT that CLIENT has awarded to CONTRACTOR for carrying out the Geotechnical soil investigations at the Nederwiek Wind Farm Zone for LOT 1 of the contract.

Also, this document contains sections on the payment schedule as well as bonus and mala mechanisms.

# Rates, prices and percentages

## Currency

The rates and prices set out in the PRICING SCHEDULE in this Annex [6] - Section IIIa (Remuneration) are in Euros (€).

## Taxes (VAT)

The rates and prices contained herein exclude Value Added Tax that shall be charged in accordance with prevailing legislation.

## Applicable rate with regard to large/ small fluctuating quantities

The rates and prices contained herein shall apply equally to executing the WORK in large, small or fluctuating quantities.

## Applicable equally to measured work

Rates, prices and percentages shall apply equally to any measured WORK and/or VARIATION regardless of ease, difficulty, location, quantity or whether it is an addition or a reduction to the WORK.

## Variations

Should the CLIENT exercise their entitlement to vary the WORK, then the amended WORK shall be valued by the CLIENT at the rates and prices contained herein insofar as it is fair and reasonable to do so or, where appropriate on a pro-rata basis and adjust the CONTRACT PRICE accordingly.

## Contract Price

The CONTRACT PRICE set out herein shall be the total remuneration payable to the CONTRACTOR for the WORK set out in the CONTRACT and shall take full account of the liabilities and obligations of the CONTRACTOR under this CONTRACT.

## Scope of work

The Scope of WORK set out in this Annex [6] - Section IIIa relates to the scope of work as detailed in Annex [6] - Section IV Scope of Work of this CONTRACT.

## Rates and prices not foreseen

When CLIENT is extending the Scope of Work and these services are not foreseen in Annex [6] - Section IV – Scope of Work, the CLIENT and the CONTRACTOR shall agree, acting reasonably, additional rates and prices as required, taking full account of rates and prices for similar work and prevailing market conditions.

All new rates, prices and percentages when approved by the CLIENT shall remain valid for the duration of the CONTRACT.

## Rates to include all CONTRACTOR’s costs

All rates and prices set out in Annex [4a] Cycle times and Prices for LOT 1 herein are inclusive of all the CONTRACTOR’s costs of whatever nature, unless otherwise agreed, associated with performing the WORK in accordance with the CONTRACT and shall include but not be limited to expenses, management time, overheads, labour (including but not limited to the cost of all productive and non-productive labour), supervision, direct remuneration and payroll related costs (including but not limited to salaries, National Insurance contributions or equivalent in the country of levy, payroll taxes, welfare funds, sick pay, bonus and incentive payments, statutory and annual holidays, health plans and the like), plant & equipment (including but not limited to maintenance and repair), goods, materials and consumables, delivery and collection charges, customs dues.

## Fixed rates and prices

The rates and prices contained herein shall be fixed for the entire period of the CONTRACT including any extensions of time to the CONTRACT term by way of VARIATION.

## Rates to include all other costs

Rates, prices and percentages shall include but not be limited to:

- all equipment, materials, consumables to conduct the WORK;

- daily and/or shift change transfer of personnel, including the CLIENT OFFSHORE REPRESENTATIVE(S) and including lost time to the schedule of or during personnel transfer activities due to delays however caused;

- accommodation, subsistence and meals onboard the vessel for the CONTRACTOR personnel and CLIENT OFFSHORE REPRESENTATIVE(S);

- port, harbour dues and pilotage;

- loading and unloading of the marine vessel(s);

- communication and transmission charges;

- redundancy of consumables, materials and equipment, as appropriate, to avoid non-productive time;

- data processing;

- port calls for equipment and crew change out;

- transfer vessel for moving crews between the land and the marine vessel(s)

## Operational regime

All day rates are based on twenty four (24) hours per day. In the event that only part of a day is worked the day rates shall be reduced pro rata.

## Professional attendance

Professional attendance associated with the supervision and technical direction of the fieldwork and other duties as required by the CONTRACT shall be included in the appropriate rates.

## Payment for PCPTs, SCPTs, Thermal Conductivity Tests and Vibrocores,

Payment for completed PCPTs, SCPTs, thermal conductivity tests and vibrocores, shall be based on:

- Full thickness of strata investigated and interpreted in accordance with the Specification;

Depths measured from seabed level.

## Payment for Dissipation Tests

Payment for dissipation tests shall be based on:

- Selected intervals of strata investigated and interpreted in accordance with the Specification; the number of tests will be limited by total time allowance.

## Payment for laboratory tests

Payment for onshore and offshore standard laboratory testing on Vibrocore samples, including laboratory thermal conductivity testing shall be based on acceptance of the test results by the CLIENT or the CLIENT OFFSHORE REPRESENTATIVE.

## Rates for testing shall include for:

- The supply of a copy of the preliminary test results to the CLIENT OFFSHORE REPRESENTATIVE or the CLIENT REPRESENTATIVE as required by the CLIENT;

- The cost of moisture content or density determinations where they form part of the test;

- The cost of supplying example excel files showing the method of calculation for each test.

# Payment Schedule

Payment shall be based on the pro-rata amount of completed Works up to a maximum of 90% of the total CONTRACT PRICE at time of the CONTRACT signature.

CONTRACTOR is eligible for payment of the remaining 9,8% of the CONTRACT PRICE, after completion and approval of both the CLIENT and certifying body of all final reports. For an overview of the final reports please refer to Annex [4a] – Cycle Times and Prices.

A retainer of 0,2% of the total CONTRACT PRICE, excluding the price of potential variation orders, is in place and will be paid after finalisation of the webinar(s).

Applications for payment shall be at monthly intervals with the exception of the milestone mobilisation of vessel(s), equipment and personnel.

CONTRACTOR can apply for payment of the vessel (and equipment) mobilisation after the CLIENT OFFSHORE REPRESENTATIVE has signed the mobilisation certificate, the vessel has transited to the Investigation Area and the first issue of the mobilisation report has been provided to the (onshore) CLIENT.

CONTRACTOR can apply for payment of the laboratory test results after the Client has been provided with the possibility to check and verify lab results.

# Pricing Schedule

The WORK as set out in the CONTRACT shall be undertaken for a lump sum total CONTRACT PRICE of [●]. The CONTRACT PRICE [●] includes/excludes WAITING ON WEATHER and excludes any additional authorised work chargeable at the rates set out in the Schedule of Rates contained within paragraph 4.3 .

## Limitations of proposed equipment

| Descriptions | WORKABLE WEATHER LIMITS |  |  |
| --- | --- | --- | --- |
|  | Wave height (Hs) | Wind speed (m/s) (Ws_10) | Required Window (Ww) |
| Vessel 1: Part A |  |  |  |
| Working at site | [●]m | [●]m/s | [●]hrs |
| Vessel 2: Part B |  |  |  |
| Working at site | [●]m | [●]m/s | [●]hrs |

Table 1		Maximum allowable weather conditions for carrying out the geotechnical survey works.

- Hs means the significant wave height in meters.

- Ws_10 means 10-minute mean wind speed 10 m above Mean Sea Level.

- Ww means minimum time in hours for an operation i.e. weather window required to start and execute the operation.

## Waiting on Weather

[The options which are not selected will be deleted]

Option 1: Lump sum including weather

CONTRACTOR has allowed for WAITING ON WEATHER as per Table 2. In case of VARIATIONS to the specified amounts (more or less seabed tests) the CONTRACT PRICE shall be adapted on the basis of the rates as specified in the PRICING SCHEDULE and the WAITING ON WEATHER allowance shall be adapted on a pro rata basis.

CONTRACTOR shall in no case be entitled to any additional compensation or reimbursement on the basis of WAITING ON WEATHER other than the WAITING ON WEATHER ALLOWANCE and possible VARIATIONS.

The WEATHER DOWNTIME ALLOWANCE DAYS as specified in Table 2 shall be used for the determination of EXCEPTIONAL WEATHER DELAY as basis for adjustment of KEY DATES as determined by Annex [6] – Section VI (Quality requirements & Administrative instructions).

| Activity | Allowance |  |
| --- | --- | --- |
| Vessel 1: Part A (activities to be copied from Annex [4a]) | €[●] | [●] days |
| Vessel 2: Part B (activities to be copied from Annex [4a]) | €[●] | [●] days |

Table 2		Allowance in euros and days for WAITING ON WEATHER during the geotechnical survey.

Option 2: Lump sum excluding weather

CONTRACTOR has not allowed for any compensation for WAITING ON WEATHER. The CONTRACT PRICE shall be adjusted by way of VARIATION for WAITING ON WEATHER and such adjustment shall be on a pro-rata basis measured to the nearest minute based upon the standby rate set out in this document.

Option 3: Lump sum including risk sharing mechanism

CONTRACTOR has allowed for a compensation of WAITING ON WEATHER days as per Table 3. In case the actual amount of WAITING ON WEATHER days deviates from the estimated amount of WAITING ON WEATHER days, the CONTRACT PRICE shall be adjusted by multiplying the difference between the estimated WAITING ON WEATHER days and the actual WAITING ON WEATHER days by 50% of the standby rate set out in this document.

| Activity | Allowance |
| --- | --- |
| Vessel 1: Part A (activities to be copied from Annex [4a]) | [●] days |
| Vessel 2: Part B (activities to be copied from Annex [4a]) | [●] days |

Table 3		Allowance for WAITING ON WEATHER during the geotechnical survey.

## Rates and prices

The elements of the CONTRACT PRICE together with rates and prices for all known variations to the WORK are presented in Annex [4a] for LOT 1.

# Bonus and Malus

The Contracting Authority has included a bonus and malus performance system as an incentive for an early offshore completion and timely issuing of data and reports milestones. The bonus malus performance system in this document applies to Lot 1.

## Bonus and Malus milestones

The CLIENT stipulates 3 key milestones which are used in the Bonus and Mala mechanism:

- [1] DELIVERY OF 100% OF CPT DRAFT DIGITAL DATA (see Annex [4a] Cycle times and Prices).

- [2] DELIVERY AND CLIENT ACCEPTANCE OF FINAL SEABED IN SITU TESTING REPORT, (incl. WOW) (see Annex [4a] Cycle times and Prices).

- [3] DELIVERY AND CLIENT ACCEPTANCE OF FINAL SEABED SAMPLING REPORT including lab testing, (incl. WOW) (see Annex [4a] Cycle times and Prices).

The CLIENT has set a desired date and ultimate dates for the milestones [1], [2] and [3] in Annex 4a Cycle times and Prices.

Completion of a milestone before or on the desired date will help CLIENT to meet the project schedule. Meeting the desired date or close to this date will be awarded with a bonus as described in section 5.2.

Completion of any Key Date as mentioned in Annex [4a] (shown in bold, underscored and green), later than the ultimate date will interfere with other commitments of the CLIENT and/or will cause delay to the schedule. Not completing the WORKS or delivery of documentation prior or onto the ultimate date will cause the CLIENT to charge mala to the CONTRACTOR as described in section 5.3.

The CONTRACTOR has issued Annex [4a] (Cycle times and Prices) of the tender documentation with proposed dates for the milestones [1], [2] and [3]. The dates provided by CONTRACTOR will be used by CLIENT to make agreements with other parties, therefore mala will be charged to the CONTRACTOR when completion of the milestone is exceeding the dates as described in section 5.3.

## Bonus

If the Contractor succeeds to complete milestones [1], [2] and/or [3] as described in section 5.1 on or before the DESIRED DATE set by CLIENT, taking into account all requirements of (Annex [6] Section IV Scope of Work and Annex [6] Section VI Quality Requirements and Administrative Instructions), and are approved by the CLIENT, then the CONTRACTOR is awarded a bonus of up to 1,5% the Contract Value.

The CLIENT has set desired and ultimate dates for [1], [2] and [3] in Annex [4a] Cycle Times and Prices. Bonus can be achieved by CONTRACTOR by meeting the DESIRED DATE. If the delivery is later than the CLIENT’s desired date the reduction per day is -0.025% of the CONTRACT PRICE per day until 0% bonus is reached. Table 5 present the bonus that can be achieved by completion and/or delivery.

Table 4: Maximum bonus per key milestone [1] [2] and [3]

| Bonus |  |
| --- | --- |
| 1. DELIVERY OF 100% OF CPT DRAFT DIGITAL DATA (incl. WOW) | 0.5% of CONTRACT PRICE |
| 2. DELIVERY AND CLIENT ACCEPTANCE OF FINAL SEABED IN SITU TESTING REPORT (incl. WOW) | 0.5% of CONTRACT PRICE |
| 3. DELIVERY AND CLIENT ACCEPTANCE OF FINAL SEABED SAMPLING REPORT including lab testing, (incl. WOW) | 0.5% of CONTRACT PRICE |

Table 5: Table of maximum bonus for delivery later than the desired date by the Client in Annex [4a] of [1], [2] and [3]

| 1. DELIVERY OF 100% OF CPT DRAFT DIGITAL DATA (incl. WOW) |  | 2. DELIVERY AND CLIENT ACCEPTANCE OF FINAL SEABED IN SITU TESTING REPORT (incl. WOW) |  | 3. DELIVERY AND CLIENT ACCEPTANCE OF FINAL SEABED SAMPLING REPORT including lab testing, (incl. WOW) |  |
| --- | --- | --- | --- | --- | --- |
| Bonus (% of CONTRACT PRICE) | Delivery date | Bonus (% of CONTRACT PRICE) | Delivery date | Bonus (% of CONTRACT PRICE) | Delivery date |
| 0.50% | Before/on 01-04-2024 (Desired date) | 0.50% | Before/on 22-06-2024 (Desired date) | 0.50% | Before/on 22-09-2024 (Desired date) |
| 0.475% | 02-04-2024 (+ 1 calendar day) | 0.475% | 23-06-2024 (+ 1 calendar day) | 0.475% | 23-09-2024(+ 1 calendar day) |
| 0.45% | 03-04-2024 (+ 2 calendar days) | 0.45% | 24-06-2024 (+ 2 calendar days) | 0.45% | 24-09-2024 (+ 2 calendar days) |
| 0.425% | 04-04-2024 (etc.) | 0.425% | 25-06-2024 (etc.) | 0.425% | 25-09-2024 (etc.) |
| 0.40% | 05-04-2024 | 0.40% | 26-06-2024 | 0.40% | 26-09-2024 |
| 0.375% | 06-04-2024 | 0.375% | 27-06-2024 | 0.375% | 27-09-2024 |
| 0.35% | 07-04-2024 | 0.35% | 28-06-2024 | 0.35% | 28-09-2024 |
| 0.325% | 08-04-2024 | 0.325% | 29-06-2024 | 0.325% | 29-09-2024 |
| 0.30% | 09-04-2024 | 0.30% | 30-06-2024 | 0.30% | 30-09-2024 |
| 0.275% | 10-04-2024 | 0.275% | 01-07-2024 | 0.275% | 10-10-2024 |
| 0.25% | 11-04-2024 | 0.25% | 02-07-2024 | 0.25% | 02-10-2024 |
| 0.225% | 12-04-2024 | 0.225% | 03-07-2024 | 0.225% | 03-10-2024 |
| 0.20% | 13-04-2024 | 0.20% | 04-07-2024 | 0.20% | 04-10-2024 |
| 0.175% | 14-04-2024 | 0.175% | 05-07-2024 | 0.175% | 05-10-2024 |
| 0.15% | 15-04-2024 | 0.15% | 06-07-2024 | 0.15% | 06-10-2024 |
| 0.125% | 16-04-2024 | 0.125% | 07-07-2024 | 0.125% | 07-10-2024 |
| 0.10% | 17-04-2024 | 0.10% | 08-07-2024 | 0.10% | 08-10-2024 |
| 0.075% | 18-04-2024 | 0.075% | 09-07-2024 | 0.075% | 09-10-2024 |
| 0.05% | 19-04-2024 | 0.05% | 10-07-2024 | 0.05% | 10-10-2024 |
| 0.025% | 20-04-2024 | 0.025% | 11-07-2024 | 0.025% | 11-10-2024 |
| 0.00% | 21-04-2024 or later | 0.00% | 12-07-2024 or later | 0.00% | 12-10-2024 or later |

## Mala

Two types of mala are applicable if CONTRACTOR does not complete the milestones [1] [2] and/or [3] in time. The mala types are:

      - [A] Completion date later than the Ultimate date set by CLIENT: if CONTRACTOR does not complete milestones [1], [2] and/or [3] on or before the date as set by CLIENT as ultimate date in the Tender in Annex [4a] (Cycle time and Prices), the CLIENT will charge a malus of 0.2% of the CONTRACT PRICE for each calendar day that the CONTRACTOR fails to complete milestone [1], [2] and/or [3].

      - [B] Completion date later than the proposed date set by CONTRACTOR: If CONTRACTOR is not able to complete milestones [1], [2] and/or [3] on or before the date set by CONTRACTOR in Annex [4a] submitted as part of the Tender, the CLIENT will charge a malus of 0.1% of the CONTRACT PRICE for each calendar day that the CONTRACTOR fails to complete milestones [1],[2] and/or [3] as per the set date in Annex [4a] (Cycle time and Prices) until the Ultimate date as set by CLIENT. The cumulative mala for type B are 2% for each of the individual milestones [1], [2] and/or [3].

The situation could occur that the CONTRACTOR has set a proposed date in its Tender before the ultimate date of the CLIENT and, based on section 5.2 and 5.3, the CONTRACTOR is entitled to a bonus (of meeting the desired date) and also charged with a mala (of completion after the proposed date). In this event the mala will be reduced from the bonus.

The mala are capped at a cumulative maximum of 10% (ten per cent) of the CONTRACT PRICE for all combined mala of type [A] and type [B].

If, other than through force majeure, the CONTRACTOR is permanently unable to perform the WORK as agreed, the mala will be immediately payable in full as specified above.

The mala will be payable to the Contracting Authority, without prejudice to all other rights and claims, including:

- the right to demand that the WORK be performed as agreed;

- the right to damages.

All amounts of such mala for which the Contractor may become liable are agreed as a genuine pre-estimate of the losses which may be sustained by the Contracting Authority in the event that the CONTRACTOR fails in its respective obligations under the CONTRACT. Such mala shall be the sole and exclusive financial remedy of the Contracting Authority in respect of such failure.

The mala will be set off against amounts payable by the Contracting Authority regardless of whether the claim for payment of such amounts has been transferred to a third party.

Dependent of the waiting on weather option that will be chosen, to be updated at finalization of the CONTRACT documents after award