Geotechnical Survey Nederwiek Wind Farm Zone

Annex 6 - Section IIIb Remuneration

Geotechnical Survey – Lot 2

Colophon

| Project name | Geotechnical Survey Nederwiek Wind Farm Zone |
| --- | --- |
| Project number | WOZ2230070/WOZ2230071 |
| Version | Final |
| File name | NWN_20230324_GT_ Annex 6 Section IIIb Remuneration_F01 |
| Project manager | M. Vrolijk |
| Annex(es) |  |
| Author | M. Vrolijk |
| Reviewed | U. Gerdes |
| Approved | P. Lebbink |

Contents

1	Introduction	4

2	Rates, prices and percentages	5

3	Payment Schedule 	8

4	Pricing Schedule	9

5	Bonus and Malus	11

# Introduction

## Remuneration document

This document details the CONTRACT PRICE as part of the CONTRACT that CLIENT has awarded to CONTRACTOR for carrying out the Geotechnical soil investigations at the Nederwiek Wind Farm Zone for LOT 2 of the CONTRACT.

Also, this document contains sections on the payment schedule as well as bonus and mala mechanisms.

# Rates, prices and percentages

## Currency

The rates and prices set out in the PRICING SCHEDULE in this Annex [6] - Section IIIb (Remuneration) are in Euros (€).

## Taxes (VAT)

The rates and prices contained herein exclude Value Added Tax that shall be charged in accordance with prevailing legislation.

## Applicable rate with regard to large/ small fluctuating quantities

The rates and prices contained herein shall apply equally to executing the WORK in large, small or fluctuating quantities.

## Applicable equally to measured work

Rates, prices and percentages shall apply equally to any measured WORK and/or VARIATION regardless of ease, difficulty, location, quantity or whether it is an addition or a reduction to the WORK.

## Variations

Should the CLIENT exercise their entitlement to vary the WORK, then the amended WORK shall be valued by the CLIENT at the rates and prices contained herein insofar as it is fair and reasonable to do so or, where appropriate on a pro-rata basis and adjust the CONTRACT PRICE accordingly.

## Contract Price

The CONTRACT PRICE set out herein shall be the total remuneration payable to the CONTRACTOR for the WORK set out in the CONTRACT and shall take full account of the liabilities and obligations of the CONTRACTOR under this CONTRACT.

## Scope of work

The Scope of WORK set out in this Annex [6] - Section IIIb relates to the scope of work as detailed in Annex [6] - Section IV Scope of Work of this CONTRACT.

## Rates and prices not foreseen

When CLIENT is extending the Scope of Work and these services are not foreseen in Annex [6] - Section IV – Scope of Work, the CLIENT and the CONTRACTOR shall agree, acting reasonably, additional rates and prices as required, taking full account of rates and prices for similar work and prevailing market conditions.

All new rates, prices and percentages when approved by the CLIENT shall remain valid for the duration of the CONTRACT.

## Rates to include all CONTRACTOR’s costs

All rates and prices set out in Annex [4b] Cycle times and Prices for LOT 2 herein are inclusive of all the CONTRACTOR’s costs of whatever nature, unless otherwise agreed, associated with performing the WORK in accordance with the CONTRACT and shall include but not be limited to expenses, management time, overheads, labour (including but not limited to the cost of all productive and non-productive labour), supervision, direct remuneration and payroll related costs (including but not limited to salaries, National Insurance contributions or equivalent in the country of levy, payroll taxes, welfare funds, sick pay, bonus and incentive payments, statutory and annual holidays, health plans and the like), plant & equipment (including but not limited to maintenance and repair), goods, materials and consumables, delivery and collection charges, customs dues.

## Fixed rates and prices

The rates and prices contained herein shall be fixed for the entire period of the CONTRACT including any extensions of time to the CONTRACT term by way of VARIATION.

## Rates to include all other costs

Rates, prices and percentages shall include but not be limited to:

- all equipment, materials, consumables to conduct the WORK;

- daily and/or shift change transfer of personnel, including the CLIENT OFFSHORE REPRESENTATIVE(S) and including lost time to the schedule of or during personnel transfer activities due to delays however caused;

- accommodation, subsistence and meals onboard the vessel for the CONTRACTOR personnel and CLIENT OFFSHORE REPRESENTATIVE(S);

- port, harbour dues and pilotage;

- loading and unloading of the marine vessel(s);

- communication and transmission charges;

- redundancy of consumables, materials and equipment, as appropriate, to avoid non-productive time;

- data processing;

- port calls for equipment and crew change out;

- transfer vessel for moving crews between the land and the marine vessel(s)

## Operational regime

All day rates are based on twenty four (24) hours per day. In the event that only part of a day is worked the day rates shall be reduced pro rata.

## Professional attendance

Professional attendance associated with the supervision and technical direction of the fieldwork and other duties as required by the CONTRACT shall be included in the appropriate rates.

## Payment for Boreholes, P-S logging, downhole density and/or porosity logging

Payment for Borehole, PS-logging, downhole density and/or porosity logging is based on the logged time in the daily progress report.

## Payment for Dissipation Tests

Payment for dissipation tests shall be based on:

- Selected intervals of strata investigated and interpreted in accordance with the Specification; the number of tests will be limited by total time allowance.

## Payment for laboratory tests

Payment shall be done according to the section 3 Payment Schedule of this document.

## Rates for testing shall include for:

- The supply of a copy of the preliminary test results to the CLIENT OFFSHORE REPRESENTATIVE or the CLIENT REPRESENTATIVE as required by the CLIENT;

- The cost of moisture content or density determinations where they form part of the test;

- The cost of supplying example excel files showing the method of calculation for each test.

# Payment Schedule

Payment shall be based on the pro-rata amount of completed Works up to a maximum of 90% of the total CONTRACT PRICE at time of the CONTRACT signature.

CONTRACTOR is eligible for payment of the remaining 9,8% of the CONTRACT PRICE, after completion and approval of both the CLIENT and certifying body of all final reports. For an overview of the final reports please refer to Annex [4b] – Cycle Times and Prices.

A retainer of 0,2% of the total CONTRACT PRICE, excluding the price of potential variation orders, is in place and will be paid after finalisation of the webinar(s).

Applications for payment shall be at monthly intervals with the exception of the milestone mobilisation of vessel(s), equipment and personnel.

CONTRACTOR can apply for payment of the vessel (and equipment) mobilisation after the CLIENT OFFSHORE REPRESENTATIVE has signed the mobilisation certificate, the vessel has transited to the Investigation Area and the first issue of the mobilisation report has been provided to the (onshore) CLIENT.

CONTRACTOR can apply for payment of the laboratory test results after the Client has been provided with the possibility to check and verify lab results.

# Pricing Schedule

The WORK as set out in the CONTRACT shall be undertaken for a lump sum total CONTRACT PRICE of [●]. The CONTRACT PRICE [●] includes WAITING ON WEATHER and excludes any additional authorised work chargeable at the rates set out in the Schedule of Rates contained within paragraph 4.3.

## Limitations of proposed equipment

| Descriptions | WORKABLE WEATHER LIMITS |  |  |
| --- | --- | --- | --- |
|  | Wave height (Hs) | Wind speed (m/s) (Ws_10) | Required Window (Ww) |
| Vessel 1: Part A |  |  |  |
| Working at site | [●]m | [●]m/s | [●]hrs |
| Vessel 2: Part B |  |  |  |
| Working at site | [●]m | [●]m/s | [●]hrs |

Table 1		Maximum allowable weather conditions for carrying out the geotechnical survey works.

- Hs means the significant wave height in meters.

- Ws_10 means 10-minute mean wind speed 10 m above Mean Sea Level.

- Ww means minimum time in hours for an operation i.e. weather window required to start and execute the operation.

## Offshore Operations

CONTRACTOR shall be entitled for vessel day rates for Operational works as per 4.2.1 and for Waiting on Weather Standby as per 4.2.2. Vessel Port calls are including transit and will be based on a rate per port call based on the minimum endurance of 28 days.

The total BUDGET for the Offshore Activities including Vessel Day rates, Waiting on Weather and Port Calls are presented in Table 2. The BUDGET is calculated by Client as per Annex 4b, based on the CONTRACTOR provided vessel performance and the preferred quantities by CLIENT. CONTRACTOR shall perform offshore activities as per CLIENT instructions (within the works described in the SOW) until the budget is consumed or the CLIENT scope is completed (whichever comes first).

| Activity | Budget |
| --- | --- |
| Vessel 1: Part A (activities to be copied from Annex 4b) | €[●] |
| Vessel 2: Part B (activities to be copied from Annex 4b) | €[●] |

Table 2		Budget for offshore geotechnical activities per vessel.

### Operational vessel days

CONTRACTOR vessel day rate shall be applicable for all activities as presented in the SOW. In case multiple vessels are used all vessels shall require to have the equipment on board to conduct the offshore in-situ testing and sampling as per Scope of WORK. All equipment shall be operational to be able to perform works as instructed by CLIENT. In event the Vessel is not operational [for example during breakdowns] the vessel will be on Standby/Breakdown on CONTRACTORS costs.

In the event CLIENT utilize the OPTIONAL SCOPE the CONTRACTOR shall ensure that the required equipment is on board of the relevant vessel and operational.

CONTRACTOR is allowed for Vessel Operational days from the moment the vessel completed mobilization and is ready for Operations inside the Investigation Area as long as weather conditions are within the limitations provided by CONTRACTOR.

Operational vessel rate shall stop when the vessel is on weather standby, not operational or from the moment the vessel is outside the Investigation area and/or is in transit to or from port.

CLIENT has calculated the expected required VESSEL OPERATIONAL DAYS to complete the planned Scope based on the by CONTRACTOR provided vessel performance. The Operational Vessel Days based on the proposed vessel operations for this contract are presented in Table 3.

During the project CLIENT will monitor the offshore performance of the CONTRACTOR to verify if the CONTRACTOR aligns (on average) with the operational performance (durations) as proposed by CONTRACTOR during the Tender. In the event significant difference (>10%) are observed (on average) the CLIENT will request CONTRACTOR to justify the difference and/or to provide a plan of improvement. If CONTRACTOR thereafter is unable to execute the works within the by CONTRACT proposed operational performance (durations) the operational rates can be adjusted pro rato to the actual performance.

| Activity | Day Rate |  |
| --- | --- | --- |
| Vessel 1: Part A (activities to be copied from Annex 4b) | €[●] | [●] days |
| Vessel 2: Part B (activities to be copied from Annex 4b) | €[●] | [●] days |

Table 3		Day rate in euros and expected days for vessel operations to conduct geotechnical survey activities.

### Waiting on weather

CONTRACTOR vessel WAITING ON WEATHER day rate shall be applicable once the vessel is on Waiting on Weather and weather criteria is above the workable limits as provided by CONTRACTOR and are presented in Table 1. Details of the determination of Waiting on Weather criteria and workable limits are presented in Annex 6 – Section VI Chapter 8.

The WAITING ON WEATHER budget is calculated by CLIENT based on the vessel workability from CONTRACTOR and the schedule.

CONTRACTOR is entitled for WAITING ON WEATHER day rate as per Table 4 as the weather conditions are above the limitations provided by contractor per Table 1.

In the event the vessel is not operational and weather conditions are above the limitations as per Table 1 the vessel shall be on Standby/Breakdown on CONTRACTORS costs. In this event CONTRACTOR is not entitled to apply the WAITING ON WEATHER dayrate.

CONTRACTOR shall in no case be entitled to any additional compensation or reimbursement on the basis of WAITING ON WEATHER other than the WAITING ON WEATHER DAYRATE as presented in Table 4 and agreed VARIATIONS.

| Activity | Day Rate |  |
| --- | --- | --- |
| Vessel 1: Part A (activities to be copied from annex 4b) | €[●] | [●] days |
| Vessel 2: Part B (activities to be copied from annex 4b) | €[●] | [●] days |

Table 4		Day rate in euros and expected days for WAITING ON WEATHER during the geotechnical survey.

## Rates and prices

The elements of the CONTRACT PRICE together with rates and prices for all known variations to the WORK are presented in Annex [4b] for LOT 2.

# Bonus and Malus

The CLIENT has included a bonus performance system as an incentive for completion of the (by CLIENT) intended offshore activities within the budget limit and within the proposed durations by the CONTRACTOR. A malus system is applied to delivery of reports and/or results subjected to rely upon information for other works from CLIENT. The bonus malus performance system in this document applies to Lot 2.

## Bonus and Malus milestones

As the operational works are based on a day-Rate mechanism, the offshore performance from the COTNRACTOR will determine the amount of site characterization that will be available. As an Incentive to complete the (by CLIENT) intended scope according to the proposed operational performance by the CONTRACTOR a bonus mechanism is applicable as described in section 5.2.

The CLIENT stipulates key milestones in Annex [4b], which are used Mala mechanism:

- [1] Start of Survey WORK

- [2] DELIVERY OF FINAL GEOTECHNICAL BOREHOLE REPORT;

- [3] DELIVERY OF FINAL Cyclic lab REPORT;

The CLIENT has set an ultimate dates for the milestones [1].[2] and [3] in Annex [4b] Cycle times and Prices. The CONTRACTOR will include a proposed data for these milestones in Annex [4b] of its Tender.

Completion of any Key Date as mentioned in Annex [4b] (shown in bold, underscored and green), later than the ultimate date will interfere with other commitments of the CLIENT and/or will cause delay to the schedule. Not completing the WORKS or delivery of documentation prior or onto the ultimate date will cause the CLIENT to charge mala to the CONTRACTOR as described in section 5.3.

The CONTRACTOR has issued Annex [4b] (Cycle times and Prices) of the tender documentation with proposed dates for the milestones [1],[2] and [3]. The dates provided by CONTRACTOR will be used by CLIENT to make agreements with other parties, therefore mala will be charged to the CONTRACTOR when completion of the milestone is exceeding the dates as described in section 5.3.

## Bonus

If the Contractor succeeds to complete at least 95% of the by CLIENT intended boreholes including associated in situ- testing and sampling within the budget for offshore operations (based on CONTRACORS tender input) and results are approved by the CLIENT, then the CONTRACTOR is awarded a bonus of up to 250.000,-

Table 5: Maximum bonus for offshore performance

| Bonus |  |
| --- | --- |
| Completion of 100% of the intended (107) BH locations including associated in situ testing and sampling and Operational costs remain below 95% of the budget as presented in Section 4.2 for offshore activities. | 250.000,- |
| Completion of 100% of the intended (107) BH locations including associated in situ testing and sampling within (but higher than 95% of) the budget as presented in Section 4.2 for offshore activities. | 125.000,- |
| Completion of minimum 95% (>102) of the intended (107) BH locations including associated in situ testing and sampling within the budget as presented in Section 4.2 for offshore activities. | 50.000,- |

## Mala

Three types of mala can be applicable if CONTRACTOR does not complete the milestones [1]. [2] or [3] on or before the agreed date. The mala types are:

      - [A] Completion date later than the Ultimate date set by CLIENT: if CONTRACTOR does not complete milestones [2] and/or [3] on or before the date as set by CLIENT as ultimate date in the Tender in Annex [4b] (Cycle time and Prices), the CLIENT will charge a malus of 0.1% of the CONTRACT PRICE for each calendar day that the CONTRACTOR fails to complete milestone [1] and/or [2].

      - [B] Completion date later than the proposed date set by CONTRACTOR: If CONTRACTOR is not able to complete milestones [2] and/or [3] on or before the date set by CONTRACTOR in Annex [4b] submitted as part of the Tender, the CLIENT will charge a malus of 0.05% of the CONTRACT PRICE for each calendar day that the CONTRACTOR fails to complete milestones [2] and/or [3] as per the set date in Annex [4b] (Cycle time and Prices) until the Ultimate date as set by CLIENT. The cumulative mala for type B are 1% for each of the individual milestones [2]

      - [C] Start date of the Survey Works later than the proposed date By CONTRACTOR; if CONTRACTOR fails to start the milestone [1] on or before the data as set by CONTRACTOR in the Tender in Annex [4b] (Cycle time and Prices), the CLIENT will charge a malus of 0.1% of the CONTRACT PRICE for each calendar day that the CONTRACTOR fails to complete milestone [1] to compensate for increased Weather Risk for the CLIENT.

The situation could occur that the CONTRACTOR has set a proposed date in its Tender before the ultimate date of the CLIENT and, based on section 5.2 and 5.3, the CONTRACTOR is entitled to a bonus (of meeting the desired date) and also charged with a mala (of completion after the proposed date). In this event the mala will be reduced from the bonus.

The mala are capped at a cumulative maximum of 5% (five per cent) of the CONTRACT PRICE for all combined mala of type [A], type [B] and type [C].

If, other than through force majeure, the CONTRACTOR is permanently unable to perform the WORK as agreed, the mala will be immediately payable in full as specified above.

The mala will be payable to the Contracting Authority, without prejudice to all other rights and claims, including:

- the right to demand that the WORK be performed as agreed;

- the right to damages.

All amounts of such mala for which the Contractor may become liable are agreed as a genuine pre-estimate of the losses which may be sustained by the Contracting Authority in the event that the CONTRACTOR fails in its respective obligations under the CONTRACT. Such mala shall be the sole and exclusive financial remedy of the Contracting Authority in respect of such failure.

The mala will be set off against amounts payable by the Contracting Authority regardless of whether the claim for payment of such amounts has been transferred to a third party.