## Delivery Dates and Prices
DELIVERY DATES & PRICES FOR GEOTECHNICAL INTERPRETIVE REPORT ¦& INTEGRATED GROUND MODEL
| Project: | Nederwiek Zuid: Geotechnical Interpretation and Integrated Ground Model |  | Hide column
| Company: | Company name | [8 empty] | Error message if no price in remuneration section
| Originator: | Originator name
[10 empty] | Note | FILL UNIT RATE
| I. Delivery Dates |  |  | max duration (days) | Unit | Cycle |  |  | (end) date | I.0
| Key dates | [9 empty] | Days between desired and ultimate report due date
| 1a | COMMENCEMENT DATE WORK | [6 empty] | 2023-05-29
| 1b | GT Information (Nederwiek Zuid Lot 1): Final report "Seabed In Situ Testing Report" | [6 empty] | 2023-08-13 |  | 30
| 1c | GT Information (Nederwiek Zuid Lot 1): Final "Seabed Sampling Report" | [6 empty] | 31-sep-2023 | I.1
| 1d | GT Information (Nederwiek Zuid Lot 2): Field report "Geotechnical Boreholes Report", including draft GT BH Logs, and downhole testing results | [6 empty] | 2023-12-23
| 1e | GT Information (Nederwiek Zuid Lot 2): Final revision "Geotechnical Boreholes Report" | [6 empty] | 2024-06-26
| 1f | GT Information (Nederwiek Zuid Lot 2): Final "Age Dating Report" | [6 empty] | 2024-02-12
| 1g | GT Information (Nederwiek Zuid Lot 2): Final "Advanced Cyclic Laboratory Testing Report" | [6 empty] | 2024-09-01
| 1h | GP Information (Nederwiek Zuid 2D Seabed Survey): Processed survey data for priority lines (2DUHRS, MBES, SSS, Magnetometer and SBP) | [6 empty] | 2023-05-30
| 1i | GP Information (Nederwiek Zuid 2D Seabed Survey): Processed survey data for all lines (2DUHRS, MBES, SSS, Magnetometer and SBP) | [6 empty] | 2023-12-01
| 1k | GP Information (Nederwiek Zuid 2D Seabed Survey): Final revision "Geophysical Seabed Survey Report", including all raw, processend and interpreted digital data. | [6 empty] | 2023-12-01
Preparation
| 2a | Provision of 1st revision of project documentation (days after contract award, 1a) | (max 8 weeks) | 56 | days |  | Fill number of days |  | 2023-05-29
| 2b | Client review 1st revision project documentation |  |  | days | 7 |  |  | 2023-06-05
| 2c | Provision of final version of project documentation (after receipt priority lines data 2D UHRS Survey, item 1h) | (Max: 4 weeks) | 28 | days |  | Fill number of days |  | 2023-05-30
| 2d | Review final version of project documentation |  |  | days | 7 |  |  | 2023-06-06
| 2g | Provision of Laboratory Testing Strategy Plan for downhole GT campaign (after receipt priority lines data 2D UHRS Survey, item 1h) | (Max: 6 weeks) | 42 | days |  | Fill number of days |  | 2023-05-30
| 2h | Review of Laboratory Testing Strategy Plan |  |  | days | 14 |  |  | 2023-06-13
| 2i | Provision of Final Laboratory Testing Strategy Plan | (Max: 1 week) | 7 | days |  | Fill number of days |  | 2023-06-13
| 2j | Provision of Lot 2 Borehole sampling and CPT plan (days after contract award, item 1a) | (Max: 6 weeks) | 42 | days |  | Fill number of days |  | 2023-05-29
| 2k | Delivery of Geological Ground Model Report Template, GGM (days after contract award, item 1a) | (Max: 8 weeks) | 56 | days |  | Fill number of days |  | 2023-05-29 | I.2
| 2l | Delivery of Geotechnical Interpretation Report Template, GIR (days after provision of final laboratory testing strategy plan, item 2i) | (Max: 6 weeks) | 42 | days |  | Fill number of days |  | 2023-06-13 | I.2
| 2m | Delivery of example of IGM database format (days after contract award, item 1a) | (Max: 26 weeks) | 182 | days |  | Fill number of days |  | 2023-05-29 | I.2
Data processing and reporting
| 3a | Delivery of Draft Report Geological Ground Model (after receiving of final geophysical 2D reports, item 1o) | (Max: 26 weeks) | 182 | days |  | Fill number of days |  | 2023-12-01 | I.3
| 3b | CLIENT review of Draft Report Geological Ground Model |  |  | days | 21 |  |  | 2023-12-22
| 3c | Delivery of 2nd revision Draft Report Geological Ground Model | (Max: 4 weeks) | 28 | days |  | Fill number of days |  | 2023-12-22
| 3d | CLIENT review of 2nd revision Draft Report Geological Ground Model |  |  | days | 14 |  |  | 2024-01-05
| 3e | Delivery of 3rd revision Draft Report Geological Ground Model | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2024-01-05
| 3f | CLIENT review of 3rd revision Draft Report Geological Ground Model |  |  | days | 7 |  |  | 2024-01-12
| 3g | Final Report Geological Ground Model | (Max: 2 weeks) | 14 | days |  | Fill number of days |  | 2024-01-12
| 3h | CLIENT review of Final Report Geological Ground Model |  |  | days | 7 |  |  | 2024-01-19
| 3i | Delivery of Draft Report Geotechnical Interpretation Report (after reception of final BH Locations report and final data, item 1e) | (Max: 8 weeks) | 56 | days |  | Fill number of days |  | 2024-06-26
| 3j | CLIENT review of Draft Geotechnical Interpretation Report |  |  | days | 21 |  |  | 2024-07-17
| 3k | Delivery of Final Geotechnical Interpretation Report (excluding interpretation of cyclic test results) | (Max: 7 weeks) | 49 | days |  | Fill number of days |  | 2024-07-17
| 3l | CLIENT review of Final Geotechnical Interpretation Report |  |  | days | 14 |  |  | 2024-07-31
| 3m | Delivery of Draft Cyclic Test Results Interpretation Report (after receiving final Advanced Cyclic Laboratory Testing Report, item 1g) | (Max: 5 weeks) | 35 | days |  | Fill number of days |  | 2024-09-01
| 3n | CLIENT review of Draft Cyclic Test Results Interpretation Report |  |  | days | 7 |  |  | 2024-09-08
| 3o | Delivery of Final Cyclic Test Results Interpretation Report | (Max: 2 weeks) | 14 | days |  |  |  | 2024-09-08
| 3p | CLIENT review of Final Cyclic Test Results Interpretation Report |  |  |  | 7 |  |  | 2024-09-15
| 3q | Delivery of Interim Report Integrated Ground Model (after reception of final BH Locations Report and data, item 1e) | (Max: 16 weeks) | 112 | days |  | Fill number of days |  | 2024-06-26
| 3r | CLIENT review of Interim Report Integrated Ground Model |  |  | days | 21 |  |  | 2024-07-17
| 3u | Final Report Integrated Ground Model | (Max: 5 weeks) | 35 | days |  | Fill number of days |  | 2024-07-17
| 3v | CLIENT review of Final Report Integrated Ground Model |  |  | days | 14 |  |  | 2024-07-31
| TOTAL DURATION CYCLE TIME | [6 empty] | 415 | days
II. Prices and Rates
| ITEM |  |  |  |  | Unit Rate | Unit | Qty | Price | II.0
| 1 | Reporting
| 1.1 | Project Execution Plan |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.2 | Reprocessing of seismic data |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.3 | Velocity picking |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.4 | Reinterpretation of structural geological model |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.5 | Laboratory Test Strategy |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.6 | Geological Ground Model Report (GGM) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.7 | Geotechnical Interpretation Report (GIR) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.8 | Cyclic Testing Interpretation Report |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.9 | Prediction of CPTs based on seismic data |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.10 | Integrated Ground Model Report (IGM) |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 1.11 | Optional: Assessment and integration into IGM of 3D UHRS seismic data along corridor, refer to section 2.2.3 of Annex 6-V-Scope of work |  |  |  |  | Lump sum | 1 | FILL UNIT RATE
| 2 | Other
| 2.1 | Project meetings to be held in CLIENT offices (Utrecht or The Hague) |  |  |  |  | /meeting | 5 | FILL UNIT RATE
| 2.2 | Online meetings and workshops | [6 empty] | 0
| 2.2.1 | Bi-weekly Work Progress Meetings (RVO-Contractor) |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE
| 2.2.2 | Four-weekly Joint Progress Meetings (RVO-Contractor-GT Contractor) |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE
| 2.2.3 | Expert/ specialist meetings |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE
| 2.2.4 | Workshops |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE
| 2.3 | Activities related to dissemination of results (webinar and Project Site Description) |  |  |  |  | Lump Sum | 1 | FILL UNIT RATE | II.1
| 2.4 | Hourly rate for Project Manager |  |  |  |  | hr | 0 | FILL UNIT RATE
| 2.5 | Hourly rate for Senior Specialist |  |  |  |  | hr | 0 | FILL UNIT RATE
| 2.6 | Hourly rate for Medior Specialist |  |  |  |  | hr | 0 | FILL UNIT RATE
III. INPUT FOR ASSESSMENT OF THE OFFER
INPUT FOR ASSESSMENT OF THE PRICE CRITERION - Fixed prices/rates
| Costs |  | Reporting works and meetings |  |  |  |  | 0
|  |  | Webinar Activities |  |  |  |  | FILL UNIT RATE
| TOTAL PRICE for assessment | [6 empty] | 0 |  | III.0
|  |  | Max. number of points that can be awarded |  |  |  |  | 20
|  |  | Minimum Price (determined by CLIENT) |  |  |  |  | 1400000
|  |  | Maximum Price (determined by CLIENT) |  |  |  |  | 2000000
|  |  | Points gained for the TOTAL PRICE proposed: |  |  |  |  | 0 | Points | III.0
| INPUT FOR ASSESSMENT OF THE COMPLETION DATE / DELIVERY DATE CRITERION (Ability to finalize the offshore campaign at the preferred end date as set by CLIENT): | [8 empty] | III.1
| Key Completion dates |  | Desired date for Delivery of Final Report (3g,3k,3q), set by CLIENT |  |  |  |  | 2024-09-30
|  |  | Ultimate date for Delivery of Final Reports set by CLIENT |  |  |  |  | 2024-10-30
|  |  |  | Date determined by input TENDERER |  |  |  | 2024-07-17 |  | III.2
|  |  | TOTAL difference from desired date (for assessment) |  |  |  |  | -75 | days
|  |  | Max. number of points that can be awarded |  |  |  |  | 5
|  |  | Points for the TOTAL CYCLE TIME proposed: |  |  |  |  | 5 | Points
| TOTAL POINTS GAINED BY TENDERER | [6 empty] | 5 | Points
VI. NOTES
| I.0 | IN CASE A CELL IN THIS ANNEX 4 IS COLORED RED AS SHOWN IN THIS CELL THE PROPOSAL IS NOT VALID.
| I.0 | All numbers indicated in green are starting points set by CLIENT.
| I.0 | All numbers indicated in blue (yellow cells) are to be provided by TENDERER and will form part of the PRICING SCHEDULE / CONTRACT PRICE as included in Annex 6 - Contract Section IV (Remuneration), and/or KEY DATES as included in Annex 6 - Contract Section V (Scope of Work). All quantities will be used for assessment purposes and will also be the basis for determining the final CONTRACT PRICE and KEY DATES for these activities to be carried out under the CONTRACT. IN CASE THE BLUE TEXT TURNS RED, THIS MEANS THAT TENDERER ENTERED A VALUE OUTSIDE THE ALLOWABLE RANGES. This colour coding is for convenience only; the TENDERER is responsible for ensuring that the correct values are submitted by the TENDERER.
| I.0 | TENDERER shall specify the durations for executing the works. Based upon these durations, the key dates are determined. At Contract award these dates will be taken over in Annex 6 - Section V (Scope of Work) Please note that Liquidated Damages become applicable in case TENDERER fails to meet Key Dates as per Annex 6 - Contract Section III (Conditions of Contract)- Clause 42!
| I.1 | In case of a delay of the delivery of the data and reports from the geophysical and geotechnical contractor(s) as indicated in 1b to 1j (during execution phase of the contract), the dates for data processing and reporting (3a-3v) will be shifted accordingly.
| I.2 | TENDERER to provide dates for issue of report template based on the key dates indicated.
| I.3 | TENDERER to provide the number of days required for preparing & updating of the reports. Key dates are generated automatically based on these cycle times. Please note CLIENT as set maximum durations for delivery of the reports
| II.0 | At Contract award, all rates specified in this Annex 4 shall be taken over in the PRICING SCHEDULE in Annex 6 - Contract Section IV (Remuneration). See sheet [Remuneration Table] for the table and its format as will be used in Annex 6 - Contract Section IV (Remuneration).
| II.1 | Lump sum for Activities related to dissemination of results (webinar and Project Site Description) shall be paid upon completion of the webinar and PSD, in accordance with Annex 6 - Contract Section IV (Remuneration).
| III.0 | The number of points that can be awarded is determined through linear interpolation between the minimum and maximum price. IN CASE THE TOTAL VIRTUAL PRICE OFFERED IS HIGHER THAN THE MAXIMUM PRICE THEN THE PROPOSAL IS NOT VALID!
| III.1 | The TENDERER gains points when able to deliver the final report close to or before the date desired by CLIENT. The number of points that is awarded is determined through linear interpolation between the minimum and maximum number of days. In case the completion date is later than the Ultimate date set by CLIENT the proposal will be rejected! The weather downtime days as specified by the TENDERER under items 3k and 4k are included in the calculation of the OFFSHORE COMPLETION DATE (5a).
| III.2 | IN CASE THIS DATE IS LATER THAN THE ULTIMATE DUE DATE SET BY THE CLIENT THIS CELL IS COLORED RED. THIS MEANS THE PROPOSAL NOT VALID!

## Key dates
Items in green, bold and underlined, highlight key dates for which contractor is liable for liquidated damages in case of failure to complete these dates
No. | Description | Date
1a | COMMENCEMENT DATE WORK | 2023-05-29
2a | Provision of 1st revision of project documentation (days after contract award, 1a) | 2023-05-29
2b | Client review 1st revision project documentation | 2023-06-05
2c | Provision of final version of project documentation (after receipt priority lines data 2D UHRS Survey, item 1h) | 2023-05-30
2d | Review final version of project documentation | 2023-06-06
2g | Provision of Laboratory Testing Strategy Plan for downhole GT campaign (after receipt priority lines data 2D UHRS Survey, item 1h) | 2023-05-30
2h | Review of Laboratory Testing Strategy Plan | 2023-06-13
2i | Provision of Final Laboratory Testing Strategy Plan | 2023-06-13
2j | Provision of Lot 2 Borehole sampling and CPT plan (days after contract award, item 1a) | 2023-05-29
2k | Delivery of Geological Ground Model Report Template, GGM (days after contract award, item 1a) | 2023-05-29
2l | Delivery of Geotechnical Interpretation Report Template, GIR (days after provision of final laboratory testing strategy plan, item 2i) | 2023-06-13
2m | Delivery of example of IGM database format (days after contract award, item 1a) | 2023-05-29
3a | Delivery of Draft Report Geological Ground Model (after receiving of final geophysical 2D reports, item 1o) | 2023-12-01
3b | CLIENT review of Draft Report Geological Ground Model | 2023-12-22
3c | Delivery of 2nd revision Draft Report Geological Ground Model | 2023-12-22
3d | CLIENT review of 2nd revision Draft Report Geological Ground Model | 2024-01-05
3e | Delivery of 3rd revision Draft Report Geological Ground Model | 2024-01-05
3f | CLIENT review of 3rd revision Draft Report Geological Ground Model | 2024-01-12
3g | Final Report Geological Ground Model | 2024-01-12
3h | CLIENT review of Final Report Geological Ground Model | 2024-01-19
3i | Delivery of Draft Report Geotechnical Interpretation Report (after reception of final BH Locations report and final data, item 1e) | 2024-06-26
3j | CLIENT review of Draft Geotechnical Interpretation Report | 2024-07-17
3k | Delivery of Final Geotechnical Interpretation Report (excluding interpretation of cyclic test results) | 2024-07-17
3l | CLIENT review of Final Geotechnical Interpretation Report | 2024-07-31
3m | Delivery of Draft Cyclic Test Results Interpretation Report (after receiving final Advanced Cyclic Laboratory Testing Report, item 1g) | 2024-09-01
3n | CLIENT review of Draft Cyclic Test Results Interpretation Report | 2024-09-08
3o | Delivery of Final Cyclic Test Results Interpretation Report | 2024-09-08
3p | CLIENT review of Final Cyclic Test Results Interpretation Report | 2024-09-15
3q | Delivery of Interim Report Integrated Ground Model (after reception of final BH Locations Report and data, item 1e) | 2024-06-26
3r | CLIENT review of Interim Report Integrated Ground Model | 2024-07-17
3u | Final Report Integrated Ground Model | 2024-07-17
3v | CLIENT review of Final Report Integrated Ground Model | 2024-07-31

## Remuneration Table
Item | Description | Unit | Unit Rate | Quantity | Price
Reporting
1.1 | Project Execution Plan | Lump sum | 0 | 1 | FILL UNIT RATE
1.2 | Reprocessing of seismic data | Lump sum | 0 | 1 | FILL UNIT RATE
1.3 | Velocity picking | Lump sum | 0 | 1 | FILL UNIT RATE
1.4 | Reinterpretation of structural geological model | Lump sum | 0 | 1 | FILL UNIT RATE
1.5 | Laboratory Test Strategy | Lump sum | 0 | 1 | FILL UNIT RATE
1.6 | Geological Ground Model Report (GGM) | Lump sum | 0 | 1 | FILL UNIT RATE
1.7 | Geotechnical Interpretation Report (GIR) | Lump sum | 0 | 1 | FILL UNIT RATE
1.8 | Cyclic Testing Interpretation Report | Lump sum | 0 | 1 | FILL UNIT RATE
1.9 | Prediction of CPTs based on seismic data | Lump sum | 0 | 1 | FILL UNIT RATE
1.10 | Integrated Ground Model Report (IGM) | Lump sum | 0 | 1 | FILL UNIT RATE
1.11 | Optional: Assessment and integration into IGM of 3D UHRS seismic data along corridor, refer to section 2.2.3 of Annex 6-V-Scope of work | Lump sum | 0 | 1 | FILL UNIT RATE
Other
2.1 | Project meetings to be held in CLIENT offices (Utrecht or The Hague) | /meeting | 0 | 5 | FILL UNIT RATE
2.2 | Online meetings and workshops |  |  |  | 0
2.2.1 | Bi-weekly Work Progress Meetings (RVO-Contractor) | Lump Sum | 0 | 1 | FILL UNIT RATE
2.2.2 | Four-weekly Joint Progress Meetings (RVO-Contractor-GT Contractor) | Lump Sum | 0 | 1 | FILL UNIT RATE
2.2.3 | Expert/ specialist meetings | Lump Sum | 0 | 1 | FILL UNIT RATE
2.2.4 | Workshops | Lump Sum | 0 | 1 | FILL UNIT RATE
2.3 | Activities related to dissemination of results (webinar and Project Site Description) | Lump Sum | 0 | 1 | FILL UNIT RATE
2.4 | Hourly rate for Project Manager | hr | 0 | 0 | FILL UNIT RATE
2.5 | Hourly rate for Senior Specialist | hr | 0 | 0 | FILL UNIT RATE
2.6 | Hourly rate for Medior Specialist | hr | 0 | 0 | FILL UNIT RATE