## Appendix A - HSE Risk Register
HSE Action & Response Sheet
Document No.: 416041-47990/G.06/007 - Appendix A | [9 empty] | Revision: | A
Client: AEB Amsterdam | [9 empty] | Revision Date: | 2023-07-14
Project Name: | Aurora Project | [8 empty] | Originator: | Amit Munshi
HSE Action originates from:
Study Identifier | Document number |  |  | Description | [5 empty] | Revision | Date
H1 | 416041-47990/G.06/006, Rev. A |  |  | HAZID Project Title | [5 empty] | A | 2023-06-19
H2
H3
H4
H5
H6
H7
H8
H9
HSE Action | Study Identifier | MOD file | Study Action | Description | Owner | Project Stage | Due date | Response | Status | Latest update | Approved
1 | H1 | 1 | 1 | CO2 Personal Gas detectors should be provided to staff to carry in the field. Fixed CO2 Gas Detection System(s) shall be designed as part of the project. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
2 | H1 | 1 | 2 | Take ice formation risks into account during design of the installation. Related operational work procedures to be developed. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
3 | H1 | 1 | 3 | Logistics Plan to be made with attention to proper lining, safety signs, vehicle routing and lighting around the roads with low visibility conditions. | AEB | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
4 | H1 | 1 | 4 | Heavy rain scenario to be considered for the design of the new sewer system of the new PCC plant. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
5 | H1 | 1 | 5 | Design shall ensure that loss of power shall not lead to hazardous consequences. Solutions such as fail-safe design, use of emergency/UPS power etc. to be considered. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
6 | H1 | 1 | 6 | Emergency Response procedures to be developed/updated for high CO2 leakage scenarios. | AEB | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
7 | H1 | 1 | 7 | Waternet QRA & BEN QRA to be reviewed to assess the potential impact and safety risks for e.g., the scenarios of nearby biogas tank explosion/ wood gasifier factory fire. | AEB | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
8 | H1 | 1 | 8 | Traffic Plan to be updated to reduce the impact from the scenario of "Unloading of bulk chemicals from truck for HRC and AEC". QRA for truck unloading operations to be shared with the neighbours as well. | AEB | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
9 | H1 | 1 | 9 | Manage the interface (including process control and safety systems) with OCAP | AEB | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
10 | H1 | 1 | 10 | Sourcing Strategy to be developed for all the consumables & spares availability. | AEB | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
11 | H1 | 1 | 11 | Investigate if the existing warehouse is sufficiently sized to include new spares, if not, proper action should be initiated. | AEB | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
12 | H1 | 1 | 12 | Process should be designed to reduce ammonia emissions | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
13 | H1 | 1 | 13 | Consider reducing ammonia in the existing process (De-NOx). | AEB | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
14 | H1 | 1 | 14 | Consider pilot project to test various solvents including SVHC (Dutch: ZZS) content, ammonia in flue gas, wastewater contamination and CO2 quality. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
15 | H1 | 1 | 15 | Consider bringing back the CO2 stream including hot air back into the stack as it is included in the permit. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
16 | H1 | 1 | 16 | Analyse the wastewater stream and consider designing the wastewater treatment to handle ammonia after looking into various options. Optimize De-NOx. Online monitoring for ammonia and mercury to be considered. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
17 | H1 | 1 | 17 | Consider sampling the wastewater stream to prevent sending wastewater to municipal sewage treatment potentially violating the permit. Consider a retention tank in design. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
18 | H1 | 1 | 18 | Add chlorine inline measurement in the PCC cooling water inlet downstream the anti-biofouling system. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
19 | H1 | 1 | 19 | Good House Keeping and proper maintenance on filters and water separators. Integration into monitoring plan should be considered. | AEB | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
20 | H1 | 1 | 20 | Waste Streams must be formally approved by Acceptation Teams. | AEB | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
21 | H1 | 1 | 21 | Construction activities to be planned whilst taking breeding season of birds into account. Consult ecological expert. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
22 | H1 | 1 | 22 | Consider use of quick release coupling for loading/Unloading operation. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
23 | H1 | 1 | 23 | Local Control panel station should be installed in the PCC plant | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
24 | H1 | 1 | 24 | Well defined operating window aligned with AEB’s internal Operating, Control & Alarm philosophy. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
25 | H1 | 1 | 25 | Investigate the best solution to prevent failure of louvre dampers and/or mitigate failure cases. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
26 | H1 | 1 | 26 | Tracing needs to be in operation during the power failure. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
27 | H1 | 1 | 27 | Align PCC plant’s maintenance philosophy of PCC plant with AEB’s present maintenance philosophy for the existing operations | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
28 | H1 | 1 | 28 | Well defined maintenance and spare part work instructions to be prepared including PO orders in the ERP system. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
29 | H1 | 1 | 29 | Engineer an isolation method to keep the availability of PCC high. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
30 | H1 | 1 | 30 | A maintenance review session on P&ID level to be organised prior to the HAZOP session. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
31 | H1 | 1 | 31 | Integrate PCC plant in the existing Emergency Plan and communicate with Fire Brigade. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
32 | H1 | 1 | 32 | Consider using lined steel & discuss with insurance company. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
33 | H1 | 1 | 33 | Consider other coolant than ammonia for the chiller. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
34 | H1 | 1 | 34 | Material Selection study to be executed. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
35 | H1 | 1 | 35 | Design, Handling (loading/unloading) and Operational requirements related to amine storage and transport to be reviewed in the HAZOP session. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
36 | H1 | 1 | 36 | Design, Handling (loading/unloading) and operation requirements related to sulphuric acid storage and transport to be reviewed in the HAZOP session | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
37 | H1 | 1 | 37 | CO2 gas detectors to be provided in the areas where CO2 leakage may be expected. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
38 | H1 | 1 | 38 | Ensure proper ventilation is provided for the indoor areas (e.g., acoustic enclosures). | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
39 | H1 | 1 | 39 | Organise technical alignment meetings with Offtaker (OCAP) | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
40 | H1 | 1 | 40 | Control philosophy for flue gas fan & louvre dampers to be reviewed during HAZOP session. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
41 | H1 | 1 | 41 | Investigate if flushing of the system is needed after drainage of the amine solution. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
42 | H1 | 1 | 42 | Material to be selected for CO2 looking into JT effect. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
43 | H1 | 1 | 43 | Acceptance including testing requirements procedure for Amine should be prepared. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
44 | H1 | 1 | 44 | Solvent Management Plan to be investigated. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
45 | H1 | 1 | 45 | Add a TOC (Total Organic Contamination) measurement into the condensate line. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
46 | H1 | 1 | 46 | Design the drains such that (also at start up, shutdown and maintenance) medium is properly recovered. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
47 | H1 | 1 | 47 | Make reservation for storage and dosing of auxiliary chemicals. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
48 | H1 | 1 | 48 | Every instrument, valve and operable equipment has to be accessible and visible without the need of any additional temporary measures (like ladders etc.). | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
49 | H1 | 1 | 49 | Accessibility of Louver dampers in the flue gas lines should be reviewed in detail. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
50 | H1 | 1 | 50 | Make sure that there is enough space to install cranes for maintenance | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
51 | H1 | 1 | 51 | Ensure the passage height under pipe bridges is sufficient. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
52 | H1 | 1 | 52 | Erect a first line maintenance station for the operators including LOTOTO near the PCC plant. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
53 | H1 | 1 | 53 | Safety Effect Calculations for safe location to atmosphere of the vents to be performed. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
54 | H1 | 1 | 54 | Health risks of amine to be further investigated and define impact for plant design. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
55 | H1 | 1 | 55 | Select solvent based on health, safety requirements. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
56 | H1 | 1 | 56 | Bow-tie analysis to be performed for safe use of selected solvent. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
57 | H1 | 1 | 57 | Define the necessary PPE for safe working with amine. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
58 | H1 | 1 | 58 | Plant installed outdoor (ensuring proper ventilation) to be kept in mind when applying for Building Permit. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
59 | H1 | 1 | 59 | CO2 Compressor will be installed in an acoustic enclosure. Conditional access to be considered for this enclosed space. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
60 | H1 | 1 | 60 | Formation of carcinogenic degradation products of amines need to be minimized by proper process design. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
61 | H1 | 1 | 61 | Requirement of Safety Shower and Eye Wash for diphtheriae to be checked for areas where exposure to amine is expected. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
62 | H1 | 1 | 62 | Check if expansion of CO2 from 23bar to atmospheric pressure may trigger a hazardous situation leading to cold burns | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
63 | H1 | 1 | 63 | Ensure noise requirements are met by the Vendor | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
64 | H1 | 1 | 64 | Evaluate the design of the nitrogen system if it is considered indoor. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
65 | H1 | 1 | 65 | Consider “man down” function on the portaphone system. | AEB/EPC Contractor | FEED/EPC | TBD | To be closed in Feed/EPC Phase. | Pending | 2023-07-14
Note on F19: First complete List of Action Owners on Summary Sheet

## Backup (hidden)
Study Identifier | MOD file | Party | Discipline | Project Stage | Type of Acton | Status
H1 | 1 | JNL | CSA | FEED/EPC | PEFS | Pending
H2 | 2 | SNR | Electrical | Define | ACM | Resolved
H3 | 3 |  | HSE | Execute | SGM | Closed
H4 | 4 |  | Inspection | As-Built | Work Instruction
H5 | 5 |  | Instrumentation |  | Vendor
H6 | 6 |  | Operations |  | Source Analysis/ MDB
H7 | 7 |  | Piping |  | Instrumented Function
H8 | 8 |  | Process |  | Engineering Other
H9 | 9 |  | Process Control |  | LOPA/ IPF
H10 | 10 |  | Project |  | Construction/ Commissioning
Technology
Other1
Other2
Other3