## Timeline Release
Timeline - Supplier release(s)
Version: 0.9
Date: 08-08-2022
Week | - | Milestone/phase/activity | Entry criteria | Exit criteria | Documents | Environment | Remarks
|  | GeneralAvailable Test Supplier |  |  |  | Test
|  | Complete systemtest |  | All components and functionality tested | Compatibility matrix | Testenvironment Supplier
|  |  |  | All interfaces tested | Installation manual incl.rollback
|  |  |  | End to end tests performed | Releasenotes
Non-functional tests performed
Known issues
Compatibility matrix
Software General Available
t = 0 |  | Release Definition Phase - Erasmus MC & Supplier
|  | Consensus about scope and timeline | Advise (scope, risks, impact en timeline) | Scope | GA-version(s)
|  |  | Compatibility matrix | Risks and impact | Releasenotes
|  |  | Software GA | Milestones and Go-live date | Installation manual
|  |  | Releasenotes | Resources available | Roll out plan (concept)
|  |  | Installation manual incl. rollback |  | FD and TD (concept)
Trained Service Engineers
Milestone: Approval on scope and date implementation production
|  | Deployment and test on Acceptance Environment |  |  |  | Acceptance
|  | Deployment according to rollout plan (draaiboek) | Rollout plan incl. rollback | Testresults, known issues (optional) | Rollout plan incl. rollback |  | Short communication lines with Supplier (in case of issues)
|  | System Integration Test incl. regression test | Testscipts SIT |  | Testscipts and testresults
|  | Rollback incl. regression test |  |  | FD and TD (final) |  | Complete release validated by Supplier
|  | Acceptance Tests Erasmus MC |  |  |  | Acceptance
|  | Deployment according to rollout plan (draaiboek) | Trained technical and functional specialists available | Software release-level | Rolloutplan incl. rollback
|  |  | Rolloutplan incl. rollback | Questions/issues/remarks raised and analyzed
FunctionalDesign incl. configuration, TechnicalDesign
|  | Acceptance tests | Testscripts ACC (incl. rollback, non-functional) | Testresults, known issues (optional) | Testscripts, -results and issues (in TFS) |  | Acceptance by application management and/or projectmembers Erasmus MC. Other acceptors/stakeholders if applicable
|  | Milestone: Go/No-Go (P) |  |  |  | Production
|  | Preparation Go-live |  |  |  | Production
|  |  |  | Business implementationplan if applicable | Rolloutplan incl. rollback definitive (P)
|  |  |  | Agreement support after Go-live | Checklist functional test (P)
Rolloutplan incl. rollback definitive (P)
|  | Go-live (P) |  |  |  | Production
|  | Deployment (P) according to rollout plan (draaiboek) | Trained technical and functional specialists available | New release fully operational
|  | Functional tests (P) | Rolloutplan incl. rollback definitive (P)
Active monitoring / after care
Evalation and project closure
|  | Milestone: project closure |  |  |  | Production
Regular maintenance

## RASCI
RASCI
Version: 0.9
Date: 08-08-2022
R | Responsible | Those who do the work to complete the task. There is at least one role with a participation type of responsible, although others can be delegated to assist in the work required.
A | Accountable | The one ultimately answerable for the correct and thorough completion of the deliverable or task, the one who ensures the prerequisites of the task are met and who delegates the work to those responsible. In other words, an accountable must sign off (approve) work that responsible provides. There must be only one accountable specified for each task or deliverable.
S | Support | Resources which play a supporting role in implementation. Who provides support during the implementation of the activity / process / service?
C | Consulted | Those whose opinions are sought, typically subject matter experts; and with whom there is two-way communication.
I | Informed | Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication.
# | Deliverable | Responsible | Accountable | Support | Consulted | Informed
| All Erasmus MC integrations tested | TBD | TBD | TBD | TBD | TBD
| General Available | … | … | … | … | …
| Compatibility matrix | … | … | … | … | …
| Installation Manual | .. | .. | .. | .. | ..
| Releasenotes | … | … | … | … | …
| Rolloutplan incl. rollback | … | … | … | … | …
| FD and TD | … | … | … | … | …
| Advise (scope, risks, impact en timeline) | … | … | … | … | …
| Resources available | … | … | … | … | …
| Approval on scope and date implementation production | … | … | … | … | …
| Trained Service Engineers | … | … | … | … | …
| Deployment and test on Acceptance Environment | … | … | … | … | …
| Acceptance Tests Erasmus MC | … | … | … | … | …
| Milestone: Go/No-Go (P) | … | … | … | … | …
| Deployment (P) according to rollout plan (draaiboek) | … | … | … | … | …
| Milestone: project closure | … | … | … | … | …