Client Representatives Geophysical Survey Doordewind Wind Farm Zone

Annex 8a

Scope of Work

Colophon

| Project name | Client Representatives Geophysical Survey Doordewind Wind Farm Zone |
| --- | --- |
| Project number | 202307200 |
| Version | Draft_03 |
| File name | VS_20230817_RVO_CR GP_Annex 8_Scope of Work_D03 |
| Project manager | S. Wezenberg |
|  | M. Witteveen |
| Author | S. Wezenberg |
| Reviewed | P. Lebbink |
| Approved | XXX |

Table of Contents

1	Introduction	5

1.1	Scope of this document	5

1.2	Contract Parties	5

1.3	Background	5

1.4	Site Description	5

1.5	Three tenders for Geophysical Survey Campaigns	7

1.6	Investigation Areas	8

1.7	Aims of the geophysical survey	11

1.8	Timing of the Investigations	11

1.9	Available Information	11

1.9.1	WFZ specific information	11

1.9.2	Other information	11

1.9.3	Geophysical Survey Tender	12

2	Scope of Work	13

2.1	Monitoring of Survey Activities	13

2.2	Health Safety Environmental and Quality monitoring	13

2.3	Number of Client Representatives	13

2.4	Requirements to Offshore Client representatives	14

2.5	Schedule of the Work	14

2.6	Mobilization / demobilization	15

2.7	Team set-up	15

2.8	Communication	16

2.9	Reporting	17

3	Survey Requirements	18

3.1	Requirements of the Survey Layout and Configuration 	18

3.2	Mobilization and demobilization	18

3.3	Lost Equipment	18

3.4	Testing	18

# Introduction

## Scope of this document

This document and its appendices detail the scope of the Work as part of the Contract that Client has awarded to Contractor for provision of Offshore Client Representatives during the geophysical survey at the Doordewind (DDW) Wind Farm Zone.

## Contract Parties

| Expert Contractor | BLIX Consultancy B.V. who has been awarded by Client to perform the technical due diligence related to soil at the DDW WFZ |
| --- | --- |
| Client Contracting Authority | Netherlands Enterprise Agency (RVO) Netherlands Enterprise Agency (RVO) |
| Offshore Client Representative (CR) | Person working for Contractor on the project of Client to monitor daily HSE, QC and progress for Client |
| Contractor | Contracting party which supplies the offshore client representatives as part of the Work |
| Survey Contractor | Contractor awarded by Client who will provide the survey vessels, equipment and personnel to perform the geophysical site investigation |

## Background

The Ministry of Economic Affairs and Climate Policy is responsible for the legislative framework for the development of offshore wind farms in the Netherlands. Within this framework (a) (concession) permit tender(s) for construction and operation of (a) wind farm(s) will be organized under the current regulation. As part of the tender documentation, the participants will receive an information package in which detailed information on the offshore site is included. Detailed information on the soil conditions at the site will be part of this information package.

Information on the soil conditions at the site is to be developed through a sequence of commissions for geological, geophysical, geotechnical and morphodynamical studies. Information will be presented as factual data, integrated and interpreted data (an Integrated Ground Model) and will be comprehensively reported.

The Integrated Ground Model is to be of sufficient precision to allow participants to make initial plans and costings for foundation design and cable installation.

This assignment is containing the request for Offshore Client Representatives to monitor the field works of the geophysical investigation.

## Site Description

Please see ‘Annex 9a: Starting Points and Assumptions’ for more details on general site characteristic.

## Three tenders for Geophysical Survey Campaigns

The Contracting Authority has chosen to split the planned geophysical survey campaign for the DDWWFZ into three Scopes of Work (SoW):

- Lot 1: the SoW for Seabed Survey (SS) focuses on a Seabed Survey in the eastern DDW Investigation Area (DDW-IA-Lot1). This lot encompasses a survey of 310 km2.

- Lot 2: the SoW for a 2D-UHRS survey and Seabed Survey (SS), focuses on a full coverage 2D-UHRS and Seabed Survey in the western DDW Investigation Area DDW-IA-Lot2. Moreover, it covers Seabed Sampling over both DDW-IA-Lot1 and DDW-IA-Lot2. This lot encompasses a survey of 268 km2.

- Lot 3: the SoW for 3D-UHRS survey, including MBES, focuses on a full coverage 3D-UHRS survey in the eastern DDW Investigation Area (DDW-IA-Lot3). This lot encompasses a survey of 310 km2.

With three SoWs, the Contracting Authority aims to provide an opportunity for various Survey Contractors to bid for one or a combination of these SoWs.

The Scopes of Work for survey contractors consist of the three DDW Lots covers three lots and separate investigation areas. Investigation area DDW-IA-Lot2 in the west, and DDW-IA-Lot1 and DDW-IA-Lot3 in the east. DDW-IA-Lot1 and DDW-IA-Lot3 are almost fully overlapping with the only difference that DDW-IA-Lot3 is slightly (10km2) smaller. The three investigation areas, and accompanying Lots, have different geophysical scopes as listed in Table 1.

Table 1 Division over Lots of geophysical surveys per Investigation Area.

The execution phase of the different Lots will run parallel between Q1 2024 and Q4 2024.

## Investigation Areas

It is the intention of the Contracting Authority to obtain a single, comprehensive set of geophysical data, reports, and drawings for the Doordewind Investigation Areas. For the DDWWFZ the Investigation Areas cover the area to be occupied by the Wind Farm Zone (WFZ). Table 2 represents the coordinates of the Investigation Areas to be surveyed to specification by the survey contractor(s) within the three Lots. The IAs for this tender are presented in Figure 1.

Table 2 Coordinates of the vertices of DDW-IA-Lot1, DDW-IA-Lot2, and DDW-IA-Lot3 for the Geophysical Surveys for Doordewind WFZ

| Investigation Area DDW-IA-LOT1 (310 km2) |  |  |  |
| --- | --- | --- | --- |
| Coordinates according EPSG 25831 |  |  |  |
| Point No. | Easting |  | Northing |
| SS_IA_01 | 654713,6 |  | 6035963,4 |
| SS_IA_02 | 687376,6 |  | 6013454,6 |
| SS_IA_03 | 674986,6 |  | 6011203,8 |
| SS_IA_04 | 650456,1 |  | 6027944,9 |
| SS_IA_05 | 650459,1 |  | 6028068,5 |
| Investigation Area DDW-IA-LOT2 (268 km2) |  |  |  |
| Coordinates according EPSG 25831 |  |  |  |
| Point No. |  | Easting | Northing |
| 2D_IA_01 |  | 650459,1 | 6028068,5 |
| 2D_IA_02 |  | 675126,0 | 6011229,1 |
| 2D_IA_03 |  | 651377,0 | 6006914,0 |
| 2D_IA_04 |  | 649971,0 | 6006646,0 |
| Investigation Area DDW-IA-LOT3 (310 km2) |  |  |  |
| Coordinates according EPSG 25831 |  |  |  |
| Point No. |  | Easting | Northing |
| 3D_IA_01 |  | 654758,4 | 6035783,5 |
| 3D_IA_02 |  | 687040,2 | 6013535,8 |
| 3D_IA_03 |  | 674988,3 | 6011323,1 |
| 3D_IA_04 |  | 650565,2 | 6027994,7 |

A single tie-line between the seabed surveys of Lot1 (DDW-IA-Lot1) and Lot2 (DDW-IA-Lot2) is requested by Client and shall be offered by the survey contractor. The tie-line has a planned length of 30km. See SOW GP survey contractor for more details.

Figure 1 DDW-IA-Lot1, DDW-IA-Lot2, and DDW-IA-Lot3 to be surveyed during the geophysical campaigns within the three Lots at the DDWWFZ. DDW-IA-Lot1: vertical green stripes: 310 km2. DDW-IA-Lot2: horizontal blue stripes: 268 km2. DDW-IA-Lot3: diagonal purple stripe.

## Aims of the geophysical survey

The aim of the geophysical soil investigations carried out by the survey contractor(s) is to contribute to the geological understanding of Doordewind Wind Farm Zone. The investigation is required to obtain seabed and sub-seabed information. The information is in turn required to be suitable for the planning and preparation of geotechnical investigations, and suitable for integration into a ground model of sufficient quality to progress the design and installation requirements for offshore wind farms, including, but not limited to, foundations and cables.

The investigation is expected to provide:

• An accurate bathymetric dataset.

• Information describing all seabed features of significance to the construction of wind farm facilities including but not limited to:

- Sea floor sediments, their variation and morphology;

- Any natural features such as boulders, scour hollows, pockmarks;

- Any non-natural features such as wrecks and debris (both known and previously unmapped), pipelines, cables, trawl-marks, and infrastructure.

• Sub-Seabed datasets of sufficient penetration and quality to support construction of a ground model, with resolution and signal-to-noise ratio optimized for production of a Preliminary Ground Model (PGM).

• The current position of existing (in service & out of service) cables and pipelines.

• A comprehensive Final Interpretation Report on the survey results obtained, which will be used as input to the PGM.;

The output of the investigation shall be delivered in formats defined in the scope of work including digital data, Seismic Interpretation System Package and Geographic Information System project filesystems, chart data, and reports.

The Geophysical Survey follows and receives information from the Geological, Archaeological and UXO Desk Studies, and it is expected to precede and supply information to a geotechnical investigation, an Integrated Ground Model (IGM, integrating the results of Geological, Geophysical and Geotechnical investigations) and a morphodynamical investigation.

## Timing of the Investigations

The data acquisition for the geophysical survey (all Lots) shall be carried out in Q1-Q4 2023.

## Available Information

### WFZ specific information

Client will carry out desk studies on DDWWFZ. The following desk studies will be available on https://offshorewind.rvo.nl from the end of 2024:

- Geological desk study;

- Archaeological desk study;

- UXO desk study.

### Other information

Further, for information, the results of the geophysical and geotechnical surveys carried out for other Wind Farm Zones are available at https://offshorewind.rvo.nl/. It should be noted that this scope of work deviates from those of previous investigations and the current geophysical work may introduce additional requirements.

### Geophysical Tender

Client has published the tenders to select the survey contractor. Information regarding the requirements set for the survey contractor can be found in the tender documents by link below.

Link to tender documents published at Tenderned for the DDW geophysical tender: Geophysical survey at the offshore Doordewind Wind Farm Zone - Details - TenderNed

# Scope of Work

This section describes the Scope of Work for the CR. Details of the Survey works are presented in Section3.

## Monitoring of Survey Activities

The CR will monitor the field works performed by the Survey Contractor during the execution of the works. The CR will have the task to monitor safety, quality and progress of the data acquisition. The geophysical survey works will consist of the following:

- A seabed survey (SS), which includes MBES, MAG, SSS and SBP.

- A Full 2D-UHRS survey, which includes MBES, MAG, SSS, SBP and 2D UHRS.

- Seabed sampling by means of grab samples (56 in total).

- A 3D-UHRS survey (incl. MBES).

As such, the Offshore Client Representatives should have experience with:

- High resolution bathymetric and backscatter survey

- High resolution side scan sonar survey

- Magnetometer survey

- Shallow Penetration Sub-Bottom Profiler (SBP) survey

- 2D Multi-Channel Ultra High-Resolution Seismic (2D-UHRS) profiling survey

- Two (2) of the ten (10) offered CRs should have experience with 3D Multi-Channel Ultra High-Resolution Seismic (3D-UHRS) profiling survey.

## Health Safety Environmental and Quality monitoring

The CR will monitor daily the Health, Safety, Environmental and Quality (HSEQ) of the works performed by the Survey Contractor. The CR will assess if the Survey Contractor is working according their own HSEQ procedures and as per the requirements as set by Client. Reference is made to the HSE and Quality requirements as set in the tender for the Survey Contractor.

Furthermore, the CR will monitor if  the Survey Contractor respects the criteria, which will be provided as part of the exemption for underwater noise, which are likely to include;

- Use of Acoustic Deterrent Device (ADD) for porpoises, before sub-bottom profilers will be turned on.

- Soft start procedure of the sub-bottom equipment with description of duration and power settings of the equipment to allow porpoise mammals to leave site.

## Number of Client Representatives

Client expects the Survey Contractors will work with a different number of vessels for the execution of the different LOTs within the geophysical survey:

For the Seabed Survey (LOT 1) one (1) to two (2) vessels are expected to perform the work, with the possibility that the works might be performed by Unmanned Survey Vessel (USVs). For the full 2D UHRS survey (LOT 2) one (1) to two (2) vessels are expected to perform the work. For the 3D UHRS survey (LOT 3) one vessel is expected to perform the work.

For each vessel one (1) CR shall be available on the vessel and will work in a 12 hour shift. In case USVs are deployed the CR will be required to monitor multiple USVs simultaneously during the 12 hour shift. Sufficient personnel should be available to allow for CR change-outs (e.g., during crew changes).

The duration of rotations between crew changes is to be determined by the Survey Contractor. The CR rotation schedule shall be based on the Survey Contractor’s rotation plan. Client expects a possibility to change CR each 3-5 weeks.

Client requests Tenderers  to submit ten (10) CRs during the tender phase, who are able to perform the work. CRs will be selected from the offered CR pool during the scheduled work. For clarity, not all ten CRs are expected to perform the works simultaneously, but according to the schedule of the GP Survey Contractors.

## Schedule of the Work

Duration of the Work will be depending on the workability, the amount and efficiency of the vessels as provided by the Survey Contractor.

The Surveys will start in Q1 2024 and will continue until Q4 2024. Client expects starting date of the mobilization in March 2024 at the earliest. However, the CR should be present (preferably in person) during the technical Kick off-meeting, approximately three weeks before the start of work, as well as being able to perform a review on the project documentation.

For the purpose of this Scope of Work a total number of 200 vessel days are expected.

The timeline specifying the starting date of the offshore works for which the CR need to be made available, will be defined as follows:

- Client will as soon as possible provide information on the indicative period in which the survey will take place.

- One month before the intended start of the offshore works, Client will provide a best estimation of the mobilisation date and location.

- One week before the intended start of the offshore works, Client will provide an update with best estimation of the mobilisation date and location.

- After award of the contract with the Survey Contractors, a more detailed overall planning can be made with the winner of this tender.

After the start of the Work notifications on the exact crew change date will be provided by Client as follows:

- One week before crew change, the crew change date can be specified with a precision of 2 days;

- 48 hours before crew change, the exact crew change date shall be specified.

One or two months prior to the start of the campaign, a kick-off meeting is held between Client and Survey Contractor. At least one of the CRs who will join the first rotation on the vessel is requested to attend this meeting in person in order to learn and give input on the campaign strategy. In case other CRs cannot attend the meeting, the attending CR will brief the other CRs on the content. If the attending CR is not available at the start of the campaign, the substitute CR should be briefed on the content of this meeting as well.

## Mobilization / demobilization

Contractor shall arrange all travel arrangements from and towards the mobilization port set by the Survey Contractor.

Travel arrangements include:

  - Flight / train or other travel costs

  - Hotel and foods

  - Mandatory vaccinations if applicable / test to be able to travel

Client expects the mobilization port of the Survey Contractor to be within the Netherlands.

## Team set-up

The Client has organized the project set-up within the Doordewind investigations by splitting the works of Wind & Water investigations and Soil investigations. The Geophysical survey is part of the Soil site investigation.

The Soil site investigation for DDW is managed by RVO project managers together with a team of contracted experts. The package is set up under supervision of a package manager from RVO overseeing all the studies related to soil for DDW. The RVO package manager is supported by a lead expert who is involved as well in all studies. Both the package manager as the lead expert will manage all interfaces between the studies. The Geophysical survey will be managed by an RVO project manager who is supported by a team of contracted experts with in-depth knowledge related to the study. Organogram of the project set-up is presented in Figure 2.

The position of the CR in the organogram is highlighted red.

Figure 2. Organogram soil package Doordewind

## Communication

The communication lines are based on the team organization as presented in Section 2.7. The communication from the CR shall always include the RVO project manager and related expert(s). The expert team will advise together with the RVO project manager on any queries from the CR regarding to contract, HSEQ and or progress. The CR shall discuss queries during the WORK with Client’s on-shore team, consisting of the RVO project manager and the Expert Contractor. For the CR first point of communications is presented as below:

      - Contractor; Travel arrangements

      - RVO project manager; for planning, contractual items and approval of travel arrangements

      - Lead Expert; for technical questions and data acquisition

Figure 3 presents the communication lines within the Doordewind Geophysical investigation with the position of the CR indicated in red.

Figure 3. Communication lines

## Reporting

The reporting requirements for the geophysical survey work are as follows:

Daily & Weekly reporting

The Survey Contractor is to submit daily reports throughout the period of the fieldwork, providing full details of previous 24 hours’ work and results.

The Survey Contractor may be requested by the Client to provide Data Quality Reports (“DQR”) when appropriate. The DQR will not have to be provided on a daily basis but the Survey Contractor must be prepared to compile and provide these reports under the supervision of the CR. Content of standardised elements of DQRs is to be established at the TKOM (Technical Kick Off-Meeting).

The CR will issue a daily update to the Client including:

  - Summary of works completed last 24 hours

  - Planning upcoming 24 hours

  - HSE items of last 24 hours

  - Quality items of last 24 hours

  - Any observations and/or notes

Furthermore, the CR will participate in short progress meetings with Client and Survey Contractor, three (3) times a week (vessel progress calls).

Client also suggests to have an internal call between CR and Client to get a short update on works one (1) time a week (internal vessel progress call).

# Survey Requirements

The CR shall monitor the field works as performed by the Survey Contractor. This section describes the main requirements of the survey components. Detailed information can be found in the Scope of Work for the Survey Contractor.

Link to tender documents published at Tenderned for the DDW geophysical tender: Geophysical survey at the offshore Doordewind Wind Farm Zone - Details - TenderNed

## Requirements of the Survey Layout and Configuration

It is anticipated that the acquisition of geophysical, hydrographic and environmental datasets may involve one or more passes across the IA. The Survey Contractor shall select their optimum survey layout and acquisition configuration (e.g. single or multiple passes, single- or multi-vessel solution) to achieve the survey objectives and data quality requirements.

## Mobilization and demobilization

Mobilization of the vessel(s) to the site will be considered completed when all necessary survey and Project Documentation, equipment, critical spares and personnel are accepted as operational to the specification agreed by the Client and approved by the Client. Verification of performance shall be made according to an agreed plan with all required testing and calibration of vessel and equipment (defined during TKOM) documented and signed off (this is regarded as part of the mobilization).

The harbour to be used for mobilization of survey vessel(s), equipment and personnel is chosen by the Survey Contractor with approval of the Client.

Demobilization of the vessel will be authorised when all the data required have been acquired and have passed field QA & QC criteria to the satisfaction of the CR.

## Lost Equipment

Survey Contractor shall be responsible at his own cost for marking the location and recovery of equipment dropped or lost during the execution of the project.  Survey Contractor shall mark the positions of equipment on or below the seabed with marker buoys if necessary and recover the equipment at the earliest possible opportunity.  All equipment shall be removed to a reference level which is the trough of mobile sand waves in the area.

## Testing

Following mobilization, a testing phase shall be implemented to establish the appropriate configuration and parameterisation of data acquisition equipment and finalisation of the survey QA parameters. Where data processing operations are critical to either in-field QA/QC or evaluation of the suitability of the data acquisition configuration, design and parameterisation of these operations shall be part of the testing phase.

A testing programme shall be agreed as part of the planning phase, and should include the collection of data properly representative of the range of ground conditions at the site. Provision shall be made for tests to be evaluated by both CR and Quality experts onshore.

The CR shall not sign off for mobilization unless the testing phase is considered completed and approved for, in close consultation with Client and onshore quality experts.

Acceptance by Client of data acquisition configuration is expected to take place as soon as possible after mobilization and testing. Production data acquired prior to acceptance of the data acquisition configuration is acquired at the Survey Contractor’s risk, shall be subject to rigorous QC and may be rejected by the CR.

During the Testing phase and first data acquisition Client will have the option to send one of the experts to join the vessel for the first one – two weeks to assist the CR with the set-up and first data collection.

If works are performed by means of Unmanned Service Vessels (USVs) RVO and GP Contractor will need to define in the lead up to the WORKS how CRs will perform their activities. There is a possibility that GP Contractor will offer CR to perform works at their base of operation or the CR might be requested to work from home.