Client Representatives Geotechnical Survey Nederwiek noord Wind Farm Zone

Annex 8b

Scope of Work

Colophon

| Project name | Client Representatives Geotechnical Survey Nederwiek noord Wind Farm Zone |
| --- | --- |
| Project number | 202307200 |
| Version | Draft_03 |
| File name | VS_20230817_RVO_CR GT_Annex 8_Scope of Work_D03 |
| Project manager | S. Wezenberg |
|  | M. Witteveen |
| Author | S. Wezenberg |
| Reviewed | P. Lebbink |
| Approved | XXX |

Table of Contents

1	Introduction	4

1.1	Scope of this document	4

1.2	Contract Parties	4

1.3	Background	4

1.4	Site Description	4

1.5	Two tenders for Geotechnical Campaigns	5

1.6	Investigation Area	5

1.7	Aims of the geotechnical survey	6

1.8	Timing of the Investigations	7

1.9	Available Information	7

1.9.1	WFZ specific information	7

1.9.2	Other information	8

1.9.3	Geotechnical Tender	8

2	Scope of Work	9

2.1	Monitoring of Survey Activities	9

2.2	Health Safety Environmental and Quality monitoring	9

2.3	Number of Client representatives	9

2.4	Know how requirements for offered Offshore Client Representatives	10

2.5	Schedule of the Work	10

2.6	Mobilization / demobilization	11

2.7	Team set-up	11

2.8	Communication	12

2.9	Reporting	13

3	Survey Requirements	14

3.1	Requirements for Geotechnical survey works 	14

3.2	Mobilization and demobilization	15

3.3	Lost Equipment	15

# Introduction

## Scope of this document

This document and its appendices detail the scope of the Work as part of the Contract that Client has awarded to Contractor for provision of Offshore Client Representatives during the geotechnical survey at the Nederwiek noord (NWN) Wind Farm Zone.

## Contract Parties

| Expert Contractor | Arcadis Nederland B.V. who has been awarded by Client to perform the technical due diligence related to soil |
| --- | --- |
| Client Contracting Authority | Netherlands Enterprise Agency (RVO) Netherlands Enterprise Agency (RVO) |
| Offshore Client Representative (CR) | Person working for Contractor on the project of Client to monitor daily HSE, QC and progress for Client |
| Contractor | Contracting party which supplies the offshore client representatives as part of the Work |
| Survey Contractor | Contractor awarded by Client who will provide the survey vessels, equipment and personnel to perform the geotechnical site investigation |

## Background

The Ministry of Economic Affairs and Climate Policy is responsible for the legislative framework for the development of offshore wind farms in the Netherlands. Within this framework (a) (concession) permit tender(s) for construction and operation of (a) wind farm(s) will be organized under the current regulation. As part of the tender documentation, the participants will receive an information package in which detailed information on the offshore site is included. Detailed information on the soil conditions at the site will be part of this information package.

Information on the soil conditions at the site is to be developed through a sequence of commissions for geological, geophysical, geotechnical and morphodynamical studies. Information will be presented as factual data, integrated and interpreted data (a Ground Model) and will be comprehensively reported.

This assignment is containing the request for Offshore Client Representative to monitor the field works of the geotechnical investigation.

## Site Description

Please see ‘Annex 9b: Starting Points and Assumptions’ for more details on general site characteristic.

## Two tenders for Geotechnical Campaigns

The Contacting Authority has chosen to split the planned geotechnical survey campaign for the NWNWFZ into two Scopes of Work (SoW):

- Lot 1: the SoW for geotechnical survey contains a seabed CPT and vibrocore campaign at the Nederwiek Investigation Area including basic laboratory testing and reporting; and ecological water and soil sampling;

- Lot 2: the SoW for geotechnical survey contains a borehole campaign comprising borehole sampling, downhole in-situ testing and including of all basic and cyclic laboratory testing and reporting.

The size of the Investigation Areas for the Geotechnical Survey is approximately 400 km2.

With two SoWs, the Contracting Authority aims to provide an opportunity for various Survey Contractors to bid for one of the SOWs or the combined SOWs.

The execution phase of the different LOTs will run in sequence between Q1 2024 and Q4 2024. LOT1 will be executed first, followed by LOT2.

## Investigation Area

It is the intention of the Contracting Authority to obtain comprehensive set of geotechnical data, reports, and drawings for the Nederwiek noord Investigation Area. Table 1 represents the coordinates of the Investigation Area for the two LOTs. An overview of the Investigation Area is presented in Figure 1.

Table 1 Coordinates for Investigation Area Nederwiek noord.

| Nederwiek Wind Farm Zone noord coordinates |  |  |
| --- | --- | --- |
| Point No. | Easting | Northing |
| GT_IA_01 | 522313.6 | 5894778.0 |
| GT_IA_02 | 507039.2 | 5911494.3 |
| GT_IA_03 | 501892.9 | 5921837.6 |
| GT_IA_04 | 503352.4 | 5925523.5 |
| GT_IA_05 | 506453.8 | 5931232.7 |
| GT_IA_06 | 530982.3 | 5923941.9 |
| Coordinate system: ETRS_1989_UTM_Zone_31N |  |  |
| WKID: 25831 Authority: EPSG |  |  |

Figure 1 : Map of the Nederwiek Wind Farm Zone, including cables and pipelines. The Nederwiek noord IA for LOT1 and LOT2 is highlighted by the black dot-dashed line.

## Aims of the geotechnical survey

The overall objective of the geotechnical soil investigation is to collect factual geotechnical data that enables the creation of a Geotechnical Interpretive Report and Ground Model in order to improve the geological and geotechnical understanding of the Investigation Areas in NWNWFZ, suitable to progress the design and installation requirements for offshore wind farm including, but not limited to foundations and cables.

The objective of the investigation and laboratory testing programme is to:

- Determine the vertical and lateral variability in soil conditions;

- Provide relevant factual geotechnical data for the design including, but not limited to foundations and cables;

- Provide information on the ecological conditions at the Investigation Areas in NWNWFZ;

- Where applicable, supplement the findings of the geological desk study and the geophysical survey;

- Contribute to an Integrated Ground Model and Geotechnical Interpretative Report

Note that the development of the Integrated Ground Model may be executed by a different contractor than the Survey Contractor. Furthermore, the geotechnical works have been divided into two LOTs;

- LOT1: the Sow is a shallow geotechnical investigation (including PCPT’s, SCPT’s, thermal conductivity testing, vibrocores and ecological sampling),

- LOT2: the Sow is a borehole geotechnical investigation (including boreholes in combination with downhole sampling, downhole CPT’s and SCPT’s, P-S suspension logging, density logging, and downhole magnetic resonance logging).

These parts are also tendered in two lots, therefore these works may be executed by two different Survey Contractors. Further information on the geotechnical tender can be found at: Geotechnical surveys at Nederwiek Wind Farm Zone - Details - TenderNed (https://www.tenderned.nl/aankondigingen/overzicht/292670/details).

The laboratory test programme for determination of soil strength and deformation properties are to include different types and quantities of tests, but should permit preliminary foundation design to be performed and to establish a design basis for the detailed foundation design.

## Timing of the Investigations

The offshore shallow soil investigation campaign (investigation in seabed mode) is foreseen to be carried out from February 2024 until April 2024. An ecological survey will be supplementary to the geotechnical seabed investigation. The shallow geotechnical investigations are required to commence at NWNWFZ to enable timely input into the Integrated Ground Model for this area.

The offshore borehole geotechnical campaign will follow the offshore shallow soil investigation campaign .

It is anticipated that the borehole investigations shall commence from May 2024 to September 2024.

The borehole geotechnical investigation Survey Contractor can only commence at a borehole location once the shallow geotechnical investigations by Survey Contractor is finished.

## Available Information

### WFZ specific information

Client has carried out desk studies on the entire NWWFZ. The following desk studies are available on https://offshorewind.rvo.nl;

- Geological desk study;

- Archaeological desk study;

- UXO desk study.

For NWWFZ, the above desk studies can be provided to the CR(s) prior to the start of the field works.

### Other information

Further, for information, the results of the geophysical and geotechnical surveys carried out for other areas are available at https://offshorewind.rvo.nl/. It should be noted that this scope of work may deviate from those of previous investigations and may introduce additional requirements.

### Geotechnical Tender

Client has published the tenders to select the survey contractor. Information regarding the requirements set for the survey contractor can be found in the tender documents by link below.

Link to tender documents published at Tenderned for the geotechnical tender: Geotechnical surveys at Nederwiek Wind Farm Zone - Details - TenderNed (https://www.tenderned.nl/aankondigingen/overzicht/292670/details).

# Scope of Work

This section describes the Scope of Work for the CR. Details of the Survey works are presented in section 3.

## Monitoring of Survey Activities

The CR will monitor the field works performed by the Survey Contractor during the execution of the works. The CR will have the task to monitor safety, Quality and progress of the data acquisition.

The shallow geotechnical investigations shall consist of a combination of sampling with subsequent laboratory testing and in situ testing. Both data acquisition techniques must provide geotechnical insights. The works comprise the following tasks;

- Seabed cone penetration tests (CPT) using standard piezocones (PCPT) and seismic cones (SCPT);

- Dissipation tests during seabed PCPT;

- Thermal conductivity testing using a thermal cone penetrometer, FIELAX Vibroheat or similar as proposed by the Contractor;

- Vibrocore sampling;

- Ecological soil and water sampling.

- Associated operational and factual reporting (results to be presented in “Seabed Sampling Report” and “Seabed In Situ Testing Report”, each of which covers the whole site;

- Delivery of associated digital data

The borehole geotechnical investigation of the Investigation Areas shall consist of a combination of sampling and in situ testing followed by laboratory testing. Both data acquisition techniques must provide geotechnical insights. The works comprise the following tasks;

- Boreholes with a combination of downhole sampling, downhole PCPT and downhole SCPT;

- P-S suspension logging, density logging, spectral gamma ray logging, and downhole magnetic resonance logging tests in completed boreholes;

- Associated reporting;

- Delivery of associated digital data.

## Health Safety Environmental and Quality monitoring

The CR will monitor daily the Health, Safety, Environmental and Quality (HSEQ) of the works performed by the Survey Contractor. The CR will assess if the Survey Contractor is working according their own HSEQ procedures and as per the requirements as set by Client.

## Number of Client representatives

Client expects the Survey Contractors will work with one (1) vessel simultaneously. However, there is a very small possibility that the two lots overlap for a short period of time, so this possibility has to be accounted for when planning for CR availability. For each vessel two (2) CRs shall be available on the vessel and the CRs will work in rotating a 12 hour shift.

The duration of rotations between crew changes is to be determined by the Survey Contractor. The CR rotation schedule shall be based on the Survey Contractor’s rotation plan. Client expects a possibility to change CR each 2-4 weeks.

Client requests Tenderers  to submit ten (8) CRs during the tender phase, who are able to perform the work. CRs will be selected from the offered CR pool during the scheduled work. For clarity, not all ten CRs are expected to perform the works simultaneously, but according to the schedule of the GT Survey Contractors.

## Know how requirements for offered Offshore Client Representatives

Requirements relating to Personnel offered in the role as CR for the geotechnical survey. The personnel involved in the executing of the work, must have:

- Experience with the execution of geotechnical soil investigations carried out for offshore wind projects, including:

  - (Deep) CPTs between 10 meters to 60 meters;

    - Standard PCPTs;

    - Temperature CPTs;

    - Seismic cone CPTs;

    - Seismic seabed CPTs

  - Performing performance dissipation tests during seabed PCPT tests and in situ thermal conductivity tests using a cone

  - Executing vibrocores.

  - Obtaining ecological soil and water samples.

  - Drilling boreholes with a combination of sampling, downhole piezocone penetration tests (PCPT) and downhole seismic cone penetration tests (SCPT) to at least target depth of between 60m and 80m.

    - This includes P-S logging, Density logging, spectral gamma ray logging and downhole magnetic resonance logging.

    - Oversampling of a PCPT or SCPT stroke.

  - Preparation of borehole log and borehole laboratory testing schedule after borehole completion.

  - Other projects for which similar investigations are carried out, and have proven in depth knowledge on technical and contractual issues relevant for these works;

## Schedule of the Work

Duration of the Work will be depending on the workability, the amount and efficiency of the vessels as provided by the Survey Contractor.

The Survey will start in February 2024 and will, in stages, continue until September 2024. Client expects starting date of the mobilization in January 2024 at the earliest.

For the purpose of this Scope of Work a number of 200 vessel days is expected, divided over the two LOTs, with an estimation of one vessel performing the works per LOT.

The timeline specifying the starting date of the offshore works for which the CR need to be made available, will be defined as follows:

- Client will as soon as possible provide information on the indicative period in which the survey will take place.

- One month before the intended start of the offshore works, Client will provide a best estimation of the mobilisation date and location.

- One week before the intended start of the offshore works, Client will provide an update with best estimation of the mobilisation date and location.

- After award of the contract with both Survey Contractors, a more detailed overall planning can be made with the winner of this tender.

After the start of the Work notifications on the exact crew change date will be provided by Client as follows:

- One week before crew change, the crew change date can be specified with a precision of 2 days;

- 48 hours before crew change, the exact crew change date shall be specified.

One or two months prior to the start of the campaign, a kick-off meeting is held between Client and Survey Contractor. At least one of the CRs who will join the first rotation on the vessel is requested to attend this meeting in person in order to learn and give input on the campaign strategy. In case other CRs cannot attend the meeting, the attending CR will brief the other CRs on the content. If the attending CR is not available at the start of the campaign, the substitute CR should be briefed on the content of this meeting as well.

## Mobilization / demobilization

Contractor shall arrange all travel arrangements from and towards the mobilization port set by the Survey Contractor.

Travel arrangements include:

  - Flight / train or other travel costs

  - Hotel and foods

  - Mandatory vaccinations if applicable / test to be able to travel

Client expects the mobilization port of the Survey Contractor to be within the Netherlands.

## Team set-up

The Client has organized the project set-up within the Nederwiek investigation by splitting the works of Wind & Water investigations and Soil investigations. The Geophysical survey is part of the Soil site investigation.

The Soil site investigation for NWN is managed by RVO project managers together with a team of contracted experts. The package is set up under supervision of a package manager from RVO overseeing all the studies related to soil for NW. The RVO package manager is supported by a lead expert who is involved as well in all studies. Both the package manager as the lead expert will manage all interfaces between the studies. The Geophysical survey will be managed by an RVO project manager who is supported by a team of contracted experts with in-depth knowledge related to the study.

Organogram of the project set-up is presented in Figure 2.

The position of the CR in the organogram is highlighted red.

Figure 2 Organogram soil package

## Communication

The communication lines are based on the team organization as presented in section 2.7. The communication from the CR shall always include the RVO project manager and related expert(s). The expert team will advise together with the RVO project manager on any queries from the CR regarding to contract, HSEQ and or progress. The CR shall discuss queries during the WORK with Client’s on-shore team, consisting of the RVO project manager and the Expert Contractor. For the CR first point of communications is presented as below:

      - Contractor; Travel arrangements

      - RVO project manager; for planning, contractual items and approval of travel arrangements

      - Lead Expert; for technical questions and data acquisition

Figure 3 presents the communication lines within the Nederwiek Geotechnical investigation with the position of the CR indicated in red.

Figure 3 Communication lines

## Reporting

The reporting requirements for the geophysical survey work are as follows:

Daily & Weekly reporting

The Survey Contractor is to submit daily reports throughout the period of the fieldwork, providing full details of previous 24 hours’ work and results.

The Survey Contractor may be requested by the Client to provide Data Quality Reports (“DQR”) when appropriate. The DQR will not have to be provided on a daily basis but the Survey Contractor must be prepared to compile and provide these reports under the supervision of the CR. Content of standardised elements of DQRs is to be established at the TKOM (Technical Kick Off-Meeting).

The CR will issue a daily update to the Client including:

  - Summary of works completed last 24 hours

  - Planning upcoming 24 hours

  - HSE items of last 24 hours

  - Quality items of last 24 hours

  - Any observations and/or notes

Furthermore, the CR will participate in short progress meetings with Client and Survey Contractor, three (3) times a week (vessel progress calls).

Client also suggests to have an internal call between CR and Client to get a short update on works one (1) time a week (internal vessel progress call).

# Survey Requirements

The CR shall monitor the field works as performed by the Survey Contractor. This section describes the main requirements of the survey components of Client and Survey Contractor. Detailed information can be found in the Scope of Work for the geotechnical survey contractor: Geotechnical surveys at Nederwiek Wind Farm Zone - Details - TenderNed  (https://www.tenderned.nl/aankondigingen/overzicht/292670/details).

## Requirements for Geotechnical survey works

The requirements for the shallow geotechnical investigation (LOT1 of geotechnical investigation) are as follows:

- Carry out seabed CPT with a target depth of 60m, using either a standard piezocone penetrometer (PCPT) or a seismic cone (SCPT). Minimal CPT length of at least 25m corrected vertical penetration.

- Seismic seabed CPTs (SCPT) at a target depth of 60m.

- Perform in situ thermal conductivity tests using a cone (or similar method) at selected locations for subsea electrical cable design.

- Perform dissipation tests during seabed PCPT tests.

- Perform vibrocore at selected locations for the purpose of subsea electrical cable design with a minimal recovery of 3 and 6 meters below the subsea bed.

- Ecological soil and water samples to collected base line ecological information.

The requirements for the borehole geotechnical investigation are as follows:

- Drilling boreholes with a combination of sampling, downhole piezocone penetration tests (PCPT) and downhole seismic cone penetration tests (SCPT) to a target depth of between 60m and 80m. The boreholes can be sub-divided into three types, as follows:

  - Type 1 - where the sampling/testing regime consists of quasi-continuous sampling from seabed to a predetermined depth following by a combination of sampling and PCPT to a target depth of 60-80m. The main purpose is to obtain general soil data (i.e. samples and PCPT) for developing geological and engineering soil models.

  - Type 2 – where the sampling/testing regime consists of quasi-continuous SCPTs carried out to a target depth of 60m or the depth at which the seismic signal is no longer strong enough to provide reliable results. The main purpose of the Type 2 borehole is to obtain in situ shear wave velocity measurements for deriving the small-strain shear modulus.

  - Type 3 –boreholes drilled purely for the purpose of extending a seabed CPT from the shallow geotechnical investigation to a depth of 60m because of the shallow refusal depth of the seabed CPT.

  - P-S logging, density logging, spectral gamma ray logging and downhole magnetic resonance logging is to be performed in selected Type 1 boreholes.

  - In some of the Type 1 or Type 3 boreholes, selected downhole PCPTs may be replaced with downhole SCPTs.

  - For any of the borehole types, oversampling of a PCPT or SCPT stroke to verify the soil material type being tested;

  - Preparation of borehole log and borehole laboratory testing schedule after borehole completion.

## Mobilization and demobilization

Mobilisation of the vessel(s) to the site, complete with all necessary geotechnical equipment and personnel. Survey Contractor shall include sufficient consumables and equipment spares in the mobilisation plan to allow for any foreseeable events. Survey Contractor shall indicate the proposed port of mobilisation/demobilisation as well as the number of port calls foreseen during the survey.

The Client requires a port call approximately every four weeks (as a minimum) for Offshore Client Representative crew changes (applies to Lots 1 and 2 of the Survey Works).

The Client requires a regular transport of soil samples to laboratory, typically biweekly, (applies to Lots 1 and 2). In addition, Survey Contractor shall make use of any periods of weather standby to undertake such port calls to facilitate offload and transport of samples.

The harbour to be used for mobilisation of survey vessel(s), equipment and personnel shall be approved by the Client.

Demobilization of the vessel will be authorised when all the data required have been acquired and have passed field QA & QC criteria to the satisfaction of the CR.

## Lost Equipment

Survey Contractor shall be responsible at his own cost for the marking the location and recovery of equipment dropped or lost during the execution of the project.  Survey Contractor shall mark the positions of equipment on or below the seabed with marker buoys if necessary and recover the equipment at the earliest possible opportunity.  All equipment shall be removed to a reference level which is the trough of mobile sand waves in the area.