## Revision log
Revision log |  |  | Annex 4a - Lot 1
The main/ relevant updates related to a new revision are listed below. Minor editorial updates are not listed below.
The line or cell numbers refer to this revision, they could differ from a previous revision due to addition or removal of lines
Revision | Date | Tab | Explanation
1 | 2024-04-05 | Cycle times & Prices | General: Some locked cells that were supposed to be unlocked have been unlocked; Some unlocked cells that were supposed to be locked have been locked.
1 | 2024-04-05 | Cycle times & Prices | Lines 17-20: The values for Hs, Vw and Ww that could be selected per vessel have been updated (in line with the table on tab "U10-wave")
1 | 2024-04-05 | Cycle times & Prices | Commencement date (L25) updated (from 15 July to 17 July)
1 | 2024-04-05 | Cycle times & Prices | Date for "CLIENT provision of first set of target coordinates of seabed CPTs/VCs" (cell L25) updated (from 15 January 2025 to 01 October 2024)
1 | 2024-04-05 | Cycle times & Prices | Line 35 added: Clearance of borehole locations
1 | 2024-04-05 | Cycle times & Prices | Lines 110 & 117 (3.12 and 3.18) text edited (method removed, shall be in accordance with ISO standards)
1 | 2024-04-05 | Cycle times & Prices | Line 193: Note III.0 Terminology slightly adjusted
1 | 2024-04-05 | Cycle times & Prices | Lines 126-134 (Lab tests/ Archeological dating): Unit and quantities updates (now defined per m instead of per sample, resulting in 6*6 = 36 tests per test type/ per line item)
1 | 2024-04-05 | Remuneration Table | Entire tab has been removed
2 | 2024-04-12 | Cycle times & Prices | Archeological dating tests quantities have been adjusted (item 3,26-3,34).
2 | 2024-04-12 | Cycle times & Prices | Item 2g: terminology adjusted (removal clearance "borehole" location).
2 | 2024-04-12 | Cycle times & Prices | Item 6.2, quantities updated. Total of 192 locations need ALARP clearance.
2 | 2024-04-12 | Cycle times & Prices | Maximum price has been adjusted from 11.000.000EUR to 12.100.000EUR. Minimum price has remained the same.
3 | 2024-04-18 | Cycle times & Prices | Item 1a, "COMMENCEMENT DATE WORK set by CLIENT" changed from 17-7-2024 to 22-7-2024 to represent changes in the tender planning and commencement date of the contract.
3 | 2024-04-18 | Cycle times & Prices | Item 2g "Clearance of locations (days after CLIENT issues first target locations: see 1b & continuously afterwards)" maximum days changed from 14 weeks to 14 days.
4 | 2024-05-13 | Cycle times & Prices | Row 87 containing item 2.6 was hidden in Annex 4a LOT 1 revision 3. Row was a duplication of item 2.5 and was deleted.
4 | 2024-05-13 | Cycle times & Prices | Item 2.5 wording changed from "Seabed SCPT performance excluding seismic tests for depths between 0-60 m" to Seabed SCPT performance including seismic tests for depths between 0-60 m

## Cycle times & prices
VIRTUAL CYCLE TIME & PRICE GEOTECHNICAL SURVEY - LOT 1
Project: | Geotechnical Survey - Doordewind Wind Farm Zone
Tenderer: | Tenderer name | [9 empty] | Error message if no price in remuneration section
Originator: | Originator name
[10 empty] | Note | FILL UNIT RATE
I. Doordewind Wind Farm Zone Geotechnical Investigation Area and Number of Tests | [9 empty] | I.0
Test type - Description |  |  |  |  | Target depth (m bsf) |  | Total Number | Short name
Seabed Cone Penetration Tests with Pore pressure measurement |  |  |  |  | 60 |  | 96 | SB PCPT
Seabed Seismic Cone Penetration Tests |  |  |  |  | 60 |  | 32 | SB SCPT
Dissipation test performed during PCPT or SCPT testing, (total no of hours) |  |  |  |  | 60 |  | 34 | DT
Thermal conductivity tests (test every meter by location) |  |  |  |  | 6 |  | 32 | TC
Vibrocores |  |  |  |  | 6 |  | 64 | VC
Thermal Conductivity Test (in hours per test) | [6 empty] | 0.25 | TC
Percentage retest | [6 empty] | 10%
II. Vessels used for which equipment & Limiting condition and required weather window | [5 empty] | Hs (m) | Vw (m/s) | Ww (hrs) |  | II.0
Required | Name of vessel A | [8 empty] | II.1 | Hs [m] | Vw [m/s] | Ww [hr]
Optional | Name of vessel B
Optional | Name of vessel C | [9 empty] | 0.5 | 2 | 1 | updated 29-3-2024 by Hugo
Optional | Name of vessel D | [9 empty] | 0.75 | 4 | 2
| PCPT: Piezoelectric Cone Penetration Test ¦ SCPT: Seismic Cone Penetration Test ¦ DT: Dissipation Testing ¦ TC: Thermal Conductivity and Shallow CPT ¦ VC: Vibrocoring | [9 empty] | 1 | 6 | 4
[11 empty] | 1.25 | 8 | 6
III. Cycle Time Geotechnical Survey (excluding weather) |  |  |  | Max duration (days) | Unit | Cycle | Qty | Total (days) | (end) date | III.0 | 1.5 | 9 | 12
Key dates | [10 empty] | 1.75 | 10 | 18
1a | COMMENCEMENT DATE WORK set by CLIENT | [7 empty] | 2024-07-22 |  | 2 | 11 | 24
1b | CLIENT provision of first set of target coordinates of seabed CPTs/VCs | [7 empty] | 2024-10-01 |  | 2.25 | 12 | 48
Preparation | [9 empty] | III.1 | 2.5 | 15 | 72
2a | 1st revision of project documentation (PQP, PEP) | [5 empty] | Fill in date; INVALID IF COLOURED RED: Cannot start before Commencement date work (see 1a) |  |  |  | 2.75 | 20
2b | CLIENT Review 1st revision project documentation (PQP, PEP) |  |  |  | days | 14 |  |  |  | III.1 | 3 | 25
2c | 2nd revision of project documentation (PQP, PEP) |  | (Max: 3 weeks) | 21 | days |  | Fill number of days |  |  | III.1 | 3.25
2d | CLIENT Review 2nd revision project documentation (PQP, PEP) |  |  |  | days | 14 |  |  |  |  | 3.5
2e | Finalise project documentation (incl additional revisions/review rounds) |  | (Max: 3 weeks) | 21 | days |  | Fill number of days |  |  |  | 3.75
| Shall be earlier than 2f | [5 empty] | INVALID IF COLOURED RED: Shall be earlier than 2f |  |  |  | 4
2f | Minimum number of days between finalization project documentation and start mobilization ( before 3a) |  | (Min: 4 weeks) | 28 | days | 28
2g | Clearance of locations (days after CLIENT issues first target locations: see 1b & continuously afterwards) |  | (Max: 2 weeks) | 14 | days |  | Fill number of days
2h | Provision of Pilot Digital Data Format. Latest 4 weeks before start mobilisation (before 3a) |  | (Min: 4 weeks) | 28 | days | 28
Field work | [9 empty] | III.2 | 2025-01-15 | 2025-02-22
3a | Start of Mobilisation (between 15 January - 22 February 2025) | [5 empty] | Fill in start date: INVALID IF COLOURED RED: |  |  |  | Start date between 15 Jan 25 and 22 Feb 25
3b | Mobilisation, including transit to site, testing and set up; MIN: 2 days / MAX: 7 days |  | (Max: 1 week) | 7 | days |  | Fill number of days |  |  | III.3
3c | Total Seabed Survey duration (CPT & VC) Excluding WAITING ON WEATHER |  | (Max: 10 weeks) | 70 | days |  | Fill number of days
3d | Offshore completion date (CPT & VC) ¦ Excluding WAITING ON WEATHER | [8 empty] | III.4
3e | Offshore completion date (CPT & VC) ¦ Including WAITING ON WEATHER calculated by CLIENT |  |  |  | days | WoW calculated by CLIENT (calculated based on II): |  |  |  | III.4
3f | Offshore completion date (CPT & VC) ¦ Including WAITING ON WEATHER calculated by CONTRACTOR |  | (Max: 10 weeks WOW) | 70 | days | Fill in WoW calculated by CONTRACTOR: INVALID IF COLOURED RED:
Explanation for difference between WOW calculated by CLIENT and WOW according to TENDERER.
Data Processing and report
4a | OFFSHORE COMPLETION DATE (CPT & VC) (including WAITING ON WEATHER) - Lot 1 = 3f
4b | Continuous delivery of CPT draft digital data between 00-01-yyyy and 01-05-yyyy | [8 empty] | III.5 | ultimate VC date
4c | Key Milestone: Delivery of 100 % CPT draft digital data (before 01-05-yyyy) |  |  |  | days |  |  |  | 2025-05-01
4d | Delivery of 1st version "Operations Report (Lot 1)" (days after OFFSHORE COMPLETION DATE) (days after 4a) |  | (Max: 4 weeks) | 28 | days |  | Fill number of days
4e | CLIENT review of 1st revision "Operations Report (Lot 1)" |  |  |  | days | 14
4f | Delivery of Final Version of "Operations Report (Lot 1)" |  | (Max: 2 weeks) | 14 | days |  | Fill number of days
4g | CLIENT Review of Final Version of "Operations Report (Lot 1)" |  |  |  | days | 7
4h | Acceptance of Final Version of "Operations Report (Lot 1)" including Final CPT & VC Digital Data |  | (Max: 1 week) | 7 | days |  | Fill number of days
4i | Delivery of 1st Version (Field Report) "Seabed In Situ Testing Report" (days after 4c) |  | (Max: 11 weeks) | 77 | days |  | Fill number of days
4j | CLIENT review of 1st Version (Field Report) "Seabed In Situ Testing Report" |  |  |  | days | 14
4k | Delivery of 2nd Version "Seabed In Situ Testing Report" |  | (Max: 2 weeks) | 14 | days |  | Fill number of days
4l | CLIENT review of 2nd Version "Seabed In Situ Testing Report" |  |  |  | days | 14
4m | Delivery of Final Version Seabed In Situ Testing Report before |  | (Max: 2 weeks) | 14 | days |  | Fill number of days
4n | CLIENT Review of Final Version Seabed In Situ Testing Report before |  |  |  | days | 7
4o | Key Milestone: Acceptance of Final Version Seabed In Situ Testing Report (before 15-9-2025) |  | (Max: 1 week) | 7 | days |  | Fill number of days
4p | Delivery of 1st Version (Field Report) "Seabed Sampling Report (VC)" (days after 4a) |  | (Max: 12 weeks) | 84 | days |  | Fill number of days
4q | CLIENT review of 1st Version (Field Report) "Seabed Sampling Report" |  |  |  | days | 14
4r | Delivery of 2nd Version "Seabed Sampling Report" |  | (Max: 3 weeks) | 21 | days |  | Fill number of days
4s | CLIENT review of 2nd Version "Seabed Sampling Report" |  |  |  | days | 14
4t | Delivery of Final Version Seabed Sampling Report before |  | (Max: 1 week) | 7 | days |  | Fill number of days
4u | CLIENT Review of Final Version Seabed Sampling Report before |  |  |  | days | 7
4v | Key Milestone: Acceptance of Final Version Seabed Sampling Report (before 01-11-yyyy) |  | (Max: 1 week) | 7 | days |  | Fill number of days
4w | Delivery of 1st Version "Archaeological Dating Report" (days after 4a) |  | (Max: 15 weeks) | 105 | days |  | Fill number of days
4x | CLIENT review of 1st Version "Archaeological Dating Report" |  |  |  | days | 14
4y | Delivery of Final Version Archaeological Dating Report before |  | (Max: 3 weeks) | 21 | days |  | Fill number of days
4z | CLIENT review of Final Version Archaeological Dating Report before |  |  |  | days | 7
4za | Acceptance of Final Version Archaeological Dating Report before 01-11-yyyy |  | (Max: 1 week) | 7 | days |  | Fill number of days
4zb | Reporting end date | [7 empty] | 0
Total time from start of contract till reporting end date | [7 empty] | -45495 | days
IV.0
IV. Rates Geotechnical Site Survey - DDW IA
ITEM | [5 empty] | Unit Rate | Unit | Qty | Price
1 | Mobilisation/demobilisation of vessel(s), survey equipment and personnel to site
1.1 | Mob/demob vessels and equipment | [5 empty] | Lump sum | 1 | FILL UNIT RATE
2 | Survey Operations incl transit from and to site excluding WOW
2.1 | Positioning and setting-up equipment at each location for seabed PCPT and dissipation tests, SCPT) | [5 empty] | /location | 96 | FILL UNIT RATE
2.2 | Seabed PCPT performance for depths between 0-60 m | [5 empty] | /m | 5760 | FILL UNIT RATE
2.3 | Execution of dissipation tests in seabed PCPT mode (N.B. number of tests will be limited by total time allowance) | [5 empty] | /hour | 34 | FILL UNIT RATE
2.4 | Positioning and setting-up equipment at each location for seabed SCPT | [5 empty] | /location | 32 | FILL UNIT RATE
2.5 | Seabed SCPT performance including seismic tests for depths between 0-60 m | [5 empty] | /m | 1920 | FILL UNIT RATE
2.7 | Positioning and setting-up equipment at each location for thermal conductivity cone testing | [5 empty] | /location | 32 | FILL UNIT RATE
2.8 | Seabed in situ thermal conductivity performance (including any re-tests and any associated data) for depths between 0-6m | [5 empty] | /m | 192 | FILL UNIT RATE
2.9 | Execution of in situ thermal conductivity tests during pause in penetration (assuming 15 minute per test) | [5 empty] | /hour | 48 | FILL UNIT RATE
2.10 | Re-positioning and setting-up for any re-tests at same location (seabed PCPT/dissipation tests, SCPT, thermal conductivity testing) - assumed 10% of total PCPT+SCPT+Thermal conductivity tests | [5 empty] | /location | 16 | FILL UNIT RATE
2.11 | Positioning and setting-up equipment at vibrocore location | [5 empty] | /location | 64 | FILL UNIT RATE
2.12 | Execution of vibrocores (including any re-tests) to target depth of up to 6m | [5 empty] | /m | 384 | FILL UNIT RATE
2.13 | Re-positioning and setting-up for 10% re-tests at same location for vibrocoring | [5 empty] | /location | 6.4 | FILL UNIT RATE | IV.1
2.14 | CLIENT requested port call for vessels during surveying | [5 empty] | /call | 1 | FILL UNIT RATE
3 | Lab Testing
All Soil types
3.1 | Natural Moisture content | [5 empty] | /test | 384 | FILL UNIT RATE
3.2 | Bulk density | [5 empty] | /test | 384 | FILL UNIT RATE
3.3 | Particle density | [5 empty] | /test | 192 | FILL UNIT RATE
3.4 | Carbonate content | [5 empty] | /test | 12.8 | FILL UNIT RATE
3.5 | Organic content (dichromate) | [5 empty] | /test | 12.8 | FILL UNIT RATE
3.6 | Organic content (loss on ignition) | [5 empty] | /test | 12.8 | FILL UNIT RATE
3.7 | Organic and total carbon content (Elementary analysis - dry combustion) | [5 empty] | /test | 12.8 | FILL UNIT RATE
3.8 | Electrical resistivity (as input for heat capacity calculations) | [5 empty] | /test | 32 | FILL UNIT RATE
3.9 | Pore water salinity (as input for heat capacity calculations) | [5 empty] | /test | 32 | FILL UNIT RATE
3.10 | Microscopic photography (as input for heat capacity calculations) | [5 empty] | /test | 32 | FILL UNIT RATE
Granular Soil
3.11 | Particle size analysis (sieve) | [5 empty] | /test | 384 | FILL UNIT RATE
3.12 | Particle size analysis (including fines) | [5 empty] | /test | 192 | FILL UNIT RATE
3.13 | Particle size analysis, including particle shape assessment (using dynamic imaging analyses, optional) | [5 empty] | /test | 0 | FILL UNIT RATE
3.14 | Min-max density | [5 empty] | /test | 64 | FILL UNIT RATE | IV.2
3.15 | Thermal conductivity tests on fully-saturated cohesionless samples using needle probe (ASTM D5334-14) | [5 empty] | /test | 64 | FILL UNIT RATE | IV.2
3.16 | Thermal conductivity tests on fully-saturated cohesionless samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). | [5 empty] | /test | 20 | FILL UNIT RATE
3.17 | Consolidated drained direct shear (shear box) tests (N.B. one "test" constitutes three individual sub-test on three specimens at three different normal pressures) | [5 empty] | /test | 32 | FILL UNIT RATE
Cohesive Soil
3.18 | Particle size analysis (including fines) | [5 empty] | /test | 19 | FILL UNIT RATE
3.19 | Atterberg limits (liquid and plastic limits, cone method) | [5 empty] | /test | 19 | FILL UNIT RATE | IV.2
3.20 | Thermal conductivity tests on fully-saturated undisturbed cohesive samples using needle probe (ASTM D5334-14) | [5 empty] | /test | 6 | FILL UNIT RATE | IV.2
3.21 | Thermal conductivity tests on fully-saturated remoulded cohesive samples using needle probe (ASTM D5334-14) | [5 empty] | /test | 6 | FILL UNIT RATE | IV.2
3.22 | Thermal conductivity tests on fully-saturated undisturbed cohesive samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). | [5 empty] | /test | 6 | FILL UNIT RATE | IV.2
3.23 | Thermal conductivity tests on fully-saturated remoulded cohesive samples using "Hot disc" method (Method 2: ISO 220007‐2.2008). | [5 empty] | /test | 6 | FILL UNIT RATE
3.24 | Unconsolidated-undrained triaxial compression tests on undisturbed samples | [5 empty] | /test | 19 | FILL UNIT RATE
3.25 | Unconsolidated-undrained triaxial compression tests on remoulded samples | [5 empty] | /test | 19 | FILL UNIT RATE
Archaeological dating
3.26 | Palynology analysis | [5 empty] | /test | 20 | FILL UNIT RATE
3.27 | Analysis of Algae | [5 empty] | /test | 20 | FILL UNIT RATE
3.28 | Analysis of Fungi | [5 empty] | /test | 20 | FILL UNIT RATE
3.29 | Analysis of Spores | [5 empty] | /test | 20 | FILL UNIT RATE
3.30 | Nano- or micro-fossil analysis including Dinoflagellate Cysts and Foraminifera | [5 empty] | /test | 20 | FILL UNIT RATE
3.31 | Carbon dating analysis | [5 empty] | /test | 20 | FILL UNIT RATE
3.32 | Mollucs | [5 empty] | /test | 20 | FILL UNIT RATE
3.33 | Diatoms | [5 empty] | /test | 20 | FILL UNIT RATE
3.34 | OSL | [5 empty] | /test | 10 | FILL UNIT RATE
Archaeology
3.35 | Archaeological logging of selected Vibrocores (based on 6 VCs with 6m recovery) | [5 empty] | /m | 36 | FILL UNIT RATE
4 | Reporting
4.1 | Operations Report (Lot 1) | [5 empty] | Lump sum | 1 | FILL UNIT RATE
4.2 | Seabed In Situ Testing Report (Lot 1) | [5 empty] | Lump sum | 1 | FILL UNIT RATE
4.3 | Seabed Sampling Report (Lot 1) | [5 empty] | Lump sum | 1 | FILL UNIT RATE
4.4 | Archaeological Dating Report (including all results of age dating programme) (to be appended to Vestigia report) | [5 empty] | Lump sum | 1 | FILL UNIT RATE
4.5 | Additional reporting of any seabed PCPTs in excess of base scope | [5 empty] | /location | 0 | FILL UNIT RATE
4.6 | Additional reporting of any seabed SCPTs in excess of base scope (excluding the seismic test results) | [5 empty] | /location | 0 | FILL UNIT RATE
4.7 | Additional reporting of any seismic tests during seabed SCPTs in excess of base scope | [5 empty] | /test | 0 | FILL UNIT RATE
4.8 | Additional reporting of any dissipation tests in excess of base scope | [5 empty] | /test | 0 | FILL UNIT RATE
4.9 | Additional reporting of any in situ thermal conductivity tests in excess of base scope | [5 empty] | /location | 0 | FILL UNIT RATE
4.10 | Additional reporting of any vibrocores in excess of base scope | [5 empty] | /location | 0 | FILL UNIT RATE
4.11 | Additional reporting of age dating tests in excess of base scope | [5 empty] | /test | 0 | FILL UNIT RATE
4.12 | Lab test processing/reporting and any other expenses associated with lab testing not covered by other items above | [5 empty] | % of lab testing price |  | FILL UNIT RATE
5 | Waiting on Weather
5.1 | Waiting on Weather during surveying calculated by CONTRACTOR | [5 empty] | /day | 0 | FILL UNIT RATE
6 | Other
6.1 | Project meetings to be held in CLIENT offices (Utrecht or The Hague) | [5 empty] | /meeting | 5 | FILL UNIT RATE
6.2 | Any activities required for the purpose of seabed clearance measures in accordance with CS-OOO regulations for seabed PCPT/SCPT, in situ thermal conductivity tests, or vibrocores to be included in price. | [5 empty] | /location | 192 | FILL UNIT RATE
6.3.a | Interaction with IGM contractor (estimated 300hrs for senior level personnel) | [5 empty] | Lump Sum | 1 | FILL UNIT RATE
6.3.b | Interaction with Certification Authorities (5 one day meetings + estimated 80hrs for senior level personnel) | [5 empty] | Lump Sum | 1 | FILL UNIT RATE
6.3.c | Interaction with Archaeological Contractor (2 interface meetings + 80hrs for senior level personnel) | [5 empty] | Lump Sum | 1 | FILL UNIT RATE
6.4 | Any activities required for the purpose of compliance with BRO requirements and transferring data to the BRO database | [5 empty] | Hr | 160 | FILL UNIT RATE
6.5 | Hourly rate for Project Manager | [5 empty] | Hr | 0 | FILL UNIT RATE
6.6 | Hourly rate for Senior Specialist | [5 empty] | Hr | 0 | FILL UNIT RATE
6.7 | Hourly rate for Medior Specialist | [5 empty] | Hr | 0 | FILL UNIT RATE | IV.3
6.8 | Activities related to dissemination of results (Project Site Description, Webinar, and Certification) | [5 empty] | Lump Sum | 1 | FILL UNIT RATE
V. INPUT FOR ASSESSMENT OF THE OFFER
INPUT FOR ASSESSMENT OF THE PRICE CRITERION - Fixed prices/rates
Weighing
Option 1/3 | Total virtual price for executing the survey excluding WAITING ON WEATHER / risk sharing |  | Survey works |  |  |  | 0 | 50% |  | V.1
Expected price for WOW (item 5.1)
Option 2 | Total virtual price for executing the survey including WAITING ON WEATHER |  | Survey works |  |  |  | 0 | 50% |  | V.2
|  |  | Allowance for WOW | [6 empty] | V.3
TOTAL VIRTUAL PRICE for assessment | [7 empty] | 0
V.4
|  |  | Max. number of points that can be awarded |  |  |  |  | 25
|  |  | Minimum Virtual Price (determined by CLIENT) |  |  |  |  | 6500000
|  |  | Maximum Virtual Price (determined by CLIENT) |  |  |  |  | 12100000 |  | V.5
|  |  | Points gained for the TOTAL VIRTUAL PRICE proposed: |  |  |  |  | 0 | Points | V.5
INPUT FOR ASSESSMENT OF THE COMPLETION DATE / CYCLE TIME CRITERION (Ability to finalize the offshore campaign at the preferred end date as set by CLIENT):
|  | Ultimate DATE FOR PROVIDING 100% of CPT DRAFT DIGITAL DATA (4c) set by CLIENT (incl. WOW) | [5 empty] | 2025-05-01
|  | Ultimate date for DELIVERY OF FINAL SEABED IN SITU TESTING set by CLIENT (incl. WOW) | [5 empty] | 2025-09-15
|  | Ultimate date for DELIVERY OF FINAL SEABED SAMPLING, AND ARCHAEOLOGICAL DATING REPORT set by CLIENT (incl. WOW) | [5 empty] | 2025-11-01
TOTAL POINTS GAINED BY TENDERER | [7 empty] | 0 | Points
VI. NOTES
I.0 | IN CASE A CELL IN THIS ANNEX 4a IS COLORED RED AS SHOWN IN THIS CELL THE PROPOSAL IS NOT VALID.
I.0 | TENDERER to check verify whether: - The project documentation is finalized 4 weeks before the first mobilisation date as set by TENDERER; - The planned completion date for the final report is not later than the ultimate date set by CLIENT; - The TOTAL VIRTUAL PRICE is within the range set by CLIENT; - Cycle times are within ranges allowed by CLIENT
I.0 | All numbers indicated in green are starting points set by CLIENT.
I.0 | All numbers indicated in blue (yellow cells) are to be provided by TENDERER and will form part of the PRICING SCHEDULE / CONTRACT PRICE as included in Annex 6 - Contract Section IIIa (Remuneration), and/or KEY DATES as included in Annex 6 - Contract Section IV (Scope of Work). All quantities will be used for assessment purposes and will also be the basis for determining the final CONTRACT PRICE and KEY DATES for these activities to be carried out under the CONTRACT. IN CASE THE BLUE TEXT TURNS RED, THIS MEANS THAT TENDERER ENTERED A VALUE OUTSIDE THE ALLOWABLE RANGES. This colour coding is for convenience only; the TENDERER is responsible for ensuring that the correct values are submitted by the TENDERER.
II.0 | TENDERER shall identify the vessels with which the survey shall be carried out. TENDERER may carry out the surveys with the amount of vessels it deems necessary and there is no need to specify which vessel shall perform what scope. The combination of survey equipment items to be run from the vessels shall be compliant with the Annex 6 - Contract Section IV (Scope of Work) At CONTRACT award, the values specified in this Annex 4 shall be taken over in Annex 6 - Contract Section IIIa (Remuneration)
II.0 | TENDERER to provide limiting operational conditions and minimum required weather window to perform the survey for the vessels proposed. These data are input for adverse weather determination as specified in Annex 6 - Contract Section.
II.1 | TENDERER may propose multiple vessels including equipment for the execution of the survey works. The overall limiting operational conditions will need to be specified by TENDERER for the whole proposed fleet, including equipment. CLIENT will only use the given vessel characteristics to prepare a comparative adverse weather calculation based on the average of all vessels. This calculation will only be used by CLIENT for reference and as cross-check of TENDERER's proposed WAITING ON WEATHER. TENDERER shall specify the number of WAITING ON WEATHER days to be included and if this deviates significantly from the calculated value, an explanation shall be provided as part of the tender submission. These days will be taken as the WAITING ON WEATHER ALLOWANCE DAYS in Annex 6 - Contract Section IIIa (Remuneration) The values in this section will ONLY be used by CLIENT to calculate weather downtime compensation when (a part of) the fleet is not able to work due to weather. In case of reported waiting on weather of (part of ) the fleet, the individual vessel characteristics on workability will be used to calculate any possible compensation for this waiting on weather.
III.0 | TENDERER shall specify the cycle times for executing the works. Key dates are set by the CLIENT due to schedule requirements. At CONTRACT award these dates will be taken over in Annex 6 - Contract Section IV (Scope of Work) / Table 1 Please note that Liquidated Damages/ mala become applicable in case CONTRACTOR fails to meet Key Dates as per Annex 6 - Contract Section IIIa (Remuneration), Chapter 5 (Bonus and malus)
III.1 | TENDERER to provide the number of days required for preparing & updating after review 1 & 2 of project documentation. Dates 2a-h are generated automatically based on these cycle times. Finalization of project documentation must be 28 days before the actual commencement of the offshore work (project documentation to comply with requirements as stated in Annex 6).
III.1 | In case the finalization date of the project documentation is later than 28 days before the start of the mobilization, this cell is coloured red. This means that the time allowed for preparation, review and acceptance is not sufficient in relation to the planned mobilisation date and as such the proposal not valid! Note that the starting date of the Mobilisation for the Lot 1 survey work shall be between 15 January 2025 (earliest) and 22 February 2025 (latest).
III.2 | Start of mobilisation shall be within the indicated range. In case the mobilisation is outside the range, this cell is coloured red. Please refer to Annex 6 - Contract Section IV (Scope of Work) for the deinition of mobilisation (when it is considered complete)
III.3 | TENDERER will need to allocate time and resources for the total scope, for which the total quantities are given in cells J8-12.
III.4 | 3f is the OFFSHORE COMPLETION DATE (including WAITING ON WEATHER calculated by CONTRACTOR).
The number of WAITING ON WEATHER DAYS is automatically determined in tab [WDT Calculation] based upon the end of mobilisation (incl. transit to site), limiting conditions and cycle times given by TENDERER and the persistence percentages given in tab [U10-wave].The automatic calculation of WAITING ON WEATHER is for Client reference only. The TENDERER shall specify the number of WAITING ON WEATHER DAYS, accounting more detailed limits than specified in this Annex 4. If there is a significant difference between the automatically-calculated and TENDERER-calculated WAITING ON WEATHER days, TENDERER shall explain the reason for this difference. The explanation will be used in the evaluation of the vessel and equipment according to Annex 3. Note that WAITING ON WEATHER will be calculated as an average over the whole fleet. The number of WAITING ON WEATHER days shall be input for WAITING ON WEATHER ALLOWANCE DAYS dependent on the chosen Waiting on Weather option and weather down time principles as specified in Annex 6 - Contract Section IIIa (Remuneration) and Annex 6 - Contract Section VI (Quality requirements & Administrative instructions).
III.5 | Please note that Contractor is required to provide a date for the delivery of 100% of the CPT data (as pdf and digital) and subsequent reports. The delivery of 100% the CPT data needs to be before the date stated in item 4c; CONTRACTOR shall deliver the draft CPT data continuously during the campaign to allow optimization for GT-Lot2 (Downhole campaign). The Vibrocore data is not on the critical path as much as the CPT data and hence a later delivery of the VC is allowed.
IV.0 | Costs associated with extra work caused by mechanical breakdowns - e.g. re-positioning, bump-overs, etc. following equipment failure - are not chargeable under the operational or weather standby rates, but are at Contractors own costs. All these costs are assumed to be considered in the total project execution duration and price.
IV.1 | Additional port calls requested by CLIENT are independent of duration of the fieldwork and are additional to "regular" port calls scheduled by the Contractor as part of the operations. The additional port calls requested by CLIENT may be requested and as such are considered optional. Since the price of these port calls will be included in the overall contract price, the total amount of CLIENT requested port calls will be checked upon the completion of the project and any additional or less port calls will be subject to a Variation Order.
IV.2 | Thermal conductivity tests to include specific heat capacity. Tests include duplicate tests on two separate specimens from one sample. Tests include testing at five different densities (for cohesionless samples).
IV.3 | Lump sum for activities related to dissemination of results (item 6.8) shall be paid upon completion of the webinar and PSD, in accordance with Annex 6 - Contract Section IIIa (Remuneration)
V.1 | The price for WAITING ON WEATHER is calculated automatically based on the WAITING ON WEATHER DAYS as specified by TENDERER under items 3f and 5.1. The price determined here is used determining the TOTAL VIRTUAL PRICE as explained in the Tender Document.
V.2 | TENDERER shall specify the allowance for WAITING ON WEATHER for the Lumpsum including weather. This WAITING ON WEATHER ALLOWANCE shall cover all WEATHER DOWNTIME that could be encountered during the execution of the works. At Contract award the values specified in this Annex 4a shall be taken over in Annex 6 - Contract Section IIIa (Remuneration)
V.3 | The TOTAL VIRTUAL PRICE is determined by averaging two weather down time calculations. Weather downtime options and weather down time principles are specified in Annex 6 - Section IIIa (Remuneration) and Annex 6 - Section VI (Quality requirements & Administrative instructions). IN CASE THE TOTAL VIRTUAL PRICE OFFERED IS HIGHER THAN THE MAXIMUM PRICE THAN THE PROPOSAL IS NOT VALID!
V.4 | The TENDERER gains points when able to complete the works below the set maximum price. The number of points that are awarded is determined through linear interpolation between the minimum and maximum price.
V.5 | The weather downtime days as specified by the TENDERER are included in the calculation of the OFFSHORE COMPLETION DATES and the consequential reporting and deliverable milestones as set by CLIENT. IN CASE THIS DATE IS LATER THAN THE ULTIMATE DUE DATE SET BY THE CLIENT THIS CELL IS COLORED RED. THIS MEANS THE PROPOSAL NOT VALID!

## Key Dates
in green, bold and underlined key date for which contractor is liable for liquidated damages in case of failure to complete these dates
No. | Description | Date
1a | COMMENCEMENT DATE WORK set by CLIENT | 2024-07-22
2a | 1st revision of project documentation (PQP, PEP) | 0
2b | CLIENT Review 1st revision project documentation (PQP, PEP)
2c | 2nd revision of project documentation (PQP, PEP)
2d | CLIENT Review 2nd revision project documentation (PQP, PEP)
2e | Finalise project documentation (incl additional revisions/review rounds) |  |  | Survey type | Dates
2f | Finalise project documentation (incl additional revisions/review rounds) |  |  |  | Start Mob | Start work
2g | Clearance of locations (days after CLIENT issues first target locations: see 1b & continuously afterwards) |  | SB | SB | #REF! | #REF!
2h | Provision of Pilot Digital Data Format. Latest 4 weeks before start mobilisation (before 3a)
Field work | 0 | 0
3a | Start of Mobilisation (between 15 January - 22 February 2025) | 0
3b | Mobilisation, including transit to site, testing and set up; MIN: 2 days / MAX: 7 days
3c | Total Seabed Survey duration (CPT & VC) Excluding WAITING ON WEATHER
3d | Offshore completion date (CPT & VC) ¦ Excluding WAITING ON WEATHER
3e | Offshore completion date (CPT & VC) ¦ Including WAITING ON WEATHER calculated by CLIENT
3f | Offshore completion date (CPT & VC) ¦ Including WAITING ON WEATHER calculated by CONTRACTOR
Explanation for difference between WOW calculated by CLIENT and WOW according to TENDERER. | 0 | 0
Data Processing and report | 0 | 0
4a | OFFSHORE COMPLETION DATE (CPT & VC) (including WAITING ON WEATHER) - Lot 1 = 3f
4b | Continuous delivery of CPT draft digital data between 00-01-yyyy and 01-05-yyyy
4c | Key Milestone: Delivery of 100 % CPT draft digital data (before 01-05-yyyy) | 2025-05-01
#REF! | #REF! | #REF!
4d | Delivery of 1st version "Operations Report (Lot 1)" (days after OFFSHORE COMPLETION DATE) (days after 4a)
4e | CLIENT review of 1st revision "Operations Report (Lot 1)"
4f | Delivery of Final Version of "Operations Report (Lot 1)"
4g | CLIENT Review of Final Version of "Operations Report (Lot 1)"
4h | Acceptance of Final Version of "Operations Report (Lot 1)" including Final CPT & VC Digital Data
4i | Delivery of 1st Version (Field Report) "Seabed In Situ Testing Report" (days after 4c)
4j | CLIENT review of 1st Version (Field Report) "Seabed In Situ Testing Report"
4k | Delivery of 2nd Version "Seabed In Situ Testing Report"
4l | CLIENT review of 2nd Version "Seabed In Situ Testing Report"
4m | Delivery of Final Version Seabed In Situ Testing Report before
4n | CLIENT Review of Final Version Seabed In Situ Testing Report before
4o | Key Milestone: Acceptance of Final Version Seabed In Situ Testing Report (before 15-9-2025)
4p | Delivery of 1st Version (Field Report) "Seabed Sampling Report (VC)" (days after 4a)
4q | CLIENT review of 1st Version (Field Report) "Seabed Sampling Report"
4r | Delivery of 2nd Version "Seabed Sampling Report"
4s | CLIENT review of 2nd Version "Seabed Sampling Report"
4t | Delivery of Final Version Seabed Sampling Report before
4u | CLIENT Review of Final Version Seabed Sampling Report before
4v | Key Milestone: Acceptance of Final Version Seabed Sampling Report (before 01-11-yyyy)
4w | Delivery of 1st Version "Archaeological Dating Report" (days after 4a)
4x | CLIENT review of 1st Version "Archaeological Dating Report"
4y | Delivery of Final Version Archaeological Dating Report before
4z | CLIENT review of Final Version Archaeological Dating Report before
4za | Acceptance of Final Version Archaeological Dating Report before 01-11-yyyy
4zb | Reporting end date | 0

## WDT Calculation
WORKABILITY CALCULATION
| PART | Limiting conditions |  |  | Total Durations (days)
| N | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW | P20/P50/P80 | WoW combined
|  | 0 | 0 | 0 | 0 | #VALUE! | 0.5 | #VALUE! | #VALUE!
CALCULATION |  |  |  |  | Nett days | Working days |  |  | #VALUE!
Month | Month | Start | End | Persistence | in month | in month | left |  | #VALUE!
1 | #VALUE! |  | #VALUE! | #N/A | #VALUE! | #N/A | #N/A |  | #VALUE!
2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
WORKABILITY CALCULATION
| PART | Limiting conditions |  |  | Total Durations (days)
| N | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW | P20/P50/P80
|  | 0 | 0 | 0 | 0 | #VALUE! | 0.5
CALCULATION |  |  |  |  | Nett days | Working days
Month | Month | Start | End | Persistence | in month | in month | left
1 | #VALUE! |  | #VALUE! | #N/A | #VALUE! | #N/A | #N/A
2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
WORKABILITY CALCULATION
| PART | Limiting conditions |  |  | Total Durations (days)
| N | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW | P20/P50/P80
[5 empty] | 0 | #VALUE! | 0.5
CALCULATION |  |  |  |  | Nett days | Working days
Month | Month | Start | End | Persistence | in month | in month | left
1 | #VALUE! |  | #VALUE! | #N/A | #VALUE! | #N/A | #N/A
2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
WORKABILITY CALCULATION
| PART | Limiting conditions |  |  | Total Durations (days)
| N | Hs (m) | Vw (m/s) | Ww (hrs) | nett | WoW | P20/P50/P80
[5 empty] | 0 | #VALUE! | 0.5
CALCULATION |  |  |  |  | Nett days | Working days
Month | Month | Start | End | Persistence | in month | in month | left
1 | #VALUE! |  | #VALUE! | #N/A | #VALUE! | #N/A | #N/A
2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Formulas:
Total Durations (days) = IFERROR(IF(G5/F8<EOMONTH([Limiting conditions],0)+1-[Limiting conditions],G5/F8,EOMONTH([Limiting conditions],0)+1-[Limiting conditions]),EOMONTH([Limiting conditions],0)-[Limiting conditions]+1)
Total Durations (days) = IFERROR(IF(I8/F9<EOMONTH([Limiting conditions],0)+1-[Limiting conditions],I8/F9,EOMONTH([Limiting conditions],0)+1-[Limiting conditions]),EOMONTH([Limiting conditions],0)-[Limiting conditions]+1)
End = IF([Limiting conditions]+[Total Durations (days)]-1<EOMONTH([Limiting conditions],0),[Limiting conditions]+[Total Durations (days)]-1,EOMONTH([Limiting conditions],0))
End = IF([left, row above]>0,IF([Limiting conditions]+[Total Durations (days)]-1<EOMONTH([Limiting conditions],0),[Limiting conditions]+[Total Durations (days)]-1,EOMONTH([Limiting conditions],0)),[Limiting conditions])

## U10-wave
Weather window (%) |  | Month | January |  |  | February |  |  | March |  |  | April |  |  | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December
|  | Quantile | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80% | 20% | 50% | 80%
duration (h) | Hm0 (m) < | U10 (m/s) < | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12
1 | 0.5 | 2 | 0 | 0 | 0 | 0.59524 | 0 | 0 | 0.47043 | 0 | 0 | 2.4306 | 0.48611 | 0 | 2.3522 | 1.1425 | 0 | 4.6528 | 2.0833 | 0.27778 | 4.2339 | 1.6129 | 0.47043 | 3.293 | 1.4113 | 0.67204 | 1.5972 | 0.27778 | 0 | 0.53763 | 0 | 0 | 0.20833 | 0 | 0 | 0.33602 | 0 | 0
1 | 0.5 | 4 | 0.60484 | 0 | 0 | 2.0448 | 0 | 0 | 2.6882 | 0.13441 | 0 | 7.4306 | 3.2639 | 0.69444 | 8.4677 | 5.5108 | 2.5538 | 14.4444 | 8.6806 | 2.8472 | 15.457 | 7.7957 | 4.4355 | 12.3656 | 6.1828 | 3.4274 | 5 | 2.2917 | 0.48611 | 2.0833 | 0.40323 | 0 | 1.5972 | 0 | 0 | 1.8145 | 0.067204 | 0
1 | 0.5 | 6 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.2419 | 0.53763 | 0 | 11.4583 | 7.2222 | 1.5278 | 15.121 | 10.7527 | 5.5108 | 19.4444 | 13.6806 | 5.2778 | 22.7151 | 13.7769 | 7.5269 | 18.6156 | 9.8118 | 6.1828 | 10.3472 | 4.375 | 0.97222 | 3.7634 | 1.1425 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
1 | 0.5 | 8 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.3333 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4861 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1317 | 20.0941 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
1 | 0.5 | 9 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.3333 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4861 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 20.0941 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
1 | 0.5 | 10 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.3333 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4861 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 20.0941 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
1 | 0.5 | 11 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.3333 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4861 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 20.0941 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
1 | 0.5 | 12 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.3333 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4861 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 20.0941 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
1 | 0.5 | 15 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.3333 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4861 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 20.0941 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
1 | 0.5 | 20 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.3333 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4861 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 20.0941 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
1 | 0.5 | 25 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.3333 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4861 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 20.0941 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
1 | 0.75 | 2 | 1.0081 | 0 | 0 | 1.8601 | 0.14881 | 0 | 1.7473 | 0.53763 | 0 | 3.5417 | 1.9444 | 0.90278 | 4.2339 | 1.8817 | 0.53763 | 6.6667 | 3.0556 | 1.0417 | 5.578 | 2.621 | 1.3441 | 4.1667 | 2.4194 | 1.3441 | 2.2917 | 1.4583 | 0.27778 | 1.4113 | 0.53763 | 0 | 0.90278 | 0.27778 | 0 | 1.1425 | 0.13441 | 0
1 | 0.75 | 4 | 2.8898 | 1.0753 | 0 | 6.2115 | 2.6042 | 0 | 7.9973 | 2.5538 | 1.1425 | 14.0972 | 9.4444 | 4.5833 | 14.3817 | 10.2151 | 5.4435 | 22.4306 | 12.3611 | 7.3611 | 19.086 | 12.9032 | 8.9382 | 18.2796 | 10.8871 | 9.0054 | 10.9722 | 6.5972 | 2.3611 | 4.4355 | 2.4866 | 0.067204 | 3.6111 | 1.3194 | 0.20833 | 4.8387 | 2.2849 | 0
1 | 0.75 | 6 | 6.9892 | 2.621 | 0 | 11.5661 | 5.2083 | 0.29762 | 15.7258 | 6.7876 | 2.957 | 26.1111 | 19.2361 | 10.5556 | 28.0914 | 21.5726 | 14.9866 | 36.3194 | 23.5417 | 18.2639 | 34.207 | 26.4113 | 20.3629 | 34.4086 | 23.2527 | 17.3387 | 23.75 | 13.125 | 7.0833 | 11.1559 | 5.3763 | 1.8145 | 6.5278 | 2.5 | 0.55556 | 6.9892 | 3.8306 | 0
1 | 0.75 | 8 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 18.8172 | 7.7285 | 4.0323 | 32.0833 | 23.6806 | 13.8889 | 37.2312 | 27.8226 | 20.1613 | 43.75 | 30.8333 | 23.4028 | 45.0941 | 34.6774 | 26.8817 | 43.078 | 29.2339 | 22.1102 | 29.2361 | 16.875 | 9.3056 | 13.5753 | 7.1909 | 2.5538 | 7.6389 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
1 | 0.75 | 9 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.0188 | 7.7285 | 4.0323 | 32.7083 | 24.4444 | 14.3056 | 38.1048 | 28.2258 | 20.6989 | 44.2361 | 31.1806 | 23.8194 | 45.6989 | 35.4839 | 27.4194 | 43.4812 | 30.2419 | 22.7151 | 29.4444 | 17.1528 | 9.3056 | 13.5753 | 7.3925 | 2.5538 | 7.6389 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
1 | 0.75 | 10 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.7285 | 4.0323 | 32.7778 | 24.4444 | 14.3056 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.1806 | 23.8889 | 45.7661 | 35.5511 | 27.5538 | 43.4812 | 30.3763 | 22.7151 | 29.4444 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.6389 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
1 | 0.75 | 11 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.7285 | 4.0323 | 32.7778 | 24.4444 | 14.3056 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.25 | 23.8889 | 45.7661 | 35.5511 | 27.5538 | 43.4812 | 30.3763 | 22.7151 | 29.4444 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.6389 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
1 | 0.75 | 12 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.7285 | 4.0323 | 32.7778 | 24.4444 | 14.3056 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.25 | 23.8889 | 45.7661 | 35.5511 | 27.5538 | 43.4812 | 30.3763 | 22.7151 | 29.4444 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.6389 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
1 | 0.75 | 15 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.7285 | 4.0323 | 32.7778 | 24.4444 | 14.3056 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.25 | 23.8889 | 45.7661 | 35.5511 | 27.5538 | 43.4812 | 30.3763 | 22.7151 | 29.4444 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.6389 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
1 | 0.75 | 20 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.7285 | 4.0323 | 32.7778 | 24.4444 | 14.3056 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.25 | 23.8889 | 45.7661 | 35.5511 | 27.5538 | 43.4812 | 30.3763 | 22.7151 | 29.4444 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.6389 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
1 | 0.75 | 25 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.7285 | 4.0323 | 32.7778 | 24.4444 | 14.3056 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.25 | 23.8889 | 45.7661 | 35.5511 | 27.5538 | 43.4812 | 30.3763 | 22.7151 | 29.4444 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.6389 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
1 | 1 | 2 | 1.7473 | 0.33602 | 0 | 2.2989 | 0.74405 | 0 | 2.2177 | 1.0753 | 0.33602 | 4.1667 | 2.7778 | 1.3194 | 5.1747 | 2.2849 | 1.2097 | 7.5 | 3.6806 | 1.6667 | 6.1156 | 3.4274 | 1.4785 | 5.2419 | 3.0914 | 1.7473 | 3.1944 | 1.875 | 0.69444 | 1.8145 | 1.0081 | 0.26882 | 1.7361 | 0.41667 | 0 | 1.7473 | 0.80645 | 0
1 | 1 | 4 | 4.9731 | 2.1505 | 0.26882 | 9.57 | 4.3847 | 1.3906 | 11.7608 | 4.4355 | 2.3522 | 16.4583 | 11.5278 | 6.25 | 17.6075 | 13.1048 | 9.7446 | 24.375 | 15 | 10.9722 | 22.043 | 15.0538 | 10.5511 | 21.5054 | 14.3817 | 10.7527 | 13.4722 | 9.2361 | 4.5139 | 7.2581 | 4.4355 | 1.7473 | 6.1806 | 3.2639 | 1.1111 | 7.1909 | 3.5618 | 0.80645
1 | 1 | 6 | 12.9032 | 5.8468 | 1.6129 | 19.1964 | 12.3538 | 3.869 | 21.5726 | 13.172 | 6.4516 | 32.5 | 24.8611 | 17.6389 | 36.4919 | 30.7124 | 23.1183 | 44.9306 | 35.4861 | 25.2778 | 42.1371 | 35.2151 | 27.957 | 42.8763 | 30.4435 | 24.4624 | 30.9028 | 20.4167 | 12.8472 | 17.6075 | 10.8871 | 5.0403 | 13.6806 | 7.3611 | 2.7083 | 14.7177 | 7.5941 | 1.2769
1 | 1 | 8 | 19.8925 | 8.9382 | 2.5538 | 27.5298 | 17.7827 | 5.4315 | 31.3844 | 19.8253 | 9.6774 | 45 | 36.1806 | 26.7361 | 52.7554 | 44.6909 | 36.2231 | 56.8056 | 48.1944 | 39.375 | 62.6344 | 50.2016 | 40.0538 | 57.9973 | 45.2957 | 38.172 | 41.1111 | 31.9444 | 22.4306 | 22.7151 | 15.2554 | 8.3333 | 17.9167 | 10.3472 | 3.6111 | 20.9677 | 10.4839 | 2.7554
1 | 1 | 9 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 32.8629 | 21.5726 | 10.0134 | 48.3333 | 39.4444 | 28.2639 | 56.922 | 47.1102 | 39.3817 | 60.0694 | 51.25 | 40.625 | 66.8683 | 52.8898 | 42.9435 | 62.0968 | 48.7231 | 40.9274 | 43.6806 | 34.3056 | 23.2639 | 23.7903 | 15.9274 | 8.6694 | 18.3333 | 10.8333 | 3.6806 | 21.3038 | 10.9543 | 2.957
1 | 1 | 10 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.5349 | 21.9758 | 10.5511 | 48.6111 | 40.7639 | 28.8889 | 58.0645 | 47.9839 | 40.8602 | 60.4861 | 52.4306 | 41.0417 | 68.1452 | 54.3683 | 45.1613 | 62.9704 | 49.9328 | 41.3978 | 44.3056 | 34.7222 | 23.3333 | 24.1263 | 16.129 | 8.7366 | 18.4722 | 10.9028 | 3.6806 | 21.371 | 11.0215 | 3.0914
1 | 1 | 11 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.7366 | 22.043 | 10.5511 | 48.8194 | 40.9722 | 28.8889 | 58.0645 | 48.3199 | 40.8602 | 60.4861 | 52.5694 | 41.0417 | 68.3468 | 54.4355 | 45.5645 | 63.172 | 50.0672 | 41.4651 | 44.3056 | 34.7917 | 23.3333 | 24.1263 | 16.1962 | 8.7366 | 18.5417 | 10.9028 | 3.6806 | 21.371 | 11.0215 | 3.0914
1 | 1 | 12 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.7366 | 22.043 | 10.5511 | 48.8194 | 40.9722 | 28.8889 | 58.0645 | 48.3199 | 40.8602 | 60.4861 | 52.5694 | 41.0417 | 68.414 | 54.4355 | 45.5645 | 63.172 | 50.0672 | 41.4651 | 44.3056 | 34.7917 | 23.3333 | 24.1263 | 16.1962 | 8.7366 | 18.5417 | 10.9028 | 3.6806 | 21.371 | 11.0215 | 3.0914
1 | 1 | 15 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.7366 | 22.043 | 10.5511 | 48.8194 | 40.9722 | 28.8889 | 58.0645 | 48.3199 | 40.8602 | 60.4861 | 52.5694 | 41.0417 | 68.414 | 54.4355 | 45.5645 | 63.172 | 50.0672 | 41.4651 | 44.3056 | 34.7917 | 23.3333 | 24.1263 | 16.1962 | 8.7366 | 18.5417 | 10.9028 | 3.6806 | 21.371 | 11.0215 | 3.0914
1 | 1 | 20 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.7366 | 22.043 | 10.5511 | 48.8194 | 40.9722 | 28.8889 | 58.0645 | 48.3199 | 40.8602 | 60.4861 | 52.5694 | 41.0417 | 68.414 | 54.4355 | 45.5645 | 63.172 | 50.0672 | 41.4651 | 44.3056 | 34.7917 | 23.3333 | 24.1263 | 16.1962 | 8.7366 | 18.5417 | 10.9028 | 3.6806 | 21.371 | 11.0215 | 3.0914
1 | 1 | 25 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.7366 | 22.043 | 10.5511 | 48.8194 | 40.9722 | 28.8889 | 58.0645 | 48.3199 | 40.8602 | 60.4861 | 52.5694 | 41.0417 | 68.414 | 54.4355 | 45.5645 | 63.172 | 50.0672 | 41.4651 | 44.3056 | 34.7917 | 23.3333 | 24.1263 | 16.1962 | 8.7366 | 18.5417 | 10.9028 | 3.6806 | 21.371 | 11.0215 | 3.0914
1 | 1.25 | 2 | 1.8817 | 0.53763 | 0 | 2.4836 | 1.17 | 0.14881 | 3.0914 | 1.0753 | 0.40323 | 4.7222 | 3.125 | 1.5278 | 5.2419 | 2.7554 | 1.4785 | 7.9167 | 3.8889 | 2.1528 | 6.1156 | 3.4274 | 1.6129 | 5.4435 | 3.4274 | 1.8145 | 3.8194 | 2.0833 | 0.76389 | 2.2849 | 1.1425 | 0.47043 | 2.1528 | 0.83333 | 0.34722 | 2.6882 | 1.0081 | 0
1 | 1.25 | 4 | 7.6613 | 3.0914 | 1.2097 | 10.899 | 6.1422 | 2.2321 | 13.0376 | 6.6532 | 3.293 | 17.6389 | 12.9167 | 8.8194 | 19.4892 | 14.1129 | 10.6855 | 26.0417 | 16.3194 | 12.3611 | 22.379 | 16.5995 | 11.2231 | 21.6398 | 16.2634 | 10.9543 | 14.9306 | 11.0417 | 4.9306 | 9.0726 | 5.7796 | 3.0914 | 9.0278 | 5 | 1.3889 | 8.2661 | 4.9059 | 1.0753
1 | 1.25 | 6 | 19.2204 | 8.4677 | 4.9059 | 23.4657 | 15.0144 | 6.1756 | 26.4113 | 20.2285 | 8.7366 | 35.3472 | 29.9306 | 22.5694 | 40.5242 | 35.3495 | 26.5457 | 48.75 | 40.2083 | 28.5417 | 45.4301 | 38.7097 | 30.7796 | 44.0188 | 33.6022 | 27.8898 | 34.5833 | 26.9444 | 17.4306 | 20.7661 | 14.1129 | 8.9382 | 16.7361 | 10.9028 | 5.9722 | 17.9435 | 10.6183 | 4.5699
1 | 1.25 | 8 | 28.9651 | 14.6505 | 7.9973 | 38.244 | 25.744 | 11.4583 | 40.5242 | 31.3172 | 17.2043 | 54.4444 | 46.875 | 37.4306 | 61.0887 | 53.4946 | 46.8414 | 65.9028 | 60.8333 | 48.0556 | 71.9758 | 60.4839 | 49.7312 | 64.1129 | 55.6452 | 47.2446 | 49.5139 | 42.0139 | 28.4028 | 30.8468 | 24.3952 | 13.8441 | 27.9167 | 16.5278 | 9.2361 | 29.4355 | 18.414 | 6.1828
1 | 1.25 | 9 | 31.4516 | 16.3306 | 8.4677 | 41.2946 | 29.0179 | 13.0208 | 43.0108 | 34.879 | 19.7581 | 61.3889 | 50.2083 | 41.8056 | 67.0027 | 59.879 | 51.8817 | 72.0139 | 67.0139 | 52.8472 | 77.621 | 65.9946 | 58.1989 | 72.1102 | 59.9462 | 52.957 | 54.8611 | 45.2083 | 33.5417 | 34.3414 | 27.621 | 15.9946 | 30.1389 | 20.4861 | 9.4444 | 31.25 | 19.6909 | 6.922
1 | 1.25 | 10 | 32.4597 | 16.8011 | 8.9382 | 42.9315 | 29.8953 | 13.5417 | 43.9516 | 36.5591 | 21.2366 | 65.2778 | 53.5417 | 44.6528 | 69.6909 | 63.5081 | 53.9651 | 74.7222 | 68.4722 | 54.375 | 80.5108 | 70.2957 | 61.3575 | 74.4624 | 62.2984 | 54.5027 | 58.125 | 47.0139 | 35.625 | 35.2151 | 29.9059 | 17.0699 | 31.25 | 21.6667 | 9.5139 | 31.7204 | 20.2957 | 7.8629
1 | 1.25 | 11 | 32.6613 | 16.8683 | 9.0726 | 42.9315 | 30.116 | 13.6161 | 45.2285 | 36.9624 | 21.2366 | 66.1806 | 54.7917 | 45.2083 | 70.2285 | 64.9194 | 54.3683 | 75.0694 | 68.8889 | 54.7222 | 81.0484 | 71.371 | 61.8952 | 74.9328 | 62.9032 | 55.1747 | 60 | 47.5 | 36.1111 | 35.4839 | 30.4435 | 17.4059 | 31.3889 | 21.6667 | 9.5833 | 31.922 | 20.5645 | 7.9301
1 | 1.25 | 12 | 32.6613 | 16.8683 | 9.0726 | 42.9315 | 30.1904 | 13.6161 | 45.2957 | 37.0296 | 21.371 | 66.3194 | 54.8611 | 45.2778 | 70.2957 | 65.2554 | 54.5027 | 75.2083 | 69.0972 | 54.7222 | 81.1828 | 71.5726 | 62.2312 | 75.1344 | 63.0376 | 55.4435 | 60.1389 | 47.6389 | 36.3194 | 35.5511 | 30.5108 | 17.4731 | 31.4583 | 21.6667 | 9.5833 | 31.9892 | 20.6317 | 7.9301
1 | 1.25 | 15 | 32.6613 | 16.8683 | 9.0726 | 42.9315 | 30.1904 | 13.6905 | 45.2957 | 37.0296 | 21.371 | 66.3194 | 54.8611 | 45.2778 | 70.2957 | 65.2554 | 54.5027 | 75.2083 | 69.0972 | 54.7222 | 81.1828 | 71.5726 | 62.3656 | 75.1344 | 63.1048 | 55.5108 | 60.1389 | 47.6389 | 36.3194 | 35.5511 | 30.5108 | 17.5403 | 31.4583 | 21.6667 | 9.5833 | 31.9892 | 20.6317 | 7.9301
1 | 1.25 | 20 | 32.6613 | 16.8683 | 9.0726 | 42.9315 | 30.1904 | 13.6905 | 45.2957 | 37.0296 | 21.371 | 66.3194 | 54.8611 | 45.2778 | 70.2957 | 65.2554 | 54.5027 | 75.2083 | 69.0972 | 54.7222 | 81.1828 | 71.5726 | 62.3656 | 75.1344 | 63.1048 | 55.5108 | 60.1389 | 47.6389 | 36.3194 | 35.5511 | 30.5108 | 17.5403 | 31.4583 | 21.6667 | 9.5833 | 31.9892 | 20.6317 | 7.9301
1 | 1.25 | 25 | 32.6613 | 16.8683 | 9.0726 | 42.9315 | 30.1904 | 13.6905 | 45.2957 | 37.0296 | 21.371 | 66.3194 | 54.8611 | 45.2778 | 70.2957 | 65.2554 | 54.5027 | 75.2083 | 69.0972 | 54.7222 | 81.1828 | 71.5726 | 62.3656 | 75.1344 | 63.1048 | 55.5108 | 60.1389 | 47.6389 | 36.3194 | 35.5511 | 30.5108 | 17.5403 | 31.4583 | 21.6667 | 9.5833 | 31.9892 | 20.6317 | 7.9301
1 | 1.5 | 2 | 2.1505 | 0.73925 | 0 | 2.7786 | 1.2649 | 0.29762 | 3.4946 | 1.4113 | 0.67204 | 4.8611 | 3.3333 | 1.5278 | 5.4435 | 2.8898 | 1.5457 | 8.0556 | 3.9583 | 2.2917 | 6.1156 | 3.4274 | 1.6801 | 5.5108 | 3.4274 | 1.8145 | 3.9583 | 2.0833 | 0.90278 | 2.4866 | 1.4113 | 0.53763 | 2.2917 | 1.0417 | 0.34722 | 3.0242 | 1.0753 | 0.13441
1 | 1.5 | 4 | 9.207 | 3.4274 | 1.9489 | 12.0536 | 7.4584 | 2.4861 | 13.2392 | 8.0645 | 4.3683 | 18.4028 | 14.0278 | 9.7917 | 20.1613 | 15.3226 | 10.7527 | 26.3194 | 16.7361 | 13.0556 | 22.6478 | 16.7339 | 11.2903 | 21.7742 | 16.5323 | 11.1559 | 15.4167 | 11.1806 | 5 | 10.3495 | 6.586 | 4.0323 | 9.5139 | 5.6944 | 2.0139 | 9.4758 | 6.0484 | 1.8145
1 | 1.5 | 6 | 22.7151 | 10.4839 | 6.4516 | 24.9974 | 17.7571 | 7.8125 | 27.6882 | 22.5134 | 11.0887 | 37.7778 | 32.9167 | 24.2361 | 42.8091 | 38.0376 | 28.8978 | 50.625 | 40.625 | 30 | 46.9086 | 39.6505 | 31.7876 | 44.422 | 35.8871 | 29.0323 | 36.7361 | 29.5139 | 20.1389 | 23.5887 | 17.2715 | 9.7446 | 19.3056 | 13.5417 | 7.9861 | 20.0269 | 13.6425 | 5.9812
1 | 1.5 | 8 | 33.2661 | 21.1022 | 11.2903 | 43.8757 | 31.7708 | 16.5923 | 45.4301 | 35.7527 | 22.2446 | 59.5139 | 51.5972 | 43.75 | 66.0618 | 60.2151 | 51.6129 | 70.9028 | 65.2778 | 53.8194 | 73.9919 | 64.9194 | 52.7554 | 66.1962 | 60.8199 | 50.7392 | 54.9306 | 47.7083 | 34.3056 | 36.2903 | 30.3763 | 18.6156 | 34.7222 | 22.9861 | 14.7222 | 34.9462 | 23.5215 | 10.3495
1 | 1.5 | 9 | 37.7016 | 24.664 | 14.6505 | 48.5119 | 36.6918 | 20.3869 | 51.9489 | 41.1962 | 26.8817 | 67.2222 | 58.5417 | 51.0417 | 74.328 | 67.0699 | 60.0134 | 77.6389 | 73.4722 | 63.125 | 81.7204 | 73.1855 | 64.9194 | 75.672 | 67.7419 | 59.543 | 63.5417 | 53.6806 | 42.4306 | 41.5323 | 36.5591 | 23.7231 | 40.2778 | 27.7083 | 15.6944 | 38.5753 | 28.0242 | 13.172
1 | 1.5 | 10 | 40.0538 | 26.9489 | 16.9355 | 52.0089 | 38.4673 | 22.0982 | 56.0484 | 43.8844 | 30.2419 | 71.3194 | 62.7083 | 56.1111 | 78.4946 | 71.707 | 64.5161 | 81.25 | 77.5 | 68.8889 | 86.9624 | 79.0995 | 70.6317 | 80.4435 | 72.8495 | 63.8441 | 67.9861 | 57.9861 | 46.9444 | 46.2366 | 39.6505 | 25.6048 | 43.6806 | 31.8056 | 17.0833 | 41.5323 | 30.7124 | 14.9866
1 | 1.5 | 11 | 41.6667 | 27.8898 | 18.2796 | 52.9018 | 39.2113 | 22.8423 | 57.8629 | 45.6317 | 31.4516 | 73.9583 | 64.9306 | 57.6389 | 80.3763 | 75.2016 | 67.0027 | 82.7083 | 79.4444 | 69.9306 | 88.7097 | 81.6532 | 72.8495 | 82.1909 | 74.328 | 65.457 | 71.5278 | 59.5833 | 48.125 | 47.1774 | 41.5995 | 27.1505 | 44.8611 | 33.4722 | 17.7778 | 42.3387 | 32.1237 | 15.457
1 | 1.5 | 12 | 41.8011 | 27.957 | 18.5484 | 53.1994 | 39.2755 | 22.9167 | 58.3333 | 45.9005 | 32.0565 | 74.1667 | 65.3472 | 58.2639 | 81.3172 | 75.8065 | 68.414 | 83.2639 | 79.7222 | 70.1389 | 88.9785 | 82.5941 | 73.3199 | 82.9301 | 74.4624 | 66.5995 | 71.8056 | 60.0694 | 48.75 | 47.7823 | 41.9355 | 27.4194 | 45.4861 | 33.75 | 17.8472 | 42.6075 | 32.5269 | 15.6586
1 | 1.5 | 15 | 41.9355 | 28.0242 | 18.6156 | 53.2738 | 39.3473 | 22.9911 | 58.4677 | 45.9677 | 32.0565 | 74.2361 | 65.3472 | 58.3333 | 81.586 | 76.0081 | 68.6156 | 83.5417 | 79.8611 | 70.1389 | 89.0457 | 82.7957 | 73.7231 | 83.1317 | 74.5296 | 66.7339 | 71.875 | 60.2083 | 48.75 | 47.8495 | 41.9355 | 27.621 | 45.5556 | 33.75 | 18.0556 | 42.6075 | 32.6613 | 15.7258
1 | 1.5 | 20 | 41.9355 | 28.0242 | 18.6156 | 53.2738 | 39.3473 | 22.9911 | 58.4677 | 45.9677 | 32.0565 | 74.2361 | 65.3472 | 58.3333 | 81.586 | 76.0081 | 68.6156 | 83.5417 | 79.8611 | 70.1389 | 89.0457 | 82.7957 | 73.7231 | 83.1317 | 74.5296 | 66.7339 | 71.875 | 60.2083 | 48.75 | 47.8495 | 41.9355 | 27.621 | 45.5556 | 33.75 | 18.0556 | 42.6075 | 32.6613 | 15.7258
1 | 1.5 | 25 | 41.9355 | 28.0242 | 18.6156 | 53.2738 | 39.3473 | 22.9911 | 58.4677 | 45.9677 | 32.0565 | 74.2361 | 65.3472 | 58.3333 | 81.586 | 76.0081 | 68.6156 | 83.5417 | 79.8611 | 70.1389 | 89.0457 | 82.7957 | 73.7231 | 83.1317 | 74.5296 | 66.7339 | 71.875 | 60.2083 | 48.75 | 47.8495 | 41.9355 | 27.621 | 45.5556 | 33.75 | 18.0556 | 42.6075 | 32.6613 | 15.7258
1 | 1.75 | 2 | 2.4194 | 0.87366 | 0.13441 | 2.8505 | 1.3393 | 0.50287 | 3.4946 | 1.5457 | 0.67204 | 4.9306 | 3.5417 | 1.7361 | 5.578 | 2.957 | 1.5457 | 8.0556 | 3.9583 | 2.3611 | 6.1156 | 3.4274 | 1.6801 | 5.5108 | 3.4274 | 1.8145 | 3.9583 | 2.1528 | 0.90278 | 2.4866 | 1.4785 | 0.53763 | 2.3611 | 1.1806 | 0.41667 | 3.2258 | 1.3441 | 0.26882
1 | 1.75 | 4 | 9.4086 | 4.3683 | 2.3522 | 12.3512 | 8.1922 | 2.9018 | 13.6425 | 8.2661 | 5.1075 | 19.4444 | 14.7917 | 9.9306 | 20.6989 | 15.8602 | 10.8871 | 26.3194 | 16.7361 | 13.3333 | 22.6478 | 16.8011 | 11.2903 | 21.8414 | 16.5323 | 11.4919 | 15.5556 | 11.1806 | 5.1389 | 11.1559 | 6.7876 | 4.3683 | 10.1389 | 6.0417 | 2.5 | 9.7446 | 6.7876 | 1.8145
1 | 1.75 | 6 | 24.2608 | 12.164 | 7.5269 | 27.0089 | 18.6063 | 9.375 | 29.1667 | 23.0511 | 13.6425 | 39.5139 | 33.6806 | 25.1389 | 43.2124 | 39.1801 | 29.4355 | 50.625 | 41.6667 | 30.625 | 46.9086 | 39.7849 | 32.1909 | 44.4892 | 36.7608 | 29.3683 | 37.1528 | 30.625 | 20.2778 | 24.7312 | 18.0108 | 11.2903 | 21.0417 | 14.9306 | 9.1667 | 21.9758 | 14.3145 | 6.5188
1 | 1.75 | 8 | 36.8952 | 23.7231 | 13.9113 | 45.6255 | 36.6225 | 18.1548 | 48.6559 | 37.9704 | 26.7473 | 63.6806 | 54.7917 | 46.5278 | 67.9435 | 62.4328 | 53.4274 | 72.9167 | 67.4306 | 55.4861 | 74.8656 | 65.7258 | 54.0323 | 67.4059 | 62.9032 | 52.6882 | 59.2361 | 50.0694 | 37.1528 | 41.0618 | 34.1398 | 22.5806 | 39.375 | 26.7361 | 17.8472 | 38.1048 | 25.2688 | 14.0457
1 | 1.75 | 9 | 42.2715 | 29.7043 | 18.3468 | 52.0089 | 43.2292 | 23.7351 | 56.7876 | 45.3629 | 33.0645 | 73.0556 | 62.5 | 54.4444 | 78.293 | 70.4301 | 62.9704 | 81.4583 | 76.1111 | 66.5972 | 84.0054 | 76.1425 | 67.6075 | 77.0161 | 71.2366 | 63.4409 | 66.9444 | 56.9444 | 47.0139 | 46.8414 | 40.793 | 29.0323 | 44.3056 | 34.1667 | 21.875 | 43.5484 | 32.0565 | 16.6667
1 | 1.75 | 10 | 47.1102 | 35.8199 | 21.707 | 58.9286 | 47.8756 | 27.1885 | 64.7177 | 51.5457 | 39.1129 | 79.6528 | 68.8889 | 62.7778 | 83.1317 | 76.9489 | 70.5645 | 86.25 | 82.9861 | 73.6111 | 90.5914 | 84.0726 | 75.5376 | 83.4677 | 77.4866 | 68.8844 | 73.4722 | 63.1944 | 53.0556 | 53.2258 | 45.4973 | 33.7366 | 50.4861 | 38.0556 | 25.5556 | 48.3199 | 37.0296 | 20.7661
1 | 1.75 | 11 | 50.2016 | 37.0968 | 24.1263 | 63.8393 | 49.9153 | 29.1718 | 69.086 | 56.8548 | 43.414 | 82.5694 | 73.6806 | 65.625 | 87.4328 | 81.9892 | 75.9409 | 88.6806 | 85.625 | 77.9861 | 93.75 | 88.1048 | 78.6962 | 86.8952 | 80.5108 | 73.3199 | 79.5139 | 67.3611 | 55.5556 | 56.586 | 48.8575 | 38.7097 | 55.2083 | 41.5972 | 27.5 | 50.2688 | 38.9785 | 22.3118
1 | 1.75 | 12 | 50.8065 | 37.836 | 25 | 64.881 | 50.136 | 30.5804 | 71.7742 | 57.8629 | 44.3548 | 83.6111 | 75.0694 | 66.25 | 88.7769 | 84.4086 | 78.629 | 89.4444 | 86.8056 | 79.5139 | 95.0269 | 88.7097 | 80.8468 | 88.6425 | 81.9892 | 74.5296 | 79.9306 | 68.6111 | 57.6389 | 58.1317 | 51.0081 | 40.5242 | 56.875 | 43.75 | 28.1944 | 50.672 | 39.8522 | 23.1855
1 | 1.75 | 15 | 50.9409 | 38.5753 | 25.4704 | 65.7738 | 50.2104 | 30.878 | 72.1774 | 57.8629 | 44.6909 | 84.0278 | 75.3472 | 66.4583 | 88.9113 | 85.0134 | 79.1667 | 89.6528 | 86.9444 | 79.6528 | 95.1613 | 89.3145 | 81.5188 | 88.9113 | 82.2581 | 75 | 80.1389 | 69.375 | 58.2639 | 58.6694 | 51.5457 | 41.3978 | 57.5694 | 44.0278 | 28.75 | 51.2097 | 40.3226 | 23.3871
1 | 1.75 | 20 | 50.9409 | 38.5753 | 25.4704 | 65.7738 | 50.2104 | 30.878 | 72.1774 | 57.8629 | 44.6909 | 84.0278 | 75.3472 | 66.4583 | 88.9113 | 85.0134 | 79.1667 | 89.6528 | 86.9444 | 79.6528 | 95.1613 | 89.3145 | 81.5188 | 88.9113 | 82.2581 | 75 | 80.1389 | 69.375 | 58.2639 | 58.6694 | 51.5457 | 41.3978 | 57.6389 | 44.0278 | 28.75 | 51.2097 | 40.3226 | 23.3871
1 | 1.75 | 25 | 50.9409 | 38.5753 | 25.4704 | 65.7738 | 50.2104 | 30.878 | 72.1774 | 57.8629 | 44.6909 | 84.0278 | 75.3472 | 66.4583 | 88.9113 | 85.0134 | 79.1667 | 89.6528 | 86.9444 | 79.6528 | 95.1613 | 89.3145 | 81.5188 | 88.9113 | 82.2581 | 75 | 80.1389 | 69.375 | 58.2639 | 58.6694 | 51.5457 | 41.3978 | 57.6389 | 44.0278 | 28.75 | 51.2097 | 40.3226 | 23.3871
1 | 2 | 2 | 2.4194 | 0.87366 | 0.13441 | 2.8505 | 1.3393 | 0.50287 | 3.4946 | 1.6129 | 0.73925 | 5.0694 | 3.6111 | 1.7361 | 5.578 | 2.957 | 1.5457 | 8.125 | 3.9583 | 2.3611 | 6.1156 | 3.4274 | 1.6801 | 5.5108 | 3.4274 | 1.8145 | 3.9583 | 2.1528 | 1.0417 | 2.621 | 1.5457 | 0.53763 | 2.6389 | 1.25 | 0.41667 | 3.2258 | 1.3441 | 0.26882
1 | 2 | 4 | 9.4086 | 4.5699 | 2.621 | 12.6488 | 8.7054 | 3.125 | 13.7097 | 8.8038 | 5.5108 | 19.4444 | 14.8611 | 10.2778 | 20.9005 | 15.8602 | 11.0215 | 26.3194 | 16.7361 | 13.3333 | 22.6478 | 16.8011 | 11.2903 | 21.8414 | 16.5323 | 11.4919 | 15.5556 | 11.3889 | 5.8333 | 11.1559 | 6.9892 | 4.3683 | 10.2083 | 6.3194 | 2.7083 | 10.1478 | 7.5269 | 2.0161
1 | 2 | 6 | 24.7984 | 13.8532 | 7.9973 | 27.6786 | 19.5402 | 9.4494 | 30.0403 | 23.5215 | 14.2473 | 40 | 34.3056 | 26.5972 | 43.2124 | 39.3145 | 29.5027 | 50.625 | 41.6667 | 30.625 | 46.9086 | 39.7849 | 32.1909 | 44.4892 | 37.0296 | 29.3683 | 37.5 | 30.9028 | 20.625 | 25.4704 | 18.8172 | 12.3656 | 21.3194 | 15.9028 | 9.9306 | 23.1855 | 15.2554 | 7.6613
1 | 2 | 8 | 38.5081 | 25.4032 | 15.9946 | 47.5934 | 38.1466 | 18.8988 | 49.9328 | 39.7849 | 28.8978 | 66.875 | 56.4583 | 47.8472 | 68.2124 | 63.4409 | 53.7634 | 73.0556 | 68.0556 | 56.1111 | 75 | 65.793 | 54.0995 | 68.0108 | 63.0376 | 53.3602 | 60.0694 | 51.4583 | 38.75 | 43.078 | 35.6183 | 25 | 40.5556 | 28.5417 | 20.5556 | 40.7258 | 28.0242 | 16.3306
1 | 2 | 9 | 45.0269 | 32.8629 | 21.9086 | 55.4315 | 46.9494 | 25.9673 | 60.4167 | 47.5806 | 37.0968 | 74.7917 | 65.2083 | 57.9167 | 79.5027 | 71.9086 | 64.6505 | 82.6389 | 77.6389 | 68.1944 | 85.5511 | 76.8817 | 68.414 | 78.0914 | 72.5806 | 64.2473 | 69.0278 | 58.9583 | 50 | 49.8656 | 42.8091 | 32.1237 | 46.8056 | 36.25 | 25 | 47.4462 | 34.543 | 19.8253
1 | 2 | 10 | 52.2177 | 38.5753 | 25.672 | 63.1696 | 52.8274 | 33.5565 | 70.9677 | 56.3844 | 44.4892 | 83.8194 | 73.0556 | 67.1528 | 85.8199 | 79.4355 | 73.7231 | 89.0278 | 84.7222 | 77.7778 | 92.2715 | 85.8871 | 78.1586 | 85.1478 | 79.2339 | 73.2527 | 76.8056 | 65.9722 | 57.4306 | 57.7957 | 50.2016 | 37.9032 | 54.4444 | 43.6111 | 31.8056 | 54.5027 | 40.5242 | 24.5968
1 | 2 | 11 | 56.6532 | 42.6075 | 30.7124 | 69.7173 | 56.994 | 36.2351 | 77.3522 | 63.2392 | 51.4785 | 87.7778 | 78.8194 | 71.4583 | 90.457 | 85.0134 | 80.8468 | 92.1528 | 88.5417 | 83.6806 | 95.4301 | 90.793 | 82.9301 | 88.8441 | 84.4086 | 79.3683 | 82.7778 | 72.5 | 64.0278 | 64.4489 | 54.3683 | 46.3038 | 61.3889 | 49.7917 | 37.1528 | 57.7285 | 43.6156 | 29.0995
1 | 2 | 12 | 59.8118 | 44.086 | 34.4086 | 72.4702 | 59.9702 | 39.1754 | 80.1075 | 66.129 | 53.5618 | 91.0417 | 82.5694 | 74.5139 | 92.8091 | 88.3065 | 83.9382 | 93.1944 | 89.7917 | 85.7639 | 96.9758 | 92.7419 | 85.3495 | 91.1962 | 87.5 | 81.3172 | 83.4722 | 74.7917 | 66.4583 | 68.6828 | 57.9301 | 49.9328 | 63.8194 | 51.4583 | 38.8889 | 60.1478 | 46.4382 | 31.3172
1 | 2 | 15 | 63.1048 | 45.0941 | 36.6935 | 73.3631 | 60.9606 | 39.7655 | 81.3172 | 66.8683 | 54.4355 | 91.7361 | 83.5417 | 76.1111 | 93.414 | 89.8522 | 85.6183 | 93.8889 | 90.4167 | 86.4583 | 97.1774 | 93.3468 | 86.4919 | 92.4731 | 88.172 | 81.9892 | 84.7917 | 75.9722 | 68.0556 | 71.5726 | 60.1478 | 52.5538 | 66.1111 | 53.3333 | 40.1389 | 60.9543 | 49.3952 | 32.1909
1 | 2 | 20 | 63.1048 | 45.0941 | 36.6935 | 73.3631 | 60.9606 | 39.7655 | 81.3172 | 66.8683 | 54.4355 | 91.7361 | 83.5417 | 76.1111 | 93.414 | 89.9866 | 85.6183 | 93.8889 | 90.4167 | 86.5278 | 97.1774 | 93.3468 | 86.5591 | 92.4731 | 88.172 | 81.9892 | 84.8611 | 76.0417 | 68.0556 | 71.5726 | 60.1478 | 52.5538 | 66.1111 | 53.3333 | 40.2083 | 60.9543 | 49.3952 | 32.1909
1 | 2 | 25 | 63.1048 | 45.0941 | 36.6935 | 73.3631 | 60.9606 | 39.7655 | 81.3172 | 66.8683 | 54.4355 | 91.7361 | 83.5417 | 76.1111 | 93.414 | 89.9866 | 85.6183 | 93.8889 | 90.4167 | 86.5278 | 97.1774 | 93.3468 | 86.5591 | 92.4731 | 88.172 | 81.9892 | 84.8611 | 76.0417 | 68.0556 | 71.5726 | 60.1478 | 52.5538 | 66.1111 | 53.3333 | 40.2083 | 60.9543 | 49.3952 | 32.1909
1 | 2.25 | 2 | 2.4194 | 1.0081 | 0.13441 | 2.8505 | 1.3393 | 0.58498 | 3.4946 | 1.6129 | 0.73925 | 5.0694 | 3.6111 | 1.7361 | 5.578 | 2.957 | 1.5457 | 8.125 | 3.9583 | 2.3611 | 6.1156 | 3.4274 | 1.6801 | 5.5108 | 3.4274 | 1.8145 | 3.9583 | 2.2222 | 1.0417 | 2.621 | 1.5457 | 0.53763 | 2.6389 | 1.25 | 0.41667 | 3.293 | 1.3441 | 0.26882
1 | 2.25 | 4 | 9.543 | 4.6371 | 2.621 | 12.6488 | 8.8542 | 3.497 | 13.7097 | 8.8038 | 5.5108 | 19.4444 | 14.9306 | 10.2778 | 20.9005 | 15.8602 | 11.0215 | 26.3194 | 16.7361 | 13.3333 | 22.6478 | 16.8011 | 11.2903 | 21.8414 | 16.5323 | 11.4919 | 15.5556 | 11.5278 | 5.9028 | 11.1559 | 7.1237 | 4.3683 | 10.4861 | 6.5278 | 2.7083 | 10.3495 | 7.5269 | 2.2177
1 | 2.25 | 6 | 25.0672 | 14.5833 | 8.3333 | 28.2738 | 20.1149 | 10.119 | 30.4435 | 23.5215 | 14.5833 | 40 | 34.6528 | 27.7083 | 43.2124 | 39.3145 | 29.5027 | 50.625 | 41.6667 | 30.7639 | 46.9086 | 39.7849 | 32.1909 | 44.4892 | 37.0296 | 29.3683 | 37.6389 | 30.9028 | 20.625 | 25.672 | 19.3548 | 12.6344 | 21.5972 | 16.5278 | 10.5556 | 23.9919 | 15.8602 | 7.7957
1 | 2.25 | 8 | 39.3145 | 26.6801 | 17.0699 | 48.4811 | 38.7213 | 19.494 | 51.7473 | 41.4651 | 30.1075 | 67.3611 | 57.1528 | 49.0972 | 68.4812 | 63.6425 | 53.8978 | 73.0556 | 68.0556 | 56.3194 | 75 | 65.793 | 54.0995 | 68.414 | 63.2392 | 53.4274 | 60.2778 | 52.1528 | 39.375 | 44.0188 | 36.0215 | 26.2769 | 40.8333 | 29.6528 | 21.4583 | 42.3387 | 29.5699 | 17.4731
1 | 2.25 | 9 | 46.371 | 34.4086 | 24.4624 | 56.9196 | 49.256 | 26.7113 | 61.5591 | 48.9919 | 38.9113 | 75.0694 | 66.25 | 60.1389 | 79.7043 | 72.5806 | 65.3226 | 82.8472 | 78.8889 | 68.9583 | 86.4247 | 77.0833 | 68.414 | 78.9651 | 72.8495 | 65.2554 | 69.6528 | 60.0694 | 50.9028 | 51.3441 | 44.2876 | 33.7366 | 48.2639 | 38.4028 | 26.5278 | 49.3952 | 37.0968 | 21.5726
1 | 2.25 | 10 | 55.4435 | 41.8683 | 28.9651 | 64.6577 | 56.1756 | 36.3095 | 74.328 | 58.6694 | 47.379 | 84.6528 | 74.7222 | 69.5139 | 86.4919 | 80.914 | 75.0672 | 89.9306 | 85.7639 | 79.375 | 93.414 | 86.5591 | 79.1667 | 85.3495 | 80.4435 | 74.2608 | 78.6806 | 67.8472 | 59.8611 | 60.5511 | 52.5538 | 39.9866 | 57.5694 | 46.5278 | 34.1667 | 57.3253 | 43.8172 | 27.2849
1 | 2.25 | 11 | 61.7608 | 46.5054 | 35.1478 | 71.6518 | 61.8304 | 39.9554 | 80.914 | 67.2715 | 55.1747 | 89.5139 | 82.0833 | 76.25 | 92.4731 | 86.6935 | 82.5941 | 93.125 | 90.2778 | 86.25 | 96.1694 | 92.0699 | 84.8118 | 90.5242 | 87.7688 | 81.0484 | 85.2083 | 74.9306 | 67.9861 | 70.0941 | 58.2661 | 49.7984 | 63.125 | 54.4444 | 42.0139 | 61.1559 | 50.2688 | 36.2231
1 | 2.25 | 12 | 66.4651 | 49.2608 | 39.4489 | 76.2649 | 65.997 | 44.494 | 84.1398 | 71.4382 | 59.4086 | 92.7083 | 85.9028 | 79.9306 | 95.0941 | 90.7258 | 87.7016 | 94.7222 | 92.0833 | 88.9583 | 98.1183 | 94.3548 | 87.164 | 93.8844 | 91.2634 | 84.4086 | 87.2222 | 80 | 72.5 | 75.2688 | 62.7688 | 54.9731 | 69.7917 | 59.3056 | 46.3194 | 64.5833 | 54.1667 | 39.2473
1 | 2.25 | 15 | 71.7742 | 52.8898 | 43.078 | 78.3482 | 68.006 | 48.3682 | 86.4247 | 73.6559 | 63.3737 | 94.9306 | 87.9861 | 83.5417 | 96.9086 | 93.5484 | 90.457 | 95.8333 | 93.125 | 90.625 | 98.8575 | 96.1022 | 89.1129 | 95.9677 | 92.0699 | 86.5591 | 90.1389 | 82.7083 | 74.7917 | 78.1586 | 66.2634 | 61.4247 | 73.5417 | 63.6111 | 50.4167 | 66.9355 | 57.5941 | 41.9355
1 | 2.25 | 20 | 71.7742 | 52.8898 | 43.2124 | 78.4226 | 68.006 | 48.4426 | 86.4247 | 73.9247 | 63.3737 | 94.9306 | 87.9861 | 83.5417 | 96.9086 | 93.5484 | 90.5914 | 95.9028 | 93.125 | 90.625 | 98.8575 | 96.1022 | 89.1801 | 95.9677 | 92.0699 | 86.5591 | 90.4167 | 82.7083 | 74.9306 | 78.293 | 66.3978 | 61.4247 | 73.6111 | 63.8194 | 50.6944 | 67.0027 | 57.7957 | 41.9355
1 | 2.25 | 25 | 71.7742 | 52.8898 | 43.2124 | 78.4226 | 68.006 | 48.4426 | 86.4247 | 73.9247 | 63.3737 | 94.9306 | 87.9861 | 83.5417 | 96.9086 | 93.5484 | 90.5914 | 95.9028 | 93.125 | 90.625 | 98.8575 | 96.1022 | 89.1801 | 95.9677 | 92.0699 | 86.5591 | 90.4167 | 82.7083 | 74.9306 | 78.293 | 66.3978 | 61.4247 | 73.6111 | 63.8194 | 50.6944 | 67.0027 | 57.7957 | 41.9355
1 | 2.5 | 2 | 2.4194 | 1.0081 | 0.20161 | 2.8505 | 1.388 | 0.58498 | 3.4946 | 1.6129 | 0.73925 | 5.0694 | 3.6111 | 1.7361 | 5.7124 | 2.957 | 1.5457 | 8.125 | 3.9583 | 2.3611 | 6.1156 | 3.4274 | 1.6801 | 5.5108 | 3.4274 | 1.8145 | 3.9583 | 2.2222 | 1.0417 | 2.621 | 1.5457 | 0.53763 | 2.6389 | 1.25 | 0.41667 | 3.293 | 1.3441 | 0.33602
1 | 2.5 | 4 | 9.543 | 4.7715 | 2.621 | 12.6488 | 9.0774 | 3.869 | 13.7097 | 8.8038 | 5.5108 | 19.4444 | 14.9306 | 10.2778 | 20.9005 | 15.8602 | 11.0215 | 26.3194 | 16.7361 | 13.3333 | 22.6478 | 16.8011 | 11.2903 | 21.8414 | 16.5323 | 11.4919 | 15.5556 | 11.5278 | 5.9028 | 11.1559 | 7.3253 | 4.3683 | 10.4861 | 6.5278 | 2.7083 | 10.4839 | 7.5269 | 2.6882
1 | 2.5 | 6 | 25.0672 | 14.6505 | 8.3333 | 28.497 | 20.546 | 10.7887 | 30.4435 | 23.5215 | 14.6505 | 40 | 35 | 27.7083 | 43.2124 | 39.3145 | 29.5027 | 50.625 | 41.6667 | 30.7639 | 46.9086 | 39.7849 | 32.1909 | 44.4892 | 37.0296 | 29.3683 | 37.9861 | 30.9028 | 20.625 | 25.672 | 19.6909 | 12.6344 | 21.5972 | 16.6667 | 10.9028 | 24.664 | 16.0618 | 7.8629
1 | 2.5 | 8 | 39.3817 | 27.4194 | 17.8763 | 49.1456 | 39.5833 | 19.6429 | 52.0833 | 41.6667 | 31.1828 | 67.3611 | 57.5 | 49.375 | 68.4812 | 63.7769 | 53.8978 | 73.0556 | 68.0556 | 56.3194 | 75 | 65.793 | 54.0995 | 68.6156 | 63.3065 | 53.4274 | 60.2778 | 52.6389 | 39.7222 | 44.8253 | 36.1559 | 26.6801 | 41.25 | 30.2083 | 21.875 | 43.1452 | 29.7715 | 18.4812
1 | 2.5 | 9 | 47.379 | 35.4405 | 25.4032 | 58.3333 | 50.0744 | 27.5298 | 62.164 | 49.9328 | 39.7849 | 75.4167 | 68.0556 | 61.3194 | 80.0403 | 73.1855 | 65.3226 | 82.9861 | 78.9583 | 69.0278 | 86.828 | 77.0833 | 68.414 | 79.0323 | 72.9839 | 65.3226 | 69.7917 | 60.5556 | 51.1806 | 51.9489 | 45.1613 | 34.8118 | 49.5833 | 39.2361 | 27.5 | 50.336 | 37.9704 | 23.5215
1 | 2.5 | 10 | 56.6532 | 44.086 | 31.7204 | 66.0997 | 57.2942 | 37.3512 | 75.2016 | 59.9462 | 49.1263 | 84.8611 | 76.4583 | 70.3472 | 86.7608 | 81.586 | 75.4032 | 90.4861 | 86.1111 | 79.5139 | 93.8844 | 86.6935 | 79.8387 | 85.8871 | 80.8468 | 74.7312 | 79.0278 | 68.5417 | 60.7639 | 61.828 | 53.9651 | 41.5323 | 59.5139 | 48.5417 | 35.7639 | 58.6694 | 45.0941 | 29.8387
1 | 2.5 | 11 | 63.9785 | 50.6048 | 37.5672 | 73.3811 | 64.8373 | 43.1548 | 82.2581 | 69.086 | 56.5188 | 90.0694 | 83.9583 | 77.8472 | 92.9435 | 87.2312 | 83.0645 | 93.8194 | 90.9028 | 86.7361 | 96.8414 | 92.4731 | 85.7527 | 91.5995 | 88.4409 | 81.9892 | 86.1806 | 76.4583 | 70.4861 | 71.1694 | 60.2151 | 51.6801 | 65.8333 | 56.7361 | 44.0972 | 63.0376 | 52.2849 | 40.5242
1 | 2.5 | 12 | 69.8925 | 55.914 | 42.8763 | 80.1083 | 69.8917 | 49.3304 | 86.2231 | 74.4624 | 63.2392 | 93.4722 | 87.9861 | 83.5417 | 95.6989 | 91.9355 | 89.4489 | 96.1806 | 93.4722 | 90.2083 | 99.2608 | 96.371 | 88.9113 | 96.707 | 92.6075 | 86.4247 | 89.8611 | 83.1944 | 76.1111 | 77.4866 | 65.0538 | 59.3414 | 72.6389 | 63.6806 | 49.9306 | 69.2204 | 57.8629 | 44.2876
1 | 2.5 | 15 | 79.0995 | 63.5081 | 48.7903 | 84.1518 | 74.1815 | 55.3058 | 90.457 | 78.1586 | 70.5645 | 96.4583 | 91.5972 | 88.125 | 98.3871 | 96.1022 | 93.2796 | 97.3611 | 95.2083 | 92.9861 | 100 | 98.1183 | 92.0699 | 98.2527 | 93.8844 | 89.6505 | 93.2639 | 88.0556 | 80.2778 | 84.7446 | 73.8575 | 67.3387 | 80.1389 | 70.9722 | 56.9444 | 75.4032 | 65.7258 | 49.7312
1 | 2.5 | 20 | 79.4355 | 63.7097 | 49.0591 | 84.1518 | 74.4048 | 55.4521 | 90.5242 | 78.5618 | 70.6317 | 96.6667 | 91.8056 | 88.2639 | 98.3871 | 96.1022 | 93.6156 | 97.3611 | 95.2083 | 93.125 | 100 | 98.1855 | 92.2043 | 98.2527 | 93.9516 | 89.7177 | 93.2639 | 88.0556 | 80.4167 | 85.2151 | 74.0591 | 67.6747 | 80.2083 | 71.6667 | 57.7083 | 75.672 | 66.1962 | 50.1344
1 | 2.5 | 25 | 79.4355 | 63.7097 | 49.0591 | 84.1518 | 74.4048 | 55.4521 | 90.5242 | 78.5618 | 70.6317 | 96.6667 | 91.8056 | 88.2639 | 98.3871 | 96.1022 | 93.6156 | 97.3611 | 95.2083 | 93.125 | 100 | 98.1855 | 92.2043 | 98.2527 | 93.9516 | 89.7177 | 93.2639 | 88.0556 | 80.4167 | 85.2823 | 74.0591 | 67.6747 | 80.2083 | 71.6667 | 57.7083 | 75.672 | 66.1962 | 50.1344
1 | 2.75 | 2 | 2.4194 | 1.0081 | 0.20161 | 2.8736 | 1.388 | 0.58498 | 3.4946 | 1.6129 | 0.73925 | 5.0694 | 3.6111 | 1.7361 | 5.7124 | 2.957 | 1.5457 | 8.125 | 3.9583 | 2.3611 | 6.1156 | 3.4274 | 1.6801 | 5.5108 | 3.4274 | 1.8145 | 3.9583 | 2.2222 | 1.0417 | 2.621 | 1.5457 | 0.53763 | 2.6389 | 1.25 | 0.41667 | 3.293 | 1.3441 | 0.40323
1 | 2.75 | 4 | 9.543 | 4.7715 | 2.621 | 12.9464 | 9.0774 | 3.869 | 13.7097 | 8.8038 | 5.5108 | 19.4444 | 14.9306 | 10.2778 | 20.9005 | 15.8602 | 11.0215 | 26.3194 | 16.7361 | 13.3333 | 22.6478 | 16.8011 | 11.2903 | 21.8414 | 16.5323 | 11.4919 | 15.5556 | 11.5278 | 5.9028 | 11.1559 | 7.3253 | 4.3683 | 10.4861 | 6.5278 | 2.7778 | 10.4839 | 7.5941 | 2.7554
1 | 2.75 | 6 | 25.0672 | 14.6505 | 8.4677 | 28.497 | 20.546 | 11.0119 | 30.4435 | 23.5215 | 14.6505 | 40 | 35 | 27.8472 | 43.2124 | 39.3145 | 29.5027 | 50.625 | 41.6667 | 30.7639 | 46.9086 | 39.7849 | 32.1909 | 44.4892 | 37.0296 | 29.3683 | 37.9861 | 30.9028 | 20.625 | 25.672 | 19.8253 | 12.6344 | 21.5972 | 16.8056 | 11.0417 | 24.664 | 16.3306 | 8.4005
1 | 2.75 | 8 | 39.3817 | 27.5538 | 18.1452 | 49.2944 | 39.9425 | 20.5357 | 52.1505 | 41.7339 | 31.3844 | 67.3611 | 57.5 | 49.4444 | 68.4812 | 63.7769 | 53.8978 | 73.0556 | 68.0556 | 56.3194 | 75 | 65.793 | 54.0995 | 68.6156 | 63.3065 | 53.4946 | 60.2778 | 52.8472 | 39.9306 | 44.8925 | 36.1559 | 26.8145 | 41.3889 | 30.9028 | 22.1528 | 43.4812 | 29.9731 | 19.3548
1 | 2.75 | 9 | 47.5806 | 35.7527 | 26.0081 | 58.9132 | 50.5208 | 28.5714 | 62.3656 | 50.336 | 40.457 | 75.4167 | 68.4028 | 62.2222 | 80.0403 | 73.1855 | 65.3226 | 82.9861 | 78.9583 | 69.0278 | 86.828 | 77.0833 | 68.414 | 79.0323 | 72.9839 | 65.3226 | 69.7917 | 60.9722 | 51.3889 | 52.2177 | 46.4382 | 35.4167 | 50.0694 | 39.5139 | 28.125 | 50.9409 | 38.3737 | 25.4704
1 | 2.75 | 10 | 57.2581 | 44.7581 | 33.1989 | 66.8899 | 58.2564 | 38.1696 | 75.4704 | 60.4167 | 49.7984 | 85.3472 | 77.2917 | 70.3472 | 87.0968 | 82.0565 | 75.7392 | 90.4861 | 86.3194 | 79.5833 | 93.8844 | 86.7608 | 79.9059 | 85.9543 | 81.1156 | 74.8656 | 79.0972 | 68.6111 | 62.8472 | 62.0296 | 55.0403 | 41.9355 | 61.5278 | 50.2083 | 37.0139 | 59.8118 | 45.4301 | 32.3253
1 | 2.75 | 11 | 65.3226 | 52.4866 | 39.3817 | 74.3304 | 66.0714 | 47.3214 | 83.1989 | 69.6237 | 56.9892 | 90.4861 | 84.7222 | 78.8194 | 93.1452 | 87.7016 | 83.1317 | 94.4444 | 91.3194 | 86.9444 | 96.9758 | 92.6075 | 86.6263 | 92.0027 | 88.8441 | 82.5269 | 86.3889 | 77.4306 | 71.5278 | 72.1102 | 61.2903 | 52.4194 | 69.8611 | 59.0972 | 45.9722 | 64.8522 | 52.8898 | 42.5403
1 | 2.75 | 12 | 73.1183 | 57.9973 | 46.371 | 81.9196 | 70.3869 | 55.4315 | 87.5672 | 76.8817 | 66.6667 | 93.4722 | 90.4167 | 85 | 96.3038 | 92.5403 | 90.5914 | 97.0139 | 94.375 | 91.5972 | 99.328 | 97.043 | 90.2554 | 97.3118 | 93.078 | 87.2984 | 91.0417 | 84.0972 | 78.75 | 78.6962 | 66.2634 | 61.5591 | 75.4861 | 65.8333 | 52.6389 | 71.707 | 60.5511 | 47.7151
1 | 2.75 | 15 | 82.5269 | 68.2124 | 54.3011 | 86.4045 | 79.0923 | 63.516 | 93.6828 | 82.8629 | 75.7392 | 98.125 | 94.5833 | 91.3889 | 99.2608 | 97.7823 | 95.4301 | 98.75 | 96.8056 | 94.7222 | 100 | 98.9919 | 94.5565 | 99.328 | 96.3038 | 92.1371 | 95 | 90.7639 | 83.75 | 89.7849 | 78.4946 | 72.6478 | 84.2361 | 76.25 | 62.7778 | 78.9651 | 72.4462 | 57.3925
1 | 2.75 | 20 | 82.9973 | 68.4812 | 55.0403 | 86.6969 | 79.5284 | 63.8085 | 94.1532 | 84.0726 | 75.9409 | 98.3333 | 94.7222 | 91.6667 | 99.3952 | 97.9167 | 95.6317 | 98.75 | 96.875 | 94.8611 | 100 | 98.9919 | 94.6237 | 99.328 | 96.5054 | 92.3387 | 95.5556 | 90.9722 | 84.2361 | 90.6586 | 79.5027 | 73.5887 | 84.7917 | 77.5694 | 63.9583 | 80.0403 | 72.9839 | 58.2661
1 | 2.75 | 25 | 82.9973 | 68.4812 | 55.0403 | 86.6969 | 79.5284 | 63.8085 | 94.1532 | 84.0726 | 75.9409 | 98.3333 | 94.7222 | 91.6667 | 99.3952 | 97.9167 | 95.6317 | 98.75 | 96.875 | 94.8611 | 100 | 98.9919 | 94.6237 | 99.328 | 96.5054 | 92.3387 | 95.5556 | 90.9722 | 84.2361 | 90.6586 | 79.5027 | 73.5887 | 84.7917 | 77.5694 | 63.9583 | 80.0403 | 72.9839 | 58.2661
1 | 3 | 2 | 2.4194 | 1.0081 | 0.20161 | 2.8736 | 1.388 | 0.58498 | 3.4946 | 1.6129 | 0.73925 | 5.0694 | 3.6111 | 1.7361 | 5.7124 | 2.957 | 1.5457 | 8.125 | 3.9583 | 2.3611 | 6.1156 | 3.4274 | 1.6801 | 5.5108 | 3.4274 | 1.8145 | 3.9583 | 2.2222 | 1.0417 | 2.621 | 1.5457 | 0.53763 | 2.6389 | 1.25 | 0.41667 | 3.293 | 1.3441 | 0.40323
1 | 3 | 4 | 9.543 | 4.7715 | 2.6882 | 12.9464 | 9.0774 | 3.869 | 13.7097 | 8.8038 | 5.578 | 19.4444 | 14.9306 | 10.2778 | 20.9005 | 15.8602 | 11.0215 | 26.3194 | 16.7361 | 13.3333 | 22.6478 | 16.8011 | 11.2903 | 21.8414 | 16.5323 | 11.4919 | 15.5556 | 11.5278 | 5.9028 | 11.1559 | 7.3253 | 4.3683 | 10.4861 | 6.5278 | 2.7778 | 10.6855 | 7.5941 | 2.7554
1 | 3 | 6 | 25.0672 | 14.6505 | 8.4677 | 28.497 | 20.546 | 11.0119 | 30.4435 | 23.5215 | 14.7849 | 40 | 35 | 27.8472 | 43.2124 | 39.3145 | 29.5027 | 50.625 | 41.6667 | 30.7639 | 46.9086 | 39.7849 | 32.1909 | 44.4892 | 37.0296 | 29.3683 | 37.9861 | 30.9028 | 20.625 | 25.672 | 19.8253 | 12.6344 | 21.5972 | 16.875 | 11.0417 | 24.664 | 16.4651 | 8.4005
1 | 3 | 8 | 39.3817 | 27.7554 | 18.2124 | 49.2944 | 40.7251 | 20.7589 | 52.1505 | 41.9355 | 31.7204 | 67.3611 | 57.5 | 49.4444 | 68.4812 | 63.7769 | 53.8978 | 73.0556 | 68.0556 | 56.3194 | 75 | 65.793 | 54.0995 | 68.6156 | 63.3065 | 53.4946 | 60.2778 | 52.8472 | 40.1389 | 44.8925 | 36.2231 | 27.4194 | 41.4583 | 31.1111 | 22.2917 | 43.8172 | 30.1747 | 19.9597
1 | 3 | 9 | 47.5806 | 35.8871 | 26.2097 | 58.9132 | 50.8929 | 28.7202 | 62.4328 | 50.4704 | 40.6586 | 75.4167 | 68.5417 | 62.3611 | 80.0403 | 73.1855 | 65.3226 | 82.9861 | 78.9583 | 69.0278 | 86.828 | 77.0833 | 68.414 | 79.0323 | 72.9839 | 65.3226 | 69.9306 | 60.9722 | 51.5278 | 52.4194 | 46.7742 | 35.9543 | 50.4167 | 40.0694 | 28.4722 | 51.4785 | 38.3737 | 26.6129
1 | 3 | 10 | 57.5941 | 45.2589 | 34.0054 | 67.5595 | 58.5463 | 39.0625 | 75.5376 | 60.4167 | 50.336 | 85.625 | 77.3611 | 70.3472 | 87.3656 | 82.0565 | 75.8737 | 90.4861 | 86.3889 | 79.6528 | 93.8844 | 86.7608 | 79.9059 | 86.2903 | 81.1156 | 74.8656 | 79.1667 | 68.6111 | 63.3333 | 62.4328 | 55.1747 | 43.4812 | 61.875 | 51.875 | 37.5694 | 60.8199 | 45.8333 | 33.6022
1 | 3 | 11 | 66.0618 | 53.0914 | 40.6586 | 74.9923 | 66.8155 | 49.3304 | 83.7366 | 69.8925 | 57.9301 | 90.9722 | 85.3472 | 79.2361 | 93.6828 | 88.1048 | 83.1317 | 94.6528 | 91.3889 | 87.0833 | 96.9758 | 92.6075 | 86.8952 | 92.0699 | 89.1129 | 82.6613 | 86.5972 | 77.6389 | 71.7361 | 72.379 | 62.2312 | 53.9651 | 71.25 | 60.625 | 47.2222 | 67.0699 | 53.5618 | 43.75
1 | 3 | 12 | 74.9328 | 59.4086 | 47.9839 | 82.3661 | 71.4286 | 58.1845 | 88.3065 | 77.1505 | 67.8763 | 93.9583 | 91.5278 | 85.4861 | 96.3038 | 93.3468 | 91.129 | 97.3611 | 95 | 91.875 | 99.328 | 97.043 | 91.0618 | 97.4462 | 93.3468 | 87.7016 | 91.8056 | 84.8611 | 79.5139 | 79.5027 | 67.6075 | 63.5753 | 77.0139 | 68.1944 | 54.1667 | 73.9919 | 62.7688 | 49.9328
1 | 3 | 15 | 86.6263 | 72.9167 | 58.7366 | 89.3601 | 83.631 | 69.7147 | 95.2285 | 86.7608 | 78.9651 | 98.4028 | 96.0417 | 92.9167 | 100 | 98.5887 | 96.9086 | 99.7917 | 97.8472 | 95.6944 | 100 | 99.9328 | 96.3038 | 99.664 | 98.1183 | 93.8172 | 96.875 | 92.2222 | 85.9028 | 92.2043 | 82.1237 | 77.621 | 87.9861 | 80 | 68.2639 | 82.6613 | 76.2769 | 62.9704
1 | 3 | 20 | 87.4328 | 74.1263 | 59.9462 | 89.881 | 84.5238 | 70.6589 | 96.3038 | 87.7688 | 79.5699 | 99.0278 | 96.1806 | 93.6806 | 100 | 99.1935 | 97.1774 | 99.8611 | 98.0556 | 95.7639 | 100 | 100 | 96.4382 | 99.7984 | 98.3199 | 94.086 | 96.9444 | 92.8472 | 86.9444 | 93.2796 | 84.3414 | 79.1667 | 89.1667 | 82.4306 | 70.1389 | 84.4758 | 77.6882 | 64.9194
1 | 3 | 25 | 87.4328 | 74.1263 | 59.9462 | 89.881 | 84.5238 | 70.6589 | 96.3038 | 87.7688 | 79.5699 | 99.0278 | 96.1806 | 93.6806 | 100 | 99.1935 | 97.1774 | 99.8611 | 98.0556 | 95.7639 | 100 | 100 | 96.4382 | 99.7984 | 98.3199 | 94.086 | 96.9444 | 92.8472 | 86.9444 | 93.2796 | 84.3414 | 79.1667 | 89.1667 | 82.4306 | 70.1389 | 84.4758 | 77.6882 | 64.9194
1 | 3.25 | 2 | 2.4194 | 1.0081 | 0.20161 | 2.9454 | 1.388 | 0.58498 | 3.4946 | 1.6129 | 0.73925 | 5.0694 | 3.6111 | 1.7361 | 5.7124 | 2.957 | 1.5457 | 8.125 | 3.9583 | 2.3611 | 6.1156 | 3.4274 | 1.6801 | 5.5108 | 3.4274 | 1.8145 | 3.9583 | 2.2222 | 1.0417 | 2.621 | 1.5457 | 0.53763 | 2.6389 | 1.25 | 0.41667 | 3.293 | 1.3441 | 0.40323
1 | 3.25 | 4 | 9.543 | 4.7715 | 2.6882 | 12.9464 | 9.0774 | 3.869 | 13.7097 | 8.8038 | 5.7124 | 19.4444 | 14.9306 | 10.2778 | 20.9005 | 15.8602 | 11.0215 | 26.3194 | 16.7361 | 13.3333 | 22.6478 | 16.8011 | 11.2903 | 21.8414 | 16.5323 | 11.4919 | 15.5556 | 11.5278 | 5.9028 | 11.1559 | 7.3253 | 4.3683 | 10.4861 | 6.5278 | 2.7778 | 10.6855 | 7.5941 | 2.7554
1 | 3.25 | 6 | 25.0672 | 14.6505 | 8.4677 | 28.497 | 20.546 | 11.0119 | 30.4435 | 23.5215 | 14.9866 | 40 | 35 | 27.8472 | 43.2124 | 39.3145 | 29.5027 | 50.625 | 41.6667 | 30.7639 | 46.9086 | 39.7849 | 32.1909 | 44.4892 | 37.0296 | 29.3683 | 37.9861 | 30.9028 | 20.625 | 25.672 | 19.8253 | 12.6344 | 21.5972 | 16.875 | 11.0417 | 24.664 | 16.4651 | 8.4005
1 | 3.25 | 8 | 39.3817 | 27.7554 | 18.2796 | 49.2944 | 40.9406 | 20.8333 | 52.1505 | 41.9355 | 31.7204 | 67.3611 | 57.5 | 49.5139 | 68.4812 | 63.7769 | 53.8978 | 73.0556 | 68.0556 | 56.3194 | 75 | 65.793 | 54.0995 | 68.6156 | 63.3065 | 53.4946 | 60.2778 | 52.8472 | 40.1389 | 44.8925 | 36.2903 | 27.4194 | 41.4583 | 31.1111 | 22.3611 | 43.8844 | 30.3091 | 20.2957
1 | 3.25 | 9 | 47.5806 | 35.9543 | 26.4113 | 58.9132 | 51.3239 | 28.9435 | 62.4328 | 50.6048 | 40.6586 | 75.4167 | 68.5417 | 62.4306 | 80.0403 | 73.1855 | 65.3226 | 82.9861 | 78.9583 | 69.0278 | 86.828 | 77.0833 | 68.414 | 79.0323 | 72.9839 | 65.3226 | 70 | 60.9722 | 51.6667 | 52.4866 | 47.1102 | 36.0887 | 50.6944 | 40.1389 | 28.6111 | 52.0833 | 38.3737 | 27.1505
1 | 3.25 | 10 | 57.7285 | 45.6989 | 34.543 | 67.9315 | 58.6925 | 39.4345 | 75.5376 | 60.4167 | 50.7392 | 85.625 | 77.5694 | 70.3472 | 87.3656 | 82.0565 | 75.8737 | 90.4861 | 86.3889 | 79.6528 | 93.8844 | 86.7608 | 79.9059 | 86.4247 | 81.1156 | 74.8656 | 79.1667 | 68.6111 | 63.6111 | 62.4328 | 55.3091 | 43.8844 | 62.0833 | 52.0139 | 37.6389 | 61.5591 | 45.9005 | 34.1398
1 | 3.25 | 11 | 67.0027 | 53.5975 | 42.6747 | 75.6542 | 66.9643 | 50 | 83.871 | 70.4301 | 58.6694 | 91.25 | 85.625 | 79.7917 | 93.6828 | 88.172 | 83.2661 | 94.7917 | 91.5278 | 87.0833 | 96.9758 | 92.6075 | 86.9624 | 92.0699 | 89.1129 | 82.9301 | 86.7361 | 77.7778 | 72.0833 | 72.6478 | 62.6344 | 54.7043 | 72.0833 | 61.3194 | 47.9861 | 67.7419 | 54.5027 | 44.422
1 | 3.25 | 12 | 76.2769 | 60.4839 | 49.5296 | 83.4077 | 72.2342 | 59.4494 | 89.1129 | 77.4194 | 68.414 | 94.1667 | 92.0833 | 85.8333 | 96.3038 | 93.5484 | 91.1962 | 97.6389 | 95.1389 | 92.0833 | 99.328 | 97.043 | 91.2634 | 97.4462 | 93.6828 | 87.9704 | 92.0833 | 85.0694 | 79.8611 | 79.7715 | 68.6828 | 64.4489 | 77.4306 | 69.5833 | 55 | 74.664 | 63.172 | 52.0161
1 | 3.25 | 15 | 88.8441 | 75.672 | 65.5914 | 91.5179 | 86.2351 | 72.7525 | 95.9677 | 88.8441 | 81.5188 | 99.1667 | 97.1528 | 94.0278 | 100 | 99.0591 | 97.9839 | 100 | 98.8889 | 96.25 | 100 | 100 | 96.8414 | 100 | 98.9919 | 95.0941 | 97.0833 | 94.0972 | 89.375 | 93.8844 | 85.4167 | 80.6452 | 90.3472 | 83.75 | 72.1528 | 84.8118 | 80.3091 | 67.6747
1 | 3.25 | 20 | 90.793 | 79.4355 | 67.5403 | 92.3363 | 88.3005 | 76.6472 | 97.5806 | 91.8011 | 82.8629 | 99.7917 | 97.5 | 95.0694 | 100 | 99.9328 | 98.0511 | 100 | 99.1667 | 96.3889 | 100 | 100 | 97.1774 | 100 | 99.3952 | 95.9677 | 97.8472 | 94.9306 | 90.7639 | 96.1694 | 87.3656 | 83.8038 | 92.3611 | 86.6667 | 75.8333 | 87.6344 | 82.5941 | 70.0269
1 | 3.25 | 25 | 90.793 | 79.4355 | 67.5403 | 92.3363 | 88.3005 | 76.7216 | 97.5806 | 91.8011 | 82.8629 | 99.7917 | 97.5 | 95.0694 | 100 | 99.9328 | 98.0511 | 100 | 99.1667 | 96.3889 | 100 | 100 | 97.1774 | 100 | 99.3952 | 95.9677 | 97.9167 | 94.9306 | 90.8333 | 96.1694 | 87.3656 | 83.8038 | 92.3611 | 86.6667 | 75.8333 | 87.6344 | 82.5941 | 70.0269
1 | 3.5 | 2 | 2.4194 | 1.0081 | 0.20161 | 2.9454 | 1.388 | 0.58498 | 3.4946 | 1.6129 | 0.73925 | 5.0694 | 3.6111 | 1.7361 | 5.7124 | 2.957 | 1.5457 | 8.125 | 3.9583 | 2.3611 | 6.1156 | 3.4274 | 1.6801 | 5.5108 | 3.4274 | 1.8145 | 3.9583 | 2.2222 | 1.0417 | 2.621 | 1.5457 | 0.53763 | 2.6389 | 1.25 | 0.41667 | 3.293 | 1.3441 | 0.40323
1 | 3.5 | 4 | 9.543 | 4.7715 | 2.6882 | 12.9464 | 9.0774 | 3.869 | 13.7097 | 8.8038 | 5.7124 | 19.4444 | 14.9306 | 10.2778 | 20.9005 | 15.8602 | 11.0215 | 26.3194 | 16.7361 | 13.3333 | 22.6478 | 16.8011 | 11.2903 | 21.8414 | 16.5323 | 11.4919 | 15.5556 | 11.5278 | 5.9028 | 11.1559 | 7.3253 | 4.3683 | 10.4861 | 6.5278 | 2.7778 | 10.6855 | 7.5941 | 2.7554
1 | 3.5 | 6 | 25.0672 | 14.6505 | 8.4677 | 28.497 | 20.546 | 11.0119 | 30.4435 | 23.5215 | 14.9866 | 40 | 35 | 27.8472 | 43.2124 | 39.3145 | 29.5027 | 50.625 | 41.6667 | 30.7639 | 46.9086 | 39.7849 | 32.1909 | 44.4892 | 37.0296 | 29.3683 | 37.9861 | 30.9028 | 20.625 | 25.672 | 19.8253 | 12.6344 | 21.5972 | 16.875 | 11.0417 | 24.664 | 16.4651 | 8.4005
1 | 3.5 | 8 | 39.3817 | 27.7554 | 18.414 | 49.2944 | 40.9406 | 20.9077 | 52.1505 | 41.9355 | 31.7876 | 67.3611 | 57.5 | 49.5139 | 68.4812 | 63.7769 | 53.8978 | 73.0556 | 68.0556 | 56.3194 | 75 | 65.793 | 54.0995 | 68.6156 | 63.3065 | 53.4946 | 60.2778 | 52.8472 | 40.1389 | 44.8925 | 36.3575 | 27.4194 | 41.4583 | 31.1111 | 22.3611 | 43.8844 | 30.3763 | 20.2957
1 | 3.5 | 9 | 47.5806 | 35.9543 | 26.5457 | 58.9132 | 51.6112 | 29.1667 | 62.4328 | 50.6048 | 40.793 | 75.4167 | 68.5417 | 62.5694 | 80.0403 | 73.3871 | 65.3226 | 82.9861 | 78.9583 | 69.0278 | 86.828 | 77.0833 | 68.414 | 79.0323 | 72.9839 | 65.3226 | 70 | 60.9722 | 51.6667 | 52.4866 | 47.2446 | 36.0887 | 50.7639 | 40.1389 | 28.6111 | 52.2177 | 38.3737 | 27.3522
1 | 3.5 | 10 | 57.7285 | 45.6989 | 34.879 | 68.006 | 58.8388 | 39.6577 | 75.5376 | 60.4167 | 50.8737 | 85.625 | 77.5694 | 70.4861 | 87.3656 | 82.0565 | 75.8737 | 90.4861 | 86.3889 | 79.6528 | 93.8844 | 86.7608 | 79.9059 | 86.4247 | 81.1156 | 74.8656 | 79.1667 | 68.6111 | 63.6111 | 62.4328 | 55.3091 | 44.0188 | 62.1528 | 52.1528 | 37.7083 | 61.6263 | 45.9005 | 34.4086
1 | 3.5 | 11 | 67.4059 | 54.2704 | 43.6828 | 75.9493 | 67.0387 | 50.2976 | 83.871 | 70.7661 | 59.4758 | 91.3889 | 85.6944 | 80 | 93.6828 | 88.3065 | 83.4005 | 94.7917 | 91.5278 | 87.0833 | 96.9758 | 92.6075 | 86.9624 | 92.4059 | 89.1129 | 82.9301 | 86.7361 | 77.7778 | 72.0833 | 72.7823 | 62.7016 | 55.0403 | 72.5694 | 62.1528 | 48.4722 | 68.078 | 54.5699 | 44.6237
1 | 3.5 | 12 | 77.1505 | 60.8607 | 50.8065 | 83.4077 | 72.3779 | 60.1216 | 89.2473 | 77.8898 | 68.6828 | 94.375 | 92.2917 | 85.9028 | 96.5726 | 93.6828 | 91.1962 | 97.7083 | 95.1389 | 92.2222 | 99.328 | 97.043 | 91.3306 | 97.4462 | 93.6828 | 88.0376 | 92.2222 | 85.2083 | 80 | 80.1075 | 69.422 | 64.7849 | 78.1944 | 70.0694 | 55.6944 | 75.0672 | 63.3737 | 52.6882
1 | 3.5 | 15 | 89.8522 | 78.2258 | 70.2285 | 92.4851 | 86.9792 | 76.8114 | 97.9839 | 91.1962 | 82.8629 | 99.5833 | 97.5694 | 94.8611 | 100 | 99.4624 | 98.3871 | 100 | 99.3056 | 97.2222 | 100 | 100 | 97.7151 | 100 | 99.2608 | 95.8333 | 97.9167 | 95.2778 | 90.3472 | 94.8253 | 87.9032 | 82.7957 | 91.25 | 85.8333 | 76.1111 | 86.6263 | 82.3925 | 70.6317
1 | 3.5 | 20 | 92.9435 | 84.3414 | 73.5887 | 95.0149 | 90.7918 | 81.994 | 98.9247 | 94.0188 | 85.0134 | 100 | 99.0972 | 95.7639 | 100 | 100 | 98.9247 | 100 | 99.5139 | 97.5 | 100 | 100 | 98.0511 | 100 | 100 | 97.4462 | 98.8889 | 96.5972 | 92.5694 | 98.3871 | 91.0618 | 87.5 | 94.5833 | 89.3056 | 80.9028 | 90.121 | 87.0968 | 74.8656
1 | 3.5 | 25 | 92.9435 | 84.3414 | 73.5887 | 95.0149 | 90.7918 | 82.0685 | 98.9247 | 94.0188 | 85.0134 | 100 | 99.0972 | 95.7639 | 100 | 100 | 98.9247 | 100 | 99.5139 | 97.5 | 100 | 100 | 98.0511 | 100 | 100 | 97.4462 | 98.8889 | 96.5972 | 92.6389 | 98.3871 | 91.0618 | 87.5 | 94.5833 | 89.375 | 80.9722 | 90.121 | 87.0968 | 74.8656
1 | 3.75 | 2 | 2.4194 | 1.0081 | 0.20161 | 2.9454 | 1.388 | 0.58498 | 3.4946 | 1.6129 | 0.73925 | 5.0694 | 3.6111 | 1.7361 | 5.7124 | 2.957 | 1.5457 | 8.125 | 3.9583 | 2.3611 | 6.1156 | 3.4274 | 1.6801 | 5.5108 | 3.4274 | 1.8145 | 3.9583 | 2.2222 | 1.0417 | 2.621 | 1.5457 | 0.53763 | 2.6389 | 1.25 | 0.41667 | 3.293 | 1.3441 | 0.40323
1 | 3.75 | 4 | 9.543 | 4.7715 | 2.6882 | 12.9464 | 9.0774 | 3.869 | 13.7097 | 8.8038 | 5.7124 | 19.4444 | 14.9306 | 10.2778 | 20.9005 | 15.8602 | 11.0215 | 26.3194 | 16.7361 | 13.3333 | 22.6478 | 16.8011 | 11.2903 | 21.8414 | 16.5323 | 11.4919 | 15.5556 | 11.5278 | 5.9028 | 11.1559 | 7.3253 | 4.3683 | 10.4861 | 6.5278 | 2.7778 | 10.6855 | 7.5941 | 2.7554
1 | 3.75 | 6 | 25.0672 | 14.6505 | 8.4677 | 28.497 | 20.546 | 11.0119 | 30.4435 | 23.5215 | 14.9866 | 40 | 35 | 27.8472 | 43.2124 | 39.3145 | 29.5027 | 50.625 | 41.6667 | 30.7639 | 46.9086 | 39.7849 | 32.1909 | 44.4892 | 37.0296 | 29.3683 | 37.9861 | 30.9028 | 20.625 | 25.672 | 19.8253 | 12.6344 | 21.5972 | 16.875 | 11.0417 | 24.664 | 16.4651 | 8.4005
1 | 3.75 | 8 | 39.3817 | 27.7554 | 18.4812 | 49.2944 | 40.9406 | 20.9077 | 52.1505 | 41.9355 | 31.922 | 67.3611 | 57.5 | 49.5139 | 68.4812 | 63.7769 | 53.8978 | 73.0556 | 68.0556 | 56.3194 | 75 | 65.793 | 54.0995 | 68.6156 | 63.3065 | 53.4946 | 60.2778 | 52.8472 | 40.1389 | 44.8925 | 36.3575 | 27.4194 | 41.4583 | 31.1806 | 22.3611 | 43.8844 | 30.3763 | 20.2957
1 | 3.75 | 9 | 47.5806 | 35.9543 | 26.6129 | 58.9132 | 51.6857 | 29.2411 | 62.4328 | 50.6048 | 41.0618 | 75.4167 | 68.5417 | 62.6389 | 80.0403 | 73.3871 | 65.3226 | 82.9861 | 78.9583 | 69.0278 | 86.828 | 77.0833 | 68.414 | 79.0323 | 72.9839 | 65.3226 | 70 | 60.9722 | 51.6667 | 52.4866 | 47.2446 | 36.0887 | 50.7639 | 40.1389 | 28.6111 | 52.2177 | 38.3737 | 27.4866
1 | 3.75 | 10 | 57.7285 | 45.6989 | 34.9462 | 68.006 | 58.9106 | 39.7321 | 75.5376 | 60.4167 | 51.0081 | 85.625 | 77.5694 | 70.625 | 87.3656 | 82.0565 | 75.8737 | 90.4861 | 86.3889 | 79.6528 | 93.8844 | 86.7608 | 79.9059 | 86.4247 | 81.1156 | 74.8656 | 79.1667 | 68.6111 | 63.6111 | 62.4328 | 55.3091 | 44.0188 | 62.1528 | 52.3611 | 37.7083 | 61.6263 | 45.9005 | 34.6102
1 | 3.75 | 11 | 67.4059 | 54.3683 | 43.8844 | 76.093 | 67.5441 | 50.372 | 83.871 | 71.0349 | 60.0134 | 91.3889 | 85.8333 | 80.1389 | 93.6828 | 88.3065 | 83.4005 | 94.7917 | 91.5278 | 87.0833 | 96.9758 | 92.6075 | 86.9624 | 92.4731 | 89.1129 | 82.9301 | 86.7361 | 77.7778 | 72.0833 | 72.7823 | 62.7016 | 55.0403 | 72.7778 | 62.1528 | 48.75 | 68.078 | 54.6371 | 44.7581
1 | 3.75 | 12 | 77.3522 | 61.4919 | 51.4113 | 83.4821 | 73.0244 | 60.3423 | 89.2473 | 78.629 | 69.2876 | 94.5833 | 92.2917 | 85.9722 | 96.6398 | 93.6828 | 91.1962 | 97.7778 | 95.1389 | 92.2917 | 99.328 | 97.043 | 91.3306 | 97.4462 | 93.6828 | 88.0376 | 92.2222 | 85.2083 | 80 | 80.3091 | 69.5565 | 64.8522 | 78.4028 | 70.9028 | 55.9722 | 75.2016 | 63.8441 | 52.8226
1 | 3.75 | 15 | 90.793 | 80.2419 | 72.9839 | 93.1548 | 87.7232 | 79.3745 | 97.9839 | 92.0027 | 84.4086 | 99.7917 | 97.9167 | 95.2778 | 100 | 99.7312 | 98.5215 | 100 | 99.3056 | 97.5 | 100 | 100 | 98.0511 | 100 | 99.4624 | 96.1694 | 98.5417 | 95.5556 | 91.3194 | 95.1613 | 88.8441 | 83.6022 | 92.1528 | 87.5694 | 78.6111 | 88.4409 | 83.7366 | 72.6478
1 | 3.75 | 20 | 94.4892 | 88.3065 | 79.6371 | 96.5774 | 92.3209 | 85.3423 | 99.5296 | 96.1694 | 87.836 | 100 | 99.4444 | 96.4583 | 100 | 100 | 99.5968 | 100 | 100 | 98.1944 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.5 | 93.8889 | 99.4624 | 93.4812 | 90.6586 | 96.6667 | 91.875 | 84.7222 | 92.7419 | 88.8441 | 80.1747
1 | 3.75 | 25 | 94.4892 | 88.3065 | 79.6371 | 96.5774 | 92.3209 | 85.4167 | 99.5296 | 96.1694 | 87.836 | 100 | 99.5139 | 96.4583 | 100 | 100 | 99.5968 | 100 | 100 | 98.1944 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.5 | 93.8889 | 99.4624 | 93.4812 | 90.7258 | 96.6667 | 92.0139 | 84.7222 | 92.7419 | 88.8441 | 80.1747
1 | 4 | 2 | 2.4194 | 1.0081 | 0.20161 | 2.9454 | 1.388 | 0.58498 | 3.4946 | 1.6129 | 0.73925 | 5.0694 | 3.6111 | 1.7361 | 5.7124 | 2.957 | 1.5457 | 8.125 | 3.9583 | 2.3611 | 6.1156 | 3.4274 | 1.6801 | 5.5108 | 3.4274 | 1.8145 | 3.9583 | 2.2222 | 1.0417 | 2.621 | 1.5457 | 0.53763 | 2.6389 | 1.25 | 0.41667 | 3.293 | 1.3441 | 0.40323
1 | 4 | 4 | 9.543 | 4.7715 | 2.6882 | 12.9464 | 9.0774 | 3.869 | 13.7097 | 8.8038 | 5.7124 | 19.4444 | 14.9306 | 10.2778 | 20.9005 | 15.8602 | 11.0215 | 26.3194 | 16.7361 | 13.3333 | 22.6478 | 16.8011 | 11.2903 | 21.8414 | 16.5323 | 11.4919 | 15.5556 | 11.5278 | 5.9028 | 11.1559 | 7.3253 | 4.3683 | 10.4861 | 6.5278 | 2.7778 | 10.6855 | 7.5941 | 2.7554
1 | 4 | 6 | 25.0672 | 14.6505 | 8.4677 | 28.497 | 20.546 | 11.0119 | 30.4435 | 23.5215 | 14.9866 | 40 | 35 | 27.8472 | 43.2124 | 39.3145 | 29.5027 | 50.625 | 41.6667 | 30.7639 | 46.9086 | 39.7849 | 32.1909 | 44.4892 | 37.0296 | 29.3683 | 37.9861 | 30.9028 | 20.625 | 25.672 | 19.8253 | 12.6344 | 21.5972 | 16.875 | 11.0417 | 24.664 | 16.4651 | 8.4005
1 | 4 | 8 | 39.3817 | 27.7554 | 18.4812 | 49.2944 | 40.9406 | 20.9077 | 52.1505 | 41.9355 | 31.922 | 67.3611 | 57.5 | 49.5139 | 68.4812 | 63.7769 | 53.8978 | 73.0556 | 68.0556 | 56.3194 | 75 | 65.793 | 54.0995 | 68.6156 | 63.3065 | 53.4946 | 60.2778 | 52.8472 | 40.1389 | 44.8925 | 36.3575 | 27.4194 | 41.4583 | 31.1806 | 22.3611 | 43.8844 | 30.3763 | 20.2957
1 | 4 | 9 | 47.5806 | 35.9543 | 26.6801 | 58.9132 | 51.6857 | 29.2411 | 62.4328 | 50.6048 | 41.0618 | 75.4167 | 68.5417 | 62.6389 | 80.0403 | 73.3871 | 65.3226 | 82.9861 | 78.9583 | 69.0278 | 86.828 | 77.0833 | 68.414 | 79.0323 | 72.9839 | 65.3226 | 70 | 60.9722 | 51.6667 | 52.4866 | 47.2446 | 36.0887 | 50.7639 | 40.1389 | 28.6111 | 52.2177 | 38.3737 | 27.4866
1 | 4 | 10 | 57.7285 | 45.6989 | 35.1478 | 68.006 | 59.1954 | 39.8065 | 75.5376 | 60.4167 | 51.0081 | 85.625 | 77.5694 | 70.6944 | 87.3656 | 82.0565 | 75.8737 | 90.4861 | 86.3889 | 79.6528 | 93.8844 | 86.7608 | 79.9059 | 86.4247 | 81.1156 | 74.8656 | 79.1667 | 68.6111 | 63.6111 | 62.4328 | 55.3091 | 44.0188 | 62.1528 | 52.5 | 37.7083 | 61.6263 | 45.9005 | 34.6774
1 | 4 | 11 | 67.4059 | 54.3683 | 44.1532 | 76.093 | 68.1548 | 50.4464 | 83.871 | 71.1022 | 60.2151 | 91.3889 | 85.8333 | 80.2083 | 93.6828 | 88.3065 | 83.4005 | 94.7917 | 91.5278 | 87.0833 | 96.9758 | 92.6075 | 86.9624 | 92.4731 | 89.1129 | 82.9301 | 86.7361 | 77.7778 | 72.0833 | 72.7823 | 62.7016 | 55.0403 | 72.7778 | 62.2222 | 48.75 | 68.078 | 54.6371 | 44.7581
1 | 4 | 12 | 77.3522 | 61.4919 | 52.2849 | 83.554 | 74.1815 | 60.3423 | 89.2473 | 78.8978 | 69.4892 | 94.5833 | 92.2917 | 85.9722 | 96.6398 | 93.6828 | 91.1962 | 97.7778 | 95.1389 | 92.2917 | 99.328 | 97.043 | 91.3306 | 97.4462 | 93.6828 | 88.0376 | 92.2222 | 85.2083 | 80 | 80.3763 | 69.5565 | 64.9194 | 78.5417 | 70.9722 | 56.25 | 75.2688 | 63.9113 | 52.8898
1 | 4 | 15 | 91.3306 | 81.25 | 74.1935 | 93.8244 | 88.3929 | 80.9011 | 98.1183 | 92.6747 | 84.9462 | 99.7917 | 98.125 | 95.6944 | 100 | 99.7984 | 98.8575 | 100 | 99.3056 | 98.0556 | 100 | 100 | 98.2527 | 100 | 99.5296 | 96.7742 | 98.8194 | 96.1111 | 91.8056 | 95.6317 | 89.5161 | 84.2742 | 92.6389 | 88.6111 | 80.0694 | 89.5161 | 84.6774 | 74.8656
1 | 4 | 20 | 95.8333 | 91.2634 | 82.5941 | 97.9911 | 94.1964 | 89.296 | 99.9328 | 97.4462 | 90.1882 | 100 | 99.7917 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.4722 | 95.9028 | 99.7984 | 95.6317 | 92.8763 | 98.0556 | 94.375 | 88.125 | 94.9597 | 90.793 | 85.0806
1 | 4 | 25 | 95.8333 | 91.3306 | 82.6613 | 97.9911 | 94.1964 | 89.4397 | 99.9328 | 97.5134 | 90.1882 | 100 | 99.8611 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.6806 | 95.9028 | 99.9328 | 95.6317 | 92.9435 | 98.0556 | 94.5833 | 88.125 | 94.9597 | 90.793 | 85.2151
2 | 0.5 | 2 | 0 | 0 | 0 | 0.59524 | 0 | 0 | 0.47043 | 0 | 0 | 2.2917 | 0.41667 | 0 | 2.2177 | 1.0753 | 0 | 4.5139 | 2.0139 | 0.27778 | 3.9651 | 1.5457 | 0.40323 | 3.293 | 1.2769 | 0.67204 | 1.5972 | 0.27778 | 0 | 0.53763 | 0 | 0 | 0.13889 | 0 | 0 | 0.33602 | 0 | 0
2 | 0.5 | 4 | 0.60484 | 0 | 0 | 2.0448 | 0 | 0 | 2.5538 | 0 | 0 | 7.4306 | 3.2639 | 0.625 | 8.3333 | 5.4435 | 2.4866 | 14.375 | 8.4722 | 2.6389 | 15.2554 | 7.6613 | 4.3683 | 12.2312 | 6.0484 | 3.4274 | 4.6528 | 2.2222 | 0.48611 | 2.0833 | 0.40323 | 0 | 1.5972 | 0 | 0 | 1.8145 | 0 | 0
2 | 0.5 | 6 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.2419 | 0.53763 | 0 | 11.3889 | 7.1528 | 1.5278 | 15.121 | 10.7527 | 5.5108 | 19.4444 | 13.6806 | 5.2778 | 22.7151 | 13.7769 | 7.5269 | 18.414 | 9.6774 | 6.1828 | 10.3472 | 4.375 | 0.97222 | 3.7634 | 1.1425 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
2 | 0.5 | 8 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.2639 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4167 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1317 | 19.8925 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
2 | 0.5 | 9 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.2639 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4167 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 19.8925 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
2 | 0.5 | 10 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.2639 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4167 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 19.8925 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
2 | 0.5 | 11 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.2639 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4167 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 19.8925 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
2 | 0.5 | 12 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.2639 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4167 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 19.8925 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
2 | 0.5 | 15 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.2639 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4167 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 19.8925 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
2 | 0.5 | 20 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.2639 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4167 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 19.8925 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
2 | 0.5 | 25 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.2639 | 1.5972 | 15.3898 | 11.6935 | 5.7796 | 20.4167 | 14.3056 | 5.6944 | 23.9919 | 15.0538 | 8.1989 | 19.8925 | 10.6855 | 6.6532 | 10.5556 | 4.6528 | 0.97222 | 3.8978 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0.20161 | 0
2 | 0.75 | 2 | 0.94086 | 0 | 0 | 1.7857 | 0 | 0 | 1.6129 | 0.53763 | 0 | 3.2639 | 1.875 | 0.83333 | 4.0995 | 1.8145 | 0.47043 | 6.4583 | 2.9167 | 0.83333 | 5.4435 | 2.5538 | 1.2097 | 4.0323 | 2.3522 | 1.2097 | 2.2222 | 1.3889 | 0.27778 | 1.4113 | 0.47043 | 0 | 0.83333 | 0.27778 | 0 | 1.1425 | 0 | 0
2 | 0.75 | 4 | 2.8898 | 1.0753 | 0 | 6.2115 | 2.6042 | 0 | 7.6613 | 2.4866 | 1.0081 | 13.8889 | 9.1667 | 4.5139 | 14.0457 | 10.0806 | 5.2419 | 22.1528 | 12.0833 | 7.2917 | 18.9516 | 12.5 | 8.5349 | 17.9435 | 10.7527 | 8.871 | 10.6944 | 6.4583 | 2.2917 | 4.4355 | 2.2849 | 0 | 3.5417 | 1.3194 | 0.20833 | 4.7715 | 2.1505 | 0
2 | 0.75 | 6 | 6.9892 | 2.621 | 0 | 11.4763 | 5.2083 | 0.22321 | 15.5914 | 6.7876 | 2.957 | 25.9722 | 19.0278 | 10.5556 | 28.0242 | 21.5726 | 14.9866 | 36.1111 | 23.4722 | 17.9861 | 34.0054 | 26.2769 | 20.2957 | 34.0054 | 23.1183 | 17.2715 | 23.75 | 13.125 | 7.0139 | 11.0215 | 5.3091 | 1.8145 | 6.5278 | 2.5 | 0.55556 | 6.9892 | 3.8306 | 0
2 | 0.75 | 8 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 18.8172 | 7.6613 | 4.0323 | 32.0139 | 23.6806 | 13.8889 | 37.2312 | 27.8226 | 20.1613 | 43.6111 | 30.7639 | 23.3333 | 44.9597 | 34.6774 | 26.8817 | 43.0108 | 29.0995 | 22.1102 | 29.1667 | 16.875 | 9.3056 | 13.5753 | 7.1909 | 2.5538 | 7.5694 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
2 | 0.75 | 9 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.0188 | 7.6613 | 4.0323 | 32.7083 | 24.4444 | 14.2361 | 38.1048 | 28.2258 | 20.6989 | 44.2361 | 31.1111 | 23.75 | 45.5645 | 35.4839 | 27.4194 | 43.4812 | 30.1075 | 22.7151 | 29.375 | 17.1528 | 9.3056 | 13.5753 | 7.3925 | 2.5538 | 7.5694 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
2 | 0.75 | 10 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.6613 | 4.0323 | 32.7083 | 24.4444 | 14.2361 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.1111 | 23.8194 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.2419 | 22.7151 | 29.375 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.5694 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
2 | 0.75 | 11 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.6613 | 4.0323 | 32.7083 | 24.4444 | 14.2361 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.1806 | 23.8194 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.2419 | 22.7151 | 29.375 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.5694 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
2 | 0.75 | 12 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.6613 | 4.0323 | 32.7083 | 24.4444 | 14.2361 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.1806 | 23.8194 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.2419 | 22.7151 | 29.375 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.5694 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
2 | 0.75 | 15 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.6613 | 4.0323 | 32.7083 | 24.4444 | 14.2361 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.1806 | 23.8194 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.2419 | 22.7151 | 29.375 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.5694 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
2 | 0.75 | 20 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.6613 | 4.0323 | 32.7083 | 24.4444 | 14.2361 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.1806 | 23.8194 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.2419 | 22.7151 | 29.375 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.5694 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
2 | 0.75 | 25 | 8.7366 | 2.957 | 0 | 12.7232 | 6.3013 | 0.58241 | 19.086 | 7.6613 | 4.0323 | 32.7083 | 24.4444 | 14.2361 | 38.3737 | 28.2258 | 20.9005 | 44.2361 | 31.1806 | 23.8194 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.2419 | 22.7151 | 29.375 | 17.1528 | 9.375 | 13.5753 | 7.3925 | 2.5538 | 7.5694 | 2.9861 | 0.55556 | 7.5941 | 4.0323 | 0
2 | 1 | 2 | 1.5457 | 0.26882 | 0 | 2.2655 | 0.73122 | 0 | 2.0161 | 0.94086 | 0.26882 | 4.0972 | 2.7083 | 1.1111 | 4.9059 | 2.1505 | 1.0753 | 7.2917 | 3.5417 | 1.3194 | 5.9812 | 3.0914 | 1.3441 | 5.1075 | 2.8898 | 1.6801 | 3.0556 | 1.875 | 0.55556 | 1.7473 | 0.80645 | 0.26882 | 1.6667 | 0.41667 | 0 | 1.6129 | 0.60484 | 0
2 | 1 | 4 | 4.7043 | 2.1505 | 0.26882 | 9.4982 | 4.3103 | 1.3188 | 11.6263 | 4.3683 | 2.2177 | 16.3194 | 11.3889 | 6.0417 | 17.4059 | 12.7688 | 9.4758 | 24.2361 | 14.5833 | 10.7639 | 21.707 | 14.7177 | 10.4167 | 20.8333 | 13.9113 | 10.6183 | 13.2639 | 9.0278 | 4.4444 | 7.2581 | 4.3683 | 1.5457 | 6.0417 | 2.9861 | 1.1111 | 6.9892 | 3.4946 | 0.80645
2 | 1 | 6 | 12.7016 | 5.8468 | 1.6129 | 19.0476 | 12.2101 | 3.869 | 21.4382 | 12.9704 | 6.4516 | 32.2917 | 24.6528 | 17.3611 | 36.4247 | 30.578 | 22.7823 | 44.7222 | 35.4167 | 25.0694 | 42.0027 | 35.0806 | 27.7554 | 42.4059 | 30.3763 | 24.328 | 30.6944 | 20.3472 | 12.7083 | 17.5403 | 10.7527 | 5.0403 | 13.5417 | 7.3611 | 2.5694 | 14.4489 | 7.5269 | 1.2769
2 | 1 | 8 | 19.8925 | 8.9382 | 2.5538 | 27.5298 | 17.7827 | 5.4315 | 31.3172 | 19.6237 | 9.6102 | 44.9306 | 36.1111 | 26.6667 | 52.5538 | 44.6237 | 36.0215 | 56.7361 | 48.125 | 39.375 | 62.3656 | 50.0672 | 39.9866 | 57.7957 | 45.1613 | 37.9032 | 41.1111 | 31.8056 | 22.2917 | 22.6478 | 15.2554 | 8.2661 | 17.9167 | 10.2778 | 3.5417 | 20.9677 | 10.4167 | 2.7554
2 | 1 | 9 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 32.8629 | 21.5054 | 9.879 | 48.3333 | 39.4444 | 28.2639 | 56.8548 | 46.9086 | 39.2473 | 59.9306 | 51.1806 | 40.625 | 66.8011 | 52.8226 | 42.8091 | 62.0296 | 48.5887 | 40.793 | 43.6806 | 34.1667 | 23.2639 | 23.7231 | 15.9274 | 8.6694 | 18.3333 | 10.8333 | 3.6111 | 21.3038 | 10.9543 | 2.957
2 | 1 | 10 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.5349 | 21.9758 | 10.4839 | 48.6111 | 40.7639 | 28.8889 | 58.0645 | 47.9167 | 40.8602 | 60.4861 | 52.4306 | 41.0417 | 68.1452 | 54.3011 | 45.1613 | 62.9704 | 49.8656 | 41.2634 | 44.3056 | 34.5833 | 23.3333 | 24.0591 | 16.129 | 8.7366 | 18.4722 | 10.9028 | 3.6111 | 21.371 | 10.9543 | 3.0914
2 | 1 | 11 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.7366 | 22.043 | 10.4839 | 48.8194 | 40.9722 | 28.8889 | 58.0645 | 48.1855 | 40.8602 | 60.4861 | 52.5694 | 41.0417 | 68.3468 | 54.4355 | 45.5645 | 63.172 | 50 | 41.3306 | 44.3056 | 34.6528 | 23.3333 | 24.0591 | 16.1962 | 8.7366 | 18.5417 | 10.9028 | 3.6111 | 21.371 | 10.9543 | 3.0914
2 | 1 | 12 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.7366 | 22.043 | 10.4839 | 48.8194 | 40.9722 | 28.8889 | 58.0645 | 48.1855 | 40.8602 | 60.4861 | 52.5694 | 41.0417 | 68.414 | 54.4355 | 45.5645 | 63.172 | 50 | 41.3306 | 44.3056 | 34.6528 | 23.3333 | 24.0591 | 16.1962 | 8.7366 | 18.5417 | 10.9028 | 3.6111 | 21.371 | 10.9543 | 3.0914
2 | 1 | 15 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.7366 | 22.043 | 10.4839 | 48.8194 | 40.9722 | 28.8889 | 58.0645 | 48.1855 | 40.8602 | 60.4861 | 52.5694 | 41.0417 | 68.414 | 54.4355 | 45.5645 | 63.172 | 50 | 41.3306 | 44.3056 | 34.6528 | 23.3333 | 24.0591 | 16.1962 | 8.7366 | 18.5417 | 10.9028 | 3.6111 | 21.371 | 10.9543 | 3.0914
2 | 1 | 20 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.7366 | 22.043 | 10.4839 | 48.8194 | 40.9722 | 28.8889 | 58.0645 | 48.1855 | 40.8602 | 60.4861 | 52.5694 | 41.0417 | 68.414 | 54.4355 | 45.5645 | 63.172 | 50 | 41.3306 | 44.3056 | 34.6528 | 23.3333 | 24.0591 | 16.1962 | 8.7366 | 18.5417 | 10.9028 | 3.6111 | 21.371 | 10.9543 | 3.0914
2 | 1 | 25 | 20.2285 | 9.6774 | 2.5538 | 28.7305 | 18.1548 | 5.6548 | 33.7366 | 22.043 | 10.4839 | 48.8194 | 40.9722 | 28.8889 | 58.0645 | 48.1855 | 40.8602 | 60.4861 | 52.5694 | 41.0417 | 68.414 | 54.4355 | 45.5645 | 63.172 | 50 | 41.3306 | 44.3056 | 34.6528 | 23.3333 | 24.0591 | 16.1962 | 8.7366 | 18.5417 | 10.9028 | 3.6111 | 21.371 | 10.9543 | 3.0914
2 | 1.25 | 2 | 1.7473 | 0.47043 | 0 | 2.4092 | 0.95187 | 0 | 2.957 | 1.0081 | 0.40323 | 4.6528 | 2.9167 | 1.3889 | 5.0403 | 2.621 | 1.2769 | 7.5694 | 3.6111 | 1.6667 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.6801 | 3.75 | 2.0833 | 0.69444 | 2.2177 | 1.0753 | 0.47043 | 2.0139 | 0.76389 | 0.27778 | 2.4866 | 0.87366 | 0
2 | 1.25 | 4 | 7.3925 | 3.0242 | 1.2097 | 10.8272 | 6.1422 | 2.0833 | 12.836 | 6.3844 | 3.2258 | 17.4306 | 12.7083 | 8.5417 | 19.2876 | 13.9113 | 10.4839 | 25.8333 | 15.9722 | 12.1528 | 22.1102 | 16.3306 | 10.9543 | 21.1694 | 15.9946 | 10.8199 | 14.7917 | 10.7639 | 4.8611 | 8.9382 | 5.6452 | 2.8898 | 8.8889 | 4.8611 | 1.3194 | 8.0645 | 4.8387 | 1.0081
2 | 1.25 | 6 | 18.8844 | 8.3333 | 4.9059 | 23.3195 | 14.8399 | 6.1756 | 26.3441 | 19.8925 | 8.7366 | 35.2778 | 29.6528 | 22.4306 | 40.457 | 34.9462 | 26.4113 | 48.5417 | 39.8611 | 28.125 | 45.0269 | 38.5081 | 30.6452 | 43.414 | 33.4005 | 27.621 | 34.5833 | 26.8056 | 17.1528 | 20.5645 | 13.7769 | 8.8038 | 16.7361 | 10.6944 | 5.9722 | 17.6075 | 10.5511 | 4.5027
2 | 1.25 | 8 | 28.6962 | 14.5833 | 7.9973 | 38.1696 | 25.6696 | 11.4583 | 40.5242 | 30.9812 | 17.2043 | 54.3056 | 46.8056 | 37.2917 | 61.0215 | 53.4946 | 46.707 | 65.6944 | 60.5556 | 47.9167 | 71.5726 | 60.1478 | 49.328 | 63.7769 | 55.578 | 47.1102 | 49.375 | 41.9444 | 28.2639 | 30.6452 | 24.2608 | 13.7097 | 27.8472 | 16.5278 | 9.0972 | 29.4355 | 18.414 | 6.1156
2 | 1.25 | 9 | 31.4516 | 16.3306 | 8.4677 | 41.2946 | 29.0179 | 12.9464 | 43.0108 | 34.879 | 19.4892 | 61.25 | 50.0694 | 41.6667 | 66.8683 | 59.879 | 51.6801 | 71.9444 | 66.9444 | 52.7083 | 77.4866 | 65.9946 | 58.1317 | 72.043 | 59.9462 | 52.8898 | 54.7917 | 45.2083 | 33.3333 | 34.2742 | 27.5538 | 15.8602 | 30.1389 | 20.3472 | 9.375 | 31.25 | 19.6237 | 6.7876
2 | 1.25 | 10 | 32.4597 | 16.8011 | 8.9382 | 42.9315 | 29.8953 | 13.4673 | 43.8844 | 36.5591 | 21.1694 | 65.2083 | 53.4722 | 44.6528 | 69.6237 | 63.5081 | 53.9651 | 74.7222 | 68.4722 | 54.3056 | 80.5108 | 70.2957 | 61.3575 | 74.4624 | 62.2984 | 54.4355 | 58.0556 | 47.0139 | 35.5556 | 35.0806 | 29.8387 | 17.0027 | 31.25 | 21.6667 | 9.4444 | 31.7204 | 20.2957 | 7.7957
2 | 1.25 | 11 | 32.6613 | 16.8683 | 9.0726 | 42.9315 | 30.116 | 13.5417 | 45.2285 | 36.9624 | 21.1694 | 66.1111 | 54.7917 | 45.2083 | 70.2285 | 64.8522 | 54.3683 | 75.0694 | 68.8889 | 54.5833 | 80.9812 | 71.371 | 61.8952 | 74.9328 | 62.9032 | 55.1747 | 59.9306 | 47.4306 | 36.0417 | 35.3495 | 30.3763 | 17.3387 | 31.3889 | 21.6667 | 9.5139 | 31.922 | 20.5645 | 7.8629
2 | 1.25 | 12 | 32.6613 | 16.8683 | 9.0726 | 42.9315 | 30.1724 | 13.5417 | 45.2957 | 37.0296 | 21.3038 | 66.25 | 54.8611 | 45.2778 | 70.2285 | 65.2554 | 54.5027 | 75.2083 | 69.0972 | 54.5833 | 81.1828 | 71.5726 | 62.164 | 75.1344 | 63.0376 | 55.4435 | 60 | 47.6389 | 36.25 | 35.4167 | 30.4435 | 17.4059 | 31.4583 | 21.6667 | 9.5139 | 31.9892 | 20.6317 | 7.8629
2 | 1.25 | 15 | 32.6613 | 16.8683 | 9.0726 | 42.9315 | 30.1724 | 13.6161 | 45.2957 | 37.0296 | 21.3038 | 66.25 | 54.8611 | 45.2778 | 70.2957 | 65.2554 | 54.5027 | 75.2083 | 69.0972 | 54.5833 | 81.1828 | 71.5726 | 62.2984 | 75.1344 | 63.1048 | 55.5108 | 60 | 47.6389 | 36.25 | 35.4167 | 30.4435 | 17.4731 | 31.4583 | 21.6667 | 9.5139 | 31.9892 | 20.6317 | 7.8629
2 | 1.25 | 20 | 32.6613 | 16.8683 | 9.0726 | 42.9315 | 30.1724 | 13.6161 | 45.2957 | 37.0296 | 21.3038 | 66.25 | 54.8611 | 45.2778 | 70.2957 | 65.2554 | 54.5027 | 75.2083 | 69.0972 | 54.5833 | 81.1828 | 71.5726 | 62.2984 | 75.1344 | 63.1048 | 55.5108 | 60 | 47.6389 | 36.25 | 35.4167 | 30.4435 | 17.4731 | 31.4583 | 21.6667 | 9.5139 | 31.9892 | 20.6317 | 7.8629
2 | 1.25 | 25 | 32.6613 | 16.8683 | 9.0726 | 42.9315 | 30.1724 | 13.6161 | 45.2957 | 37.0296 | 21.3038 | 66.25 | 54.8611 | 45.2778 | 70.2957 | 65.2554 | 54.5027 | 75.2083 | 69.0972 | 54.5833 | 81.1828 | 71.5726 | 62.2984 | 75.1344 | 63.1048 | 55.5108 | 60 | 47.6389 | 36.25 | 35.4167 | 30.4435 | 17.4731 | 31.4583 | 21.6667 | 9.5139 | 31.9892 | 20.6317 | 7.8629
2 | 1.5 | 2 | 2.0833 | 0.67204 | 0 | 2.6324 | 1.0955 | 0.29762 | 3.293 | 1.2769 | 0.53763 | 4.7917 | 3.2639 | 1.4583 | 5.1747 | 2.6882 | 1.2769 | 7.7083 | 3.6806 | 1.875 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.6801 | 3.9583 | 2.0833 | 0.83333 | 2.4194 | 1.4113 | 0.53763 | 2.1528 | 0.83333 | 0.27778 | 2.7554 | 1.0753 | 0
2 | 1.5 | 4 | 8.871 | 3.3602 | 1.8817 | 11.8304 | 7.3096 | 2.2655 | 12.9032 | 7.8629 | 4.2339 | 18.2639 | 13.6806 | 9.4444 | 19.8925 | 15.1882 | 10.6855 | 26.0417 | 16.5278 | 12.8472 | 22.3118 | 16.4651 | 11.0887 | 21.3038 | 16.1962 | 10.9543 | 15.2778 | 11.0417 | 4.8611 | 10.2823 | 6.4516 | 3.6962 | 9.375 | 5.6944 | 1.875 | 9.3414 | 5.914 | 1.7473
2 | 1.5 | 6 | 22.379 | 10.2151 | 6.4516 | 24.6357 | 17.3979 | 7.6637 | 27.4866 | 22.3118 | 11.0887 | 37.7083 | 32.5694 | 24.2361 | 42.4059 | 37.836 | 28.4946 | 50.2778 | 40.4167 | 29.2361 | 46.5054 | 39.4489 | 31.6532 | 43.8844 | 35.6183 | 28.8306 | 36.5278 | 29.375 | 20 | 23.4543 | 16.9355 | 9.7446 | 19.2361 | 13.4028 | 7.9167 | 19.6909 | 13.4409 | 5.8468
2 | 1.5 | 8 | 33.0645 | 20.9677 | 11.2903 | 43.6576 | 31.622 | 16.2946 | 44.9597 | 35.7527 | 22.1102 | 59.3056 | 51.3194 | 43.6111 | 65.8602 | 59.7446 | 51.4785 | 70.6944 | 65.1389 | 53.6806 | 73.6559 | 64.5833 | 52.3522 | 65.793 | 60.5511 | 50.6048 | 54.7222 | 47.5694 | 34.2361 | 36.0887 | 30.1075 | 18.414 | 34.5833 | 22.7778 | 14.7222 | 34.7446 | 23.3871 | 10.3495
2 | 1.5 | 9 | 37.6344 | 24.3952 | 14.5833 | 48.5119 | 36.4737 | 20.3869 | 51.7473 | 40.9946 | 26.5457 | 67.2222 | 58.5417 | 50.7639 | 74.1935 | 67.0027 | 59.7446 | 77.5 | 73.2639 | 62.7083 | 81.586 | 73.1183 | 64.7849 | 75.4704 | 67.6747 | 59.543 | 63.5417 | 53.6111 | 42.2222 | 41.3978 | 36.4247 | 23.5887 | 40.2778 | 27.6389 | 15.6944 | 38.3737 | 27.8898 | 13.1048
2 | 1.5 | 10 | 39.9866 | 26.8817 | 16.9355 | 51.9345 | 38.3929 | 22.0982 | 55.8468 | 43.8172 | 30.1747 | 71.25 | 62.7083 | 56.0417 | 78.4946 | 71.707 | 64.5161 | 81.25 | 77.3611 | 68.8194 | 86.8952 | 79.0995 | 70.6317 | 80.4435 | 72.7823 | 63.8441 | 67.8472 | 57.7778 | 46.8056 | 46.1694 | 39.3817 | 25.5376 | 43.6806 | 31.7361 | 16.9444 | 41.4651 | 30.578 | 14.9866
2 | 1.5 | 11 | 41.5995 | 27.8898 | 18.2796 | 52.9018 | 39.2113 | 22.7679 | 57.8629 | 45.6317 | 31.3172 | 73.9583 | 64.9306 | 57.5694 | 80.3763 | 75.1344 | 66.9355 | 82.6389 | 79.375 | 69.9306 | 88.7097 | 81.6532 | 72.8495 | 82.1909 | 74.328 | 65.3226 | 71.5278 | 59.5139 | 48.125 | 47.1102 | 41.3978 | 27.0161 | 44.7917 | 33.4028 | 17.6389 | 42.3387 | 31.9892 | 15.3898
2 | 1.5 | 12 | 41.7339 | 27.957 | 18.5484 | 53.1994 | 39.2755 | 22.8423 | 58.3333 | 45.8333 | 31.922 | 74.1667 | 65.3472 | 58.1944 | 81.3172 | 75.8065 | 68.414 | 83.1944 | 79.7222 | 70.1389 | 88.9785 | 82.5941 | 73.3199 | 82.9301 | 74.4624 | 66.4651 | 71.8056 | 60 | 48.75 | 47.7823 | 41.8683 | 27.3522 | 45.4861 | 33.75 | 17.7083 | 42.6075 | 32.3925 | 15.6586
2 | 1.5 | 15 | 41.8683 | 28.0242 | 18.6156 | 53.2738 | 39.3473 | 22.9167 | 58.4677 | 45.9005 | 31.922 | 74.2361 | 65.3472 | 58.2639 | 81.586 | 76.0081 | 68.6156 | 83.5417 | 79.8611 | 70.1389 | 89.0457 | 82.7957 | 73.7231 | 83.1317 | 74.5296 | 66.6667 | 71.875 | 60.1389 | 48.75 | 47.8495 | 41.9355 | 27.5538 | 45.5556 | 33.75 | 17.9167 | 42.6075 | 32.5269 | 15.7258
2 | 1.5 | 20 | 41.8683 | 28.0242 | 18.6156 | 53.2738 | 39.3473 | 22.9167 | 58.4677 | 45.9005 | 31.922 | 74.2361 | 65.3472 | 58.2639 | 81.586 | 76.0081 | 68.6156 | 83.5417 | 79.8611 | 70.1389 | 89.0457 | 82.7957 | 73.7231 | 83.1317 | 74.5296 | 66.6667 | 71.875 | 60.1389 | 48.75 | 47.8495 | 41.9355 | 27.5538 | 45.5556 | 33.75 | 17.9167 | 42.6075 | 32.5269 | 15.7258
2 | 1.5 | 25 | 41.8683 | 28.0242 | 18.6156 | 53.2738 | 39.3473 | 22.9167 | 58.4677 | 45.9005 | 31.922 | 74.2361 | 65.3472 | 58.2639 | 81.586 | 76.0081 | 68.6156 | 83.5417 | 79.8611 | 70.1389 | 89.0457 | 82.7957 | 73.7231 | 83.1317 | 74.5296 | 66.6667 | 71.875 | 60.1389 | 48.75 | 47.8495 | 41.9355 | 27.5538 | 45.5556 | 33.75 | 17.9167 | 42.6075 | 32.5269 | 15.7258
2 | 1.75 | 2 | 2.1505 | 0.80645 | 0 | 2.7761 | 1.17 | 0.43873 | 3.293 | 1.3441 | 0.53763 | 4.9306 | 3.2639 | 1.5972 | 5.3091 | 2.7554 | 1.2769 | 7.7083 | 3.6806 | 2.0833 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.7473 | 3.9583 | 2.0833 | 0.90278 | 2.4194 | 1.4785 | 0.53763 | 2.2917 | 1.1111 | 0.27778 | 3.1586 | 1.2097 | 0.26882
2 | 1.75 | 4 | 9.0726 | 4.3011 | 2.3522 | 12.1357 | 8.0434 | 2.7863 | 13.3065 | 8.1317 | 5.1075 | 19.2361 | 14.3056 | 9.6528 | 20.4301 | 15.7258 | 10.8199 | 26.0417 | 16.5278 | 13.0556 | 22.3118 | 16.5323 | 11.0887 | 21.371 | 16.1962 | 11.1559 | 15.4167 | 11.0417 | 4.9306 | 11.0887 | 6.7876 | 4.2339 | 9.9306 | 5.9722 | 2.4306 | 9.4758 | 6.7876 | 1.7473
2 | 1.75 | 6 | 24.0591 | 11.828 | 7.4597 | 26.7857 | 18.3395 | 9.3006 | 28.8978 | 22.7151 | 13.5753 | 39.5139 | 33.4028 | 25.0694 | 42.6075 | 38.9785 | 28.8978 | 50.2778 | 41.25 | 30.0694 | 46.707 | 39.5833 | 32.0565 | 43.9516 | 36.4919 | 29.1667 | 36.9444 | 30.1389 | 20.2083 | 24.5968 | 17.7419 | 11.1559 | 20.8333 | 14.8611 | 8.8889 | 21.7742 | 14.1801 | 6.3172
2 | 1.75 | 8 | 36.6263 | 23.4543 | 13.7097 | 45.2586 | 36.407 | 17.9315 | 48.1855 | 37.9032 | 26.6129 | 63.6111 | 54.5139 | 46.1806 | 67.6747 | 62.3656 | 53.2258 | 72.6389 | 67.0139 | 55.2083 | 74.5296 | 65.2554 | 53.629 | 67.3387 | 62.6344 | 52.2177 | 58.9583 | 49.9306 | 36.875 | 40.9946 | 33.9382 | 22.3118 | 39.2361 | 26.4583 | 17.7083 | 37.9032 | 25.1344 | 13.9785
2 | 1.75 | 9 | 42.0699 | 29.5699 | 18.2124 | 51.9345 | 42.9315 | 23.3631 | 56.7204 | 45.0269 | 32.8629 | 72.9861 | 62.3611 | 54.1667 | 78.2258 | 70.3629 | 62.6344 | 81.25 | 75.9028 | 66.4583 | 83.9382 | 76.0081 | 67.4059 | 76.8817 | 71.1694 | 63.3065 | 66.875 | 56.875 | 46.7361 | 46.7742 | 40.457 | 28.7634 | 44.3056 | 34.0278 | 21.5278 | 43.414 | 31.922 | 16.5995
2 | 1.75 | 10 | 47.043 | 35.6855 | 21.5726 | 58.7054 | 47.8423 | 27.1141 | 64.6505 | 51.3441 | 38.9785 | 79.4444 | 68.8194 | 62.7083 | 82.9301 | 76.8817 | 70.4973 | 86.1806 | 82.9167 | 73.4028 | 90.5914 | 84.0054 | 75.4704 | 83.3333 | 77.3522 | 68.75 | 73.2639 | 62.8472 | 53.0556 | 53.0242 | 45.3629 | 33.4677 | 50.3472 | 37.9861 | 25.4167 | 48.1183 | 36.9624 | 20.6317
2 | 1.75 | 11 | 50.2016 | 37.0968 | 24.1263 | 63.7649 | 49.9153 | 29.023 | 69.086 | 56.7204 | 43.414 | 82.5694 | 73.6806 | 65.5556 | 87.4328 | 81.922 | 75.9409 | 88.6806 | 85.625 | 77.9167 | 93.75 | 88.0376 | 78.6962 | 86.8952 | 80.5108 | 73.3199 | 79.5139 | 67.2222 | 55.3472 | 56.4516 | 48.8575 | 38.5753 | 55.2083 | 41.5278 | 27.5 | 50.1344 | 38.9785 | 22.1774
2 | 1.75 | 12 | 50.8065 | 37.836 | 25 | 64.881 | 50.136 | 30.5804 | 71.6398 | 57.7957 | 44.2204 | 83.6111 | 75.0694 | 66.25 | 88.7769 | 84.4086 | 78.629 | 89.4444 | 86.8056 | 79.5139 | 95.0269 | 88.7097 | 80.7796 | 88.6425 | 81.9892 | 74.4624 | 79.9306 | 68.6111 | 57.6389 | 57.9973 | 50.9409 | 40.5242 | 56.875 | 43.6806 | 28.125 | 50.5376 | 39.8522 | 23.0511
2 | 1.75 | 15 | 50.8737 | 38.5753 | 25.4704 | 65.7738 | 50.2104 | 30.878 | 72.1102 | 57.7957 | 44.6237 | 84.0278 | 75.3472 | 66.4583 | 88.9113 | 85.0134 | 79.1667 | 89.6528 | 86.9444 | 79.6528 | 95.1613 | 89.3145 | 81.5188 | 88.9113 | 82.2581 | 74.9328 | 80.1389 | 69.375 | 58.2639 | 58.6022 | 51.4785 | 41.3978 | 57.5694 | 43.9583 | 28.75 | 51.1425 | 40.3226 | 23.2527
2 | 1.75 | 20 | 50.8737 | 38.5753 | 25.4704 | 65.7738 | 50.2104 | 30.878 | 72.1102 | 57.7957 | 44.6237 | 84.0278 | 75.3472 | 66.4583 | 88.9113 | 85.0134 | 79.1667 | 89.6528 | 86.9444 | 79.6528 | 95.1613 | 89.3145 | 81.5188 | 88.9113 | 82.2581 | 74.9328 | 80.1389 | 69.375 | 58.2639 | 58.6022 | 51.4785 | 41.3978 | 57.6389 | 43.9583 | 28.75 | 51.1425 | 40.3226 | 23.2527
2 | 1.75 | 25 | 50.8737 | 38.5753 | 25.4704 | 65.7738 | 50.2104 | 30.878 | 72.1102 | 57.7957 | 44.6237 | 84.0278 | 75.3472 | 66.4583 | 88.9113 | 85.0134 | 79.1667 | 89.6528 | 86.9444 | 79.6528 | 95.1613 | 89.3145 | 81.5188 | 88.9113 | 82.2581 | 74.9328 | 80.1389 | 69.375 | 58.2639 | 58.6022 | 51.4785 | 41.3978 | 57.6389 | 43.9583 | 28.75 | 51.1425 | 40.3226 | 23.2527
2 | 2 | 2 | 2.1519 | 0.87366 | 0 | 2.7761 | 1.17 | 0.43873 | 3.293 | 1.4785 | 0.53763 | 5.0694 | 3.2639 | 1.5972 | 5.3091 | 2.8898 | 1.2769 | 7.8472 | 3.6806 | 2.0833 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.7473 | 3.9583 | 2.0833 | 1.0417 | 2.4194 | 1.4785 | 0.53763 | 2.5 | 1.1111 | 0.27778 | 3.1586 | 1.2097 | 0.26882
2 | 2 | 4 | 9.0726 | 4.5699 | 2.5538 | 12.5 | 8.4821 | 3.0095 | 13.3737 | 8.5349 | 5.4435 | 19.2361 | 14.375 | 10 | 20.5645 | 15.7258 | 10.8199 | 26.0417 | 16.5278 | 13.0556 | 22.3118 | 16.5323 | 11.0887 | 21.371 | 16.1962 | 11.1559 | 15.4167 | 11.1111 | 5.625 | 11.0887 | 6.8548 | 4.2339 | 10.0694 | 6.1806 | 2.5694 | 9.9462 | 7.3925 | 1.9489
2 | 2 | 6 | 24.5968 | 13.3826 | 7.7285 | 27.6042 | 19.2529 | 9.375 | 29.8387 | 23.0511 | 14.1129 | 40 | 34.0278 | 26.25 | 42.6075 | 39.1129 | 28.9651 | 50.2778 | 41.25 | 30.2083 | 46.707 | 39.5833 | 32.0565 | 43.9516 | 36.5591 | 29.1667 | 37.2917 | 30.625 | 20.4861 | 25.4032 | 18.5484 | 12.2984 | 21.1806 | 15.625 | 9.7222 | 23.0511 | 15.121 | 7.5269
2 | 2 | 8 | 38.4409 | 25.4032 | 15.6586 | 47.3009 | 38.1466 | 18.6756 | 49.7312 | 39.6505 | 28.4946 | 66.8056 | 56.3889 | 47.5 | 68.0108 | 63.3737 | 53.5618 | 72.7083 | 67.8472 | 55.6944 | 74.7312 | 65.3226 | 53.7634 | 67.9435 | 62.7688 | 53.0242 | 59.6528 | 51.25 | 38.4028 | 43.0108 | 35.4839 | 24.664 | 40.2778 | 28.4028 | 20.3472 | 40.5242 | 27.8898 | 16.2634
2 | 2 | 9 | 44.6909 | 32.5941 | 21.707 | 55.3571 | 46.875 | 25.6696 | 60.2151 | 47.2446 | 36.6935 | 74.5833 | 65.0694 | 57.5694 | 79.3683 | 71.7742 | 64.2473 | 82.4306 | 77.5694 | 67.9167 | 85.4167 | 76.7473 | 68.078 | 77.957 | 72.379 | 63.9785 | 69.0278 | 58.75 | 49.7222 | 49.7312 | 42.4059 | 31.9892 | 46.7361 | 36.1111 | 24.7917 | 47.3118 | 34.4758 | 19.5565
2 | 2 | 10 | 52.2177 | 38.4409 | 25.336 | 63.0208 | 52.753 | 33.4077 | 70.8333 | 56.3172 | 44.1532 | 83.6806 | 72.9861 | 67.0139 | 85.6183 | 79.2339 | 73.3871 | 88.8889 | 84.6528 | 77.5694 | 92.2715 | 85.8199 | 78.0242 | 84.879 | 79.1667 | 73.1183 | 76.6667 | 65.7639 | 57.3611 | 57.6613 | 50.0672 | 37.7016 | 54.4444 | 43.5417 | 31.5278 | 54.5027 | 40.457 | 24.1935
2 | 2 | 11 | 56.6532 | 42.4731 | 30.7124 | 69.7173 | 56.8452 | 35.9375 | 77.2177 | 62.9704 | 51.4113 | 87.7083 | 78.6806 | 71.25 | 90.3898 | 84.879 | 80.6452 | 92.1528 | 88.5417 | 83.5417 | 95.4301 | 90.793 | 82.7285 | 88.8441 | 84.4086 | 79.3683 | 82.7778 | 72.5 | 64.0278 | 64.3145 | 54.3011 | 46.2366 | 61.3889 | 49.6528 | 37.0139 | 57.6613 | 43.4812 | 29.0323
2 | 2 | 12 | 59.6774 | 44.0188 | 34.3414 | 72.4702 | 59.9702 | 39.1036 | 80.1075 | 66.129 | 53.4274 | 91.0417 | 82.5694 | 74.4444 | 92.7419 | 88.3065 | 83.871 | 93.1944 | 89.7917 | 85.7639 | 96.9758 | 92.6747 | 85.2823 | 91.129 | 87.4328 | 81.3172 | 83.4722 | 74.7917 | 66.4583 | 68.6828 | 57.7957 | 49.9328 | 63.75 | 51.3194 | 38.8194 | 60.0806 | 46.371 | 31.25
2 | 2 | 15 | 63.0376 | 45.0269 | 36.6263 | 73.3631 | 60.9606 | 39.6937 | 81.3172 | 66.8683 | 54.3011 | 91.7361 | 83.5417 | 76.1111 | 93.414 | 89.8522 | 85.5511 | 93.8889 | 90.4167 | 86.4583 | 97.1774 | 93.3468 | 86.4919 | 92.4731 | 88.172 | 81.9892 | 84.7917 | 75.9722 | 68.0556 | 71.5726 | 60.1478 | 52.5538 | 66.1111 | 53.3333 | 40.0694 | 60.8871 | 49.2608 | 32.1237
2 | 2 | 20 | 63.0376 | 45.0269 | 36.6263 | 73.3631 | 60.9606 | 39.6937 | 81.3172 | 66.8683 | 54.3011 | 91.7361 | 83.5417 | 76.1111 | 93.414 | 89.9866 | 85.5511 | 93.8889 | 90.4167 | 86.5278 | 97.1774 | 93.3468 | 86.5591 | 92.4731 | 88.172 | 81.9892 | 84.8611 | 76.0417 | 68.0556 | 71.5726 | 60.1478 | 52.5538 | 66.1111 | 53.3333 | 40.1389 | 60.8871 | 49.2608 | 32.1237
2 | 2 | 25 | 63.0376 | 45.0269 | 36.6263 | 73.3631 | 60.9606 | 39.6937 | 81.3172 | 66.8683 | 54.3011 | 91.7361 | 83.5417 | 76.1111 | 93.414 | 89.9866 | 85.5511 | 93.8889 | 90.4167 | 86.5278 | 97.1774 | 93.3468 | 86.5591 | 92.4731 | 88.172 | 81.9892 | 84.8611 | 76.0417 | 68.0556 | 71.5726 | 60.1478 | 52.5538 | 66.1111 | 53.3333 | 40.1389 | 60.8871 | 49.2608 | 32.1237
2 | 2.25 | 2 | 2.2849 | 0.94086 | 0 | 2.7761 | 1.1905 | 0.51057 | 3.293 | 1.4785 | 0.53763 | 5.0694 | 3.2639 | 1.5972 | 5.3091 | 2.8898 | 1.2769 | 7.8472 | 3.6806 | 2.0833 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.7473 | 3.9583 | 2.0833 | 1.0417 | 2.4194 | 1.5457 | 0.53763 | 2.5 | 1.1111 | 0.27778 | 3.1586 | 1.2097 | 0.26882
2 | 2.25 | 4 | 9.207 | 4.5699 | 2.621 | 12.5 | 8.631 | 3.4226 | 13.3737 | 8.5349 | 5.4435 | 19.2361 | 14.375 | 10 | 20.5645 | 15.7258 | 10.8199 | 26.0417 | 16.5278 | 13.0556 | 22.3118 | 16.5323 | 11.0887 | 21.371 | 16.1962 | 11.1559 | 15.4167 | 11.1806 | 5.7639 | 11.0887 | 7.1237 | 4.2339 | 10.2778 | 6.3194 | 2.6389 | 10.1478 | 7.3925 | 2.0833
2 | 2.25 | 6 | 24.8656 | 14.1129 | 7.9973 | 28.1994 | 19.7557 | 10.0446 | 30.2419 | 23.0511 | 14.3817 | 40 | 34.4444 | 27.0833 | 42.6075 | 39.1129 | 28.9651 | 50.2778 | 41.25 | 30.3472 | 46.707 | 39.5833 | 32.0565 | 43.9516 | 36.5591 | 29.1667 | 37.5 | 30.625 | 20.4861 | 25.5376 | 19.0188 | 12.5672 | 21.4583 | 16.3194 | 10.3472 | 23.9919 | 15.7258 | 7.6613
2 | 2.25 | 8 | 39.3145 | 26.3619 | 16.7339 | 48.1886 | 38.6494 | 19.122 | 51.5457 | 41.3978 | 29.7043 | 67.2917 | 57.0833 | 48.8889 | 68.1452 | 63.5753 | 53.6962 | 72.7083 | 67.8472 | 56.0417 | 74.7312 | 65.3226 | 53.7634 | 68.3468 | 62.9032 | 53.0914 | 59.9306 | 51.875 | 39.0972 | 43.75 | 35.8871 | 25.8065 | 40.4861 | 29.3056 | 21.25 | 42.0027 | 29.3683 | 17.2043
2 | 2.25 | 9 | 45.9005 | 34.207 | 24.328 | 56.8452 | 49.1815 | 26.2649 | 61.3575 | 48.6559 | 38.6425 | 74.8611 | 65.9722 | 59.9306 | 79.5027 | 72.379 | 65.0538 | 82.7083 | 78.75 | 68.6806 | 86.2903 | 77.0161 | 68.078 | 78.8306 | 72.6478 | 64.8522 | 69.6528 | 59.8611 | 50.7639 | 51.2097 | 43.8172 | 33.6022 | 48.125 | 38.125 | 26.3194 | 49.1935 | 36.828 | 21.371
2 | 2.25 | 10 | 55.3763 | 41.6667 | 28.8306 | 64.5089 | 56.1192 | 36.1607 | 74.1935 | 58.4677 | 47.043 | 84.375 | 74.6528 | 69.4444 | 86.4247 | 80.8468 | 74.7312 | 89.9306 | 85.6944 | 79.0972 | 93.414 | 86.5591 | 78.8978 | 85.2151 | 80.3091 | 73.9919 | 78.4722 | 67.5694 | 59.7917 | 60.2823 | 52.4866 | 39.7849 | 57.4306 | 46.3889 | 33.75 | 57.1909 | 43.6156 | 26.8817
2 | 2.25 | 11 | 61.6263 | 46.371 | 35.1478 | 71.4286 | 61.8304 | 39.5089 | 80.914 | 67.0699 | 55.1747 | 89.375 | 81.875 | 76.0417 | 92.4731 | 86.6263 | 82.3925 | 93.125 | 90.1389 | 85.8333 | 96.1694 | 92.0699 | 84.6102 | 90.3898 | 87.7688 | 81.0484 | 85.1389 | 74.7917 | 67.9861 | 70.0941 | 58.0645 | 49.328 | 62.8472 | 54.3056 | 41.875 | 61.0215 | 50.2016 | 35.8871
2 | 2.25 | 12 | 66.1962 | 49.1263 | 39.3145 | 76.2649 | 65.997 | 44.1964 | 84.0054 | 71.4382 | 59.3414 | 92.6389 | 85.8333 | 79.7222 | 94.8925 | 90.7258 | 87.6344 | 94.7222 | 92.0833 | 88.9583 | 98.1183 | 94.2876 | 87.164 | 93.8844 | 91.2634 | 84.2742 | 87.2222 | 79.9306 | 72.5 | 75.2688 | 62.6344 | 54.9059 | 69.7917 | 59.0972 | 46.1806 | 64.5833 | 53.8978 | 39.1129
2 | 2.25 | 15 | 71.7742 | 52.8226 | 42.8763 | 78.3482 | 68.006 | 48.3682 | 86.4247 | 73.6559 | 63.3737 | 94.9306 | 87.9861 | 83.5417 | 96.9086 | 93.5484 | 90.3898 | 95.8333 | 93.125 | 90.625 | 98.8575 | 96.1022 | 89.1129 | 95.9677 | 92.0699 | 86.4919 | 90.1389 | 82.7083 | 74.7222 | 78.1586 | 66.2634 | 61.4247 | 73.4722 | 63.4722 | 50.3472 | 66.9355 | 57.5269 | 41.8011
2 | 2.25 | 20 | 71.7742 | 52.8226 | 43.0108 | 78.4226 | 68.006 | 48.4426 | 86.4247 | 73.9247 | 63.3737 | 94.9306 | 87.9861 | 83.5417 | 96.9086 | 93.5484 | 90.5242 | 95.9028 | 93.125 | 90.625 | 98.8575 | 96.1022 | 89.1801 | 95.9677 | 92.0699 | 86.4919 | 90.4167 | 82.7083 | 74.8611 | 78.293 | 66.3978 | 61.4247 | 73.5417 | 63.6806 | 50.6944 | 67.0027 | 57.7285 | 41.8011
2 | 2.25 | 25 | 71.7742 | 52.8226 | 43.0108 | 78.4226 | 68.006 | 48.4426 | 86.4247 | 73.9247 | 63.3737 | 94.9306 | 87.9861 | 83.5417 | 96.9086 | 93.5484 | 90.5242 | 95.9028 | 93.125 | 90.625 | 98.8575 | 96.1022 | 89.1801 | 95.9677 | 92.0699 | 86.4919 | 90.4167 | 82.7083 | 74.8611 | 78.293 | 66.3978 | 61.4247 | 73.5417 | 63.6806 | 50.6944 | 67.0027 | 57.7285 | 41.8011
2 | 2.5 | 2 | 2.2849 | 0.94086 | 0 | 2.7761 | 1.2649 | 0.51057 | 3.293 | 1.4785 | 0.53763 | 5.0694 | 3.2639 | 1.5972 | 5.578 | 2.8898 | 1.2769 | 7.8472 | 3.6806 | 2.0833 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.7473 | 3.9583 | 2.0833 | 1.0417 | 2.4194 | 1.5457 | 0.53763 | 2.5 | 1.1806 | 0.27778 | 3.1586 | 1.2097 | 0.26882
2 | 2.5 | 4 | 9.207 | 4.7043 | 2.621 | 12.5 | 8.8542 | 3.7946 | 13.3737 | 8.5349 | 5.4435 | 19.2361 | 14.375 | 10 | 20.5645 | 15.7258 | 10.8199 | 26.0417 | 16.5278 | 13.0556 | 22.3118 | 16.5323 | 11.0887 | 21.371 | 16.1962 | 11.1559 | 15.4167 | 11.1806 | 5.8333 | 11.0887 | 7.2581 | 4.2339 | 10.2778 | 6.3194 | 2.6389 | 10.2823 | 7.3925 | 2.5538
2 | 2.5 | 6 | 24.8656 | 14.1801 | 7.9973 | 28.3482 | 20.4023 | 10.6399 | 30.2419 | 23.0511 | 14.5161 | 40 | 34.8611 | 27.0833 | 42.6075 | 39.1129 | 28.9651 | 50.2778 | 41.25 | 30.3472 | 46.707 | 39.5833 | 32.0565 | 43.9516 | 36.5591 | 29.1667 | 37.7083 | 30.625 | 20.4861 | 25.5376 | 19.3548 | 12.5672 | 21.4583 | 16.4583 | 10.6944 | 24.664 | 15.9274 | 7.7957
2 | 2.5 | 8 | 39.3817 | 27.0833 | 17.5403 | 48.7787 | 39.2241 | 19.2708 | 51.8817 | 41.5995 | 30.8468 | 67.2917 | 57.2917 | 49.3056 | 68.1452 | 63.6425 | 53.6962 | 72.7083 | 67.8472 | 56.0417 | 74.7312 | 65.3226 | 53.7634 | 68.4812 | 63.0376 | 53.0914 | 59.9306 | 52.5 | 39.4444 | 44.6237 | 36.0215 | 26.4113 | 41.1111 | 30.0694 | 21.6667 | 42.7419 | 29.5699 | 18.2796
2 | 2.5 | 9 | 47.1102 | 35.306 | 25.2016 | 58.1845 | 50 | 27.2321 | 61.9624 | 49.5296 | 39.6505 | 75.0694 | 67.8472 | 61.1111 | 79.9731 | 72.9839 | 65.0538 | 82.8472 | 78.8194 | 68.75 | 86.6935 | 77.0161 | 68.1452 | 78.8978 | 72.7823 | 64.9194 | 69.7917 | 60.0694 | 51.1111 | 51.8817 | 44.9597 | 34.7446 | 49.3056 | 38.9583 | 27.2917 | 50.0672 | 37.7688 | 23.1183
2 | 2.5 | 10 | 56.5188 | 43.8172 | 31.5188 | 65.9534 | 56.9299 | 37.0536 | 75.1344 | 59.7446 | 48.8575 | 84.5833 | 76.3194 | 70.2778 | 86.7608 | 81.3844 | 75.2016 | 90.3472 | 86.0417 | 79.2361 | 93.8844 | 86.6935 | 79.5027 | 85.6855 | 80.578 | 74.328 | 78.8194 | 68.1944 | 60.6944 | 61.5591 | 53.5618 | 41.3306 | 59.3056 | 48.4028 | 35.2083 | 58.4005 | 44.8253 | 29.5027
2 | 2.5 | 11 | 63.6425 | 50.336 | 37.3656 | 73.2374 | 64.7629 | 42.8571 | 82.2581 | 68.9516 | 56.5188 | 90 | 83.6806 | 77.5694 | 92.9435 | 87.2312 | 82.7957 | 93.8194 | 90.9028 | 86.3194 | 96.8414 | 92.4059 | 85.5511 | 91.3306 | 88.4409 | 81.9892 | 85.9722 | 76.0417 | 70.4167 | 71.1694 | 60.0806 | 51.2097 | 65.7639 | 56.5278 | 43.8194 | 63.0376 | 52.0833 | 40.121
2 | 2.5 | 12 | 69.6237 | 55.578 | 42.6747 | 79.9595 | 69.7481 | 49.1815 | 86.0887 | 74.328 | 63.172 | 93.4722 | 87.9861 | 83.4722 | 95.6989 | 91.9355 | 89.3817 | 96.0417 | 93.4722 | 90.0694 | 99.2608 | 96.371 | 88.8441 | 96.707 | 92.6075 | 86.2903 | 89.8611 | 82.9167 | 75.9028 | 77.4866 | 65.0538 | 59.2742 | 72.6389 | 63.5417 | 49.7222 | 69.2204 | 57.7285 | 44.086
2 | 2.5 | 15 | 79.0323 | 63.5081 | 48.6559 | 84.1518 | 74.1071 | 55.234 | 90.3898 | 78.1586 | 70.5645 | 96.4583 | 91.5972 | 87.9861 | 98.3871 | 96.1022 | 93.2124 | 97.3611 | 95.2083 | 92.9861 | 100 | 98.1183 | 92.0699 | 98.2527 | 93.8172 | 89.6505 | 93.2639 | 88.0556 | 80.2778 | 84.543 | 73.8575 | 67.2715 | 80.1389 | 70.8333 | 56.9444 | 75.4032 | 65.6586 | 49.7312
2 | 2.5 | 20 | 79.3683 | 63.7097 | 48.9247 | 84.1518 | 74.3304 | 55.3802 | 90.457 | 78.5618 | 70.6317 | 96.6667 | 91.8056 | 88.125 | 98.3871 | 96.1022 | 93.6156 | 97.3611 | 95.2083 | 93.125 | 100 | 98.1855 | 92.2043 | 98.2527 | 93.8844 | 89.7177 | 93.2639 | 88.0556 | 80.4167 | 85.1478 | 74.0591 | 67.6747 | 80.2083 | 71.5278 | 57.6389 | 75.672 | 66.129 | 50.1344
2 | 2.5 | 25 | 79.3683 | 63.7097 | 48.9247 | 84.1518 | 74.3304 | 55.3802 | 90.457 | 78.5618 | 70.6317 | 96.6667 | 91.8056 | 88.125 | 98.3871 | 96.1022 | 93.6156 | 97.3611 | 95.2083 | 93.125 | 100 | 98.1855 | 92.2043 | 98.2527 | 93.8844 | 89.7177 | 93.2639 | 88.0556 | 80.4167 | 85.2823 | 74.0591 | 67.6747 | 80.2083 | 71.5278 | 57.6389 | 75.672 | 66.129 | 50.1344
2 | 2.75 | 2 | 2.2849 | 0.94086 | 0 | 2.8017 | 1.2649 | 0.51057 | 3.293 | 1.4785 | 0.53763 | 5.0694 | 3.2639 | 1.5972 | 5.578 | 2.8898 | 1.2769 | 7.8472 | 3.6806 | 2.0833 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.7473 | 3.9583 | 2.0833 | 1.0417 | 2.4194 | 1.5457 | 0.53763 | 2.5 | 1.1806 | 0.27778 | 3.1586 | 1.2097 | 0.26882
2 | 2.75 | 4 | 9.207 | 4.7043 | 2.621 | 12.6488 | 8.9286 | 3.7946 | 13.3737 | 8.5349 | 5.4435 | 19.2361 | 14.375 | 10 | 20.5645 | 15.7258 | 10.8199 | 26.0417 | 16.5278 | 13.0556 | 22.3118 | 16.5323 | 11.0887 | 21.371 | 16.1962 | 11.1559 | 15.4167 | 11.1806 | 5.8333 | 11.0887 | 7.2581 | 4.2339 | 10.2778 | 6.3194 | 2.7083 | 10.2823 | 7.3925 | 2.621
2 | 2.75 | 6 | 24.8656 | 14.1801 | 8.1317 | 28.3482 | 20.4023 | 10.8631 | 30.2419 | 23.0511 | 14.5161 | 40 | 34.8611 | 27.2222 | 42.6075 | 39.1129 | 28.9651 | 50.2778 | 41.25 | 30.3472 | 46.707 | 39.5833 | 32.0565 | 43.9516 | 36.5591 | 29.1667 | 37.7083 | 30.625 | 20.4861 | 25.5376 | 19.4892 | 12.5672 | 21.4583 | 16.5972 | 10.8333 | 24.664 | 16.0618 | 8.3333
2 | 2.75 | 8 | 39.3817 | 27.2849 | 17.8091 | 48.8839 | 39.7989 | 20.0893 | 51.8817 | 41.6667 | 31.0484 | 67.2917 | 57.4306 | 49.4444 | 68.1452 | 63.6425 | 53.6962 | 72.7083 | 67.8472 | 56.0417 | 74.7312 | 65.3226 | 53.7634 | 68.4812 | 63.0376 | 53.1586 | 59.9306 | 52.5694 | 39.5833 | 44.6909 | 36.0215 | 26.5457 | 41.25 | 30.5556 | 22.0833 | 42.9435 | 29.7043 | 19.2876
2 | 2.75 | 9 | 47.3118 | 35.5511 | 25.672 | 58.8388 | 50.4464 | 28.3482 | 62.164 | 49.9328 | 40.3226 | 75.0694 | 68.125 | 62.0139 | 79.9731 | 72.9839 | 65.0538 | 82.8472 | 78.8194 | 68.75 | 86.6935 | 77.0161 | 68.1452 | 78.8978 | 72.7823 | 64.9194 | 69.7917 | 60.4861 | 51.3194 | 52.0833 | 46.1694 | 35.2823 | 50 | 39.375 | 27.9167 | 50.7392 | 38.172 | 25.1344
2 | 2.75 | 10 | 57.1237 | 44.5565 | 32.9301 | 66.7411 | 57.892 | 37.872 | 75.4032 | 60.1478 | 49.4624 | 85.1389 | 77.0139 | 70.2778 | 87.0968 | 81.7876 | 75.4032 | 90.3472 | 86.25 | 79.2361 | 93.8844 | 86.7608 | 79.5699 | 85.7527 | 80.7124 | 74.5296 | 78.8194 | 68.1944 | 62.7778 | 61.7608 | 54.9059 | 41.8011 | 61.1111 | 50.0694 | 36.5278 | 59.4758 | 45.2957 | 31.9892
2 | 2.75 | 11 | 64.9194 | 52.2177 | 39.2473 | 74.1123 | 65.7738 | 47.0982 | 83.1317 | 69.4892 | 56.922 | 90.4861 | 84.6528 | 78.6111 | 93.1452 | 87.6344 | 82.8629 | 94.375 | 91.3194 | 86.5278 | 96.9758 | 92.5403 | 86.4247 | 91.9355 | 88.8441 | 82.5269 | 86.1111 | 77.2917 | 71.5278 | 72.1102 | 61.0887 | 52.3522 | 69.6528 | 58.75 | 45.8333 | 64.8522 | 52.7554 | 42.2715
2 | 2.75 | 12 | 72.9839 | 57.9301 | 46.2366 | 81.6964 | 70.3869 | 55.2083 | 87.3656 | 76.6801 | 66.5323 | 93.4722 | 90.4167 | 84.8611 | 96.1694 | 92.5403 | 90.3226 | 97.0139 | 94.375 | 91.5278 | 99.328 | 97.043 | 90.1882 | 97.2446 | 93.078 | 87.2984 | 90.9722 | 84.0278 | 78.5417 | 78.5618 | 65.9274 | 61.3575 | 75.3472 | 65.6944 | 52.5694 | 71.5054 | 60.4167 | 47.4462
2 | 2.75 | 15 | 82.5269 | 68.2124 | 54.3011 | 86.4045 | 79.0179 | 63.516 | 93.6828 | 82.8629 | 75.672 | 98.125 | 94.5833 | 91.3889 | 99.2608 | 97.7823 | 95.3629 | 98.75 | 96.8056 | 94.7222 | 100 | 98.9919 | 94.4892 | 99.328 | 96.2366 | 92.1371 | 95 | 90.7639 | 83.75 | 89.6505 | 78.4274 | 72.5134 | 84.2361 | 76.25 | 62.7083 | 78.9651 | 72.4462 | 57.3925
2 | 2.75 | 20 | 82.9973 | 68.4812 | 55.0403 | 86.6969 | 79.454 | 63.8085 | 94.1532 | 84.0054 | 75.9409 | 98.3333 | 94.7222 | 91.6667 | 99.3952 | 97.9167 | 95.5645 | 98.75 | 96.875 | 94.8611 | 100 | 98.9919 | 94.5565 | 99.328 | 96.5054 | 92.3387 | 95.5556 | 90.9722 | 84.2361 | 90.6586 | 79.5027 | 73.4543 | 84.7917 | 77.5694 | 63.9583 | 80.0403 | 72.9839 | 58.2661
2 | 2.75 | 25 | 82.9973 | 68.4812 | 55.0403 | 86.6969 | 79.454 | 63.8085 | 94.1532 | 84.0054 | 75.9409 | 98.3333 | 94.7222 | 91.6667 | 99.3952 | 97.9167 | 95.5645 | 98.75 | 96.875 | 94.8611 | 100 | 98.9919 | 94.5565 | 99.328 | 96.5054 | 92.3387 | 95.5556 | 90.9722 | 84.2361 | 90.6586 | 79.5027 | 73.4543 | 84.7917 | 77.5694 | 63.9583 | 80.0403 | 72.9839 | 58.2661
2 | 3 | 2 | 2.2849 | 0.94086 | 0 | 2.8017 | 1.2649 | 0.51057 | 3.293 | 1.4785 | 0.53763 | 5.0694 | 3.2639 | 1.5972 | 5.578 | 2.8898 | 1.2769 | 7.8472 | 3.6806 | 2.0833 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.7473 | 3.9583 | 2.0833 | 1.0417 | 2.4194 | 1.5457 | 0.53763 | 2.5 | 1.1806 | 0.27778 | 3.1586 | 1.2097 | 0.26882
2 | 3 | 4 | 9.207 | 4.7043 | 2.6882 | 12.6488 | 8.9286 | 3.7946 | 13.3737 | 8.5349 | 5.4435 | 19.2361 | 14.375 | 10 | 20.5645 | 15.7258 | 10.8199 | 26.0417 | 16.5278 | 13.0556 | 22.3118 | 16.5323 | 11.0887 | 21.371 | 16.1962 | 11.1559 | 15.4167 | 11.1806 | 5.8333 | 11.0887 | 7.2581 | 4.2339 | 10.2778 | 6.3194 | 2.7083 | 10.5511 | 7.3925 | 2.6882
2 | 3 | 6 | 24.8656 | 14.1801 | 8.1317 | 28.3482 | 20.4023 | 10.8631 | 30.2419 | 23.0511 | 14.5833 | 40 | 34.8611 | 27.2222 | 42.6075 | 39.1129 | 28.9651 | 50.2778 | 41.25 | 30.3472 | 46.707 | 39.5833 | 32.0565 | 43.9516 | 36.5591 | 29.1667 | 37.7083 | 30.625 | 20.4861 | 25.5376 | 19.4892 | 12.5672 | 21.4583 | 16.6667 | 10.8333 | 24.664 | 16.2634 | 8.3333
2 | 3 | 8 | 39.3817 | 27.4194 | 17.8763 | 48.8839 | 40.5788 | 20.3125 | 51.8817 | 41.7339 | 31.4516 | 67.2917 | 57.4306 | 49.4444 | 68.1452 | 63.6425 | 53.6962 | 72.7083 | 67.8472 | 56.0417 | 74.7312 | 65.3226 | 53.7634 | 68.4812 | 63.0376 | 53.1586 | 59.9306 | 52.5694 | 39.7917 | 44.6909 | 36.0215 | 27.2177 | 41.3194 | 30.7639 | 22.2222 | 43.3468 | 29.9059 | 19.7581
2 | 3 | 9 | 47.3118 | 35.6855 | 25.8065 | 58.8388 | 50.8185 | 28.497 | 62.164 | 50.0672 | 40.5242 | 75.0694 | 68.2639 | 62.2222 | 79.9731 | 72.9839 | 65.0538 | 82.8472 | 78.8194 | 68.75 | 86.6935 | 77.0161 | 68.1452 | 78.8978 | 72.7823 | 64.9194 | 69.8611 | 60.4861 | 51.4583 | 52.2849 | 46.5726 | 35.6183 | 50.2083 | 39.8611 | 28.1944 | 51.3441 | 38.172 | 26.2769
2 | 3 | 10 | 57.3925 | 45.1244 | 33.8038 | 67.4107 | 58.182 | 38.7649 | 75.4704 | 60.1478 | 50.1344 | 85.4167 | 77.2222 | 70.2778 | 87.3656 | 81.7876 | 75.5376 | 90.3472 | 86.25 | 79.375 | 93.8844 | 86.7608 | 79.5699 | 86.1559 | 80.7124 | 74.5296 | 78.9583 | 68.1944 | 63.2639 | 62.164 | 55.0403 | 43.2124 | 61.5278 | 51.6667 | 37.1528 | 60.6183 | 45.6989 | 33.3333
2 | 3 | 11 | 65.7258 | 52.7554 | 40.5914 | 74.8486 | 66.6667 | 49.1815 | 83.6694 | 69.6237 | 57.7285 | 90.9722 | 85.0694 | 79.0278 | 93.6156 | 88.0376 | 82.9301 | 94.6528 | 91.3889 | 86.6667 | 96.9758 | 92.5403 | 86.6935 | 92.0027 | 89.1129 | 82.6613 | 86.3889 | 77.4306 | 71.6667 | 72.379 | 62.0968 | 53.629 | 71.1806 | 60.2778 | 47.0833 | 66.8011 | 53.3602 | 43.2124
2 | 3 | 12 | 74.7984 | 59.207 | 47.9167 | 82.2917 | 71.3542 | 57.9613 | 88.172 | 76.8817 | 67.7419 | 93.9583 | 91.3194 | 85.2778 | 96.1694 | 93.2124 | 90.9274 | 97.2917 | 95 | 91.8056 | 99.328 | 97.043 | 90.9946 | 97.379 | 93.2796 | 87.6344 | 91.7361 | 84.7917 | 79.5139 | 79.2339 | 67.4059 | 63.3737 | 76.9444 | 68.0556 | 54.0278 | 73.5887 | 62.7016 | 49.5296
2 | 3 | 15 | 86.4919 | 72.8495 | 58.7366 | 89.2857 | 83.5565 | 69.7147 | 95.2285 | 86.6935 | 78.9651 | 98.4028 | 96.0417 | 92.9167 | 100 | 98.5887 | 96.9086 | 99.7917 | 97.8472 | 95.6944 | 100 | 99.9328 | 96.3038 | 99.664 | 98.0511 | 93.75 | 96.8056 | 92.2222 | 85.9028 | 92.1371 | 82.0565 | 77.4194 | 87.9861 | 80 | 68.125 | 82.6613 | 76.2769 | 62.9032
2 | 3 | 20 | 87.3656 | 74.0591 | 59.9462 | 89.881 | 84.5238 | 70.6589 | 96.3038 | 87.7688 | 79.5699 | 99.0278 | 96.1806 | 93.6806 | 100 | 99.1935 | 97.1774 | 99.8611 | 98.0556 | 95.7639 | 100 | 100 | 96.4382 | 99.7984 | 98.2527 | 94.086 | 96.9444 | 92.8472 | 86.875 | 93.2796 | 84.3414 | 79.0995 | 89.1667 | 82.4306 | 70.0694 | 84.4758 | 77.6882 | 64.9194
2 | 3 | 25 | 87.3656 | 74.0591 | 59.9462 | 89.881 | 84.5238 | 70.6589 | 96.3038 | 87.7688 | 79.5699 | 99.0278 | 96.1806 | 93.6806 | 100 | 99.1935 | 97.1774 | 99.8611 | 98.0556 | 95.7639 | 100 | 100 | 96.4382 | 99.7984 | 98.2527 | 94.086 | 96.9444 | 92.8472 | 86.875 | 93.2796 | 84.3414 | 79.0995 | 89.1667 | 82.4306 | 70.0694 | 84.4758 | 77.6882 | 64.9194
2 | 3.25 | 2 | 2.2849 | 0.94086 | 0 | 2.8736 | 1.2649 | 0.51057 | 3.293 | 1.4785 | 0.53763 | 5.0694 | 3.2639 | 1.5972 | 5.578 | 2.8898 | 1.2769 | 7.8472 | 3.6806 | 2.0833 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.7473 | 3.9583 | 2.0833 | 1.0417 | 2.4194 | 1.5457 | 0.53763 | 2.5 | 1.1806 | 0.27778 | 3.1586 | 1.2097 | 0.26882
2 | 3.25 | 4 | 9.207 | 4.7043 | 2.6882 | 12.6488 | 8.9286 | 3.7946 | 13.3737 | 8.5349 | 5.578 | 19.2361 | 14.375 | 10 | 20.5645 | 15.7258 | 10.8199 | 26.0417 | 16.5278 | 13.0556 | 22.3118 | 16.5323 | 11.0887 | 21.371 | 16.1962 | 11.1559 | 15.4167 | 11.1806 | 5.8333 | 11.0887 | 7.2581 | 4.2339 | 10.2778 | 6.3194 | 2.7083 | 10.5511 | 7.3925 | 2.6882
2 | 3.25 | 6 | 24.8656 | 14.1801 | 8.1317 | 28.3482 | 20.4023 | 10.8631 | 30.2419 | 23.0511 | 14.7849 | 40 | 34.8611 | 27.2222 | 42.6075 | 39.1129 | 28.9651 | 50.2778 | 41.25 | 30.3472 | 46.707 | 39.5833 | 32.0565 | 43.9516 | 36.5591 | 29.1667 | 37.7083 | 30.625 | 20.4861 | 25.5376 | 19.4892 | 12.5672 | 21.4583 | 16.6667 | 10.8333 | 24.664 | 16.2634 | 8.3333
2 | 3.25 | 8 | 39.3817 | 27.4194 | 17.8763 | 48.8839 | 40.7943 | 20.4613 | 51.8817 | 41.7339 | 31.5188 | 67.2917 | 57.4306 | 49.4444 | 68.1452 | 63.6425 | 53.6962 | 72.7083 | 67.8472 | 56.0417 | 74.7312 | 65.3226 | 53.7634 | 68.4812 | 63.0376 | 53.1586 | 59.9306 | 52.5694 | 39.7917 | 44.6909 | 36.0215 | 27.2177 | 41.3194 | 30.7639 | 22.2917 | 43.4812 | 30.0403 | 20.0941
2 | 3.25 | 9 | 47.3118 | 35.6855 | 26.0081 | 58.8388 | 51.2521 | 28.6458 | 62.164 | 50.2016 | 40.5242 | 75.0694 | 68.2639 | 62.2917 | 79.9731 | 72.9839 | 65.0538 | 82.8472 | 78.8194 | 68.75 | 86.6935 | 77.0161 | 68.1452 | 78.8978 | 72.7823 | 64.9194 | 70 | 60.4861 | 51.5972 | 52.4194 | 46.8414 | 35.7527 | 50.4167 | 39.8611 | 28.3333 | 51.9489 | 38.172 | 26.8145
2 | 3.25 | 10 | 57.5269 | 45.5645 | 34.2742 | 67.7083 | 58.3282 | 39.0625 | 75.4704 | 60.1478 | 50.6048 | 85.4861 | 77.2917 | 70.2778 | 87.3656 | 81.7876 | 75.5376 | 90.3472 | 86.25 | 79.375 | 93.8844 | 86.7608 | 79.5699 | 86.3575 | 80.7124 | 74.5296 | 78.9583 | 68.1944 | 63.4028 | 62.2312 | 55.1747 | 43.6156 | 61.7361 | 51.8056 | 37.2222 | 61.2231 | 45.7661 | 33.871
2 | 3.25 | 11 | 66.8011 | 53.2258 | 42.5403 | 75.5106 | 66.7411 | 49.7024 | 83.8038 | 70.1613 | 58.4005 | 91.1111 | 85.3472 | 79.5139 | 93.6156 | 88.1048 | 83.0645 | 94.7222 | 91.5278 | 86.6667 | 96.9758 | 92.5403 | 86.7608 | 92.0027 | 89.1129 | 82.9301 | 86.5278 | 77.5694 | 72.0139 | 72.5806 | 62.4328 | 54.3683 | 72.0139 | 61.1111 | 47.8472 | 67.6075 | 54.1667 | 43.9516
2 | 3.25 | 12 | 76.1425 | 60.4167 | 49.328 | 83.3308 | 71.9494 | 59.2262 | 88.9785 | 77.0833 | 68.2796 | 94.1667 | 91.9444 | 85.625 | 96.2366 | 93.4812 | 90.9274 | 97.6389 | 95.1389 | 92.0139 | 99.328 | 97.043 | 91.129 | 97.379 | 93.6156 | 87.9704 | 92.0139 | 84.9306 | 79.8611 | 79.6371 | 68.5484 | 64.0457 | 77.3611 | 69.5833 | 54.9306 | 74.3952 | 63.0376 | 51.6801
2 | 3.25 | 15 | 88.8441 | 75.6048 | 65.3226 | 91.5179 | 86.1607 | 72.6037 | 95.9677 | 88.8441 | 81.5188 | 99.1667 | 97.1528 | 94.0278 | 100 | 99.0591 | 97.9167 | 100 | 98.8889 | 96.25 | 100 | 100 | 96.8414 | 100 | 98.9919 | 95.0941 | 97.0833 | 94.0278 | 89.375 | 93.8172 | 85.4167 | 80.578 | 90.1389 | 83.6806 | 72.1528 | 84.7446 | 80.3091 | 67.5403
2 | 3.25 | 20 | 90.793 | 79.3683 | 67.4731 | 92.3363 | 88.3005 | 76.6472 | 97.5806 | 91.7339 | 82.8629 | 99.7917 | 97.4306 | 95.0694 | 100 | 99.9328 | 98.0511 | 100 | 99.1667 | 96.3889 | 100 | 100 | 97.1774 | 100 | 99.328 | 95.9677 | 97.8472 | 94.9306 | 90.7639 | 96.1694 | 87.3656 | 83.8038 | 92.3611 | 86.6667 | 75.8333 | 87.6344 | 82.5941 | 70.0269
2 | 3.25 | 25 | 90.793 | 79.3683 | 67.4731 | 92.3363 | 88.3005 | 76.7216 | 97.5806 | 91.7339 | 82.8629 | 99.7917 | 97.4306 | 95.0694 | 100 | 99.9328 | 98.0511 | 100 | 99.1667 | 96.3889 | 100 | 100 | 97.1774 | 100 | 99.328 | 95.9677 | 97.9167 | 94.9306 | 90.8333 | 96.1694 | 87.3656 | 83.8038 | 92.3611 | 86.6667 | 75.8333 | 87.6344 | 82.5941 | 70.0269
2 | 3.5 | 2 | 2.2849 | 0.94086 | 0 | 2.8736 | 1.2649 | 0.51057 | 3.293 | 1.4785 | 0.53763 | 5.0694 | 3.2639 | 1.5972 | 5.578 | 2.8898 | 1.2769 | 7.8472 | 3.6806 | 2.0833 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.7473 | 3.9583 | 2.0833 | 1.0417 | 2.4194 | 1.5457 | 0.53763 | 2.5 | 1.1806 | 0.27778 | 3.1586 | 1.2097 | 0.26882
2 | 3.5 | 4 | 9.207 | 4.7043 | 2.6882 | 12.6488 | 8.9286 | 3.7946 | 13.3737 | 8.5349 | 5.578 | 19.2361 | 14.375 | 10 | 20.5645 | 15.7258 | 10.8199 | 26.0417 | 16.5278 | 13.0556 | 22.3118 | 16.5323 | 11.0887 | 21.371 | 16.1962 | 11.1559 | 15.4167 | 11.1806 | 5.8333 | 11.0887 | 7.2581 | 4.2339 | 10.2778 | 6.3194 | 2.7083 | 10.5511 | 7.3925 | 2.6882
2 | 3.5 | 6 | 24.8656 | 14.1801 | 8.1317 | 28.3482 | 20.4023 | 10.8631 | 30.2419 | 23.0511 | 14.7849 | 40 | 34.8611 | 27.2222 | 42.6075 | 39.1129 | 28.9651 | 50.2778 | 41.25 | 30.3472 | 46.707 | 39.5833 | 32.0565 | 43.9516 | 36.5591 | 29.1667 | 37.7083 | 30.625 | 20.4861 | 25.5376 | 19.4892 | 12.5672 | 21.4583 | 16.6667 | 10.8333 | 24.664 | 16.2634 | 8.3333
2 | 3.5 | 8 | 39.3817 | 27.4194 | 18.078 | 48.8839 | 40.7943 | 20.5357 | 51.8817 | 41.7339 | 31.5188 | 67.2917 | 57.4306 | 49.4444 | 68.1452 | 63.6425 | 53.6962 | 72.7083 | 67.8472 | 56.0417 | 74.7312 | 65.3226 | 53.7634 | 68.4812 | 63.0376 | 53.1586 | 59.9306 | 52.5694 | 39.7917 | 44.6909 | 36.0215 | 27.2177 | 41.3194 | 30.7639 | 22.2917 | 43.4812 | 30.0403 | 20.0941
2 | 3.5 | 9 | 47.3118 | 35.6855 | 26.2097 | 58.8388 | 51.6112 | 28.9435 | 62.164 | 50.2016 | 40.5242 | 75.0694 | 68.2639 | 62.4306 | 79.9731 | 73.1183 | 65.0538 | 82.8472 | 78.8194 | 68.75 | 86.6935 | 77.0161 | 68.1452 | 78.8978 | 72.7823 | 64.9194 | 70 | 60.4861 | 51.5972 | 52.4194 | 46.9758 | 35.7527 | 50.5556 | 39.8611 | 28.3333 | 52.0833 | 38.172 | 27.0161
2 | 3.5 | 10 | 57.5269 | 45.5645 | 34.6102 | 67.7827 | 58.4744 | 39.3601 | 75.4704 | 60.1478 | 50.7392 | 85.4861 | 77.2917 | 70.4167 | 87.3656 | 81.7876 | 75.5376 | 90.3472 | 86.25 | 79.375 | 93.8844 | 86.7608 | 79.5699 | 86.3575 | 80.7124 | 74.5296 | 78.9583 | 68.1944 | 63.4028 | 62.2984 | 55.1747 | 43.6828 | 61.8056 | 51.9444 | 37.2917 | 61.2231 | 45.7661 | 34.1398
2 | 3.5 | 11 | 67.1371 | 53.9339 | 43.4812 | 75.8056 | 66.7411 | 50.0744 | 83.8038 | 70.4973 | 59.2742 | 91.3194 | 85.4167 | 79.7222 | 93.6156 | 88.2392 | 83.1989 | 94.7222 | 91.5278 | 86.6667 | 96.9758 | 92.5403 | 86.7608 | 92.3387 | 89.1129 | 82.9301 | 86.5278 | 77.5694 | 72.0139 | 72.7151 | 62.5 | 54.7043 | 72.5 | 61.7361 | 48.2639 | 67.9435 | 54.2339 | 44.086
2 | 3.5 | 12 | 77.0161 | 60.7934 | 50.5376 | 83.3333 | 72.0161 | 59.9035 | 89.1129 | 77.621 | 68.5484 | 94.375 | 92.0833 | 85.6944 | 96.4382 | 93.6156 | 90.9274 | 97.7083 | 95.1389 | 92.1528 | 99.328 | 97.043 | 91.1962 | 97.379 | 93.6156 | 88.0376 | 92.1528 | 85.0694 | 79.8611 | 79.9731 | 69.2204 | 64.4489 | 78.125 | 70 | 55.625 | 74.7984 | 63.3065 | 52.3522
2 | 3.5 | 15 | 89.7849 | 78.1586 | 70.1613 | 92.4851 | 86.9048 | 76.5907 | 97.9839 | 91.1962 | 82.7957 | 99.5833 | 97.5694 | 94.8611 | 100 | 99.4624 | 98.3199 | 100 | 99.3056 | 97.2222 | 100 | 100 | 97.7151 | 100 | 99.2608 | 95.8333 | 97.9167 | 95.2778 | 90.2778 | 94.6909 | 87.7688 | 82.7285 | 91.25 | 85.7639 | 76.0417 | 86.5591 | 82.1909 | 70.4301
2 | 3.5 | 20 | 92.9435 | 84.3414 | 73.5887 | 95.0149 | 90.7328 | 81.994 | 98.9247 | 94.0188 | 85.0134 | 100 | 99.0972 | 95.7639 | 100 | 100 | 98.9247 | 100 | 99.5139 | 97.5 | 100 | 100 | 98.0511 | 100 | 100 | 97.4462 | 98.8889 | 96.5972 | 92.5694 | 98.3871 | 91.0618 | 87.5 | 94.5833 | 89.3056 | 80.9028 | 90.121 | 87.0968 | 74.7984
2 | 3.5 | 25 | 92.9435 | 84.3414 | 73.5887 | 95.0149 | 90.7328 | 82.0685 | 98.9247 | 94.0188 | 85.0134 | 100 | 99.0972 | 95.7639 | 100 | 100 | 98.9247 | 100 | 99.5139 | 97.5 | 100 | 100 | 98.0511 | 100 | 100 | 97.4462 | 98.8889 | 96.5972 | 92.6389 | 98.3871 | 91.0618 | 87.5 | 94.5833 | 89.375 | 80.9722 | 90.121 | 87.0968 | 74.7984
2 | 3.75 | 2 | 2.2849 | 0.94086 | 0 | 2.8736 | 1.2649 | 0.51057 | 3.293 | 1.4785 | 0.53763 | 5.0694 | 3.2639 | 1.5972 | 5.578 | 2.8898 | 1.2769 | 7.8472 | 3.6806 | 2.0833 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.7473 | 3.9583 | 2.0833 | 1.0417 | 2.4194 | 1.5457 | 0.53763 | 2.5 | 1.1806 | 0.27778 | 3.1586 | 1.2097 | 0.26882
2 | 3.75 | 4 | 9.207 | 4.7043 | 2.6882 | 12.6488 | 8.9286 | 3.7946 | 13.3737 | 8.5349 | 5.578 | 19.2361 | 14.375 | 10 | 20.5645 | 15.7258 | 10.8199 | 26.0417 | 16.5278 | 13.0556 | 22.3118 | 16.5323 | 11.0887 | 21.371 | 16.1962 | 11.1559 | 15.4167 | 11.1806 | 5.8333 | 11.0887 | 7.2581 | 4.2339 | 10.2778 | 6.3194 | 2.7083 | 10.5511 | 7.3925 | 2.6882
2 | 3.75 | 6 | 24.8656 | 14.1801 | 8.1317 | 28.3482 | 20.4023 | 10.8631 | 30.2419 | 23.0511 | 14.7849 | 40 | 34.8611 | 27.2222 | 42.6075 | 39.1129 | 28.9651 | 50.2778 | 41.25 | 30.3472 | 46.707 | 39.5833 | 32.0565 | 43.9516 | 36.5591 | 29.1667 | 37.7083 | 30.625 | 20.4861 | 25.5376 | 19.4892 | 12.5672 | 21.4583 | 16.6667 | 10.8333 | 24.664 | 16.2634 | 8.3333
2 | 3.75 | 8 | 39.3817 | 27.4194 | 18.1452 | 48.8839 | 40.7943 | 20.5357 | 51.8817 | 41.7339 | 31.7204 | 67.2917 | 57.4306 | 49.4444 | 68.1452 | 63.6425 | 53.6962 | 72.7083 | 67.8472 | 56.0417 | 74.7312 | 65.3226 | 53.7634 | 68.4812 | 63.0376 | 53.1586 | 59.9306 | 52.5694 | 39.7917 | 44.6909 | 36.0215 | 27.2177 | 41.3194 | 30.8333 | 22.2917 | 43.4812 | 30.0403 | 20.0941
2 | 3.75 | 9 | 47.3118 | 35.6855 | 26.2769 | 58.8388 | 51.6112 | 29.0179 | 62.164 | 50.2016 | 40.9274 | 75.0694 | 68.2639 | 62.4306 | 79.9731 | 73.1183 | 65.0538 | 82.8472 | 78.8194 | 68.75 | 86.6935 | 77.0161 | 68.1452 | 78.8978 | 72.7823 | 64.9194 | 70 | 60.4861 | 51.5972 | 52.4194 | 47.043 | 35.7527 | 50.5556 | 39.8611 | 28.3333 | 52.0833 | 38.172 | 27.1505
2 | 3.75 | 10 | 57.5269 | 45.5645 | 34.6102 | 67.7827 | 58.5489 | 39.4345 | 75.4704 | 60.1478 | 50.8737 | 85.4861 | 77.2917 | 70.5556 | 87.3656 | 81.7876 | 75.5376 | 90.3472 | 86.25 | 79.375 | 93.8844 | 86.7608 | 79.5699 | 86.3575 | 80.7124 | 74.5296 | 78.9583 | 68.1944 | 63.4028 | 62.2984 | 55.1747 | 43.6828 | 61.8056 | 52.1528 | 37.2917 | 61.2231 | 45.7661 | 34.3414
2 | 3.75 | 11 | 67.1371 | 54.2339 | 43.6828 | 75.9493 | 67.2491 | 50.2232 | 83.8038 | 70.6989 | 59.8118 | 91.3194 | 85.5556 | 79.8611 | 93.6156 | 88.2392 | 83.1989 | 94.7222 | 91.5278 | 86.6667 | 96.9758 | 92.5403 | 86.7608 | 92.4059 | 89.1129 | 82.9301 | 86.5278 | 77.5694 | 72.0139 | 72.7151 | 62.5 | 54.7715 | 72.6389 | 61.9444 | 48.4722 | 67.9435 | 54.2339 | 44.2204
2 | 3.75 | 12 | 77.1505 | 61.2903 | 51.2097 | 83.3333 | 72.8782 | 60.1242 | 89.1129 | 78.4274 | 68.9516 | 94.5139 | 92.0833 | 85.7639 | 96.5054 | 93.6156 | 90.9946 | 97.7778 | 95.1389 | 92.2222 | 99.328 | 97.043 | 91.1962 | 97.379 | 93.6156 | 88.0376 | 92.1528 | 85.0694 | 79.8611 | 80.2419 | 69.3548 | 64.5833 | 78.3333 | 70.6944 | 55.9028 | 74.9328 | 63.7769 | 52.4866
2 | 3.75 | 15 | 90.6586 | 80.1075 | 72.8495 | 93.0804 | 87.6488 | 78.9332 | 97.9839 | 92.0027 | 84.2742 | 99.7917 | 97.9167 | 95.2778 | 100 | 99.7312 | 98.5215 | 100 | 99.3056 | 97.5 | 100 | 100 | 98.0511 | 100 | 99.4624 | 96.1694 | 98.5417 | 95.5556 | 91.3194 | 95.0941 | 88.6425 | 83.6022 | 92.1528 | 87.4306 | 78.4028 | 88.4409 | 83.7366 | 72.5134
2 | 3.75 | 20 | 94.422 | 88.3065 | 79.5699 | 96.5774 | 92.3209 | 85.3423 | 99.5296 | 96.1694 | 87.836 | 100 | 99.4444 | 96.4583 | 100 | 100 | 99.5968 | 100 | 100 | 98.1944 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.5 | 93.8889 | 99.4624 | 93.4812 | 90.5914 | 96.6667 | 91.875 | 84.7222 | 92.7419 | 88.8441 | 80.1075
2 | 3.75 | 25 | 94.422 | 88.3065 | 79.5699 | 96.5774 | 92.3209 | 85.4167 | 99.5296 | 96.1694 | 87.836 | 100 | 99.5139 | 96.4583 | 100 | 100 | 99.5968 | 100 | 100 | 98.1944 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.5 | 93.8889 | 99.4624 | 93.4812 | 90.6586 | 96.6667 | 92.0139 | 84.7222 | 92.7419 | 88.8441 | 80.1075
2 | 4 | 2 | 2.2849 | 0.94086 | 0 | 2.8736 | 1.2649 | 0.51057 | 3.293 | 1.4785 | 0.53763 | 5.0694 | 3.2639 | 1.5972 | 5.578 | 2.8898 | 1.2769 | 7.8472 | 3.6806 | 2.0833 | 5.9812 | 3.1586 | 1.4785 | 5.3763 | 3.293 | 1.7473 | 3.9583 | 2.0833 | 1.0417 | 2.4194 | 1.5457 | 0.53763 | 2.5 | 1.1806 | 0.27778 | 3.1586 | 1.2097 | 0.26882
2 | 4 | 4 | 9.207 | 4.7043 | 2.6882 | 12.6488 | 8.9286 | 3.7946 | 13.3737 | 8.5349 | 5.578 | 19.2361 | 14.375 | 10 | 20.5645 | 15.7258 | 10.8199 | 26.0417 | 16.5278 | 13.0556 | 22.3118 | 16.5323 | 11.0887 | 21.371 | 16.1962 | 11.1559 | 15.4167 | 11.1806 | 5.8333 | 11.0887 | 7.2581 | 4.2339 | 10.2778 | 6.3194 | 2.7083 | 10.5511 | 7.3925 | 2.6882
2 | 4 | 6 | 24.8656 | 14.1801 | 8.1317 | 28.3482 | 20.4023 | 10.8631 | 30.2419 | 23.0511 | 14.7849 | 40 | 34.8611 | 27.2222 | 42.6075 | 39.1129 | 28.9651 | 50.2778 | 41.25 | 30.3472 | 46.707 | 39.5833 | 32.0565 | 43.9516 | 36.5591 | 29.1667 | 37.7083 | 30.625 | 20.4861 | 25.5376 | 19.4892 | 12.5672 | 21.4583 | 16.6667 | 10.8333 | 24.664 | 16.2634 | 8.3333
2 | 4 | 8 | 39.3817 | 27.4194 | 18.1452 | 48.8839 | 40.7943 | 20.5357 | 51.8817 | 41.7339 | 31.7204 | 67.2917 | 57.4306 | 49.4444 | 68.1452 | 63.6425 | 53.6962 | 72.7083 | 67.8472 | 56.0417 | 74.7312 | 65.3226 | 53.7634 | 68.4812 | 63.0376 | 53.1586 | 59.9306 | 52.5694 | 39.7917 | 44.6909 | 36.0215 | 27.2177 | 41.3194 | 30.8333 | 22.2917 | 43.4812 | 30.0403 | 20.0941
2 | 4 | 9 | 47.3118 | 35.6855 | 26.2769 | 58.8388 | 51.6112 | 29.0179 | 62.164 | 50.2016 | 40.9274 | 75.0694 | 68.2639 | 62.4306 | 79.9731 | 73.1183 | 65.0538 | 82.8472 | 78.8194 | 68.75 | 86.6935 | 77.0161 | 68.1452 | 78.8978 | 72.7823 | 64.9194 | 70 | 60.4861 | 51.5972 | 52.4194 | 47.043 | 35.7527 | 50.5556 | 39.8611 | 28.3333 | 52.0833 | 38.172 | 27.1505
2 | 4 | 10 | 57.5269 | 45.5645 | 34.8118 | 67.7827 | 58.7644 | 39.5089 | 75.4704 | 60.1478 | 50.8737 | 85.4861 | 77.2917 | 70.625 | 87.3656 | 81.7876 | 75.5376 | 90.3472 | 86.25 | 79.375 | 93.8844 | 86.7608 | 79.5699 | 86.3575 | 80.7124 | 74.5296 | 78.9583 | 68.1944 | 63.4028 | 62.2984 | 55.1747 | 43.6828 | 61.8056 | 52.2917 | 37.2917 | 61.2231 | 45.7661 | 34.4086
2 | 4 | 11 | 67.1371 | 54.2339 | 43.9516 | 75.9493 | 67.8571 | 50.2976 | 83.8038 | 70.7661 | 60.0134 | 91.3194 | 85.5556 | 79.9306 | 93.6156 | 88.2392 | 83.1989 | 94.7222 | 91.5278 | 86.6667 | 96.9758 | 92.5403 | 86.7608 | 92.4059 | 89.1129 | 82.9301 | 86.5278 | 77.5694 | 72.0139 | 72.7151 | 62.5 | 54.7715 | 72.6389 | 62.0833 | 48.4722 | 67.9435 | 54.2339 | 44.2204
2 | 4 | 12 | 77.1505 | 61.2903 | 52.0833 | 83.4796 | 74.0327 | 60.1242 | 89.1129 | 78.6962 | 69.086 | 94.5833 | 92.0833 | 85.7639 | 96.5054 | 93.6156 | 90.9946 | 97.7778 | 95.1389 | 92.2222 | 99.328 | 97.043 | 91.2634 | 97.379 | 93.6156 | 88.0376 | 92.1528 | 85.0694 | 79.8611 | 80.3091 | 69.422 | 64.6505 | 78.4722 | 70.7639 | 56.1806 | 75 | 63.8441 | 52.5538
2 | 4 | 15 | 91.2634 | 81.1828 | 74.1263 | 93.6756 | 88.3185 | 80.4623 | 98.1183 | 92.6747 | 84.7446 | 99.7917 | 98.125 | 95.625 | 100 | 99.7984 | 98.7903 | 100 | 99.3056 | 97.9167 | 100 | 100 | 98.2527 | 100 | 99.5296 | 96.7742 | 98.8194 | 96.1111 | 91.5972 | 95.5645 | 89.4489 | 84.207 | 92.6389 | 88.4028 | 79.7917 | 89.2473 | 84.6102 | 74.7312
2 | 4 | 20 | 95.8333 | 91.2634 | 82.5941 | 97.9911 | 94.1964 | 89.296 | 99.9328 | 97.4462 | 90.1882 | 100 | 99.7917 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.4722 | 95.9028 | 99.7984 | 95.6317 | 92.8763 | 98.0556 | 94.375 | 88.125 | 94.8925 | 90.793 | 85.0134
2 | 4 | 25 | 95.8333 | 91.3306 | 82.6613 | 97.9911 | 94.1964 | 89.4397 | 99.9328 | 97.5134 | 90.1882 | 100 | 99.8611 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.6806 | 95.9028 | 99.9328 | 95.6317 | 92.9435 | 98.0556 | 94.5833 | 88.125 | 94.8925 | 90.793 | 85.1478
4 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1528 | 0 | 0 | 1.7473 | 0.60484 | 0 | 3.5417 | 0.90278 | 0 | 2.8226 | 1.0753 | 0 | 2.1505 | 0.80645 | 0 | 1.25 | 0 | 0 | 0.53763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0.5 | 4 | 0.53763 | 0 | 0 | 1.7857 | 0 | 0 | 2.2849 | 0 | 0 | 7.0139 | 3.0556 | 0.27778 | 7.9973 | 4.9731 | 1.9489 | 14.1667 | 8.1944 | 2.3611 | 13.5753 | 6.7876 | 4.1667 | 11.5591 | 5.8468 | 2.8226 | 4.3056 | 1.875 | 0.069444 | 1.9489 | 0.26882 | 0 | 1.3889 | 0 | 0 | 1.6129 | 0 | 0
4 | 0.5 | 6 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.1075 | 0.53763 | 0 | 11.25 | 6.875 | 1.3889 | 15.121 | 10.5511 | 5.3091 | 19.0972 | 13.4722 | 5.1389 | 22.5806 | 13.3065 | 7.5269 | 17.7419 | 9.4758 | 6.1828 | 9.7222 | 4.0972 | 0.97222 | 3.5618 | 1.1425 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0 | 0
4 | 0.5 | 8 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.0556 | 1.3889 | 15.3898 | 11.4919 | 5.578 | 20.4167 | 13.8889 | 5.5556 | 23.7903 | 15.0538 | 8.1317 | 19.4892 | 10.5511 | 6.6532 | 10.4167 | 4.4444 | 0.97222 | 3.6962 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0 | 0
4 | 0.5 | 9 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.0556 | 1.3889 | 15.3898 | 11.5591 | 5.578 | 20.4167 | 13.8889 | 5.5556 | 23.7903 | 15.0538 | 8.1989 | 19.4892 | 10.5511 | 6.6532 | 10.4167 | 4.4444 | 0.97222 | 3.6962 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0 | 0
4 | 0.5 | 10 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.0556 | 1.3889 | 15.3898 | 11.5591 | 5.578 | 20.4167 | 13.8889 | 5.5556 | 23.8575 | 15.0538 | 8.1989 | 19.4892 | 10.5511 | 6.6532 | 10.4167 | 4.4444 | 0.97222 | 3.6962 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0 | 0
4 | 0.5 | 11 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.0556 | 1.3889 | 15.3898 | 11.5591 | 5.578 | 20.4167 | 13.8889 | 5.5556 | 23.8575 | 15.0538 | 8.1989 | 19.4892 | 10.5511 | 6.6532 | 10.4167 | 4.4444 | 0.97222 | 3.6962 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0 | 0
4 | 0.5 | 12 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.0556 | 1.3889 | 15.3898 | 11.5591 | 5.578 | 20.4167 | 13.8889 | 5.5556 | 23.8575 | 15.0538 | 8.1989 | 19.4892 | 10.5511 | 6.6532 | 10.4167 | 4.4444 | 0.97222 | 3.6962 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0 | 0
4 | 0.5 | 15 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.0556 | 1.3889 | 15.3898 | 11.5591 | 5.578 | 20.4167 | 13.8889 | 5.5556 | 23.8575 | 15.0538 | 8.1989 | 19.4892 | 10.5511 | 6.6532 | 10.4167 | 4.4444 | 0.97222 | 3.6962 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0 | 0
4 | 0.5 | 20 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.0556 | 1.3889 | 15.3898 | 11.5591 | 5.578 | 20.4167 | 13.8889 | 5.5556 | 23.8575 | 15.0538 | 8.1989 | 19.4892 | 10.5511 | 6.6532 | 10.4167 | 4.4444 | 0.97222 | 3.6962 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0 | 0
4 | 0.5 | 25 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.9812 | 0.53763 | 0 | 12.7083 | 8.0556 | 1.3889 | 15.3898 | 11.5591 | 5.578 | 20.4167 | 13.8889 | 5.5556 | 23.8575 | 15.0538 | 8.1989 | 19.4892 | 10.5511 | 6.6532 | 10.4167 | 4.4444 | 0.97222 | 3.6962 | 1.2097 | 0 | 1.7361 | 0 | 0 | 2.2849 | 0 | 0
4 | 0.75 | 2 | 0.73925 | 0 | 0 | 1.5343 | 0 | 0 | 1.2097 | 0 | 0 | 2.7083 | 1.5278 | 0.34722 | 3.1586 | 1.2769 | 0 | 4.8611 | 2.5 | 0.27778 | 4.4355 | 1.4785 | 0.53763 | 3.0914 | 1.4785 | 0.80645 | 2.1528 | 0.69444 | 0 | 1.2769 | 0 | 0 | 0.625 | 0 | 0 | 0.80645 | 0 | 0
4 | 0.75 | 4 | 2.621 | 1.0753 | 0 | 5.9883 | 2.2655 | 0 | 7.6613 | 2.3522 | 0.87366 | 13.4028 | 8.75 | 3.6111 | 13.4409 | 9.4758 | 4.7043 | 21.4583 | 11.5972 | 6.875 | 17.8763 | 11.9624 | 7.6613 | 16.5323 | 10.0806 | 7.7957 | 10.0694 | 6.0417 | 1.4583 | 3.6962 | 2.1505 | 0 | 3.4028 | 1.3194 | 0 | 4.6371 | 2.1505 | 0
4 | 0.75 | 6 | 6.7876 | 2.621 | 0 | 11.2582 | 4.9107 | 0 | 15.5914 | 6.7876 | 2.5538 | 25.4861 | 19.0278 | 10.1389 | 28.0242 | 21.4382 | 14.5833 | 35.7639 | 23.3333 | 17.2917 | 33.5349 | 25.4704 | 19.9597 | 33.4677 | 22.7151 | 16.5995 | 23.125 | 12.6389 | 7.0139 | 10.2151 | 5.3091 | 1.6129 | 6.3889 | 2.5 | 0.55556 | 6.9892 | 3.629 | 0
4 | 0.75 | 8 | 8.7366 | 2.8898 | 0 | 12.7232 | 6.0781 | 0.3592 | 18.6156 | 7.5941 | 4.0323 | 32.0139 | 23.6806 | 13.6806 | 36.6935 | 27.6882 | 20.0941 | 43.2639 | 30.5556 | 22.9861 | 44.9597 | 34.4086 | 26.7473 | 43.0108 | 29.0323 | 21.707 | 28.8194 | 16.4583 | 8.8194 | 13.4409 | 7.0565 | 2.4194 | 7.3611 | 2.7778 | 0.55556 | 7.5941 | 3.9651 | 0
4 | 0.75 | 9 | 8.7366 | 2.8898 | 0 | 12.7232 | 6.0781 | 0.3592 | 18.8172 | 7.5941 | 4.0323 | 32.7083 | 24.4444 | 14.0278 | 37.7688 | 28.0914 | 20.6989 | 43.75 | 30.9028 | 23.4028 | 45.5645 | 35.4839 | 27.4194 | 43.4812 | 29.9731 | 22.5806 | 29.0278 | 16.7361 | 8.8194 | 13.4409 | 7.2581 | 2.4194 | 7.3611 | 2.7778 | 0.55556 | 7.5941 | 3.9651 | 0
4 | 0.75 | 10 | 8.7366 | 2.8898 | 0 | 12.7232 | 6.0781 | 0.3592 | 18.8844 | 7.5941 | 4.0323 | 32.7083 | 24.4444 | 14.0278 | 38.0376 | 28.0914 | 20.8333 | 43.75 | 30.9028 | 23.4722 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.1075 | 22.5806 | 29.0278 | 16.7361 | 8.8889 | 13.4409 | 7.3253 | 2.4194 | 7.3611 | 2.7778 | 0.55556 | 7.5941 | 3.9651 | 0
4 | 0.75 | 11 | 8.7366 | 2.8898 | 0 | 12.7232 | 6.0781 | 0.3592 | 18.8844 | 7.5941 | 4.0323 | 32.7083 | 24.4444 | 14.0278 | 38.0376 | 28.0914 | 20.8333 | 43.75 | 30.9722 | 23.4722 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.1075 | 22.5806 | 29.0278 | 16.7361 | 8.8889 | 13.4409 | 7.3253 | 2.4194 | 7.3611 | 2.7778 | 0.55556 | 7.5941 | 3.9651 | 0
4 | 0.75 | 12 | 8.7366 | 2.8898 | 0 | 12.7232 | 6.0781 | 0.3592 | 18.8844 | 7.5941 | 4.0323 | 32.7083 | 24.4444 | 14.0278 | 38.0376 | 28.0914 | 20.8333 | 43.75 | 30.9722 | 23.4722 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.1075 | 22.5806 | 29.0278 | 16.7361 | 8.8889 | 13.4409 | 7.3253 | 2.4194 | 7.3611 | 2.7778 | 0.55556 | 7.5941 | 3.9651 | 0
4 | 0.75 | 15 | 8.7366 | 2.8898 | 0 | 12.7232 | 6.0781 | 0.3592 | 18.8844 | 7.5941 | 4.0323 | 32.7083 | 24.4444 | 14.0278 | 38.0376 | 28.0914 | 20.8333 | 43.75 | 30.9722 | 23.4722 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.1075 | 22.5806 | 29.0278 | 16.7361 | 8.8889 | 13.4409 | 7.3253 | 2.4194 | 7.3611 | 2.7778 | 0.55556 | 7.5941 | 3.9651 | 0
4 | 0.75 | 20 | 8.7366 | 2.8898 | 0 | 12.7232 | 6.0781 | 0.3592 | 18.8844 | 7.5941 | 4.0323 | 32.7083 | 24.4444 | 14.0278 | 38.0376 | 28.0914 | 20.8333 | 43.75 | 30.9722 | 23.4722 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.1075 | 22.5806 | 29.0278 | 16.7361 | 8.8889 | 13.4409 | 7.3253 | 2.4194 | 7.3611 | 2.7778 | 0.55556 | 7.5941 | 3.9651 | 0
4 | 0.75 | 25 | 8.7366 | 2.8898 | 0 | 12.7232 | 6.0781 | 0.3592 | 18.8844 | 7.5941 | 4.0323 | 32.7083 | 24.4444 | 14.0278 | 38.0376 | 28.0914 | 20.8333 | 43.75 | 30.9722 | 23.4722 | 45.6317 | 35.5511 | 27.5538 | 43.4812 | 30.1075 | 22.5806 | 29.0278 | 16.7361 | 8.8889 | 13.4409 | 7.3253 | 2.4194 | 7.3611 | 2.7778 | 0.55556 | 7.5941 | 3.9651 | 0
4 | 1 | 2 | 1.2097 | 0 | 0 | 1.6805 | 0 | 0 | 1.7473 | 0.53763 | 0 | 3.125 | 2.0139 | 0.34722 | 3.9651 | 1.5457 | 0.60484 | 5.625 | 2.8472 | 0.625 | 4.4355 | 1.7473 | 0.73925 | 4.2339 | 2.0161 | 1.2769 | 2.7083 | 1.0417 | 0.27778 | 1.4785 | 0.60484 | 0 | 0.97222 | 0 | 0 | 1.2097 | 0.53763 | 0
4 | 1 | 4 | 3.8978 | 1.7473 | 0 | 8.6925 | 3.7279 | 0.94674 | 11.0887 | 4.0323 | 1.7473 | 15.0694 | 10.7639 | 5.6944 | 16.8011 | 12.164 | 7.9973 | 22.7778 | 13.5417 | 9.6528 | 20.4973 | 14.1129 | 9.1398 | 19.9597 | 13.0376 | 9.1398 | 12.5 | 8.4028 | 3.3333 | 6.586 | 3.9651 | 1.4113 | 6.0417 | 2.6389 | 0.90278 | 6.7876 | 3.1586 | 0.40323
4 | 1 | 6 | 12.0968 | 5.8468 | 1.6129 | 18.6756 | 11.6328 | 3.6458 | 20.8333 | 12.836 | 5.914 | 31.3194 | 24.0972 | 17.0833 | 35.5511 | 29.5027 | 21.8414 | 44.2361 | 34.5139 | 24.1667 | 41.2634 | 34.2742 | 26.5457 | 40.3226 | 29.5699 | 23.6559 | 30.1389 | 19.4444 | 12.1528 | 17.0699 | 10.6183 | 4.7043 | 13.1944 | 7.1528 | 2.5694 | 14.1129 | 7.3253 | 1.1425
4 | 1 | 8 | 19.8925 | 8.9382 | 2.5538 | 27.3065 | 17.7827 | 5.2083 | 31.1156 | 19.4892 | 9.4758 | 44.5833 | 35.8333 | 26.4583 | 51.6129 | 44.086 | 35.6183 | 56.3194 | 47.9861 | 38.8194 | 62.2312 | 49.5296 | 39.7849 | 57.4597 | 44.6237 | 37.3656 | 41.1111 | 31.5972 | 21.1111 | 22.4462 | 15.2554 | 8.1989 | 17.5694 | 10 | 3.125 | 20.9677 | 10.2823 | 2.7554
4 | 1 | 9 | 20.2285 | 9.6774 | 2.5538 | 28.5073 | 18.006 | 5.6548 | 32.8629 | 21.2366 | 9.879 | 47.9861 | 39.4444 | 28.125 | 56.6532 | 46.707 | 39.1801 | 59.7222 | 50.4861 | 40.625 | 66.8011 | 52.621 | 42.6747 | 61.6935 | 48.1183 | 40.793 | 43.6806 | 33.9583 | 23.125 | 23.7231 | 15.9274 | 8.4677 | 18.1944 | 10.2778 | 3.1944 | 21.3038 | 10.6855 | 2.957
4 | 1 | 10 | 20.2285 | 9.6774 | 2.5538 | 28.5073 | 18.006 | 5.6548 | 33.4005 | 21.707 | 10.4839 | 48.4722 | 40.625 | 28.8889 | 57.7285 | 47.7151 | 40.6586 | 60.3472 | 51.875 | 41.0417 | 68.1452 | 54.2339 | 45.1613 | 62.6344 | 49.5968 | 41.2634 | 44.3056 | 34.375 | 23.125 | 24.0591 | 16.129 | 8.5349 | 18.3333 | 10.3472 | 3.1944 | 21.371 | 10.7527 | 3.0914
4 | 1 | 11 | 20.2285 | 9.6774 | 2.5538 | 28.5073 | 18.006 | 5.6548 | 33.6022 | 21.707 | 10.4839 | 48.6806 | 40.9722 | 28.8889 | 57.7285 | 47.9839 | 40.7258 | 60.3472 | 51.9444 | 41.0417 | 68.3468 | 54.2339 | 45.3629 | 62.836 | 49.7312 | 41.3306 | 44.3056 | 34.4444 | 23.125 | 24.0591 | 16.1962 | 8.5349 | 18.4028 | 10.3472 | 3.1944 | 21.371 | 10.7527 | 3.0914
4 | 1 | 12 | 20.2285 | 9.6774 | 2.5538 | 28.5073 | 18.006 | 5.6548 | 33.6022 | 21.707 | 10.4839 | 48.6806 | 40.9722 | 28.8889 | 57.7285 | 47.9839 | 40.7258 | 60.3472 | 52.0139 | 41.0417 | 68.414 | 54.2339 | 45.3629 | 62.836 | 49.7312 | 41.3306 | 44.3056 | 34.4444 | 23.125 | 24.0591 | 16.1962 | 8.5349 | 18.4028 | 10.3472 | 3.1944 | 21.371 | 10.7527 | 3.0914
4 | 1 | 15 | 20.2285 | 9.6774 | 2.5538 | 28.5073 | 18.006 | 5.6548 | 33.6022 | 21.707 | 10.4839 | 48.6806 | 40.9722 | 28.8889 | 57.7285 | 47.9839 | 40.7258 | 60.3472 | 52.0139 | 41.0417 | 68.414 | 54.3011 | 45.3629 | 62.836 | 49.7312 | 41.3306 | 44.3056 | 34.4444 | 23.125 | 24.0591 | 16.1962 | 8.5349 | 18.4028 | 10.3472 | 3.1944 | 21.371 | 10.7527 | 3.0914
4 | 1 | 20 | 20.2285 | 9.6774 | 2.5538 | 28.5073 | 18.006 | 5.6548 | 33.6022 | 21.707 | 10.4839 | 48.6806 | 40.9722 | 28.8889 | 57.7285 | 47.9839 | 40.7258 | 60.3472 | 52.0139 | 41.0417 | 68.414 | 54.3011 | 45.3629 | 62.836 | 49.7312 | 41.3306 | 44.3056 | 34.4444 | 23.125 | 24.0591 | 16.1962 | 8.5349 | 18.4028 | 10.3472 | 3.1944 | 21.371 | 10.7527 | 3.0914
4 | 1 | 25 | 20.2285 | 9.6774 | 2.5538 | 28.5073 | 18.006 | 5.6548 | 33.6022 | 21.707 | 10.4839 | 48.6806 | 40.9722 | 28.8889 | 57.7285 | 47.9839 | 40.7258 | 60.3472 | 52.0139 | 41.0417 | 68.414 | 54.3011 | 45.3629 | 62.836 | 49.7312 | 41.3306 | 44.3056 | 34.4444 | 23.125 | 24.0591 | 16.1962 | 8.5349 | 18.4028 | 10.3472 | 3.1944 | 21.371 | 10.7527 | 3.0914
4 | 1.25 | 2 | 1.5457 | 0 | 0 | 1.7549 | 0.29762 | 0 | 2.0161 | 0.73925 | 0 | 3.75 | 2.0833 | 0.69444 | 4.0995 | 1.9489 | 0.73925 | 5.8333 | 2.9861 | 0.76389 | 4.4355 | 1.9489 | 0.80645 | 4.5027 | 2.1505 | 1.2769 | 3.2639 | 1.3889 | 0.55556 | 1.9489 | 0.67204 | 0 | 1.5278 | 0 | 0 | 1.8145 | 0.60484 | 0
4 | 1.25 | 4 | 6.3844 | 2.4194 | 1.0753 | 9.8753 | 5.6958 | 1.4137 | 12.2312 | 6.0484 | 2.957 | 16.9444 | 11.7361 | 7.8472 | 18.4812 | 13.172 | 8.871 | 24.7917 | 15.2778 | 10.5556 | 21.0349 | 15.3898 | 9.6774 | 20.2957 | 14.4489 | 9.9462 | 14.0972 | 9.4444 | 4.1667 | 8.1989 | 5.1075 | 2.5538 | 7.7083 | 4.375 | 1.25 | 7.9301 | 3.9651 | 0.94086
4 | 1.25 | 6 | 18.5484 | 7.5269 | 4.7043 | 22.8423 | 14.3601 | 5.7292 | 25.8065 | 19.4892 | 8.6694 | 34.5139 | 28.4722 | 22.2222 | 39.2473 | 33.7366 | 25.4032 | 47.9861 | 38.6111 | 27.0833 | 44.3548 | 37.836 | 29.1667 | 41.4651 | 32.1237 | 26.9489 | 34.2361 | 26.1806 | 15.8333 | 19.9597 | 12.7688 | 8.4677 | 16.5972 | 10.5556 | 5.625 | 16.6667 | 10.4167 | 4.0323
4 | 1.25 | 8 | 28.5618 | 14.5833 | 7.7285 | 37.0536 | 25.372 | 11.4583 | 40.3226 | 30.5108 | 16.5323 | 53.9583 | 46.0417 | 37.0139 | 60.7527 | 53.0242 | 46.5054 | 65.3472 | 59.5139 | 46.7361 | 71.2366 | 59.6102 | 48.7231 | 62.9704 | 54.7715 | 46.4382 | 48.5417 | 41.7361 | 27.2917 | 29.6371 | 23.4543 | 13.2392 | 27.1528 | 16.1111 | 8.8889 | 28.4946 | 17.5403 | 5.914
4 | 1.25 | 9 | 31.1156 | 16.3306 | 8.1989 | 40.6404 | 28.6458 | 12.7232 | 43.0108 | 34.1398 | 19.422 | 60.8333 | 49.7222 | 41.25 | 66.4651 | 59.6102 | 51.6801 | 71.4583 | 66.5278 | 52.5 | 77.2849 | 65.5914 | 57.1909 | 71.6398 | 59.8118 | 52.4866 | 54.4444 | 45.0694 | 32.9861 | 34.2742 | 27.2177 | 15.7258 | 29.7222 | 20.1389 | 8.9583 | 30.7124 | 19.3548 | 6.6532
4 | 1.25 | 10 | 32.2581 | 16.5995 | 8.6022 | 42.5185 | 29.6721 | 13.244 | 43.8844 | 36.3575 | 20.9677 | 64.9306 | 53.4722 | 44.4444 | 69.6237 | 63.5081 | 53.8306 | 74.4444 | 68.4028 | 54.2361 | 80.5108 | 70.2285 | 60.9543 | 74.4624 | 62.0968 | 53.9651 | 57.7083 | 46.875 | 35.2083 | 35.0806 | 29.7715 | 16.6667 | 30.9722 | 21.3194 | 9.0278 | 31.1156 | 20.0269 | 7.5941
4 | 1.25 | 11 | 32.4597 | 16.6667 | 8.7366 | 42.9315 | 29.8363 | 13.3185 | 45.0941 | 36.9624 | 20.9677 | 65.9722 | 54.5139 | 44.9306 | 70.2285 | 64.5161 | 54.3683 | 74.7917 | 68.6806 | 54.3056 | 80.9812 | 71.371 | 61.8952 | 74.9328 | 62.7016 | 54.5699 | 59.5833 | 47.4306 | 35.8333 | 35.2151 | 30.3763 | 17.0027 | 31.1111 | 21.3194 | 9.0278 | 31.5188 | 20.2957 | 7.6613
4 | 1.25 | 12 | 32.4597 | 16.6667 | 8.7366 | 42.9315 | 29.9107 | 13.3185 | 45.1613 | 37.0296 | 21.1022 | 66.1111 | 54.5833 | 45.0694 | 70.2285 | 65.1882 | 54.5027 | 74.9306 | 68.8889 | 54.3056 | 81.1828 | 71.5726 | 62.0296 | 75.1344 | 62.836 | 54.8387 | 59.7222 | 47.6389 | 36.0417 | 35.4167 | 30.4435 | 17.0699 | 31.1806 | 21.3194 | 9.0972 | 31.586 | 20.3629 | 7.7957
4 | 1.25 | 15 | 32.4597 | 16.6667 | 8.7366 | 42.9315 | 29.9107 | 13.6161 | 45.1613 | 37.0296 | 21.1022 | 66.1111 | 54.5833 | 45.0694 | 70.2957 | 65.1882 | 54.5027 | 75 | 68.8889 | 54.3056 | 81.1828 | 71.5726 | 62.0968 | 75.1344 | 62.9032 | 54.9059 | 59.7222 | 47.6389 | 36.0417 | 35.4167 | 30.4435 | 17.1371 | 31.1806 | 21.3194 | 9.0972 | 31.586 | 20.3629 | 7.7957
4 | 1.25 | 20 | 32.4597 | 16.6667 | 8.7366 | 42.9315 | 29.9107 | 13.6161 | 45.1613 | 37.0296 | 21.1022 | 66.1111 | 54.5833 | 45.0694 | 70.2957 | 65.1882 | 54.5027 | 75 | 68.8889 | 54.3056 | 81.1828 | 71.5726 | 62.0968 | 75.1344 | 62.9032 | 54.9059 | 59.7222 | 47.6389 | 36.0417 | 35.4167 | 30.4435 | 17.1371 | 31.1806 | 21.3194 | 9.0972 | 31.586 | 20.3629 | 7.7957
4 | 1.25 | 25 | 32.4597 | 16.6667 | 8.7366 | 42.9315 | 29.9107 | 13.6161 | 45.1613 | 37.0296 | 21.1022 | 66.1111 | 54.5833 | 45.0694 | 70.2957 | 65.1882 | 54.5027 | 75 | 68.8889 | 54.3056 | 81.1828 | 71.5726 | 62.0968 | 75.1344 | 62.9032 | 54.9059 | 59.7222 | 47.6389 | 36.0417 | 35.4167 | 30.4435 | 17.1371 | 31.1806 | 21.3194 | 9.0972 | 31.586 | 20.3629 | 7.7957
4 | 1.5 | 2 | 1.7473 | 0 | 0 | 1.8986 | 0.65681 | 0 | 2.8226 | 0.94086 | 0 | 4.0972 | 2.2917 | 0.69444 | 4.5027 | 2.0833 | 0.73925 | 5.9722 | 2.9861 | 1.25 | 4.4355 | 1.9489 | 0.80645 | 4.7043 | 2.1505 | 1.2769 | 3.4722 | 1.5278 | 0.55556 | 2.2849 | 0.80645 | 0 | 1.5278 | 0.55556 | 0 | 2.2849 | 0.67204 | 0
4 | 1.5 | 4 | 8.6022 | 2.957 | 1.3441 | 11.0863 | 6.6964 | 2.0833 | 12.7016 | 7.1909 | 3.8306 | 17.7778 | 12.7083 | 9.2361 | 18.8172 | 15.0538 | 9.4758 | 25 | 15.625 | 11.0417 | 21.2366 | 15.3898 | 9.7446 | 20.2957 | 14.4489 | 10.0134 | 14.6528 | 10 | 4.7222 | 8.7366 | 5.9812 | 3.4274 | 8.8194 | 4.7222 | 1.875 | 8.9382 | 5.7796 | 1.6129
4 | 1.5 | 6 | 21.707 | 9.8118 | 6.25 | 24.0327 | 17.2491 | 6.9196 | 27.2849 | 21.5726 | 10.6183 | 36.5278 | 31.7361 | 23.8889 | 41.9355 | 36.6263 | 27.7554 | 49.7917 | 39.8611 | 28.3333 | 45.3629 | 38.4409 | 29.9059 | 41.8011 | 34.0726 | 27.3522 | 35.9028 | 28.125 | 19.1667 | 22.7151 | 16.129 | 9.1398 | 18.2639 | 12.8472 | 7.9167 | 18.9516 | 13.0376 | 5.5108
4 | 1.5 | 8 | 32.6613 | 20.8333 | 10.7527 | 42.7135 | 31.25 | 15.6994 | 44.5565 | 35.2151 | 21.5054 | 59.1667 | 50.9028 | 42.7778 | 64.7849 | 58.871 | 50.1344 | 70.0694 | 63.8194 | 52.5 | 73.3871 | 63.5081 | 51.9489 | 65.5914 | 59.4758 | 49.5968 | 53.9583 | 46.9444 | 32.7083 | 35.8871 | 29.5699 | 17.4059 | 33.9583 | 22.2222 | 14.3056 | 34.4086 | 22.5806 | 10.1478
4 | 1.5 | 9 | 37.0968 | 23.9919 | 14.0457 | 48.0655 | 36.4737 | 20.3869 | 51.0753 | 40.457 | 26.4113 | 66.6667 | 58.4028 | 50.2083 | 73.6559 | 66.5995 | 59.2742 | 77.1528 | 73.1944 | 62.4306 | 81.3844 | 72.1774 | 63.7769 | 75.2688 | 67.5403 | 58.4005 | 63.5417 | 53.2639 | 41.5278 | 40.9274 | 35.9543 | 23.1183 | 39.7917 | 27.2917 | 15.4861 | 38.1048 | 27.4194 | 13.1048
4 | 1.5 | 10 | 39.5833 | 26.3441 | 16.8011 | 51.2649 | 38.2235 | 22.0982 | 55.5108 | 43.3468 | 29.8387 | 71.0417 | 62.7083 | 55.9722 | 78.1586 | 71.371 | 64.1129 | 81.0417 | 77.3611 | 68.3333 | 86.7608 | 78.9651 | 70.6317 | 80.2419 | 72.1774 | 63.6425 | 67.7083 | 57.1528 | 46.8056 | 45.9005 | 39.1129 | 25.2016 | 43.5417 | 31.7361 | 16.6667 | 41.2634 | 30.3091 | 14.7177
4 | 1.5 | 11 | 41.1962 | 27.4866 | 18.1452 | 52.9018 | 39.2113 | 22.7679 | 57.8629 | 45.4301 | 31.3172 | 73.9583 | 64.5833 | 57.5694 | 80.1075 | 74.5296 | 65.9274 | 82.6389 | 79.375 | 69.9306 | 88.4409 | 81.5188 | 72.7823 | 82.1909 | 74.1935 | 65.3226 | 71.5278 | 59.375 | 47.9861 | 46.8414 | 41.0618 | 27.0161 | 44.7917 | 33.2639 | 17.3611 | 42.3387 | 31.7204 | 15.2554
4 | 1.5 | 12 | 41.3306 | 27.621 | 18.4812 | 53.125 | 39.2755 | 22.8423 | 58.2661 | 45.6989 | 31.922 | 74.1667 | 64.9306 | 58.1944 | 81.1156 | 75.4032 | 67.8091 | 83.1944 | 79.7222 | 70.1389 | 88.9785 | 82.5941 | 73.3199 | 82.9301 | 74.3952 | 66.4651 | 71.8056 | 59.8611 | 48.6111 | 47.4462 | 41.5323 | 27.2177 | 45.3472 | 33.4722 | 17.4306 | 42.6075 | 31.922 | 15.5242
4 | 1.5 | 15 | 41.4651 | 27.6882 | 18.5484 | 53.125 | 39.3473 | 22.9167 | 58.4005 | 45.7661 | 31.922 | 74.2361 | 65 | 58.2639 | 81.25 | 75.6048 | 68.078 | 83.5417 | 79.8611 | 70.1389 | 89.0457 | 82.7957 | 73.7231 | 83.1317 | 74.4624 | 66.6667 | 71.875 | 60 | 48.6111 | 47.5134 | 41.5995 | 27.4194 | 45.4167 | 33.4722 | 17.6389 | 42.6075 | 31.922 | 15.5914
4 | 1.5 | 20 | 41.4651 | 27.6882 | 18.5484 | 53.125 | 39.3473 | 22.9167 | 58.4005 | 45.7661 | 31.922 | 74.2361 | 65 | 58.2639 | 81.25 | 75.6048 | 68.078 | 83.5417 | 79.8611 | 70.1389 | 89.0457 | 82.7957 | 73.7231 | 83.1317 | 74.4624 | 66.6667 | 71.875 | 60 | 48.6111 | 47.5134 | 41.5995 | 27.4194 | 45.4167 | 33.4722 | 17.6389 | 42.6075 | 31.922 | 15.5914
4 | 1.5 | 25 | 41.4651 | 27.6882 | 18.5484 | 53.125 | 39.3473 | 22.9167 | 58.4005 | 45.7661 | 31.922 | 74.2361 | 65 | 58.2639 | 81.25 | 75.6048 | 68.078 | 83.5417 | 79.8611 | 70.1389 | 89.0457 | 82.7957 | 73.7231 | 83.1317 | 74.4624 | 66.6667 | 71.875 | 60 | 48.6111 | 47.5134 | 41.5995 | 27.4194 | 45.4167 | 33.4722 | 17.6389 | 42.6075 | 31.922 | 15.5914
4 | 1.75 | 2 | 1.7473 | 0 | 0 | 2.0474 | 0.73122 | 0 | 2.8226 | 1.0081 | 0 | 4.0972 | 2.2917 | 0.76389 | 4.5027 | 2.2177 | 0.73925 | 5.9722 | 2.9861 | 1.3889 | 4.4355 | 1.9489 | 0.80645 | 4.7043 | 2.1505 | 1.2769 | 3.4722 | 1.5278 | 0.55556 | 2.2849 | 0.80645 | 0 | 1.5972 | 0.55556 | 0 | 2.4194 | 0.67204 | 0
4 | 1.75 | 4 | 8.6022 | 3.629 | 1.6129 | 11.2351 | 7.4559 | 2.6375 | 13.0376 | 7.4597 | 4.5027 | 18.6111 | 12.7778 | 9.375 | 19.4892 | 15.5914 | 9.6102 | 25 | 15.8333 | 11.4583 | 21.2366 | 15.3898 | 9.7446 | 20.2957 | 14.4489 | 10.0134 | 14.7917 | 10.1389 | 4.7917 | 9.879 | 6.1156 | 3.6962 | 9.5833 | 5.1389 | 2.2222 | 9.0726 | 6.1828 | 1.6129
4 | 1.75 | 6 | 23.5215 | 11.0215 | 6.586 | 26.1161 | 17.6211 | 8.4821 | 28.3602 | 21.9758 | 13.1048 | 38.125 | 32.8472 | 24.5139 | 42.0027 | 37.9032 | 28.293 | 49.7917 | 39.9306 | 29.1667 | 45.6317 | 38.5081 | 30.4435 | 41.8683 | 34.9462 | 27.8898 | 36.5972 | 28.6806 | 19.5833 | 24.0591 | 17.0027 | 10.6183 | 20 | 14.0278 | 8.8889 | 21.3038 | 13.4409 | 5.914
4 | 1.75 | 8 | 36.0887 | 22.8495 | 12.7016 | 44.3196 | 35.6399 | 17.2619 | 47.7151 | 37.2984 | 26.0753 | 62.7778 | 54.0972 | 44.9306 | 66.6667 | 61.7608 | 52.3522 | 71.3889 | 65.9028 | 53.75 | 73.5887 | 64.1801 | 53.0914 | 66.4651 | 61.1559 | 50.6048 | 57.7083 | 49.3056 | 35.4167 | 40.793 | 32.5269 | 20.6989 | 38.8889 | 26.3194 | 17.2222 | 37.164 | 24.1935 | 13.5753
4 | 1.75 | 9 | 41.3978 | 28.8306 | 17.6747 | 51.4881 | 42.4107 | 23.2143 | 56.3172 | 44.6909 | 32.1909 | 72.5 | 62.0139 | 53.1944 | 77.7554 | 70.1613 | 62.4328 | 80.6944 | 75.4861 | 65.9722 | 83.0645 | 75.0672 | 66.0618 | 76.3441 | 70.9005 | 62.3656 | 66.8056 | 56.3194 | 45.7639 | 46.1022 | 39.4489 | 28.0242 | 43.5417 | 33.1944 | 21.1111 | 42.8091 | 31.586 | 16.3306
4 | 1.75 | 10 | 46.9086 | 34.8118 | 21.2366 | 58.4821 | 46.8519 | 26.8165 | 63.9113 | 50.7392 | 38.6425 | 79.0278 | 68.5417 | 61.8056 | 82.9301 | 76.7473 | 69.9597 | 86.1806 | 82.5694 | 73.4028 | 90.457 | 83.5349 | 75.2688 | 83.1989 | 77.0833 | 68.078 | 72.9861 | 62.2222 | 52.5694 | 52.2177 | 44.6237 | 33.2661 | 49.7222 | 37.7083 | 24.8611 | 47.379 | 36.5591 | 20.4973
4 | 1.75 | 11 | 50.2016 | 36.6935 | 23.6559 | 63.5417 | 49.7665 | 28.7254 | 68.5484 | 56.6532 | 43.3468 | 82.1528 | 73.2639 | 65.5556 | 87.4328 | 81.5188 | 75.4032 | 88.6806 | 85.4861 | 77.9167 | 93.75 | 88.0376 | 78.5618 | 86.5591 | 80.0403 | 73.1855 | 79.0972 | 66.875 | 55.2778 | 55.9812 | 48.3199 | 38.0376 | 55.0694 | 41.0417 | 27.2222 | 49.9328 | 38.5753 | 22.043
4 | 1.75 | 12 | 50.8065 | 37.0968 | 24.7312 | 64.881 | 49.9872 | 30.5804 | 71.6398 | 57.7957 | 44.086 | 83.1944 | 74.5139 | 66.25 | 88.4409 | 84.2742 | 78.629 | 89.4444 | 86.8056 | 79.5139 | 95.0269 | 88.7097 | 80.7796 | 88.6425 | 81.8548 | 74.0591 | 79.7222 | 68.0556 | 57.6389 | 57.8629 | 50.9409 | 39.7849 | 56.7361 | 43.2639 | 27.8472 | 50.336 | 39.6505 | 22.9167
4 | 1.75 | 15 | 50.8737 | 38.5081 | 25.2016 | 65.7738 | 50.2104 | 30.878 | 72.1102 | 57.7957 | 44.4892 | 83.6111 | 75.0694 | 66.4583 | 88.6425 | 85.0134 | 79.1667 | 89.6528 | 86.9444 | 79.5833 | 95.1613 | 89.3145 | 81.5188 | 88.9113 | 82.1237 | 74.9328 | 79.9306 | 68.8194 | 58.2639 | 58.4677 | 51.4785 | 41.0618 | 57.5694 | 43.6111 | 28.75 | 50.8065 | 40.3226 | 23.1183
4 | 1.75 | 20 | 50.8737 | 38.5081 | 25.2016 | 65.7738 | 50.2104 | 30.878 | 72.1102 | 57.7957 | 44.4892 | 83.6111 | 75.0694 | 66.4583 | 88.6425 | 85.0134 | 79.1667 | 89.6528 | 86.9444 | 79.5833 | 95.1613 | 89.3145 | 81.5188 | 88.9113 | 82.1237 | 74.9328 | 79.9306 | 68.8194 | 58.2639 | 58.4677 | 51.4785 | 41.0618 | 57.6389 | 43.6111 | 28.75 | 50.8065 | 40.3226 | 23.1183
4 | 1.75 | 25 | 50.8737 | 38.5081 | 25.2016 | 65.7738 | 50.2104 | 30.878 | 72.1102 | 57.7957 | 44.4892 | 83.6111 | 75.0694 | 66.4583 | 88.6425 | 85.0134 | 79.1667 | 89.6528 | 86.9444 | 79.5833 | 95.1613 | 89.3145 | 81.5188 | 88.9113 | 82.1237 | 74.9328 | 79.9306 | 68.8194 | 58.2639 | 58.4677 | 51.4785 | 41.0618 | 57.6389 | 43.6111 | 28.75 | 50.8065 | 40.3226 | 23.1183
4 | 2 | 2 | 1.7473 | 0 | 0 | 2.0474 | 0.73122 | 0 | 2.8226 | 1.0753 | 0 | 4.0972 | 2.2917 | 0.76389 | 4.5027 | 2.2177 | 0.94086 | 5.9722 | 2.9861 | 1.3889 | 4.4355 | 1.9489 | 0.80645 | 4.7043 | 2.1505 | 1.2769 | 3.4722 | 1.5278 | 0.55556 | 2.2849 | 0.80645 | 0 | 1.5972 | 0.625 | 0 | 2.5538 | 0.67204 | 0
4 | 2 | 4 | 8.6022 | 3.8978 | 2.0161 | 11.4583 | 7.5149 | 2.6375 | 13.0376 | 7.5941 | 4.8387 | 18.75 | 12.8472 | 9.7222 | 19.4892 | 15.5914 | 9.6102 | 25 | 15.8333 | 11.4583 | 21.2366 | 15.3898 | 9.7446 | 20.2957 | 14.4489 | 10.0134 | 14.7917 | 10.2083 | 4.9306 | 10.2151 | 6.25 | 3.6962 | 9.5833 | 5.1389 | 2.2222 | 9.207 | 6.6532 | 1.6801
4 | 2 | 6 | 24.3952 | 12.3656 | 7.1237 | 27.0089 | 18.2471 | 8.7798 | 29.2339 | 22.3118 | 13.8441 | 38.6806 | 33.2639 | 25.4167 | 42.0027 | 38.172 | 28.3602 | 49.7917 | 39.9306 | 29.1667 | 45.6317 | 38.5081 | 30.4435 | 41.8683 | 34.9462 | 27.8898 | 36.6667 | 29.0972 | 20.0694 | 24.5296 | 18.0108 | 11.7608 | 20.625 | 15.1389 | 9.6528 | 22.379 | 14.2473 | 6.7876
4 | 2 | 8 | 38.1048 | 24.7312 | 14.3145 | 46.0642 | 37.4282 | 17.8571 | 49.3952 | 38.9785 | 27.621 | 65.7639 | 55.6944 | 46.25 | 66.9355 | 62.4328 | 52.6882 | 71.5278 | 65.9722 | 54.4444 | 73.8575 | 64.2473 | 53.1586 | 67.2043 | 61.2903 | 51.3441 | 58.6111 | 50.2778 | 36.7361 | 42.5403 | 34.7446 | 23.5887 | 39.9306 | 27.7083 | 19.5139 | 39.3817 | 27.2177 | 16.2634
4 | 2 | 9 | 43.6828 | 31.9892 | 21.1022 | 54.7619 | 45.9693 | 25 | 59.6774 | 47.1102 | 35.6183 | 73.6806 | 64.5139 | 56.1111 | 78.8306 | 71.6398 | 64.2473 | 82.0139 | 77.3611 | 67.0833 | 84.543 | 75.4704 | 66.9355 | 77.621 | 72.2446 | 63.3065 | 68.8889 | 58.125 | 49.3056 | 49.1935 | 41.3978 | 31.1156 | 45.8333 | 34.8611 | 24.375 | 46.7742 | 33.5349 | 18.8844
4 | 2 | 10 | 51.3441 | 38.1048 | 24.8656 | 61.9048 | 52.2321 | 33.0357 | 70.0941 | 55.1075 | 43.6156 | 83.4722 | 72.0833 | 66.4583 | 85.4839 | 78.8978 | 72.1102 | 88.6111 | 84.4444 | 76.5972 | 92.2715 | 85.5511 | 77.7554 | 84.543 | 79.1667 | 72.043 | 76.5278 | 65.4167 | 56.9444 | 57.6613 | 48.9919 | 37.5672 | 54.0972 | 43.3333 | 30.9722 | 53.629 | 40.0538 | 23.7903
4 | 2 | 11 | 56.3172 | 42.0027 | 30.4435 | 69.5685 | 56.5887 | 35.7887 | 76.8817 | 62.2984 | 50.672 | 87.3611 | 78.6806 | 71.1111 | 90.3898 | 84.543 | 80.4435 | 92.0139 | 88.4028 | 83.4028 | 95.4301 | 90.793 | 82.5941 | 88.6425 | 84.2742 | 79.0995 | 82.5694 | 71.7361 | 63.75 | 64.1129 | 54.1667 | 45.6989 | 60.6944 | 48.9583 | 36.8056 | 57.0565 | 42.9435 | 28.6962
4 | 2 | 12 | 59.4758 | 43.8844 | 33.8038 | 72.247 | 59.747 | 39.1036 | 79.9059 | 65.9274 | 53.0242 | 91.0417 | 82.5 | 74.0278 | 92.6075 | 87.836 | 83.5349 | 93.1944 | 89.7917 | 85.5556 | 96.9758 | 92.6747 | 85.2823 | 90.9274 | 87.2984 | 80.7124 | 83.4722 | 74.4444 | 66.4583 | 68.1452 | 57.3925 | 48.9919 | 63.6111 | 51.1806 | 38.6111 | 59.7446 | 46.0349 | 30.914
4 | 2 | 15 | 62.7688 | 44.8925 | 36.4919 | 73.3631 | 60.9606 | 39.6937 | 81.1156 | 66.6667 | 54.0323 | 91.7361 | 83.5417 | 75.7639 | 93.3468 | 89.8522 | 85.4167 | 93.8889 | 90.2083 | 86.4583 | 97.1774 | 93.3468 | 86.4919 | 92.4731 | 87.9704 | 81.7876 | 84.5833 | 75.625 | 68.0556 | 71.5726 | 60.1478 | 52.5538 | 66.1111 | 53.3333 | 39.8611 | 60.5511 | 49.0591 | 31.7876
4 | 2 | 20 | 62.7688 | 44.8925 | 36.4919 | 73.3631 | 60.9606 | 39.6937 | 81.1156 | 66.6667 | 54.0323 | 91.7361 | 83.5417 | 75.7639 | 93.3468 | 89.9866 | 85.4167 | 93.8889 | 90.2083 | 86.5278 | 97.1774 | 93.3468 | 86.5591 | 92.4731 | 87.9704 | 81.7876 | 84.6528 | 75.625 | 68.0556 | 71.5726 | 60.1478 | 52.5538 | 66.1111 | 53.3333 | 39.9306 | 60.5511 | 49.0591 | 31.7876
4 | 2 | 25 | 62.7688 | 44.8925 | 36.4919 | 73.3631 | 60.9606 | 39.6937 | 81.1156 | 66.6667 | 54.0323 | 91.7361 | 83.5417 | 75.7639 | 93.3468 | 89.9866 | 85.4167 | 93.8889 | 90.2083 | 86.5278 | 97.1774 | 93.3468 | 86.5591 | 92.4731 | 87.9704 | 81.7876 | 84.6528 | 75.625 | 68.0556 | 71.5726 | 60.1478 | 52.5538 | 66.1111 | 53.3333 | 39.9306 | 60.5511 | 49.0591 | 31.7876
4 | 2.25 | 2 | 1.7473 | 0.26882 | 0 | 2.0474 | 0.73122 | 0 | 2.8226 | 1.0753 | 0 | 4.0972 | 2.2917 | 0.76389 | 4.5027 | 2.2177 | 0.94086 | 5.9722 | 2.9861 | 1.3889 | 4.4355 | 1.9489 | 0.80645 | 4.7043 | 2.1505 | 1.2769 | 3.4722 | 1.5278 | 0.55556 | 2.2849 | 0.80645 | 0 | 1.5972 | 0.625 | 0 | 2.5538 | 0.67204 | 0
4 | 2.25 | 4 | 8.6022 | 3.8978 | 2.0161 | 11.6944 | 7.5893 | 2.8607 | 13.0376 | 7.5941 | 4.8387 | 18.75 | 12.8472 | 9.7222 | 19.4892 | 15.5914 | 9.6102 | 25 | 15.8333 | 11.4583 | 21.2366 | 15.3898 | 9.7446 | 20.2957 | 14.4489 | 10.0134 | 14.7917 | 10.2778 | 5.2778 | 10.2151 | 6.5188 | 3.6962 | 9.6528 | 5.1389 | 2.2222 | 9.2742 | 6.6532 | 1.8817
4 | 2.25 | 6 | 24.664 | 12.5757 | 7.3925 | 27.3065 | 18.5781 | 9.4494 | 29.7043 | 22.3118 | 13.8441 | 38.6806 | 33.6806 | 26.1111 | 42.0027 | 38.172 | 28.3602 | 49.7917 | 39.9306 | 29.1667 | 45.6317 | 38.5081 | 30.4435 | 41.8683 | 34.9462 | 27.8898 | 36.9444 | 29.1667 | 20.0694 | 24.664 | 18.4812 | 11.9624 | 20.9028 | 15.8333 | 10.1389 | 23.1183 | 14.7849 | 7.1909
4 | 2.25 | 8 | 38.5753 | 26.0753 | 15.121 | 46.8057 | 38.0029 | 18.5268 | 51.0081 | 40.457 | 28.8978 | 66.4583 | 56.0417 | 48.2639 | 67.0699 | 62.5672 | 52.8226 | 71.9444 | 65.9722 | 54.5139 | 73.8575 | 64.2473 | 53.1586 | 67.3387 | 61.2903 | 51.4113 | 58.8889 | 50.9722 | 37.3611 | 43.2796 | 35.2823 | 24.3952 | 40.1389 | 28.8889 | 20.2778 | 41.2634 | 28.4946 | 17.0699
4 | 2.25 | 9 | 45.1613 | 33.871 | 23.4543 | 56.3988 | 48.2476 | 25.5208 | 61.0887 | 48.3871 | 37.4328 | 73.9583 | 65.4167 | 59.0278 | 78.8978 | 72.1102 | 64.6505 | 82.2222 | 78.125 | 67.9167 | 85.4167 | 75.9409 | 67.0699 | 78.1586 | 72.5134 | 64.1129 | 69.5139 | 59.6528 | 50.2778 | 50.6048 | 43.2124 | 32.9301 | 47.3611 | 36.8056 | 25.5556 | 48.5215 | 36.0215 | 20.2285
4 | 2.25 | 10 | 54.3011 | 40.793 | 28.293 | 63.3185 | 55.6753 | 34.8214 | 73.4543 | 57.4597 | 46.6398 | 84.0278 | 74.2361 | 68.3333 | 86.4247 | 80.6452 | 73.6559 | 89.375 | 85.5556 | 78.75 | 93.414 | 86.3575 | 78.5618 | 84.7446 | 80.1747 | 72.9167 | 78.4722 | 66.6667 | 59.375 | 59.6102 | 51.2769 | 39.5161 | 57.2222 | 45.4167 | 32.0833 | 56.1156 | 43.414 | 25.8065
4 | 2.25 | 11 | 60.8199 | 45.6989 | 34.6774 | 71.0565 | 61.4583 | 39.0625 | 80.1075 | 66.6667 | 54.5699 | 89.0278 | 81.7361 | 75.8333 | 92.4731 | 86.3575 | 82.3925 | 93.0556 | 90.1389 | 85.6944 | 96.1694 | 91.8683 | 83.9382 | 90.121 | 87.0968 | 80.914 | 85 | 73.3333 | 66.3889 | 69.3548 | 57.7285 | 48.8575 | 62.2917 | 53.6806 | 41.1111 | 60.8871 | 49.1263 | 34.0726
4 | 2.25 | 12 | 65.3898 | 48.3871 | 38.6425 | 76.1161 | 65.997 | 44.0476 | 84.0054 | 71.4382 | 59.0054 | 92.5 | 85.5556 | 79.5833 | 94.8925 | 90.6586 | 87.4328 | 94.7222 | 92.0833 | 88.6111 | 97.9167 | 94.086 | 87.164 | 93.6828 | 90.7258 | 84.1398 | 87.1528 | 79.7222 | 72.1528 | 74.7984 | 62.164 | 54.3683 | 69.375 | 58.5417 | 45.4861 | 64.1801 | 53.293 | 38.1048
4 | 2.25 | 15 | 71.6398 | 52.6882 | 42.7419 | 78.3482 | 68.006 | 48.3682 | 86.3575 | 73.5215 | 63.3737 | 94.9306 | 87.9861 | 83.4028 | 96.9086 | 93.5484 | 90.3898 | 95.8333 | 93.125 | 90.625 | 98.7231 | 96.1022 | 89.1129 | 95.9677 | 92.0699 | 86.4919 | 90.1389 | 82.4306 | 74.7222 | 78.0242 | 66.129 | 61.1559 | 73.4722 | 63.1944 | 50 | 66.9355 | 57.5269 | 41.2634
4 | 2.25 | 20 | 71.6398 | 52.6882 | 42.8763 | 78.4226 | 68.006 | 48.4426 | 86.3575 | 73.7903 | 63.3737 | 94.9306 | 87.9861 | 83.4028 | 96.9086 | 93.5484 | 90.5242 | 95.9028 | 93.125 | 90.625 | 98.7231 | 96.1022 | 89.1801 | 95.9677 | 92.0699 | 86.4919 | 90.4167 | 82.4306 | 74.8611 | 78.1586 | 66.3978 | 61.1559 | 73.5417 | 63.4028 | 50.2778 | 67.0027 | 57.7285 | 41.3978
4 | 2.25 | 25 | 71.6398 | 52.6882 | 42.8763 | 78.4226 | 68.006 | 48.4426 | 86.3575 | 73.7903 | 63.3737 | 94.9306 | 87.9861 | 83.4028 | 96.9086 | 93.5484 | 90.5242 | 95.9028 | 93.125 | 90.625 | 98.7231 | 96.1022 | 89.1801 | 95.9677 | 92.0699 | 86.4919 | 90.4167 | 82.4306 | 74.8611 | 78.1586 | 66.3978 | 61.1559 | 73.5417 | 63.4028 | 50.2778 | 67.0027 | 57.7285 | 41.3978
4 | 2.5 | 2 | 1.7473 | 0.53763 | 0 | 2.0474 | 0.73122 | 0 | 2.8226 | 1.0753 | 0 | 4.0972 | 2.2917 | 0.76389 | 4.5027 | 2.2177 | 0.94086 | 5.9722 | 2.9861 | 1.3889 | 4.4355 | 1.9489 | 0.80645 | 4.7043 | 2.1505 | 1.2769 | 3.4722 | 1.5278 | 0.55556 | 2.2849 | 0.80645 | 0 | 1.5972 | 0.625 | 0 | 2.5538 | 0.67204 | 0
4 | 2.5 | 4 | 8.6022 | 4.0323 | 2.0161 | 11.6944 | 7.8125 | 3.3482 | 13.0376 | 7.5941 | 4.8387 | 18.75 | 12.8472 | 9.7222 | 19.4892 | 15.5914 | 9.6102 | 25 | 15.8333 | 11.4583 | 21.2366 | 15.3898 | 9.7446 | 20.2957 | 14.4489 | 10.0134 | 14.7917 | 10.2778 | 5.3472 | 10.2151 | 6.586 | 3.6962 | 9.6528 | 5.1389 | 2.2222 | 9.4086 | 6.6532 | 2.2849
4 | 2.5 | 6 | 24.664 | 13.4499 | 7.3925 | 27.3065 | 19.1631 | 9.8958 | 29.7043 | 22.3118 | 13.8441 | 38.6806 | 34.1667 | 26.1111 | 42.0027 | 38.172 | 28.3602 | 49.7917 | 39.9306 | 29.1667 | 45.6317 | 38.5081 | 30.4435 | 41.8683 | 34.9462 | 27.8898 | 36.9444 | 29.1667 | 20.0694 | 24.664 | 18.6828 | 11.9624 | 20.9028 | 15.9722 | 10.4167 | 23.5215 | 15.121 | 7.2581
4 | 2.5 | 8 | 38.5753 | 26.2097 | 15.5914 | 47.3137 | 38.7213 | 18.6756 | 51.3441 | 40.457 | 29.9059 | 66.4583 | 56.4583 | 48.6111 | 67.4731 | 62.5672 | 52.8226 | 72.0139 | 65.9722 | 54.5139 | 73.8575 | 64.2473 | 53.1586 | 67.4731 | 61.2903 | 51.4113 | 58.8889 | 51.3194 | 37.9167 | 43.8172 | 35.4167 | 25.2688 | 40.5556 | 29.0972 | 20.8333 | 42.0027 | 28.6962 | 17.6747
4 | 2.5 | 9 | 46.1022 | 34.9026 | 24.5296 | 57.4559 | 49.3329 | 26.6369 | 61.4247 | 49.1263 | 38.5753 | 74.1667 | 66.3889 | 59.9306 | 79.2339 | 72.5806 | 64.7177 | 82.3611 | 78.1944 | 68.1944 | 85.8199 | 75.9409 | 67.2043 | 78.2258 | 72.6478 | 64.1129 | 69.6528 | 59.7222 | 50.4861 | 51.3441 | 44.2204 | 34.0054 | 48.5417 | 37.5694 | 26.8056 | 49.5296 | 37.0968 | 22.1774
4 | 2.5 | 10 | 55.6452 | 42.3387 | 30.914 | 64.4781 | 56.7067 | 35.2679 | 74.1935 | 58.5349 | 48.1855 | 84.2361 | 75.8333 | 69.375 | 86.4247 | 81.25 | 74.1263 | 90.0694 | 85.9028 | 78.8889 | 93.6828 | 86.3575 | 78.9651 | 85.2151 | 80.3091 | 73.3871 | 78.8194 | 67.2222 | 60.2778 | 60.8871 | 51.9489 | 40.5914 | 58.75 | 47.1528 | 34.1667 | 57.6613 | 44.6237 | 27.8226
4 | 2.5 | 11 | 62.9704 | 49.1263 | 36.7608 | 72.655 | 64.4653 | 41.8155 | 81.6532 | 68.1452 | 56.25 | 89.3056 | 83.1944 | 77.0139 | 92.9435 | 87.0968 | 82.7285 | 93.6111 | 90.8333 | 86.1806 | 96.8414 | 92.4059 | 85.0134 | 91.129 | 87.9704 | 81.5188 | 85.9722 | 74.8611 | 68.3333 | 70.2957 | 59.6102 | 50.5376 | 64.5139 | 55.4861 | 43.4028 | 62.5 | 51.8145 | 39.2473
4 | 2.5 | 12 | 69.3548 | 54.3683 | 42.0699 | 79.5951 | 69.24 | 48.8095 | 85.7527 | 73.9247 | 62.3656 | 93.125 | 87.7083 | 83.3333 | 95.6989 | 91.8011 | 89.2473 | 95.8333 | 93.2639 | 90 | 99.2608 | 96.1694 | 88.7097 | 96.5054 | 92.0699 | 86.1559 | 89.7222 | 82.5 | 75.2778 | 76.2769 | 64.6505 | 58.1989 | 72.2222 | 63.1944 | 49.2361 | 68.4812 | 57.3253 | 43.6828
4 | 2.5 | 15 | 79.0323 | 63.4409 | 48.3199 | 84.1518 | 73.8839 | 55.0903 | 90.3898 | 77.8898 | 70.0269 | 96.4583 | 91.4583 | 87.9167 | 98.3871 | 96.1022 | 93.2124 | 97.3611 | 95.2083 | 92.9861 | 100 | 98.1183 | 91.7339 | 98.2527 | 93.8172 | 89.5833 | 93.2639 | 88.0556 | 80.2083 | 84.2742 | 73.8575 | 67.2715 | 79.8611 | 70.625 | 56.8056 | 74.8656 | 65.3898 | 49.328
4 | 2.5 | 20 | 79.3683 | 63.5753 | 48.5887 | 84.1518 | 74.1071 | 55.2366 | 90.457 | 78.3602 | 70.0941 | 96.6667 | 91.5972 | 88.0556 | 98.3871 | 96.1022 | 93.6156 | 97.3611 | 95.2083 | 93.125 | 100 | 98.1855 | 91.9355 | 98.2527 | 93.8844 | 89.5833 | 93.2639 | 88.0556 | 80.4167 | 84.8118 | 74.0591 | 67.6747 | 80.2083 | 71.3194 | 57.3611 | 75.2688 | 65.793 | 49.7312
4 | 2.5 | 25 | 79.3683 | 63.5753 | 48.5887 | 84.1518 | 74.1071 | 55.2366 | 90.457 | 78.3602 | 70.0941 | 96.6667 | 91.5972 | 88.0556 | 98.3871 | 96.1022 | 93.6156 | 97.3611 | 95.2083 | 93.125 | 100 | 98.1855 | 91.9355 | 98.2527 | 93.8844 | 89.5833 | 93.2639 | 88.0556 | 80.4167 | 84.8118 | 74.0591 | 67.6747 | 80.2083 | 71.3194 | 57.3611 | 75.2688 | 65.793 | 49.7312
4 | 2.75 | 2 | 1.7473 | 0.53763 | 0 | 2.0474 | 0.81845 | 0 | 2.8226 | 1.0753 | 0 | 4.0972 | 2.2917 | 0.76389 | 4.5027 | 2.2177 | 0.94086 | 5.9722 | 2.9861 | 1.3889 | 4.4355 | 1.9489 | 0.80645 | 4.7043 | 2.1505 | 1.2769 | 3.4722 | 1.5278 | 0.55556 | 2.2849 | 0.80645 | 0 | 1.5972 | 0.625 | 0 | 2.5538 | 0.67204 | 0
4 | 2.75 | 4 | 8.6022 | 4.0323 | 2.0161 | 11.992 | 8.1101 | 3.3482 | 13.0376 | 7.5941 | 4.8387 | 18.75 | 12.8472 | 9.7222 | 19.4892 | 15.5914 | 9.6102 | 25 | 15.8333 | 11.4583 | 21.2366 | 15.3898 | 9.7446 | 20.2957 | 14.4489 | 10.0134 | 14.7917 | 10.2778 | 5.3472 | 10.2151 | 6.586 | 3.6962 | 9.6528 | 5.1389 | 2.2222 | 9.4086 | 6.6532 | 2.2849
4 | 2.75 | 6 | 24.664 | 13.6425 | 7.3925 | 27.3065 | 19.1631 | 10.2679 | 29.7043 | 22.3118 | 13.8441 | 38.6806 | 34.1667 | 26.1111 | 42.0027 | 38.172 | 28.3602 | 49.7917 | 39.9306 | 29.1667 | 45.6317 | 38.5081 | 30.4435 | 41.8683 | 34.9462 | 27.8898 | 36.9444 | 29.1667 | 20.0694 | 24.664 | 18.8172 | 11.9624 | 20.9028 | 16.1806 | 10.4167 | 23.5215 | 15.121 | 8.0645
4 | 2.75 | 8 | 38.5753 | 26.4785 | 15.9946 | 47.3881 | 39.0317 | 19.2708 | 51.3441 | 40.7258 | 30.1075 | 66.4583 | 56.5278 | 48.75 | 67.5403 | 62.5672 | 52.8226 | 72.0139 | 65.9722 | 54.5139 | 73.8575 | 64.2473 | 53.1586 | 67.4731 | 61.2903 | 51.4113 | 58.8889 | 51.4583 | 38.3333 | 43.8172 | 35.4167 | 25.4032 | 40.9028 | 29.5139 | 21.0417 | 42.2043 | 28.6962 | 18.75
4 | 2.75 | 9 | 46.371 | 35.0806 | 25.0672 | 57.7535 | 49.8384 | 27.753 | 61.7608 | 49.1263 | 39.3145 | 74.1667 | 66.9444 | 60.6944 | 79.2339 | 72.5806 | 64.7177 | 82.3611 | 78.1944 | 68.1944 | 85.8199 | 75.9409 | 67.2043 | 78.2258 | 72.6478 | 64.1129 | 69.6528 | 60.1389 | 50.6944 | 51.8145 | 44.6237 | 34.543 | 49.0972 | 37.8472 | 27.2917 | 50.2016 | 37.7688 | 23.9919
4 | 2.75 | 10 | 56.1156 | 42.9435 | 31.922 | 65.7738 | 57.6688 | 36.0863 | 74.4624 | 58.7366 | 48.6559 | 84.7917 | 76.5278 | 69.7222 | 86.8952 | 81.6532 | 74.1935 | 90.2083 | 86.0417 | 78.8889 | 93.6828 | 86.3575 | 78.9651 | 85.2823 | 80.4435 | 73.4543 | 78.8194 | 67.2222 | 62.3611 | 61.2903 | 53.5618 | 40.9946 | 60.3472 | 49.0972 | 35.3472 | 58.4005 | 45.2285 | 30.578
4 | 2.75 | 11 | 64.0457 | 52.0161 | 38.7097 | 73.7454 | 65.4993 | 45.9821 | 82.3253 | 68.5484 | 56.7876 | 90.1389 | 84.0972 | 77.9167 | 93.1452 | 87.4328 | 82.7957 | 94.0278 | 91.1111 | 86.3889 | 96.9758 | 92.5403 | 85.8199 | 91.5995 | 88.4409 | 82.2581 | 86.1111 | 76.25 | 70 | 71.2366 | 60.6183 | 51.0081 | 68.9583 | 57.5694 | 45.0694 | 64.0457 | 52.2849 | 41.7339
4 | 2.75 | 12 | 72.5806 | 57.1237 | 45.3629 | 81.5476 | 70.1637 | 55.0595 | 87.3656 | 76.1425 | 65.7258 | 93.125 | 90.2778 | 84.5833 | 96.1694 | 92.3387 | 89.8522 | 97.0139 | 94.375 | 91.1806 | 99.2608 | 96.9758 | 90.0538 | 97.2446 | 92.5403 | 87.164 | 90.8333 | 83.6806 | 77.8472 | 77.4866 | 65.5914 | 59.879 | 74.5833 | 64.7917 | 51.7361 | 70.9005 | 59.9462 | 46.5726
4 | 2.75 | 15 | 82.3925 | 68.2124 | 53.8978 | 86.2556 | 79.0179 | 63.1491 | 93.6828 | 82.7285 | 75.672 | 98.125 | 94.375 | 91.3889 | 99.2608 | 97.7823 | 95.3629 | 98.75 | 96.8056 | 94.7222 | 100 | 98.9919 | 94.4892 | 99.328 | 96.2366 | 92.1371 | 95 | 90.625 | 83.6111 | 89.4489 | 78.4274 | 72.1774 | 84.2361 | 75.9028 | 62.4306 | 78.7634 | 71.9758 | 57.1237
4 | 2.75 | 20 | 82.8629 | 68.2796 | 54.6371 | 86.4737 | 79.2385 | 63.4416 | 94.1532 | 83.5349 | 75.9409 | 98.3333 | 94.6528 | 91.6667 | 99.3952 | 97.9167 | 95.5645 | 98.75 | 96.875 | 94.8611 | 100 | 98.9919 | 94.5565 | 99.328 | 96.5054 | 92.3387 | 95.5556 | 90.9722 | 84.0278 | 90.6586 | 79.5027 | 73.1183 | 84.5833 | 77.3611 | 63.9583 | 80.0403 | 72.4462 | 58.0645
4 | 2.75 | 25 | 82.8629 | 68.2796 | 54.6371 | 86.4737 | 79.2385 | 63.4416 | 94.1532 | 83.5349 | 75.9409 | 98.3333 | 94.6528 | 91.6667 | 99.3952 | 97.9167 | 95.5645 | 98.75 | 96.875 | 94.8611 | 100 | 98.9919 | 94.5565 | 99.328 | 96.5054 | 92.3387 | 95.5556 | 90.9722 | 84.0278 | 90.6586 | 79.5027 | 73.1183 | 84.5833 | 77.3611 | 63.9583 | 80.0403 | 72.4462 | 58.0645
4 | 3 | 2 | 1.7473 | 0.53763 | 0 | 2.0474 | 0.81845 | 0 | 2.8226 | 1.0753 | 0 | 4.0972 | 2.2917 | 0.76389 | 4.5027 | 2.2177 | 0.94086 | 5.9722 | 2.9861 | 1.3889 | 4.4355 | 1.9489 | 0.80645 | 4.7043 | 2.1505 | 1.2769 | 3.4722 | 1.5278 | 0.55556 | 2.2849 | 0.80645 | 0 | 1.5972 | 0.625 | 0 | 2.5538 | 0.67204 | 0
4 | 3 | 4 | 8.6022 | 4.0323 | 2.1505 | 11.992 | 8.1101 | 3.3482 | 13.0376 | 7.5941 | 4.8387 | 18.75 | 12.8472 | 9.7222 | 19.4892 | 15.5914 | 9.6102 | 25 | 15.8333 | 11.4583 | 21.2366 | 15.3898 | 9.7446 | 20.2957 | 14.4489 | 10.0134 | 14.7917 | 10.2778 | 5.3472 | 10.2151 | 6.586 | 3.6962 | 9.6528 | 5.1389 | 2.2222 | 9.6774 | 6.6532 | 2.2849
4 | 3 | 6 | 24.664 | 13.6425 | 7.3925 | 27.3065 | 19.1631 | 10.2679 | 29.7043 | 22.3118 | 13.8441 | 38.6806 | 34.1667 | 26.1111 | 42.0027 | 38.172 | 28.3602 | 49.7917 | 39.9306 | 29.1667 | 45.6317 | 38.5081 | 30.4435 | 41.8683 | 34.9462 | 27.8898 | 36.9444 | 29.1667 | 20.0694 | 24.664 | 18.8172 | 11.9624 | 20.9028 | 16.1806 | 10.4167 | 23.5215 | 15.121 | 8.0645
4 | 3 | 8 | 38.5753 | 26.5457 | 16.1962 | 47.3881 | 39.5525 | 19.3452 | 51.3441 | 40.7258 | 30.5108 | 66.4583 | 56.5278 | 48.75 | 67.5403 | 62.6344 | 52.8226 | 72.0139 | 65.9722 | 54.5139 | 73.8575 | 64.2473 | 53.1586 | 67.4731 | 61.2903 | 51.4113 | 58.8889 | 51.4583 | 38.4722 | 43.8172 | 35.4167 | 26.0081 | 40.9722 | 29.7917 | 21.3889 | 42.6075 | 28.6962 | 19.086
4 | 3 | 9 | 46.371 | 35.2151 | 25.2688 | 57.7535 | 50.2027 | 27.8274 | 61.7608 | 49.1263 | 39.4489 | 74.1667 | 67.0833 | 60.8333 | 79.2339 | 72.5806 | 64.7177 | 82.3611 | 78.1944 | 68.1944 | 85.8199 | 75.9409 | 67.2043 | 78.2258 | 72.6478 | 64.1129 | 69.6528 | 60.1389 | 50.8333 | 51.9489 | 44.9597 | 34.879 | 49.3056 | 38.125 | 27.7778 | 50.8737 | 37.7688 | 25
4 | 3 | 10 | 56.3172 | 43.8172 | 32.5269 | 66.369 | 57.8151 | 37.128 | 74.5296 | 58.8038 | 49.4624 | 84.7917 | 76.5278 | 70 | 87.164 | 81.6532 | 74.1935 | 90.2083 | 86.0417 | 78.8889 | 93.6828 | 86.3575 | 78.9651 | 85.8871 | 80.4435 | 73.4543 | 78.8194 | 67.2222 | 62.7083 | 61.4247 | 53.9651 | 41.6667 | 60.7639 | 50.6944 | 35.9028 | 59.8118 | 45.2957 | 31.8548
4 | 3 | 11 | 64.7849 | 52.4194 | 39.7177 | 74.5561 | 66.369 | 47.6935 | 82.8629 | 68.6828 | 57.1909 | 90.5556 | 84.5139 | 78.0556 | 93.5484 | 87.9032 | 82.9301 | 94.2361 | 91.25 | 86.5278 | 96.9758 | 92.5403 | 86.2231 | 91.6667 | 88.9113 | 82.3925 | 86.25 | 76.4583 | 70.2778 | 71.8414 | 61.2903 | 52.2849 | 70.4167 | 59.6528 | 46.7361 | 66.1962 | 52.8226 | 42.6075
4 | 3 | 12 | 74.0591 | 58.6694 | 46.5726 | 82.1429 | 70.9821 | 57.8125 | 87.9032 | 76.4785 | 66.9355 | 93.8194 | 91.1806 | 85.1389 | 96.1694 | 92.8763 | 90.3898 | 97.2917 | 94.8611 | 91.4583 | 99.2608 | 97.043 | 90.7258 | 97.2446 | 92.8763 | 87.5 | 91.5972 | 84.2361 | 79.1667 | 78.2258 | 66.8011 | 62.2312 | 75.9722 | 67.2917 | 53.1944 | 73.1183 | 61.7608 | 48.6559
4 | 3 | 15 | 86.2903 | 72.7151 | 58.3333 | 89.2857 | 83.4077 | 69.063 | 94.9597 | 86.2903 | 78.4946 | 98.4028 | 96.0417 | 92.7778 | 100 | 98.5887 | 96.9086 | 99.7917 | 97.8472 | 95.6944 | 100 | 99.9328 | 96.3038 | 99.664 | 98.0511 | 93.5484 | 96.6667 | 92.0139 | 85.6944 | 92.1371 | 81.8548 | 77.2177 | 87.7778 | 79.7222 | 67.9167 | 82.3253 | 76.1425 | 62.5
4 | 3 | 20 | 87.0296 | 73.9247 | 59.7446 | 89.881 | 84.5084 | 69.9405 | 96.1022 | 87.5672 | 79.4355 | 99.0278 | 96.1806 | 93.6806 | 100 | 99.1935 | 97.1774 | 99.8611 | 98.0556 | 95.7639 | 100 | 100 | 96.4382 | 99.7984 | 98.2527 | 93.8844 | 96.9444 | 92.6389 | 86.8056 | 93.2796 | 84.3414 | 78.7634 | 89.1667 | 82.2222 | 69.6528 | 84.2742 | 77.4866 | 64.3817
4 | 3 | 25 | 87.0296 | 73.9247 | 59.7446 | 89.881 | 84.5084 | 69.9405 | 96.1022 | 87.5672 | 79.4355 | 99.0278 | 96.1806 | 93.6806 | 100 | 99.1935 | 97.1774 | 99.8611 | 98.0556 | 95.7639 | 100 | 100 | 96.4382 | 99.7984 | 98.2527 | 93.8844 | 96.9444 | 92.6389 | 86.8056 | 93.2796 | 84.3414 | 78.7634 | 89.1667 | 82.2222 | 69.6528 | 84.2742 | 77.4866 | 64.3817
4 | 3.25 | 2 | 1.7473 | 0.53763 | 0 | 2.0474 | 0.81845 | 0 | 2.8226 | 1.0753 | 0 | 4.0972 | 2.2917 | 0.76389 | 4.5027 | 2.2177 | 0.94086 | 5.9722 | 2.9861 | 1.3889 | 4.4355 | 1.9489 | 0.80645 | 4.7043 | 2.1505 | 1.2769 | 3.4722 | 1.5278 | 0.55556 | 2.2849 | 0.80645 | 0 | 1.5972 | 0.625 | 0 | 2.5538 | 0.67204 | 0
4 | 3.25 | 4 | 8.6022 | 4.0323 | 2.1505 | 11.992 | 8.1101 | 3.3482 | 13.0376 | 7.5941 | 4.8387 | 18.75 | 12.8472 | 9.7222 | 19.4892 | 15.5914 | 9.6102 | 25 | 15.8333 | 11.4583 | 21.2366 | 15.3898 | 9.7446 | 20.2957 | 14.4489 | 10.0134 | 14.7917 | 10.2778 | 5.3472 | 10.2151 | 6.586 | 3.6962 | 9.6528 | 5.1389 | 2.2222 | 9.6774 | 6.6532 | 2.2849
4 | 3.25 | 6 | 24.664 | 13.6425 | 7.3925 | 27.3527 | 19.1631 | 10.2679 | 29.7043 | 22.3118 | 14.2473 | 38.6806 | 34.1667 | 26.1111 | 42.0027 | 38.172 | 28.3602 | 49.7917 | 39.9306 | 29.1667 | 45.6317 | 38.5081 | 30.4435 | 41.8683 | 34.9462 | 27.8898 | 36.9444 | 29.1667 | 20.0694 | 24.664 | 18.8172 | 11.9624 | 20.9028 | 16.1806 | 10.4167 | 23.5215 | 15.121 | 8.0645
4 | 3.25 | 8 | 38.5753 | 26.5457 | 16.3306 | 47.3881 | 39.7681 | 19.4196 | 51.3441 | 40.7258 | 30.6452 | 66.4583 | 56.5278 | 48.75 | 67.5403 | 62.7016 | 52.8226 | 72.0139 | 65.9722 | 54.5139 | 73.8575 | 64.2473 | 53.1586 | 67.4731 | 61.2903 | 51.4113 | 58.8889 | 51.4583 | 38.4722 | 43.8172 | 35.6855 | 26.0081 | 40.9722 | 29.7917 | 21.4583 | 42.7419 | 29.0323 | 19.2876
4 | 3.25 | 9 | 46.371 | 35.2151 | 25.336 | 57.7535 | 50.2155 | 28.1994 | 61.7608 | 49.1935 | 39.7177 | 74.1667 | 67.0833 | 60.9028 | 79.2339 | 72.7151 | 64.7177 | 82.3611 | 78.1944 | 68.1944 | 85.8199 | 75.9409 | 67.2043 | 78.2258 | 72.6478 | 64.1129 | 69.6528 | 60.1389 | 50.9722 | 52.2177 | 45.2285 | 34.9462 | 49.375 | 38.125 | 27.9167 | 51.2769 | 37.7688 | 25.4704
4 | 3.25 | 10 | 56.6532 | 44.1532 | 32.8629 | 66.5307 | 57.8895 | 37.6488 | 74.5296 | 58.8038 | 50.0672 | 84.7917 | 76.5278 | 70.0694 | 87.164 | 81.6532 | 74.1935 | 90.2083 | 86.0417 | 78.8889 | 93.6828 | 86.3575 | 78.9651 | 86.0887 | 80.4435 | 73.4543 | 78.8194 | 67.2222 | 62.8472 | 61.4247 | 54.1667 | 41.8011 | 60.9722 | 51.0417 | 35.9722 | 60.3495 | 45.6317 | 32.3925
4 | 3.25 | 11 | 65.8602 | 52.4866 | 41.0618 | 75.2181 | 66.523 | 48.5863 | 82.9973 | 68.9516 | 58.1317 | 90.9028 | 84.7222 | 78.5417 | 93.5484 | 87.9704 | 82.9301 | 94.3056 | 91.5278 | 86.5278 | 96.9758 | 92.5403 | 86.2903 | 91.6667 | 88.9113 | 82.6613 | 86.3889 | 76.5972 | 70.7639 | 72.2446 | 61.6935 | 53.8306 | 71.1111 | 60.6944 | 47.3611 | 66.8011 | 53.3602 | 43.078
4 | 3.25 | 12 | 75.1344 | 59.3414 | 48.4543 | 83.1845 | 71.2798 | 58.7798 | 88.8441 | 76.6801 | 67.4731 | 94.0972 | 91.7361 | 85.625 | 96.1694 | 93.078 | 90.5242 | 97.6389 | 94.8611 | 91.7361 | 99.2608 | 97.043 | 90.8602 | 97.2446 | 93.414 | 87.7016 | 91.875 | 84.5833 | 79.375 | 78.4946 | 67.8091 | 63.0376 | 76.3194 | 69.1667 | 54.0278 | 73.9247 | 62.0968 | 50.2688
4 | 3.25 | 15 | 88.8441 | 75.336 | 65.0538 | 91.5179 | 86.1607 | 72.46 | 95.8333 | 88.6425 | 81.3172 | 99.1667 | 97.1528 | 94.0278 | 100 | 99.0591 | 97.9167 | 100 | 98.8889 | 96.25 | 100 | 100 | 96.8414 | 100 | 98.9919 | 95.0941 | 96.875 | 93.8889 | 89.375 | 93.8172 | 85.0806 | 80.578 | 90.1389 | 83.4722 | 71.8056 | 84.4086 | 80.1075 | 67.0699
4 | 3.25 | 20 | 90.7258 | 79.0323 | 67.3387 | 92.3363 | 88.1696 | 76.2803 | 97.5806 | 91.3978 | 82.8629 | 99.7917 | 97.4306 | 95.0694 | 100 | 99.9328 | 98.0511 | 100 | 99.1667 | 96.3889 | 100 | 100 | 97.1774 | 100 | 99.328 | 95.6317 | 97.8472 | 94.7917 | 90.7639 | 96.1694 | 87.164 | 83.8038 | 92.3611 | 86.5278 | 75.625 | 87.6344 | 82.5941 | 69.8253
4 | 3.25 | 25 | 90.7258 | 79.0323 | 67.3387 | 92.3363 | 88.1696 | 76.3547 | 97.5806 | 91.3978 | 82.8629 | 99.7917 | 97.4306 | 95.0694 | 100 | 99.9328 | 98.0511 | 100 | 99.1667 | 96.3889 | 100 | 100 | 97.1774 | 100 | 99.328 | 95.6317 | 97.9167 | 94.7917 | 90.8333 | 96.1694 | 87.164 | 83.8038 | 92.3611 | 86.5278 | 75.625 | 87.6344 | 82.5941 | 69.8253
4 | 3.5 | 2 | 1.7473 | 0.53763 | 0 | 2.0474 | 0.81845 | 0 | 2.8226 | 1.0753 | 0 | 4.0972 | 2.2917 | 0.76389 | 4.5027 | 2.2177 | 0.94086 | 5.9722 | 2.9861 | 1.3889 | 4.4355 | 1.9489 | 0.80645 | 4.7043 | 2.1505 | 1.2769 | 3.4722 | 1.5278 | 0.55556 | 2.2849 | 0.80645 | 0 | 1.5972 | 0.625 | 0 | 2.5538 | 0.67204 | 0
4 | 3.5 | 4 | 8.6022 | 4.0323 | 2.1505 | 11.992 | 8.1101 | 3.3482 | 13.0376 | 7.5941 | 4.8387 | 18.75 | 12.8472 | 9.7222 | 19.4892 | 15.5914 | 9.6102 | 25 | 15.8333 | 11.4583 | 21.2366 | 15.3898 | 9.7446 | 20.2957 | 14.4489 | 10.0134 | 14.7917 | 10.2778 | 5.3472 | 10.2151 | 6.586 | 3.6962 | 9.6528 | 5.1389 | 2.2222 | 9.6774 | 6.6532 | 2.2849
4 | 3.5 | 6 | 24.664 | 13.6425 | 7.3925 | 27.4246 | 19.1631 | 10.2679 | 29.7043 | 22.3118 | 14.2473 | 38.6806 | 34.1667 | 26.1111 | 42.0027 | 38.172 | 28.3602 | 49.7917 | 39.9306 | 29.1667 | 45.6317 | 38.5081 | 30.4435 | 41.8683 | 34.9462 | 27.8898 | 36.9444 | 29.1667 | 20.0694 | 24.664 | 18.8172 | 11.9624 | 20.9028 | 16.1806 | 10.4167 | 23.5215 | 15.121 | 8.0645
4 | 3.5 | 8 | 38.5753 | 26.5457 | 16.5323 | 47.3881 | 39.7681 | 19.494 | 51.3441 | 40.7258 | 30.6452 | 66.4583 | 56.5278 | 48.75 | 67.5403 | 62.7016 | 52.8226 | 72.0139 | 65.9722 | 54.5139 | 73.8575 | 64.2473 | 53.1586 | 67.4731 | 61.2903 | 51.4113 | 58.8889 | 51.4583 | 38.4722 | 43.8172 | 35.6855 | 26.0081 | 40.9722 | 29.7917 | 21.4583 | 42.7419 | 29.0323 | 19.2876
4 | 3.5 | 9 | 46.371 | 35.2151 | 25.336 | 57.7535 | 50.7184 | 28.2738 | 61.7608 | 49.1935 | 39.7849 | 74.1667 | 67.0833 | 60.9028 | 79.2339 | 72.8495 | 64.7177 | 82.3611 | 78.1944 | 68.1944 | 85.8199 | 75.9409 | 67.2043 | 78.2258 | 72.6478 | 64.1129 | 69.6528 | 60.1389 | 50.9722 | 52.2177 | 45.3629 | 34.9462 | 49.375 | 38.125 | 27.9167 | 51.3441 | 37.7688 | 25.672
4 | 3.5 | 10 | 56.6532 | 44.2204 | 33.1989 | 66.6025 | 58.1845 | 37.7232 | 74.5296 | 58.8038 | 50.4032 | 84.7917 | 76.5972 | 70.0694 | 87.164 | 81.6532 | 74.1935 | 90.2083 | 86.0417 | 78.8889 | 93.6828 | 86.3575 | 78.9651 | 86.0887 | 80.4435 | 73.4543 | 78.8194 | 67.2222 | 62.8472 | 61.4247 | 54.1667 | 41.8683 | 61.0417 | 51.25 | 36.0417 | 60.3495 | 45.6317 | 32.5941
4 | 3.5 | 11 | 66.1962 | 52.4866 | 42.2043 | 75.5131 | 66.5948 | 48.8839 | 82.9973 | 69.2876 | 58.6022 | 90.9028 | 84.7917 | 78.75 | 93.5484 | 88.0376 | 83.1989 | 94.375 | 91.5278 | 86.5278 | 96.9758 | 92.5403 | 86.2903 | 92.1371 | 88.9113 | 82.6613 | 86.3889 | 76.5972 | 70.7639 | 72.379 | 61.8952 | 54.0995 | 71.4583 | 61.25 | 47.7778 | 67.1371 | 53.629 | 43.2124
4 | 3.5 | 12 | 75.4704 | 59.9191 | 49.9328 | 83.1845 | 71.29 | 59.6726 | 88.9113 | 77.1505 | 67.7419 | 94.375 | 92.0833 | 85.6944 | 96.2366 | 93.2124 | 90.6586 | 97.7083 | 94.8611 | 91.875 | 99.2608 | 97.043 | 90.9274 | 97.2446 | 93.414 | 87.7688 | 92.0139 | 84.5833 | 79.375 | 78.9651 | 68.75 | 63.2392 | 76.5972 | 69.6528 | 55 | 74.2608 | 63.0376 | 51.0753
4 | 3.5 | 15 | 89.6505 | 77.621 | 69.6237 | 92.2619 | 86.9048 | 76.5907 | 97.9839 | 91.1962 | 82.6613 | 99.5833 | 97.5694 | 94.6528 | 100 | 99.4624 | 98.3199 | 100 | 99.3056 | 97.0139 | 100 | 100 | 97.5806 | 100 | 99.2608 | 95.8333 | 97.9167 | 95.0694 | 90.1389 | 94.6909 | 87.0968 | 82.4597 | 91.25 | 85.4167 | 75.6944 | 86.1559 | 81.7876 | 69.9597
4 | 3.5 | 20 | 92.6075 | 84.3414 | 73.0511 | 94.8661 | 90.643 | 81.6451 | 98.9247 | 94.0188 | 84.8118 | 100 | 99.0972 | 95.6944 | 100 | 100 | 98.9247 | 100 | 99.5139 | 97.2917 | 100 | 100 | 98.0511 | 100 | 100 | 97.4462 | 98.8889 | 96.5972 | 92.5694 | 98.3871 | 91.0618 | 87.5 | 94.5833 | 89.0972 | 80.7639 | 90.121 | 87.0968 | 74.664
4 | 3.5 | 25 | 92.6075 | 84.3414 | 73.0511 | 94.8661 | 90.643 | 81.6451 | 98.9247 | 94.0188 | 84.8118 | 100 | 99.0972 | 95.6944 | 100 | 100 | 98.9247 | 100 | 99.5139 | 97.2917 | 100 | 100 | 98.0511 | 100 | 100 | 97.4462 | 98.8889 | 96.5972 | 92.6389 | 98.3871 | 91.0618 | 87.5 | 94.5833 | 89.1667 | 80.8333 | 90.121 | 87.0968 | 74.664
4 | 3.75 | 2 | 1.7473 | 0.53763 | 0 | 2.0474 | 0.81845 | 0 | 2.8226 | 1.0753 | 0 | 4.0972 | 2.2917 | 0.76389 | 4.5027 | 2.2177 | 0.94086 | 5.9722 | 2.9861 | 1.3889 | 4.4355 | 1.9489 | 0.80645 | 4.7043 | 2.1505 | 1.2769 | 3.4722 | 1.5278 | 0.55556 | 2.2849 | 0.80645 | 0 | 1.5972 | 0.625 | 0 | 2.5538 | 0.67204 | 0
4 | 3.75 | 4 | 8.6022 | 4.0323 | 2.1505 | 11.992 | 8.1101 | 3.3482 | 13.0376 | 7.5941 | 4.8387 | 18.75 | 12.8472 | 9.7222 | 19.4892 | 15.5914 | 9.6102 | 25 | 15.8333 | 11.4583 | 21.2366 | 15.3898 | 9.7446 | 20.2957 | 14.4489 | 10.0134 | 14.7917 | 10.2778 | 5.3472 | 10.2151 | 6.586 | 3.6962 | 9.6528 | 5.1389 | 2.2222 | 9.6774 | 6.6532 | 2.2849
4 | 3.75 | 6 | 24.664 | 13.6425 | 7.3925 | 27.4246 | 19.1631 | 10.2679 | 29.7043 | 22.3118 | 14.2473 | 38.6806 | 34.1667 | 26.1111 | 42.0027 | 38.172 | 28.3602 | 49.7917 | 39.9306 | 29.1667 | 45.6317 | 38.5081 | 30.4435 | 41.8683 | 34.9462 | 27.8898 | 36.9444 | 29.1667 | 20.0694 | 24.664 | 18.8172 | 11.9624 | 20.9028 | 16.1806 | 10.4167 | 23.5215 | 15.121 | 8.0645
4 | 3.75 | 8 | 38.5753 | 26.5457 | 16.8011 | 47.3881 | 39.7681 | 19.494 | 51.3441 | 40.7258 | 30.6452 | 66.4583 | 56.5278 | 48.75 | 67.5403 | 62.7016 | 52.8226 | 72.0139 | 65.9722 | 54.5139 | 73.8575 | 64.2473 | 53.1586 | 67.4731 | 61.2903 | 51.4113 | 58.8889 | 51.4583 | 38.4722 | 43.8172 | 35.6855 | 26.0081 | 40.9722 | 29.7917 | 21.4583 | 42.7419 | 29.0323 | 19.2876
4 | 3.75 | 9 | 46.371 | 35.2151 | 25.5376 | 57.7535 | 50.7492 | 28.3482 | 61.7608 | 49.1935 | 40.0538 | 74.1667 | 67.0833 | 60.9028 | 79.2339 | 72.8495 | 64.7177 | 82.3611 | 78.1944 | 68.1944 | 85.8199 | 75.9409 | 67.2043 | 78.2258 | 72.6478 | 64.1129 | 69.6528 | 60.1389 | 50.9722 | 52.2177 | 45.4301 | 34.9462 | 49.375 | 38.125 | 27.9167 | 51.3441 | 37.7688 | 25.8065
4 | 3.75 | 10 | 56.6532 | 44.2204 | 33.3333 | 66.7462 | 58.1845 | 37.7976 | 74.5296 | 58.8038 | 50.5376 | 84.7917 | 76.5972 | 70.4167 | 87.164 | 81.6532 | 74.1935 | 90.2083 | 86.0417 | 78.8889 | 93.6828 | 86.3575 | 78.9651 | 86.0887 | 80.4435 | 73.4543 | 78.8194 | 67.2222 | 62.8472 | 61.4247 | 54.1667 | 41.8683 | 61.0417 | 51.3194 | 36.0417 | 60.3495 | 45.6317 | 33.1317
4 | 3.75 | 11 | 66.1962 | 52.8581 | 42.3387 | 75.6568 | 66.6667 | 48.9583 | 82.9973 | 69.422 | 59.0726 | 90.9028 | 84.9306 | 78.8889 | 93.5484 | 88.0376 | 83.1989 | 94.375 | 91.5278 | 86.5278 | 96.9758 | 92.5403 | 86.2903 | 92.2043 | 88.9113 | 82.6613 | 86.3889 | 76.5972 | 70.7639 | 72.379 | 61.9624 | 54.1667 | 71.6667 | 61.25 | 47.9861 | 67.2715 | 53.629 | 43.2124
4 | 3.75 | 12 | 75.7392 | 60.3228 | 50.8737 | 83.1845 | 72.2239 | 60.1242 | 88.9113 | 77.8898 | 68.0108 | 94.5139 | 92.0833 | 85.7639 | 96.3038 | 93.2124 | 90.7258 | 97.7778 | 94.9306 | 91.9444 | 99.2608 | 97.043 | 90.9274 | 97.2446 | 93.414 | 87.7688 | 92.0139 | 84.5833 | 79.375 | 79.2339 | 68.8844 | 63.3737 | 77.5 | 69.9306 | 55.4167 | 74.2608 | 63.5081 | 51.2097
4 | 3.75 | 15 | 90.0538 | 79.5027 | 72.1102 | 92.7827 | 87.6488 | 78.6407 | 97.9839 | 92.0027 | 83.6694 | 99.7917 | 97.9167 | 95.2778 | 100 | 99.7312 | 98.5215 | 100 | 99.3056 | 97.5 | 100 | 100 | 97.9167 | 100 | 99.4624 | 96.1694 | 98.5417 | 95.5556 | 91.0417 | 94.8925 | 88.3065 | 83.3333 | 92.1528 | 86.9444 | 77.7778 | 87.9032 | 83.1317 | 72.2446
4 | 3.75 | 20 | 94.422 | 88.3065 | 79.3011 | 96.5774 | 92.3209 | 85.3423 | 99.5296 | 96.1022 | 87.6344 | 100 | 99.4444 | 96.4583 | 100 | 100 | 99.5968 | 100 | 100 | 97.9861 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.5 | 93.8889 | 99.4624 | 93.414 | 90.5914 | 96.6667 | 91.7361 | 84.5833 | 92.7419 | 88.7097 | 79.7043
4 | 3.75 | 25 | 94.422 | 88.3065 | 79.3011 | 96.5774 | 92.3209 | 85.4167 | 99.5296 | 96.1022 | 87.6344 | 100 | 99.5139 | 96.4583 | 100 | 100 | 99.5968 | 100 | 100 | 97.9861 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.5 | 93.8889 | 99.4624 | 93.4812 | 90.6586 | 96.6667 | 91.875 | 84.5833 | 92.7419 | 88.7097 | 79.7043
4 | 4 | 2 | 1.7473 | 0.53763 | 0 | 2.0474 | 0.81845 | 0 | 2.8226 | 1.0753 | 0 | 4.0972 | 2.2917 | 0.76389 | 4.5027 | 2.2177 | 0.94086 | 5.9722 | 2.9861 | 1.3889 | 4.4355 | 1.9489 | 0.80645 | 4.7043 | 2.1505 | 1.2769 | 3.4722 | 1.5278 | 0.55556 | 2.2849 | 0.80645 | 0 | 1.5972 | 0.625 | 0 | 2.5538 | 0.67204 | 0
4 | 4 | 4 | 8.6022 | 4.0323 | 2.1505 | 11.992 | 8.1101 | 3.3482 | 13.0376 | 7.5941 | 4.8387 | 18.75 | 12.8472 | 9.7222 | 19.4892 | 15.5914 | 9.6102 | 25 | 15.8333 | 11.4583 | 21.2366 | 15.3898 | 9.7446 | 20.2957 | 14.4489 | 10.0134 | 14.7917 | 10.2778 | 5.3472 | 10.2151 | 6.586 | 3.6962 | 9.6528 | 5.1389 | 2.2222 | 9.6774 | 6.6532 | 2.2849
4 | 4 | 6 | 24.664 | 13.6425 | 7.3925 | 27.4246 | 19.1631 | 10.2679 | 29.7043 | 22.3118 | 14.2473 | 38.6806 | 34.1667 | 26.1111 | 42.0027 | 38.172 | 28.3602 | 49.7917 | 39.9306 | 29.1667 | 45.6317 | 38.5081 | 30.4435 | 41.8683 | 34.9462 | 27.8898 | 36.9444 | 29.1667 | 20.0694 | 24.664 | 18.8172 | 11.9624 | 20.9028 | 16.1806 | 10.4167 | 23.5215 | 15.121 | 8.0645
4 | 4 | 8 | 38.5753 | 26.5457 | 16.8011 | 47.3881 | 39.7681 | 19.494 | 51.3441 | 40.7258 | 30.6452 | 66.4583 | 56.5278 | 48.75 | 67.5403 | 62.7016 | 52.8226 | 72.0139 | 65.9722 | 54.5139 | 73.8575 | 64.2473 | 53.1586 | 67.4731 | 61.2903 | 51.4113 | 58.8889 | 51.4583 | 38.4722 | 43.8172 | 35.6855 | 26.0081 | 40.9722 | 29.7917 | 21.4583 | 42.7419 | 29.0323 | 19.2876
4 | 4 | 9 | 46.371 | 35.2151 | 25.5376 | 57.7535 | 50.7492 | 28.3482 | 61.7608 | 49.1935 | 40.0538 | 74.1667 | 67.0833 | 60.9028 | 79.2339 | 72.8495 | 64.7177 | 82.3611 | 78.1944 | 68.1944 | 85.8199 | 75.9409 | 67.2043 | 78.2258 | 72.6478 | 64.1129 | 69.6528 | 60.1389 | 50.9722 | 52.2177 | 45.4301 | 34.9462 | 49.375 | 38.125 | 27.9167 | 51.3441 | 37.7688 | 25.8065
4 | 4 | 10 | 56.6532 | 44.2204 | 33.3333 | 66.7462 | 58.1845 | 38.0952 | 74.5296 | 58.8038 | 50.5376 | 84.7917 | 76.5972 | 70.4861 | 87.164 | 81.6532 | 74.1935 | 90.2083 | 86.0417 | 78.8889 | 93.6828 | 86.3575 | 78.9651 | 86.0887 | 80.4435 | 73.4543 | 78.8194 | 67.2222 | 62.8472 | 61.4247 | 54.1667 | 41.8683 | 61.0417 | 51.5972 | 36.0417 | 60.3495 | 45.6317 | 33.1989
4 | 4 | 11 | 66.1962 | 52.9254 | 42.6075 | 75.6568 | 67.4107 | 49.0327 | 82.9973 | 69.4892 | 59.3414 | 90.9028 | 84.9306 | 78.9583 | 93.5484 | 88.0376 | 83.1989 | 94.375 | 91.5278 | 86.5278 | 96.9758 | 92.5403 | 86.2903 | 92.2043 | 88.9113 | 82.6613 | 86.3889 | 76.5972 | 70.7639 | 72.379 | 62.0296 | 54.1667 | 71.6667 | 61.3194 | 47.9861 | 67.2715 | 53.629 | 43.2124
4 | 4 | 12 | 75.7392 | 60.3495 | 51.6801 | 83.1845 | 73.5889 | 60.1242 | 88.9113 | 78.0242 | 68.1452 | 94.5139 | 92.0833 | 85.7639 | 96.3038 | 93.2124 | 90.7258 | 97.7778 | 94.9306 | 91.9444 | 99.2608 | 97.043 | 90.9274 | 97.2446 | 93.414 | 87.7688 | 92.0139 | 84.5833 | 79.375 | 79.3011 | 68.8844 | 63.5081 | 77.6389 | 70 | 55.6944 | 74.2608 | 63.5753 | 51.2769
4 | 4 | 15 | 90.8602 | 80.8468 | 73.7903 | 93.378 | 88.3185 | 79.7311 | 98.1183 | 92.6747 | 84.4086 | 99.7917 | 98.125 | 95.625 | 100 | 99.7984 | 98.7231 | 100 | 99.3056 | 97.9167 | 100 | 100 | 98.1183 | 100 | 99.5296 | 96.7742 | 98.8194 | 95.9722 | 91.5972 | 95.3629 | 88.8441 | 83.6022 | 92.6389 | 88.4028 | 79.2361 | 88.9113 | 84.3414 | 74.1935
4 | 4 | 20 | 95.6317 | 91.2634 | 82.1909 | 97.9911 | 94.1964 | 89.1831 | 99.9328 | 97.4462 | 90.0538 | 100 | 99.7917 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.4722 | 95.7639 | 99.7984 | 95.4973 | 92.8763 | 98.0556 | 94.1667 | 88.125 | 94.8925 | 90.793 | 84.6102
4 | 4 | 25 | 95.6317 | 91.3306 | 82.2581 | 97.9911 | 94.1964 | 89.2549 | 99.9328 | 97.5134 | 90.0538 | 100 | 99.8611 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.6806 | 95.8333 | 99.9328 | 95.6317 | 92.9435 | 98.0556 | 94.375 | 88.125 | 94.8925 | 90.793 | 84.7446
6 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5972 | 0 | 0 | 1.5457 | 0 | 0 | 2.4306 | 0.41667 | 0 | 1.7473 | 0 | 0 | 1.6129 | 0.40323 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0.5 | 4 | 0 | 0 | 0 | 1.0417 | 0 | 0 | 2.0833 | 0 | 0 | 5.8333 | 3.0556 | 0 | 7.1237 | 4.0995 | 1.5457 | 13.0556 | 7.2917 | 1.7361 | 13.2392 | 6.0484 | 3.0914 | 11.2903 | 5.2419 | 2.5538 | 4.0972 | 1.5278 | 0 | 1.9489 | 0 | 0 | 1.1806 | 0 | 0 | 1.5457 | 0 | 0
6 | 0.5 | 6 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 4.8387 | 0 | 0 | 10.9028 | 5.9722 | 1.3889 | 14.8522 | 10.2151 | 4.9731 | 19.0972 | 13.4722 | 4.5139 | 21.9086 | 12.6344 | 7.2581 | 17.6075 | 9.4086 | 5.578 | 9.6528 | 4.0972 | 0.90278 | 3.5618 | 1.0081 | 0 | 1.3194 | 0 | 0 | 2.2849 | 0 | 0
6 | 0.5 | 8 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.6452 | 0 | 0 | 12.0833 | 7.3611 | 1.3889 | 15.0538 | 11.0887 | 5.2419 | 20.4167 | 13.8889 | 5.3472 | 23.4543 | 14.5833 | 8.1317 | 19.1532 | 10.2823 | 5.9812 | 10.1389 | 4.2361 | 0.97222 | 3.6962 | 1.1425 | 0 | 1.4583 | 0 | 0 | 2.2849 | 0 | 0
6 | 0.5 | 9 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.6452 | 0 | 0 | 12.0833 | 7.3611 | 1.3889 | 15.0538 | 11.0887 | 5.2419 | 20.4167 | 13.8889 | 5.3472 | 23.4543 | 14.5833 | 8.1989 | 19.1532 | 10.2823 | 5.9812 | 10.1389 | 4.2361 | 0.97222 | 3.6962 | 1.1425 | 0 | 1.4583 | 0 | 0 | 2.2849 | 0 | 0
6 | 0.5 | 10 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.6452 | 0 | 0 | 12.0833 | 7.3611 | 1.3889 | 15.0538 | 11.0887 | 5.2419 | 20.4167 | 13.8889 | 5.3472 | 23.5215 | 14.5833 | 8.1989 | 19.1532 | 10.2823 | 5.9812 | 10.1389 | 4.2361 | 0.97222 | 3.6962 | 1.1425 | 0 | 1.4583 | 0 | 0 | 2.2849 | 0 | 0
6 | 0.5 | 11 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.6452 | 0 | 0 | 12.0833 | 7.3611 | 1.3889 | 15.0538 | 11.0887 | 5.2419 | 20.4167 | 13.8889 | 5.3472 | 23.5215 | 14.5833 | 8.1989 | 19.1532 | 10.2823 | 5.9812 | 10.1389 | 4.2361 | 0.97222 | 3.6962 | 1.1425 | 0 | 1.4583 | 0 | 0 | 2.2849 | 0 | 0
6 | 0.5 | 12 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.6452 | 0 | 0 | 12.0833 | 7.3611 | 1.3889 | 15.0538 | 11.0887 | 5.2419 | 20.4167 | 13.8889 | 5.3472 | 23.5215 | 14.5833 | 8.1989 | 19.1532 | 10.2823 | 5.9812 | 10.1389 | 4.2361 | 0.97222 | 3.6962 | 1.1425 | 0 | 1.4583 | 0 | 0 | 2.2849 | 0 | 0
6 | 0.5 | 15 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.6452 | 0 | 0 | 12.0833 | 7.3611 | 1.3889 | 15.0538 | 11.0887 | 5.2419 | 20.4167 | 13.8889 | 5.3472 | 23.5215 | 14.5833 | 8.1989 | 19.1532 | 10.2823 | 5.9812 | 10.1389 | 4.2361 | 0.97222 | 3.6962 | 1.1425 | 0 | 1.4583 | 0 | 0 | 2.2849 | 0 | 0
6 | 0.5 | 20 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.6452 | 0 | 0 | 12.0833 | 7.3611 | 1.3889 | 15.0538 | 11.0887 | 5.2419 | 20.4167 | 13.8889 | 5.3472 | 23.5215 | 14.5833 | 8.1989 | 19.1532 | 10.2823 | 5.9812 | 10.1389 | 4.2361 | 0.97222 | 3.6962 | 1.1425 | 0 | 1.4583 | 0 | 0 | 2.2849 | 0 | 0
6 | 0.5 | 25 | 0.87366 | 0 | 0 | 2.753 | 0 | 0 | 5.6452 | 0 | 0 | 12.0833 | 7.3611 | 1.3889 | 15.0538 | 11.0887 | 5.2419 | 20.4167 | 13.8889 | 5.3472 | 23.5215 | 14.5833 | 8.1989 | 19.1532 | 10.2823 | 5.9812 | 10.1389 | 4.2361 | 0.97222 | 3.6962 | 1.1425 | 0 | 1.4583 | 0 | 0 | 2.2849 | 0 | 0
6 | 0.75 | 2 | 0 | 0 | 0 | 1.0417 | 0 | 0 | 0.94086 | 0 | 0 | 2.2222 | 0.97222 | 0 | 2.6882 | 0.87366 | 0 | 4.3056 | 1.7361 | 0 | 3.0242 | 0.80645 | 0 | 2.4194 | 0.94086 | 0 | 1.7361 | 0 | 0 | 0.87366 | 0 | 0 | 0 | 0 | 0 | 0.80645 | 0 | 0
6 | 0.75 | 4 | 2.0833 | 0.87366 | 0 | 5.4777 | 1.7549 | 0 | 7.3253 | 1.9489 | 0.40323 | 12.2917 | 7.8472 | 3.0556 | 12.2312 | 8.1317 | 3.2258 | 20.4167 | 10.9028 | 6.1806 | 17.2715 | 11.0887 | 6.9892 | 15.2554 | 8.6694 | 6.8548 | 8.8194 | 5.4861 | 1.3889 | 3.3602 | 1.8817 | 0 | 3.4028 | 1.3194 | 0 | 4.1667 | 1.9489 | 0
6 | 0.75 | 6 | 6.7876 | 2.4194 | 0 | 10.5988 | 4.5387 | 0 | 13.9113 | 6.1828 | 2.5538 | 25.1389 | 18.8889 | 9.5833 | 26.6129 | 20.9677 | 14.3145 | 35.0694 | 22.7083 | 16.1111 | 31.7876 | 24.7312 | 19.6909 | 32.8629 | 22.1774 | 15.5914 | 22.3611 | 12.3611 | 5.4861 | 9.4086 | 4.7043 | 1.6129 | 6.1806 | 2.0833 | 0.13889 | 6.9892 | 3.4946 | 0
6 | 0.75 | 8 | 8.7366 | 2.7554 | 0 | 12.7232 | 5.7292 | 0 | 18.6156 | 7.5941 | 3.9651 | 32.0139 | 23.3333 | 12.9167 | 35.7527 | 27.2849 | 19.6237 | 43.2639 | 29.9306 | 22.9861 | 44.2204 | 34.0726 | 25.4032 | 42.2715 | 28.7634 | 21.0349 | 28.4722 | 15.8333 | 8.3333 | 13.4409 | 6.8548 | 2.0833 | 7.0833 | 2.7083 | 0.13889 | 7.2581 | 3.8978 | 0
6 | 0.75 | 9 | 8.7366 | 2.7554 | 0 | 12.7232 | 5.7292 | 0 | 18.8172 | 7.5941 | 3.9651 | 32.7083 | 24.4444 | 13.125 | 37.164 | 27.8226 | 19.8253 | 43.75 | 30.2778 | 23.4028 | 44.9597 | 35.1478 | 26.2769 | 42.3387 | 29.7043 | 22.043 | 28.6806 | 16.3889 | 8.3333 | 13.4409 | 7.0565 | 2.0833 | 7.0833 | 2.7083 | 0.13889 | 7.2581 | 3.8978 | 0
6 | 0.75 | 10 | 8.7366 | 2.7554 | 0 | 12.7232 | 5.7292 | 0 | 18.8844 | 7.5941 | 3.9651 | 32.7083 | 24.4444 | 13.125 | 37.4328 | 27.957 | 20.2285 | 43.75 | 30.2778 | 23.4722 | 45.0269 | 35.2151 | 26.4113 | 42.3387 | 29.8387 | 22.043 | 28.6806 | 16.3889 | 8.3333 | 13.4409 | 7.1237 | 2.0833 | 7.0833 | 2.7083 | 0.13889 | 7.2581 | 3.8978 | 0
6 | 0.75 | 11 | 8.7366 | 2.7554 | 0 | 12.7232 | 5.7292 | 0 | 18.8844 | 7.5941 | 3.9651 | 32.7083 | 24.4444 | 13.125 | 37.5 | 27.957 | 20.2285 | 43.75 | 30.3472 | 23.4722 | 45.0269 | 35.2151 | 26.4113 | 42.3387 | 29.8387 | 22.043 | 28.6806 | 16.3889 | 8.3333 | 13.4409 | 7.1237 | 2.0833 | 7.0833 | 2.7083 | 0.13889 | 7.2581 | 3.8978 | 0
6 | 0.75 | 12 | 8.7366 | 2.7554 | 0 | 12.7232 | 5.7292 | 0 | 18.8844 | 7.5941 | 3.9651 | 32.7083 | 24.4444 | 13.125 | 37.5 | 27.957 | 20.2285 | 43.75 | 30.3472 | 23.4722 | 45.0269 | 35.2151 | 26.4113 | 42.3387 | 29.8387 | 22.043 | 28.6806 | 16.3889 | 8.3333 | 13.4409 | 7.1237 | 2.0833 | 7.0833 | 2.7083 | 0.13889 | 7.2581 | 3.8978 | 0
6 | 0.75 | 15 | 8.7366 | 2.7554 | 0 | 12.7232 | 5.7292 | 0 | 18.8844 | 7.5941 | 3.9651 | 32.7083 | 24.4444 | 13.125 | 37.5 | 27.957 | 20.2285 | 43.75 | 30.3472 | 23.4722 | 45.0269 | 35.2151 | 26.4113 | 42.3387 | 29.8387 | 22.043 | 28.6806 | 16.3889 | 8.3333 | 13.4409 | 7.1237 | 2.0833 | 7.0833 | 2.7083 | 0.13889 | 7.2581 | 3.8978 | 0
6 | 0.75 | 20 | 8.7366 | 2.7554 | 0 | 12.7232 | 5.7292 | 0 | 18.8844 | 7.5941 | 3.9651 | 32.7083 | 24.4444 | 13.125 | 37.5 | 27.957 | 20.2285 | 43.75 | 30.3472 | 23.4722 | 45.0269 | 35.2151 | 26.4113 | 42.3387 | 29.8387 | 22.043 | 28.6806 | 16.3889 | 8.3333 | 13.4409 | 7.1237 | 2.0833 | 7.0833 | 2.7083 | 0.13889 | 7.2581 | 3.8978 | 0
6 | 0.75 | 25 | 8.7366 | 2.7554 | 0 | 12.7232 | 5.7292 | 0 | 18.8844 | 7.5941 | 3.9651 | 32.7083 | 24.4444 | 13.125 | 37.5 | 27.957 | 20.2285 | 43.75 | 30.3472 | 23.4722 | 45.0269 | 35.2151 | 26.4113 | 42.3387 | 29.8387 | 22.043 | 28.6806 | 16.3889 | 8.3333 | 13.4409 | 7.1237 | 2.0833 | 7.0833 | 2.7083 | 0.13889 | 7.2581 | 3.8978 | 0
6 | 1 | 2 | 0.80645 | 0 | 0 | 1.1905 | 0 | 0 | 1.2097 | 0 | 0 | 2.7083 | 0.97222 | 0 | 2.8898 | 0.94086 | 0 | 5 | 2.0833 | 0 | 3.0242 | 0.80645 | 0 | 2.957 | 1.5457 | 0 | 2.1528 | 0 | 0 | 1.4113 | 0 | 0 | 0.83333 | 0 | 0 | 0.87366 | 0 | 0
6 | 1 | 4 | 3.1586 | 1.4785 | 0 | 8.2589 | 3.497 | 0.44643 | 10.1478 | 3.629 | 1.5457 | 14.375 | 9.5833 | 4.7222 | 15.9946 | 10.0134 | 6.1156 | 22.1528 | 12.9861 | 8.6806 | 19.2876 | 12.6344 | 8.3333 | 18.8172 | 11.2903 | 7.7957 | 11.9444 | 7.1528 | 3.0556 | 6.0484 | 3.7634 | 0.87366 | 4.8611 | 2.4306 | 0.83333 | 6.1828 | 2.4866 | 0
6 | 1 | 6 | 11.2231 | 5.3763 | 1.4113 | 18.006 | 11.0376 | 3.2738 | 20.0941 | 12.164 | 5.1075 | 30.6944 | 23.2639 | 16.8056 | 34.2742 | 29.2339 | 21.5054 | 43.0556 | 32.6389 | 22.7778 | 38.8441 | 32.2581 | 25.9409 | 39.5833 | 27.8226 | 21.4382 | 29.5139 | 18.6111 | 11.3194 | 16.3978 | 10.2151 | 4.3683 | 12.2917 | 6.875 | 2.2222 | 12.9704 | 7.3253 | 1.0753
6 | 1 | 8 | 19.8925 | 8.4005 | 2.3522 | 26.9345 | 17.0387 | 5.2083 | 30.5108 | 18.8172 | 9.207 | 44.4444 | 35.4861 | 25.6944 | 50.7392 | 43.414 | 35.3495 | 56.3194 | 47.2222 | 37.9167 | 61.6263 | 48.5887 | 38.5753 | 56.25 | 44.6237 | 37.0296 | 40.2083 | 31.3194 | 20.8333 | 22.1774 | 14.9866 | 7.8629 | 16.875 | 9.375 | 3.0556 | 20.6989 | 10.2823 | 2.4866
6 | 1 | 9 | 20.2285 | 9.4086 | 2.4194 | 27.4887 | 17.6339 | 5.3571 | 32.5269 | 20.6989 | 9.879 | 47.9861 | 39.0972 | 27.8472 | 56.5188 | 46.1022 | 38.3737 | 58.75 | 50.4167 | 40.3472 | 66.129 | 52.3522 | 42.3387 | 60.5511 | 47.1774 | 40.5914 | 43.6806 | 33.9583 | 22.0833 | 23.4543 | 15.793 | 8.4677 | 17.6389 | 9.8611 | 3.0556 | 20.9677 | 10.6855 | 2.621
6 | 1 | 10 | 20.2285 | 9.4086 | 2.4194 | 27.4887 | 17.6339 | 5.3571 | 32.9301 | 21.707 | 10.4839 | 48.4722 | 40.2083 | 28.8889 | 57.0565 | 47.1774 | 39.9866 | 59.8611 | 51.5972 | 40.7639 | 67.3387 | 53.6962 | 44.2204 | 61.4247 | 48.2527 | 41.2634 | 44.3056 | 34.375 | 22.1528 | 23.7903 | 15.9946 | 8.5349 | 17.7778 | 9.8611 | 3.0556 | 21.0349 | 10.7527 | 2.7554
6 | 1 | 11 | 20.2285 | 9.4086 | 2.4194 | 27.4887 | 17.6339 | 5.3571 | 33.0645 | 21.707 | 10.4839 | 48.6806 | 40.5556 | 28.8889 | 57.0565 | 47.5134 | 39.9866 | 59.9306 | 51.5972 | 40.7639 | 67.4059 | 53.8978 | 44.6237 | 61.6263 | 48.4543 | 41.3306 | 44.3056 | 34.375 | 22.1528 | 23.7903 | 16.0618 | 8.5349 | 17.7778 | 9.8611 | 3.0556 | 21.0349 | 10.7527 | 2.7554
6 | 1 | 12 | 20.2285 | 9.4086 | 2.4194 | 27.4887 | 17.6339 | 5.3571 | 33.0645 | 21.707 | 10.4839 | 48.6806 | 40.5556 | 28.8889 | 57.0565 | 47.5134 | 39.9866 | 59.9306 | 51.6667 | 40.7639 | 67.4731 | 53.8978 | 44.6237 | 61.6263 | 48.4543 | 41.3306 | 44.3056 | 34.375 | 22.1528 | 23.7903 | 16.0618 | 8.5349 | 17.7778 | 9.8611 | 3.0556 | 21.0349 | 10.7527 | 2.7554
6 | 1 | 15 | 20.2285 | 9.4086 | 2.4194 | 27.4887 | 17.6339 | 5.3571 | 33.0645 | 21.707 | 10.4839 | 48.6806 | 40.5556 | 28.8889 | 57.0565 | 47.5134 | 39.9866 | 59.9306 | 51.6667 | 40.7639 | 67.4731 | 53.8978 | 44.6237 | 61.6263 | 48.4543 | 41.3306 | 44.3056 | 34.375 | 22.1528 | 23.7903 | 16.0618 | 8.5349 | 17.7778 | 9.8611 | 3.0556 | 21.0349 | 10.7527 | 2.7554
6 | 1 | 20 | 20.2285 | 9.4086 | 2.4194 | 27.4887 | 17.6339 | 5.3571 | 33.0645 | 21.707 | 10.4839 | 48.6806 | 40.5556 | 28.8889 | 57.0565 | 47.5134 | 39.9866 | 59.9306 | 51.6667 | 40.7639 | 67.4731 | 53.8978 | 44.6237 | 61.6263 | 48.4543 | 41.3306 | 44.3056 | 34.375 | 22.1528 | 23.7903 | 16.0618 | 8.5349 | 17.7778 | 9.8611 | 3.0556 | 21.0349 | 10.7527 | 2.7554
6 | 1 | 25 | 20.2285 | 9.4086 | 2.4194 | 27.4887 | 17.6339 | 5.3571 | 33.0645 | 21.707 | 10.4839 | 48.6806 | 40.5556 | 28.8889 | 57.0565 | 47.5134 | 39.9866 | 59.9306 | 51.6667 | 40.7639 | 67.4731 | 53.8978 | 44.6237 | 61.6263 | 48.4543 | 41.3306 | 44.3056 | 34.375 | 22.1528 | 23.7903 | 16.0618 | 8.5349 | 17.7778 | 9.8611 | 3.0556 | 21.0349 | 10.7527 | 2.7554
6 | 1.25 | 2 | 0.80645 | 0 | 0 | 1.1905 | 0 | 0 | 1.7473 | 0 | 0 | 2.8472 | 1.0417 | 0 | 3.1586 | 0.94086 | 0 | 5 | 2.1528 | 0.41667 | 3.0242 | 0.80645 | 0 | 3.0914 | 1.6129 | 0 | 2.3611 | 0.90278 | 0 | 1.6129 | 0 | 0 | 0.97222 | 0 | 0 | 1.1425 | 0 | 0
6 | 1.25 | 4 | 5.5108 | 1.8817 | 0.67204 | 9.6572 | 4.7619 | 1.17 | 11.3575 | 5.4435 | 2.4194 | 15.9028 | 10.5556 | 7.0833 | 16.6667 | 12.3656 | 6.7876 | 22.9861 | 14.4444 | 9.3056 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.1989 | 12.5 | 7.7083 | 3.6806 | 7.3925 | 4.6371 | 2.2177 | 6.7361 | 4.0278 | 1.1111 | 7.6613 | 3.5618 | 0.94086
6 | 1.25 | 6 | 16.6667 | 6.922 | 3.9651 | 21.5774 | 14.3601 | 5.7292 | 24.9328 | 18.2124 | 7.7957 | 33.8889 | 27.9167 | 21.7361 | 38.4409 | 32.5269 | 24.7984 | 46.9444 | 36.3889 | 26.1111 | 42.7419 | 35.8199 | 27.5538 | 40.8602 | 30.578 | 25.0672 | 33.2639 | 24.5139 | 14.6528 | 19.0188 | 12.164 | 7.3253 | 15.9722 | 10.5556 | 4.7222 | 15.2554 | 8.9382 | 3.6962
6 | 1.25 | 8 | 28.293 | 14.2473 | 7.0565 | 36.4583 | 24.5792 | 11.4583 | 39.7177 | 29.6371 | 16.129 | 53.0556 | 45.7639 | 36.3889 | 60.1478 | 53.0242 | 46.1694 | 65.3472 | 58.75 | 45.3472 | 69.5565 | 58.7366 | 48.3871 | 62.0968 | 53.293 | 45.4301 | 48.2639 | 40.9722 | 26.9444 | 29.0323 | 22.9839 | 12.9704 | 26.4583 | 15.9028 | 8.6111 | 28.1586 | 17.0027 | 5.914
6 | 1.25 | 9 | 30.8468 | 16.129 | 7.7957 | 40.4762 | 27.381 | 11.9048 | 43.0108 | 33.8038 | 19.422 | 60.5556 | 49.0972 | 40.9028 | 66.3978 | 59.207 | 50.7392 | 71.1806 | 65.7639 | 51.875 | 77.0161 | 64.4489 | 56.1828 | 71.1022 | 58.4677 | 51.6801 | 53.6111 | 44.8611 | 32.8472 | 33.6694 | 26.6129 | 14.7849 | 29.0278 | 19.3056 | 8.6806 | 30.4435 | 19.3548 | 6.3844
6 | 1.25 | 10 | 32.2581 | 16.5995 | 8.3333 | 41.8719 | 29.3129 | 12.2768 | 43.8844 | 36.0215 | 20.6989 | 64.6528 | 53.0556 | 44.2361 | 69.422 | 63.5081 | 53.2258 | 74.4444 | 68.125 | 53.9583 | 80.3091 | 69.9597 | 60.1478 | 74.4624 | 61.7608 | 53.629 | 57.3611 | 46.875 | 35.2083 | 34.8118 | 29.4355 | 16.3306 | 29.7917 | 20.625 | 8.75 | 30.7796 | 20.0269 | 6.8548
6 | 1.25 | 11 | 32.4597 | 16.6667 | 8.4677 | 42.3363 | 29.3847 | 12.3512 | 45.0941 | 36.6263 | 20.6989 | 65.6944 | 54.0278 | 44.5833 | 70.2285 | 64.5161 | 53.629 | 74.7917 | 68.125 | 54.0278 | 80.9812 | 71.1022 | 61.8952 | 74.9328 | 62.7016 | 54.2339 | 59.5833 | 47.4306 | 35.7639 | 34.9462 | 30.0403 | 16.6667 | 29.8611 | 20.625 | 8.8194 | 31.1828 | 20.2957 | 6.922
6 | 1.25 | 12 | 32.4597 | 16.6667 | 8.4677 | 42.3363 | 29.3847 | 12.3512 | 45.1613 | 36.7608 | 20.8333 | 65.8333 | 54.0278 | 44.7222 | 70.2285 | 65.1882 | 53.8306 | 74.9306 | 68.6806 | 54.0278 | 81.1828 | 71.3038 | 62.0296 | 75.1344 | 62.836 | 54.5027 | 59.7222 | 47.6389 | 35.9722 | 35.1478 | 30.4435 | 16.7339 | 30.2083 | 20.625 | 8.8889 | 31.1828 | 20.3629 | 6.922
6 | 1.25 | 15 | 32.4597 | 16.6667 | 8.4677 | 42.3363 | 29.3847 | 12.3512 | 45.1613 | 36.7608 | 20.8333 | 65.8333 | 54.0278 | 44.7222 | 70.2957 | 65.1882 | 53.8306 | 75 | 68.6806 | 54.0278 | 81.1828 | 71.3038 | 62.0968 | 75.1344 | 62.9032 | 54.5699 | 59.7222 | 47.6389 | 35.9722 | 35.1478 | 30.4435 | 16.8011 | 30.2083 | 20.625 | 8.8889 | 31.1828 | 20.3629 | 6.922
6 | 1.25 | 20 | 32.4597 | 16.6667 | 8.4677 | 42.3363 | 29.3847 | 12.3512 | 45.1613 | 36.7608 | 20.8333 | 65.8333 | 54.0278 | 44.7222 | 70.2957 | 65.1882 | 53.8306 | 75 | 68.6806 | 54.0278 | 81.1828 | 71.3038 | 62.0968 | 75.1344 | 62.9032 | 54.5699 | 59.7222 | 47.6389 | 35.9722 | 35.1478 | 30.4435 | 16.8011 | 30.2083 | 20.625 | 8.8889 | 31.1828 | 20.3629 | 6.922
6 | 1.25 | 25 | 32.4597 | 16.6667 | 8.4677 | 42.3363 | 29.3847 | 12.3512 | 45.1613 | 36.7608 | 20.8333 | 65.8333 | 54.0278 | 44.7222 | 70.2957 | 65.1882 | 53.8306 | 75 | 68.6806 | 54.0278 | 81.1828 | 71.3038 | 62.0968 | 75.1344 | 62.9032 | 54.5699 | 59.7222 | 47.6389 | 35.9722 | 35.1478 | 30.4435 | 16.8011 | 30.2083 | 20.625 | 8.8889 | 31.1828 | 20.3629 | 6.922
6 | 1.5 | 2 | 1.0081 | 0 | 0 | 1.1905 | 0 | 0 | 1.9489 | 0 | 0 | 2.8472 | 1.3889 | 0 | 3.4946 | 1.0753 | 0 | 5 | 2.1528 | 0.83333 | 3.0242 | 0.80645 | 0 | 3.3602 | 1.6129 | 0.067204 | 2.5 | 0.90278 | 0 | 1.9489 | 0 | 0 | 0.97222 | 0 | 0 | 1.3441 | 0 | 0
6 | 1.5 | 4 | 7.0565 | 2.3522 | 0.94086 | 10.0446 | 5.7009 | 1.465 | 11.4247 | 6.4516 | 3.2258 | 16.4583 | 11.3889 | 7.5694 | 17.0027 | 13.3737 | 7.5269 | 23.75 | 14.7917 | 9.8611 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.5349 | 12.5 | 8.1944 | 4.4444 | 8.1317 | 5.3763 | 2.4194 | 7.7083 | 4.5139 | 1.25 | 8.4005 | 5.3091 | 1.3441
6 | 1.5 | 6 | 21.2366 | 9.0054 | 5.7796 | 23.6838 | 15.6994 | 6.9196 | 26.2769 | 20.6317 | 9.3414 | 35.9028 | 30.625 | 23.0556 | 40.8602 | 35.4167 | 26.3441 | 48.8889 | 37.7083 | 27.2917 | 43.75 | 36.3575 | 28.4946 | 40.9274 | 31.6532 | 25.4704 | 34.6528 | 26.3194 | 16.9444 | 21.9086 | 15.3898 | 8.6694 | 17.9167 | 12.2917 | 7.0833 | 17.4731 | 11.7608 | 4.9059
6 | 1.5 | 8 | 32.6613 | 19.4892 | 10.0806 | 42.0387 | 31.0268 | 15.0298 | 44.4892 | 34.879 | 21.0349 | 58.4722 | 50.5556 | 42.1528 | 64.7849 | 57.5941 | 49.2608 | 69.375 | 62.5694 | 50.2778 | 72.379 | 62.836 | 50.8065 | 64.7849 | 58.5349 | 47.7823 | 53.125 | 45.9028 | 32.0833 | 35.5511 | 28.7634 | 17.1371 | 33.0556 | 20.6944 | 13.2639 | 33.7366 | 21.9758 | 9.543
6 | 1.5 | 9 | 36.7608 | 23.0511 | 13.3065 | 47.2932 | 36.1017 | 19.122 | 50.9409 | 40.2554 | 26.0753 | 66.3889 | 57.7778 | 49.375 | 73.0511 | 65.2554 | 58.3333 | 76.875 | 71.9444 | 61.875 | 81.0484 | 71.2366 | 63.4409 | 74.7312 | 66.5323 | 57.9301 | 63.2639 | 52.5 | 40.6944 | 39.8522 | 35.6855 | 21.9086 | 39.1667 | 25.9028 | 14.7222 | 38.1048 | 26.6129 | 12.7688
6 | 1.5 | 10 | 39.5833 | 25.7392 | 15.7258 | 51.2649 | 38.2235 | 20.8333 | 54.9059 | 42.7419 | 29.5699 | 70.9028 | 62.1528 | 55.4167 | 78.0242 | 71.1022 | 63.9113 | 80.7639 | 76.8056 | 67.7083 | 86.6263 | 78.6962 | 69.422 | 79.9059 | 71.9086 | 63.3737 | 67.7083 | 56.875 | 46.8056 | 45.9005 | 38.8441 | 23.7903 | 43.1944 | 31.1806 | 15.9028 | 40.9946 | 29.9059 | 14.7177
6 | 1.5 | 11 | 41.1962 | 26.8817 | 16.7339 | 52.5298 | 39.2113 | 21.503 | 57.5941 | 45.0269 | 31.3172 | 73.5417 | 64.1667 | 56.9444 | 80.1075 | 74.328 | 65.9274 | 82.6389 | 79.0278 | 69.2361 | 88.4409 | 81.3844 | 72.1774 | 82.1909 | 73.8575 | 65.3226 | 71.5278 | 59.0278 | 47.9861 | 46.8414 | 40.7258 | 25.8737 | 44.4444 | 32.7083 | 16.25 | 42.0699 | 30.7796 | 15.2554
6 | 1.5 | 12 | 41.3306 | 27.0161 | 17.4059 | 52.8274 | 39.2755 | 21.5774 | 58.0645 | 45.6317 | 31.922 | 74.0278 | 64.5833 | 57.5694 | 81.1156 | 75.4032 | 67.5403 | 83.1944 | 79.7222 | 69.4444 | 88.7097 | 82.5941 | 73.3199 | 82.9301 | 74.0591 | 66.2634 | 71.8056 | 59.5139 | 48.6111 | 47.4462 | 41.3978 | 26.0753 | 45 | 32.8472 | 16.3194 | 42.3387 | 30.9812 | 15.5242
6 | 1.5 | 15 | 41.4651 | 27.0833 | 17.4731 | 52.9018 | 39.3473 | 22.0238 | 58.1317 | 45.6989 | 31.922 | 74.0972 | 64.6528 | 57.6389 | 81.25 | 75.6048 | 67.6747 | 83.5417 | 79.8611 | 69.4444 | 88.7769 | 82.7957 | 73.7231 | 83.1317 | 74.1263 | 66.6667 | 71.875 | 59.6528 | 48.6111 | 47.5134 | 41.5995 | 26.2769 | 45.0694 | 32.8472 | 16.4583 | 42.3387 | 30.9812 | 15.5914
6 | 1.5 | 20 | 41.4651 | 27.0833 | 17.4731 | 52.9018 | 39.3473 | 22.0238 | 58.1317 | 45.6989 | 31.922 | 74.0972 | 64.6528 | 57.6389 | 81.25 | 75.6048 | 67.6747 | 83.5417 | 79.8611 | 69.4444 | 88.7769 | 82.7957 | 73.7231 | 83.1317 | 74.1263 | 66.6667 | 71.875 | 59.6528 | 48.6111 | 47.5134 | 41.5995 | 26.2769 | 45.0694 | 32.8472 | 16.4583 | 42.3387 | 30.9812 | 15.5914
6 | 1.5 | 25 | 41.4651 | 27.0833 | 17.4731 | 52.9018 | 39.3473 | 22.0238 | 58.1317 | 45.6989 | 31.922 | 74.0972 | 64.6528 | 57.6389 | 81.25 | 75.6048 | 67.6747 | 83.5417 | 79.8611 | 69.4444 | 88.7769 | 82.7957 | 73.7231 | 83.1317 | 74.1263 | 66.6667 | 71.875 | 59.6528 | 48.6111 | 47.5134 | 41.5995 | 26.2769 | 45.0694 | 32.8472 | 16.4583 | 42.3387 | 30.9812 | 15.5914
6 | 1.75 | 2 | 1.2097 | 0 | 0 | 1.5086 | 0 | 0 | 1.9489 | 0 | 0 | 2.8472 | 1.3889 | 0 | 3.4946 | 1.1425 | 0 | 5 | 2.1528 | 0.83333 | 3.0242 | 0.80645 | 0 | 3.3602 | 1.6129 | 0.47043 | 2.5 | 0.90278 | 0 | 1.9489 | 0 | 0 | 1.1111 | 0 | 0 | 1.8145 | 0 | 0
6 | 1.75 | 4 | 7.0565 | 2.621 | 1.0753 | 10.5655 | 6.3578 | 2.0423 | 11.4247 | 6.586 | 3.629 | 17.3611 | 11.875 | 7.7778 | 17.2715 | 13.5753 | 7.5269 | 23.75 | 15 | 9.9306 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.5349 | 12.7778 | 8.75 | 4.4444 | 8.9382 | 5.6452 | 2.5538 | 8.2639 | 4.7222 | 2.0139 | 8.6022 | 5.578 | 1.3441
6 | 1.75 | 6 | 22.9167 | 10.4839 | 6.3172 | 25.744 | 16.2946 | 8.1845 | 27.4866 | 21.371 | 11.6935 | 37.5 | 31.7361 | 23.9583 | 41.1962 | 36.0215 | 26.7473 | 48.8889 | 38.3333 | 27.3611 | 43.75 | 36.3575 | 29.0323 | 40.9274 | 31.922 | 26.2097 | 35.8333 | 26.9444 | 17.4306 | 22.8495 | 15.8602 | 10.5511 | 18.3333 | 13.5417 | 7.8472 | 20.1613 | 11.8952 | 5.0403
6 | 1.75 | 8 | 36.0215 | 22.2446 | 12.2984 | 43.6756 | 34.4186 | 15.8482 | 47.1102 | 36.6935 | 25.4704 | 61.875 | 53.1944 | 43.6806 | 66.5995 | 60.8199 | 51.5457 | 70.4167 | 65.0694 | 52.8472 | 72.6478 | 63.3737 | 52.2849 | 66.1962 | 59.8118 | 50 | 56.5972 | 48.2639 | 34.5139 | 39.1129 | 31.922 | 20.4301 | 38.1944 | 24.375 | 17.1528 | 36.0887 | 22.9167 | 13.2392
6 | 1.75 | 9 | 41.0618 | 27.2849 | 16.4651 | 51.1161 | 42.1875 | 23.2143 | 54.5699 | 43.3468 | 31.8548 | 70.625 | 61.8056 | 52.8472 | 76.8145 | 69.7581 | 60.8871 | 80.625 | 74.9306 | 65.6944 | 82.7285 | 74.1263 | 65.6586 | 76.3441 | 69.6237 | 61.6263 | 66.5278 | 55.9028 | 44.3056 | 45.1613 | 38.4409 | 26.5457 | 43.1944 | 32.4306 | 19.5139 | 42.2043 | 30.6452 | 16.2634
6 | 1.75 | 10 | 46.5726 | 33.4677 | 20.6317 | 58.1101 | 46.4901 | 26.3393 | 63.6425 | 49.5968 | 37.836 | 79.0278 | 67.2222 | 61.5278 | 82.9301 | 76.4113 | 69.2204 | 86.1806 | 82.0139 | 72.7083 | 90.457 | 82.9973 | 74.664 | 83.1317 | 76.7473 | 68.0108 | 72.3611 | 61.7361 | 52.5694 | 51.8145 | 43.8844 | 32.4597 | 49.5139 | 37.2917 | 24.5139 | 47.1102 | 35.3495 | 19.8925
6 | 1.75 | 11 | 50.2016 | 36.6935 | 23.1855 | 63.1696 | 48.5991 | 28.4278 | 67.9435 | 54.9059 | 43.0108 | 81.8056 | 73.2639 | 65.2083 | 87.0968 | 81.4516 | 75.2688 | 88.6111 | 85.1389 | 77.9167 | 93.414 | 87.7688 | 78.5618 | 86.3575 | 80.0403 | 72.8495 | 78.6806 | 66.875 | 55.2778 | 55.7124 | 47.7151 | 37.164 | 55.0694 | 40.6944 | 27.2222 | 49.328 | 37.7016 | 21.7742
6 | 1.75 | 12 | 50.8065 | 37.0968 | 24.1263 | 64.2113 | 49.3406 | 30.2083 | 71.6398 | 56.9892 | 43.8172 | 83.1944 | 74.2361 | 66.25 | 88.1048 | 83.871 | 78.3602 | 89.4444 | 86.8056 | 79.5139 | 95.0269 | 88.5081 | 80.4435 | 88.3737 | 81.8548 | 74.0591 | 79.1667 | 68.0556 | 57.0833 | 57.8629 | 50.0672 | 39.1801 | 56.4583 | 42.5694 | 27.8472 | 49.8656 | 38.9785 | 22.5806
6 | 1.75 | 15 | 50.8737 | 37.6344 | 24.8656 | 64.7321 | 49.5638 | 30.506 | 72.1102 | 57.5269 | 44.2204 | 83.6111 | 74.7917 | 66.4583 | 88.3065 | 84.8118 | 78.8978 | 89.6528 | 86.9444 | 79.5833 | 95.1613 | 89.3145 | 81.1828 | 88.6425 | 82.1237 | 74.9328 | 79.4444 | 68.8194 | 58.2639 | 58.4677 | 51.0081 | 40.121 | 57.2222 | 42.7778 | 28.75 | 50.2016 | 40.121 | 22.7823
6 | 1.75 | 20 | 50.8737 | 37.6344 | 24.8656 | 64.7321 | 49.5638 | 30.506 | 72.1102 | 57.5269 | 44.2204 | 83.6111 | 74.7917 | 66.4583 | 88.3065 | 84.879 | 78.8978 | 89.6528 | 86.9444 | 79.5833 | 95.1613 | 89.3145 | 81.1828 | 88.6425 | 82.1237 | 74.9328 | 79.4444 | 68.8194 | 58.2639 | 58.4677 | 51.0081 | 40.121 | 57.2917 | 42.7778 | 28.75 | 50.2016 | 40.121 | 22.7823
6 | 1.75 | 25 | 50.8737 | 37.6344 | 24.8656 | 64.7321 | 49.5638 | 30.506 | 72.1102 | 57.5269 | 44.2204 | 83.6111 | 74.7917 | 66.4583 | 88.3065 | 84.879 | 78.8978 | 89.6528 | 86.9444 | 79.5833 | 95.1613 | 89.3145 | 81.1828 | 88.6425 | 82.1237 | 74.9328 | 79.4444 | 68.8194 | 58.2639 | 58.4677 | 51.0081 | 40.121 | 57.2917 | 42.7778 | 28.75 | 50.2016 | 40.121 | 22.7823
6 | 2 | 2 | 1.2097 | 0 | 0 | 1.5086 | 0 | 0 | 1.9489 | 0 | 0 | 2.8472 | 1.3889 | 0 | 3.4946 | 1.1425 | 0 | 5 | 2.1528 | 0.83333 | 3.0242 | 0.80645 | 0 | 3.3602 | 1.6129 | 0.47043 | 2.5 | 0.90278 | 0 | 1.9489 | 0 | 0 | 1.1111 | 0 | 0 | 2.2177 | 0 | 0
6 | 2 | 4 | 7.1237 | 2.8226 | 1.2097 | 10.8631 | 6.6554 | 2.0423 | 11.4247 | 6.6532 | 3.629 | 17.3611 | 11.9444 | 7.9167 | 17.6747 | 13.5753 | 7.7957 | 23.75 | 15 | 9.9306 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.5349 | 12.7778 | 8.75 | 4.4444 | 9.543 | 5.6452 | 2.5538 | 8.2639 | 4.7222 | 2.0139 | 8.6694 | 6.3172 | 1.3441
6 | 2 | 6 | 23.6559 | 12.2984 | 6.3172 | 26.4137 | 17.3979 | 8.4821 | 27.8898 | 21.707 | 12.7688 | 38.0556 | 32.2222 | 24.8611 | 41.1962 | 36.2903 | 26.8145 | 48.8889 | 38.3333 | 27.3611 | 43.75 | 36.3575 | 29.0323 | 40.9274 | 32.3925 | 26.2769 | 35.9028 | 27.1528 | 18.125 | 23.6559 | 17.0699 | 10.7527 | 19.375 | 14.0972 | 8.4028 | 21.5726 | 12.9032 | 6.3172
6 | 2 | 8 | 37.2984 | 23.5215 | 13.5753 | 44.8661 | 35.8143 | 17.4851 | 47.9839 | 38.2392 | 26.8145 | 64.5833 | 54.3056 | 45.625 | 66.6667 | 61.2231 | 52.2177 | 70.5556 | 65.3472 | 53.5417 | 72.6478 | 63.4409 | 52.3522 | 66.5995 | 60.1478 | 50.4704 | 57.1528 | 49.4444 | 35.625 | 42.1371 | 33.8038 | 22.5806 | 39.375 | 25.4167 | 19.375 | 38.3065 | 25.672 | 15.3226
6 | 2 | 9 | 43.3468 | 31.3172 | 20.0269 | 54.0153 | 45.8256 | 24.4792 | 58.1989 | 46.8414 | 35.0806 | 72.2222 | 63.6111 | 55.4167 | 77.7554 | 71.1022 | 63.7097 | 81.3889 | 76.3889 | 66.8056 | 84.2742 | 74.664 | 66.7339 | 77.4866 | 71.4382 | 62.7688 | 68.3333 | 57.5694 | 47.3611 | 48.3199 | 39.9194 | 29.3683 | 45.4861 | 34.2361 | 24.0278 | 45.5645 | 32.4597 | 18.8172
6 | 2 | 10 | 50.1344 | 37.6344 | 24.1263 | 61.1607 | 52.0833 | 32.1429 | 68.6156 | 54.3011 | 42.9435 | 82.9167 | 71.25 | 66.0417 | 84.879 | 78.4274 | 71.4382 | 88.1944 | 84.1667 | 76.5278 | 92.0027 | 85.2823 | 77.0833 | 84.543 | 79.0323 | 71.371 | 76.5278 | 65.2083 | 56.9444 | 56.3844 | 48.1855 | 36.5591 | 53.8194 | 42.9861 | 30.2778 | 52.6882 | 38.7769 | 23.7231
6 | 2 | 11 | 55.7796 | 41.3306 | 29.8387 | 69.1964 | 56.3013 | 35.4911 | 76.5457 | 61.3575 | 49.7312 | 86.7361 | 77.9861 | 70.8333 | 89.8522 | 84.1398 | 79.6371 | 92.0139 | 88.4028 | 82.8472 | 95.0941 | 89.9194 | 82.1237 | 88.3065 | 84.207 | 78.629 | 81.9444 | 71.7361 | 63.4722 | 63.0376 | 53.8978 | 45.3629 | 60.6944 | 48.6111 | 35.9028 | 56.4516 | 42.4731 | 27.8898
6 | 2 | 12 | 58.871 | 43.75 | 33.2661 | 71.875 | 59.4494 | 38.7444 | 79.3683 | 65.6586 | 52.4194 | 91.0417 | 82.4306 | 73.125 | 92.6075 | 87.2312 | 83.5349 | 93.1944 | 89.7917 | 85.4861 | 96.9758 | 92.5403 | 85.2823 | 90.9274 | 87.0968 | 80.7124 | 83.1944 | 74.3056 | 66.1806 | 67.4731 | 56.7204 | 48.9919 | 63.3333 | 50.5556 | 37.5694 | 59.0726 | 45.7661 | 30.3763
6 | 2 | 15 | 62.5 | 44.6237 | 35.4167 | 72.9911 | 60.0036 | 39.3345 | 80.3763 | 66.5995 | 52.957 | 91.7361 | 83.2639 | 75.1389 | 93.3468 | 89.3145 | 85.4167 | 93.8889 | 90.2083 | 86.4583 | 97.1774 | 93.3468 | 86.4919 | 92.4731 | 87.9704 | 81.6532 | 84.3056 | 75.5556 | 67.7778 | 70.9677 | 59.543 | 52.0161 | 65.8333 | 52.7778 | 39.2361 | 60.5511 | 48.7903 | 31.1828
6 | 2 | 20 | 62.5 | 44.6237 | 35.4167 | 72.9911 | 60.0036 | 39.3345 | 80.3763 | 66.5995 | 52.957 | 91.7361 | 83.2639 | 75.1389 | 93.3468 | 89.3817 | 85.4167 | 93.8889 | 90.2083 | 86.4583 | 97.1774 | 93.3468 | 86.5591 | 92.4731 | 87.9704 | 81.6532 | 84.375 | 75.625 | 67.7778 | 70.9677 | 59.9462 | 52.0161 | 65.8333 | 52.7778 | 39.3056 | 60.5511 | 48.7903 | 31.1828
6 | 2 | 25 | 62.5 | 44.6237 | 35.4167 | 72.9911 | 60.0036 | 39.3345 | 80.3763 | 66.5995 | 52.957 | 91.7361 | 83.2639 | 75.1389 | 93.3468 | 89.3817 | 85.4167 | 93.8889 | 90.2083 | 86.4583 | 97.1774 | 93.3468 | 86.5591 | 92.4731 | 87.9704 | 81.6532 | 84.375 | 75.625 | 67.7778 | 70.9677 | 59.9462 | 52.0161 | 65.8333 | 52.7778 | 39.3056 | 60.5511 | 48.7903 | 31.1828
6 | 2.25 | 2 | 1.2097 | 0 | 0 | 1.5086 | 0 | 0 | 1.9489 | 0 | 0 | 2.8472 | 1.3889 | 0 | 3.4946 | 1.1425 | 0 | 5 | 2.1528 | 0.83333 | 3.0242 | 0.80645 | 0 | 3.3602 | 1.6129 | 0.47043 | 2.5 | 0.90278 | 0 | 1.9489 | 0 | 0 | 1.1111 | 0 | 0 | 2.2177 | 0 | 0
6 | 2.25 | 4 | 7.1237 | 2.8226 | 1.2097 | 10.8631 | 6.6554 | 2.4887 | 11.4247 | 6.6532 | 3.629 | 17.3611 | 11.9444 | 7.9167 | 17.6747 | 13.5753 | 7.7957 | 23.75 | 15 | 9.9306 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.5349 | 12.7778 | 8.75 | 4.6528 | 9.543 | 5.6452 | 2.5538 | 8.4028 | 4.7222 | 2.0139 | 8.7366 | 6.3172 | 1.6129
6 | 2.25 | 6 | 23.6559 | 12.5 | 7.1237 | 26.5625 | 17.6724 | 9.4494 | 28.293 | 21.707 | 12.9032 | 38.0556 | 32.2222 | 25.4861 | 41.1962 | 36.3575 | 26.8145 | 48.8889 | 38.3333 | 27.4306 | 43.75 | 36.3575 | 29.0323 | 40.9274 | 32.5269 | 26.2769 | 35.9028 | 27.2222 | 18.1944 | 24.0591 | 17.4731 | 10.8199 | 19.6528 | 14.1667 | 9.0278 | 22.2446 | 13.5081 | 6.3172
6 | 2.25 | 8 | 37.9032 | 25 | 14.5833 | 45.7589 | 36.6815 | 18.1548 | 49.7312 | 39.5161 | 27.6882 | 65.2778 | 54.8611 | 47.7083 | 66.8011 | 61.2231 | 52.2177 | 70.9722 | 65.3472 | 53.8194 | 72.6478 | 63.4409 | 52.4194 | 67.0027 | 60.2151 | 50.5376 | 57.7778 | 49.9306 | 36.1806 | 42.9435 | 34.3414 | 23.0511 | 39.4444 | 27.3611 | 19.9306 | 39.7849 | 26.6129 | 16.4651
6 | 2.25 | 9 | 43.6156 | 32.9973 | 22.2446 | 55.6317 | 47.4856 | 24.9256 | 59.2742 | 48.3871 | 36.5591 | 72.9167 | 64.4444 | 59.0278 | 77.7554 | 71.1022 | 64.2473 | 81.5972 | 77.0833 | 67.2917 | 85.1478 | 75.0672 | 66.8011 | 78.1586 | 71.5054 | 63.5753 | 68.8889 | 58.6111 | 48.75 | 49.664 | 42.3387 | 30.914 | 47.0139 | 36.0417 | 25.1389 | 47.6478 | 35.4167 | 20.2285
6 | 2.25 | 10 | 53.293 | 39.7849 | 27.957 | 62.7232 | 55.0262 | 34.4494 | 73.1183 | 57.1909 | 46.0349 | 84.0278 | 73.2639 | 67.5694 | 85.5511 | 80.3763 | 72.2446 | 89.3056 | 85.5556 | 77.5694 | 93.1452 | 86.2903 | 77.8226 | 84.6774 | 80.1747 | 71.9086 | 78.125 | 66.3889 | 59.0972 | 58.7366 | 50.9409 | 38.5753 | 56.25 | 45.0694 | 32.0139 | 55.5108 | 42.4731 | 25.5376
6 | 2.25 | 11 | 60.2151 | 44.5565 | 33.7366 | 70.8333 | 60.8015 | 38.6905 | 79.2339 | 65.9946 | 53.293 | 88.5417 | 80.9722 | 74.8611 | 92.2043 | 85.5511 | 81.25 | 93.0556 | 90.1389 | 85.2083 | 96.1694 | 91.7339 | 83.6694 | 90.121 | 86.4919 | 80.3091 | 84.3056 | 72.7778 | 66.3889 | 68.4812 | 57.5269 | 48.5887 | 61.9444 | 52.8472 | 40.1389 | 60.4839 | 48.1855 | 33.4005
6 | 2.25 | 12 | 64.7177 | 47.6478 | 37.9032 | 75.744 | 65.6994 | 44.0476 | 83.5349 | 71.4382 | 58.4677 | 92.5 | 85.5556 | 79.3056 | 94.6909 | 90.5242 | 87.3656 | 94.5833 | 92.0833 | 88.6111 | 97.9167 | 94.086 | 87.164 | 93.6828 | 90.7258 | 83.3333 | 87.1528 | 79.2361 | 71.7361 | 73.6559 | 61.2903 | 53.6962 | 69.0972 | 57.8472 | 45.1389 | 64.1801 | 52.6882 | 37.4328
6 | 2.25 | 15 | 71.0349 | 51.4785 | 42.7419 | 78.3482 | 68.006 | 47.7935 | 86.3575 | 73.5215 | 63.3737 | 94.9306 | 87.9861 | 83.4028 | 96.9086 | 93.5484 | 90.3898 | 95.6944 | 93.125 | 90.5556 | 98.7231 | 96.1022 | 89.1129 | 95.6989 | 91.9355 | 86.4247 | 89.7917 | 81.875 | 73.8194 | 77.7554 | 65.8602 | 60.5511 | 73.1944 | 62.7778 | 48.8194 | 66.9355 | 56.25 | 40.7258
6 | 2.25 | 20 | 71.0349 | 51.4785 | 42.8763 | 78.4226 | 68.006 | 47.8679 | 86.3575 | 73.7903 | 63.3737 | 94.9306 | 87.9861 | 83.4028 | 96.9086 | 93.5484 | 90.5242 | 95.7639 | 93.125 | 90.5556 | 98.7231 | 96.1022 | 89.1801 | 95.6989 | 92.0699 | 86.4247 | 90.4167 | 81.875 | 73.8889 | 77.8898 | 66.129 | 60.5511 | 73.2639 | 62.9167 | 48.9583 | 67.0027 | 56.4516 | 40.793
6 | 2.25 | 25 | 71.0349 | 51.4785 | 42.8763 | 78.4226 | 68.006 | 47.8679 | 86.3575 | 73.7903 | 63.3737 | 94.9306 | 87.9861 | 83.4028 | 96.9086 | 93.5484 | 90.5242 | 95.7639 | 93.125 | 90.5556 | 98.7231 | 96.1022 | 89.1801 | 95.6989 | 92.0699 | 86.4247 | 90.4167 | 81.875 | 73.8889 | 77.8898 | 66.129 | 60.5511 | 73.2639 | 62.9167 | 48.9583 | 67.0027 | 56.4516 | 40.793
6 | 2.5 | 2 | 1.2097 | 0 | 0 | 1.5086 | 0 | 0 | 1.9489 | 0 | 0 | 2.8472 | 1.3889 | 0 | 3.4946 | 1.1425 | 0 | 5 | 2.1528 | 0.83333 | 3.0242 | 0.80645 | 0 | 3.3602 | 1.6129 | 0.47043 | 2.5 | 0.90278 | 0 | 1.9489 | 0 | 0 | 1.1111 | 0 | 0 | 2.2177 | 0 | 0
6 | 2.5 | 4 | 7.1237 | 2.8226 | 1.2097 | 10.8631 | 6.953 | 2.4887 | 11.4247 | 6.6532 | 3.629 | 17.3611 | 11.9444 | 7.9167 | 17.6747 | 13.5753 | 7.7957 | 23.75 | 15 | 9.9306 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.5349 | 12.7778 | 8.75 | 4.6528 | 9.543 | 5.6452 | 2.5538 | 8.4028 | 4.7222 | 2.0139 | 8.7366 | 6.3172 | 1.8145
6 | 2.5 | 6 | 24.1263 | 12.5672 | 7.1237 | 26.5625 | 17.6724 | 9.8958 | 28.293 | 21.707 | 12.9032 | 38.0556 | 32.9167 | 25.4861 | 41.1962 | 36.6263 | 26.8145 | 48.8889 | 38.3333 | 27.4306 | 43.75 | 36.3575 | 29.0323 | 40.9274 | 32.5269 | 26.2769 | 35.9028 | 27.2222 | 18.1944 | 24.1935 | 17.6747 | 10.8199 | 19.6528 | 14.9306 | 9.1667 | 22.379 | 13.5753 | 6.3172
6 | 2.5 | 8 | 37.9032 | 25.8065 | 15.0538 | 45.9077 | 37.3589 | 18.3036 | 50.1344 | 39.5161 | 28.6962 | 65.2778 | 55.4167 | 47.8472 | 66.8011 | 61.2231 | 52.2177 | 71.0417 | 65.3472 | 53.8194 | 72.6478 | 63.4409 | 52.4194 | 67.1371 | 60.2151 | 50.5376 | 57.7778 | 49.9306 | 36.4583 | 43.078 | 34.7446 | 23.7903 | 39.5139 | 27.9861 | 20.4861 | 41.129 | 27.2849 | 17.0699
6 | 2.5 | 9 | 45.2957 | 34.0955 | 23.0511 | 56.5476 | 48.9737 | 25.6696 | 60.2151 | 49.1263 | 37.7016 | 73.1944 | 65.2778 | 59.375 | 78.1586 | 71.4382 | 64.2473 | 81.5972 | 77.2222 | 67.2917 | 85.5511 | 75.0672 | 66.8683 | 78.2258 | 71.5054 | 63.6425 | 69.0278 | 59.0278 | 49.3056 | 50.4704 | 43.2796 | 32.5941 | 47.5 | 36.6667 | 25.7639 | 48.3199 | 36.2231 | 21.5726
6 | 2.5 | 10 | 54.6371 | 40.8602 | 29.9731 | 63.6058 | 56.1859 | 34.8958 | 73.8575 | 57.8629 | 47.5806 | 84.2361 | 75.0694 | 68.75 | 85.5511 | 80.7796 | 73.0511 | 89.7222 | 85.7639 | 77.7083 | 93.3468 | 86.3575 | 78.0242 | 84.879 | 80.3091 | 72.1102 | 78.4722 | 66.875 | 60 | 59.7446 | 51.6129 | 39.6505 | 57.7778 | 46.875 | 32.7778 | 57.2581 | 43.6828 | 27.2849
6 | 2.5 | 11 | 61.6935 | 48.2527 | 35.6183 | 71.9494 | 63.6905 | 41.1458 | 80.1075 | 67.5403 | 55.914 | 88.9583 | 82.7778 | 76.25 | 92.5403 | 86.6935 | 81.7876 | 93.6111 | 90.7639 | 86.0417 | 96.8414 | 92.4059 | 84.4758 | 91.129 | 87.5 | 80.914 | 85.4167 | 74.3056 | 67.9861 | 70.2957 | 59.0726 | 50.336 | 63.6806 | 55.1389 | 42.0833 | 62.4328 | 50.8065 | 39.2473
6 | 2.5 | 12 | 68.75 | 52.957 | 41.4651 | 78.7946 | 68.9424 | 48.4375 | 85.4839 | 73.9247 | 62.0296 | 93.125 | 87.4306 | 82.9861 | 95.3629 | 91.7339 | 88.7769 | 95.6944 | 93.2639 | 90 | 99.0591 | 95.8333 | 88.4409 | 96.2366 | 92.0699 | 85.8199 | 89.1667 | 81.7361 | 75 | 75.4032 | 63.3737 | 57.7957 | 71.6667 | 62.3611 | 47.7083 | 67.3387 | 57.1237 | 43.6828
6 | 2.5 | 15 | 78.8306 | 62.164 | 47.7823 | 83.8644 | 73.5863 | 54.7183 | 90.2554 | 77.4866 | 69.7581 | 96.3889 | 91.4583 | 87.9167 | 98.3871 | 96.0349 | 92.9435 | 97.2222 | 95.2083 | 92.9861 | 100 | 98.1183 | 91.7339 | 98.0511 | 93.8172 | 89.3817 | 93.2639 | 87.7083 | 80.2083 | 83.9382 | 73.6559 | 66.9355 | 79.5833 | 70.3472 | 56.8056 | 73.7903 | 64.8522 | 48.5215
6 | 2.5 | 20 | 79.0995 | 62.5 | 48.3199 | 83.8644 | 73.8095 | 54.8645 | 90.2554 | 78.0242 | 69.8253 | 96.6667 | 91.5972 | 88.0556 | 98.3871 | 96.1022 | 93.3468 | 97.2222 | 95.2083 | 93.125 | 100 | 98.1855 | 91.9355 | 98.0511 | 93.8844 | 89.5161 | 93.2639 | 87.7083 | 80.4167 | 84.8118 | 73.9919 | 67.2715 | 80.0694 | 71.0417 | 57.1528 | 74.328 | 65.2554 | 48.8575
6 | 2.5 | 25 | 79.0995 | 62.5 | 48.3199 | 83.8644 | 73.8095 | 54.8645 | 90.2554 | 78.0242 | 69.8253 | 96.6667 | 91.5972 | 88.0556 | 98.3871 | 96.1022 | 93.3468 | 97.2222 | 95.2083 | 93.125 | 100 | 98.1855 | 91.9355 | 98.0511 | 93.8844 | 89.5161 | 93.2639 | 87.7083 | 80.4167 | 84.8118 | 73.9919 | 67.2715 | 80.0694 | 71.0417 | 57.1528 | 74.328 | 65.2554 | 48.8575
6 | 2.75 | 2 | 1.2097 | 0 | 0 | 1.5086 | 0 | 0 | 1.9489 | 0 | 0 | 2.8472 | 1.3889 | 0 | 3.4946 | 1.1425 | 0 | 5 | 2.1528 | 0.83333 | 3.0242 | 0.80645 | 0 | 3.3602 | 1.6129 | 0.47043 | 2.5 | 0.90278 | 0 | 1.9489 | 0 | 0 | 1.1111 | 0 | 0 | 2.2177 | 0 | 0
6 | 2.75 | 4 | 7.1237 | 2.8226 | 1.2097 | 11.0376 | 6.953 | 2.4887 | 11.4247 | 6.6532 | 3.629 | 17.3611 | 11.9444 | 7.9167 | 18.0108 | 13.5753 | 7.7957 | 23.75 | 15 | 9.9306 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.5349 | 12.7778 | 8.75 | 4.6528 | 9.543 | 5.6452 | 2.5538 | 8.4028 | 4.7222 | 2.0139 | 8.7366 | 6.3172 | 1.8145
6 | 2.75 | 6 | 24.1263 | 12.5672 | 7.1237 | 26.5625 | 17.6724 | 9.8958 | 28.293 | 21.707 | 12.9032 | 38.0556 | 32.9167 | 25.4861 | 41.1962 | 36.6263 | 26.8145 | 48.8889 | 38.3333 | 27.4306 | 43.75 | 36.3575 | 29.0323 | 40.9274 | 32.5269 | 26.2769 | 35.9028 | 27.2222 | 18.1944 | 24.1935 | 17.8091 | 10.8199 | 19.6528 | 15 | 9.3056 | 22.379 | 13.5753 | 6.8548
6 | 2.75 | 8 | 37.9032 | 25.8065 | 15.121 | 45.9821 | 38.0875 | 18.6756 | 50.1344 | 39.6505 | 28.8978 | 65.2778 | 55.4167 | 47.8472 | 66.8011 | 61.3575 | 52.2177 | 71.0417 | 65.3472 | 53.8194 | 72.6478 | 63.4409 | 52.4194 | 67.1371 | 60.2151 | 50.5376 | 57.7778 | 49.9306 | 36.5278 | 43.078 | 34.7446 | 23.9247 | 39.8611 | 28.3333 | 20.5556 | 41.3306 | 27.2849 | 17.6075
6 | 2.75 | 9 | 45.2957 | 34.7684 | 23.6559 | 56.8452 | 49.1918 | 26.4881 | 60.2823 | 49.1263 | 37.9704 | 73.1944 | 65.7639 | 59.9306 | 78.1586 | 71.4382 | 64.2473 | 81.5972 | 77.2222 | 67.2917 | 85.5511 | 75.0672 | 66.8683 | 78.2258 | 71.5054 | 63.6425 | 69.0278 | 59.4444 | 49.7222 | 51.1425 | 43.9516 | 33.3333 | 47.6389 | 37.2222 | 27.0139 | 48.8575 | 36.2903 | 23.3871
6 | 2.75 | 10 | 55.1075 | 41.4651 | 30.914 | 64.8065 | 56.994 | 35.7143 | 74.1263 | 58.4677 | 48.0511 | 84.3056 | 75.9028 | 69.7222 | 86.0215 | 81.0484 | 73.3871 | 89.7222 | 85.8333 | 77.7083 | 93.3468 | 86.3575 | 78.0242 | 84.879 | 80.3091 | 72.1102 | 78.4722 | 66.9444 | 61.5972 | 59.8118 | 52.4866 | 40.3898 | 59.0972 | 48.1944 | 34.4444 | 57.7957 | 44.0188 | 30.3091
6 | 2.75 | 11 | 63.3737 | 50.4704 | 37.836 | 72.619 | 64.904 | 44.8661 | 81.5188 | 67.9435 | 56.1828 | 89.7917 | 83.8194 | 77.2917 | 92.6075 | 86.8952 | 82.1237 | 94.0278 | 90.9722 | 86.3194 | 96.9758 | 92.4059 | 84.9462 | 91.1962 | 87.9704 | 81.3172 | 85.5556 | 75.0694 | 69.5139 | 71.1022 | 59.6774 | 50.672 | 67.8472 | 56.5972 | 44.3056 | 63.4409 | 51.4113 | 41.129
6 | 2.75 | 12 | 71.9758 | 55.9812 | 44.4892 | 81.1756 | 69.8661 | 54.3899 | 86.8952 | 75.336 | 64.5833 | 93.125 | 89.5833 | 84.4444 | 96.1694 | 92.1371 | 89.3817 | 97.0139 | 94.2361 | 90.9028 | 99.1935 | 96.8414 | 89.3817 | 97.2446 | 92.5403 | 86.4919 | 90.4167 | 83.0556 | 77.5694 | 76.9489 | 64.3145 | 59.0054 | 74.2361 | 64.4444 | 50.5556 | 69.8253 | 59.4086 | 46.3038
6 | 2.75 | 15 | 82.3925 | 67.6747 | 52.7554 | 86.2556 | 79.0179 | 62.5744 | 93.3468 | 82.1909 | 75.336 | 98.125 | 94.375 | 91.1806 | 99.2608 | 97.7823 | 95.3629 | 98.75 | 96.8056 | 94.7222 | 100 | 98.9919 | 94.4892 | 99.328 | 95.9677 | 92.1371 | 95 | 90.4167 | 83.6111 | 89.1129 | 78.4274 | 72.1774 | 83.6111 | 75.625 | 62.1528 | 78.4946 | 71.5726 | 56.7876
6 | 2.75 | 20 | 82.8629 | 67.9435 | 53.4274 | 86.4737 | 79.2385 | 62.8669 | 94.1532 | 82.8629 | 75.8065 | 98.3333 | 94.6528 | 91.5278 | 99.3952 | 97.9167 | 95.5645 | 98.75 | 96.875 | 94.8611 | 100 | 98.9919 | 94.5565 | 99.328 | 96.2366 | 92.3387 | 95.5556 | 90.6944 | 84.0278 | 90.6586 | 79.1667 | 72.9839 | 83.9583 | 77.0833 | 63.4722 | 79.7715 | 71.8414 | 57.5269
6 | 2.75 | 25 | 82.8629 | 67.9435 | 53.4274 | 86.4737 | 79.2385 | 62.8669 | 94.1532 | 82.8629 | 75.8065 | 98.3333 | 94.6528 | 91.5278 | 99.3952 | 97.9167 | 95.5645 | 98.75 | 96.875 | 94.8611 | 100 | 98.9919 | 94.5565 | 99.328 | 96.2366 | 92.3387 | 95.5556 | 90.6944 | 84.0278 | 90.6586 | 79.1667 | 72.9839 | 83.9583 | 77.0833 | 63.4722 | 79.7715 | 71.8414 | 57.5269
6 | 3 | 2 | 1.2097 | 0 | 0 | 1.5086 | 0 | 0 | 1.9489 | 0 | 0 | 2.8472 | 1.3889 | 0 | 3.4946 | 1.1425 | 0 | 5 | 2.1528 | 0.83333 | 3.0242 | 0.80645 | 0 | 3.3602 | 1.6129 | 0.47043 | 2.5 | 0.90278 | 0 | 1.9489 | 0 | 0 | 1.1111 | 0 | 0 | 2.2177 | 0 | 0
6 | 3 | 4 | 7.1237 | 2.8226 | 1.2097 | 11.0376 | 6.953 | 2.4887 | 11.4247 | 6.6532 | 3.629 | 17.3611 | 11.9444 | 7.9167 | 18.0108 | 13.5753 | 7.7957 | 23.75 | 15 | 9.9306 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.5349 | 12.7778 | 8.75 | 4.6528 | 9.543 | 5.6452 | 2.5538 | 8.4028 | 4.7222 | 2.0139 | 8.9382 | 6.3172 | 1.8145
6 | 3 | 6 | 24.1263 | 12.5672 | 7.1237 | 26.5625 | 17.6724 | 9.8958 | 28.293 | 21.707 | 12.9032 | 38.0556 | 32.9167 | 25.4861 | 41.1962 | 36.6263 | 26.8145 | 48.8889 | 38.3333 | 27.4306 | 43.75 | 36.3575 | 29.0323 | 40.9274 | 32.5269 | 26.2769 | 35.9028 | 27.2222 | 18.1944 | 24.1935 | 17.8091 | 10.8199 | 19.6528 | 15 | 9.3056 | 22.379 | 13.5753 | 6.8548
6 | 3 | 8 | 37.9032 | 25.8065 | 15.6586 | 45.9821 | 38.1619 | 18.6756 | 50.1344 | 39.6505 | 29.0323 | 65.2778 | 55.4167 | 47.8472 | 66.8011 | 61.6935 | 52.2177 | 71.0417 | 65.3472 | 53.8194 | 72.6478 | 63.4409 | 52.4194 | 67.1371 | 60.2151 | 50.5376 | 57.7778 | 49.9306 | 36.7361 | 43.078 | 34.7446 | 24.3952 | 39.8611 | 28.75 | 20.625 | 41.3978 | 27.2849 | 17.8763
6 | 3 | 9 | 45.2957 | 34.9462 | 23.7903 | 56.8452 | 49.3406 | 26.5625 | 60.2823 | 49.1263 | 38.172 | 73.1944 | 66.0417 | 60 | 78.629 | 71.4382 | 64.2473 | 81.5972 | 77.2222 | 67.2917 | 85.5511 | 75.0672 | 66.8683 | 78.2258 | 71.5054 | 63.6425 | 69.0278 | 59.4444 | 49.8611 | 51.2097 | 43.9516 | 34.2742 | 48.1944 | 37.5 | 27.2917 | 49.0591 | 36.2903 | 23.8575
6 | 3 | 10 | 55.3091 | 42.3001 | 31.5188 | 65.6994 | 57.0685 | 36.4583 | 74.1935 | 58.5349 | 48.3871 | 84.3056 | 76.0417 | 70 | 86.2903 | 81.0484 | 73.4543 | 89.7222 | 85.8333 | 77.7083 | 93.3468 | 86.3575 | 78.0242 | 84.879 | 80.3091 | 72.1102 | 78.4722 | 66.9444 | 61.6667 | 59.879 | 52.621 | 41.3306 | 59.0972 | 49.9306 | 35 | 58.4005 | 44.4892 | 30.9812
6 | 3 | 11 | 64.1129 | 50.5376 | 38.8441 | 73.027 | 66.0175 | 47.0982 | 82.1909 | 68.078 | 56.3844 | 90.5556 | 84.1667 | 77.4306 | 93.0108 | 87.2312 | 82.2581 | 94.0972 | 91.0417 | 86.5278 | 96.9758 | 92.4059 | 85.0806 | 91.2634 | 88.1048 | 81.7876 | 85.5556 | 75.2778 | 70.1389 | 71.8414 | 60.3495 | 51.8817 | 69.0972 | 58.8889 | 44.9306 | 65.3226 | 51.6801 | 41.6667
6 | 3 | 12 | 74.0591 | 57.5269 | 45.7661 | 81.622 | 70.6845 | 57.2173 | 87.7016 | 75.5376 | 65.3898 | 93.8194 | 90.625 | 84.5139 | 96.1694 | 92.4731 | 89.7177 | 97.2917 | 94.6528 | 91.1806 | 99.1935 | 96.8414 | 90.0538 | 97.2446 | 92.8763 | 86.6263 | 90.9722 | 83.5417 | 78.8889 | 77.2849 | 66.3306 | 61.3575 | 75.625 | 66.7361 | 51.5972 | 71.5054 | 61.4247 | 48.1183
6 | 3 | 15 | 85.7527 | 72.4462 | 57.0565 | 88.9881 | 82.8869 | 68.4165 | 94.9597 | 86.1559 | 78.4946 | 98.4028 | 96.0417 | 92.7778 | 100 | 98.4543 | 96.707 | 99.7917 | 97.7778 | 95.6944 | 100 | 99.9328 | 96.3038 | 99.664 | 97.9839 | 93.5484 | 96.6667 | 92.0139 | 85.625 | 91.5995 | 81.7876 | 77.1505 | 87.7778 | 79.4444 | 67.2917 | 82.0565 | 75.6048 | 62.4328
6 | 3 | 20 | 86.6263 | 73.5887 | 58.8038 | 89.5833 | 84.5084 | 69.6531 | 96.1022 | 87.3656 | 79.4355 | 99.0278 | 96.1806 | 93.6111 | 100 | 99.1935 | 97.1774 | 99.8611 | 97.9861 | 95.7639 | 100 | 100 | 96.4382 | 99.7984 | 97.9839 | 93.8844 | 96.9444 | 92.6389 | 86.4583 | 93.2796 | 84.3414 | 78.7634 | 89.0278 | 81.9444 | 68.9583 | 84.0054 | 77.0161 | 64.2473
6 | 3 | 25 | 86.6263 | 73.5887 | 58.8038 | 89.5833 | 84.5084 | 69.6531 | 96.1022 | 87.3656 | 79.4355 | 99.0278 | 96.1806 | 93.6111 | 100 | 99.1935 | 97.1774 | 99.8611 | 97.9861 | 95.7639 | 100 | 100 | 96.4382 | 99.7984 | 97.9839 | 93.8844 | 96.9444 | 92.6389 | 86.4583 | 93.2796 | 84.3414 | 78.7634 | 89.0278 | 81.9444 | 68.9583 | 84.0054 | 77.0161 | 64.2473
6 | 3.25 | 2 | 1.2097 | 0 | 0 | 1.5086 | 0 | 0 | 1.9489 | 0 | 0 | 2.8472 | 1.3889 | 0 | 3.4946 | 1.1425 | 0 | 5 | 2.1528 | 0.83333 | 3.0242 | 0.80645 | 0 | 3.3602 | 1.6129 | 0.47043 | 2.5 | 0.90278 | 0 | 1.9489 | 0 | 0 | 1.1111 | 0 | 0 | 2.2177 | 0 | 0
6 | 3.25 | 4 | 7.1237 | 2.8226 | 1.2097 | 11.0863 | 6.953 | 2.4887 | 11.4247 | 6.6532 | 3.629 | 17.3611 | 11.9444 | 7.9167 | 18.0108 | 13.5753 | 7.7957 | 23.75 | 15 | 9.9306 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.5349 | 12.7778 | 8.75 | 4.6528 | 9.543 | 5.6452 | 2.5538 | 8.4028 | 4.7222 | 2.0139 | 8.9382 | 6.3172 | 1.8145
6 | 3.25 | 6 | 24.1263 | 12.9032 | 7.1237 | 26.5625 | 17.6724 | 9.8958 | 28.293 | 21.707 | 13.3065 | 38.0556 | 32.9167 | 25.4861 | 41.1962 | 36.6263 | 26.8145 | 48.8889 | 38.3333 | 27.4306 | 43.75 | 36.3575 | 29.0323 | 40.9274 | 32.5269 | 26.2769 | 35.9028 | 27.2222 | 18.1944 | 24.1935 | 17.8091 | 10.8199 | 19.6528 | 15 | 9.3056 | 22.379 | 13.5753 | 6.8548
6 | 3.25 | 8 | 37.9032 | 25.8065 | 15.793 | 45.9821 | 38.1619 | 18.6756 | 50.1344 | 39.6505 | 29.4355 | 65.2778 | 55.4167 | 47.8472 | 66.8011 | 61.7608 | 52.2177 | 71.0417 | 65.3472 | 53.8194 | 72.6478 | 63.4409 | 52.4194 | 67.1371 | 60.2151 | 50.5376 | 57.7778 | 49.9306 | 36.7361 | 43.078 | 34.7446 | 24.3952 | 39.8611 | 28.8194 | 20.625 | 41.6667 | 27.3522 | 18.078
6 | 3.25 | 9 | 45.2957 | 34.9462 | 23.7903 | 56.8452 | 49.8435 | 26.5625 | 60.2823 | 49.1263 | 38.5753 | 73.1944 | 66.25 | 60.0694 | 78.629 | 71.4382 | 64.2473 | 81.5972 | 77.2222 | 67.2917 | 85.5511 | 75.0672 | 66.8683 | 78.2258 | 71.5054 | 63.6425 | 69.0278 | 59.4444 | 50 | 51.2097 | 44.2204 | 34.2742 | 48.2639 | 37.5 | 27.4306 | 49.664 | 36.2903 | 24.5968
6 | 3.25 | 10 | 55.3763 | 42.6747 | 31.9892 | 65.6994 | 57.4405 | 36.5327 | 74.1935 | 58.5349 | 49.1935 | 84.3056 | 76.0417 | 70.0694 | 86.2903 | 81.0484 | 73.4543 | 89.7222 | 85.8333 | 77.7083 | 93.3468 | 86.3575 | 78.0242 | 85.2151 | 80.3091 | 72.1102 | 78.4722 | 66.9444 | 61.7361 | 59.9462 | 53.0914 | 41.7339 | 59.5139 | 50.4861 | 35.0694 | 58.7366 | 45.0941 | 31.7876
6 | 3.25 | 11 | 64.5833 | 51.2097 | 39.9194 | 74.4048 | 66.2356 | 47.3214 | 82.3925 | 68.2124 | 56.586 | 90.625 | 84.4444 | 77.5694 | 93.0108 | 87.5 | 82.2581 | 94.1667 | 91.0417 | 86.5278 | 96.9758 | 92.4059 | 85.0806 | 91.2634 | 88.1048 | 82.0565 | 85.5556 | 75.4861 | 70.2778 | 72.1774 | 60.3495 | 52.6882 | 69.4444 | 60.3472 | 45.3472 | 66.2634 | 52.2849 | 42.2715
6 | 3.25 | 12 | 74.5968 | 58.1989 | 47.4462 | 82.1429 | 70.9821 | 58.4821 | 87.9032 | 75.8065 | 66.3978 | 94.0972 | 91.3889 | 85.1389 | 96.1694 | 92.7419 | 89.7849 | 97.3611 | 94.6528 | 91.4583 | 99.1935 | 96.8414 | 90.5242 | 97.2446 | 93.078 | 86.9624 | 91.1806 | 83.5417 | 79.0972 | 77.4194 | 67.0699 | 62.9032 | 75.9722 | 68.4722 | 52.1528 | 72.1102 | 62.0296 | 49.4624
6 | 3.25 | 15 | 88.7097 | 75.336 | 63.9785 | 91.1458 | 86.1607 | 72.0238 | 95.6317 | 88.3065 | 80.9812 | 98.9583 | 97.1528 | 94.0278 | 100 | 99.0591 | 97.9167 | 100 | 98.8889 | 96.25 | 100 | 100 | 96.8414 | 100 | 98.9919 | 95.0941 | 96.875 | 93.8889 | 89.2361 | 93.8172 | 85.0806 | 79.8387 | 90 | 83.4722 | 71.3194 | 84.207 | 79.8387 | 66.4651
6 | 3.25 | 20 | 90.7258 | 78.8306 | 67.0699 | 92.1875 | 88.1696 | 75.9929 | 97.5806 | 91.3978 | 82.3253 | 99.7917 | 97.4306 | 95.0694 | 100 | 99.9328 | 98.0511 | 100 | 99.1667 | 96.3889 | 100 | 100 | 97.1774 | 100 | 99.328 | 95.6317 | 97.8472 | 94.7917 | 90.7639 | 96.1694 | 87.164 | 83.8038 | 92.3611 | 86.5278 | 75.4861 | 87.0968 | 82.4597 | 69.2204
6 | 3.25 | 25 | 90.7258 | 78.8306 | 67.0699 | 92.1875 | 88.1696 | 76.0673 | 97.5806 | 91.3978 | 82.3253 | 99.7917 | 97.4306 | 95.0694 | 100 | 99.9328 | 98.0511 | 100 | 99.1667 | 96.3889 | 100 | 100 | 97.1774 | 100 | 99.328 | 95.6317 | 97.9167 | 94.7917 | 90.8333 | 96.1694 | 87.164 | 83.8038 | 92.3611 | 86.5278 | 75.4861 | 87.0968 | 82.4597 | 69.2204
6 | 3.5 | 2 | 1.2097 | 0 | 0 | 1.5086 | 0 | 0 | 1.9489 | 0 | 0 | 2.8472 | 1.3889 | 0 | 3.4946 | 1.1425 | 0 | 5 | 2.1528 | 0.83333 | 3.0242 | 0.80645 | 0 | 3.3602 | 1.6129 | 0.47043 | 2.5 | 0.90278 | 0 | 1.9489 | 0 | 0 | 1.1111 | 0 | 0 | 2.2177 | 0 | 0
6 | 3.5 | 4 | 7.1237 | 2.8226 | 1.2097 | 11.0863 | 6.953 | 2.4887 | 11.4247 | 6.6532 | 3.629 | 17.3611 | 11.9444 | 7.9167 | 18.0108 | 13.5753 | 7.7957 | 23.75 | 15 | 9.9306 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.5349 | 12.7778 | 8.75 | 4.6528 | 9.543 | 5.6452 | 2.5538 | 8.4028 | 4.7222 | 2.0139 | 8.9382 | 6.3172 | 1.8145
6 | 3.5 | 6 | 24.1263 | 12.9032 | 7.1237 | 26.5625 | 17.6724 | 9.8958 | 28.293 | 21.707 | 13.3065 | 38.0556 | 32.9167 | 25.4861 | 41.1962 | 36.6263 | 26.8145 | 48.8889 | 38.3333 | 27.4306 | 43.75 | 36.3575 | 29.0323 | 40.9274 | 32.5269 | 26.2769 | 35.9028 | 27.2222 | 18.1944 | 24.1935 | 17.8091 | 10.8199 | 19.6528 | 15 | 9.3056 | 22.379 | 13.5753 | 6.8548
6 | 3.5 | 8 | 37.9032 | 25.8065 | 15.9946 | 45.9821 | 38.1619 | 18.6756 | 50.1344 | 39.6505 | 29.4355 | 65.2778 | 55.4167 | 47.8472 | 66.8011 | 61.7608 | 52.2177 | 71.0417 | 65.3472 | 53.8194 | 72.6478 | 63.4409 | 52.4194 | 67.1371 | 60.2151 | 50.5376 | 57.7778 | 49.9306 | 36.7361 | 43.078 | 34.7446 | 24.3952 | 39.8611 | 28.8889 | 20.625 | 41.6667 | 27.3522 | 18.078
6 | 3.5 | 9 | 45.2957 | 34.9462 | 23.7903 | 56.8452 | 49.8435 | 27.0089 | 60.2823 | 49.1263 | 38.5753 | 73.1944 | 66.25 | 60.0694 | 78.629 | 71.6398 | 64.2473 | 81.5972 | 77.2222 | 67.2917 | 85.5511 | 75.0672 | 66.8683 | 78.2258 | 71.5054 | 63.6425 | 69.0278 | 59.4444 | 50 | 51.2097 | 44.2204 | 34.2742 | 48.2639 | 37.5694 | 27.4306 | 49.7312 | 36.2903 | 24.7984
6 | 3.5 | 10 | 55.3763 | 42.9056 | 31.9892 | 65.6994 | 57.4405 | 36.9792 | 74.1935 | 58.5349 | 49.1935 | 84.7917 | 76.0417 | 70.0694 | 86.2903 | 81.0484 | 73.4543 | 89.7222 | 85.8333 | 77.7083 | 93.3468 | 86.3575 | 78.0242 | 85.2823 | 80.3091 | 72.1102 | 78.4722 | 66.9444 | 61.7361 | 60.0134 | 53.0914 | 41.8683 | 59.5833 | 50.6944 | 35.1389 | 59.0054 | 45.0941 | 31.9892
6 | 3.5 | 11 | 65.5242 | 51.2097 | 41.129 | 74.628 | 66.2356 | 47.8423 | 82.3925 | 68.2124 | 57.0565 | 90.625 | 84.4444 | 77.9861 | 93.0108 | 87.6344 | 82.2581 | 94.2361 | 91.0417 | 86.5278 | 96.9758 | 92.4059 | 85.0806 | 91.4651 | 88.1048 | 82.0565 | 85.5556 | 75.4861 | 70.2778 | 72.1774 | 60.8871 | 53.3602 | 70.1389 | 60.8333 | 45.625 | 66.5995 | 52.3522 | 42.4059
6 | 3.5 | 12 | 74.5968 | 58.4005 | 48.7903 | 82.1685 | 70.9924 | 59.0774 | 87.9704 | 76.6801 | 66.6667 | 94.375 | 91.875 | 85.2778 | 96.2366 | 92.7419 | 89.7849 | 97.7083 | 94.6528 | 91.5972 | 99.1935 | 96.8414 | 90.5914 | 97.2446 | 93.078 | 87.0296 | 91.3194 | 83.5417 | 79.0972 | 78.293 | 67.8091 | 63.2392 | 76.25 | 69.3056 | 52.9167 | 72.9839 | 62.164 | 50.2016
6 | 3.5 | 15 | 89.4489 | 76.6129 | 67.9435 | 92.2619 | 86.8304 | 75.9313 | 97.9839 | 90.8602 | 82.2581 | 99.5833 | 97.5694 | 94.6528 | 100 | 99.4624 | 98.3199 | 100 | 99.3056 | 97.0139 | 100 | 100 | 97.5806 | 100 | 99.2608 | 95.8333 | 97.9167 | 94.8611 | 90.1389 | 94.6909 | 86.828 | 82.4597 | 91.25 | 85.4167 | 75.1389 | 86.0887 | 81.4516 | 69.422
6 | 3.5 | 20 | 92.6075 | 84.0054 | 72.7823 | 94.7917 | 90.643 | 81.6451 | 98.9247 | 93.4812 | 84.8118 | 100 | 99.0972 | 95.6944 | 100 | 100 | 98.8575 | 100 | 99.5139 | 97.2917 | 100 | 100 | 98.0511 | 100 | 100 | 97.4462 | 98.8889 | 96.3194 | 92.5694 | 98.3871 | 91.0618 | 87.5 | 94.5833 | 89.0278 | 80.0694 | 89.7849 | 86.6263 | 74.664
6 | 3.5 | 25 | 92.6075 | 84.0054 | 72.7823 | 94.7917 | 90.643 | 81.6451 | 98.9247 | 93.5484 | 84.8118 | 100 | 99.0972 | 95.6944 | 100 | 100 | 98.8575 | 100 | 99.5139 | 97.2917 | 100 | 100 | 98.0511 | 100 | 100 | 97.4462 | 98.8889 | 96.3194 | 92.6389 | 98.3871 | 91.0618 | 87.5 | 94.5833 | 89.0972 | 80.1389 | 89.7849 | 86.6263 | 74.664
6 | 3.75 | 2 | 1.2097 | 0 | 0 | 1.5086 | 0 | 0 | 1.9489 | 0 | 0 | 2.8472 | 1.3889 | 0 | 3.4946 | 1.1425 | 0 | 5 | 2.1528 | 0.83333 | 3.0242 | 0.80645 | 0 | 3.3602 | 1.6129 | 0.47043 | 2.5 | 0.90278 | 0 | 1.9489 | 0 | 0 | 1.1111 | 0 | 0 | 2.2177 | 0 | 0
6 | 3.75 | 4 | 7.1237 | 2.8226 | 1.2097 | 11.0863 | 6.953 | 2.4887 | 11.4247 | 6.6532 | 3.629 | 17.3611 | 11.9444 | 7.9167 | 18.0108 | 13.5753 | 7.7957 | 23.75 | 15 | 9.9306 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.5349 | 12.7778 | 8.75 | 4.6528 | 9.543 | 5.6452 | 2.5538 | 8.4028 | 4.7222 | 2.0139 | 8.9382 | 6.3172 | 1.8145
6 | 3.75 | 6 | 24.1263 | 12.9032 | 7.1237 | 26.5625 | 17.6724 | 9.8958 | 28.293 | 21.707 | 13.3065 | 38.0556 | 32.9167 | 25.4861 | 41.1962 | 36.6263 | 26.8145 | 48.8889 | 38.3333 | 27.4306 | 43.75 | 36.3575 | 29.0323 | 40.9274 | 32.5269 | 26.2769 | 35.9028 | 27.2222 | 18.1944 | 24.1935 | 17.8091 | 10.8199 | 19.6528 | 15 | 9.3056 | 22.379 | 13.5753 | 6.8548
6 | 3.75 | 8 | 37.9032 | 25.8065 | 15.9946 | 45.9821 | 38.1619 | 18.6756 | 50.1344 | 39.6505 | 29.4355 | 65.2778 | 55.4167 | 47.8472 | 66.8011 | 61.7608 | 52.2177 | 71.0417 | 65.3472 | 53.8194 | 72.6478 | 63.4409 | 52.4194 | 67.1371 | 60.2151 | 50.5376 | 57.7778 | 49.9306 | 36.7361 | 43.078 | 34.7446 | 24.3952 | 39.8611 | 28.9583 | 20.625 | 41.6667 | 27.3522 | 18.078
6 | 3.75 | 9 | 45.2957 | 34.9462 | 23.7903 | 56.8452 | 49.8435 | 27.0833 | 60.2823 | 49.1263 | 38.5753 | 73.1944 | 66.25 | 60.0694 | 78.629 | 71.6398 | 64.2473 | 81.5972 | 77.2222 | 67.2917 | 85.5511 | 75.0672 | 66.8683 | 78.2258 | 71.5054 | 63.6425 | 69.0278 | 59.4444 | 50 | 51.2097 | 44.2204 | 34.2742 | 48.2639 | 37.6389 | 27.4306 | 49.7312 | 36.2903 | 24.9328
6 | 3.75 | 10 | 55.3763 | 42.9056 | 31.9892 | 65.7995 | 57.4405 | 37.0536 | 74.1935 | 58.5349 | 49.5968 | 84.7917 | 76.0417 | 70.0694 | 86.2903 | 81.0484 | 73.4543 | 89.7222 | 85.8333 | 77.7083 | 93.3468 | 86.3575 | 78.0242 | 85.2823 | 80.3091 | 72.1102 | 78.4722 | 66.9444 | 61.7361 | 60.0134 | 53.0914 | 41.8683 | 59.5833 | 50.7639 | 35.1389 | 59.0726 | 45.0941 | 32.2581
6 | 3.75 | 11 | 65.5242 | 51.3108 | 41.2634 | 74.628 | 66.6667 | 47.9911 | 82.3925 | 68.2124 | 57.9301 | 90.625 | 84.4444 | 77.9861 | 93.0108 | 87.6344 | 82.2581 | 94.2361 | 91.0417 | 86.5278 | 96.9758 | 92.4059 | 85.0806 | 91.5323 | 88.1048 | 82.0565 | 85.5556 | 75.4861 | 70.2778 | 72.1774 | 60.8871 | 53.4274 | 70.2778 | 60.8333 | 45.7639 | 66.7339 | 52.3522 | 42.5403
6 | 3.75 | 12 | 74.5968 | 58.6414 | 49.328 | 82.384 | 71.639 | 59.5238 | 87.9704 | 77.0161 | 67.2715 | 94.5139 | 91.875 | 85.3472 | 96.3038 | 92.7419 | 89.9194 | 97.7778 | 94.7917 | 91.6667 | 99.1935 | 96.8414 | 90.5914 | 97.2446 | 93.078 | 87.0296 | 91.3889 | 83.5417 | 79.0972 | 78.8978 | 67.8763 | 63.3737 | 77.2917 | 69.9306 | 53.0556 | 73.5887 | 62.2984 | 50.2688
6 | 3.75 | 15 | 89.7849 | 78.629 | 70.9005 | 92.5595 | 87.6488 | 77.8376 | 97.9839 | 92.0027 | 83.6694 | 99.7917 | 97.9167 | 95.0694 | 100 | 99.7312 | 98.5215 | 100 | 99.3056 | 97.4306 | 100 | 100 | 97.8495 | 100 | 99.4624 | 96.1694 | 98.5417 | 95.5556 | 91.0417 | 94.8253 | 87.7688 | 83.1989 | 92.1528 | 86.5972 | 77.0833 | 87.6344 | 82.6613 | 71.7742
6 | 3.75 | 20 | 93.8844 | 88.0376 | 79.3011 | 96.5774 | 92.3209 | 85.3423 | 99.5296 | 95.9005 | 87.2984 | 100 | 99.4444 | 96.4583 | 100 | 100 | 99.5968 | 100 | 100 | 97.9861 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.5 | 93.8889 | 99.4624 | 93.414 | 90.457 | 96.6667 | 91.4583 | 84.5833 | 92.7419 | 88.6425 | 79.4355
6 | 3.75 | 25 | 93.8844 | 88.0376 | 79.3011 | 96.5774 | 92.3209 | 85.4167 | 99.5296 | 95.9005 | 87.2984 | 100 | 99.5139 | 96.4583 | 100 | 100 | 99.5968 | 100 | 100 | 97.9861 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.5 | 93.8889 | 99.4624 | 93.414 | 90.457 | 96.6667 | 91.5972 | 84.5833 | 92.7419 | 88.6425 | 79.4355
6 | 4 | 2 | 1.2097 | 0 | 0 | 1.5086 | 0 | 0 | 1.9489 | 0 | 0 | 2.8472 | 1.3889 | 0 | 3.4946 | 1.1425 | 0 | 5 | 2.1528 | 0.83333 | 3.0242 | 0.80645 | 0 | 3.3602 | 1.6129 | 0.47043 | 2.5 | 0.90278 | 0 | 1.9489 | 0 | 0 | 1.1111 | 0 | 0 | 2.2177 | 0 | 0
6 | 4 | 4 | 7.1237 | 2.8226 | 1.2097 | 11.0863 | 6.953 | 2.4887 | 11.4247 | 6.6532 | 3.629 | 17.3611 | 11.9444 | 7.9167 | 18.0108 | 13.5753 | 7.7957 | 23.75 | 15 | 9.9306 | 19.2876 | 14.0457 | 8.5349 | 18.8844 | 12.7688 | 8.5349 | 12.7778 | 8.75 | 4.6528 | 9.543 | 5.6452 | 2.5538 | 8.4028 | 4.7222 | 2.0139 | 8.9382 | 6.3172 | 1.8145
6 | 4 | 6 | 24.1263 | 12.9032 | 7.1237 | 26.5625 | 17.6724 | 9.8958 | 28.293 | 21.707 | 13.3065 | 38.0556 | 32.9167 | 25.4861 | 41.1962 | 36.6263 | 26.8145 | 48.8889 | 38.3333 | 27.4306 | 43.75 | 36.3575 | 29.0323 | 40.9274 | 32.5269 | 26.2769 | 35.9028 | 27.2222 | 18.1944 | 24.1935 | 17.8091 | 10.8199 | 19.6528 | 15 | 9.3056 | 22.379 | 13.5753 | 6.8548
6 | 4 | 8 | 37.9032 | 25.8065 | 15.9946 | 45.9821 | 38.1619 | 18.6756 | 50.1344 | 39.6505 | 29.4355 | 65.2778 | 55.4167 | 47.8472 | 66.8011 | 61.7608 | 52.2177 | 71.0417 | 65.3472 | 53.8194 | 72.6478 | 63.4409 | 52.4194 | 67.1371 | 60.2151 | 50.5376 | 57.7778 | 49.9306 | 36.7361 | 43.078 | 34.7446 | 24.3952 | 39.8611 | 28.9583 | 20.625 | 41.6667 | 27.3522 | 18.078
6 | 4 | 9 | 45.2957 | 34.9462 | 23.7903 | 56.8452 | 49.8435 | 27.0833 | 60.2823 | 49.1263 | 38.5753 | 73.1944 | 66.25 | 60.0694 | 78.629 | 71.6398 | 64.2473 | 81.5972 | 77.2222 | 67.2917 | 85.5511 | 75.0672 | 66.8683 | 78.2258 | 71.5054 | 63.6425 | 69.0278 | 59.4444 | 50 | 51.2097 | 44.2204 | 34.2742 | 48.2639 | 37.6389 | 27.4306 | 49.7312 | 36.2903 | 24.9328
6 | 4 | 10 | 55.3763 | 42.9056 | 31.9892 | 65.7995 | 57.4405 | 37.0536 | 74.1935 | 58.5349 | 49.5968 | 84.7917 | 76.0417 | 70.4861 | 86.2903 | 81.0484 | 73.4543 | 89.7222 | 85.8333 | 77.7083 | 93.3468 | 86.3575 | 78.0242 | 85.2823 | 80.3091 | 72.1102 | 78.4722 | 66.9444 | 61.7361 | 60.0134 | 53.0914 | 41.8683 | 59.5833 | 50.7639 | 35.1389 | 59.0726 | 45.0941 | 32.3253
6 | 4 | 11 | 65.5242 | 51.3108 | 41.2634 | 74.628 | 67.1131 | 47.9911 | 82.3925 | 68.2124 | 57.9973 | 90.625 | 84.4444 | 77.9861 | 93.0108 | 87.6344 | 82.2581 | 94.2361 | 91.0417 | 86.5278 | 96.9758 | 92.4059 | 85.0806 | 91.5323 | 88.1048 | 82.0565 | 85.5556 | 75.4861 | 70.2778 | 72.1774 | 60.9543 | 53.4274 | 70.2778 | 60.8333 | 45.7639 | 66.7339 | 52.3522 | 42.5403
6 | 4 | 12 | 74.5968 | 59.3143 | 49.664 | 82.5277 | 73.0039 | 59.747 | 87.9704 | 77.5538 | 67.3387 | 94.5139 | 91.875 | 85.3472 | 96.3038 | 92.7419 | 89.9194 | 97.7778 | 94.7917 | 91.6667 | 99.1935 | 96.8414 | 90.5914 | 97.2446 | 93.078 | 87.0296 | 91.3889 | 83.5417 | 79.0972 | 78.9651 | 67.9435 | 63.5081 | 77.4306 | 70 | 53.2639 | 73.6559 | 62.3656 | 50.2688
6 | 4 | 15 | 90.3226 | 79.9731 | 72.3118 | 93.0804 | 88.3185 | 79.1564 | 98.1183 | 92.6747 | 84.1398 | 99.7917 | 98.125 | 95.625 | 100 | 99.7984 | 98.7231 | 100 | 99.3056 | 97.9167 | 100 | 100 | 98.0511 | 100 | 99.5296 | 96.5054 | 98.8194 | 95.9722 | 91.3194 | 95.0269 | 88.7097 | 83.6022 | 92.6389 | 87.8472 | 79.2361 | 88.7769 | 83.8038 | 73.5215
6 | 4 | 20 | 95.3629 | 90.9946 | 81.922 | 97.9911 | 94.1964 | 88.8213 | 99.9328 | 97.4462 | 89.7177 | 100 | 99.7917 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.4722 | 95.4861 | 99.7984 | 95.4973 | 92.8763 | 98.0556 | 94.0278 | 87.7778 | 94.8925 | 90.793 | 84.3414
6 | 4 | 25 | 95.3629 | 91.129 | 81.9892 | 97.9911 | 94.1964 | 88.8932 | 99.9328 | 97.5134 | 89.7177 | 100 | 99.8611 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.6806 | 95.8333 | 99.9328 | 95.6317 | 92.9435 | 98.0556 | 94.1667 | 87.7778 | 94.8925 | 90.793 | 84.4758
12 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 0.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80645 | 0 | 0 | 4.5139 | 0.83333 | 0 | 5.3091 | 3.4946 | 0 | 11.875 | 4.7917 | 0.83333 | 10.4839 | 3.4946 | 1.6801 | 8.0645 | 3.6962 | 0 | 2.5694 | 0 | 0 | 1.9489 | 0 | 0 | 0 | 0 | 0 | 0.80645 | 0 | 0
12 | 0.5 | 6 | 0 | 0 | 0 | 2.6042 | 0 | 0 | 3.5618 | 0 | 0 | 9.0278 | 4.8611 | 0 | 14.3817 | 8.1317 | 3.9651 | 18.1944 | 12.0139 | 3.3333 | 21.1022 | 11.0887 | 5.4435 | 17.1371 | 8.2661 | 3.8978 | 8.1944 | 3.2639 | 0 | 3.0914 | 0 | 0 | 0 | 0 | 0 | 2.2849 | 0 | 0
12 | 0.5 | 8 | 0 | 0 | 0 | 2.6042 | 0 | 0 | 4.0323 | 0 | 0 | 10.4167 | 5.6944 | 0 | 14.6505 | 9.0054 | 3.9651 | 19.8611 | 13.4722 | 4.5833 | 22.8495 | 12.836 | 6.586 | 18.1452 | 9.4086 | 4.1667 | 8.6806 | 3.8194 | 0 | 3.6962 | 0 | 0 | 0 | 0 | 0 | 2.2849 | 0 | 0
12 | 0.5 | 9 | 0 | 0 | 0 | 2.6042 | 0 | 0 | 4.0323 | 0 | 0 | 10.4167 | 5.7639 | 0 | 15.0538 | 9.4758 | 3.9651 | 19.8611 | 13.4722 | 4.5833 | 22.8495 | 12.836 | 6.922 | 18.1452 | 9.4086 | 4.1667 | 8.6806 | 3.8194 | 0 | 3.6962 | 0 | 0 | 0 | 0 | 0 | 2.2849 | 0 | 0
12 | 0.5 | 10 | 0 | 0 | 0 | 2.6042 | 0 | 0 | 4.0323 | 0 | 0 | 10.4167 | 5.7639 | 0 | 15.0538 | 9.4758 | 3.9651 | 19.8611 | 13.4722 | 4.6528 | 22.9167 | 12.836 | 6.922 | 18.1452 | 9.4086 | 4.1667 | 8.6806 | 3.8194 | 0 | 3.6962 | 0 | 0 | 0 | 0 | 0 | 2.2849 | 0 | 0
12 | 0.5 | 11 | 0 | 0 | 0 | 2.6042 | 0 | 0 | 4.0323 | 0 | 0 | 10.4167 | 5.7639 | 0 | 15.0538 | 9.4758 | 3.9651 | 19.8611 | 13.4722 | 4.6528 | 22.9167 | 12.836 | 6.922 | 18.1452 | 9.4086 | 4.1667 | 8.6806 | 3.8194 | 0 | 3.6962 | 0 | 0 | 0 | 0 | 0 | 2.2849 | 0 | 0
12 | 0.5 | 12 | 0 | 0 | 0 | 2.6042 | 0 | 0 | 4.0323 | 0 | 0 | 10.4167 | 5.7639 | 0 | 15.0538 | 9.4758 | 3.9651 | 19.8611 | 13.4722 | 4.6528 | 22.9167 | 12.836 | 6.922 | 18.1452 | 9.4086 | 4.1667 | 8.6806 | 3.8194 | 0 | 3.6962 | 0 | 0 | 0 | 0 | 0 | 2.2849 | 0 | 0
12 | 0.5 | 15 | 0 | 0 | 0 | 2.6042 | 0 | 0 | 4.0323 | 0 | 0 | 10.4167 | 5.7639 | 0 | 15.0538 | 9.4758 | 3.9651 | 19.8611 | 13.4722 | 4.6528 | 22.9167 | 12.836 | 6.922 | 18.1452 | 9.4086 | 4.1667 | 8.6806 | 3.8194 | 0 | 3.6962 | 0 | 0 | 0 | 0 | 0 | 2.2849 | 0 | 0
12 | 0.5 | 20 | 0 | 0 | 0 | 2.6042 | 0 | 0 | 4.0323 | 0 | 0 | 10.4167 | 5.7639 | 0 | 15.0538 | 9.4758 | 3.9651 | 19.8611 | 13.4722 | 4.6528 | 22.9167 | 12.836 | 6.922 | 18.1452 | 9.4086 | 4.1667 | 8.6806 | 3.8194 | 0 | 3.6962 | 0 | 0 | 0 | 0 | 0 | 2.2849 | 0 | 0
12 | 0.5 | 25 | 0 | 0 | 0 | 2.6042 | 0 | 0 | 4.0323 | 0 | 0 | 10.4167 | 5.7639 | 0 | 15.0538 | 9.4758 | 3.9651 | 19.8611 | 13.4722 | 4.6528 | 22.9167 | 12.836 | 6.922 | 18.1452 | 9.4086 | 4.1667 | 8.6806 | 3.8194 | 0 | 3.6962 | 0 | 0 | 0 | 0 | 0 | 2.2849 | 0 | 0
12 | 0.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6667 | 0 | 0 | 0 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 1.6129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 0.75 | 4 | 1.8817 | 0 | 0 | 3.6561 | 0 | 0 | 5.578 | 1.6129 | 0 | 9.7222 | 4.6528 | 0.83333 | 8.871 | 4.5699 | 0.80645 | 15.4861 | 7.9861 | 4.2361 | 13.6425 | 7.4597 | 3.293 | 12.3656 | 6.9892 | 2.8226 | 5.5556 | 2.9861 | 0 | 3.0242 | 0 | 0 | 2.4306 | 0 | 0 | 3.8306 | 0 | 0
12 | 0.75 | 6 | 6.0484 | 1.8145 | 0 | 9.7188 | 3.8716 | 0 | 12.9704 | 3.8978 | 1.7473 | 23.2639 | 14.9306 | 8.3333 | 24.3952 | 18.5484 | 11.1559 | 32.5694 | 20 | 12.4306 | 28.8978 | 22.3118 | 17.2715 | 29.2339 | 19.8253 | 12.2984 | 20.1389 | 11.1111 | 4.0972 | 8.5349 | 2.6882 | 0 | 6.0417 | 1.875 | 0 | 6.1156 | 2.6882 | 0
12 | 0.75 | 8 | 8.1317 | 2.3522 | 0 | 12.2742 | 4.8235 | 0 | 17.5403 | 6.4516 | 2.957 | 29.7917 | 22.5 | 11.5278 | 34.0054 | 25.4032 | 17.2715 | 42.7778 | 28.9583 | 20.5556 | 43.4812 | 29.7715 | 23.3199 | 40.7258 | 27.621 | 18.5484 | 26.4583 | 13.6806 | 6.9444 | 13.0376 | 4.9059 | 2.0161 | 6.7361 | 2.7083 | 0 | 7.1237 | 3.629 | 0
12 | 0.75 | 9 | 8.1317 | 2.3522 | 0 | 12.2742 | 4.8235 | 0 | 17.6747 | 6.4516 | 2.957 | 30.4861 | 23.2639 | 11.875 | 35.8871 | 26.6129 | 17.4059 | 43.2639 | 29.5833 | 20.5556 | 43.9516 | 32.2581 | 24.2608 | 41.0618 | 28.3602 | 19.3548 | 26.5972 | 13.8889 | 6.9444 | 13.0376 | 5.0403 | 2.0161 | 6.7361 | 2.7083 | 0 | 7.1237 | 3.629 | 0
12 | 0.75 | 10 | 8.1317 | 2.3522 | 0 | 12.2742 | 4.8235 | 0 | 18.2796 | 6.4516 | 2.957 | 30.9028 | 23.2639 | 11.875 | 37.0296 | 26.6801 | 17.4059 | 43.2639 | 29.7917 | 20.6944 | 44.0188 | 32.3253 | 24.328 | 41.0618 | 28.4946 | 19.3548 | 26.5972 | 13.8889 | 6.9444 | 13.0376 | 5.0403 | 2.0161 | 6.7361 | 2.7083 | 0 | 7.1237 | 3.629 | 0
12 | 0.75 | 11 | 8.1317 | 2.3522 | 0 | 12.2742 | 4.8235 | 0 | 18.2796 | 6.4516 | 2.957 | 30.9028 | 23.2639 | 11.875 | 37.0968 | 26.6801 | 17.4059 | 43.2639 | 29.7917 | 20.6944 | 44.0188 | 32.3253 | 24.328 | 41.0618 | 28.4946 | 19.3548 | 26.5972 | 13.8889 | 6.9444 | 13.0376 | 5.0403 | 2.0161 | 6.7361 | 2.7083 | 0 | 7.1237 | 3.629 | 0
12 | 0.75 | 12 | 8.1317 | 2.3522 | 0 | 12.2742 | 4.8235 | 0 | 18.2796 | 6.4516 | 2.957 | 30.9028 | 23.2639 | 11.875 | 37.0968 | 26.6801 | 17.4059 | 43.2639 | 29.7917 | 20.6944 | 44.0188 | 32.3253 | 24.328 | 41.0618 | 28.4946 | 19.4892 | 26.5972 | 13.8889 | 6.9444 | 13.0376 | 5.0403 | 2.0161 | 6.7361 | 2.7083 | 0 | 7.1237 | 3.629 | 0
12 | 0.75 | 15 | 8.1317 | 2.3522 | 0 | 12.2742 | 4.8235 | 0 | 18.2796 | 6.4516 | 2.957 | 30.9028 | 23.2639 | 11.875 | 37.0968 | 26.6801 | 17.4059 | 43.2639 | 29.7917 | 20.6944 | 44.0188 | 32.3253 | 24.328 | 41.0618 | 28.4946 | 19.4892 | 26.5972 | 13.8889 | 6.9444 | 13.0376 | 5.0403 | 2.0161 | 6.7361 | 2.7083 | 0 | 7.1237 | 3.629 | 0
12 | 0.75 | 20 | 8.1317 | 2.3522 | 0 | 12.2742 | 4.8235 | 0 | 18.2796 | 6.4516 | 2.957 | 30.9028 | 23.2639 | 11.875 | 37.0968 | 26.6801 | 17.4059 | 43.2639 | 29.7917 | 20.6944 | 44.0188 | 32.3253 | 24.328 | 41.0618 | 28.4946 | 19.4892 | 26.5972 | 13.8889 | 6.9444 | 13.0376 | 5.0403 | 2.0161 | 6.7361 | 2.7083 | 0 | 7.1237 | 3.629 | 0
12 | 0.75 | 25 | 8.1317 | 2.3522 | 0 | 12.2742 | 4.8235 | 0 | 18.2796 | 6.4516 | 2.957 | 30.9028 | 23.2639 | 11.875 | 37.0968 | 26.6801 | 17.4059 | 43.2639 | 29.7917 | 20.6944 | 44.0188 | 32.3253 | 24.328 | 41.0618 | 28.4946 | 19.4892 | 26.5972 | 13.8889 | 6.9444 | 13.0376 | 5.0403 | 2.0161 | 6.7361 | 2.7083 | 0 | 7.1237 | 3.629 | 0
12 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 0 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 1.9489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 1 | 4 | 3.1586 | 0 | 0 | 5.5521 | 2.0089 | 0 | 7.3253 | 2.1505 | 0 | 11.1111 | 6.1806 | 2.0139 | 10.7527 | 6.3844 | 1.9489 | 17.5 | 9.5833 | 5.4861 | 15.3898 | 8.8038 | 3.8306 | 15.2554 | 7.9301 | 4.5027 | 8.4028 | 4.1667 | 1.6667 | 3.9651 | 2.0833 | 0 | 3.9583 | 0.83333 | 0 | 4.5027 | 1.6801 | 0
12 | 1 | 6 | 9.8118 | 4.0995 | 0 | 16.5923 | 10.0883 | 2.0474 | 18.6828 | 9.9462 | 3.4946 | 27.2222 | 20 | 13.2639 | 30.5108 | 25.2016 | 16.5323 | 40.4861 | 28.2639 | 19.0972 | 36.2903 | 28.0242 | 21.5726 | 35.2151 | 24.2608 | 16.1962 | 26.3889 | 16.0417 | 8.4722 | 13.5753 | 6.9892 | 2.8226 | 11.1806 | 4.5833 | 0 | 12.164 | 4.9059 | 0
12 | 1 | 8 | 19.2876 | 8.3333 | 2.3522 | 25.744 | 16.2202 | 4.6875 | 28.5618 | 17.3387 | 7.9301 | 42.0139 | 33.75 | 24.1667 | 48.5887 | 40.5914 | 33.1989 | 53.8889 | 44.7222 | 36.5278 | 59.879 | 46.9086 | 36.6935 | 55.0403 | 40.0538 | 32.7285 | 39.2361 | 30.4167 | 18.6806 | 21.371 | 13.9113 | 6.5188 | 15.5556 | 7.9861 | 2.9861 | 20.6989 | 8.8038 | 1.6129
12 | 1 | 9 | 19.6909 | 9.0726 | 2.4194 | 26.8935 | 16.8155 | 4.8363 | 31.7876 | 19.6909 | 9.1398 | 45.625 | 38.6111 | 27.0833 | 54.1667 | 44.8925 | 36.4247 | 56.9444 | 48.2639 | 38.6111 | 66.129 | 50.4032 | 39.7849 | 58.8038 | 45.2957 | 39.5161 | 42.3611 | 33.4722 | 19.8611 | 22.7151 | 15.3226 | 6.922 | 16.6667 | 9.375 | 3.0556 | 20.9677 | 10.2823 | 1.7473
12 | 1 | 10 | 19.6909 | 9.1398 | 2.4194 | 26.8935 | 16.8899 | 4.8363 | 32.2581 | 20.2285 | 9.1398 | 46.25 | 39.6528 | 27.3611 | 55.1747 | 46.1694 | 37.9704 | 58.6806 | 49.5833 | 38.9583 | 66.8683 | 52.2177 | 41.2634 | 59.1398 | 46.5054 | 40.1882 | 43.3333 | 33.8889 | 20.0694 | 23.0511 | 15.457 | 7.1237 | 16.8056 | 9.5139 | 3.0556 | 21.0349 | 10.2823 | 1.8145
12 | 1 | 11 | 19.6909 | 9.1398 | 2.4194 | 26.8935 | 16.8899 | 4.8363 | 32.3925 | 20.2285 | 9.1398 | 46.25 | 40.0694 | 27.3611 | 55.3091 | 46.371 | 37.9704 | 58.6806 | 49.7222 | 38.9583 | 66.9355 | 52.2177 | 41.2634 | 59.207 | 46.5726 | 40.2554 | 43.3333 | 33.8889 | 20.0694 | 23.0511 | 15.457 | 7.8629 | 16.8056 | 9.5139 | 3.0556 | 21.0349 | 10.2823 | 1.8145
12 | 1 | 12 | 19.6909 | 9.1398 | 2.4194 | 26.8935 | 16.8899 | 4.8363 | 32.3925 | 20.2285 | 9.4086 | 46.25 | 40.0694 | 27.3611 | 55.3091 | 46.4382 | 37.9704 | 58.6806 | 49.7222 | 38.9583 | 66.9355 | 52.2177 | 41.2634 | 59.207 | 46.6398 | 40.2554 | 43.3333 | 33.8889 | 20.0694 | 23.0511 | 15.457 | 7.8629 | 16.8056 | 9.5139 | 3.0556 | 21.0349 | 10.2823 | 1.8145
12 | 1 | 15 | 19.6909 | 9.1398 | 2.4194 | 26.8935 | 16.8899 | 4.8363 | 32.3925 | 20.2285 | 9.4086 | 46.25 | 40.0694 | 27.3611 | 55.3091 | 46.4382 | 37.9704 | 58.6806 | 49.7222 | 38.9583 | 66.9355 | 52.2177 | 41.2634 | 59.207 | 46.6398 | 40.2554 | 43.3333 | 33.8889 | 20.0694 | 23.0511 | 15.457 | 7.8629 | 16.8056 | 9.5139 | 3.0556 | 21.0349 | 10.2823 | 1.8145
12 | 1 | 20 | 19.6909 | 9.1398 | 2.4194 | 26.8935 | 16.8899 | 4.8363 | 32.3925 | 20.2285 | 9.4086 | 46.25 | 40.0694 | 27.3611 | 55.3091 | 46.4382 | 37.9704 | 58.6806 | 49.7222 | 38.9583 | 66.9355 | 52.2177 | 41.2634 | 59.207 | 46.6398 | 40.2554 | 43.3333 | 33.8889 | 20.0694 | 23.0511 | 15.457 | 7.8629 | 16.8056 | 9.5139 | 3.0556 | 21.0349 | 10.2823 | 1.8145
12 | 1 | 25 | 19.6909 | 9.1398 | 2.4194 | 26.8935 | 16.8899 | 4.8363 | 32.3925 | 20.2285 | 9.4086 | 46.25 | 40.0694 | 27.3611 | 55.3091 | 46.4382 | 37.9704 | 58.6806 | 49.7222 | 38.9583 | 66.9355 | 52.2177 | 41.2634 | 59.207 | 46.6398 | 40.2554 | 43.3333 | 33.8889 | 20.0694 | 23.0511 | 15.457 | 7.8629 | 16.8056 | 9.5139 | 3.0556 | 21.0349 | 10.2823 | 1.8145
12 | 1.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 0 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 1.9489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 1.25 | 4 | 4.3683 | 0 | 0 | 5.996 | 2.7094 | 0 | 7.3925 | 2.6882 | 0 | 12.6389 | 7.5694 | 3.4028 | 11.1559 | 7.9301 | 1.9489 | 17.5 | 10.4861 | 5.9028 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 8.8038 | 4.7043 | 9.1667 | 4.3056 | 1.8056 | 5.1747 | 2.957 | 0.80645 | 4.8611 | 2.0139 | 0 | 6.3844 | 1.8145 | 0
12 | 1.25 | 6 | 13.9113 | 5.918 | 2.621 | 20.0893 | 11.6379 | 3.869 | 22.379 | 14.3817 | 5.3091 | 30.5556 | 23.6111 | 17.9167 | 33.6694 | 28.4274 | 21.6398 | 43.9583 | 32.9861 | 22.0833 | 39.3145 | 30.914 | 24.664 | 37.6344 | 26.7473 | 19.6909 | 29.1667 | 20.4167 | 11.6667 | 17.0699 | 10.1478 | 5.1747 | 13.4722 | 8.75 | 2.4306 | 14.1801 | 6.7876 | 2.621
12 | 1.25 | 8 | 26.2769 | 13.9113 | 5.4435 | 34.8958 | 23.4632 | 9.5982 | 37.7688 | 25.9409 | 14.4489 | 52.1528 | 42.7083 | 33.3333 | 56.922 | 51.0081 | 42.4059 | 64.4444 | 54.375 | 42.4306 | 66.5323 | 56.4516 | 43.75 | 59.8118 | 51.0753 | 41.5323 | 46.5972 | 38.6806 | 23.4722 | 29.0323 | 21.371 | 11.2231 | 22.2917 | 14.2361 | 7.5694 | 26.6129 | 13.5753 | 4.7715
12 | 1.25 | 9 | 27.7554 | 16.129 | 6.6532 | 39.8065 | 25.744 | 11.9048 | 41.8011 | 30.1075 | 18.2124 | 57.9861 | 48.2639 | 39.2361 | 64.7177 | 57.5941 | 50 | 68.9583 | 63.8194 | 50.3472 | 76.1425 | 62.7016 | 53.1586 | 68.8844 | 56.7204 | 50.672 | 53.4722 | 42.2222 | 28.5417 | 32.9973 | 24.8656 | 14.1129 | 26.3889 | 17.3611 | 7.7778 | 29.3011 | 17.7419 | 5.8468
12 | 1.25 | 10 | 31.1828 | 16.4651 | 6.8548 | 40.5018 | 26.8601 | 11.9792 | 42.5403 | 33.2661 | 19.5565 | 64.0278 | 51.9444 | 43.0556 | 68.2796 | 61.9624 | 52.621 | 72.8472 | 67.2222 | 52.3611 | 79.3683 | 67.9435 | 57.1909 | 72.4462 | 59.543 | 52.1505 | 56.6667 | 44.375 | 32.9167 | 34.0726 | 25.9409 | 15.9274 | 27.4306 | 19.0278 | 7.9861 | 29.8387 | 18.414 | 6.6532
12 | 1.25 | 11 | 31.3172 | 16.5323 | 6.922 | 40.6455 | 27.2321 | 11.9792 | 44.086 | 34.4086 | 20.4301 | 65 | 53.3333 | 43.3333 | 69.8253 | 63.3737 | 53.0914 | 74.6528 | 67.3611 | 52.5694 | 80.6452 | 68.75 | 59.4086 | 73.2527 | 61.828 | 53.0914 | 59.2361 | 44.6528 | 33.4722 | 34.207 | 26.4785 | 16.1962 | 27.8472 | 19.0972 | 8.0556 | 29.9731 | 18.6156 | 6.7204
12 | 1.25 | 12 | 31.3172 | 16.5323 | 6.922 | 40.6455 | 27.3065 | 11.9792 | 44.2204 | 34.4758 | 20.5645 | 65.1389 | 53.4028 | 43.4028 | 69.8253 | 63.8441 | 53.5618 | 74.7917 | 67.4306 | 52.5694 | 80.8468 | 68.8172 | 59.6102 | 73.6559 | 61.8952 | 53.2258 | 59.3056 | 44.7222 | 33.4722 | 34.4086 | 26.4785 | 16.2634 | 27.8472 | 19.0972 | 8.125 | 30.0403 | 18.6828 | 6.7876
12 | 1.25 | 15 | 31.3172 | 16.5323 | 6.922 | 40.6455 | 27.3065 | 11.9792 | 44.2204 | 34.4758 | 20.5645 | 65.1389 | 53.4028 | 43.4028 | 69.8925 | 63.8441 | 53.5618 | 74.8611 | 67.5 | 52.5694 | 80.8468 | 68.8172 | 59.7446 | 73.6559 | 61.8952 | 53.2258 | 59.3056 | 44.7222 | 33.4722 | 34.4086 | 26.4785 | 16.3306 | 27.8472 | 19.0972 | 8.125 | 30.0403 | 18.6828 | 6.7876
12 | 1.25 | 20 | 31.3172 | 16.5323 | 6.922 | 40.6455 | 27.3065 | 11.9792 | 44.2204 | 34.4758 | 20.5645 | 65.1389 | 53.4028 | 43.4028 | 69.8925 | 63.8441 | 53.5618 | 74.8611 | 67.5 | 52.5694 | 80.8468 | 68.8172 | 59.7446 | 73.6559 | 61.8952 | 53.2258 | 59.3056 | 44.7222 | 33.4722 | 34.4086 | 26.4785 | 16.3306 | 27.8472 | 19.0972 | 8.125 | 30.0403 | 18.6828 | 6.7876
12 | 1.25 | 25 | 31.3172 | 16.5323 | 6.922 | 40.6455 | 27.3065 | 11.9792 | 44.2204 | 34.4758 | 20.5645 | 65.1389 | 53.4028 | 43.4028 | 69.8925 | 63.8441 | 53.5618 | 74.8611 | 67.5 | 52.5694 | 80.8468 | 68.8172 | 59.7446 | 73.6559 | 61.8952 | 53.2258 | 59.3056 | 44.7222 | 33.4722 | 34.4086 | 26.4785 | 16.3306 | 27.8472 | 19.0972 | 8.125 | 30.0403 | 18.6828 | 6.7876
12 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 0.80645 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 2.0161 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 1.5 | 4 | 5.4435 | 0.26882 | 0 | 6.994 | 3.3482 | 0 | 7.5941 | 3.8306 | 1.7473 | 12.9861 | 8.1944 | 3.9583 | 12.2984 | 9.0726 | 1.9489 | 17.5 | 10.8333 | 5.9028 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 9.4086 | 4.9731 | 9.1667 | 4.7222 | 1.875 | 5.6452 | 3.1586 | 0.80645 | 5.4167 | 2.1528 | 0 | 7.0565 | 2.1505 | 0
12 | 1.5 | 6 | 17.4059 | 7.5269 | 3.1586 | 22.6935 | 14.6039 | 5.0595 | 24.1263 | 15.8602 | 7.3253 | 31.7361 | 25.4167 | 19.3056 | 36.0887 | 30.7124 | 22.7151 | 46.5972 | 34.5833 | 23.8889 | 40.9274 | 31.6532 | 24.7984 | 37.6344 | 27.7554 | 20.9677 | 30.9028 | 22.9167 | 12.7083 | 18.6156 | 11.4247 | 6.5188 | 15 | 9.7222 | 4.0972 | 15.793 | 9.2742 | 3.6962
12 | 1.5 | 8 | 29.5027 | 17.2715 | 7.9301 | 38.1696 | 27.1988 | 11.0119 | 42.6075 | 32.3925 | 18.3468 | 55.3472 | 49.0278 | 37.9861 | 61.6263 | 54.5027 | 45.7661 | 68.125 | 58.9583 | 46.25 | 69.6237 | 59.4758 | 47.379 | 62.6344 | 54.1667 | 44.6237 | 50.5556 | 43.1944 | 27.1528 | 34.0054 | 24.5968 | 13.3737 | 29.0278 | 19.1667 | 11.7361 | 30.1075 | 17.9435 | 8.2661
12 | 1.5 | 9 | 34.4758 | 21.6398 | 11.0887 | 45.4613 | 32.9023 | 17.0387 | 49.0591 | 37.5 | 25.2016 | 63.6806 | 55.4861 | 46.5278 | 71.1022 | 63.5753 | 55.1747 | 75 | 70.4861 | 58.9583 | 79.4355 | 69.2204 | 59.879 | 72.4462 | 64.1801 | 55.578 | 60.6944 | 49.7917 | 36.0417 | 38.5753 | 32.4597 | 19.8253 | 36.6667 | 24.8611 | 12.9167 | 37.5 | 24.2608 | 11.2231
12 | 1.5 | 10 | 38.3065 | 23.9247 | 14.5833 | 49.0327 | 37.2126 | 18.378 | 53.8978 | 42.3387 | 28.7634 | 69.7917 | 60.1389 | 52.4306 | 76.9489 | 69.9597 | 61.2231 | 79.5139 | 76.8056 | 65 | 86.6263 | 77.0161 | 68.6156 | 78.4274 | 71.371 | 60.1478 | 65.1389 | 55 | 44.7222 | 43.2796 | 36.5591 | 21.371 | 41.3194 | 30.1389 | 13.4722 | 39.7849 | 27.4194 | 12.2312
12 | 1.5 | 11 | 40.121 | 24.9328 | 15.5914 | 51.5625 | 38.4673 | 18.8988 | 56.1828 | 44.2204 | 29.7715 | 72.5 | 63.2639 | 55.2778 | 80.1075 | 72.8495 | 64.9194 | 82.0833 | 78.4722 | 67.0833 | 88.4409 | 80.9812 | 71.1022 | 81.25 | 73.3199 | 62.5 | 69.7222 | 57.7083 | 46.6667 | 45.4973 | 39.3817 | 24.1935 | 42.5 | 31.1111 | 14.5139 | 41.6667 | 28.6962 | 13.4409
12 | 1.5 | 12 | 40.3226 | 25.0672 | 15.7258 | 51.7113 | 38.7546 | 18.9732 | 56.586 | 44.6237 | 30.3763 | 72.9861 | 63.8194 | 55.9722 | 81.0484 | 73.7231 | 66.3978 | 82.6389 | 78.75 | 68.0556 | 88.7097 | 81.5188 | 71.7742 | 81.8548 | 73.5215 | 63.3737 | 70 | 58.3333 | 47.2917 | 46.3038 | 40.0538 | 24.328 | 42.9167 | 31.3889 | 14.6528 | 41.7339 | 28.8978 | 13.8441
12 | 1.5 | 15 | 40.457 | 25.9409 | 15.7258 | 51.7113 | 38.8265 | 18.9732 | 56.6532 | 44.6909 | 30.3763 | 73.0556 | 64.0972 | 55.9722 | 81.1828 | 74.1935 | 66.5323 | 82.9167 | 78.75 | 68.0556 | 88.7769 | 81.7876 | 71.9758 | 81.9892 | 73.5887 | 64.0457 | 70.0694 | 58.6111 | 47.2917 | 46.3038 | 40.5242 | 24.4624 | 42.9167 | 31.7361 | 14.6528 | 41.8011 | 28.9651 | 13.9785
12 | 1.5 | 20 | 40.457 | 25.9409 | 15.7258 | 51.7113 | 38.8265 | 18.9732 | 56.6532 | 44.6909 | 30.3763 | 73.0556 | 64.0972 | 55.9722 | 81.1828 | 74.1935 | 66.5323 | 82.9167 | 78.75 | 68.0556 | 88.7769 | 81.7876 | 71.9758 | 81.9892 | 73.5887 | 64.0457 | 70.0694 | 58.6111 | 47.2917 | 46.3038 | 40.5242 | 24.4624 | 42.9167 | 31.7361 | 14.6528 | 41.8011 | 28.9651 | 13.9785
12 | 1.5 | 25 | 40.457 | 25.9409 | 15.7258 | 51.7113 | 38.8265 | 18.9732 | 56.6532 | 44.6909 | 30.3763 | 73.0556 | 64.0972 | 55.9722 | 81.1828 | 74.1935 | 66.5323 | 82.9167 | 78.75 | 68.0556 | 88.7769 | 81.7876 | 71.9758 | 81.9892 | 73.5887 | 64.0457 | 70.0694 | 58.6111 | 47.2917 | 46.3038 | 40.5242 | 24.4624 | 42.9167 | 31.7361 | 14.6528 | 41.8011 | 28.9651 | 13.9785
12 | 1.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 1.6129 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 2.0161 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 1.75 | 4 | 5.4435 | 1.0753 | 0 | 7.2173 | 3.3482 | 0 | 7.5941 | 4.0323 | 1.7473 | 13.8194 | 8.1944 | 4.3056 | 12.4328 | 9.2742 | 2.621 | 17.5 | 10.9722 | 6.3889 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 9.4086 | 4.9731 | 9.1667 | 4.7917 | 2.2222 | 6.0484 | 3.293 | 0.80645 | 6.5972 | 2.7778 | 0 | 7.0565 | 2.6882 | 0
12 | 1.75 | 6 | 18.6156 | 8.1989 | 3.293 | 23.535 | 14.7989 | 5.6548 | 24.2608 | 16.3306 | 8.3333 | 32.9861 | 26.0417 | 20.1389 | 37.0296 | 31.1828 | 24.3952 | 46.5972 | 34.5833 | 24.3056 | 40.9274 | 31.7204 | 24.7984 | 37.6344 | 27.957 | 20.9677 | 31.1806 | 23.4028 | 12.7083 | 19.8925 | 12.0968 | 7.1237 | 15.9722 | 10.2083 | 5.2778 | 17.5403 | 9.2742 | 3.7634
12 | 1.75 | 8 | 33.1317 | 19.7581 | 10.6183 | 41.5923 | 31.5476 | 13.8393 | 44.3548 | 34.879 | 22.7823 | 59.5139 | 51.5972 | 38.9583 | 64.0457 | 57.5941 | 48.6559 | 68.6111 | 61.3889 | 47.9861 | 70.1613 | 60.9543 | 48.6559 | 63.3737 | 55.914 | 45.3629 | 53.0556 | 45.1389 | 29.2361 | 36.4247 | 27.957 | 17.6747 | 33.4722 | 22.2222 | 14.375 | 34.2742 | 20.6317 | 10.0806
12 | 1.75 | 9 | 39.1129 | 24.8656 | 14.7177 | 49.1071 | 39.1831 | 19.0476 | 53.8306 | 41.3978 | 31.25 | 68.4028 | 58.6806 | 50.625 | 74.7984 | 68.2796 | 59.207 | 78.0556 | 73.125 | 61.5972 | 80.8468 | 71.8414 | 62.9704 | 75 | 67.3387 | 57.9973 | 64.5139 | 52.2917 | 39.7917 | 44.1532 | 36.5591 | 22.2446 | 43.1944 | 30.625 | 16.8056 | 40.9274 | 27.4194 | 13.4409
12 | 1.75 | 10 | 45.0269 | 31.1156 | 19.422 | 57.089 | 45.1047 | 25.5952 | 61.5591 | 47.1774 | 35.4167 | 76.875 | 65.9722 | 59.375 | 82.1909 | 74.8656 | 66.4651 | 84.1667 | 81.3889 | 71.4583 | 89.9866 | 81.4516 | 73.9247 | 82.0565 | 74.328 | 67.2043 | 70.9028 | 60.2083 | 50.2778 | 49.9328 | 42.3387 | 28.9651 | 47.3611 | 34.5833 | 20.4167 | 44.1532 | 32.6613 | 17.1371
12 | 1.75 | 11 | 48.5887 | 34.9462 | 21.9086 | 61.9792 | 48.5247 | 28.2738 | 65.9946 | 53.5618 | 39.7177 | 81.1111 | 73.125 | 64.0278 | 87.0296 | 80.0403 | 72.9839 | 87.7778 | 84.375 | 75.4167 | 93.2796 | 87.7688 | 77.957 | 86.3575 | 79.5699 | 72.5134 | 77.0833 | 65.1389 | 54.8611 | 54.0323 | 46.7742 | 33.8038 | 53.0556 | 39.0278 | 23.6111 | 46.9758 | 35.4167 | 18.8844
12 | 1.75 | 12 | 50.8065 | 36.5591 | 22.9167 | 62.7232 | 49.1174 | 29.2411 | 71.371 | 55.2419 | 41.9355 | 82.5 | 74.2361 | 66.25 | 88.1048 | 82.9973 | 77.1505 | 89.4444 | 85.9028 | 77.4306 | 94.9597 | 88.5081 | 80.4435 | 87.9032 | 81.1156 | 74.0591 | 78.5417 | 66.25 | 56.1111 | 55.0403 | 49.7984 | 35.1478 | 54.0972 | 41.8056 | 24.8611 | 47.7823 | 36.6935 | 20.9677
12 | 1.75 | 15 | 50.8737 | 36.7608 | 23.1183 | 63.3185 | 49.1918 | 29.3155 | 71.707 | 55.7796 | 42.7419 | 83.6111 | 74.7917 | 66.4583 | 88.3065 | 84.0726 | 77.8898 | 89.6528 | 86.4583 | 77.9167 | 95.1613 | 89.3145 | 81.1828 | 88.1048 | 81.3844 | 74.5296 | 78.8194 | 67.0139 | 57.4306 | 56.3844 | 50.8065 | 36.2231 | 54.7917 | 42.0139 | 25.4861 | 48.2527 | 37.3656 | 21.1694
12 | 1.75 | 20 | 50.8737 | 36.7608 | 23.1183 | 63.3185 | 49.1918 | 29.3155 | 71.707 | 55.7796 | 42.7419 | 83.6111 | 74.7917 | 66.4583 | 88.3065 | 84.0726 | 77.8898 | 89.6528 | 86.4583 | 77.9167 | 95.1613 | 89.3145 | 81.1828 | 88.1048 | 81.3844 | 74.5296 | 78.8194 | 67.0139 | 57.4306 | 56.3844 | 50.8065 | 36.2231 | 54.8611 | 42.0139 | 25.4861 | 48.2527 | 37.3656 | 21.1694
12 | 1.75 | 25 | 50.8737 | 36.7608 | 23.1183 | 63.3185 | 49.1918 | 29.3155 | 71.707 | 55.7796 | 42.7419 | 83.6111 | 74.7917 | 66.4583 | 88.3065 | 84.0726 | 77.8898 | 89.6528 | 86.4583 | 77.9167 | 95.1613 | 89.3145 | 81.1828 | 88.1048 | 81.3844 | 74.5296 | 78.8194 | 67.0139 | 57.4306 | 56.3844 | 50.8065 | 36.2231 | 54.8611 | 42.0139 | 25.4861 | 48.2527 | 37.3656 | 21.1694
12 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 1.6129 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 2.0161 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 2 | 4 | 5.4435 | 1.1425 | 0 | 7.5893 | 3.3482 | 0 | 7.5941 | 4.0995 | 1.8145 | 13.8194 | 8.1944 | 4.3056 | 12.4328 | 9.2742 | 2.621 | 17.5 | 10.9722 | 6.5278 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 9.4086 | 4.9731 | 9.1667 | 4.7917 | 2.2222 | 6.1156 | 3.293 | 0.80645 | 6.5972 | 3.1944 | 0 | 7.0565 | 3.4946 | 0
12 | 2 | 6 | 18.75 | 8.8095 | 3.8306 | 23.9814 | 15.7199 | 5.7292 | 25 | 16.5995 | 8.3333 | 33.5417 | 26.5278 | 21.1806 | 37.2312 | 31.1828 | 24.3952 | 46.5972 | 35.2083 | 24.3056 | 40.9274 | 31.7204 | 24.7984 | 37.6344 | 28.0242 | 20.9677 | 31.1806 | 23.4028 | 12.7083 | 20.4973 | 13.1048 | 7.2581 | 16.5278 | 10.8333 | 5.6944 | 18.414 | 9.8118 | 4.3683
12 | 2 | 8 | 34.0726 | 20.6989 | 11.4247 | 42.4851 | 33.2461 | 14.8065 | 44.8253 | 35.4839 | 24.328 | 61.5278 | 53.4028 | 42.3611 | 64.2473 | 57.5941 | 48.9247 | 68.6111 | 61.6667 | 48.4722 | 70.2285 | 61.0887 | 49.328 | 63.6425 | 56.25 | 45.4301 | 53.4028 | 45.3472 | 30.7639 | 38.5753 | 30.2419 | 18.8844 | 34.7917 | 22.9861 | 15.4861 | 36.0887 | 22.6478 | 12.164
12 | 2 | 9 | 40.5914 | 27.2177 | 16.3306 | 50.2976 | 42.1875 | 19.5685 | 57.3253 | 43.0108 | 32.7285 | 70.9722 | 61.5278 | 52.7778 | 75.8065 | 69.4892 | 60.0134 | 79.4444 | 74.4444 | 62.9861 | 83.1317 | 72.2446 | 63.5753 | 76.8145 | 68.8172 | 60.0134 | 66.1111 | 53.8889 | 42.4306 | 46.8414 | 38.172 | 25.8065 | 44.9306 | 32.2222 | 19.5139 | 43.3468 | 29.1667 | 15.8602
12 | 2 | 10 | 47.379 | 35.2151 | 20.9005 | 60.2371 | 51.0417 | 30.3571 | 66.129 | 52.7554 | 39.6505 | 80.625 | 70.0694 | 63.4028 | 83.4005 | 77.0833 | 69.3548 | 86.8056 | 83.1944 | 73.8194 | 91.4651 | 83.5349 | 75.4704 | 83.6694 | 76.6129 | 69.4892 | 72.5 | 62.6389 | 54.8611 | 54.3683 | 46.3038 | 33.4005 | 52.9167 | 40.4861 | 26.8056 | 49.7312 | 36.4919 | 21.6398
12 | 2 | 11 | 54.5699 | 40.0538 | 25.6048 | 67.9315 | 54.6131 | 33.6156 | 75 | 59.2742 | 47.4462 | 86.6667 | 76.9444 | 69.7917 | 89.3817 | 82.6613 | 78.7634 | 92.0139 | 87.9861 | 81.7361 | 95.0269 | 89.9194 | 81.1156 | 88.0376 | 83.1317 | 78.4946 | 80.5556 | 70.2083 | 60 | 61.9624 | 51.8817 | 41.8683 | 59.0972 | 47.3611 | 30.2778 | 55.3763 | 40.457 | 24.328
12 | 2 | 12 | 56.1156 | 42.4731 | 30.3763 | 71.0565 | 57.3661 | 36.0581 | 79.2339 | 63.3737 | 50.7392 | 90.1389 | 81.875 | 73.125 | 91.8011 | 86.8952 | 82.7957 | 93.1944 | 89.6528 | 84.7222 | 96.707 | 92.4731 | 84.207 | 90.2554 | 86.2231 | 80.2419 | 81.875 | 73.1944 | 63.3333 | 66.0618 | 55.1075 | 46.707 | 62.8472 | 48.6806 | 34.1667 | 57.5941 | 42.9435 | 26.8817
12 | 2 | 15 | 60.4839 | 43.5484 | 33.3333 | 72.9911 | 58.8542 | 37.0202 | 80.3763 | 66.129 | 52.4866 | 90.9028 | 82.8472 | 75.1389 | 93.0108 | 89.2473 | 85.0806 | 93.8889 | 90.2083 | 85.625 | 97.1774 | 93.3468 | 86.4919 | 92.1371 | 87.0296 | 81.5188 | 83.8889 | 74.1667 | 66.1111 | 70.0941 | 57.8629 | 48.7231 | 64.6528 | 50.9028 | 36.6667 | 59.207 | 46.0349 | 29.2339
12 | 2 | 20 | 60.4839 | 43.9516 | 33.3333 | 72.9911 | 58.8542 | 37.0202 | 80.3763 | 66.129 | 52.4866 | 90.9028 | 82.8472 | 75.1389 | 93.0108 | 89.2473 | 85.0806 | 93.8889 | 90.2083 | 85.6944 | 97.1774 | 93.3468 | 86.4919 | 92.1371 | 87.0296 | 81.5188 | 83.9583 | 74.1667 | 66.1111 | 70.0941 | 57.8629 | 48.7231 | 64.8611 | 50.9028 | 36.7361 | 59.207 | 46.0349 | 29.2339
12 | 2 | 25 | 60.4839 | 43.9516 | 33.3333 | 72.9911 | 58.8542 | 37.0202 | 80.3763 | 66.129 | 52.4866 | 90.9028 | 82.8472 | 75.1389 | 93.0108 | 89.2473 | 85.0806 | 93.8889 | 90.2083 | 85.6944 | 97.1774 | 93.3468 | 86.4919 | 92.1371 | 87.0296 | 81.5188 | 83.9583 | 74.1667 | 66.1111 | 70.0941 | 57.8629 | 48.7231 | 64.8611 | 50.9028 | 36.7361 | 59.207 | 46.0349 | 29.2339
12 | 2.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 1.6129 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 2.0161 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 2.25 | 4 | 5.4435 | 1.8145 | 0 | 7.6637 | 3.3482 | 0 | 7.5941 | 4.0995 | 1.8145 | 13.8194 | 8.1944 | 4.3056 | 12.4328 | 9.2742 | 2.621 | 17.5 | 10.9722 | 6.5278 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 9.4086 | 4.9731 | 9.1667 | 5 | 2.2222 | 6.1156 | 3.293 | 0.80645 | 6.5972 | 3.1944 | 0 | 7.0565 | 3.4946 | 0
12 | 2.25 | 6 | 18.75 | 9.1398 | 4.2339 | 23.9814 | 15.7199 | 5.7292 | 25 | 16.7339 | 8.8038 | 33.5417 | 26.9444 | 21.3194 | 37.2312 | 31.1828 | 24.3952 | 46.5972 | 35.2083 | 24.3056 | 40.9274 | 31.7204 | 24.7984 | 37.6344 | 28.0242 | 20.9677 | 31.1806 | 23.4028 | 12.9861 | 20.8333 | 13.1048 | 7.2581 | 17.0833 | 10.8333 | 5.6944 | 18.6156 | 9.8118 | 4.3683
12 | 2.25 | 8 | 34.4758 | 21.1022 | 12.5672 | 42.7083 | 33.4693 | 14.9554 | 45.5645 | 36.4919 | 24.5296 | 62.0139 | 53.6806 | 44.0972 | 64.2473 | 57.5941 | 48.9247 | 68.9583 | 61.6667 | 48.4722 | 70.2285 | 61.0887 | 49.664 | 63.6425 | 56.25 | 45.4973 | 53.6111 | 46.25 | 31.875 | 39.3145 | 31.1828 | 19.6237 | 35.3472 | 24.375 | 16.6667 | 36.6263 | 22.9839 | 13.1048
12 | 2.25 | 9 | 41.1962 | 29.3011 | 19.5565 | 51.4137 | 44.1272 | 20.0149 | 57.6613 | 45.2957 | 35.0134 | 72.5 | 62.0833 | 57.8472 | 76.0081 | 69.4892 | 60.8199 | 80 | 74.7917 | 63.125 | 84.0054 | 72.4462 | 63.5753 | 77.2849 | 69.1532 | 60.5511 | 66.3194 | 54.375 | 44.7917 | 48.5887 | 39.2473 | 27.3522 | 46.3889 | 33.3333 | 22.5 | 44.5565 | 31.0484 | 17.6075
12 | 2.25 | 10 | 51.3441 | 37.7016 | 25 | 61.4583 | 53.4226 | 32.2917 | 70.9005 | 54.9731 | 42.1371 | 81.7361 | 72.3611 | 65.4861 | 83.871 | 78.1586 | 71.1694 | 88.2639 | 84.1667 | 74.2361 | 92.3387 | 84.2742 | 76.2097 | 83.7366 | 78.4946 | 70.3629 | 74.0972 | 64.4444 | 57.5 | 55.7124 | 47.9839 | 36.3575 | 55.2083 | 42.7083 | 30.1389 | 51.9489 | 39.3817 | 23.5887
12 | 2.25 | 11 | 58.4677 | 42.6075 | 29.9059 | 69.9405 | 59.4366 | 38.0208 | 77.621 | 63.3737 | 51.6129 | 88.3333 | 79.3056 | 73.5417 | 90.8602 | 84.8118 | 80.1747 | 93.0556 | 89.3056 | 84.0972 | 95.9677 | 91.129 | 82.5941 | 89.3817 | 85.8199 | 80.3091 | 82.7778 | 72.0139 | 64.7917 | 67.2043 | 55.914 | 44.6909 | 61.4583 | 50.625 | 34.1667 | 59.4758 | 44.422 | 28.8978
12 | 2.25 | 12 | 63.0376 | 47.6478 | 36.4247 | 74.628 | 64.1651 | 42.8007 | 82.8629 | 69.8253 | 57.9301 | 92.2917 | 84.1667 | 78.0556 | 94.2204 | 90.1882 | 85.8871 | 94.5833 | 92.0833 | 88.0556 | 97.5134 | 93.6828 | 86.6263 | 93.6828 | 90.6586 | 82.5941 | 86.7361 | 76.8056 | 69.0972 | 72.043 | 59.1398 | 51.1425 | 66.9444 | 55.625 | 42.7083 | 62.7016 | 51.1425 | 35.0134
12 | 2.25 | 15 | 68.4812 | 49.664 | 41.0618 | 77.0089 | 67.4107 | 47.0033 | 85.5511 | 72.9167 | 62.4328 | 94.9306 | 86.9444 | 82.5 | 96.707 | 92.9435 | 89.2473 | 95.6944 | 93.125 | 89.0972 | 98.7231 | 96.0349 | 89.1129 | 95.6989 | 91.9355 | 85.7527 | 89.3056 | 81.8056 | 73.4028 | 77.0161 | 65.0538 | 57.7285 | 72.5694 | 60.8333 | 46.875 | 66.5323 | 55.6452 | 37.7688
12 | 2.25 | 20 | 68.4812 | 49.7312 | 41.0618 | 77.0833 | 67.4107 | 47.0777 | 85.5511 | 73.2527 | 62.4328 | 94.9306 | 86.9444 | 82.5 | 96.707 | 92.9435 | 89.3145 | 95.7639 | 93.125 | 89.5139 | 98.7231 | 96.0349 | 89.1801 | 95.6989 | 92.0699 | 85.7527 | 89.5139 | 81.8056 | 73.4722 | 77.1505 | 65.3226 | 57.7285 | 72.5694 | 60.9028 | 47.3611 | 66.5323 | 55.914 | 37.836
12 | 2.25 | 25 | 68.4812 | 49.7312 | 41.0618 | 77.0833 | 67.4107 | 47.0777 | 85.5511 | 73.2527 | 62.4328 | 94.9306 | 86.9444 | 82.5 | 96.707 | 92.9435 | 89.3145 | 95.7639 | 93.125 | 89.5139 | 98.7231 | 96.0349 | 89.1801 | 95.6989 | 92.0699 | 85.7527 | 89.5139 | 81.8056 | 73.4722 | 77.1505 | 65.3226 | 57.7285 | 72.5694 | 60.9028 | 47.3611 | 66.5323 | 55.914 | 37.836
12 | 2.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 1.6129 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 2.0161 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 2.5 | 4 | 5.4435 | 1.8145 | 0 | 7.6637 | 3.3482 | 0 | 7.5941 | 4.0995 | 1.8145 | 13.8194 | 8.1944 | 4.3056 | 12.4328 | 9.2742 | 2.621 | 17.5 | 10.9722 | 6.5278 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 9.4086 | 4.9731 | 9.1667 | 5.0694 | 2.2222 | 6.1156 | 3.293 | 0.80645 | 6.5972 | 3.1944 | 0 | 7.0565 | 3.4946 | 0
12 | 2.5 | 6 | 18.75 | 9.2742 | 4.2339 | 23.9814 | 15.7199 | 6.1012 | 25 | 16.7339 | 8.8038 | 33.5417 | 27.0139 | 21.6667 | 38.1048 | 31.1828 | 24.3952 | 46.5972 | 35.2083 | 24.3056 | 40.9274 | 31.7204 | 24.7984 | 37.6344 | 28.0242 | 20.9677 | 31.1806 | 23.4028 | 13.125 | 20.8333 | 13.1048 | 7.2581 | 17.0833 | 10.8333 | 5.6944 | 18.75 | 9.8118 | 4.7043
12 | 2.5 | 8 | 34.4758 | 21.2366 | 13.3065 | 43.6012 | 35.3038 | 15.3274 | 45.6317 | 36.6263 | 24.8656 | 62.3611 | 53.75 | 44.1667 | 64.2473 | 57.5941 | 48.9247 | 68.9583 | 61.6667 | 48.4722 | 70.2285 | 61.0887 | 49.664 | 63.6425 | 56.25 | 45.4973 | 53.6806 | 46.3889 | 31.875 | 39.8522 | 31.1828 | 20.5645 | 35.625 | 24.7917 | 16.8056 | 37.2312 | 23.1855 | 13.172
12 | 2.5 | 9 | 42.0699 | 29.9059 | 21.1694 | 53.0506 | 44.7147 | 21.6518 | 58.6022 | 46.5726 | 35.4839 | 72.5694 | 62.9167 | 57.8472 | 76.1425 | 69.4892 | 60.8871 | 80.1389 | 75 | 63.125 | 84.4086 | 72.4462 | 63.5753 | 77.2849 | 69.2204 | 60.6183 | 66.3194 | 55.6944 | 45.625 | 48.7903 | 39.9866 | 27.621 | 47.1528 | 33.5417 | 22.7778 | 45.5645 | 31.5188 | 18.1452
12 | 2.5 | 10 | 53.0914 | 38.9113 | 26.7473 | 62.2768 | 53.7202 | 32.7381 | 71.6398 | 56.4516 | 42.8091 | 81.7361 | 73.125 | 66.4583 | 84.0054 | 78.1586 | 71.5054 | 88.6111 | 84.375 | 74.2361 | 92.8763 | 84.2742 | 76.4113 | 84.0054 | 78.629 | 70.5645 | 74.2361 | 64.7917 | 58.1944 | 57.4597 | 50 | 38.4409 | 56.1806 | 43.6806 | 30.7639 | 53.4274 | 39.6505 | 24.328
12 | 2.5 | 11 | 60.4167 | 45.1613 | 32.6613 | 70.9077 | 60.9888 | 39.9554 | 79.0323 | 65.457 | 54.1667 | 88.4722 | 80.9722 | 74.2361 | 91.8683 | 85.7527 | 81.3172 | 93.6111 | 89.8611 | 85.5556 | 96.7742 | 91.3306 | 83.0645 | 90.1882 | 86.9624 | 80.914 | 84.1667 | 72.8472 | 66.9444 | 69.0188 | 56.922 | 45.8333 | 63.4028 | 52.5 | 35.7639 | 61.3575 | 45.8333 | 32.5941
12 | 2.5 | 12 | 66.8011 | 51.1425 | 40.8602 | 77.7145 | 67.0361 | 47.9167 | 84.543 | 72.379 | 60.1478 | 92.9167 | 87.2917 | 81.5278 | 95.1613 | 91.0618 | 88.2392 | 95.4167 | 92.9167 | 90 | 98.9247 | 95.5645 | 87.9032 | 96.2366 | 91.2634 | 84.4758 | 88.8889 | 80.4167 | 71.9444 | 74.5296 | 63.172 | 54.7715 | 69.5833 | 60.5556 | 45.9028 | 67.3387 | 55.1747 | 40.3226
12 | 2.5 | 15 | 76.4113 | 60.4839 | 45.1613 | 83.8644 | 73.5119 | 53.3482 | 90.2554 | 77.2177 | 67.6075 | 96.25 | 90.9722 | 87.6389 | 98.3871 | 96.0349 | 92.4059 | 97.0833 | 95.0694 | 92.5 | 100 | 98.1183 | 91.7339 | 98.0511 | 93.414 | 88.172 | 92.1528 | 85.625 | 77.5694 | 83.871 | 71.5726 | 65.5242 | 77.8472 | 68.5417 | 53.9583 | 73.2527 | 62.9032 | 45.6989
12 | 2.5 | 20 | 77.0161 | 60.5511 | 46.4382 | 83.8644 | 73.5119 | 53.5714 | 90.2554 | 77.621 | 67.6747 | 96.5278 | 91.1111 | 87.6389 | 98.3871 | 96.1022 | 92.4731 | 97.1528 | 95.0694 | 92.6389 | 100 | 98.1855 | 91.9355 | 98.0511 | 93.8844 | 89.0457 | 92.2917 | 85.7639 | 77.6389 | 84.2742 | 71.7742 | 66.7339 | 78.2639 | 69.0972 | 55.2083 | 73.5215 | 63.1048 | 46.5054
12 | 2.5 | 25 | 77.0161 | 60.5511 | 46.4382 | 83.8644 | 73.5119 | 53.5714 | 90.2554 | 77.621 | 67.6747 | 96.5278 | 91.1111 | 87.6389 | 98.3871 | 96.1022 | 92.4731 | 97.1528 | 95.0694 | 92.6389 | 100 | 98.1855 | 91.9355 | 98.0511 | 93.8844 | 89.0457 | 92.2917 | 85.7639 | 77.6389 | 84.2742 | 71.7742 | 66.7339 | 78.2639 | 69.0972 | 55.2083 | 73.5215 | 63.1048 | 46.5054
12 | 2.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 1.6129 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 2.0161 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 2.75 | 4 | 5.4435 | 1.8145 | 0 | 7.6637 | 3.3482 | 0 | 7.5941 | 4.0995 | 1.8145 | 13.8194 | 8.1944 | 4.3056 | 12.4328 | 9.2742 | 2.621 | 17.5 | 10.9722 | 6.5278 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 9.4086 | 4.9731 | 9.1667 | 5.0694 | 2.2222 | 6.1156 | 3.293 | 0.80645 | 6.5972 | 3.1944 | 0 | 7.0565 | 3.4946 | 0
12 | 2.75 | 6 | 18.75 | 9.2742 | 4.2339 | 23.9814 | 15.7199 | 7.1429 | 25 | 16.7339 | 8.8038 | 33.5417 | 27.0139 | 21.6667 | 38.1048 | 31.1828 | 24.3952 | 46.5972 | 35.2083 | 24.3056 | 40.9274 | 31.7204 | 24.7984 | 37.6344 | 28.0242 | 20.9677 | 31.1806 | 23.4028 | 13.125 | 20.8333 | 13.1048 | 7.2581 | 17.0833 | 10.8333 | 6.5278 | 18.75 | 9.8118 | 4.9731
12 | 2.75 | 8 | 34.9462 | 21.3038 | 13.3737 | 43.8244 | 35.704 | 16.2946 | 45.6317 | 36.6263 | 25.4704 | 62.3611 | 53.75 | 44.1667 | 64.2473 | 57.5941 | 48.9247 | 68.9583 | 61.6667 | 48.4722 | 70.2285 | 61.0887 | 49.664 | 63.6425 | 56.25 | 45.4973 | 53.75 | 46.3889 | 31.875 | 39.8522 | 31.1828 | 20.5645 | 35.9028 | 24.7917 | 16.875 | 37.3656 | 23.2527 | 13.9113
12 | 2.75 | 9 | 42.0699 | 30.7329 | 21.1694 | 53.497 | 45.977 | 22.0982 | 58.8038 | 46.5726 | 36.4247 | 72.5694 | 63.125 | 58.125 | 76.2097 | 69.4892 | 60.8871 | 80.2083 | 75 | 63.125 | 84.4086 | 72.4462 | 63.5753 | 77.2849 | 69.2204 | 60.6183 | 66.3194 | 56.25 | 46.0417 | 48.9247 | 39.9866 | 28.8306 | 47.4306 | 34.6528 | 23.8889 | 45.9677 | 31.8548 | 19.2876
12 | 2.75 | 10 | 53.5618 | 39.3817 | 27.2849 | 63.0029 | 53.7946 | 32.9613 | 71.9086 | 56.7204 | 43.2124 | 81.7361 | 74.1667 | 67.1528 | 84.207 | 78.5618 | 71.6398 | 88.6111 | 84.4444 | 74.2361 | 92.8763 | 84.2742 | 76.4113 | 84.0054 | 78.6962 | 70.5645 | 74.2361 | 64.9306 | 58.1944 | 57.5941 | 50.2688 | 38.9785 | 57.4306 | 44.1667 | 30.8333 | 54.3683 | 40.121 | 25.0672
12 | 2.75 | 11 | 62.9032 | 46.5054 | 34.4086 | 71.503 | 63.3929 | 41.0714 | 79.6371 | 65.8602 | 55.1075 | 88.8194 | 81.5278 | 75.9028 | 92.1371 | 86.1559 | 81.6532 | 93.75 | 90.3472 | 85.9028 | 96.8414 | 91.3306 | 83.4005 | 91.1962 | 86.9624 | 81.3172 | 85.1389 | 73.4028 | 67.7778 | 69.7581 | 57.1237 | 47.2446 | 66.1111 | 54.5833 | 37.0833 | 63.0376 | 47.5806 | 35.2151
12 | 2.75 | 12 | 69.2204 | 53.4946 | 42.4731 | 79.4643 | 69.0835 | 51.2649 | 85.2823 | 73.7903 | 62.836 | 93.0556 | 87.7778 | 82.9167 | 95.7661 | 91.3978 | 89.2473 | 96.8056 | 93.9583 | 90.7639 | 99.1263 | 95.6317 | 88.8441 | 97.2446 | 91.7339 | 85.9543 | 89.5833 | 81.6667 | 75.7639 | 75.7392 | 63.8441 | 56.25 | 72.0139 | 62.8472 | 47.5 | 68.4812 | 56.8548 | 42.2043
12 | 2.75 | 15 | 81.586 | 66.5995 | 50.9409 | 85.7528 | 77.5298 | 60.5655 | 93.3468 | 81.1156 | 73.5215 | 97.6389 | 94.0972 | 90.625 | 99.2608 | 97.7823 | 95.3629 | 98.6111 | 96.8056 | 94.7222 | 100 | 98.9919 | 94.4892 | 99.328 | 95.9677 | 91.9355 | 94.7222 | 89.375 | 82.9861 | 88.5753 | 77.5538 | 69.8253 | 81.875 | 73.6806 | 60 | 77.2177 | 70.4973 | 54.1667
12 | 2.75 | 20 | 82.4597 | 67.1371 | 51.5457 | 86.1607 | 77.9942 | 61.0222 | 93.75 | 81.6532 | 73.9247 | 98.3333 | 94.1667 | 90.9722 | 99.3952 | 97.9167 | 95.5645 | 98.6111 | 96.875 | 94.8611 | 100 | 98.9919 | 94.5565 | 99.328 | 96.2366 | 92.0699 | 95.2083 | 89.6528 | 83.75 | 90.121 | 79.0323 | 71.5054 | 82.9167 | 75.4861 | 61.6667 | 78.1586 | 70.8333 | 54.9059
12 | 2.75 | 25 | 82.4597 | 67.1371 | 51.5457 | 86.1607 | 77.9942 | 61.0222 | 93.75 | 81.6532 | 73.9247 | 98.3333 | 94.1667 | 90.9722 | 99.3952 | 97.9167 | 95.5645 | 98.6111 | 96.875 | 94.8611 | 100 | 98.9919 | 94.5565 | 99.328 | 96.2366 | 92.0699 | 95.2083 | 89.6528 | 83.75 | 90.121 | 79.0323 | 71.5054 | 82.9167 | 75.4861 | 61.6667 | 78.1586 | 70.8333 | 54.9059
12 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 1.6129 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 2.0161 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 3 | 4 | 5.4435 | 1.8145 | 0 | 7.6637 | 3.3482 | 0 | 7.5941 | 4.0995 | 1.8145 | 13.8194 | 8.1944 | 4.3056 | 12.4328 | 9.2742 | 2.621 | 17.5 | 10.9722 | 6.5278 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 9.4086 | 4.9731 | 9.1667 | 5.0694 | 2.2222 | 6.1156 | 3.293 | 0.80645 | 6.5972 | 3.1944 | 0 | 7.0565 | 3.4946 | 0
12 | 3 | 6 | 18.75 | 9.2742 | 4.2339 | 23.9814 | 15.7199 | 7.1429 | 25 | 16.7339 | 8.8038 | 33.5417 | 27.0139 | 21.6667 | 38.1048 | 31.1828 | 24.3952 | 46.5972 | 35.2083 | 24.3056 | 40.9274 | 31.7204 | 24.7984 | 37.6344 | 28.0242 | 20.9677 | 31.1806 | 23.4028 | 13.125 | 20.8333 | 13.1048 | 7.2581 | 17.0833 | 10.8333 | 6.5278 | 18.75 | 9.8118 | 4.9731
12 | 3 | 8 | 34.9462 | 21.5726 | 13.4409 | 43.9732 | 35.9914 | 16.4435 | 45.6317 | 36.6263 | 25.4704 | 62.3611 | 53.75 | 44.1667 | 64.2473 | 57.5941 | 48.9247 | 68.9583 | 61.6667 | 48.4722 | 70.2285 | 61.0887 | 49.664 | 63.6425 | 56.25 | 45.4973 | 53.75 | 46.3889 | 31.875 | 39.8522 | 31.1828 | 20.5645 | 35.9722 | 24.7917 | 16.875 | 38.0376 | 23.2527 | 13.9113
12 | 3 | 9 | 42.0699 | 31.7876 | 21.1694 | 53.6458 | 46.2002 | 22.0982 | 58.8038 | 46.5726 | 36.6263 | 72.5694 | 63.125 | 58.125 | 76.2097 | 69.4892 | 60.8871 | 80.2083 | 75 | 63.125 | 84.4086 | 72.4462 | 63.5753 | 77.2849 | 69.2204 | 60.6183 | 66.3194 | 56.25 | 46.0417 | 48.9919 | 40.3898 | 29.5027 | 47.6389 | 34.6528 | 24.0278 | 47.379 | 32.0565 | 19.2876
12 | 3 | 10 | 53.7634 | 39.6505 | 27.7554 | 63.2261 | 53.9435 | 32.9613 | 71.9758 | 56.922 | 43.4812 | 81.7361 | 74.2361 | 67.2917 | 84.207 | 78.5618 | 71.707 | 88.6111 | 84.5139 | 74.2361 | 92.8763 | 84.2742 | 76.4113 | 84.0054 | 78.6962 | 70.5645 | 74.2361 | 64.9306 | 58.1944 | 57.5941 | 50.2688 | 39.2473 | 57.6389 | 44.8611 | 30.8333 | 55.914 | 40.7258 | 25.9409
12 | 3 | 11 | 63.6425 | 46.7742 | 35.2823 | 71.8006 | 64.1369 | 44.9405 | 80.1747 | 65.9946 | 55.3091 | 88.8194 | 82.5 | 77.0139 | 92.2715 | 86.3575 | 81.7876 | 93.8194 | 90.5556 | 86.3194 | 96.8414 | 91.3306 | 83.6022 | 91.2634 | 87.0296 | 81.3844 | 85.1389 | 73.4028 | 67.9167 | 70.0269 | 58.6694 | 48.4543 | 67.2917 | 56.0417 | 37.9861 | 64.5161 | 47.9839 | 37.5672
12 | 3 | 12 | 71.2366 | 54.8077 | 43.4812 | 79.8363 | 70.2381 | 55.6548 | 86.1559 | 74.4624 | 64.0457 | 93.1944 | 89.7222 | 83.5417 | 95.8333 | 91.9355 | 89.2473 | 97.0139 | 94.6528 | 90.9028 | 99.1263 | 95.6317 | 89.0457 | 97.2446 | 92.4731 | 86.3575 | 89.7222 | 82.2917 | 76.9444 | 77.0833 | 64.6505 | 57.5941 | 74.0278 | 65.2083 | 48.3333 | 69.0188 | 57.7957 | 44.3548
12 | 3 | 15 | 85.1478 | 71.5726 | 55.7796 | 88.1696 | 82.4405 | 66.7436 | 94.9597 | 85.6183 | 77.4866 | 98.4028 | 95.9722 | 92.7778 | 100 | 98.4543 | 96.4382 | 99.7917 | 97.7778 | 95.6944 | 100 | 99.9328 | 95.8333 | 99.664 | 97.9839 | 93.3468 | 96.3889 | 92.0139 | 85.0694 | 91.5995 | 80.9812 | 74.664 | 87.2222 | 77.9861 | 64.3056 | 80.914 | 73.1855 | 58.3333
12 | 3 | 20 | 86.6263 | 73.5887 | 56.4516 | 88.4673 | 84.062 | 68.1291 | 96.1022 | 86.828 | 78.5618 | 99.0278 | 96.1806 | 93.125 | 100 | 99.1935 | 97.043 | 99.8611 | 97.9861 | 95.7639 | 100 | 100 | 96.4382 | 99.7984 | 97.9839 | 93.8844 | 96.9444 | 92.5 | 86.3889 | 93.2796 | 83.6694 | 76.9489 | 88.8194 | 80.7639 | 67.0139 | 83.3333 | 75 | 61.2903
12 | 3 | 25 | 86.6263 | 73.5887 | 56.4516 | 88.4673 | 84.062 | 68.1291 | 96.1022 | 86.828 | 78.5618 | 99.0278 | 96.1806 | 93.125 | 100 | 99.1935 | 97.043 | 99.8611 | 97.9861 | 95.7639 | 100 | 100 | 96.4382 | 99.7984 | 97.9839 | 93.8844 | 96.9444 | 92.5 | 86.3889 | 93.2796 | 83.6694 | 76.9489 | 88.8194 | 80.7639 | 67.0139 | 83.3333 | 75 | 61.2903
12 | 3.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 1.6129 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 2.0161 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 3.25 | 4 | 5.4435 | 1.8145 | 0 | 7.6637 | 3.3482 | 0 | 7.5941 | 4.0995 | 1.8145 | 13.8194 | 8.1944 | 4.3056 | 12.4328 | 9.2742 | 2.621 | 17.5 | 10.9722 | 6.5278 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 9.4086 | 4.9731 | 9.1667 | 5.0694 | 2.2222 | 6.1156 | 3.293 | 0.80645 | 6.5972 | 3.1944 | 0 | 7.0565 | 3.4946 | 0
12 | 3.25 | 6 | 18.8844 | 9.4758 | 4.2339 | 23.9814 | 15.7199 | 7.1429 | 25 | 16.7339 | 8.8038 | 33.5417 | 27.0139 | 21.6667 | 38.1048 | 31.1828 | 24.3952 | 46.5972 | 35.2083 | 24.3056 | 40.9274 | 31.7204 | 24.7984 | 37.6344 | 28.0242 | 20.9677 | 31.1806 | 23.4028 | 13.125 | 20.8333 | 13.1048 | 7.2581 | 17.0833 | 10.8333 | 6.5278 | 18.75 | 9.8118 | 4.9731
12 | 3.25 | 8 | 34.9462 | 21.5726 | 13.4409 | 44.0476 | 35.9914 | 16.4435 | 45.6317 | 36.6263 | 25.4704 | 62.3611 | 53.75 | 44.1667 | 64.2473 | 57.5941 | 48.9247 | 68.9583 | 61.6667 | 48.4722 | 70.2285 | 61.0887 | 49.664 | 63.6425 | 56.25 | 45.4973 | 53.75 | 46.3889 | 31.875 | 39.8522 | 31.1828 | 20.5645 | 35.9722 | 24.7917 | 16.875 | 38.0376 | 23.2527 | 13.9113
12 | 3.25 | 9 | 42.0699 | 31.8548 | 21.1694 | 53.6458 | 46.349 | 22.0982 | 58.8038 | 46.5726 | 36.6263 | 72.5694 | 63.125 | 58.125 | 76.2097 | 69.4892 | 60.8871 | 80.2083 | 75 | 63.125 | 84.4086 | 72.4462 | 63.5753 | 77.2849 | 69.2204 | 60.6183 | 66.3194 | 56.25 | 46.0417 | 48.9919 | 40.457 | 29.5027 | 47.6389 | 34.6528 | 24.0972 | 47.8495 | 32.1237 | 19.2876
12 | 3.25 | 10 | 53.8306 | 39.7849 | 27.8898 | 63.5237 | 54.0923 | 33.0357 | 71.9758 | 56.922 | 44.8925 | 81.7361 | 74.3056 | 67.2917 | 84.207 | 78.5618 | 71.707 | 88.6111 | 84.5139 | 74.2361 | 92.8763 | 84.2742 | 76.4113 | 84.0054 | 78.6962 | 70.5645 | 74.2361 | 64.9306 | 58.1944 | 57.5941 | 50.4032 | 39.3817 | 57.7083 | 45.1389 | 30.8333 | 56.0484 | 40.7258 | 26.0081
12 | 3.25 | 11 | 64.1129 | 46.9758 | 36.4919 | 72.6935 | 64.6141 | 45.3869 | 80.7796 | 66.129 | 55.4435 | 88.8194 | 82.9167 | 77.0833 | 92.3387 | 86.3575 | 81.7876 | 93.8889 | 90.625 | 86.3194 | 96.8414 | 91.3306 | 83.6022 | 91.2634 | 87.0296 | 81.5188 | 85.1389 | 73.4722 | 67.9167 | 70.6989 | 58.9382 | 49.1263 | 67.9861 | 58.0556 | 39.0278 | 64.8522 | 48.1855 | 37.7016
12 | 3.25 | 12 | 71.6398 | 56.1536 | 45.0269 | 80.506 | 70.5357 | 57.2917 | 86.7608 | 74.664 | 64.7849 | 93.8194 | 90.2778 | 83.8889 | 96.0349 | 92.1371 | 89.2473 | 97.0833 | 94.6528 | 91.0417 | 99.1263 | 95.6317 | 89.1129 | 97.2446 | 92.5403 | 86.4247 | 89.8611 | 82.2917 | 77.0833 | 77.2849 | 65.5914 | 58.871 | 75.4861 | 66.9444 | 50.2083 | 69.5565 | 58.3333 | 44.8925
12 | 3.25 | 15 | 87.6344 | 73.9919 | 61.3575 | 90.5506 | 84.375 | 70.8333 | 95.4973 | 87.9032 | 80.5108 | 98.9583 | 97.1528 | 94.0278 | 100 | 99.0591 | 97.9167 | 100 | 98.8889 | 96.25 | 100 | 100 | 96.8414 | 100 | 98.9919 | 94.8253 | 96.875 | 93.6111 | 88.8194 | 93.8172 | 83.1317 | 78.5618 | 89.4444 | 82.9167 | 69.8611 | 83.4005 | 77.957 | 63.1048
12 | 3.25 | 20 | 90.2554 | 78.293 | 65.6586 | 91.5923 | 86.992 | 74.9666 | 97.5806 | 90.793 | 82.1237 | 99.7917 | 97.4306 | 94.7222 | 100 | 99.9328 | 98.0511 | 100 | 99.1667 | 96.3889 | 100 | 100 | 97.1774 | 100 | 99.328 | 95.5645 | 97.8472 | 94.5139 | 90.1389 | 96.1694 | 86.828 | 81.6532 | 92.3611 | 86.1111 | 72.9167 | 87.0296 | 80.7124 | 68.414
12 | 3.25 | 25 | 90.2554 | 78.3602 | 65.6586 | 91.5923 | 86.992 | 75.0411 | 97.5806 | 90.793 | 82.1237 | 99.7917 | 97.4306 | 94.7222 | 100 | 99.9328 | 98.0511 | 100 | 99.1667 | 96.3889 | 100 | 100 | 97.1774 | 100 | 99.328 | 95.5645 | 97.9167 | 94.5139 | 90.2083 | 96.1694 | 86.828 | 81.6532 | 92.3611 | 86.1111 | 72.9167 | 87.0296 | 80.7124 | 68.414
12 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 1.6129 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 2.0161 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 3.5 | 4 | 5.4435 | 1.8145 | 0 | 7.6637 | 3.3482 | 0 | 7.5941 | 4.0995 | 1.8145 | 13.8194 | 8.1944 | 4.3056 | 12.4328 | 9.2742 | 2.621 | 17.5 | 10.9722 | 6.5278 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 9.4086 | 4.9731 | 9.1667 | 5.0694 | 2.2222 | 6.1156 | 3.293 | 0.80645 | 6.5972 | 3.1944 | 0 | 7.0565 | 3.4946 | 0
12 | 3.5 | 6 | 18.8844 | 9.4758 | 4.2339 | 23.9814 | 15.7199 | 7.1429 | 25 | 16.7339 | 8.8038 | 33.5417 | 27.0139 | 21.6667 | 38.1048 | 31.1828 | 24.3952 | 46.5972 | 35.2083 | 24.3056 | 40.9274 | 31.7204 | 24.7984 | 37.6344 | 28.0242 | 20.9677 | 31.1806 | 23.4028 | 13.125 | 20.8333 | 13.1048 | 7.2581 | 17.0833 | 10.8333 | 6.5278 | 18.75 | 9.8118 | 4.9731
12 | 3.5 | 8 | 34.9462 | 21.5726 | 13.4409 | 44.0476 | 35.9914 | 16.4435 | 45.6317 | 36.6263 | 25.4704 | 62.3611 | 53.75 | 44.1667 | 64.2473 | 57.5941 | 48.9247 | 68.9583 | 61.6667 | 48.4722 | 70.2285 | 61.0887 | 49.664 | 63.6425 | 56.25 | 45.4973 | 53.75 | 46.3889 | 31.875 | 39.8522 | 31.1828 | 20.5645 | 35.9722 | 24.7917 | 16.875 | 38.0376 | 23.2527 | 13.9113
12 | 3.5 | 9 | 42.0699 | 31.8548 | 21.1694 | 53.6458 | 46.349 | 22.619 | 58.8038 | 46.5726 | 36.6263 | 72.5694 | 63.125 | 58.125 | 76.2097 | 69.4892 | 60.8871 | 80.2083 | 75 | 63.125 | 84.4086 | 72.4462 | 63.5753 | 77.2849 | 69.2204 | 60.6183 | 66.3194 | 56.25 | 46.0417 | 48.9919 | 40.457 | 29.5027 | 47.6389 | 34.6528 | 24.0972 | 47.8495 | 32.1237 | 20.9005
12 | 3.5 | 10 | 53.8306 | 39.7849 | 27.957 | 63.5981 | 54.0923 | 33.0357 | 71.9758 | 56.922 | 44.8925 | 82.6389 | 74.3056 | 67.2917 | 84.207 | 78.7634 | 71.707 | 88.6111 | 84.5139 | 74.2361 | 92.8763 | 84.2742 | 76.4113 | 84.0726 | 78.6962 | 70.5645 | 74.2361 | 64.9306 | 58.1944 | 57.8629 | 50.4032 | 39.4489 | 57.7083 | 45.1389 | 30.8333 | 56.1828 | 40.7258 | 26.3441
12 | 3.5 | 11 | 64.2473 | 46.9758 | 37.836 | 72.8423 | 64.6141 | 45.5357 | 80.7796 | 66.129 | 55.5108 | 89.5833 | 82.9167 | 77.0833 | 92.3387 | 86.3575 | 81.7876 | 93.9583 | 90.625 | 86.3194 | 96.8414 | 91.3306 | 83.6022 | 91.4651 | 87.0296 | 81.5188 | 85.1389 | 73.4722 | 68.0556 | 70.6989 | 59.0054 | 49.328 | 68.1944 | 58.1944 | 40.2083 | 64.9866 | 48.2527 | 37.7016
12 | 3.5 | 12 | 71.6398 | 56.4228 | 45.8333 | 80.5804 | 70.5614 | 57.8125 | 86.7608 | 75.2016 | 65.0538 | 93.8194 | 90.7639 | 83.9583 | 96.1694 | 92.3387 | 89.3145 | 97.0833 | 94.6528 | 91.1111 | 99.1263 | 95.6317 | 89.1801 | 97.2446 | 92.5403 | 86.4919 | 90 | 82.3611 | 77.0833 | 77.5538 | 66.129 | 59.0054 | 76.25 | 67.5 | 50.4167 | 69.8253 | 58.3333 | 46.1022
12 | 3.5 | 15 | 88.6425 | 75.6048 | 65.6358 | 91.8155 | 86.1607 | 73.0142 | 97.1102 | 89.9194 | 81.3844 | 99.5833 | 97.4306 | 94.6528 | 100 | 99.4624 | 98.3199 | 100 | 99.1667 | 97.0139 | 100 | 100 | 97.5806 | 100 | 99.2608 | 95.6317 | 97.8472 | 94.4444 | 89.3056 | 94.6909 | 85.8871 | 81.0484 | 90.4861 | 84.2361 | 71.8056 | 85.0134 | 79.5699 | 66.2634
12 | 3.5 | 20 | 92.0027 | 82.4597 | 69.5565 | 94.3452 | 90.0682 | 79.6105 | 98.9247 | 93.4812 | 84.3414 | 100 | 99.0972 | 95.5556 | 100 | 100 | 98.8575 | 100 | 99.5139 | 97.2917 | 100 | 100 | 98.0511 | 100 | 100 | 97.1102 | 98.8889 | 96.1806 | 92.5694 | 98.3871 | 89.9194 | 86.2903 | 94.375 | 88.6111 | 79.1667 | 88.8441 | 84.8118 | 72.3118
12 | 3.5 | 25 | 92.0027 | 82.4597 | 69.5565 | 94.3452 | 90.0682 | 79.6849 | 98.9247 | 93.4812 | 84.3414 | 100 | 99.0972 | 95.5556 | 100 | 100 | 98.8575 | 100 | 99.5139 | 97.2917 | 100 | 100 | 98.0511 | 100 | 100 | 97.1102 | 98.8889 | 96.1806 | 92.6389 | 98.3871 | 89.9194 | 86.2903 | 94.375 | 88.6806 | 79.1667 | 88.8441 | 84.8118 | 72.3118
12 | 3.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 1.6129 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 2.0161 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 3.75 | 4 | 5.4435 | 1.8145 | 0 | 7.6637 | 3.3482 | 0 | 7.5941 | 4.0995 | 1.8145 | 13.8194 | 8.1944 | 4.3056 | 12.4328 | 9.2742 | 2.621 | 17.5 | 10.9722 | 6.5278 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 9.4086 | 4.9731 | 9.1667 | 5.0694 | 2.2222 | 6.1156 | 3.293 | 0.80645 | 6.5972 | 3.1944 | 0 | 7.0565 | 3.4946 | 0
12 | 3.75 | 6 | 18.8844 | 9.4758 | 4.2339 | 23.9814 | 15.7199 | 7.1429 | 25 | 16.7339 | 8.8038 | 33.5417 | 27.0139 | 21.6667 | 38.1048 | 31.1828 | 24.3952 | 46.5972 | 35.2083 | 24.3056 | 40.9274 | 31.7204 | 24.7984 | 37.6344 | 28.0242 | 20.9677 | 31.1806 | 23.4028 | 13.125 | 20.8333 | 13.1048 | 7.2581 | 17.0833 | 10.8333 | 6.5278 | 18.75 | 9.8118 | 4.9731
12 | 3.75 | 8 | 34.9462 | 21.5726 | 13.4409 | 44.0476 | 35.9914 | 16.4435 | 45.6317 | 36.6263 | 25.4704 | 62.3611 | 53.75 | 44.1667 | 64.2473 | 57.5941 | 48.9247 | 68.9583 | 61.6667 | 48.4722 | 70.2285 | 61.0887 | 49.664 | 63.6425 | 56.25 | 45.4973 | 53.75 | 46.3889 | 31.875 | 39.8522 | 31.1828 | 20.5645 | 35.9722 | 24.7917 | 16.875 | 38.0376 | 23.2527 | 13.9113
12 | 3.75 | 9 | 42.0699 | 31.8548 | 21.1694 | 53.6458 | 46.349 | 22.619 | 58.8038 | 46.5726 | 36.6263 | 72.5694 | 63.125 | 58.125 | 76.2097 | 69.4892 | 60.8871 | 80.2083 | 75 | 63.125 | 84.4086 | 72.4462 | 63.5753 | 77.2849 | 69.2204 | 60.6183 | 66.3194 | 56.25 | 46.0417 | 48.9919 | 40.457 | 29.5027 | 47.6389 | 34.6528 | 24.0972 | 47.8495 | 32.1237 | 21.1022
12 | 3.75 | 10 | 53.8306 | 39.7849 | 27.957 | 63.5981 | 54.0923 | 33.0357 | 71.9758 | 56.922 | 44.8925 | 82.6389 | 74.3056 | 67.2917 | 84.207 | 78.7634 | 71.707 | 88.6111 | 84.5139 | 74.2361 | 92.8763 | 84.2742 | 76.4113 | 84.0726 | 78.6962 | 70.5645 | 74.2361 | 64.9306 | 58.1944 | 57.8629 | 50.4032 | 39.4489 | 57.7083 | 45.1389 | 30.8333 | 56.25 | 40.7258 | 26.5457
12 | 3.75 | 11 | 64.2473 | 47.6478 | 38.5081 | 72.8423 | 64.6141 | 45.5357 | 80.7796 | 66.129 | 55.5108 | 89.5833 | 82.9167 | 77.0833 | 92.3387 | 86.3575 | 81.7876 | 93.9583 | 90.625 | 86.3194 | 96.8414 | 91.3306 | 83.6022 | 91.5323 | 87.0296 | 81.5188 | 85.1389 | 73.4722 | 68.0556 | 70.6989 | 59.0054 | 49.328 | 68.1944 | 58.2639 | 40.4167 | 64.9866 | 48.2527 | 37.7016
12 | 3.75 | 12 | 71.6398 | 56.6919 | 46.4382 | 80.5804 | 71.1361 | 58.2589 | 86.7608 | 75.2688 | 65.1882 | 93.8889 | 90.9028 | 84.0278 | 96.2366 | 92.3387 | 89.3145 | 97.0833 | 94.7917 | 91.1111 | 99.1263 | 95.6317 | 89.1801 | 97.2446 | 92.5403 | 86.5591 | 90.0694 | 82.4306 | 77.0833 | 77.5538 | 66.1962 | 59.0054 | 76.7361 | 67.7778 | 50.625 | 70.1613 | 58.6022 | 46.2366
12 | 3.75 | 15 | 89.5833 | 76.9489 | 67.115 | 92.1875 | 86.5327 | 75.3438 | 97.2446 | 90.9274 | 82.3925 | 99.7917 | 97.9167 | 95.0694 | 100 | 99.7312 | 98.5215 | 100 | 99.3056 | 97.4306 | 100 | 100 | 97.8495 | 100 | 99.4624 | 96.1022 | 98.5417 | 95.5556 | 90.0694 | 94.8253 | 86.6263 | 81.586 | 91.8056 | 85.5556 | 74.6528 | 86.2903 | 80.6452 | 69.3548
12 | 3.75 | 20 | 93.2796 | 87.0296 | 76.664 | 96.5774 | 91.6667 | 83.4077 | 99.5296 | 95.8333 | 87.2984 | 100 | 99.4444 | 96.3889 | 100 | 100 | 99.5968 | 100 | 100 | 97.8472 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.5 | 93.8889 | 99.1263 | 92.7419 | 89.2473 | 96.6667 | 91.1806 | 82.9861 | 92.4731 | 87.0968 | 77.6882
12 | 3.75 | 25 | 93.2796 | 87.0296 | 76.664 | 96.5774 | 91.6667 | 83.4821 | 99.5296 | 95.8333 | 87.2984 | 100 | 99.5139 | 96.3889 | 100 | 100 | 99.5968 | 100 | 100 | 97.8472 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.5 | 93.8889 | 99.1935 | 92.7419 | 89.2473 | 96.6667 | 91.25 | 82.9861 | 92.4731 | 87.0968 | 77.6882
12 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8056 | 0 | 0 | 1.6129 | 0 | 0 | 2.0833 | 0 | 0 | 1.8817 | 0 | 0 | 2.0161 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 4 | 4 | 5.4435 | 1.8145 | 0 | 7.6637 | 3.3482 | 0 | 7.5941 | 4.0995 | 1.8145 | 13.8194 | 8.1944 | 4.3056 | 12.4328 | 9.2742 | 2.621 | 17.5 | 10.9722 | 6.5278 | 15.3898 | 8.8038 | 4.2339 | 15.5242 | 9.4086 | 4.9731 | 9.1667 | 5.0694 | 2.2222 | 6.1156 | 3.293 | 0.80645 | 6.5972 | 3.1944 | 0 | 7.0565 | 3.4946 | 0
12 | 4 | 6 | 18.8844 | 9.4758 | 4.2339 | 23.9814 | 15.7199 | 7.1429 | 25 | 16.7339 | 8.8038 | 33.5417 | 27.0139 | 21.6667 | 38.1048 | 31.1828 | 24.3952 | 46.5972 | 35.2083 | 24.3056 | 40.9274 | 31.7204 | 24.7984 | 37.6344 | 28.0242 | 20.9677 | 31.1806 | 23.4028 | 13.125 | 20.8333 | 13.1048 | 7.2581 | 17.0833 | 10.8333 | 6.5278 | 18.75 | 9.8118 | 4.9731
12 | 4 | 8 | 34.9462 | 21.5726 | 13.4409 | 44.0476 | 35.9914 | 16.4435 | 45.6317 | 36.6263 | 25.4704 | 62.3611 | 53.75 | 44.1667 | 64.2473 | 57.5941 | 48.9247 | 68.9583 | 61.6667 | 48.4722 | 70.2285 | 61.0887 | 49.664 | 63.6425 | 56.25 | 45.4973 | 53.75 | 46.3889 | 31.875 | 39.8522 | 31.1828 | 20.5645 | 35.9722 | 24.7917 | 16.875 | 38.0376 | 23.2527 | 13.9113
12 | 4 | 9 | 42.0699 | 31.8548 | 21.1694 | 53.6458 | 46.349 | 22.619 | 58.8038 | 46.5726 | 36.6263 | 72.5694 | 63.125 | 58.125 | 76.2097 | 69.4892 | 60.8871 | 80.2083 | 75 | 63.125 | 84.4086 | 72.4462 | 63.5753 | 77.2849 | 69.2204 | 60.6183 | 66.3194 | 56.25 | 46.0417 | 48.9919 | 40.457 | 29.5027 | 47.6389 | 34.6528 | 24.0972 | 47.8495 | 32.1237 | 21.1694
12 | 4 | 10 | 53.8306 | 39.7849 | 27.957 | 63.5981 | 54.0923 | 33.0357 | 71.9758 | 56.922 | 44.8925 | 82.6389 | 74.3056 | 67.2917 | 84.207 | 78.7634 | 71.707 | 88.6111 | 84.5139 | 74.2361 | 92.8763 | 84.2742 | 76.4113 | 84.0726 | 78.6962 | 70.5645 | 74.2361 | 64.9306 | 58.1944 | 57.8629 | 50.4032 | 39.4489 | 57.7083 | 45.1389 | 30.8333 | 56.25 | 40.7258 | 26.6801
12 | 4 | 11 | 64.2473 | 47.6478 | 38.7097 | 72.8423 | 65.2838 | 45.5357 | 80.7796 | 66.129 | 55.5108 | 89.5833 | 82.9167 | 77.0833 | 92.3387 | 86.3575 | 81.7876 | 93.9583 | 90.625 | 86.3194 | 96.8414 | 91.3306 | 83.6022 | 91.5323 | 87.0296 | 81.5188 | 85.1389 | 73.4722 | 68.0556 | 70.6989 | 59.0054 | 49.328 | 68.1944 | 58.2639 | 40.4167 | 64.9866 | 48.2527 | 37.7016
12 | 4 | 12 | 71.6398 | 56.7204 | 46.5054 | 80.6317 | 72.501 | 58.4077 | 86.7608 | 75.336 | 65.2554 | 93.9583 | 90.9028 | 84.0278 | 96.2366 | 92.3387 | 89.3145 | 97.0833 | 94.7917 | 91.1111 | 99.1263 | 95.6317 | 89.1801 | 97.2446 | 92.5403 | 86.5591 | 90.0694 | 82.4306 | 77.0833 | 77.5538 | 66.2634 | 59.0054 | 76.875 | 67.7778 | 50.625 | 70.2957 | 58.6022 | 46.3038
12 | 4 | 15 | 89.7849 | 78.0914 | 68.9516 | 92.4107 | 86.9792 | 77.5375 | 97.9839 | 91.3978 | 83.2661 | 99.7917 | 98.125 | 95.4861 | 100 | 99.7984 | 98.7231 | 100 | 99.3056 | 97.5694 | 100 | 100 | 98.0511 | 100 | 99.5296 | 96.5054 | 98.8194 | 95.9722 | 90.6944 | 95.0269 | 87.3656 | 81.922 | 92.5694 | 86.9444 | 76.9444 | 87.2984 | 81.7204 | 70.8333
12 | 4 | 20 | 95.3629 | 89.9866 | 80.6323 | 97.9911 | 94.1964 | 87.2024 | 99.9328 | 97.4462 | 89.1129 | 100 | 99.7917 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.4722 | 95.4861 | 99.7984 | 95.1613 | 91.4651 | 98.0556 | 94.0278 | 87.1528 | 94.8925 | 90.1882 | 83.6694
12 | 4 | 25 | 95.3629 | 90.121 | 80.6995 | 97.9911 | 94.1964 | 87.2742 | 99.9328 | 97.5134 | 89.1129 | 100 | 99.8611 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.6806 | 95.8333 | 99.9328 | 95.6317 | 91.4651 | 98.0556 | 94.1667 | 87.2222 | 94.8925 | 90.1882 | 83.8038
18 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9583 | 0 | 0 | 4.4355 | 0 | 0 | 10.1389 | 3.1944 | 0 | 6.5188 | 2.5538 | 0 | 7.2581 | 2.6882 | 0 | 2.1528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.5 | 6 | 0 | 0 | 0 | 1.3393 | 0 | 0 | 2.957 | 0 | 0 | 8.5417 | 3.2639 | 0 | 12.6344 | 7.0565 | 0 | 16.25 | 8.8889 | 2.9861 | 21.1022 | 10.2823 | 3.4274 | 15.2554 | 7.1237 | 2.957 | 7.3611 | 3.2639 | 0 | 3.0914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.5 | 8 | 0 | 0 | 0 | 1.3393 | 0 | 0 | 3.4274 | 0 | 0 | 9.375 | 4.1667 | 0 | 12.9704 | 7.7285 | 2.2177 | 19.1667 | 11.1111 | 3.8889 | 22.1102 | 11.4247 | 3.9651 | 16.5323 | 8.1317 | 3.0914 | 8.0556 | 3.3333 | 0 | 3.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.5 | 9 | 0 | 0 | 0 | 1.3393 | 0 | 0 | 3.4274 | 0 | 0 | 9.375 | 4.1667 | 0 | 13.4409 | 7.7285 | 2.2177 | 19.1667 | 11.1111 | 3.8889 | 22.1102 | 11.4247 | 3.9651 | 16.5995 | 8.1317 | 3.0914 | 8.0556 | 3.3333 | 0 | 3.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.5 | 10 | 0 | 0 | 0 | 1.3393 | 0 | 0 | 3.4274 | 0 | 0 | 9.375 | 4.1667 | 0 | 13.4409 | 7.7285 | 2.2177 | 19.1667 | 11.1111 | 3.8889 | 22.1102 | 11.4247 | 3.9651 | 16.5995 | 8.1317 | 3.0914 | 8.0556 | 3.3333 | 0 | 3.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.5 | 11 | 0 | 0 | 0 | 1.3393 | 0 | 0 | 3.4274 | 0 | 0 | 9.375 | 4.1667 | 0 | 13.4409 | 7.7285 | 2.2177 | 19.1667 | 11.1111 | 3.8889 | 22.1102 | 11.4247 | 3.9651 | 16.5995 | 8.1317 | 3.0914 | 8.0556 | 3.3333 | 0 | 3.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.5 | 12 | 0 | 0 | 0 | 1.3393 | 0 | 0 | 3.4274 | 0 | 0 | 9.375 | 4.1667 | 0 | 13.4409 | 7.7285 | 2.2177 | 19.1667 | 11.1111 | 3.8889 | 22.1102 | 11.4247 | 3.9651 | 16.5995 | 8.1317 | 3.0914 | 8.0556 | 3.3333 | 0 | 3.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.5 | 15 | 0 | 0 | 0 | 1.3393 | 0 | 0 | 3.4274 | 0 | 0 | 9.375 | 4.1667 | 0 | 13.4409 | 7.7285 | 2.2177 | 19.1667 | 11.1111 | 3.8889 | 22.1102 | 11.4247 | 3.9651 | 16.5995 | 8.1317 | 3.0914 | 8.0556 | 3.3333 | 0 | 3.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.5 | 20 | 0 | 0 | 0 | 1.3393 | 0 | 0 | 3.4274 | 0 | 0 | 9.375 | 4.1667 | 0 | 13.4409 | 7.7285 | 2.2177 | 19.1667 | 11.1111 | 3.8889 | 22.1102 | 11.4247 | 3.9651 | 16.5995 | 8.1317 | 3.0914 | 8.0556 | 3.3333 | 0 | 3.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.5 | 25 | 0 | 0 | 0 | 1.3393 | 0 | 0 | 3.4274 | 0 | 0 | 9.375 | 4.1667 | 0 | 13.4409 | 7.7285 | 2.2177 | 19.1667 | 11.1111 | 3.8889 | 22.1102 | 11.4247 | 3.9651 | 16.5995 | 8.1317 | 3.0914 | 8.0556 | 3.3333 | 0 | 3.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0.75 | 4 | 0 | 0 | 0 | 3.4226 | 0 | 0 | 3.293 | 0 | 0 | 6.1111 | 2.7778 | 0 | 6.6532 | 3.0914 | 0 | 14.5139 | 4.5139 | 2.8472 | 10.6183 | 4.0323 | 0 | 7.9301 | 4.4355 | 0 | 4.5139 | 0 | 0 | 2.8898 | 0 | 0 | 0.69444 | 0 | 0 | 2.4866 | 0 | 0
18 | 0.75 | 6 | 4.2339 | 0 | 0 | 8.1153 | 3.125 | 0 | 11.0887 | 2.957 | 0 | 22.7083 | 11.9444 | 6.7361 | 21.371 | 13.5081 | 9.7446 | 29.2361 | 18.5417 | 10.0694 | 27.0161 | 19.2204 | 14.0457 | 28.1586 | 16.5323 | 10.0806 | 17.4306 | 9.0278 | 0.55556 | 6.5188 | 2.2849 | 0 | 5.1389 | 0 | 0 | 5.1747 | 0 | 0
18 | 0.75 | 8 | 7.7957 | 0 | 0 | 10.1935 | 4.0923 | 0 | 17.0699 | 4.9731 | 1.8145 | 29.4444 | 20.3472 | 9.4444 | 31.0484 | 23.3871 | 14.3817 | 40.9028 | 25.6944 | 18.5417 | 41.2634 | 29.7715 | 21.5726 | 37.9032 | 25.5376 | 16.1962 | 24.4444 | 12.9167 | 5.9722 | 10.3495 | 3.7634 | 0 | 6.5972 | 0 | 0 | 5.914 | 2.7554 | 0
18 | 0.75 | 9 | 7.7957 | 0 | 0 | 10.1935 | 4.0923 | 0 | 17.2715 | 4.9731 | 1.8145 | 30 | 20.9722 | 9.4444 | 32.9301 | 23.8575 | 14.5161 | 41.3194 | 25.9722 | 18.75 | 41.8683 | 30.8468 | 23.3199 | 40.121 | 27.8226 | 16.7339 | 24.5833 | 12.9861 | 6.0417 | 10.3495 | 3.7634 | 0 | 6.5972 | 0 | 0 | 6.25 | 2.7554 | 0
18 | 0.75 | 10 | 7.7957 | 0 | 0 | 10.1935 | 4.0923 | 0 | 17.2715 | 4.9731 | 1.8145 | 30 | 20.9722 | 9.4444 | 34.4086 | 23.9919 | 14.5833 | 41.3194 | 25.9722 | 18.75 | 41.9355 | 30.8468 | 23.3199 | 40.121 | 27.8898 | 16.7339 | 24.5833 | 12.9861 | 6.0417 | 10.3495 | 3.7634 | 0 | 6.5972 | 0 | 0 | 6.25 | 2.7554 | 0
18 | 0.75 | 11 | 7.7957 | 0 | 0 | 10.1935 | 4.0923 | 0 | 17.2715 | 4.9731 | 1.8145 | 30 | 20.9722 | 9.4444 | 34.4758 | 23.9919 | 14.5833 | 41.3194 | 25.9722 | 18.75 | 41.9355 | 30.8468 | 23.3199 | 40.121 | 27.8898 | 16.7339 | 24.5833 | 12.9861 | 6.0417 | 10.3495 | 3.7634 | 0 | 6.5972 | 0 | 0 | 6.25 | 2.7554 | 0
18 | 0.75 | 12 | 7.7957 | 0 | 0 | 10.1935 | 4.0923 | 0 | 17.2715 | 4.9731 | 1.8145 | 30 | 20.9722 | 9.4444 | 34.4758 | 23.9919 | 14.5833 | 41.3194 | 25.9722 | 18.75 | 41.9355 | 30.8468 | 23.3199 | 40.121 | 27.8898 | 16.7339 | 24.5833 | 12.9861 | 6.0417 | 10.3495 | 3.7634 | 0 | 6.5972 | 0 | 0 | 6.25 | 2.7554 | 0
18 | 0.75 | 15 | 7.7957 | 0 | 0 | 10.1935 | 4.0923 | 0 | 17.2715 | 4.9731 | 1.8145 | 30 | 20.9722 | 9.4444 | 34.4758 | 23.9919 | 14.5833 | 41.3194 | 25.9722 | 18.75 | 41.9355 | 30.8468 | 23.3199 | 40.121 | 27.8898 | 16.7339 | 24.5833 | 12.9861 | 6.0417 | 10.3495 | 3.7634 | 0 | 6.5972 | 0 | 0 | 6.25 | 2.7554 | 0
18 | 0.75 | 20 | 7.7957 | 0 | 0 | 10.1935 | 4.0923 | 0 | 17.2715 | 4.9731 | 1.8145 | 30 | 20.9722 | 9.4444 | 34.4758 | 23.9919 | 14.5833 | 41.3194 | 25.9722 | 18.75 | 41.9355 | 30.8468 | 23.3199 | 40.121 | 27.8898 | 16.7339 | 24.5833 | 12.9861 | 6.0417 | 10.3495 | 3.7634 | 0 | 6.5972 | 0 | 0 | 6.25 | 2.7554 | 0
18 | 0.75 | 25 | 7.7957 | 0 | 0 | 10.1935 | 4.0923 | 0 | 17.2715 | 4.9731 | 1.8145 | 30 | 20.9722 | 9.4444 | 34.4758 | 23.9919 | 14.5833 | 41.3194 | 25.9722 | 18.75 | 41.9355 | 30.8468 | 23.3199 | 40.121 | 27.8898 | 16.7339 | 24.5833 | 12.9861 | 6.0417 | 10.3495 | 3.7634 | 0 | 6.5972 | 0 | 0 | 6.25 | 2.7554 | 0
18 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 1 | 4 | 0.26882 | 0 | 0 | 3.5817 | 0 | 0 | 5.2419 | 0 | 0 | 8.1944 | 3.5417 | 0 | 7.5269 | 4.2339 | 0 | 15.7639 | 7.5694 | 2.8472 | 11.1559 | 5.914 | 2.0833 | 11.828 | 5.7796 | 2.4866 | 6.1806 | 0.90278 | 0 | 3.1586 | 0 | 0 | 2.6389 | 0 | 0 | 2.957 | 0 | 0
18 | 1 | 6 | 7.9973 | 2.8898 | 0 | 14.5089 | 6.7888 | 0 | 16.6667 | 7.8629 | 2.7554 | 27.0139 | 16.5278 | 11.3889 | 27.3522 | 21.3038 | 13.9785 | 38.3333 | 23.6806 | 15.9722 | 32.6613 | 24.1935 | 17.2715 | 33.6022 | 21.3038 | 13.7769 | 22.9861 | 16.0417 | 5.3472 | 12.0968 | 5.1075 | 0 | 9.0278 | 3.5417 | 0 | 9.8118 | 4.8387 | 0
18 | 1 | 8 | 16.4651 | 6.25 | 0.94086 | 24.628 | 13.7649 | 3.4226 | 26.8145 | 15.3898 | 6.4516 | 40.8333 | 32.5 | 20.2778 | 47.6478 | 37.2312 | 29.5027 | 52.0833 | 42.1528 | 32.4306 | 56.0484 | 44.7581 | 32.4597 | 54.8387 | 37.4328 | 31.6532 | 37.7083 | 27.0139 | 16.4583 | 20.2957 | 10.4839 | 5.1075 | 14.7222 | 6.6667 | 0.69444 | 18.2124 | 6.586 | 0
18 | 1 | 9 | 17.6747 | 6.922 | 2.1505 | 25.2874 | 15.3274 | 3.7202 | 28.4274 | 18.2124 | 7.1909 | 43.9583 | 35.625 | 25.5556 | 53.293 | 41.8683 | 32.6613 | 56.3889 | 46.3194 | 36.0417 | 63.5753 | 48.0511 | 36.9624 | 58.8038 | 43.4812 | 35.2151 | 42.0139 | 31.0417 | 17.9861 | 20.4973 | 12.7016 | 5.9812 | 14.9306 | 7.7083 | 2.0139 | 19.2204 | 7.4597 | 0
18 | 1 | 10 | 17.6747 | 6.9892 | 2.1505 | 25.2874 | 15.3274 | 3.7382 | 28.5618 | 18.2796 | 7.5269 | 44.5139 | 37.0833 | 25.6944 | 54.3011 | 43.4812 | 34.8118 | 57.5 | 46.875 | 36.875 | 64.2473 | 48.9919 | 38.4409 | 59.1398 | 43.75 | 36.6263 | 42.4306 | 32.2222 | 18.6111 | 21.9758 | 12.7016 | 5.9812 | 15.0694 | 7.7083 | 2.0139 | 19.2204 | 8.6694 | 0
18 | 1 | 11 | 17.6747 | 6.9892 | 2.1505 | 25.2874 | 15.3274 | 3.7382 | 28.5618 | 18.2796 | 7.5269 | 44.5139 | 37.4306 | 26.1111 | 54.4355 | 43.5484 | 34.8118 | 57.5 | 46.875 | 36.875 | 64.3145 | 49.0591 | 38.5081 | 59.207 | 43.9516 | 36.6263 | 42.5 | 32.2222 | 18.6111 | 21.9758 | 12.7016 | 5.9812 | 15.0694 | 7.7083 | 2.0139 | 19.2204 | 8.6694 | 0
18 | 1 | 12 | 17.6747 | 6.9892 | 2.1505 | 25.2874 | 15.3274 | 3.7382 | 28.5618 | 18.2796 | 7.5269 | 44.5139 | 37.4306 | 26.1111 | 54.4355 | 43.5484 | 34.8118 | 57.5 | 46.875 | 36.875 | 64.3145 | 49.0591 | 38.5081 | 59.207 | 43.9516 | 36.6263 | 42.5 | 32.2222 | 18.6111 | 21.9758 | 12.7016 | 5.9812 | 15.0694 | 7.7083 | 2.0139 | 19.2204 | 8.6694 | 0
18 | 1 | 15 | 17.6747 | 6.9892 | 2.1505 | 25.2874 | 15.3274 | 3.7382 | 28.5618 | 18.2796 | 7.5269 | 44.5139 | 37.4306 | 26.1111 | 54.4355 | 43.5484 | 34.8118 | 57.5 | 46.875 | 36.875 | 64.3145 | 49.0591 | 38.5081 | 59.207 | 43.9516 | 36.6263 | 42.5 | 32.2222 | 18.6111 | 21.9758 | 12.7016 | 5.9812 | 15.0694 | 7.7083 | 2.0139 | 19.2204 | 8.6694 | 0
18 | 1 | 20 | 17.6747 | 6.9892 | 2.1505 | 25.2874 | 15.3274 | 3.7382 | 28.5618 | 18.2796 | 7.5269 | 44.5139 | 37.4306 | 26.1111 | 54.4355 | 43.5484 | 34.8118 | 57.5 | 46.875 | 36.875 | 64.3145 | 49.0591 | 38.5081 | 59.207 | 43.9516 | 36.6263 | 42.5 | 32.2222 | 18.6111 | 21.9758 | 12.7016 | 5.9812 | 15.0694 | 7.7083 | 2.0139 | 19.2204 | 8.6694 | 0
18 | 1 | 25 | 17.6747 | 6.9892 | 2.1505 | 25.2874 | 15.3274 | 3.7382 | 28.5618 | 18.2796 | 7.5269 | 44.5139 | 37.4306 | 26.1111 | 54.4355 | 43.5484 | 34.8118 | 57.5 | 46.875 | 36.875 | 64.3145 | 49.0591 | 38.5081 | 59.207 | 43.9516 | 36.6263 | 42.5 | 32.2222 | 18.6111 | 21.9758 | 12.7016 | 5.9812 | 15.0694 | 7.7083 | 2.0139 | 19.2204 | 8.6694 | 0
18 | 1.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 1.25 | 4 | 1.7473 | 0 | 0 | 4.5438 | 0 | 0 | 6.4516 | 0 | 0 | 9.2361 | 4.0278 | 0 | 8.0645 | 4.5027 | 0 | 16.5972 | 7.5694 | 2.9861 | 11.1559 | 5.9812 | 2.0833 | 11.8952 | 6.3172 | 2.5538 | 6.1806 | 2.0833 | 0 | 3.3602 | 0 | 0 | 3.2639 | 0 | 0 | 4.9059 | 0 | 0
18 | 1.25 | 6 | 12.9704 | 4.5027 | 0 | 18.0804 | 10.7425 | 1.7113 | 18.2796 | 10.2151 | 3.4274 | 28.8194 | 19.2361 | 12.9861 | 29.9731 | 25.1344 | 17.0699 | 40.2778 | 28.1944 | 19.4444 | 35.3495 | 26.5457 | 17.4059 | 34.9462 | 24.328 | 14.7177 | 26.6667 | 16.5278 | 9.8611 | 16.2634 | 7.0565 | 2.4866 | 11.9444 | 6.5972 | 0 | 13.3737 | 4.8387 | 0
18 | 1.25 | 8 | 24.664 | 9.9462 | 3.1586 | 32.2917 | 21.6928 | 8.4077 | 37.0296 | 22.9839 | 10.7527 | 49.4444 | 39.1667 | 29.4444 | 54.9059 | 46.1694 | 39.9866 | 61.6667 | 51.5972 | 39.375 | 64.5161 | 53.4946 | 40.5914 | 57.5269 | 47.6478 | 36.6263 | 44.6528 | 35.9028 | 21.7361 | 27.621 | 18.4812 | 10.2823 | 20.2083 | 11.5278 | 7.0139 | 25.5376 | 12.2984 | 3.0242
18 | 1.25 | 9 | 25.9409 | 12.7016 | 3.5618 | 39.5089 | 23.8506 | 11.0119 | 41.0618 | 28.4946 | 16.1962 | 55.6944 | 46.8056 | 36.8056 | 63.6425 | 55.2419 | 47.7823 | 67.2222 | 59.4444 | 48.4722 | 75.4032 | 61.828 | 48.5887 | 66.8683 | 55.578 | 47.9839 | 49.375 | 40.3472 | 25.6944 | 30.578 | 22.5134 | 11.3575 | 24.7222 | 14.7917 | 7.2222 | 28.2258 | 15.1882 | 4.8387
18 | 1.25 | 10 | 28.1586 | 13.9113 | 4.9059 | 40.1786 | 24.4971 | 11.2351 | 41.7339 | 30.7124 | 18.0108 | 64.0278 | 49.375 | 41.3194 | 68.2796 | 60.4839 | 50.9409 | 71.1111 | 65.625 | 51.6667 | 79.3683 | 66.8683 | 54.2339 | 72.1774 | 59.543 | 49.9328 | 54.3056 | 43.9583 | 30.9028 | 33.3333 | 23.3871 | 13.5081 | 26.4583 | 16.5278 | 7.3611 | 29.0323 | 16.0618 | 5.4435
18 | 1.25 | 11 | 28.1586 | 13.9113 | 4.9731 | 40.253 | 24.7024 | 11.2351 | 43.2796 | 30.914 | 18.078 | 64.7917 | 50.7639 | 41.7361 | 68.6828 | 61.6263 | 51.3441 | 72.5694 | 66.25 | 52.2222 | 80.5108 | 67.6075 | 56.3172 | 72.8495 | 61.0215 | 51.2097 | 56.1806 | 44.2361 | 31.3194 | 33.5349 | 23.7231 | 13.8441 | 26.7361 | 16.5278 | 7.4306 | 29.0995 | 16.129 | 5.5108
18 | 1.25 | 12 | 28.1586 | 13.9113 | 4.9731 | 40.253 | 24.7024 | 11.2351 | 43.414 | 31.0484 | 18.9516 | 64.7917 | 50.7639 | 41.875 | 69.0188 | 62.2312 | 52.4194 | 72.7083 | 66.4583 | 52.2917 | 80.578 | 67.6075 | 56.6532 | 73.1183 | 61.0887 | 51.3441 | 56.5972 | 44.3056 | 31.3889 | 33.7366 | 23.7231 | 13.9113 | 26.7361 | 16.5278 | 7.4306 | 29.0995 | 16.129 | 5.578
18 | 1.25 | 15 | 28.1586 | 13.9113 | 4.9731 | 40.253 | 24.7024 | 11.2351 | 43.414 | 31.0484 | 18.9516 | 64.7917 | 50.7639 | 41.875 | 69.2204 | 62.2984 | 52.4194 | 72.8472 | 66.4583 | 52.3611 | 80.578 | 67.6075 | 56.7876 | 73.1183 | 61.0887 | 51.3441 | 56.5972 | 44.3056 | 31.3889 | 33.7366 | 23.7231 | 13.9113 | 26.7361 | 16.5278 | 7.4306 | 29.0995 | 16.129 | 5.578
18 | 1.25 | 20 | 28.1586 | 13.9113 | 4.9731 | 40.253 | 24.7024 | 11.2351 | 43.414 | 31.0484 | 18.9516 | 64.7917 | 50.7639 | 41.875 | 69.2204 | 62.2984 | 52.4194 | 72.8472 | 66.4583 | 52.3611 | 80.578 | 67.6075 | 56.7876 | 73.1183 | 61.0887 | 51.3441 | 56.5972 | 44.3056 | 31.3889 | 33.7366 | 23.7231 | 13.9113 | 26.7361 | 16.5278 | 7.4306 | 29.0995 | 16.129 | 5.578
18 | 1.25 | 25 | 28.1586 | 13.9113 | 4.9731 | 40.253 | 24.7024 | 11.2351 | 43.414 | 31.0484 | 18.9516 | 64.7917 | 50.7639 | 41.875 | 69.2204 | 62.2984 | 52.4194 | 72.8472 | 66.4583 | 52.3611 | 80.578 | 67.6075 | 56.7876 | 73.1183 | 61.0887 | 51.3441 | 56.5972 | 44.3056 | 31.3889 | 33.7366 | 23.7231 | 13.9113 | 26.7361 | 16.5278 | 7.4306 | 29.0995 | 16.129 | 5.578
18 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 1.5 | 4 | 2.0161 | 0 | 0 | 4.5438 | 0 | 0 | 6.4516 | 2.4194 | 0 | 10 | 5.3472 | 0 | 8.6022 | 4.7715 | 0 | 16.5972 | 7.5694 | 2.9861 | 11.2903 | 5.9812 | 2.0833 | 11.9624 | 6.3172 | 2.5538 | 6.1806 | 2.0833 | 0 | 3.4274 | 1.4113 | 0 | 3.2639 | 0 | 0 | 6.1828 | 0 | 0
18 | 1.5 | 6 | 15.7258 | 5.4435 | 0.33602 | 21.8519 | 11.4712 | 3.3482 | 20.6317 | 10.8871 | 4.6371 | 30.2083 | 19.7222 | 15.8333 | 31.6532 | 26.8145 | 18.1452 | 43.75 | 29.4444 | 19.7917 | 35.4167 | 27.0833 | 18.6156 | 34.9462 | 25.0672 | 15.457 | 28.6111 | 17.5694 | 11.8056 | 16.7339 | 8.9382 | 3.0242 | 12.4306 | 7.4306 | 0 | 14.4489 | 7.3253 | 1.2097
18 | 1.5 | 8 | 28.629 | 14.5833 | 6.1156 | 36.9792 | 25.7902 | 10.5655 | 39.4489 | 30.0403 | 16.129 | 53.9583 | 44.9306 | 33.75 | 60.0806 | 51.3441 | 41.6667 | 65.6944 | 56.5972 | 43.8889 | 67.6075 | 56.5188 | 43.3468 | 58.871 | 50.9409 | 41.4651 | 48.2639 | 40.1389 | 23.9583 | 30.1075 | 21.5726 | 12.6344 | 24.3056 | 16.4583 | 8.6806 | 28.4946 | 14.5833 | 6.1828
18 | 1.5 | 9 | 32.6613 | 18.5484 | 8.5349 | 44.7173 | 31.0268 | 14.2113 | 44.6909 | 35.2151 | 21.0349 | 61.875 | 52.3611 | 44.9306 | 70.6989 | 60.4167 | 53.4946 | 74.1667 | 67.6389 | 56.1806 | 79.4355 | 66.4651 | 56.6532 | 72.2446 | 62.164 | 52.957 | 57.9167 | 47.2917 | 33.9583 | 37.2312 | 29.7043 | 19.3548 | 30.9722 | 21.5972 | 9.4444 | 34.207 | 21.5726 | 9.3414
18 | 1.5 | 10 | 35.9543 | 21.9086 | 11.6935 | 47.9167 | 33.4821 | 17.4107 | 49.5968 | 40.0538 | 28.5618 | 69.5833 | 59.2361 | 49.4444 | 76.3441 | 69.9597 | 58.4005 | 79.3056 | 75.4861 | 62.7778 | 84.879 | 74.7984 | 66.0618 | 78.1586 | 67.6075 | 59.6774 | 63.8889 | 52.6389 | 40.9722 | 42.1371 | 33.8038 | 21.371 | 37.2917 | 25.9722 | 10.7639 | 36.0887 | 24.328 | 10.8871
18 | 1.5 | 11 | 39.7177 | 22.7151 | 12.164 | 49.1071 | 36.2351 | 17.9315 | 52.5538 | 42.2715 | 29.3683 | 71.25 | 62.2222 | 51.5972 | 78.8978 | 72.5134 | 61.8952 | 81.5972 | 78.1944 | 66.1806 | 86.9624 | 79.5699 | 68.3468 | 80.8468 | 71.1022 | 61.3575 | 67.0139 | 54.5833 | 44.5833 | 45.2285 | 36.1559 | 24.1935 | 38.6806 | 28.4722 | 11.3889 | 37.6344 | 25 | 11.9624
18 | 1.5 | 12 | 39.9194 | 22.7823 | 12.9032 | 49.1815 | 37.3563 | 17.9315 | 53.1586 | 42.4059 | 29.7715 | 71.6667 | 62.5 | 52.2917 | 80.1747 | 73.5887 | 63.6425 | 82.5694 | 78.6111 | 67.0139 | 87.2984 | 81.1156 | 69.3548 | 81.5188 | 71.371 | 61.7608 | 67.2222 | 56.0417 | 46.1111 | 46.3038 | 36.8952 | 24.328 | 39.9306 | 28.6111 | 11.6667 | 37.9032 | 25.7392 | 11.9624
18 | 1.5 | 15 | 40.0538 | 22.7823 | 12.9032 | 49.628 | 38.6494 | 17.9315 | 53.2258 | 42.4731 | 29.7715 | 71.7361 | 62.7083 | 52.3611 | 80.2419 | 73.7231 | 63.7769 | 82.9167 | 78.75 | 67.0139 | 87.3656 | 81.1156 | 69.5565 | 81.586 | 71.4382 | 63.6425 | 67.2917 | 56.1111 | 46.1806 | 46.3038 | 37.0968 | 24.4624 | 40.0694 | 29.0972 | 11.6667 | 37.9032 | 25.8065 | 11.9624
18 | 1.5 | 20 | 40.0538 | 22.7823 | 12.9032 | 49.628 | 38.6494 | 17.9315 | 53.2258 | 42.4731 | 29.7715 | 71.7361 | 62.7083 | 52.3611 | 80.2419 | 73.7231 | 63.7769 | 82.9167 | 78.75 | 67.0139 | 87.3656 | 81.1156 | 69.5565 | 81.586 | 71.4382 | 63.6425 | 67.2917 | 56.1111 | 46.1806 | 46.3038 | 37.0968 | 24.4624 | 40.0694 | 29.0972 | 11.6667 | 37.9032 | 25.8065 | 11.9624
18 | 1.5 | 25 | 40.0538 | 22.7823 | 12.9032 | 49.628 | 38.6494 | 17.9315 | 53.2258 | 42.4731 | 29.7715 | 71.7361 | 62.7083 | 52.3611 | 80.2419 | 73.7231 | 63.7769 | 82.9167 | 78.75 | 67.0139 | 87.3656 | 81.1156 | 69.5565 | 81.586 | 71.4382 | 63.6425 | 67.2917 | 56.1111 | 46.1806 | 46.3038 | 37.0968 | 24.4624 | 40.0694 | 29.0972 | 11.6667 | 37.9032 | 25.8065 | 11.9624
18 | 1.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 1.75 | 4 | 3.0914 | 0 | 0 | 4.5438 | 1.3393 | 0 | 6.4516 | 2.4194 | 0 | 10 | 5.3472 | 0 | 8.6022 | 4.7715 | 0 | 16.5972 | 7.5694 | 3.0556 | 11.4247 | 5.9812 | 2.0833 | 11.9624 | 6.3172 | 2.5538 | 6.1806 | 2.0833 | 0 | 3.7634 | 1.4113 | 0 | 3.6111 | 0 | 0 | 6.1828 | 0 | 0
18 | 1.75 | 6 | 17.0027 | 5.9177 | 2.621 | 22.3214 | 12.2152 | 3.5714 | 20.9677 | 12.3656 | 6.6532 | 30.8333 | 20.8333 | 15.9028 | 32.9301 | 26.8145 | 18.2124 | 43.8194 | 29.9306 | 20.9028 | 35.4167 | 27.0833 | 18.75 | 35.0806 | 25.0672 | 16.0618 | 29.0278 | 18.1944 | 11.8056 | 17.6747 | 10.2151 | 3.4274 | 14.2361 | 7.9861 | 3.4028 | 14.7849 | 8.4005 | 2.621
18 | 1.75 | 8 | 29.9059 | 17.0027 | 6.5188 | 39.0625 | 27.5862 | 12.7232 | 40.793 | 31.4516 | 19.6909 | 55.625 | 45.6944 | 35.7639 | 61.7608 | 52.8898 | 43.9516 | 66.6667 | 58.6111 | 45.8333 | 68.0108 | 57.8629 | 46.6398 | 60.6855 | 53.4274 | 42.7419 | 49.4444 | 42.2917 | 25.4861 | 33.1989 | 26.9489 | 13.5081 | 30.7639 | 20.0694 | 11.8056 | 30.2419 | 17.2715 | 8.8038
18 | 1.75 | 9 | 36.4919 | 22.379 | 11.9624 | 47.5446 | 36.6379 | 17.3363 | 49.3952 | 38.7769 | 26.9489 | 66.7361 | 56.6667 | 48.2639 | 74.0591 | 63.3065 | 55.914 | 76.5972 | 70.4167 | 58.8889 | 80.8468 | 68.1452 | 57.3925 | 74.1263 | 64.1129 | 55.0403 | 62.2222 | 50.2083 | 36.9444 | 40.3226 | 34.0054 | 21.0349 | 38.3333 | 28.4028 | 13.3333 | 38.5081 | 25.2688 | 11.5591
18 | 1.75 | 10 | 44.7581 | 28.6962 | 16.5995 | 54.0923 | 42.4056 | 21.0565 | 58.871 | 45.5645 | 33.0645 | 74.8611 | 64.3056 | 56.8056 | 80.6452 | 73.9919 | 65.3226 | 83.8889 | 79.2361 | 68.1944 | 89.4489 | 80.7796 | 72.1102 | 80.914 | 71.371 | 64.3817 | 68.125 | 58.6111 | 45.8333 | 46.5726 | 39.5161 | 25.8737 | 45.9028 | 32.1528 | 17.8472 | 43.078 | 30.4435 | 15.6586
18 | 1.75 | 11 | 47.6478 | 32.8629 | 18.6156 | 60.2679 | 47.3343 | 22.9167 | 64.5833 | 50.6048 | 39.1129 | 79.7222 | 70.6944 | 62.6389 | 86.2231 | 78.8978 | 72.2446 | 87.5694 | 84.375 | 74.375 | 92.4059 | 86.5591 | 77.5538 | 85.3495 | 77.4194 | 69.9597 | 74.2361 | 62.6389 | 52.9167 | 51.5457 | 44.9597 | 30.8468 | 50.4861 | 36.9444 | 19.1667 | 44.3548 | 33.6694 | 16.3978
18 | 1.75 | 12 | 47.8495 | 33.8038 | 20.6989 | 61.0119 | 47.9885 | 25.0744 | 70.3629 | 53.2258 | 40.5242 | 81.8056 | 73.2639 | 64.0972 | 87.9032 | 82.7285 | 75.2688 | 88.8889 | 85.1389 | 77.1528 | 94.2876 | 87.5672 | 79.9059 | 86.9624 | 79.9731 | 71.6398 | 78.125 | 65.4167 | 55.2083 | 54.7043 | 47.7823 | 32.9301 | 51.6667 | 40.0694 | 20.8333 | 45.6989 | 35.4839 | 18.3468
18 | 1.75 | 15 | 47.9167 | 34.4086 | 20.9677 | 62.5 | 49.1918 | 25.372 | 70.6989 | 53.8306 | 40.9274 | 82.6389 | 74.6528 | 64.3056 | 88.2392 | 83.6694 | 75.7392 | 89.1667 | 85.625 | 77.5 | 95.1613 | 88.0376 | 80.1075 | 87.5672 | 80.1747 | 72.5134 | 78.8194 | 66.6667 | 57.3611 | 56.3844 | 48.3871 | 34.207 | 52.2222 | 40.7639 | 21.9444 | 46.1694 | 36.8952 | 18.6828
18 | 1.75 | 20 | 47.9167 | 34.4086 | 20.9677 | 62.5 | 49.1918 | 25.372 | 70.6989 | 53.8306 | 40.9274 | 82.6389 | 74.6528 | 64.3056 | 88.2392 | 83.6694 | 75.7392 | 89.1667 | 85.625 | 77.5 | 95.1613 | 88.0376 | 80.1075 | 87.5672 | 80.1747 | 72.5134 | 78.8194 | 66.6667 | 57.3611 | 56.3844 | 48.3871 | 34.207 | 52.2222 | 40.7639 | 21.9444 | 46.1694 | 36.8952 | 18.6828
18 | 1.75 | 25 | 47.9167 | 34.4086 | 20.9677 | 62.5 | 49.1918 | 25.372 | 70.6989 | 53.8306 | 40.9274 | 82.6389 | 74.6528 | 64.3056 | 88.2392 | 83.6694 | 75.7392 | 89.1667 | 85.625 | 77.5 | 95.1613 | 88.0376 | 80.1075 | 87.5672 | 80.1747 | 72.5134 | 78.8194 | 66.6667 | 57.3611 | 56.3844 | 48.3871 | 34.207 | 52.2222 | 40.7639 | 21.9444 | 46.1694 | 36.8952 | 18.6828
18 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2 | 4 | 3.293 | 0 | 0 | 4.5438 | 2.8274 | 0 | 6.4516 | 2.4194 | 0 | 10 | 5.3472 | 0 | 8.6022 | 4.7715 | 0 | 16.5972 | 7.5694 | 3.0556 | 11.4247 | 5.9812 | 2.0833 | 11.9624 | 6.3172 | 2.5538 | 6.1806 | 2.5 | 0 | 4.0995 | 1.4113 | 0 | 3.6111 | 0 | 0 | 6.1828 | 0 | 0
18 | 2 | 6 | 17.4059 | 6.2542 | 2.621 | 22.7679 | 13.0054 | 3.7946 | 21.1694 | 12.836 | 6.6532 | 31.3194 | 20.9722 | 15.9028 | 32.9301 | 26.8817 | 18.2124 | 43.8194 | 30.4167 | 20.9028 | 35.4167 | 27.0833 | 18.75 | 35.0806 | 25.0672 | 16.0618 | 29.0278 | 18.6806 | 11.8056 | 17.9435 | 10.4839 | 3.4274 | 14.5139 | 8.4028 | 3.6111 | 16.0618 | 9.0054 | 2.6882
18 | 2 | 8 | 32.3925 | 17.4731 | 7.7285 | 40.6994 | 29.7414 | 13.1696 | 40.9274 | 31.7204 | 20.1613 | 58.1944 | 48.0556 | 39.4444 | 61.828 | 54.4355 | 44.5565 | 66.8056 | 58.9583 | 46.3194 | 68.078 | 57.9301 | 47.1774 | 60.8871 | 53.4274 | 42.9435 | 51.1111 | 42.9861 | 26.4583 | 35.0134 | 27.4866 | 15.793 | 32.0833 | 20.4167 | 12.3611 | 33.4005 | 19.6237 | 9.2742
18 | 2 | 9 | 38.172 | 22.9839 | 12.9704 | 49.5536 | 39.3345 | 19.4196 | 53.2258 | 40.6586 | 29.0995 | 69.0972 | 58.1944 | 50.625 | 74.9328 | 67.2043 | 57.7285 | 77.7778 | 71.0417 | 59.5139 | 83.1317 | 68.2124 | 57.7285 | 75.672 | 65.7258 | 55.6452 | 63.1944 | 50.7639 | 37.5 | 42.6075 | 35.0134 | 22.6478 | 41.9444 | 29.5139 | 15.3472 | 39.9866 | 27.3522 | 13.4409
18 | 2 | 10 | 46.5054 | 32.2581 | 18.8844 | 58.5565 | 45.6101 | 23.7351 | 63.0376 | 49.5968 | 37.4328 | 77.9861 | 67.1528 | 60.625 | 81.9892 | 75.4704 | 67.8091 | 85.625 | 80.7639 | 71.3194 | 90.6586 | 81.6532 | 74.2608 | 82.9301 | 74.7984 | 66.8011 | 71.5278 | 61.0417 | 51.4583 | 51.8145 | 43.8844 | 30.7796 | 51.1111 | 36.8056 | 22.0833 | 46.6398 | 33.8038 | 19.086
18 | 2 | 11 | 49.9328 | 38.172 | 23.9919 | 65.6994 | 54.0281 | 28.6458 | 73.1183 | 57.0565 | 46.2366 | 83.6806 | 75.5556 | 66.6667 | 89.3817 | 81.7204 | 77.6882 | 91.3889 | 87.8472 | 79.8611 | 94.9597 | 88.3065 | 80.914 | 88.0376 | 82.5941 | 76.2769 | 79.5139 | 67.3611 | 56.3194 | 59.2742 | 50.5376 | 36.828 | 55.4861 | 45.0694 | 28.2639 | 52.4194 | 39.6505 | 21.1694
18 | 2 | 12 | 54.9731 | 41.3978 | 27.957 | 70.0149 | 56.25 | 34.4956 | 78.4946 | 63.3737 | 50 | 88.8194 | 80.2083 | 69.4444 | 91.5323 | 86.4919 | 81.6532 | 93.1944 | 89.3056 | 83.6111 | 96.707 | 91.4651 | 84.207 | 90.0538 | 85.4167 | 79.2339 | 81.0417 | 71.7361 | 60 | 64.5161 | 52.4866 | 45.6989 | 60.7639 | 46.8056 | 31.5972 | 56.0484 | 41.4651 | 24.9328
18 | 2 | 15 | 58.3333 | 43.5484 | 31.5188 | 72.9911 | 57.5893 | 35.0857 | 79.7043 | 66.0618 | 51.8145 | 90.2083 | 82.2917 | 71.3194 | 92.6075 | 88.6425 | 84.1398 | 93.8194 | 90.0694 | 85.0694 | 97.1774 | 93.0108 | 86.4919 | 92.1371 | 86.4919 | 80.3091 | 82.5 | 73.8889 | 61.7361 | 68.6156 | 56.5188 | 46.7742 | 63.6111 | 49.0278 | 33.75 | 58.1989 | 43.2796 | 25.9409
18 | 2 | 20 | 58.3333 | 43.9516 | 31.5188 | 72.9911 | 57.6637 | 35.0857 | 79.7043 | 66.0618 | 51.8145 | 90.2083 | 82.2917 | 71.3194 | 92.6075 | 88.6425 | 84.1398 | 93.8194 | 90.0694 | 85.0694 | 97.1774 | 93.0108 | 86.4919 | 92.1371 | 86.4919 | 80.3091 | 82.5 | 73.8889 | 61.7361 | 68.6156 | 56.5188 | 46.7742 | 63.6806 | 49.0278 | 33.75 | 58.1989 | 43.2796 | 25.9409
18 | 2 | 25 | 58.3333 | 43.9516 | 31.5188 | 72.9911 | 57.6637 | 35.0857 | 79.7043 | 66.0618 | 51.8145 | 90.2083 | 82.2917 | 71.3194 | 92.6075 | 88.6425 | 84.1398 | 93.8194 | 90.0694 | 85.0694 | 97.1774 | 93.0108 | 86.4919 | 92.1371 | 86.4919 | 80.3091 | 82.5 | 73.8889 | 61.7361 | 68.6156 | 56.5188 | 46.7742 | 63.6806 | 49.0278 | 33.75 | 58.1989 | 43.2796 | 25.9409
18 | 2.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2.25 | 4 | 3.293 | 0 | 0 | 4.6875 | 2.8274 | 0 | 6.4516 | 2.4194 | 0 | 10 | 5.3472 | 0 | 8.6022 | 4.7715 | 0 | 16.5972 | 7.5694 | 3.0556 | 11.4247 | 5.9812 | 2.0833 | 11.9624 | 6.3172 | 2.5538 | 6.1806 | 2.5 | 0 | 4.2339 | 1.4113 | 0 | 3.6111 | 0 | 0 | 6.1828 | 0 | 0
18 | 2.25 | 6 | 17.4059 | 6.3215 | 2.621 | 22.7679 | 13.0054 | 3.7946 | 21.1694 | 12.836 | 6.6532 | 31.5278 | 21.8056 | 15.9028 | 32.9301 | 27.0833 | 18.2124 | 43.8194 | 30.4167 | 20.9028 | 35.4167 | 27.0833 | 18.75 | 35.0806 | 25.0672 | 16.0618 | 29.0278 | 18.8194 | 11.8056 | 18.4812 | 10.4839 | 3.4274 | 14.5139 | 8.4028 | 3.6111 | 16.0618 | 9.4086 | 2.6882
18 | 2.25 | 8 | 32.3925 | 17.8763 | 8.5349 | 40.9226 | 30.1724 | 13.7649 | 41.7339 | 32.0565 | 20.2285 | 59.3056 | 48.9583 | 40.2083 | 61.828 | 54.4355 | 45.4301 | 67.2222 | 59.0278 | 46.3889 | 68.078 | 57.9301 | 47.1774 | 61.2231 | 53.4274 | 42.9435 | 51.3889 | 43.0556 | 26.4583 | 36.6935 | 28.0914 | 17.0699 | 32.1528 | 21.0417 | 12.5694 | 33.8038 | 21.3038 | 9.4086
18 | 2.25 | 9 | 38.7097 | 25.4704 | 14.5161 | 50 | 40.7738 | 19.7173 | 54.3683 | 44.1532 | 31.1156 | 69.6528 | 59.5833 | 52.2917 | 75 | 67.8091 | 58.7366 | 77.9861 | 71.0417 | 60.1389 | 83.8038 | 68.414 | 57.8629 | 76.2769 | 66.0618 | 55.6452 | 63.4028 | 51.1111 | 38.5417 | 46.1022 | 35.7527 | 24.2608 | 43.2639 | 30.2083 | 18.4722 | 41.2634 | 27.6882 | 14.9866
18 | 2.25 | 10 | 49.4624 | 33.3333 | 22.6478 | 59.5674 | 46.4209 | 26.9345 | 68.3468 | 51.1425 | 38.8441 | 79.4444 | 70.7639 | 63.5417 | 82.2581 | 76.0753 | 68.414 | 86.9444 | 82.3611 | 72.8472 | 91.7339 | 82.2581 | 74.7984 | 83.3333 | 75.336 | 67.6747 | 72.7778 | 61.9444 | 53.4028 | 54.9059 | 46.5054 | 31.3844 | 53.4028 | 38.4028 | 23.1944 | 48.9247 | 35.2151 | 21.7742
18 | 2.25 | 11 | 56.9892 | 40.7258 | 27.6882 | 68.6756 | 56.8452 | 33.5565 | 76.5457 | 61.5591 | 49.0591 | 86.0417 | 79.0972 | 70.1389 | 90.457 | 84.2742 | 79.4355 | 93.0556 | 89.3056 | 82.3611 | 95.9677 | 90.1882 | 82.5941 | 89.1129 | 84.8118 | 78.293 | 82.7778 | 70.625 | 60.2083 | 66.5323 | 53.8978 | 40.6586 | 58.8194 | 48.0556 | 31.8056 | 56.8548 | 42.5403 | 25.1344
18 | 2.25 | 12 | 61.828 | 44.2204 | 33.871 | 74.1533 | 63.1568 | 40.0785 | 81.1156 | 67.9435 | 55.7796 | 91.3194 | 83.8889 | 75.6944 | 94.2204 | 88.9785 | 84.4086 | 94.5833 | 91.0417 | 87.6389 | 97.5134 | 93.6828 | 86.6263 | 93.1452 | 88.5081 | 81.7876 | 85.4861 | 76.0417 | 66.875 | 71.5726 | 57.3253 | 48.9919 | 64.9306 | 52.5694 | 38.5417 | 60.6183 | 49.0591 | 31.3172
18 | 2.25 | 15 | 66.5995 | 48.2527 | 39.1129 | 77.0089 | 66.2946 | 44.7481 | 83.6694 | 70.7661 | 59.0726 | 94.0972 | 86.9444 | 79.7917 | 96.5054 | 92.6747 | 88.8441 | 95.6944 | 92.9861 | 89.0278 | 98.7231 | 96.0349 | 88.9785 | 95.6989 | 91.6667 | 84.8118 | 88.75 | 80.1389 | 71.1111 | 76.1425 | 62.9704 | 53.8978 | 70.6944 | 58.4722 | 43.2639 | 64.3817 | 52.2849 | 34.4086
18 | 2.25 | 20 | 66.5995 | 48.2527 | 39.1129 | 77.0833 | 66.2946 | 44.8225 | 83.6694 | 70.7661 | 59.0726 | 94.0972 | 86.9444 | 80 | 96.5054 | 92.6747 | 88.8441 | 95.7639 | 92.9861 | 89.2361 | 98.7231 | 96.0349 | 89.0457 | 95.6989 | 91.7339 | 84.879 | 88.8194 | 80.2083 | 71.1111 | 76.2769 | 63.2392 | 53.8978 | 70.6944 | 59.7222 | 43.4722 | 64.4489 | 52.2849 | 34.4758
18 | 2.25 | 25 | 66.5995 | 48.2527 | 39.1129 | 77.0833 | 66.2946 | 44.8225 | 83.6694 | 70.7661 | 59.0726 | 94.0972 | 86.9444 | 80 | 96.5054 | 92.6747 | 88.8441 | 95.7639 | 92.9861 | 89.2361 | 98.7231 | 96.0349 | 89.0457 | 95.6989 | 91.7339 | 84.879 | 88.8194 | 80.2083 | 71.1111 | 76.2769 | 63.2392 | 53.8978 | 70.6944 | 59.7222 | 43.4722 | 64.4489 | 52.2849 | 34.4758
18 | 2.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2.5 | 4 | 3.293 | 0 | 0 | 4.7619 | 2.8274 | 0 | 6.4516 | 2.4194 | 0 | 10 | 5.3472 | 0 | 8.6022 | 4.7715 | 0 | 16.5972 | 7.5694 | 3.0556 | 11.4247 | 5.9812 | 2.0833 | 11.9624 | 6.3172 | 2.5538 | 6.1806 | 2.5 | 0 | 4.2339 | 1.4113 | 0 | 3.6111 | 0 | 0 | 6.1828 | 0 | 0
18 | 2.5 | 6 | 17.4059 | 6.3215 | 2.621 | 22.7679 | 13.0054 | 3.7946 | 21.1694 | 12.836 | 6.6532 | 31.5278 | 21.8056 | 15.9028 | 32.9301 | 27.0833 | 18.2124 | 43.8194 | 30.4167 | 20.9028 | 35.4167 | 27.0833 | 18.75 | 35.0806 | 25.0672 | 16.0618 | 29.0278 | 18.8889 | 12.2222 | 18.4812 | 10.4839 | 3.4274 | 14.5139 | 8.4028 | 3.6111 | 16.0618 | 9.4086 | 2.6882
18 | 2.5 | 8 | 32.3925 | 18.2124 | 9.7446 | 40.9226 | 30.6753 | 14.0625 | 41.7339 | 32.0565 | 21.5726 | 59.3056 | 48.9583 | 40.5556 | 61.828 | 54.4355 | 45.4301 | 67.2917 | 59.0278 | 46.3889 | 68.078 | 57.9301 | 47.1774 | 61.3575 | 53.4274 | 42.9435 | 51.4583 | 43.0556 | 26.4583 | 37.2312 | 28.1586 | 17.5403 | 32.1528 | 21.8056 | 13.125 | 34.207 | 21.4382 | 9.4086
18 | 2.5 | 9 | 38.9785 | 26.4785 | 14.6505 | 51.2649 | 41.1458 | 19.7173 | 54.4355 | 44.6237 | 31.3172 | 70 | 60.4167 | 53.6806 | 75 | 67.9435 | 58.7366 | 78.1944 | 71.0417 | 60.1389 | 83.871 | 68.414 | 57.9973 | 76.4785 | 66.1962 | 55.6452 | 63.4028 | 51.3889 | 39.0278 | 46.1694 | 37.4328 | 24.7312 | 43.5417 | 30.2778 | 19.0278 | 42.6075 | 28.0914 | 15.121
18 | 2.5 | 10 | 52.2177 | 34.6774 | 25.6048 | 60.4167 | 46.934 | 27.3065 | 69.4892 | 52.6882 | 39.8522 | 79.4444 | 71.3889 | 65.1389 | 82.3925 | 76.9489 | 68.6156 | 86.9444 | 82.5694 | 72.9167 | 91.9355 | 82.3925 | 74.9328 | 83.7366 | 75.9409 | 67.7419 | 73.0556 | 62.9167 | 53.9583 | 55.3763 | 47.7151 | 33.6694 | 54.375 | 39.7917 | 24.4444 | 51.0081 | 36.2903 | 22.379
18 | 2.5 | 11 | 59.4086 | 41.8011 | 29.7715 | 69.1964 | 57.9613 | 35.1935 | 77.5538 | 62.9704 | 49.5296 | 87.4306 | 79.9306 | 72.5 | 91.8683 | 85.1478 | 80.2419 | 93.6111 | 89.8611 | 83.9583 | 96.7742 | 90.457 | 83.0645 | 89.8522 | 85.6183 | 78.8306 | 83.1944 | 70.9028 | 62.2222 | 69.0188 | 55.1075 | 42.6747 | 60.3472 | 50.3472 | 32.5694 | 59.207 | 43.5484 | 27.7554
18 | 2.5 | 12 | 63.9785 | 48.1183 | 37.836 | 77.7145 | 65.5506 | 43.6243 | 82.8629 | 71.1022 | 57.1237 | 92.8472 | 85.7639 | 79.5833 | 94.9597 | 90.2554 | 86.0215 | 95.4167 | 92.5 | 89.3056 | 98.9247 | 95.5645 | 87.9032 | 96.2366 | 89.6505 | 84.207 | 86.5278 | 79.0278 | 69.5139 | 73.3871 | 59.8118 | 51.8817 | 67.0833 | 56.1111 | 41.875 | 64.3145 | 51.2097 | 36.6263
18 | 2.5 | 15 | 73.4543 | 58.8038 | 44.7581 | 82.8972 | 72.7679 | 52.1577 | 89.9866 | 76.1425 | 66.5995 | 96.25 | 90.6944 | 87.6389 | 98.0511 | 96.0349 | 92.4059 | 97.0833 | 95.0694 | 92.2222 | 100 | 98.1183 | 91.7339 | 98.0511 | 93.414 | 87.7688 | 91.5278 | 84.9306 | 76.9444 | 82.3253 | 70.7661 | 61.2231 | 77.8472 | 65.4167 | 51.25 | 72.2446 | 59.2742 | 42.6747
18 | 2.5 | 20 | 74.1263 | 58.871 | 44.9597 | 82.8972 | 72.8423 | 52.381 | 89.9866 | 77.2177 | 66.7339 | 96.5278 | 90.6944 | 87.6389 | 98.3871 | 96.1022 | 92.4731 | 97.1528 | 95.0694 | 92.2917 | 100 | 98.1855 | 91.9355 | 98.0511 | 93.8844 | 87.836 | 92.2917 | 85.1389 | 77.0833 | 82.7285 | 71.1694 | 61.5591 | 78.2639 | 65.7639 | 52.4306 | 72.5134 | 59.3414 | 43.8172
18 | 2.5 | 25 | 74.1263 | 58.871 | 44.9597 | 82.8972 | 72.8423 | 52.381 | 89.9866 | 77.2177 | 66.7339 | 96.5278 | 90.6944 | 87.6389 | 98.3871 | 96.1022 | 92.4731 | 97.1528 | 95.0694 | 92.2917 | 100 | 98.1855 | 91.9355 | 98.0511 | 93.8844 | 87.836 | 92.2917 | 85.1389 | 77.0833 | 82.7285 | 71.1694 | 61.5591 | 78.2639 | 65.7639 | 52.4306 | 72.5134 | 59.3414 | 43.8172
18 | 2.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2.75 | 4 | 3.293 | 0 | 0 | 4.7619 | 2.8274 | 0 | 6.4516 | 2.4194 | 0 | 10 | 5.3472 | 0 | 8.6022 | 4.7715 | 0 | 16.5972 | 7.5694 | 3.0556 | 11.4247 | 5.9812 | 2.0833 | 11.9624 | 6.3172 | 2.5538 | 6.1806 | 2.5 | 0 | 4.2339 | 1.4113 | 0 | 3.6111 | 0 | 0 | 6.1828 | 0 | 0
18 | 2.75 | 6 | 17.4059 | 6.3215 | 2.621 | 22.7679 | 13.0054 | 3.7946 | 21.1694 | 12.836 | 6.6532 | 31.5278 | 21.8056 | 15.9028 | 32.9301 | 27.0833 | 18.2124 | 43.8194 | 30.4167 | 20.9028 | 35.4167 | 27.0833 | 18.75 | 35.0806 | 25.0672 | 16.0618 | 29.0278 | 18.8889 | 12.2222 | 18.4812 | 10.4839 | 3.4274 | 14.5139 | 8.4028 | 3.6111 | 16.0618 | 9.4086 | 2.6882
18 | 2.75 | 8 | 32.3925 | 18.2124 | 9.7446 | 40.9226 | 31.3167 | 14.0625 | 41.7339 | 32.0565 | 21.5726 | 59.3056 | 48.9583 | 41.4583 | 61.828 | 54.4355 | 45.4301 | 67.2917 | 59.0278 | 46.3889 | 68.078 | 57.9301 | 47.1774 | 61.3575 | 53.4274 | 42.9435 | 51.4583 | 43.0556 | 26.4583 | 37.2312 | 28.2258 | 17.6747 | 32.1528 | 21.8056 | 13.1944 | 34.879 | 21.5054 | 10.6183
18 | 2.75 | 9 | 38.9785 | 26.5457 | 14.6505 | 51.7113 | 41.2202 | 20.7589 | 54.5027 | 44.6237 | 31.6532 | 70 | 60.4861 | 53.8889 | 75 | 68.0108 | 58.7366 | 78.1944 | 71.0417 | 60.1389 | 83.871 | 68.414 | 57.9973 | 76.4785 | 66.1962 | 55.6452 | 63.4028 | 51.9444 | 39.7222 | 46.1694 | 37.4328 | 25 | 43.6806 | 30.3472 | 19.0972 | 42.8763 | 29.3683 | 16.3306
18 | 2.75 | 10 | 52.6882 | 35.1478 | 25.8065 | 60.8631 | 47.1521 | 27.9018 | 70.7661 | 52.7554 | 40.3226 | 79.4444 | 71.6667 | 65.5556 | 82.3925 | 77.4866 | 69.086 | 87.0139 | 82.7083 | 72.9167 | 91.9355 | 82.3925 | 75 | 83.8038 | 75.9409 | 67.7419 | 73.0556 | 62.9167 | 54.5833 | 55.4435 | 48.7231 | 34.207 | 55.8333 | 40.3472 | 26.3889 | 51.3441 | 37.2984 | 24.9328
18 | 2.75 | 11 | 59.9462 | 42.2715 | 30.2419 | 69.5685 | 59.5649 | 38.8393 | 78.9651 | 63.5081 | 51.4785 | 88.0556 | 80.2778 | 73.6806 | 92.1371 | 85.8199 | 80.3091 | 93.75 | 90.0694 | 84.7917 | 96.8414 | 90.457 | 83.4005 | 90.121 | 86.3575 | 79.2339 | 83.2639 | 71.8056 | 65.6944 | 69.5565 | 55.578 | 43.3468 | 62.6389 | 51.3194 | 34.6528 | 60.6855 | 44.4892 | 31.7876
18 | 2.75 | 12 | 66.5323 | 51.6801 | 39.9194 | 79.4643 | 68.7038 | 45.7589 | 84.9462 | 73.2527 | 59.879 | 93.0556 | 86.6667 | 82.0833 | 95.1613 | 90.8602 | 87.836 | 96.3889 | 93.3333 | 90.1389 | 99.1263 | 95.6317 | 88.8441 | 97.2446 | 91.3306 | 85.1478 | 89.5833 | 80.1389 | 72.8472 | 74.5296 | 60.9543 | 53.4274 | 69.8611 | 60.5556 | 44.5139 | 65.8602 | 52.2177 | 37.9704
18 | 2.75 | 15 | 78.4946 | 64.6505 | 49.1935 | 85.2319 | 77.5298 | 60.0831 | 92.3387 | 79.3683 | 71.9086 | 97.6389 | 94.0972 | 89.8611 | 99.2608 | 97.7151 | 94.6237 | 98.6111 | 96.7361 | 94.4444 | 100 | 98.9919 | 94.4892 | 99.328 | 95.7661 | 90.9946 | 93.6111 | 89.1667 | 81.7361 | 88.3065 | 77.0161 | 68.8172 | 80.6944 | 72.7778 | 56.4583 | 76.6129 | 67.4059 | 49.5968
18 | 2.75 | 20 | 80.578 | 66.3306 | 49.664 | 85.3756 | 77.6786 | 60.3756 | 92.5403 | 81.3844 | 72.6478 | 98.3333 | 94.1667 | 90.625 | 99.3952 | 97.9167 | 94.9597 | 98.6111 | 96.875 | 94.5139 | 100 | 98.9919 | 94.5565 | 99.328 | 95.7661 | 91.0618 | 94.9306 | 89.375 | 82.3611 | 90.121 | 77.8226 | 70.0941 | 81.5278 | 74.3056 | 59.0972 | 77.957 | 69.2204 | 51.6129
18 | 2.75 | 25 | 80.578 | 66.3306 | 49.664 | 85.3756 | 77.6786 | 60.3756 | 92.5403 | 81.3844 | 72.6478 | 98.3333 | 94.1667 | 90.625 | 99.3952 | 97.9167 | 94.9597 | 98.6111 | 96.875 | 94.5139 | 100 | 98.9919 | 94.5565 | 99.328 | 95.7661 | 91.0618 | 94.9306 | 89.375 | 82.3611 | 90.121 | 77.8226 | 70.0941 | 81.5278 | 74.3056 | 59.0972 | 77.957 | 69.2204 | 51.6129
18 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 3 | 4 | 3.293 | 0 | 0 | 4.7619 | 2.8274 | 0 | 6.4516 | 2.4194 | 0 | 10 | 5.3472 | 0 | 8.6022 | 4.7715 | 0 | 16.5972 | 7.5694 | 3.0556 | 11.4247 | 5.9812 | 2.0833 | 11.9624 | 6.3172 | 2.5538 | 6.1806 | 2.5 | 0 | 4.2339 | 1.4113 | 0 | 3.6111 | 0 | 0 | 6.1828 | 0 | 0
18 | 3 | 6 | 17.4059 | 6.3215 | 2.621 | 22.7679 | 13.0054 | 3.7946 | 21.1694 | 12.836 | 6.6532 | 31.5278 | 21.8056 | 15.9028 | 32.9301 | 27.0833 | 18.2124 | 43.8194 | 30.4167 | 20.9028 | 35.4167 | 27.0833 | 18.75 | 35.0806 | 25.0672 | 16.0618 | 29.0278 | 18.8889 | 12.2222 | 18.4812 | 10.4839 | 3.4274 | 14.5139 | 8.4028 | 3.6111 | 16.0618 | 9.4086 | 2.6882
18 | 3 | 8 | 32.3925 | 18.4812 | 9.7446 | 40.9226 | 31.3167 | 14.0625 | 41.7339 | 32.0565 | 21.5726 | 59.3056 | 48.9583 | 41.4583 | 61.828 | 54.4355 | 45.4301 | 67.2917 | 59.0278 | 46.3889 | 68.078 | 57.9301 | 47.1774 | 61.3575 | 53.4274 | 42.9435 | 51.4583 | 43.0556 | 26.4583 | 37.2312 | 28.2258 | 17.6747 | 32.1528 | 21.8056 | 13.1944 | 34.9462 | 21.5726 | 10.7527
18 | 3 | 9 | 38.9785 | 26.5457 | 14.6505 | 51.8601 | 41.2202 | 20.7589 | 54.5027 | 44.6237 | 31.6532 | 70 | 60.4861 | 53.9583 | 75 | 68.0108 | 58.7366 | 78.1944 | 71.0417 | 60.1389 | 83.871 | 68.414 | 57.9973 | 76.4785 | 66.1962 | 55.6452 | 63.4028 | 51.9444 | 39.7917 | 46.1694 | 38.172 | 25.1344 | 43.8194 | 30.3472 | 19.1667 | 42.8763 | 29.3683 | 16.3306
18 | 3 | 10 | 52.8898 | 35.1478 | 26.7473 | 61.1607 | 47.9911 | 27.9762 | 70.9005 | 52.8898 | 41.2634 | 79.4444 | 71.8056 | 65.9028 | 82.3925 | 77.4866 | 70.0941 | 87.1528 | 82.7083 | 72.9167 | 91.9355 | 82.3925 | 75 | 83.8038 | 75.9409 | 67.7419 | 73.0556 | 62.9167 | 54.7917 | 55.578 | 48.7231 | 35.4167 | 55.9722 | 40.9028 | 26.5278 | 52.2849 | 37.2984 | 25.2016
18 | 3 | 11 | 60.0134 | 42.5403 | 31.4516 | 70.6101 | 60.9375 | 39.3601 | 79.5027 | 63.7097 | 51.4785 | 88.0556 | 80.6944 | 74.0278 | 92.2715 | 85.8871 | 80.3763 | 93.8194 | 90.1389 | 84.8611 | 96.8414 | 90.457 | 83.4005 | 90.1882 | 86.5591 | 79.3011 | 83.2639 | 72.0139 | 65.7639 | 69.8925 | 55.7124 | 44.5565 | 63.2639 | 52.5 | 35.9028 | 62.0296 | 45.2285 | 33.1317
18 | 3 | 12 | 67.2043 | 53.1936 | 40.9274 | 79.8363 | 69.2708 | 50.9493 | 86.0215 | 73.5887 | 61.4247 | 93.125 | 88.4028 | 82.4306 | 95.4973 | 91.4651 | 88.9785 | 96.875 | 93.8194 | 90.4861 | 99.1263 | 95.6317 | 89.0457 | 97.2446 | 91.4651 | 85.2823 | 89.7222 | 80.5556 | 73.6806 | 75.7392 | 62.2312 | 55.3091 | 70.8333 | 62.1528 | 45.1389 | 67.1371 | 52.8898 | 41.5995
18 | 3 | 15 | 85.0806 | 69.422 | 53.3602 | 88.1696 | 81.0268 | 64.2857 | 94.422 | 85.4167 | 76.0753 | 98.4028 | 95.7639 | 90.9028 | 100 | 98.3871 | 96.0349 | 99.7917 | 97.7778 | 95.6944 | 100 | 99.9328 | 95.8333 | 99.664 | 97.9167 | 92.7419 | 96.1806 | 91.1111 | 85.0694 | 91.1962 | 80.2419 | 72.9839 | 85.8333 | 76.5972 | 63.4028 | 79.9731 | 71.8414 | 54.6371
18 | 3 | 20 | 86.6263 | 71.1694 | 54.3683 | 88.4673 | 82.4405 | 65.7174 | 96.1022 | 86.2231 | 77.1505 | 99.0278 | 95.9028 | 91.875 | 100 | 99.1935 | 96.4382 | 99.8611 | 97.9861 | 95.7639 | 100 | 100 | 95.9005 | 99.7984 | 97.9167 | 93.8844 | 96.9444 | 91.9444 | 86.3889 | 92.8763 | 81.7204 | 76.5457 | 87.2917 | 78.8889 | 65.8333 | 83.0645 | 73.7231 | 58.0645
18 | 3 | 25 | 86.6263 | 71.1694 | 54.3683 | 88.4673 | 82.4405 | 65.7174 | 96.1022 | 86.2231 | 77.1505 | 99.0278 | 95.9028 | 91.875 | 100 | 99.1935 | 96.4382 | 99.8611 | 97.9861 | 95.7639 | 100 | 100 | 95.9005 | 99.7984 | 97.9167 | 93.8844 | 96.9444 | 91.9444 | 86.3889 | 92.8763 | 81.7204 | 76.5457 | 87.2917 | 78.8889 | 65.8333 | 83.0645 | 73.7231 | 58.0645
18 | 3.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 3.25 | 4 | 3.293 | 0 | 0 | 4.7619 | 2.8274 | 0 | 6.4516 | 2.4194 | 0 | 10 | 5.3472 | 0 | 8.6022 | 4.7715 | 0 | 16.5972 | 7.5694 | 3.0556 | 11.4247 | 5.9812 | 2.0833 | 11.9624 | 6.3172 | 2.5538 | 6.1806 | 2.5 | 0 | 4.2339 | 1.4113 | 0 | 3.6111 | 0 | 0 | 6.1828 | 0 | 0
18 | 3.25 | 6 | 17.4059 | 6.8548 | 2.621 | 22.7679 | 13.0054 | 3.7946 | 21.1694 | 12.836 | 6.6532 | 31.5278 | 21.8056 | 15.9028 | 32.9301 | 27.0833 | 18.2124 | 43.8194 | 30.4167 | 20.9028 | 35.4167 | 27.0833 | 18.75 | 35.0806 | 25.0672 | 16.0618 | 29.0278 | 18.8889 | 12.2222 | 18.4812 | 10.4839 | 3.4274 | 14.5139 | 8.4028 | 3.6111 | 16.0618 | 9.4086 | 2.6882
18 | 3.25 | 8 | 32.8629 | 18.4812 | 9.7446 | 40.9226 | 31.3167 | 14.0625 | 41.7339 | 32.0565 | 21.5726 | 59.3056 | 48.9583 | 41.4583 | 61.828 | 54.4355 | 45.4301 | 67.2917 | 59.0278 | 46.3889 | 68.078 | 57.9301 | 47.1774 | 61.3575 | 53.4274 | 42.9435 | 51.4583 | 43.0556 | 26.4583 | 37.2312 | 28.2258 | 17.6747 | 32.1528 | 21.8056 | 13.1944 | 34.9462 | 21.5726 | 10.7527
18 | 3.25 | 9 | 39.5833 | 26.7649 | 14.6505 | 51.8601 | 41.2202 | 20.7589 | 54.5027 | 44.6237 | 31.6532 | 70 | 60.4861 | 53.9583 | 75 | 68.0108 | 58.7366 | 78.1944 | 71.5278 | 60.1389 | 83.871 | 68.414 | 57.9973 | 76.4785 | 66.1962 | 55.6452 | 63.4028 | 51.9444 | 39.7917 | 46.1694 | 38.3065 | 25.1344 | 43.8194 | 30.3472 | 19.1667 | 42.8763 | 29.3683 | 16.3306
18 | 3.25 | 10 | 52.957 | 35.7527 | 26.8817 | 61.6071 | 48.6607 | 27.9762 | 70.9005 | 53.0242 | 41.2634 | 79.4444 | 71.9444 | 65.9722 | 82.3925 | 77.4866 | 70.0941 | 87.1528 | 82.7083 | 72.9167 | 91.9355 | 82.3925 | 75 | 83.8038 | 75.9409 | 67.7419 | 73.0556 | 62.9167 | 55.0694 | 55.6452 | 49.1263 | 35.5511 | 55.9722 | 41.4583 | 26.5972 | 52.4194 | 37.2984 | 25.336
18 | 3.25 | 11 | 60.6183 | 42.8763 | 31.7204 | 72.3214 | 61.3018 | 39.4345 | 79.7043 | 63.7769 | 51.7473 | 88.0556 | 81.3889 | 74.375 | 92.3387 | 85.8871 | 80.3763 | 93.8889 | 90.2083 | 84.8611 | 96.8414 | 90.457 | 83.4005 | 90.1882 | 86.6263 | 79.4355 | 83.2639 | 72.1528 | 65.7639 | 69.8925 | 56.6532 | 45.0269 | 63.4722 | 52.9861 | 36.1806 | 62.5 | 45.3629 | 33.6694
18 | 3.25 | 12 | 67.4059 | 54.0008 | 41.3306 | 80.506 | 70.0893 | 51.3213 | 86.1559 | 73.5887 | 61.828 | 93.125 | 88.6806 | 82.5694 | 95.6989 | 91.5995 | 88.9785 | 97.0139 | 93.9583 | 90.625 | 99.1263 | 95.6317 | 89.1129 | 97.2446 | 91.9355 | 85.2823 | 89.7917 | 80.7639 | 73.8194 | 76.0081 | 62.4328 | 56.25 | 71.4583 | 62.6389 | 45.625 | 67.6747 | 54.4355 | 43.078
18 | 3.25 | 15 | 85.8199 | 72.1102 | 59.6774 | 90.253 | 83.4821 | 68.6474 | 95.4973 | 87.3656 | 78.9651 | 98.9583 | 96.8056 | 94.0278 | 100 | 98.9919 | 97.4462 | 100 | 98.8889 | 96.25 | 100 | 100 | 96.4382 | 100 | 98.9919 | 94.8253 | 96.875 | 92.9167 | 88.8194 | 93.3468 | 82.7285 | 75.1344 | 88.4028 | 81.1111 | 66.5278 | 82.9973 | 75.8065 | 59.543
18 | 3.25 | 20 | 89.1801 | 76.4785 | 63.9785 | 91.5923 | 86.1735 | 74.4253 | 97.5806 | 88.8441 | 80.9812 | 99.7917 | 97.4306 | 94.7222 | 100 | 99.9328 | 97.9167 | 100 | 99.1667 | 96.3889 | 100 | 100 | 96.7742 | 100 | 99.328 | 95.5645 | 97.8472 | 94.5139 | 89.8611 | 96.1694 | 86.828 | 80.3763 | 92.3611 | 84.7917 | 71.8056 | 87.0296 | 80.1747 | 65.1882
18 | 3.25 | 25 | 89.1801 | 76.4785 | 63.9785 | 91.5923 | 86.1735 | 74.4253 | 97.5806 | 88.8441 | 80.9812 | 99.7917 | 97.4306 | 94.7222 | 100 | 99.9328 | 97.9167 | 100 | 99.1667 | 96.3889 | 100 | 100 | 96.7742 | 100 | 99.328 | 95.5645 | 97.9167 | 94.5139 | 89.9306 | 96.1694 | 86.828 | 80.3763 | 92.3611 | 84.7917 | 71.8056 | 87.0296 | 80.1747 | 65.1882
18 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 3.5 | 4 | 3.293 | 0 | 0 | 4.7619 | 2.8274 | 0 | 6.4516 | 2.4194 | 0 | 10 | 5.3472 | 0 | 8.6022 | 4.7715 | 0 | 16.5972 | 7.5694 | 3.0556 | 11.4247 | 5.9812 | 2.0833 | 11.9624 | 6.3172 | 2.5538 | 6.1806 | 2.5 | 0 | 4.2339 | 1.4113 | 0 | 3.6111 | 0 | 0 | 6.1828 | 0 | 0
18 | 3.5 | 6 | 17.4059 | 6.8548 | 2.621 | 22.7679 | 13.0054 | 3.7946 | 21.1694 | 12.836 | 6.6532 | 31.5278 | 21.8056 | 15.9028 | 32.9301 | 27.0833 | 18.2124 | 43.8194 | 30.4167 | 20.9028 | 35.4167 | 27.0833 | 18.75 | 35.0806 | 25.0672 | 16.0618 | 29.0278 | 18.8889 | 12.2222 | 18.4812 | 10.4839 | 3.4274 | 14.5139 | 8.4028 | 3.6111 | 16.0618 | 9.4086 | 2.6882
18 | 3.5 | 8 | 32.8629 | 18.4812 | 9.7446 | 40.9226 | 31.3167 | 14.0625 | 41.7339 | 32.0565 | 21.5726 | 59.3056 | 48.9583 | 41.4583 | 61.828 | 54.4355 | 45.4301 | 67.2917 | 59.0278 | 46.3889 | 68.078 | 57.9301 | 47.1774 | 61.3575 | 53.4274 | 42.9435 | 51.4583 | 43.0556 | 26.4583 | 37.2312 | 28.2258 | 17.6747 | 32.1528 | 21.8056 | 13.1944 | 34.9462 | 21.5726 | 10.7527
18 | 3.5 | 9 | 39.5833 | 26.7649 | 14.6505 | 51.8601 | 41.2202 | 20.7589 | 54.5027 | 44.6237 | 31.6532 | 70 | 60.4861 | 53.9583 | 75 | 68.0108 | 58.7366 | 78.1944 | 71.5278 | 60.1389 | 83.871 | 68.414 | 57.9973 | 76.4785 | 66.1962 | 55.6452 | 63.4028 | 51.9444 | 39.7917 | 46.1694 | 38.3065 | 25.1344 | 43.8194 | 30.3472 | 19.1667 | 42.8763 | 29.3683 | 16.3306
18 | 3.5 | 10 | 52.957 | 35.8199 | 26.9489 | 61.6815 | 48.6607 | 28.0506 | 70.9005 | 53.0914 | 41.2634 | 79.7222 | 72.0139 | 65.9722 | 82.3925 | 77.4866 | 70.0941 | 87.1528 | 82.7083 | 72.9167 | 91.9355 | 82.3925 | 75 | 83.8038 | 75.9409 | 67.7419 | 73.0556 | 62.9167 | 55.1389 | 55.6452 | 49.1263 | 35.5511 | 55.9722 | 41.4583 | 26.5972 | 52.5538 | 37.2984 | 25.336
18 | 3.5 | 11 | 60.6855 | 43.078 | 31.922 | 72.3214 | 62.0407 | 39.4345 | 79.7043 | 63.7769 | 51.7473 | 88.0556 | 81.3889 | 74.375 | 92.3387 | 85.8871 | 80.3763 | 93.9583 | 90.2778 | 84.8611 | 96.8414 | 90.457 | 83.4005 | 90.1882 | 86.6263 | 79.4355 | 83.2639 | 72.1528 | 65.7639 | 69.8925 | 56.7204 | 45.2957 | 64.375 | 53.9583 | 37.5 | 62.6344 | 45.4973 | 33.8038
18 | 3.5 | 12 | 67.4731 | 54.3372 | 42.2715 | 80.5804 | 70.3869 | 51.4701 | 86.3575 | 73.9919 | 63.2392 | 93.4722 | 88.9583 | 82.6389 | 95.8333 | 91.8011 | 89.0457 | 97.0139 | 94.2361 | 90.625 | 99.1263 | 95.6317 | 89.1801 | 97.2446 | 92.0027 | 85.2823 | 89.8611 | 80.9722 | 74.2361 | 76.2097 | 62.4328 | 56.7876 | 71.6667 | 63.4722 | 46.4583 | 68.0108 | 54.8387 | 43.2124
18 | 3.5 | 15 | 88.6425 | 73.5215 | 63.82 | 91.8155 | 85.604 | 70.8898 | 97.1102 | 89.3145 | 81.1828 | 99.5833 | 97.3611 | 94.5139 | 100 | 99.4624 | 97.9167 | 100 | 99.1667 | 97.0139 | 100 | 100 | 97.5806 | 100 | 99.2608 | 95.6317 | 97.4306 | 94.3056 | 89.3056 | 94.2204 | 83.7366 | 77.0833 | 89.2361 | 83.4028 | 70.1389 | 85.0134 | 78.5618 | 62.5
18 | 3.5 | 20 | 92.0027 | 82.4597 | 67.5403 | 94.3452 | 89.1369 | 78.7485 | 98.9247 | 93.2796 | 84.3414 | 100 | 99.0972 | 95.4167 | 100 | 100 | 98.8575 | 100 | 99.5139 | 97.2917 | 100 | 100 | 98.0511 | 100 | 100 | 97.1102 | 98.8889 | 96.1806 | 92.0139 | 98.3871 | 89.3145 | 84.8118 | 94.375 | 87.9167 | 77.2917 | 88.8441 | 82.5269 | 69.6237
18 | 3.5 | 25 | 92.0027 | 82.4597 | 67.5403 | 94.3452 | 89.1369 | 78.8229 | 98.9247 | 93.2796 | 84.3414 | 100 | 99.0972 | 95.4167 | 100 | 100 | 98.8575 | 100 | 99.5139 | 97.2917 | 100 | 100 | 98.0511 | 100 | 100 | 97.1102 | 98.8889 | 96.1806 | 92.0833 | 98.3871 | 89.3145 | 84.8118 | 94.375 | 87.9861 | 77.2917 | 88.8441 | 82.5269 | 69.6909
18 | 3.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 3.75 | 4 | 3.293 | 0 | 0 | 4.7619 | 2.8274 | 0 | 6.4516 | 2.4194 | 0 | 10 | 5.3472 | 0 | 8.6022 | 4.7715 | 0 | 16.5972 | 7.5694 | 3.0556 | 11.4247 | 5.9812 | 2.0833 | 11.9624 | 6.3172 | 2.5538 | 6.1806 | 2.5 | 0 | 4.2339 | 1.4113 | 0 | 3.6111 | 0 | 0 | 6.1828 | 0 | 0
18 | 3.75 | 6 | 17.4059 | 6.8548 | 2.621 | 22.7679 | 13.0054 | 3.7946 | 21.1694 | 12.836 | 6.6532 | 31.5278 | 21.8056 | 15.9028 | 32.9301 | 27.0833 | 18.2124 | 43.8194 | 30.4167 | 20.9028 | 35.4167 | 27.0833 | 18.75 | 35.0806 | 25.0672 | 16.0618 | 29.0278 | 18.8889 | 12.2222 | 18.4812 | 10.4839 | 3.4274 | 14.5139 | 8.4028 | 3.6111 | 16.0618 | 9.4086 | 2.6882
18 | 3.75 | 8 | 32.8629 | 18.4812 | 9.7446 | 40.9226 | 31.3167 | 14.0625 | 41.7339 | 32.0565 | 21.5726 | 59.3056 | 48.9583 | 41.4583 | 61.828 | 54.4355 | 45.4301 | 67.2917 | 59.0278 | 46.3889 | 68.078 | 57.9301 | 47.1774 | 61.3575 | 53.4274 | 42.9435 | 51.4583 | 43.0556 | 26.4583 | 37.2312 | 28.2258 | 17.6747 | 32.1528 | 21.8056 | 13.1944 | 34.9462 | 21.5726 | 10.7527
18 | 3.75 | 9 | 39.5833 | 26.7649 | 14.6505 | 51.8601 | 41.2202 | 20.7589 | 54.5027 | 44.6237 | 31.6532 | 70 | 60.4861 | 53.9583 | 75 | 68.0108 | 58.7366 | 78.1944 | 71.5278 | 60.1389 | 83.871 | 68.414 | 57.9973 | 76.4785 | 66.1962 | 55.6452 | 63.4028 | 51.9444 | 39.7917 | 46.1694 | 38.3065 | 25.1344 | 43.8194 | 30.3472 | 19.1667 | 42.8763 | 29.3683 | 16.3306
18 | 3.75 | 10 | 52.957 | 35.8199 | 26.9489 | 61.6815 | 48.6607 | 28.0506 | 70.9005 | 53.0914 | 41.2634 | 79.7222 | 72.0139 | 65.9722 | 82.3925 | 77.4866 | 70.0941 | 87.1528 | 82.7083 | 72.9167 | 91.9355 | 82.3925 | 75 | 83.8038 | 75.9409 | 67.7419 | 73.0556 | 62.9167 | 55.2083 | 55.6452 | 49.1263 | 35.5511 | 55.9722 | 41.4583 | 26.5972 | 52.621 | 37.2984 | 25.336
18 | 3.75 | 11 | 60.6855 | 43.1739 | 33.5349 | 72.3214 | 62.0407 | 39.4345 | 79.7043 | 63.8441 | 51.7473 | 88.0556 | 81.3889 | 74.375 | 92.3387 | 85.8871 | 80.3763 | 93.9583 | 90.2778 | 84.8611 | 96.8414 | 90.457 | 83.4005 | 90.1882 | 86.6263 | 79.4355 | 83.2639 | 72.1528 | 65.7639 | 69.8925 | 56.7204 | 45.2957 | 64.375 | 54.0972 | 37.5694 | 62.7016 | 45.4973 | 33.871
18 | 3.75 | 12 | 67.5403 | 54.6063 | 44.0188 | 80.5804 | 70.4613 | 51.6189 | 86.4247 | 73.9919 | 63.2392 | 93.5417 | 88.9583 | 82.7083 | 95.9005 | 91.8011 | 89.0457 | 97.0139 | 94.4444 | 90.625 | 99.1263 | 95.6317 | 89.1801 | 97.2446 | 92.0027 | 85.2823 | 89.9306 | 80.9722 | 74.2361 | 76.3441 | 62.5 | 56.922 | 72.1528 | 63.5417 | 46.5972 | 68.2124 | 54.8387 | 43.2124
18 | 3.75 | 15 | 89.1801 | 76.0081 | 65.3664 | 92.1131 | 86.5327 | 73.5914 | 97.2446 | 90.9274 | 82.3925 | 99.7917 | 97.7778 | 94.7222 | 100 | 99.7312 | 98.3871 | 100 | 99.3056 | 97.4306 | 100 | 100 | 97.8495 | 100 | 99.4624 | 96.1022 | 98.125 | 94.7222 | 90.0694 | 94.3548 | 85.2823 | 79.0995 | 90.0694 | 83.8889 | 72.2917 | 86.2903 | 78.9651 | 64.9866
18 | 3.75 | 20 | 93.2796 | 86.2231 | 74.8484 | 96.5774 | 91.6667 | 83.2589 | 99.5296 | 95.6317 | 87.2984 | 100 | 99.4444 | 96.3889 | 100 | 100 | 99.5968 | 100 | 100 | 97.8472 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.2222 | 93.8889 | 99.1263 | 91.9355 | 88.9113 | 96.0417 | 91.1806 | 80.625 | 92.4731 | 85.5511 | 75
18 | 3.75 | 25 | 93.2796 | 86.2231 | 74.9156 | 96.5774 | 91.6667 | 83.2589 | 99.5296 | 95.6317 | 87.2984 | 100 | 99.5139 | 96.3889 | 100 | 100 | 99.5968 | 100 | 100 | 97.8472 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.2222 | 93.8889 | 99.1935 | 91.9355 | 89.1129 | 96.0417 | 91.25 | 80.625 | 92.4731 | 85.5511 | 75
18 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 4 | 4 | 3.293 | 0 | 0 | 4.7619 | 2.8274 | 0 | 6.4516 | 2.4194 | 0 | 10 | 5.3472 | 0 | 8.6022 | 4.7715 | 0 | 16.5972 | 7.5694 | 3.0556 | 11.4247 | 5.9812 | 2.0833 | 11.9624 | 6.3172 | 2.5538 | 6.1806 | 2.5 | 0 | 4.2339 | 1.4113 | 0 | 3.6111 | 0 | 0 | 6.1828 | 0 | 0
18 | 4 | 6 | 17.4059 | 6.8548 | 2.621 | 22.7679 | 13.0054 | 3.7946 | 21.1694 | 12.836 | 6.6532 | 31.5278 | 21.8056 | 15.9028 | 32.9301 | 27.0833 | 18.2124 | 43.8194 | 30.4167 | 20.9028 | 35.4167 | 27.0833 | 18.75 | 35.0806 | 25.0672 | 16.0618 | 29.0278 | 18.8889 | 12.2222 | 18.4812 | 10.4839 | 3.4274 | 14.5139 | 8.4028 | 3.6111 | 16.0618 | 9.4086 | 2.6882
18 | 4 | 8 | 32.8629 | 18.4812 | 9.7446 | 40.9226 | 31.3167 | 14.0625 | 41.7339 | 32.0565 | 21.5726 | 59.3056 | 48.9583 | 41.4583 | 61.828 | 54.4355 | 45.4301 | 67.2917 | 59.0278 | 46.3889 | 68.078 | 57.9301 | 47.1774 | 61.3575 | 53.4274 | 42.9435 | 51.4583 | 43.0556 | 26.4583 | 37.2312 | 28.2258 | 17.6747 | 32.1528 | 21.8056 | 13.1944 | 34.9462 | 21.5726 | 10.7527
18 | 4 | 9 | 39.5833 | 26.7649 | 14.6505 | 51.8601 | 41.2202 | 20.7589 | 54.5027 | 44.6237 | 31.6532 | 70 | 60.4861 | 53.9583 | 75 | 68.0108 | 58.7366 | 78.1944 | 71.5278 | 60.1389 | 83.871 | 68.414 | 57.9973 | 76.4785 | 66.1962 | 55.6452 | 63.4028 | 51.9444 | 39.7917 | 46.1694 | 38.3065 | 25.1344 | 43.8194 | 30.3472 | 19.1667 | 42.8763 | 29.3683 | 16.3306
18 | 4 | 10 | 52.957 | 35.8199 | 26.9489 | 61.6815 | 48.6607 | 28.0506 | 70.9005 | 53.0914 | 41.2634 | 79.7222 | 72.0139 | 65.9722 | 82.3925 | 77.4866 | 70.0941 | 87.1528 | 82.7083 | 72.9167 | 91.9355 | 82.3925 | 75 | 83.8038 | 75.9409 | 67.7419 | 73.0556 | 62.9167 | 55.2083 | 55.6452 | 49.1263 | 35.5511 | 55.9722 | 41.4583 | 26.5972 | 52.621 | 37.2984 | 25.336
18 | 4 | 11 | 60.6855 | 43.1739 | 33.5349 | 72.3214 | 62.0407 | 39.4345 | 79.7043 | 63.8441 | 51.7473 | 88.0556 | 81.3889 | 74.375 | 92.3387 | 85.8871 | 80.3763 | 93.9583 | 90.2778 | 84.8611 | 96.8414 | 90.457 | 83.4005 | 90.1882 | 86.6263 | 79.4355 | 83.2639 | 72.1528 | 65.7639 | 69.8925 | 56.7204 | 45.2957 | 64.375 | 54.0972 | 37.5694 | 62.836 | 45.4973 | 33.871
18 | 4 | 12 | 67.5403 | 54.8754 | 44.0188 | 80.5804 | 70.5357 | 51.6189 | 86.4247 | 73.9919 | 63.2392 | 93.5417 | 89.0972 | 82.7083 | 95.9005 | 91.8011 | 89.0457 | 97.0139 | 94.4444 | 90.625 | 99.1263 | 95.6317 | 89.1801 | 97.2446 | 92.0027 | 85.2823 | 89.9306 | 80.9722 | 74.2361 | 76.3441 | 62.5672 | 56.922 | 72.2917 | 63.5417 | 46.5972 | 68.2124 | 54.8387 | 43.2124
18 | 4 | 15 | 89.3145 | 76.3441 | 66.1733 | 92.3363 | 86.9792 | 75.2078 | 97.9839 | 91.3978 | 83.0645 | 99.7917 | 98.0556 | 95.1389 | 100 | 99.7984 | 98.3871 | 100 | 99.3056 | 97.5694 | 100 | 100 | 98.0511 | 100 | 99.5296 | 96.5054 | 98.6111 | 95.4167 | 90.6944 | 94.422 | 85.4839 | 79.5699 | 91.8056 | 85.9028 | 73.4028 | 86.4247 | 80.1747 | 67.2043
18 | 4 | 20 | 95.2285 | 89.9866 | 78.4805 | 97.9911 | 92.7083 | 87.2024 | 99.9328 | 97.4462 | 89.1129 | 100 | 99.7917 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.4722 | 95.4861 | 99.7984 | 94.5565 | 90.9946 | 97.8472 | 93.125 | 85.4861 | 94.6909 | 88.5081 | 81.7876
18 | 4 | 25 | 95.2285 | 90.0538 | 78.4805 | 97.9911 | 92.7083 | 87.2742 | 99.9328 | 97.5134 | 89.1129 | 100 | 99.8611 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.6806 | 95.8333 | 99.9328 | 94.8253 | 90.9946 | 97.8472 | 93.2639 | 85.4861 | 94.6909 | 88.9113 | 81.9892
24 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8194 | 0 | 0 | 3.7634 | 0 | 0 | 6.25 | 0 | 0 | 4.7043 | 0 | 0 | 5.0403 | 0 | 0 | 0.069444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6801 | 0 | 0 | 7.2222 | 1.4583 | 0 | 10.4839 | 5.578 | 0 | 13.3333 | 5.7639 | 0 | 15.793 | 7.7957 | 3.3602 | 15.1882 | 5.8468 | 0 | 4.8611 | 1.4583 | 0 | 1.8145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4274 | 0 | 0 | 8.3333 | 3.6806 | 0 | 12.164 | 6.3172 | 0 | 18.9583 | 8.6806 | 3.5417 | 17.8763 | 10.1478 | 3.3602 | 16.129 | 7.4597 | 1.8145 | 6.5972 | 2.8472 | 0 | 1.8145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4274 | 0 | 0 | 8.3333 | 3.6806 | 0 | 12.2312 | 6.3172 | 0 | 18.9583 | 8.75 | 3.5417 | 17.9435 | 10.1478 | 3.5618 | 16.129 | 7.7285 | 1.8145 | 6.5972 | 2.8472 | 0 | 1.8145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4274 | 0 | 0 | 8.3333 | 3.6806 | 0 | 12.2312 | 6.3172 | 0 | 18.9583 | 8.75 | 3.5417 | 17.9435 | 10.1478 | 3.5618 | 16.129 | 7.7285 | 1.8145 | 6.5972 | 2.8472 | 0 | 1.8145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4274 | 0 | 0 | 8.3333 | 3.6806 | 0 | 12.2312 | 6.3172 | 0 | 18.9583 | 8.75 | 3.5417 | 17.9435 | 10.1478 | 3.5618 | 16.129 | 7.7285 | 1.8145 | 6.5972 | 2.8472 | 0 | 1.8145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4274 | 0 | 0 | 8.3333 | 3.6806 | 0 | 12.2312 | 6.3172 | 0 | 18.9583 | 8.75 | 3.5417 | 17.9435 | 10.1478 | 3.5618 | 16.129 | 7.7285 | 1.8145 | 6.5972 | 2.8472 | 0 | 1.8145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4274 | 0 | 0 | 8.3333 | 3.6806 | 0 | 12.2312 | 6.3172 | 0 | 18.9583 | 8.75 | 3.5417 | 17.9435 | 10.1478 | 3.5618 | 16.129 | 7.7285 | 1.8145 | 6.5972 | 2.8472 | 0 | 1.8145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4274 | 0 | 0 | 8.3333 | 3.6806 | 0 | 12.2312 | 6.3172 | 0 | 18.9583 | 8.75 | 3.5417 | 17.9435 | 10.1478 | 3.5618 | 16.129 | 7.7285 | 1.8145 | 6.5972 | 2.8472 | 0 | 1.8145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4274 | 0 | 0 | 8.3333 | 3.6806 | 0 | 12.2312 | 6.3172 | 0 | 18.9583 | 8.75 | 3.5417 | 17.9435 | 10.1478 | 3.5618 | 16.129 | 7.7285 | 1.8145 | 6.5972 | 2.8472 | 0 | 1.8145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.75 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0694 | 0 | 0 | 5.2419 | 0 | 0 | 12.0139 | 4.0278 | 0 | 8.2661 | 3.629 | 0 | 7.7957 | 0 | 0 | 3.5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.75 | 6 | 3.629 | 0 | 0 | 6.4296 | 0 | 0 | 10.4839 | 0 | 0 | 18.6111 | 10 | 3.9583 | 18.5484 | 11.6263 | 7.0565 | 24.5139 | 18.5417 | 6.7361 | 25.6048 | 15.3226 | 8.9382 | 23.8575 | 13.3065 | 7.7285 | 16.5278 | 6.9444 | 0 | 5.6452 | 0 | 0 | 4.6528 | 0 | 0 | 4.8387 | 0 | 0
24 | 0.75 | 8 | 6.6532 | 0 | 0 | 8.6207 | 0 | 0 | 15.3898 | 3.8978 | 0 | 28.9583 | 17.5694 | 7.9861 | 29.8387 | 21.5726 | 12.7016 | 40.7639 | 25.6944 | 15.3472 | 41.1962 | 26.0753 | 19.4892 | 37.3656 | 21.371 | 15.9274 | 24.3056 | 11.875 | 4.5833 | 9.543 | 3.3602 | 0 | 5.4167 | 0 | 0 | 5.578 | 0 | 0
24 | 0.75 | 9 | 6.6532 | 0 | 0 | 8.6207 | 0 | 0 | 15.457 | 3.9651 | 0 | 30 | 18.125 | 8.0556 | 29.9059 | 22.6478 | 13.5753 | 41.3194 | 25.9722 | 15.4861 | 41.8683 | 29.0995 | 20.2285 | 39.1801 | 24.0591 | 15.9946 | 24.4444 | 12.7083 | 4.5833 | 9.543 | 3.3602 | 0 | 5.4167 | 0 | 0 | 5.578 | 0 | 0
24 | 0.75 | 10 | 6.6532 | 0 | 0 | 8.6207 | 0 | 0 | 15.457 | 4.0323 | 0 | 30 | 18.125 | 8.0556 | 30.0403 | 22.6478 | 13.5753 | 41.3194 | 25.9722 | 15.4861 | 41.9355 | 29.0995 | 20.2285 | 39.2473 | 24.3952 | 15.9946 | 24.4444 | 12.7083 | 4.5833 | 9.543 | 3.3602 | 0 | 5.4167 | 0 | 0 | 5.578 | 0 | 0
24 | 0.75 | 11 | 6.6532 | 0 | 0 | 8.6207 | 0 | 0 | 15.457 | 4.0323 | 0 | 30 | 18.125 | 8.0556 | 30.1075 | 22.6478 | 13.5753 | 41.3194 | 25.9722 | 15.4861 | 41.9355 | 29.0995 | 20.2285 | 39.2473 | 24.3952 | 15.9946 | 24.4444 | 12.7083 | 4.5833 | 9.543 | 3.3602 | 0 | 5.4167 | 0 | 0 | 5.578 | 0 | 0
24 | 0.75 | 12 | 6.6532 | 0 | 0 | 8.6207 | 0 | 0 | 15.457 | 4.0323 | 0 | 30 | 18.125 | 8.0556 | 30.1075 | 22.6478 | 13.5753 | 41.3194 | 25.9722 | 15.4861 | 41.9355 | 29.0995 | 20.2285 | 39.2473 | 24.3952 | 15.9946 | 24.4444 | 12.7083 | 4.5833 | 9.543 | 3.3602 | 0 | 5.4167 | 0 | 0 | 5.578 | 0 | 0
24 | 0.75 | 15 | 6.6532 | 0 | 0 | 8.6207 | 0 | 0 | 15.457 | 4.0323 | 0 | 30 | 18.125 | 8.0556 | 30.1075 | 22.6478 | 13.5753 | 41.3194 | 25.9722 | 15.4861 | 41.9355 | 29.0995 | 20.2285 | 39.2473 | 24.3952 | 15.9946 | 24.4444 | 12.7083 | 4.5833 | 9.543 | 3.3602 | 0 | 5.4167 | 0 | 0 | 5.578 | 0 | 0
24 | 0.75 | 20 | 6.6532 | 0 | 0 | 8.6207 | 0 | 0 | 15.457 | 4.0323 | 0 | 30 | 18.125 | 8.0556 | 30.1075 | 22.6478 | 13.5753 | 41.3194 | 25.9722 | 15.4861 | 41.9355 | 29.0995 | 20.2285 | 39.2473 | 24.3952 | 15.9946 | 24.4444 | 12.7083 | 4.5833 | 9.543 | 3.3602 | 0 | 5.4167 | 0 | 0 | 5.578 | 0 | 0
24 | 0.75 | 25 | 6.6532 | 0 | 0 | 8.6207 | 0 | 0 | 15.457 | 4.0323 | 0 | 30 | 18.125 | 8.0556 | 30.1075 | 22.6478 | 13.5753 | 41.3194 | 25.9722 | 15.4861 | 41.9355 | 29.0995 | 20.2285 | 39.2473 | 24.3952 | 15.9946 | 24.4444 | 12.7083 | 4.5833 | 9.543 | 3.3602 | 0 | 5.4167 | 0 | 0 | 5.578 | 0 | 0
24 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 1 | 4 | 0 | 0 | 0 | 3.497 | 0 | 0 | 1.0753 | 0 | 0 | 5.3472 | 0 | 0 | 6.25 | 2.1505 | 0 | 12.4306 | 4.4444 | 0 | 8.4677 | 3.629 | 0 | 8.0645 | 3.293 | 0 | 4.6528 | 0 | 0 | 3.0914 | 0 | 0 | 0.48611 | 0 | 0 | 0 | 0 | 0
24 | 1 | 6 | 4.8387 | 0 | 0 | 12.1382 | 4.903 | 0 | 14.9194 | 3.8306 | 0 | 23.9583 | 13.5417 | 7.6389 | 25.5376 | 18.4812 | 8.871 | 32.9167 | 21.1111 | 12.9167 | 31.0484 | 20.5645 | 13.3065 | 29.7043 | 18.0108 | 10.2151 | 20 | 10.3472 | 3.6111 | 7.4597 | 3.293 | 0 | 7.9861 | 3.3333 | 0 | 8.1989 | 2.2177 | 0
24 | 1 | 8 | 15.121 | 4.0995 | 0 | 21.7108 | 11.8304 | 3.3482 | 23.1183 | 13.6425 | 4.2339 | 39.2361 | 31.25 | 18.8194 | 44.6909 | 34.0726 | 27.7554 | 52.0139 | 39.0972 | 28.6111 | 53.2258 | 41.7339 | 30.8468 | 54.8387 | 34.6102 | 28.8978 | 37.2222 | 24.8611 | 15.2083 | 18.2796 | 8.6694 | 4.6371 | 12.5 | 5.7639 | 0 | 16.2634 | 5.7796 | 0
24 | 1 | 9 | 15.5242 | 4.5027 | 0 | 24.7768 | 12.8643 | 3.3482 | 25.1344 | 14.8522 | 5.3763 | 41.5972 | 34.8611 | 20.625 | 52.3522 | 40.7258 | 30.2419 | 54.9306 | 44.5139 | 33.125 | 62.0296 | 45.8333 | 31.9892 | 57.8629 | 41.0618 | 32.3925 | 41.8056 | 26.7361 | 15.4167 | 18.8844 | 10.3495 | 5.1075 | 12.7778 | 6.1111 | 0 | 16.4651 | 6.922 | 0
24 | 1 | 10 | 15.5242 | 4.5027 | 0 | 24.7768 | 12.8643 | 3.3482 | 25.2688 | 14.9866 | 5.4435 | 42.0139 | 37.0139 | 20.9028 | 54.3011 | 41.5995 | 30.914 | 55.9028 | 45.6944 | 35.5556 | 62.7016 | 46.5726 | 33.3333 | 59.0726 | 41.3306 | 33.6022 | 42.1528 | 27.6389 | 15.5556 | 18.8844 | 10.8199 | 5.1075 | 12.7778 | 6.1806 | 0 | 16.4651 | 6.9892 | 0
24 | 1 | 11 | 15.5242 | 4.5027 | 0 | 24.7768 | 12.8643 | 3.3482 | 25.336 | 14.9866 | 5.4435 | 42.0833 | 37.0833 | 20.9722 | 54.4355 | 41.6667 | 30.914 | 55.9722 | 45.7639 | 35.625 | 62.7688 | 46.7742 | 33.4005 | 59.1398 | 42.4059 | 33.6694 | 42.1528 | 27.6389 | 15.5556 | 18.8844 | 10.8199 | 5.1075 | 12.7778 | 6.1806 | 0 | 16.4651 | 6.9892 | 0
24 | 1 | 12 | 15.5242 | 4.5027 | 0 | 24.7768 | 12.8643 | 3.3482 | 25.336 | 14.9866 | 5.4435 | 42.0833 | 37.0833 | 20.9722 | 54.4355 | 41.6667 | 30.914 | 55.9722 | 45.7639 | 35.625 | 62.7688 | 46.7742 | 33.4005 | 59.1398 | 42.4059 | 33.6694 | 42.1528 | 27.6389 | 15.5556 | 18.8844 | 10.8199 | 5.1075 | 12.7778 | 6.1806 | 0 | 16.4651 | 6.9892 | 0
24 | 1 | 15 | 15.5242 | 4.5027 | 0 | 24.7768 | 12.8643 | 3.3482 | 25.336 | 14.9866 | 5.4435 | 42.0833 | 37.0833 | 20.9722 | 54.4355 | 41.6667 | 30.914 | 56.0417 | 45.7639 | 35.625 | 62.7688 | 46.7742 | 33.4005 | 59.1398 | 42.4059 | 33.6694 | 42.1528 | 27.6389 | 15.5556 | 18.8844 | 10.8199 | 5.1075 | 12.7778 | 6.1806 | 0 | 16.4651 | 6.9892 | 0
24 | 1 | 20 | 15.5242 | 4.5027 | 0 | 24.7768 | 12.8643 | 3.3482 | 25.336 | 14.9866 | 5.4435 | 42.0833 | 37.0833 | 20.9722 | 54.4355 | 41.6667 | 30.914 | 56.0417 | 45.7639 | 35.625 | 62.7688 | 46.7742 | 33.4005 | 59.1398 | 42.4059 | 33.6694 | 42.1528 | 27.6389 | 15.5556 | 18.8844 | 10.8199 | 5.1075 | 12.7778 | 6.1806 | 0 | 16.4651 | 6.9892 | 0
24 | 1 | 25 | 15.5242 | 4.5027 | 0 | 24.7768 | 12.8643 | 3.3482 | 25.336 | 14.9866 | 5.4435 | 42.0833 | 37.0833 | 20.9722 | 54.4355 | 41.6667 | 30.914 | 56.0417 | 45.7639 | 35.625 | 62.7688 | 46.7742 | 33.4005 | 59.1398 | 42.4059 | 33.6694 | 42.1528 | 27.6389 | 15.5556 | 18.8844 | 10.8199 | 5.1075 | 12.7778 | 6.1806 | 0 | 16.4651 | 6.9892 | 0
24 | 1.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 1.25 | 4 | 0.26882 | 0 | 0 | 3.5714 | 0 | 0 | 3.4274 | 0 | 0 | 7.1528 | 1.3194 | 0 | 6.3172 | 2.1505 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.0645 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.0914 | 0 | 0 | 2.4306 | 0 | 0 | 3.629 | 0 | 0
24 | 1.25 | 6 | 8.8038 | 3.293 | 0 | 15.5506 | 7.443 | 0 | 17.4059 | 5.8468 | 2.8226 | 26.6667 | 15.8333 | 9.1667 | 25.8065 | 21.0349 | 12.3656 | 36.1806 | 24.3056 | 15.625 | 31.1156 | 23.9919 | 14.7849 | 32.8629 | 20.1613 | 11.7608 | 24.4444 | 13.6111 | 4.0972 | 11.6263 | 4.6371 | 0 | 9.7222 | 4.4444 | 0 | 10.7527 | 4.3683 | 0
24 | 1.25 | 8 | 22.9167 | 7.5269 | 2.5538 | 28.2892 | 19.0374 | 4.9107 | 33.4005 | 21.1022 | 8.6022 | 48.0556 | 36.3889 | 24.9306 | 53.6962 | 44.0188 | 35.6855 | 59.4444 | 48.75 | 35.3472 | 62.2312 | 50.7392 | 36.6263 | 57.4597 | 44.1532 | 36.2231 | 42.0833 | 32.5694 | 19.3056 | 26.2097 | 14.2473 | 7.0565 | 19.375 | 9.0278 | 4.8611 | 22.2446 | 10.6855 | 0
24 | 1.25 | 9 | 25.0672 | 9.9462 | 3.4946 | 36.6071 | 21.5774 | 9.6726 | 38.1048 | 25.7392 | 14.4489 | 52.8472 | 44.6528 | 33.5417 | 62.2312 | 53.293 | 44.6237 | 65.7639 | 55.6944 | 44.0278 | 73.7903 | 60.7527 | 46.8414 | 65.6586 | 53.9651 | 42.7419 | 49.3056 | 38.6806 | 24.9306 | 29.8387 | 19.7581 | 10.7527 | 23.1944 | 12.8472 | 6.1806 | 26.5457 | 13.3065 | 3.2258
24 | 1.25 | 10 | 25.4032 | 11.6935 | 3.7634 | 38.2723 | 22.3958 | 9.8214 | 40.3226 | 27.8226 | 16.3306 | 61.4583 | 46.3194 | 37.7778 | 68.078 | 58.9382 | 48.1855 | 70.6944 | 62.8472 | 47.8472 | 78.293 | 64.8522 | 51.3441 | 69.8253 | 59.207 | 46.5726 | 52.4306 | 41.1111 | 27.6389 | 32.7957 | 21.7742 | 11.9624 | 24.2361 | 15.2778 | 6.1806 | 28.4274 | 13.4409 | 3.7634
24 | 1.25 | 11 | 25.4032 | 11.7608 | 4.3011 | 38.4159 | 22.5446 | 9.8958 | 42.1371 | 28.8306 | 16.5995 | 62.0833 | 48.2639 | 38.0556 | 68.6828 | 60.5511 | 48.7231 | 72.2917 | 63.1944 | 49.4444 | 78.5618 | 67.6075 | 52.621 | 71.5054 | 60.0134 | 48.1855 | 52.9167 | 41.25 | 27.8472 | 32.9301 | 23.4543 | 12.0968 | 24.4444 | 15.2778 | 6.1806 | 28.5618 | 13.5753 | 3.7634
24 | 1.25 | 12 | 25.4032 | 11.7608 | 4.3011 | 38.4159 | 22.619 | 9.8958 | 42.2043 | 28.8978 | 16.5995 | 62.0833 | 48.2639 | 38.0556 | 68.8172 | 61.0215 | 48.7231 | 72.3611 | 63.2639 | 49.7222 | 79.4355 | 67.6075 | 52.6882 | 72.5806 | 61.0887 | 48.3199 | 52.9167 | 41.3194 | 27.9167 | 32.9973 | 23.4543 | 12.0968 | 24.5139 | 15.2778 | 6.1806 | 28.629 | 13.5753 | 3.7634
24 | 1.25 | 15 | 25.4032 | 11.7608 | 4.3011 | 38.4159 | 22.619 | 9.8958 | 42.2043 | 28.8978 | 16.5995 | 62.0833 | 48.2639 | 38.0556 | 68.8172 | 61.0887 | 48.7231 | 72.3611 | 63.3333 | 49.7917 | 79.4355 | 67.6075 | 52.7554 | 72.5806 | 61.0887 | 48.3199 | 52.9167 | 41.3194 | 27.9167 | 32.9973 | 23.4543 | 12.0968 | 24.5139 | 15.2778 | 6.1806 | 28.629 | 13.5753 | 3.7634
24 | 1.25 | 20 | 25.4032 | 11.7608 | 4.3011 | 38.4159 | 22.619 | 9.8958 | 42.2043 | 28.8978 | 16.5995 | 62.0833 | 48.2639 | 38.0556 | 68.8172 | 61.0887 | 48.7231 | 72.3611 | 63.3333 | 49.7917 | 79.4355 | 67.6075 | 52.7554 | 72.5806 | 61.0887 | 48.3199 | 52.9167 | 41.3194 | 27.9167 | 32.9973 | 23.4543 | 12.0968 | 24.5139 | 15.2778 | 6.1806 | 28.629 | 13.5753 | 3.7634
24 | 1.25 | 25 | 25.4032 | 11.7608 | 4.3011 | 38.4159 | 22.619 | 9.8958 | 42.2043 | 28.8978 | 16.5995 | 62.0833 | 48.2639 | 38.0556 | 68.8172 | 61.0887 | 48.7231 | 72.3611 | 63.3333 | 49.7917 | 79.4355 | 67.6075 | 52.7554 | 72.5806 | 61.0887 | 48.3199 | 52.9167 | 41.3194 | 27.9167 | 32.9973 | 23.4543 | 12.0968 | 24.5139 | 15.2778 | 6.1806 | 28.629 | 13.5753 | 3.7634
24 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 1.5 | 4 | 2.0161 | 0 | 0 | 3.6561 | 0 | 0 | 3.4274 | 0 | 0 | 7.1528 | 2.9167 | 0 | 6.7876 | 4.0995 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.2661 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.293 | 0 | 0 | 2.4306 | 0 | 0 | 3.7634 | 0 | 0
24 | 1.5 | 6 | 11.8952 | 3.7634 | 0 | 18.7782 | 8.477 | 0 | 19.086 | 8.4005 | 3.4274 | 28.4722 | 16.8056 | 10.5556 | 27.7554 | 22.6478 | 14.5161 | 36.5278 | 25.9722 | 15.625 | 31.1156 | 24.2608 | 14.8522 | 33.2661 | 21.2366 | 12.4328 | 24.4444 | 14.8611 | 6.1111 | 12.2312 | 5.3091 | 0 | 11.1806 | 4.8611 | 0 | 12.5672 | 4.5027 | 0
24 | 1.5 | 8 | 27.8226 | 11.2231 | 3.3602 | 35.3346 | 23.9737 | 5.6471 | 38.172 | 22.7823 | 13.172 | 50.1389 | 40.9028 | 30.4861 | 59.3414 | 47.5134 | 37.9032 | 64.375 | 52.7083 | 39.7222 | 64.9194 | 55.0403 | 38.3065 | 58.6022 | 48.7231 | 38.4409 | 47.0139 | 36.1806 | 22.9167 | 28.6962 | 18.3468 | 9.879 | 22.0139 | 12.9167 | 7.7778 | 24.7312 | 13.172 | 3.6962
24 | 1.5 | 9 | 30.578 | 15.793 | 7.7957 | 43.8629 | 29.3822 | 11.9048 | 44.6237 | 33.1317 | 19.5565 | 60.2083 | 50.4167 | 40.0694 | 68.5484 | 58.1989 | 48.9919 | 72.4306 | 65.4167 | 49.9306 | 78.0242 | 65.121 | 55.1075 | 69.2204 | 59.7446 | 50.8737 | 55.2083 | 45.7639 | 29.4444 | 33.4005 | 26.0081 | 14.1801 | 27.7083 | 16.8056 | 9.4444 | 32.3253 | 17.2043 | 6.0484
24 | 1.5 | 10 | 35.4839 | 18.9516 | 8.6022 | 47.9167 | 32.6637 | 14.6552 | 48.7231 | 38.2392 | 25.4032 | 69.5833 | 57.1528 | 47.9861 | 75.2016 | 67.3387 | 57.1909 | 78.75 | 72.0139 | 61.4583 | 84.879 | 73.3199 | 63.3065 | 76.2097 | 66.6667 | 58.6022 | 63.8889 | 51.8056 | 36.5972 | 37.7016 | 31.6532 | 20.0269 | 34.7917 | 22.3611 | 9.7222 | 35.2151 | 20.7661 | 8.5349
24 | 1.5 | 11 | 38.6425 | 19.422 | 10.6183 | 49.1071 | 33.2589 | 17.4056 | 50.4032 | 40.3226 | 26.8145 | 71.25 | 60.2778 | 48.75 | 77.4866 | 69.4892 | 61.2903 | 81.0417 | 74.7917 | 65.2083 | 86.9624 | 78.4274 | 67.5403 | 80.8468 | 69.4892 | 60.9543 | 66.25 | 53.0556 | 41.4583 | 39.9866 | 34.543 | 21.6398 | 36.5972 | 23.6111 | 9.8611 | 36.7608 | 21.5726 | 8.6022
24 | 1.5 | 12 | 38.7769 | 19.4892 | 10.6855 | 49.1815 | 33.3333 | 17.4056 | 50.672 | 40.3898 | 27.0833 | 71.6667 | 61.1806 | 49.1667 | 78.8306 | 71.707 | 62.2984 | 81.5972 | 76.1111 | 65.5556 | 87.2984 | 79.3683 | 67.6747 | 81.5188 | 70.3629 | 61.6263 | 66.5278 | 54.6528 | 41.6667 | 43.3468 | 35.0134 | 21.9086 | 36.7361 | 24.1667 | 10.0694 | 37.0968 | 22.2446 | 8.6022
24 | 1.5 | 15 | 38.9113 | 19.4892 | 10.6855 | 49.256 | 33.4077 | 17.4056 | 50.8065 | 40.457 | 27.0833 | 71.7361 | 61.3889 | 49.2361 | 78.8978 | 72.4462 | 62.4328 | 81.875 | 76.25 | 65.5556 | 87.3656 | 79.6371 | 67.7419 | 81.586 | 70.4301 | 62.5 | 66.6667 | 54.7917 | 41.7361 | 43.3468 | 35.0806 | 21.9086 | 36.7361 | 24.1667 | 10.0694 | 37.164 | 22.2446 | 8.6022
24 | 1.5 | 20 | 38.9113 | 19.4892 | 10.6855 | 49.256 | 33.4077 | 17.4056 | 50.8065 | 40.457 | 27.0833 | 71.7361 | 61.3889 | 49.2361 | 78.8978 | 72.4462 | 62.4328 | 81.875 | 76.25 | 65.5556 | 87.3656 | 79.6371 | 67.8091 | 81.586 | 70.4301 | 62.5 | 66.6667 | 54.7917 | 41.7361 | 43.3468 | 35.0806 | 21.9086 | 36.7361 | 24.1667 | 10.0694 | 37.164 | 22.2446 | 8.6022
24 | 1.5 | 25 | 38.9113 | 19.4892 | 10.6855 | 49.256 | 33.4077 | 17.4056 | 50.8065 | 40.457 | 27.0833 | 71.7361 | 61.3889 | 49.2361 | 78.8978 | 72.4462 | 62.4328 | 81.875 | 76.25 | 65.5556 | 87.3656 | 79.6371 | 67.8091 | 81.586 | 70.4301 | 62.5 | 66.6667 | 54.7917 | 41.7361 | 43.3468 | 35.0806 | 21.9086 | 36.7361 | 24.1667 | 10.0694 | 37.164 | 22.2446 | 8.6022
24 | 1.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 1.75 | 4 | 2.0161 | 0 | 0 | 3.6561 | 0 | 0 | 3.4274 | 0 | 0 | 7.1528 | 2.9167 | 0 | 7.9301 | 4.4355 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.2661 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.4274 | 0 | 0 | 3.6111 | 0 | 0 | 3.7634 | 0 | 0
24 | 1.75 | 6 | 12.164 | 4.6371 | 0 | 19.8994 | 9.0671 | 0.74405 | 19.086 | 9.207 | 3.7634 | 28.4722 | 16.9444 | 10.9028 | 28.2258 | 23.1855 | 15.0538 | 36.5278 | 25.9722 | 16.0417 | 31.1156 | 24.5296 | 14.8522 | 33.2661 | 21.3038 | 12.5672 | 24.4444 | 15.2778 | 6.1111 | 12.2312 | 5.6452 | 1.8145 | 11.5278 | 4.9306 | 0 | 12.5672 | 4.6371 | 0
24 | 1.75 | 8 | 29.0323 | 13.5081 | 3.8306 | 37.5744 | 25.4387 | 7.7381 | 39.7177 | 25 | 15.3226 | 54.9306 | 44.0278 | 33.0556 | 61.0887 | 49.664 | 38.9113 | 65.625 | 55.1389 | 41.0417 | 65.1882 | 55.2419 | 38.9785 | 58.9382 | 50.6048 | 39.9194 | 47.9167 | 36.6667 | 24.7222 | 30.5108 | 21.707 | 11.0215 | 27.5 | 14.7917 | 9.1667 | 28.9651 | 15.3226 | 3.8306
24 | 1.75 | 9 | 34.4086 | 19.6909 | 8.6022 | 47.0238 | 34.4494 | 12.5 | 45.6989 | 37.7688 | 22.9167 | 63.8194 | 54.3056 | 45.9722 | 73.6559 | 60.6855 | 53.1586 | 74.2361 | 67.7083 | 52.4306 | 79.5027 | 66.3978 | 56.1156 | 71.6398 | 61.7608 | 52.957 | 60.625 | 48.2639 | 34.375 | 38.3737 | 30.4435 | 18.6156 | 33.8194 | 22.4306 | 11.8056 | 36.3575 | 22.1102 | 7.4597
24 | 1.75 | 10 | 41.8011 | 25.4032 | 13.3065 | 52.9018 | 40.0015 | 18.5268 | 54.5027 | 44.086 | 32.0565 | 73.6111 | 62.4306 | 53.5417 | 80.1075 | 71.4382 | 63.5753 | 83.6806 | 76.5278 | 65.1389 | 88.9785 | 78.293 | 68.2124 | 80.0403 | 70.3629 | 61.9624 | 68.125 | 56.1806 | 42.8472 | 44.1532 | 34.543 | 22.7151 | 41.8056 | 29.5833 | 15.0694 | 40.8602 | 27.2849 | 11.9624
24 | 1.75 | 11 | 45.3629 | 30.0403 | 16.5995 | 57.8869 | 44.7917 | 19.2708 | 63.9785 | 49.4624 | 35.6855 | 79.7222 | 68.8194 | 59.0278 | 84.0726 | 78.8978 | 70.4973 | 87.2917 | 82.2917 | 73.2639 | 92.4059 | 84.2742 | 75.8737 | 84.6774 | 76.6801 | 67.2043 | 72.0833 | 59.7222 | 50.2083 | 49.328 | 42.4731 | 29.6371 | 46.1806 | 32.7083 | 16.6667 | 42.0699 | 31.7876 | 13.9113
24 | 1.75 | 12 | 46.2366 | 31.3844 | 17.6075 | 59.0774 | 45.9283 | 21.2054 | 66.2634 | 53.1586 | 37.4328 | 80.5556 | 71.6667 | 60.3472 | 87.9032 | 82.7285 | 73.3199 | 88.6806 | 85.0694 | 75.9722 | 94.2876 | 87.5672 | 78.7634 | 86.1559 | 78.4946 | 69.5565 | 75.1389 | 63.4722 | 52.2222 | 53.0914 | 45.1613 | 31.6532 | 50.0694 | 37.2222 | 17.7778 | 42.2043 | 33.5349 | 13.9113
24 | 1.75 | 15 | 46.3038 | 31.586 | 18.414 | 59.8214 | 46.408 | 21.4286 | 68.3468 | 53.1586 | 38.2392 | 81.3194 | 72.0139 | 61.7361 | 87.9704 | 83.1317 | 74.4624 | 88.8889 | 85.4167 | 76.1806 | 94.7581 | 88.0376 | 79.5699 | 86.9624 | 78.8978 | 70.9005 | 76.4583 | 64.2361 | 53.4722 | 54.2339 | 45.6317 | 32.9301 | 50.6944 | 38.0556 | 17.8472 | 44.2204 | 34.207 | 13.9113
24 | 1.75 | 20 | 46.3038 | 31.586 | 18.414 | 59.8214 | 46.408 | 21.4286 | 68.3468 | 53.1586 | 38.2392 | 81.3194 | 72.0139 | 61.7361 | 87.9704 | 83.1317 | 74.4624 | 88.8889 | 85.4167 | 76.1806 | 94.7581 | 88.0376 | 79.5699 | 86.9624 | 78.8978 | 70.9005 | 76.4583 | 64.2361 | 53.4722 | 54.2339 | 45.6317 | 32.9301 | 50.6944 | 38.0556 | 17.8472 | 44.2204 | 34.207 | 13.9113
24 | 1.75 | 25 | 46.3038 | 31.586 | 18.414 | 59.8214 | 46.408 | 21.4286 | 68.3468 | 53.1586 | 38.2392 | 81.3194 | 72.0139 | 61.7361 | 87.9704 | 83.1317 | 74.4624 | 88.8889 | 85.4167 | 76.1806 | 94.7581 | 88.0376 | 79.5699 | 86.9624 | 78.8978 | 70.9005 | 76.4583 | 64.2361 | 53.4722 | 54.2339 | 45.6317 | 32.9301 | 50.6944 | 38.0556 | 17.8472 | 44.2204 | 34.207 | 13.9113
24 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 2 | 4 | 2.0161 | 0 | 0 | 3.6561 | 0 | 0 | 3.5618 | 0 | 0 | 7.1528 | 2.9167 | 0 | 7.9301 | 4.4355 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.2661 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.4274 | 0 | 0 | 3.6111 | 0 | 0 | 3.8978 | 0 | 0
24 | 2 | 6 | 12.4328 | 4.7715 | 0 | 19.8994 | 9.0671 | 0.74405 | 19.086 | 9.2742 | 3.7634 | 29.5139 | 17.1528 | 10.9722 | 28.4274 | 23.4543 | 15.0538 | 36.5278 | 26.0417 | 16.0417 | 31.1156 | 24.5296 | 14.8522 | 33.2661 | 21.3038 | 12.5672 | 24.7222 | 15.2778 | 6.1111 | 12.2312 | 6.0484 | 1.8145 | 11.5278 | 4.9306 | 0 | 13.3737 | 4.7715 | 0
24 | 2 | 8 | 29.1667 | 14.9866 | 4.7715 | 39.3601 | 25.8621 | 11.5327 | 39.9194 | 26.0753 | 16.5995 | 55.2778 | 44.6528 | 35.0694 | 61.0887 | 49.8656 | 40.5242 | 65.625 | 55.1389 | 41.7361 | 65.2554 | 55.2419 | 40.5242 | 59.0054 | 50.8065 | 39.9194 | 48.0556 | 37.0139 | 25.1389 | 31.3844 | 23.7231 | 12.7688 | 28.2639 | 16.5972 | 10 | 30.5108 | 16.8683 | 5.3763
24 | 2 | 9 | 35.4167 | 21.5726 | 10.1478 | 48.8095 | 36.7098 | 16.7411 | 46.9758 | 38.9113 | 25.4704 | 67.2917 | 57.3611 | 47.7778 | 74.2608 | 61.2231 | 55.0403 | 74.7917 | 68.5417 | 53.8194 | 81.1828 | 66.8683 | 56.4516 | 72.379 | 62.3656 | 53.6962 | 61.5972 | 50.2083 | 35 | 40.3226 | 31.4516 | 19.6237 | 36.25 | 23.6111 | 12.7083 | 39.5833 | 24.328 | 7.5941
24 | 2 | 10 | 46.1694 | 27.2849 | 15.3226 | 56.5476 | 44.8199 | 23.1399 | 59.6102 | 46.1694 | 35.7527 | 76.4583 | 65.2778 | 58.2639 | 81.1828 | 73.5887 | 66.3306 | 85.2083 | 78.9583 | 67.1528 | 90.6586 | 79.1667 | 71.9086 | 81.1828 | 72.2446 | 65.9274 | 68.8889 | 58.4028 | 46.5972 | 50.4704 | 40.5242 | 25.5376 | 46.25 | 34.4444 | 19.2361 | 45.5645 | 30.5108 | 18.4812
24 | 2 | 11 | 49.5968 | 35.0134 | 19.7581 | 63.3929 | 50.9621 | 24.7768 | 70.5645 | 53.8306 | 42.0699 | 83.6806 | 72.8472 | 66.6667 | 88.3737 | 81.7204 | 76.0081 | 90.5556 | 86.5972 | 78.3333 | 94.9597 | 87.836 | 78.629 | 86.5591 | 80.3763 | 72.8495 | 76.0417 | 65.1389 | 51.9444 | 56.3844 | 47.9839 | 34.4758 | 52.8472 | 43.8889 | 24.6528 | 48.8575 | 34.543 | 20.7661
24 | 2 | 12 | 53.9651 | 38.3737 | 25.672 | 67.3363 | 53.7228 | 27.0833 | 76.1425 | 60.6855 | 47.1102 | 88.8194 | 78.0556 | 69.3056 | 91.5323 | 86.0215 | 79.3683 | 93.1944 | 88.4028 | 82.2222 | 96.707 | 91.4651 | 82.9973 | 89.3817 | 84.9462 | 78.5618 | 79.5833 | 70.2083 | 58.4028 | 63.0376 | 50.672 | 41.1962 | 56.4583 | 46.8056 | 27.5694 | 53.9651 | 38.5081 | 20.7661
24 | 2 | 15 | 57.3925 | 40.7258 | 27.621 | 69.8661 | 54.1667 | 32.1839 | 78.7634 | 62.0968 | 50.672 | 90.2083 | 81.0417 | 70.2083 | 92.6075 | 87.836 | 82.6613 | 93.8194 | 89.3056 | 84.7222 | 97.1102 | 92.5403 | 84.6774 | 91.4651 | 86.4247 | 79.6371 | 82.4306 | 72.9861 | 61.1111 | 66.6667 | 54.0323 | 43.75 | 60.5556 | 48.8889 | 29.8611 | 54.9731 | 40.457 | 20.9677
24 | 2 | 20 | 57.3925 | 41.4651 | 27.621 | 69.8661 | 54.1667 | 32.1839 | 78.8306 | 62.0968 | 50.672 | 90.2083 | 81.0417 | 70.2083 | 92.6075 | 87.9704 | 82.6613 | 93.8194 | 89.3056 | 84.7222 | 97.1102 | 92.5403 | 84.6774 | 91.4651 | 86.4247 | 79.6371 | 82.4306 | 72.9861 | 61.1111 | 66.6667 | 54.0323 | 43.8172 | 60.625 | 48.8889 | 29.8611 | 54.9731 | 40.457 | 20.9677
24 | 2 | 25 | 57.3925 | 41.4651 | 27.621 | 69.8661 | 54.1667 | 32.1839 | 78.8306 | 62.0968 | 50.672 | 90.2083 | 81.0417 | 70.2083 | 92.6075 | 87.9704 | 82.6613 | 93.8194 | 89.3056 | 84.7222 | 97.1102 | 92.5403 | 84.6774 | 91.4651 | 86.4247 | 79.6371 | 82.4306 | 72.9861 | 61.1111 | 66.6667 | 54.0323 | 43.8172 | 60.625 | 48.8889 | 29.8611 | 54.9731 | 40.457 | 20.9677
24 | 2.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 2.25 | 4 | 2.0161 | 0 | 0 | 3.7279 | 0 | 0 | 3.5618 | 0 | 0 | 7.1528 | 2.9167 | 0 | 7.9301 | 4.4355 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.2661 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.4274 | 0 | 0 | 3.6111 | 0 | 0 | 3.8978 | 0 | 0
24 | 2.25 | 6 | 12.4328 | 4.7715 | 0 | 19.8994 | 9.0671 | 0.74405 | 19.086 | 10.3495 | 3.7634 | 29.5139 | 17.1528 | 10.9722 | 28.4274 | 23.4543 | 15.0538 | 36.5278 | 26.3194 | 16.0417 | 31.1156 | 24.5296 | 14.8522 | 33.2661 | 21.3038 | 12.5672 | 24.7222 | 15.2778 | 6.1111 | 13.9113 | 7.1237 | 1.8145 | 11.5278 | 4.9306 | 0 | 13.3737 | 4.7715 | 0
24 | 2.25 | 8 | 29.3011 | 15.7258 | 6.0484 | 39.5833 | 26.3649 | 12.0536 | 40.457 | 27.957 | 16.7339 | 55.2778 | 44.6528 | 36.8056 | 61.0887 | 49.8656 | 42.2043 | 66.25 | 55.1389 | 41.875 | 65.2554 | 55.2419 | 40.5914 | 59.0054 | 50.8737 | 40.5914 | 48.0556 | 37.0833 | 25.1389 | 32.9301 | 24.5296 | 12.7688 | 30.2778 | 17.4306 | 10 | 31.6532 | 16.8683 | 5.5108
24 | 2.25 | 9 | 36.3575 | 22.7823 | 10.2151 | 49.1815 | 38.1902 | 17.0387 | 49.4624 | 39.7177 | 25.9409 | 67.8472 | 57.9861 | 48.9583 | 74.4624 | 63.4409 | 55.7124 | 76.0417 | 68.5417 | 54.0278 | 81.7204 | 67.1371 | 56.586 | 73.1855 | 63.7769 | 53.9651 | 61.8056 | 50.4861 | 35.4861 | 42.7419 | 32.1909 | 20.2285 | 36.8056 | 24.6528 | 15.1389 | 40.7258 | 25.0672 | 7.9301
24 | 2.25 | 10 | 47.5134 | 30.914 | 17.8763 | 57.5149 | 46.1233 | 23.9583 | 63.6425 | 48.5215 | 38.3065 | 76.875 | 68.0556 | 61.25 | 81.3844 | 74.7312 | 67.9435 | 85.9028 | 79.7917 | 68.1944 | 91.7339 | 79.4355 | 72.9839 | 81.9892 | 72.5806 | 66.7339 | 70 | 59.4444 | 47.7778 | 53.5618 | 42.2715 | 27.1505 | 49.4444 | 36.3194 | 19.4444 | 46.5054 | 32.1909 | 20.4973
24 | 2.25 | 11 | 54.8387 | 38.2392 | 23.5215 | 65.253 | 54.9774 | 27.5298 | 75.0672 | 58.2661 | 45.6989 | 86.0417 | 75.3472 | 69.3056 | 89.0457 | 83.3333 | 77.957 | 92.2917 | 88.1944 | 81.4583 | 95.9677 | 89.3817 | 79.7715 | 88.8441 | 82.8629 | 74.664 | 80.5556 | 67.5694 | 57.5 | 61.2903 | 49.5968 | 36.828 | 57.0833 | 47.1528 | 30.2778 | 53.8978 | 38.0376 | 22.7823
24 | 2.25 | 12 | 60.0806 | 41.9355 | 29.4355 | 70.3305 | 60.5655 | 35.5655 | 80.3091 | 67.0027 | 53.629 | 90.6944 | 83.4028 | 74.2361 | 94.2204 | 88.7097 | 83.871 | 94.5833 | 90.8333 | 86.4583 | 97.5134 | 93.6156 | 86.2231 | 92.8763 | 87.9704 | 80.1747 | 84.8611 | 74.5139 | 62.7778 | 68.2124 | 54.3011 | 46.6398 | 63.8194 | 51.8056 | 36.5278 | 59.3414 | 46.5054 | 24.9328
24 | 2.25 | 15 | 64.7849 | 46.8414 | 38.0376 | 76.1905 | 63.8111 | 41.9643 | 83.1989 | 69.8925 | 59.0726 | 93.2639 | 85.8333 | 79.0972 | 96.5054 | 92.0027 | 88.4409 | 95.6944 | 92.9167 | 89.0278 | 98.7231 | 96.0349 | 88.9785 | 95.4973 | 90.793 | 83.3333 | 88.4722 | 78.6111 | 67.2917 | 74.7984 | 61.2231 | 53.0914 | 70.6944 | 58.4722 | 38.8194 | 63.1048 | 50 | 29.5027
24 | 2.25 | 20 | 64.8522 | 46.8414 | 38.1048 | 77.0833 | 63.8111 | 42.1131 | 83.1989 | 70.0269 | 59.0726 | 93.3333 | 85.9028 | 79.0972 | 96.5054 | 92.0027 | 88.4409 | 95.7639 | 92.9167 | 89.2361 | 98.7231 | 96.0349 | 89.0457 | 95.4973 | 90.8602 | 83.4005 | 88.6806 | 78.6111 | 67.2917 | 74.9328 | 61.4247 | 53.0914 | 70.6944 | 58.4722 | 38.8889 | 63.1048 | 50.0672 | 29.5027
24 | 2.25 | 25 | 64.8522 | 46.8414 | 38.1048 | 77.0833 | 63.8111 | 42.1131 | 83.1989 | 70.0269 | 59.0726 | 93.3333 | 85.9028 | 79.0972 | 96.5054 | 92.0027 | 88.4409 | 95.7639 | 92.9167 | 89.2361 | 98.7231 | 96.0349 | 89.0457 | 95.4973 | 90.8602 | 83.4005 | 88.6806 | 78.6111 | 67.2917 | 74.9328 | 61.4247 | 53.0914 | 70.6944 | 58.4722 | 38.8889 | 63.1048 | 50.0672 | 29.5027
24 | 2.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 2.5 | 4 | 2.0161 | 0 | 0 | 3.7279 | 0 | 0 | 3.5618 | 0 | 0 | 7.1528 | 2.9167 | 0 | 7.9301 | 4.4355 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.2661 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.4274 | 0 | 0 | 3.6111 | 0 | 0 | 3.8978 | 0 | 0
24 | 2.5 | 6 | 12.4328 | 4.7715 | 0 | 19.8994 | 9.0671 | 0.74405 | 19.086 | 10.3495 | 3.7634 | 29.5139 | 17.1528 | 10.9722 | 28.4274 | 23.4543 | 15.0538 | 36.5278 | 26.3194 | 16.0417 | 31.1156 | 24.5296 | 14.8522 | 33.2661 | 21.3038 | 12.5672 | 24.7222 | 15.2778 | 6.1111 | 13.9113 | 7.1237 | 1.8145 | 11.6667 | 4.9306 | 0 | 13.3737 | 4.7715 | 0
24 | 2.5 | 8 | 29.3011 | 15.7258 | 6.0484 | 39.5833 | 26.3649 | 12.128 | 40.5914 | 28.0242 | 16.7339 | 55.2778 | 45.8333 | 38.0556 | 61.0887 | 50 | 42.2043 | 66.25 | 55.1389 | 41.875 | 65.2554 | 55.2419 | 40.5914 | 59.0054 | 50.8737 | 40.5914 | 48.0556 | 37.0833 | 25.1389 | 33.4005 | 24.664 | 13.0376 | 31.0417 | 17.5 | 10 | 31.922 | 16.8683 | 5.5108
24 | 2.5 | 9 | 37.164 | 22.9167 | 10.3495 | 49.4048 | 38.6494 | 17.2619 | 49.664 | 40.1882 | 26.1425 | 67.9167 | 57.9861 | 49.6528 | 74.5968 | 64.9866 | 55.7124 | 76.1806 | 68.5417 | 54.2361 | 81.7204 | 67.2043 | 57.3925 | 73.3871 | 63.7769 | 54.0323 | 61.8056 | 50.8333 | 35.625 | 43.5484 | 32.6613 | 21.1694 | 37.2222 | 25.2083 | 15.7639 | 41.129 | 25.1344 | 8.2661
24 | 2.5 | 10 | 48.7231 | 31.3172 | 18.1452 | 58.8542 | 46.4157 | 24.256 | 64.0457 | 49.3952 | 38.5753 | 77.0139 | 69.4444 | 61.9444 | 81.586 | 76.1425 | 68.6156 | 86.25 | 80.2083 | 68.4722 | 91.9355 | 79.5699 | 72.9839 | 82.5269 | 73.6559 | 67.6747 | 70.7639 | 59.7917 | 48.4722 | 54.0323 | 44.2204 | 27.5538 | 49.9306 | 36.5278 | 19.6528 | 49.2608 | 33.3333 | 21.0349
24 | 2.5 | 11 | 56.9892 | 39.2473 | 25.2016 | 66.2202 | 56.5733 | 28.4226 | 75.6048 | 60.7527 | 48.3199 | 87.4306 | 78.5417 | 70.625 | 89.5833 | 84.7446 | 78.3602 | 93.0556 | 89.7917 | 82.5 | 96.7742 | 89.7849 | 80.914 | 89.4489 | 84.6774 | 75 | 81.6667 | 67.8472 | 57.9861 | 63.9113 | 52.4194 | 38.7769 | 58.1944 | 47.9861 | 32.5694 | 56.7204 | 39.4489 | 25.2016
24 | 2.5 | 12 | 62.2984 | 44.3548 | 33.5349 | 74.6408 | 64.3268 | 37.872 | 82.1237 | 70.0941 | 56.1828 | 90.7639 | 84.8611 | 78.9583 | 94.9597 | 90.121 | 85.4839 | 95.4167 | 92.5 | 87.5694 | 98.9247 | 95.5645 | 87.3656 | 95.0269 | 89.6505 | 81.9892 | 86.3889 | 76.3194 | 67.2917 | 71.2366 | 56.922 | 48.3199 | 65.2778 | 54.0972 | 38.6111 | 62.2312 | 48.0511 | 31.8548
24 | 2.5 | 15 | 70.9677 | 55.4435 | 41.2634 | 81.6041 | 71.9494 | 49.0327 | 88.3065 | 75.2688 | 63.7097 | 96.1111 | 90.0694 | 86.3194 | 98.0511 | 96.0349 | 92.0027 | 97.0833 | 94.9306 | 92.0139 | 100 | 98.1183 | 91.7339 | 98.0511 | 92.8091 | 87.7016 | 91.5278 | 84.8611 | 73.6111 | 82.3253 | 68.0108 | 60.2151 | 75.9722 | 62.0833 | 47.3611 | 70.4973 | 57.5941 | 40.121
24 | 2.5 | 20 | 71.6398 | 55.7796 | 41.3978 | 81.6041 | 71.9494 | 49.256 | 88.4409 | 75.8065 | 63.8441 | 96.25 | 90.1389 | 86.3194 | 98.3871 | 96.1022 | 92.1371 | 97.1528 | 94.9306 | 92.0139 | 100 | 98.1855 | 91.9355 | 98.0511 | 93.2796 | 87.7016 | 91.5278 | 84.9306 | 73.6806 | 82.7285 | 68.078 | 60.6183 | 76.0417 | 62.1528 | 48.0556 | 70.8333 | 57.8629 | 40.1882
24 | 2.5 | 25 | 71.6398 | 55.7796 | 41.3978 | 81.6041 | 71.9494 | 49.256 | 88.4409 | 75.8065 | 63.8441 | 96.25 | 90.1389 | 86.3194 | 98.3871 | 96.1022 | 92.1371 | 97.1528 | 94.9306 | 92.0139 | 100 | 98.1855 | 91.9355 | 98.0511 | 93.2796 | 87.7016 | 91.5278 | 84.9306 | 73.6806 | 82.7285 | 68.078 | 60.6183 | 76.0417 | 62.1528 | 48.0556 | 70.8333 | 57.8629 | 40.1882
24 | 2.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 2.75 | 4 | 2.0161 | 0 | 0 | 3.7279 | 0 | 0 | 3.5618 | 0 | 0 | 7.1528 | 2.9167 | 0 | 7.9301 | 4.4355 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.2661 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.4274 | 0 | 0 | 3.6111 | 0 | 0 | 3.8978 | 0 | 0
24 | 2.75 | 6 | 12.4328 | 4.7715 | 0 | 20.2586 | 9.0671 | 0.74405 | 19.086 | 10.3495 | 3.7634 | 29.5139 | 17.1528 | 10.9722 | 28.4274 | 23.4543 | 15.0538 | 36.5278 | 26.3194 | 16.0417 | 31.1156 | 24.5296 | 14.8522 | 33.2661 | 21.3038 | 12.5672 | 24.7222 | 15.2778 | 6.1111 | 13.9113 | 7.1237 | 1.8145 | 11.6667 | 4.9306 | 0 | 13.3737 | 4.7715 | 0
24 | 2.75 | 8 | 29.3011 | 15.793 | 6.0484 | 39.5833 | 26.3649 | 12.2024 | 40.6586 | 28.0242 | 16.7339 | 55.2778 | 45.8333 | 38.1944 | 61.0887 | 50 | 42.2043 | 66.25 | 55.1389 | 41.875 | 65.2554 | 55.2419 | 40.5914 | 59.0054 | 50.8737 | 40.5914 | 48.0556 | 37.0833 | 25.1389 | 33.4005 | 24.664 | 13.0376 | 31.1111 | 18.0556 | 10 | 32.1237 | 16.8683 | 7.0565
24 | 2.75 | 9 | 37.4328 | 22.9839 | 10.3495 | 49.4792 | 39.2241 | 17.3363 | 49.664 | 40.457 | 27.2849 | 67.9167 | 57.9861 | 49.6528 | 74.664 | 64.9866 | 55.7124 | 76.3194 | 68.5417 | 54.2361 | 81.7204 | 67.2043 | 57.3925 | 73.3871 | 63.7769 | 54.0323 | 61.8056 | 50.8333 | 35.8333 | 43.5484 | 33.0645 | 21.3038 | 38.5417 | 25.2778 | 15.9028 | 41.7339 | 25.1344 | 10.2823
24 | 2.75 | 10 | 49.0591 | 31.922 | 19.8925 | 59.7162 | 46.6338 | 26.5625 | 64.1129 | 49.4624 | 38.6425 | 77.0139 | 69.4444 | 62.1528 | 81.7204 | 76.1425 | 69.086 | 86.3889 | 80.2083 | 68.5417 | 91.9355 | 79.6371 | 72.9839 | 82.5269 | 73.7231 | 67.6747 | 70.9722 | 59.7917 | 49.0278 | 54.1667 | 44.8253 | 30.4435 | 50.9722 | 36.8056 | 19.6528 | 49.5968 | 33.3333 | 21.5726
24 | 2.75 | 11 | 58.4005 | 40.3226 | 27.2367 | 66.5179 | 57.0146 | 31.622 | 76.2097 | 61.8952 | 48.6559 | 88.0556 | 79.6528 | 71.875 | 89.5833 | 85.1478 | 78.6962 | 93.2639 | 89.9306 | 82.7778 | 96.8414 | 89.9194 | 81.586 | 89.6505 | 84.8118 | 75 | 82.5 | 67.9167 | 59.9306 | 65.457 | 52.5538 | 39.7177 | 59.6528 | 48.5417 | 32.9861 | 57.5941 | 41.7339 | 28.0914
24 | 2.75 | 12 | 63.5081 | 46.4382 | 36.8952 | 76.6677 | 65.625 | 40.7738 | 82.9973 | 70.6317 | 57.5269 | 91.7361 | 85.9722 | 80.9028 | 95.1613 | 90.5914 | 86.0887 | 95.9028 | 92.9861 | 87.7778 | 99.1263 | 95.6317 | 88.1048 | 96.5726 | 90.3226 | 82.5269 | 87.2917 | 77.3611 | 68.6806 | 73.0511 | 58.4005 | 49.664 | 67.3611 | 57.9167 | 39.4444 | 62.9704 | 51.3441 | 35.0806
24 | 2.75 | 15 | 77.0833 | 62.2312 | 47.5806 | 85.2319 | 76.9063 | 57.7586 | 92.3387 | 78.2258 | 71.9086 | 97.6389 | 93.8889 | 89.8611 | 99.2608 | 97.7151 | 92.9435 | 98.6111 | 96.5278 | 94.4444 | 100 | 98.9919 | 94.4892 | 99.328 | 95.7661 | 90.9946 | 93.5417 | 88.2639 | 79.1667 | 86.5591 | 76.0753 | 68.3468 | 80.4167 | 71.3194 | 54.2361 | 76.2097 | 64.0457 | 48.1183
24 | 2.75 | 20 | 78.1586 | 63.0376 | 48.1855 | 85.3756 | 76.9063 | 57.9023 | 92.5403 | 79.5027 | 72.6478 | 98.3333 | 94.0278 | 90.625 | 99.3952 | 97.9167 | 93.5484 | 98.6111 | 96.5972 | 94.5139 | 100 | 98.9919 | 94.5565 | 99.328 | 95.7661 | 91.0618 | 94.9306 | 88.4028 | 79.6528 | 89.0457 | 77.1505 | 69.2204 | 80.8333 | 72.2917 | 56.25 | 77.957 | 66.5995 | 49.0591
24 | 2.75 | 25 | 78.1586 | 63.0376 | 48.1855 | 85.3756 | 76.9063 | 57.9023 | 92.5403 | 79.5027 | 72.6478 | 98.3333 | 94.0278 | 90.625 | 99.3952 | 97.9167 | 93.5484 | 98.6111 | 96.5972 | 94.5139 | 100 | 98.9919 | 94.5565 | 99.328 | 95.7661 | 91.0618 | 94.9306 | 88.4028 | 79.6528 | 89.1129 | 77.1505 | 69.2204 | 80.8333 | 72.2917 | 56.25 | 77.957 | 66.5995 | 49.0591
24 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3 | 4 | 2.0161 | 0 | 0 | 3.7279 | 0 | 0 | 3.5618 | 0 | 0 | 7.1528 | 2.9167 | 0 | 7.9301 | 4.4355 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.2661 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.4274 | 0 | 0 | 3.6111 | 0 | 0 | 3.8978 | 0 | 0
24 | 3 | 6 | 12.4328 | 4.7715 | 0 | 20.3305 | 9.0671 | 0.74405 | 19.086 | 10.3495 | 3.7634 | 29.5139 | 17.1528 | 10.9722 | 28.4274 | 23.4543 | 15.0538 | 36.5278 | 26.3194 | 16.0417 | 31.1156 | 24.5296 | 14.8522 | 33.2661 | 21.3038 | 12.5672 | 24.7222 | 15.2778 | 6.1111 | 13.9113 | 7.1237 | 1.8145 | 11.6667 | 4.9306 | 0 | 13.3737 | 4.7715 | 0
24 | 3 | 8 | 29.3011 | 15.793 | 6.0484 | 39.5833 | 26.3649 | 12.2768 | 40.6586 | 28.0242 | 16.7339 | 55.2778 | 45.8333 | 38.1944 | 61.0887 | 50 | 42.2043 | 66.25 | 55.1389 | 41.875 | 65.2554 | 55.2419 | 40.5914 | 59.0054 | 50.8737 | 40.5914 | 48.0556 | 37.0833 | 25.625 | 33.4005 | 24.664 | 13.0376 | 31.1111 | 18.0556 | 10 | 32.1909 | 18.2124 | 7.1237
24 | 3 | 9 | 37.4328 | 22.9839 | 10.3495 | 49.4792 | 39.8707 | 17.4107 | 49.664 | 40.5914 | 27.3522 | 67.9167 | 57.9861 | 49.6528 | 74.664 | 64.9866 | 55.7124 | 76.3194 | 68.5417 | 54.2361 | 81.7204 | 67.2043 | 57.3925 | 73.3871 | 63.7769 | 54.0323 | 61.8056 | 50.8333 | 36.3889 | 43.5484 | 33.0645 | 22.5806 | 39.2361 | 25.2778 | 16.0417 | 42.0027 | 25.1344 | 10.4839
24 | 3 | 10 | 49.0591 | 31.922 | 19.8925 | 59.865 | 46.7801 | 26.6369 | 64.1129 | 49.4624 | 38.7097 | 77.0139 | 70.2778 | 62.2917 | 81.7876 | 76.1425 | 69.086 | 86.3889 | 80.2083 | 68.5417 | 91.9355 | 79.6371 | 72.9839 | 82.5269 | 73.7231 | 67.6747 | 71.1806 | 59.7917 | 50.2083 | 54.3011 | 44.8253 | 32.5941 | 51.875 | 37.0139 | 21.1111 | 50.8737 | 33.3333 | 21.5726
24 | 3 | 11 | 58.4677 | 40.6586 | 27.5538 | 68.0804 | 57.384 | 31.8452 | 77.957 | 63.4409 | 49.0591 | 88.0556 | 80.1389 | 72.9167 | 89.9194 | 85.3495 | 78.7634 | 93.5417 | 90.0694 | 82.8472 | 96.8414 | 89.9194 | 81.7876 | 89.7849 | 84.8118 | 75 | 82.5694 | 68.4028 | 59.9306 | 67.2715 | 53.1586 | 41.8011 | 59.7222 | 48.8889 | 33.2639 | 58.9382 | 41.9355 | 28.6962
24 | 3 | 12 | 65.0538 | 49.0907 | 38.1048 | 78.6689 | 66.2946 | 43.8834 | 83.5349 | 70.6317 | 59.7446 | 91.9444 | 87.2222 | 81.9444 | 95.4973 | 90.9946 | 86.4247 | 96.875 | 93.2639 | 88.6806 | 99.1263 | 95.6317 | 88.5753 | 96.5726 | 90.457 | 82.5941 | 87.6389 | 78.0556 | 68.9583 | 74.5296 | 59.1398 | 50.336 | 68.4028 | 58.75 | 39.7917 | 64.5833 | 52.1505 | 35.5511
24 | 3 | 15 | 83.871 | 67.5403 | 51.1425 | 87.0767 | 79.9851 | 62.6488 | 94.422 | 83.0645 | 74.8656 | 98.4028 | 95.1389 | 90.4861 | 100 | 98.3871 | 95.9677 | 99.7917 | 97.7778 | 95.6944 | 100 | 99.9328 | 95.8333 | 99.664 | 97.9167 | 92.7419 | 96.1806 | 91.1111 | 84.1667 | 89.9194 | 78.1586 | 71.5726 | 84.8611 | 73.8194 | 59.3056 | 79.9731 | 68.75 | 53.4274
24 | 3 | 20 | 85.7527 | 69.6909 | 52.621 | 87.5154 | 81.3244 | 64.0805 | 96.1022 | 84.0726 | 76.8817 | 99.0278 | 95.2778 | 91.1111 | 100 | 99.1935 | 96.2366 | 99.8611 | 97.9861 | 95.7639 | 100 | 100 | 95.9005 | 99.7984 | 97.9167 | 93.2796 | 96.5278 | 91.8056 | 85.3472 | 92.4731 | 81.5188 | 73.1183 | 86.875 | 78.2639 | 64.2361 | 81.6532 | 71.3038 | 55.7796
24 | 3 | 25 | 85.7527 | 69.6909 | 52.621 | 87.5154 | 81.3244 | 64.0805 | 96.1022 | 84.0726 | 76.8817 | 99.0278 | 95.2778 | 91.1111 | 100 | 99.1935 | 96.2366 | 99.8611 | 97.9861 | 95.7639 | 100 | 100 | 95.9005 | 99.7984 | 97.9167 | 93.2796 | 96.5278 | 91.8056 | 85.3472 | 92.5403 | 81.5188 | 73.1183 | 86.875 | 78.2639 | 64.2361 | 81.6532 | 71.3038 | 55.7796
24 | 3.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3.25 | 4 | 2.0161 | 0 | 0 | 3.7279 | 0 | 0 | 3.5618 | 0 | 0 | 7.1528 | 2.9167 | 0 | 7.9301 | 4.4355 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.2661 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.4274 | 0 | 0 | 3.6111 | 0 | 0 | 3.8978 | 0 | 0
24 | 3.25 | 6 | 12.4328 | 4.7715 | 0 | 20.3305 | 9.0671 | 0.74405 | 19.086 | 10.3495 | 3.7634 | 29.5139 | 17.1528 | 10.9722 | 28.4274 | 23.4543 | 15.0538 | 36.5278 | 26.3194 | 16.0417 | 31.1156 | 24.5296 | 14.8522 | 33.2661 | 21.3038 | 12.5672 | 24.7222 | 15.2778 | 6.1111 | 13.9113 | 7.1237 | 1.8145 | 11.6667 | 4.9306 | 0 | 13.3737 | 4.7715 | 0
24 | 3.25 | 8 | 29.3011 | 15.8031 | 6.0484 | 39.5833 | 26.3649 | 12.2768 | 40.6586 | 28.0242 | 16.7339 | 55.2778 | 45.8333 | 38.1944 | 61.0887 | 50 | 42.2043 | 66.25 | 55.1389 | 41.875 | 65.2554 | 55.2419 | 40.5914 | 59.0054 | 50.8737 | 40.5914 | 48.0556 | 37.0833 | 25.625 | 33.4005 | 24.664 | 13.0376 | 31.1111 | 18.0556 | 10 | 32.1909 | 18.2124 | 7.1237
24 | 3.25 | 9 | 37.4328 | 23.4029 | 10.3495 | 49.4792 | 40.3736 | 17.4107 | 49.664 | 40.5914 | 27.3522 | 67.9167 | 57.9861 | 49.6528 | 74.664 | 64.9866 | 55.7124 | 76.3194 | 68.5417 | 54.2361 | 81.7204 | 67.2043 | 57.3925 | 73.3871 | 63.7769 | 54.0323 | 61.8056 | 50.8333 | 36.3889 | 43.5484 | 33.0645 | 22.5806 | 39.2361 | 25.2778 | 16.1111 | 42.0699 | 25.1344 | 10.6855
24 | 3.25 | 10 | 49.0591 | 31.922 | 19.8925 | 59.9394 | 46.7801 | 26.6369 | 64.1129 | 49.5968 | 38.7097 | 77.0139 | 70.3472 | 62.3611 | 81.7876 | 76.1425 | 69.086 | 86.3889 | 80.2083 | 68.5417 | 91.9355 | 79.6371 | 72.9839 | 82.5269 | 73.7231 | 67.6747 | 71.4583 | 59.7917 | 50.2083 | 54.3683 | 45.4973 | 32.8629 | 51.9444 | 37.1528 | 21.1806 | 50.9409 | 33.3333 | 21.6398
24 | 3.25 | 11 | 58.4677 | 40.6586 | 27.8226 | 70.9821 | 58.6438 | 33.631 | 78.0242 | 63.6425 | 49.2608 | 88.0556 | 80.2778 | 73.125 | 90.0538 | 85.4167 | 78.7634 | 93.6111 | 90.1389 | 82.9167 | 96.8414 | 89.9194 | 81.7876 | 89.7849 | 84.9462 | 75 | 82.5694 | 68.4722 | 60 | 67.2715 | 53.3602 | 43.2124 | 59.7222 | 49.7222 | 33.3333 | 59.0726 | 41.9355 | 28.7634
24 | 3.25 | 12 | 65.3898 | 49.7633 | 39.5833 | 79.6875 | 68.3036 | 45.9462 | 86.1559 | 70.7661 | 59.9462 | 92.0139 | 88.125 | 81.9444 | 95.6989 | 90.9946 | 86.4247 | 97.0139 | 93.4722 | 88.8194 | 99.1263 | 95.6317 | 88.6425 | 96.5726 | 90.5242 | 82.5941 | 87.9167 | 78.125 | 69.1667 | 74.5968 | 59.879 | 50.4704 | 69.375 | 59.2361 | 40.2083 | 66.129 | 52.5538 | 36.2903
24 | 3.25 | 15 | 85.3495 | 71.371 | 55.7796 | 89.7321 | 83.0357 | 66.2946 | 95.4973 | 86.0215 | 77.8226 | 98.9583 | 96.5972 | 94.0278 | 100 | 98.9919 | 97.4462 | 100 | 98.8889 | 96.25 | 100 | 100 | 96.4382 | 100 | 98.9919 | 94.5565 | 96.875 | 92.7778 | 86.3889 | 92.3387 | 80.914 | 72.5806 | 87.2917 | 78.9583 | 63.1944 | 82.5269 | 74.328 | 58.1317
24 | 3.25 | 20 | 87.6344 | 75.4704 | 59.6102 | 91.2946 | 85.3807 | 71.8109 | 97.5806 | 88.8441 | 80.7796 | 99.7917 | 97.4306 | 94.7222 | 100 | 99.9328 | 97.9167 | 100 | 99.1667 | 96.3889 | 100 | 100 | 96.7742 | 100 | 99.328 | 95.1613 | 97.8472 | 94.1667 | 89.2361 | 95.5645 | 86.2903 | 79.0995 | 92.1528 | 83.5417 | 69.7917 | 86.0887 | 78.0242 | 62.0968
24 | 3.25 | 25 | 87.6344 | 75.4704 | 59.6102 | 91.2946 | 85.3807 | 71.8109 | 97.5806 | 88.8441 | 80.7796 | 99.7917 | 97.4306 | 94.7222 | 100 | 99.9328 | 97.9167 | 100 | 99.1667 | 96.3889 | 100 | 100 | 96.7742 | 100 | 99.328 | 95.1613 | 97.9167 | 94.1667 | 89.2361 | 95.5645 | 86.2903 | 79.0995 | 92.1528 | 83.5417 | 69.7917 | 86.0887 | 78.0242 | 62.0968
24 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3.5 | 4 | 2.0161 | 0 | 0 | 3.7279 | 0 | 0 | 3.5618 | 0 | 0 | 7.1528 | 2.9167 | 0 | 7.9301 | 4.4355 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.2661 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.4274 | 0 | 0 | 3.6111 | 0 | 0 | 3.8978 | 0 | 0
24 | 3.5 | 6 | 12.4328 | 4.7715 | 0 | 20.3305 | 9.0671 | 0.74405 | 19.086 | 10.3495 | 3.7634 | 29.5139 | 17.1528 | 10.9722 | 28.4274 | 23.4543 | 15.0538 | 36.5278 | 26.3194 | 16.0417 | 31.1156 | 24.5296 | 14.8522 | 33.2661 | 21.3038 | 12.5672 | 24.7222 | 15.2778 | 6.1111 | 13.9113 | 7.1237 | 1.8145 | 11.6667 | 4.9306 | 0 | 13.3737 | 4.7715 | 0
24 | 3.5 | 8 | 29.3011 | 15.8031 | 6.0484 | 39.5833 | 26.3649 | 12.2768 | 40.6586 | 28.0242 | 16.7339 | 55.2778 | 45.8333 | 38.1944 | 61.0887 | 50 | 42.2043 | 66.25 | 55.1389 | 41.875 | 65.2554 | 55.2419 | 40.5914 | 59.0054 | 50.8737 | 40.5914 | 48.0556 | 37.0833 | 25.625 | 33.4005 | 24.664 | 13.0376 | 31.1111 | 18.0556 | 10 | 32.1909 | 18.2124 | 7.1237
24 | 3.5 | 9 | 37.4328 | 23.4029 | 10.3495 | 49.4792 | 40.5891 | 17.4107 | 49.664 | 40.5914 | 27.3522 | 67.9167 | 57.9861 | 49.6528 | 74.664 | 64.9866 | 56.1156 | 76.3194 | 68.5417 | 54.2361 | 81.7204 | 67.2043 | 57.3925 | 73.3871 | 63.7769 | 54.0323 | 61.8056 | 50.8333 | 36.3889 | 43.5484 | 33.0645 | 22.5806 | 39.2361 | 25.2778 | 16.1111 | 42.0699 | 25.1344 | 10.7527
24 | 3.5 | 10 | 49.0591 | 31.922 | 19.8925 | 59.9394 | 46.7801 | 26.7113 | 64.1129 | 49.664 | 38.7097 | 77.0139 | 70.4167 | 62.3611 | 81.7876 | 76.1425 | 69.2204 | 86.3889 | 80.2083 | 68.5417 | 91.9355 | 79.6371 | 72.9839 | 82.5269 | 73.7231 | 67.6747 | 71.4583 | 59.7917 | 50.2083 | 54.3683 | 45.9677 | 32.9301 | 51.9444 | 38.2639 | 21.1806 | 50.9409 | 33.3333 | 21.6398
24 | 3.5 | 11 | 58.5349 | 40.793 | 28.0242 | 71.7262 | 58.7054 | 33.7054 | 78.0242 | 63.7097 | 49.328 | 88.0556 | 80.4861 | 73.125 | 90.0538 | 85.8199 | 78.7634 | 93.6806 | 90.2083 | 82.9167 | 96.8414 | 89.9194 | 81.7876 | 89.7849 | 84.9462 | 75 | 82.5694 | 68.4722 | 60.0694 | 67.2715 | 53.4946 | 43.6828 | 59.7222 | 50 | 33.3333 | 59.2742 | 41.9355 | 28.7634
24 | 3.5 | 12 | 65.3898 | 49.9651 | 39.7177 | 79.6875 | 68.75 | 46.3106 | 86.3575 | 71.1022 | 60.6183 | 92.5 | 88.4028 | 82.0139 | 95.8333 | 91.4651 | 86.4247 | 97.0139 | 93.75 | 88.8889 | 99.1263 | 95.6317 | 88.7097 | 96.5726 | 91.0618 | 82.5941 | 87.9861 | 78.4028 | 69.8611 | 74.5968 | 59.9462 | 52.4194 | 69.7222 | 61.6667 | 40.4861 | 66.3306 | 53.3602 | 36.8952
24 | 3.5 | 15 | 87.5 | 72.1774 | 57.5941 | 90.4018 | 83.8542 | 68.75 | 97.1102 | 89.3145 | 79.3683 | 99.5833 | 97.3611 | 94.5139 | 100 | 99.4624 | 97.9167 | 100 | 99.1667 | 96.5972 | 100 | 100 | 97.5806 | 100 | 99.2608 | 95.6317 | 97.4306 | 94.3056 | 88.6806 | 93.1452 | 82.5269 | 76.8817 | 88.3333 | 81.3194 | 64.6528 | 85.0134 | 78.5618 | 59.0054
24 | 3.5 | 20 | 92.0027 | 79.7043 | 65.3226 | 94.3452 | 88.8932 | 76.6112 | 98.9247 | 93.078 | 83.0645 | 100 | 99.0972 | 95.4167 | 100 | 100 | 98.8575 | 100 | 99.5139 | 96.8056 | 100 | 100 | 98.0511 | 100 | 100 | 96.7742 | 98.8889 | 95.8333 | 92.0139 | 98.3871 | 88.5081 | 83.871 | 94.2361 | 86.8056 | 74.7917 | 88.8441 | 82.5269 | 68.2124
24 | 3.5 | 25 | 92.0027 | 79.7043 | 65.3226 | 94.3452 | 88.8932 | 76.6857 | 98.9247 | 93.078 | 83.0645 | 100 | 99.0972 | 95.4167 | 100 | 100 | 98.8575 | 100 | 99.5139 | 96.8056 | 100 | 100 | 98.0511 | 100 | 100 | 96.7742 | 98.8889 | 95.8333 | 92.0833 | 98.3871 | 88.8441 | 83.871 | 94.2361 | 86.8056 | 74.7917 | 88.8441 | 82.5269 | 68.2124
24 | 3.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3.75 | 4 | 2.0161 | 0 | 0 | 3.7279 | 0 | 0 | 3.5618 | 0 | 0 | 7.1528 | 2.9167 | 0 | 7.9301 | 4.4355 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.2661 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.4274 | 0 | 0 | 3.6111 | 0 | 0 | 3.8978 | 0 | 0
24 | 3.75 | 6 | 12.4328 | 4.7715 | 0 | 20.3305 | 9.0671 | 0.74405 | 19.086 | 10.3495 | 3.7634 | 29.5139 | 17.1528 | 10.9722 | 28.4274 | 23.4543 | 15.0538 | 36.5278 | 26.3194 | 16.0417 | 31.1156 | 24.5296 | 14.8522 | 33.2661 | 21.3038 | 12.5672 | 24.7222 | 15.2778 | 6.1111 | 13.9113 | 7.1237 | 1.8145 | 11.6667 | 4.9306 | 0 | 13.3737 | 4.7715 | 0
24 | 3.75 | 8 | 29.3011 | 15.8031 | 6.0484 | 39.5833 | 26.3649 | 12.2768 | 40.6586 | 28.0242 | 16.7339 | 55.2778 | 45.8333 | 38.1944 | 61.0887 | 50 | 42.2043 | 66.25 | 55.1389 | 41.875 | 65.2554 | 55.2419 | 40.5914 | 59.0054 | 50.8737 | 40.5914 | 48.0556 | 37.0833 | 25.625 | 33.4005 | 24.664 | 13.0376 | 31.1111 | 18.0556 | 10 | 32.1909 | 18.2124 | 7.1237
24 | 3.75 | 9 | 37.4328 | 23.4029 | 10.3495 | 49.4792 | 40.5891 | 17.4107 | 49.664 | 40.5914 | 27.3522 | 67.9167 | 57.9861 | 49.6528 | 74.664 | 64.9866 | 56.1156 | 76.3194 | 68.5417 | 54.2361 | 81.7204 | 67.2043 | 57.3925 | 73.3871 | 63.7769 | 54.0323 | 61.8056 | 50.8333 | 36.3889 | 43.5484 | 33.0645 | 22.5806 | 39.2361 | 25.2778 | 16.1111 | 42.0699 | 25.1344 | 10.7527
24 | 3.75 | 10 | 49.0591 | 31.922 | 19.8925 | 59.9394 | 46.8391 | 26.7113 | 64.1129 | 49.664 | 38.7097 | 77.0139 | 70.4167 | 62.3611 | 81.7876 | 76.1425 | 69.2204 | 86.3889 | 80.2083 | 68.5417 | 91.9355 | 79.6371 | 72.9839 | 82.5269 | 73.7231 | 67.6747 | 71.4583 | 59.7917 | 50.2083 | 54.3683 | 45.9677 | 32.9301 | 51.9444 | 38.2639 | 21.1806 | 50.9409 | 33.3333 | 21.6398
24 | 3.75 | 11 | 58.6022 | 40.8602 | 28.0914 | 71.7262 | 58.7054 | 33.7054 | 78.0242 | 63.8441 | 49.328 | 88.0556 | 80.625 | 73.125 | 90.0538 | 85.8199 | 78.7634 | 93.6806 | 90.2083 | 82.9167 | 96.8414 | 89.9194 | 81.7876 | 89.7849 | 84.9462 | 75 | 82.5694 | 68.4722 | 60.1389 | 67.2715 | 53.5618 | 43.75 | 59.7222 | 50.0694 | 33.3333 | 59.4758 | 41.9355 | 28.7634
24 | 3.75 | 12 | 65.457 | 51.7147 | 41.2634 | 79.6875 | 68.75 | 46.5979 | 86.3575 | 71.1022 | 60.6183 | 92.5 | 88.4028 | 82.0833 | 95.9005 | 91.4651 | 86.4247 | 97.0139 | 93.8194 | 88.8889 | 99.1263 | 95.6317 | 88.7097 | 96.5726 | 91.0618 | 82.5941 | 87.9861 | 78.4722 | 69.9306 | 74.5968 | 60.0134 | 52.621 | 70.1389 | 61.6667 | 40.6944 | 66.3306 | 53.4274 | 36.8952
24 | 3.75 | 15 | 87.7688 | 72.5806 | 58.6694 | 91.0714 | 85.2986 | 71.2772 | 97.2446 | 90.9274 | 80.1075 | 99.7917 | 97.7778 | 94.7222 | 100 | 99.7312 | 98.3871 | 100 | 99.3056 | 97.4306 | 100 | 100 | 97.8495 | 100 | 99.4624 | 96.1022 | 98.125 | 94.7222 | 89.5833 | 93.2124 | 84.7446 | 78.0242 | 89.5139 | 82.0139 | 70.9722 | 86.2903 | 78.9651 | 63.5753
24 | 3.75 | 20 | 93.2796 | 84.8118 | 72.7151 | 96.5774 | 91.6667 | 82.8972 | 99.5296 | 95.6317 | 86.7608 | 100 | 99.4444 | 96.3889 | 100 | 100 | 99.5968 | 100 | 100 | 97.8472 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.2222 | 93.8889 | 99.1263 | 91.3306 | 87.3656 | 95.9028 | 90.0694 | 80.4861 | 92.4731 | 84.6774 | 71.1694
24 | 3.75 | 25 | 93.2796 | 84.8118 | 72.7151 | 96.5774 | 91.6667 | 82.8972 | 99.5296 | 95.6317 | 86.7608 | 100 | 99.5139 | 96.3889 | 100 | 100 | 99.5968 | 100 | 100 | 97.8472 | 100 | 100 | 98.7903 | 100 | 100 | 98.5887 | 99.6528 | 97.2222 | 93.8889 | 99.1935 | 91.3306 | 87.9704 | 95.9028 | 90.0694 | 80.4861 | 92.4731 | 84.6774 | 71.3038
24 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 4 | 4 | 2.0161 | 0 | 0 | 3.7279 | 0 | 0 | 3.5618 | 0 | 0 | 7.1528 | 2.9167 | 0 | 7.9301 | 4.4355 | 0 | 13.2639 | 4.5139 | 0 | 8.4677 | 3.629 | 0 | 8.2661 | 3.629 | 0 | 4.6528 | 0 | 0 | 3.4274 | 0 | 0 | 3.6111 | 0 | 0 | 3.8978 | 0 | 0
24 | 4 | 6 | 12.4328 | 4.7715 | 0 | 20.3305 | 9.0671 | 0.74405 | 19.086 | 10.3495 | 3.7634 | 29.5139 | 17.1528 | 10.9722 | 28.4274 | 23.4543 | 15.0538 | 36.5278 | 26.3194 | 16.0417 | 31.1156 | 24.5296 | 14.8522 | 33.2661 | 21.3038 | 12.5672 | 24.7222 | 15.2778 | 6.1111 | 13.9113 | 7.1237 | 1.8145 | 11.6667 | 4.9306 | 0 | 13.3737 | 4.7715 | 0
24 | 4 | 8 | 29.3011 | 15.8031 | 6.0484 | 39.5833 | 26.3649 | 12.2768 | 40.6586 | 28.0242 | 16.7339 | 55.2778 | 45.8333 | 38.1944 | 61.0887 | 50 | 42.2043 | 66.25 | 55.1389 | 41.875 | 65.2554 | 55.2419 | 40.5914 | 59.0054 | 50.8737 | 40.5914 | 48.0556 | 37.0833 | 25.625 | 33.4005 | 24.664 | 13.0376 | 31.1111 | 18.0556 | 10 | 32.1909 | 18.2124 | 7.1237
24 | 4 | 9 | 37.4328 | 23.4029 | 10.3495 | 49.4792 | 40.5891 | 17.4107 | 49.664 | 40.5914 | 27.3522 | 67.9167 | 57.9861 | 49.6528 | 74.664 | 64.9866 | 56.1156 | 76.3194 | 68.5417 | 54.2361 | 81.7204 | 67.2043 | 57.3925 | 73.3871 | 63.7769 | 54.0323 | 61.8056 | 50.8333 | 36.3889 | 43.5484 | 33.0645 | 22.5806 | 39.2361 | 25.2778 | 16.1111 | 42.0699 | 25.1344 | 10.7527
24 | 4 | 10 | 49.0591 | 31.922 | 19.8925 | 59.9394 | 46.9109 | 26.7113 | 64.1129 | 49.664 | 38.7097 | 77.0139 | 70.4167 | 62.3611 | 81.7876 | 76.1425 | 69.2204 | 86.3889 | 80.2083 | 68.5417 | 91.9355 | 79.6371 | 72.9839 | 82.5269 | 73.7231 | 67.6747 | 71.4583 | 59.7917 | 50.2083 | 54.3683 | 45.9677 | 32.9301 | 51.9444 | 38.2639 | 21.1806 | 50.9409 | 33.3333 | 21.6398
24 | 4 | 11 | 58.6022 | 40.8602 | 28.0914 | 71.7262 | 58.7054 | 33.7054 | 78.0242 | 63.8441 | 49.328 | 88.0556 | 80.625 | 73.125 | 90.0538 | 85.8199 | 78.7634 | 93.6806 | 90.2083 | 82.9167 | 96.8414 | 89.9194 | 81.7876 | 89.7849 | 84.9462 | 75 | 82.5694 | 68.4722 | 60.2083 | 67.2715 | 53.5618 | 43.75 | 59.7222 | 50.0694 | 33.3333 | 59.6102 | 41.9355 | 28.7634
24 | 4 | 12 | 65.457 | 51.9838 | 41.5995 | 79.6875 | 68.75 | 46.875 | 86.3575 | 71.1022 | 60.6183 | 92.5 | 88.4028 | 82.0833 | 95.9005 | 91.4651 | 86.4247 | 97.0139 | 93.8194 | 88.8889 | 99.1263 | 95.6317 | 88.7097 | 96.5726 | 91.0618 | 82.5941 | 87.9861 | 78.4722 | 70 | 74.5968 | 60.0134 | 52.7554 | 70.1389 | 61.8056 | 40.6944 | 66.3306 | 53.4274 | 36.8952
24 | 4 | 15 | 88.0376 | 74.1263 | 63.7097 | 91.4435 | 85.7887 | 72.4343 | 97.5806 | 91.3978 | 80.7124 | 99.7917 | 98.0556 | 95.1389 | 100 | 99.7984 | 98.3871 | 100 | 99.3056 | 97.5694 | 100 | 100 | 98.0511 | 100 | 99.5296 | 96.5054 | 98.6111 | 94.9306 | 89.8611 | 93.2124 | 84.9462 | 78.4946 | 90.4167 | 82.9861 | 72.2917 | 86.4247 | 79.5699 | 65.3226
24 | 4 | 20 | 94.6909 | 88.7097 | 75.8579 | 97.9911 | 92.7083 | 87.2024 | 99.9328 | 97.043 | 89.1129 | 100 | 99.7917 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.4722 | 95.4861 | 99.7984 | 93.9516 | 89.9194 | 97.8472 | 93.125 | 83.3333 | 94.6909 | 87.6344 | 80.0403
24 | 4 | 25 | 94.7581 | 88.7097 | 75.8579 | 97.9911 | 92.7083 | 87.2742 | 99.9328 | 97.1102 | 89.1129 | 100 | 99.8611 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.6806 | 95.8333 | 99.9328 | 94.0188 | 90.0538 | 97.8472 | 93.2639 | 83.3333 | 94.6909 | 87.6344 | 80.1747
48 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8629 | 0 | 0 | 10.3472 | 0 | 0 | 9.0726 | 0 | 0 | 8.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7361 | 0 | 0 | 9.6102 | 0 | 0 | 11.1806 | 1.0417 | 0 | 11.0215 | 1.4785 | 0 | 9.4086 | 0 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7361 | 0 | 0 | 9.6102 | 0 | 0 | 11.1806 | 1.0417 | 0 | 11.0215 | 1.4785 | 0 | 9.4086 | 0 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7361 | 0 | 0 | 9.6102 | 0 | 0 | 11.1806 | 1.0417 | 0 | 11.0215 | 1.4785 | 0 | 9.4086 | 0 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7361 | 0 | 0 | 9.6102 | 0 | 0 | 11.1806 | 1.0417 | 0 | 11.0215 | 1.4785 | 0 | 9.4086 | 0 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7361 | 0 | 0 | 9.6102 | 0 | 0 | 11.1806 | 1.0417 | 0 | 11.0215 | 1.4785 | 0 | 9.4086 | 0 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7361 | 0 | 0 | 9.6102 | 0 | 0 | 11.1806 | 1.0417 | 0 | 11.0215 | 1.4785 | 0 | 9.4086 | 0 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7361 | 0 | 0 | 9.6102 | 0 | 0 | 11.1806 | 1.0417 | 0 | 11.0215 | 1.4785 | 0 | 9.4086 | 0 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7361 | 0 | 0 | 9.6102 | 0 | 0 | 11.1806 | 1.0417 | 0 | 11.0215 | 1.4785 | 0 | 9.4086 | 0 | 0 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.75 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.75 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0694 | 1.5278 | 0 | 14.1129 | 8.1317 | 0 | 14.7917 | 8.0556 | 0 | 16.3978 | 6.6532 | 0 | 13.8441 | 6.9892 | 0 | 7.6389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.75 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1317 | 0 | 0 | 21.3194 | 9.7222 | 0 | 22.4462 | 13.7097 | 7.1909 | 29.0278 | 17.2917 | 4.3056 | 30.9812 | 14.6505 | 7.3925 | 29.7715 | 14.1801 | 6.8548 | 15.3472 | 6.875 | 0 | 7.1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.75 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 23.6111 | 10.2778 | 0 | 23.4543 | 15.1882 | 8.2661 | 30.9028 | 18.6806 | 6.8056 | 31.3172 | 17.8091 | 9.4086 | 30.7796 | 15.121 | 7.0565 | 15.3472 | 7.2917 | 0 | 7.1909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.75 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 23.6111 | 10.2778 | 0 | 23.4543 | 15.1882 | 8.2661 | 30.9028 | 18.6806 | 6.8056 | 31.3172 | 17.8091 | 9.4086 | 30.7796 | 15.793 | 7.0565 | 15.3472 | 7.2917 | 0 | 7.1909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.75 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 23.6111 | 10.2778 | 0 | 23.4543 | 15.1882 | 8.2661 | 30.9028 | 18.6806 | 6.8056 | 31.3172 | 17.8091 | 9.4086 | 30.7796 | 15.793 | 7.0565 | 15.3472 | 7.2917 | 0 | 7.1909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.75 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 23.6111 | 10.2778 | 0 | 23.4543 | 15.1882 | 8.2661 | 30.9028 | 18.6806 | 6.8056 | 31.3172 | 17.8091 | 9.4086 | 30.7796 | 15.793 | 7.0565 | 15.3472 | 7.2917 | 0 | 7.1909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.75 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 23.6111 | 10.2778 | 0 | 23.4543 | 15.1882 | 8.2661 | 30.9028 | 18.6806 | 6.8056 | 31.3172 | 17.8091 | 9.4086 | 30.7796 | 15.793 | 7.0565 | 15.3472 | 7.2917 | 0 | 7.1909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.75 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 23.6111 | 10.2778 | 0 | 23.4543 | 15.1882 | 8.2661 | 30.9028 | 18.6806 | 6.8056 | 31.3172 | 17.8091 | 9.4086 | 30.7796 | 15.793 | 7.0565 | 15.3472 | 7.2917 | 0 | 7.1909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0.75 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 23.6111 | 10.2778 | 0 | 23.4543 | 15.1882 | 8.2661 | 30.9028 | 18.6806 | 6.8056 | 31.3172 | 17.8091 | 9.4086 | 30.7796 | 15.793 | 7.0565 | 15.3472 | 7.2917 | 0 | 7.1909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1 | 6 | 0 | 0 | 0 | 7.9741 | 0 | 0 | 7.9301 | 0 | 0 | 14.7222 | 7.3611 | 0 | 15.9946 | 9.0054 | 0 | 19.3056 | 9.8611 | 0 | 17.4059 | 8.3333 | 0 | 18.6156 | 8.1317 | 0 | 14.1667 | 0 | 0 | 4.9731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1 | 8 | 10.9543 | 0 | 0 | 14.5346 | 0.59524 | 0 | 20.8333 | 5.9812 | 0 | 29.2361 | 15.7639 | 7.2222 | 33.7366 | 23.3199 | 14.4489 | 40.7639 | 28.5417 | 15.2083 | 47.1102 | 28.5618 | 14.6505 | 44.086 | 25.0672 | 14.1801 | 27.4306 | 14.7917 | 7.2222 | 10.4167 | 0 | 0 | 7.3611 | 0 | 0 | 9.1398 | 0 | 0
48 | 1 | 9 | 11.0215 | 0 | 0 | 15.4018 | 3.1814 | 0 | 21.5726 | 7.3925 | 0 | 36.0417 | 22.9167 | 10.0694 | 39.6505 | 31.0484 | 17.8091 | 45.4167 | 35.1389 | 24.0972 | 51.8817 | 31.922 | 21.2366 | 50.672 | 31.6532 | 21.8414 | 33.6806 | 18.6806 | 7.8472 | 12.5 | 5.8468 | 0 | 7.5 | 0 | 0 | 9.207 | 0 | 0
48 | 1 | 10 | 11.0215 | 0 | 0 | 15.4018 | 3.1814 | 0 | 21.5726 | 8.9382 | 0 | 36.6667 | 22.9861 | 10.0694 | 40.3898 | 32.0565 | 19.6909 | 49.3056 | 35.3472 | 25.9028 | 54.3683 | 36.6263 | 23.9247 | 51.6129 | 34.0726 | 24.328 | 34.1667 | 20.9722 | 7.8472 | 12.5 | 5.914 | 0 | 7.5694 | 0 | 0 | 9.207 | 0 | 0
48 | 1 | 11 | 11.0215 | 0 | 0 | 15.4018 | 3.1814 | 0 | 21.5726 | 8.9382 | 0 | 36.7361 | 22.9861 | 10.0694 | 40.5242 | 32.0565 | 19.6909 | 49.3056 | 35.3472 | 25.9722 | 54.3683 | 36.6263 | 24.7312 | 51.6129 | 34.0726 | 24.328 | 34.2361 | 20.9722 | 7.8472 | 12.5 | 5.914 | 0 | 7.5694 | 0 | 0 | 9.207 | 0.33602 | 0
48 | 1 | 12 | 11.0215 | 0 | 0 | 15.4018 | 3.1814 | 0 | 21.5726 | 8.9382 | 0 | 36.7361 | 22.9861 | 10.0694 | 40.5242 | 32.0565 | 19.6909 | 49.3056 | 35.3472 | 25.9722 | 54.3683 | 36.6263 | 24.7312 | 51.6129 | 34.0726 | 24.328 | 34.2361 | 20.9722 | 7.8472 | 12.5 | 5.914 | 0 | 7.5694 | 0 | 0 | 9.207 | 0.33602 | 0
48 | 1 | 15 | 11.0215 | 0 | 0 | 15.4018 | 3.1814 | 0 | 21.5726 | 8.9382 | 0 | 36.7361 | 22.9861 | 10.0694 | 40.5242 | 32.0565 | 19.6909 | 50.9028 | 35.3472 | 25.9722 | 54.3683 | 36.6263 | 24.7312 | 51.6129 | 34.0726 | 24.328 | 34.2361 | 20.9722 | 7.8472 | 12.5 | 5.914 | 0 | 7.5694 | 0 | 0 | 9.207 | 0.33602 | 0
48 | 1 | 20 | 11.0215 | 0 | 0 | 15.4018 | 3.1814 | 0 | 21.5726 | 8.9382 | 0 | 36.7361 | 22.9861 | 10.0694 | 40.5242 | 32.0565 | 19.6909 | 50.9028 | 35.3472 | 25.9722 | 54.3683 | 36.6263 | 24.7312 | 51.6129 | 34.0726 | 24.328 | 34.2361 | 20.9722 | 7.8472 | 12.5 | 5.914 | 0 | 7.5694 | 0 | 0 | 9.207 | 0.33602 | 0
48 | 1 | 25 | 11.0215 | 0 | 0 | 15.4018 | 3.1814 | 0 | 21.5726 | 8.9382 | 0 | 36.7361 | 22.9861 | 10.0694 | 40.5242 | 32.0565 | 19.6909 | 50.9028 | 35.3472 | 25.9722 | 54.3683 | 36.6263 | 24.7312 | 51.6129 | 34.0726 | 24.328 | 34.2361 | 20.9722 | 7.8472 | 12.5 | 5.914 | 0 | 7.5694 | 0 | 0 | 9.207 | 0.33602 | 0
48 | 1.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1.25 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1.25 | 6 | 1.9489 | 0 | 0 | 9.4494 | 0 | 0 | 7.9973 | 0 | 0 | 15.2083 | 7.7083 | 0 | 18.0108 | 9.543 | 0 | 22.3611 | 14.0972 | 2.4306 | 17.7419 | 9.4086 | 0 | 20.0269 | 8.8038 | 0 | 15 | 0 | 0 | 4.9731 | 0 | 0 | 4.2361 | 0 | 0 | 6.8548 | 0 | 0
48 | 1.25 | 8 | 16.1962 | 4.3011 | 0 | 17.9777 | 9.6495 | 0 | 25.8065 | 10.6183 | 0 | 33.6111 | 19.5833 | 11.8056 | 40.9274 | 32.0565 | 19.6237 | 47.0139 | 37.4306 | 18.6111 | 50 | 33.2661 | 19.7581 | 47.9167 | 30.0403 | 19.7581 | 32.8472 | 21.875 | 12.5694 | 17.0027 | 7.7957 | 0 | 10.3472 | 7.0139 | 0 | 16.3306 | 6.9892 | 0
48 | 1.25 | 9 | 18.414 | 7.1237 | 0 | 25.4464 | 11.7739 | 0 | 28.9651 | 17.3387 | 0 | 45.7639 | 29.8611 | 22.5694 | 51.0081 | 40.457 | 31.0484 | 59.5833 | 47.0833 | 31.1806 | 62.6344 | 47.3118 | 35.9543 | 60.8871 | 43.078 | 34.0726 | 40.0694 | 27.2917 | 16.5278 | 22.4462 | 11.8952 | 6.6532 | 14.3056 | 7.9167 | 0 | 18.078 | 8.7366 | 0
48 | 1.25 | 10 | 19.0188 | 7.1909 | 0 | 25.9673 | 14.2113 | 1.7113 | 32.1237 | 20.9005 | 7.8629 | 52.9167 | 38.4028 | 27.5694 | 60.8199 | 49.1935 | 37.4328 | 64.1667 | 53.0556 | 36.4583 | 74.3952 | 55.578 | 40.793 | 68.078 | 49.2608 | 38.9113 | 45.3472 | 31.3889 | 19.1667 | 24.5968 | 13.9785 | 7.1909 | 15.0694 | 8.3333 | 0 | 18.1452 | 9.2742 | 0
48 | 1.25 | 11 | 19.0188 | 7.1909 | 0 | 25.9673 | 15.5506 | 1.7113 | 35.6855 | 22.043 | 7.8629 | 53.2639 | 40.1389 | 27.6389 | 63.172 | 49.5296 | 39.3817 | 64.7222 | 53.1944 | 39.1667 | 75.7392 | 58.1317 | 45.0269 | 68.6156 | 54.2339 | 39.9194 | 46.9444 | 32.7778 | 20.0694 | 26.2769 | 15.3226 | 7.2581 | 15.1389 | 8.4028 | 0 | 18.1452 | 9.2742 | 0
48 | 1.25 | 12 | 19.0188 | 7.1909 | 0 | 25.9673 | 15.5506 | 1.7113 | 35.6855 | 22.1102 | 7.8629 | 53.2639 | 40.1389 | 28.8889 | 64.3817 | 50.4032 | 39.8522 | 64.7222 | 53.1944 | 39.3056 | 75.7392 | 58.1317 | 45.0941 | 69.6909 | 54.2339 | 39.9194 | 46.9444 | 32.7778 | 20.0694 | 26.2769 | 15.3226 | 7.2581 | 15.1389 | 8.4028 | 0 | 18.1452 | 9.2742 | 0
48 | 1.25 | 15 | 19.0188 | 7.1909 | 0 | 25.9673 | 15.5506 | 1.7113 | 35.6855 | 22.1102 | 7.8629 | 53.2639 | 40.1389 | 28.8889 | 64.4489 | 50.4032 | 39.8522 | 64.7222 | 53.1944 | 39.375 | 75.7392 | 58.1317 | 45.0941 | 69.6909 | 54.3011 | 39.9194 | 46.9444 | 32.7778 | 20.0694 | 26.2769 | 15.3226 | 7.2581 | 15.1389 | 8.4028 | 0 | 18.1452 | 9.2742 | 0
48 | 1.25 | 20 | 19.0188 | 7.1909 | 0 | 25.9673 | 15.5506 | 1.7113 | 35.6855 | 22.1102 | 7.8629 | 53.2639 | 40.1389 | 28.8889 | 64.4489 | 50.4032 | 39.8522 | 64.7222 | 53.1944 | 39.375 | 75.7392 | 58.1317 | 45.0941 | 69.6909 | 54.3011 | 39.9194 | 46.9444 | 32.7778 | 20.0694 | 26.2769 | 15.3226 | 7.2581 | 15.1389 | 8.4028 | 0 | 18.1452 | 9.2742 | 0
48 | 1.25 | 25 | 19.0188 | 7.1909 | 0 | 25.9673 | 15.5506 | 1.7113 | 35.6855 | 22.1102 | 7.8629 | 53.2639 | 40.1389 | 28.8889 | 64.4489 | 50.4032 | 39.8522 | 64.7222 | 53.1944 | 39.375 | 75.7392 | 58.1317 | 45.0941 | 69.6909 | 54.3011 | 39.9194 | 46.9444 | 32.7778 | 20.0694 | 26.2769 | 15.3226 | 7.2581 | 15.1389 | 8.4028 | 0 | 18.1452 | 9.2742 | 0
48 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1.5 | 6 | 4.6371 | 0 | 0 | 9.5982 | 0 | 0 | 7.9973 | 0 | 0 | 15.8333 | 7.7778 | 0 | 18.75 | 9.9462 | 0 | 22.5694 | 14.0972 | 4.7917 | 18.1452 | 9.4086 | 0 | 21.371 | 8.8038 | 0 | 15.3472 | 0 | 0 | 6.922 | 0 | 0 | 6.6667 | 0 | 0 | 7.1909 | 0 | 0
48 | 1.5 | 8 | 18.2124 | 6.922 | 0 | 20.6897 | 11.4583 | 0 | 27.0161 | 14.1129 | 0 | 38.75 | 27.5 | 13.75 | 44.086 | 34.2742 | 22.1102 | 51.5972 | 43.5417 | 25.4167 | 51.6129 | 35.0134 | 22.5806 | 49.664 | 33.1317 | 21.5726 | 34.375 | 25.0694 | 13.75 | 19.4892 | 7.9973 | 0 | 12.0139 | 7.8472 | 0 | 17.6075 | 8.5349 | 0
48 | 1.5 | 9 | 22.9167 | 8.6022 | 0 | 31.5733 | 17.6981 | 4.5182 | 33.3333 | 22.5134 | 7.4597 | 53.5417 | 41.3889 | 27.1528 | 59.7446 | 48.7903 | 36.2231 | 66.1111 | 56.7361 | 36.3889 | 66.3306 | 51.1425 | 40.0538 | 66.129 | 50.8737 | 39.1129 | 45.2083 | 35.0694 | 20.8333 | 24.5296 | 15.7258 | 7.8629 | 18.2639 | 9.4444 | 0 | 26.7473 | 10.6183 | 0
48 | 1.5 | 10 | 29.1667 | 12.6344 | 0 | 36.6815 | 22.0135 | 6.7708 | 40.2554 | 28.629 | 12.0296 | 69.5833 | 48.2639 | 38.3333 | 71.4382 | 58.1989 | 46.7742 | 76.3194 | 63.0556 | 51.5278 | 81.3844 | 65.2554 | 50.5376 | 72.9167 | 58.9382 | 44.6237 | 53.6111 | 42.2222 | 27.2917 | 31.586 | 18.8172 | 10.4167 | 25.4167 | 12.7083 | 3.4028 | 30.2419 | 13.6425 | 1.7473
48 | 1.5 | 11 | 30.3091 | 15.9274 | 0 | 40.7841 | 22.2368 | 9.3006 | 44.422 | 33.3333 | 17.0027 | 71.0417 | 54.3056 | 40 | 75.2688 | 61.4247 | 53.3602 | 79.4444 | 65.4167 | 54.6528 | 86.2903 | 71.371 | 56.25 | 74.5296 | 65.3226 | 52.2177 | 57.0139 | 44.9306 | 31.4583 | 31.9892 | 25.8737 | 14.1801 | 26.9444 | 13.8889 | 7.7778 | 30.3763 | 14.5161 | 4.9731
48 | 1.5 | 12 | 30.3091 | 15.9946 | 0 | 41.2279 | 23.0655 | 9.3006 | 44.6237 | 33.6022 | 17.4059 | 71.6667 | 54.7222 | 42.2917 | 78.2258 | 65.2554 | 56.1828 | 80.0694 | 69.4444 | 55.5556 | 87.2984 | 74.9328 | 57.0565 | 77.957 | 65.457 | 53.6962 | 57.7083 | 50.7639 | 33.2639 | 34.207 | 26.6129 | 14.3817 | 27.0139 | 15.625 | 7.7778 | 30.3763 | 14.5833 | 4.9731
48 | 1.5 | 15 | 30.3091 | 15.9946 | 0 | 41.2279 | 23.1399 | 9.3006 | 44.6909 | 33.6022 | 17.4059 | 71.7361 | 54.7917 | 42.2917 | 78.3602 | 65.2554 | 56.3172 | 80.1389 | 69.6528 | 55.7639 | 87.3656 | 75.4032 | 57.0565 | 77.957 | 65.5242 | 53.8306 | 57.7778 | 50.7639 | 33.3333 | 34.207 | 26.6801 | 14.5161 | 27.1528 | 15.625 | 7.7778 | 30.3763 | 14.5833 | 4.9731
48 | 1.5 | 20 | 30.3091 | 15.9946 | 0 | 41.2279 | 23.1399 | 9.3006 | 44.6909 | 33.6022 | 17.4059 | 71.7361 | 54.7917 | 42.2917 | 78.3602 | 65.2554 | 56.3172 | 80.1389 | 69.6528 | 55.7639 | 87.3656 | 75.4032 | 57.0565 | 77.957 | 65.5242 | 53.8306 | 57.7778 | 50.7639 | 33.3333 | 34.207 | 26.6801 | 14.5161 | 27.1528 | 15.625 | 7.7778 | 30.3763 | 14.5833 | 4.9731
48 | 1.5 | 25 | 30.3091 | 15.9946 | 0 | 41.2279 | 23.1399 | 9.3006 | 44.6909 | 33.6022 | 17.4059 | 71.7361 | 54.7917 | 42.2917 | 78.3602 | 65.2554 | 56.3172 | 80.1389 | 69.6528 | 55.7639 | 87.3656 | 75.4032 | 57.0565 | 77.957 | 65.5242 | 53.8306 | 57.7778 | 50.7639 | 33.3333 | 34.207 | 26.6801 | 14.5161 | 27.1528 | 15.625 | 7.7778 | 30.3763 | 14.5833 | 4.9731
48 | 1.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1.75 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1.75 | 6 | 6.7204 | 0 | 0 | 9.5982 | 0 | 0 | 8.1317 | 0 | 0 | 16.3194 | 8.4722 | 0 | 18.75 | 10.6183 | 5.1075 | 22.5694 | 14.0972 | 4.7917 | 18.1452 | 9.4086 | 0 | 21.371 | 8.8038 | 0 | 15.3472 | 0 | 0 | 7.1237 | 0 | 0 | 6.875 | 0 | 0 | 7.5941 | 0 | 0
48 | 1.75 | 8 | 18.2796 | 7.7285 | 0 | 21.1207 | 12.7976 | 0 | 28.3602 | 14.4489 | 1.1425 | 39.0972 | 28.0556 | 18.6111 | 45.3629 | 35.9543 | 23.0511 | 54.7222 | 44.2361 | 25.9722 | 52.2177 | 39.1801 | 22.5806 | 50.4032 | 35.0134 | 22.2446 | 35.7639 | 25.6944 | 13.8889 | 19.6237 | 8.871 | 3.2258 | 14.8611 | 8.1944 | 0 | 20.5645 | 9.8118 | 0
48 | 1.75 | 9 | 25.2016 | 9.9462 | 0 | 34.9369 | 20.3022 | 6.3988 | 36.2231 | 23.6559 | 8.5349 | 56.25 | 43.8194 | 29.6528 | 60.8199 | 51.3441 | 39.5161 | 68.75 | 59.375 | 42.4306 | 68.1452 | 56.7204 | 42.8763 | 66.5995 | 56.3844 | 42.3387 | 47.4306 | 37.8472 | 22.2222 | 25.4032 | 17.0699 | 8.1989 | 25.4861 | 11.3194 | 0.069444 | 28.9651 | 14.1801 | 0
48 | 1.75 | 10 | 33.6694 | 17.1486 | 0 | 41.7436 | 27.753 | 8.1845 | 48.3871 | 33.3333 | 20.7661 | 72.9167 | 52.3611 | 44.4444 | 74.3952 | 62.6344 | 54.7715 | 80.3472 | 69.6528 | 55.3472 | 87.2984 | 71.0349 | 55.7124 | 74.7984 | 65.7258 | 50.1344 | 60.0694 | 46.5278 | 30 | 33.6694 | 24.8656 | 13.2392 | 29.375 | 18.2639 | 8.8194 | 35.5511 | 18.6156 | 7.1909
48 | 1.75 | 11 | 36.6263 | 21.1022 | 2.7554 | 49.7024 | 34.8958 | 13.0927 | 54.8387 | 40.0538 | 25.8737 | 74.8611 | 62.5694 | 49.1667 | 81.7876 | 68.9516 | 64.7849 | 82.8472 | 79.5833 | 65.4167 | 91.8011 | 83.4677 | 68.078 | 80.914 | 72.6478 | 61.6935 | 68.75 | 52.9167 | 40.3472 | 42.6747 | 33.0645 | 20.9677 | 36.9444 | 22.0139 | 11.4583 | 38.3065 | 19.8253 | 8.0645
48 | 1.75 | 12 | 38.9785 | 24.7984 | 2.8226 | 51.1802 | 39.0625 | 14.0625 | 57.6613 | 42.0027 | 28.8978 | 76.0417 | 64.6528 | 55.3472 | 85.7527 | 77.621 | 68.1452 | 85.4167 | 81.25 | 69.4444 | 93.414 | 84.9462 | 70.7661 | 82.7957 | 76.0753 | 64.5833 | 72.7778 | 59.5139 | 44.8611 | 45.9677 | 35.2151 | 21.4382 | 37.2917 | 26.6667 | 11.5278 | 41.0618 | 22.9167 | 9.2742
48 | 1.75 | 15 | 39.5161 | 24.8656 | 6.0484 | 51.4137 | 39.0625 | 14.1369 | 57.9973 | 46.5054 | 29.2339 | 76.875 | 65.625 | 55.5556 | 86.6263 | 79.4355 | 69.086 | 85.625 | 81.3194 | 70.0694 | 93.9516 | 85.9543 | 75.4032 | 82.9973 | 76.7473 | 66.3978 | 73.125 | 59.8611 | 45.1389 | 46.4382 | 36.5591 | 22.3118 | 38.9583 | 26.875 | 11.5278 | 41.129 | 23.0511 | 9.4086
48 | 1.75 | 20 | 39.5161 | 24.8656 | 6.0484 | 51.4137 | 39.0625 | 14.1369 | 57.9973 | 46.5054 | 29.2339 | 76.875 | 65.625 | 55.5556 | 86.6263 | 79.4355 | 69.086 | 85.625 | 81.3194 | 70.0694 | 93.9516 | 85.9543 | 75.4032 | 82.9973 | 76.7473 | 66.3978 | 73.125 | 59.8611 | 45.1389 | 46.4382 | 36.5591 | 22.3118 | 38.9583 | 26.875 | 11.5278 | 41.129 | 23.0511 | 9.4086
48 | 1.75 | 25 | 39.5161 | 24.8656 | 6.0484 | 51.4137 | 39.0625 | 14.1369 | 57.9973 | 46.5054 | 29.2339 | 76.875 | 65.625 | 55.5556 | 86.6263 | 79.4355 | 69.086 | 85.625 | 81.3194 | 70.0694 | 93.9516 | 85.9543 | 75.4032 | 82.9973 | 76.7473 | 66.3978 | 73.125 | 59.8611 | 45.1389 | 46.4382 | 36.5591 | 22.3118 | 38.9583 | 26.875 | 11.5278 | 41.129 | 23.0511 | 9.4086
48 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 2 | 6 | 6.7204 | 0 | 0 | 9.5982 | 0 | 0 | 8.4005 | 0 | 0 | 16.3194 | 8.4722 | 0 | 18.75 | 11.1559 | 5.1075 | 22.5694 | 14.0972 | 4.7917 | 18.1452 | 9.4086 | 0 | 21.371 | 8.8038 | 0 | 15.3472 | 0 | 0 | 7.1237 | 0 | 0 | 6.875 | 0 | 0 | 7.5941 | 0 | 0
48 | 2 | 8 | 18.2796 | 9.0726 | 0 | 22.0058 | 13.1696 | 0 | 29.0995 | 14.5833 | 1.1425 | 42.2222 | 28.4722 | 18.6111 | 46.2366 | 35.9543 | 24.1935 | 54.8611 | 44.2361 | 26.1806 | 52.2849 | 39.1801 | 22.5806 | 50.672 | 35.0134 | 22.2446 | 35.9722 | 27.7083 | 13.8889 | 19.6237 | 10.8871 | 3.2258 | 17.0833 | 8.3333 | 0 | 22.043 | 9.8118 | 0
48 | 2 | 9 | 25.9409 | 15.6012 | 0 | 35.8195 | 20.9077 | 6.4732 | 37.9032 | 25.672 | 8.5349 | 58.1944 | 46.25 | 30.3472 | 61.2903 | 51.9489 | 39.5161 | 71.1111 | 60 | 42.9167 | 68.2796 | 57.1909 | 42.8763 | 67.7419 | 56.5188 | 44.6237 | 47.5694 | 38.1944 | 23.6806 | 27.6882 | 17.9435 | 8.1989 | 25.5556 | 12.6389 | 6.8056 | 31.5188 | 14.9866 | 0
48 | 2 | 10 | 37.9704 | 20.0941 | 2.3522 | 44.7917 | 28.9486 | 8.4821 | 53.8978 | 38.7097 | 22.7823 | 73.75 | 59.7917 | 45.4861 | 76.1425 | 63.6425 | 55.578 | 81.1806 | 72.2222 | 59.2361 | 87.7688 | 73.4543 | 56.8548 | 75.4704 | 67.0027 | 53.8306 | 61.6667 | 48.1944 | 31.875 | 39.6505 | 27.0161 | 15.5914 | 32.5694 | 21.7361 | 9.5833 | 37.836 | 20.6989 | 7.3253
48 | 2 | 11 | 44.1532 | 26.1425 | 6.1156 | 55.6317 | 39.3601 | 16.4435 | 63.9785 | 46.9086 | 29.4355 | 79.7222 | 67.7778 | 55.2778 | 86.8952 | 73.7231 | 67.4731 | 89.8611 | 82.4306 | 69.5833 | 94.2876 | 85.2823 | 73.9247 | 84.207 | 78.2258 | 67.8763 | 73.3333 | 58.1944 | 42.5 | 47.2446 | 37.9704 | 22.379 | 42.0833 | 29.5139 | 14.7222 | 42.8091 | 25.4032 | 9.3414
48 | 2 | 12 | 47.379 | 33.4677 | 10.0134 | 61.0863 | 46.054 | 19.3452 | 75.4704 | 54.1667 | 39.5161 | 86.3194 | 70.4167 | 62.4306 | 91.1962 | 84.6774 | 73.8575 | 91.1111 | 86.0417 | 77.3611 | 96.707 | 89.9866 | 81.3844 | 88.5753 | 81.6532 | 73.1855 | 75 | 63.6111 | 47.5 | 57.1237 | 44.0188 | 25 | 47.2222 | 36.1111 | 15.9722 | 45.6989 | 33.3333 | 10.8871
48 | 2 | 15 | 50.9409 | 35.2151 | 12.7688 | 64.5833 | 47.6139 | 19.7173 | 76.0081 | 56.3844 | 40.9274 | 87.1528 | 75 | 63.2639 | 92.0699 | 86.9624 | 77.1505 | 91.5972 | 87.1528 | 79.5833 | 97.1102 | 91.129 | 82.5941 | 91.1962 | 83.1317 | 74.5296 | 79.6528 | 65.6944 | 55.5556 | 59.543 | 47.3118 | 33.2661 | 53.8889 | 37.7778 | 19.8611 | 49.3952 | 34.7446 | 12.5
48 | 2 | 20 | 50.9409 | 35.2151 | 12.7688 | 64.5833 | 47.6139 | 19.7173 | 76.0081 | 56.3844 | 40.9274 | 87.1528 | 75 | 63.2639 | 92.0699 | 86.9624 | 77.1505 | 91.5972 | 87.1528 | 79.5833 | 97.1102 | 91.129 | 82.5941 | 91.1962 | 83.1317 | 74.5296 | 79.6528 | 65.6944 | 55.5556 | 59.543 | 47.3118 | 33.2661 | 53.9583 | 37.7778 | 19.8611 | 49.3952 | 34.7446 | 12.5
48 | 2 | 25 | 50.9409 | 35.2151 | 12.7688 | 64.5833 | 47.6139 | 19.7173 | 76.0081 | 56.3844 | 40.9274 | 87.1528 | 75 | 63.2639 | 92.0699 | 86.9624 | 77.1505 | 91.5972 | 87.1528 | 79.5833 | 97.1102 | 91.129 | 82.5941 | 91.1962 | 83.1317 | 74.5296 | 79.6528 | 65.6944 | 55.5556 | 59.543 | 47.3118 | 33.2661 | 53.9583 | 37.7778 | 19.8611 | 49.3952 | 34.7446 | 12.5
48 | 2.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 2.25 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 2.25 | 6 | 7.0565 | 0 | 0 | 9.5982 | 0 | 0 | 8.4005 | 0 | 0 | 16.3194 | 8.4722 | 0 | 18.75 | 11.3575 | 5.1075 | 22.5694 | 14.0972 | 4.7917 | 18.1452 | 9.4086 | 0 | 21.371 | 8.8038 | 0 | 15.3472 | 0 | 0 | 7.1237 | 0 | 0 | 6.875 | 0 | 0 | 7.5941 | 0 | 0
48 | 2.25 | 8 | 18.2796 | 9.543 | 0 | 22.0777 | 13.3929 | 0 | 31.1828 | 14.6505 | 1.1425 | 42.9861 | 28.6806 | 20.4167 | 46.4382 | 35.9543 | 25 | 54.9306 | 44.2361 | 27.4306 | 52.2849 | 39.1801 | 22.5806 | 50.8737 | 35.0134 | 23.7231 | 36.1806 | 28.4722 | 13.8889 | 21.8414 | 12.7016 | 3.2258 | 17.3611 | 8.3333 | 0 | 22.379 | 9.8118 | 0
48 | 2.25 | 9 | 26.0753 | 16.6667 | 0 | 36.9792 | 24.3304 | 6.622 | 40.3898 | 28.629 | 9.4758 | 58.6806 | 46.9444 | 30.3472 | 61.6935 | 53.0914 | 39.6505 | 71.1111 | 60.1389 | 42.9861 | 68.414 | 57.1909 | 42.8763 | 68.3468 | 56.5188 | 44.8925 | 47.6389 | 38.4722 | 23.6806 | 28.7634 | 18.8172 | 8.9382 | 25.5556 | 12.6389 | 6.875 | 32.9301 | 14.9866 | 0
48 | 2.25 | 10 | 38.7097 | 21.2366 | 5.7124 | 46.4209 | 33.0768 | 8.8542 | 54.0995 | 41.5995 | 23.3199 | 75 | 60.3472 | 51.7361 | 76.4113 | 66.5323 | 55.578 | 81.1806 | 72.9861 | 59.5139 | 87.836 | 73.8575 | 57.9301 | 75.672 | 68.0108 | 54.5027 | 62.1528 | 49.5139 | 34.5139 | 43.9516 | 27.2849 | 17.2043 | 33.0556 | 23.6111 | 10.4861 | 39.1801 | 23.5215 | 8.3333
48 | 2.25 | 11 | 46.7742 | 30.6452 | 9.0726 | 57.9613 | 46.3465 | 17.5595 | 69.3548 | 51.2097 | 34.0726 | 83.125 | 70.5556 | 60.1389 | 87.5 | 76.8145 | 68.3468 | 90.7639 | 84.1667 | 74.1667 | 95.6317 | 86.0215 | 75.5376 | 84.543 | 79.7715 | 68.414 | 74.7222 | 60.0694 | 43.4722 | 53.0914 | 38.9785 | 24.5968 | 43.6806 | 32.0139 | 19.4444 | 45.5645 | 27.957 | 10.8199
48 | 2.25 | 12 | 51.0081 | 39.0457 | 17.2715 | 67.7827 | 54.1667 | 21.6518 | 78.8978 | 56.9892 | 43.2124 | 88.2639 | 78.1944 | 66.9444 | 92.7419 | 87.0296 | 77.2177 | 93.8194 | 90.2778 | 82.5694 | 97.5134 | 93.4812 | 85.0806 | 92.6747 | 85.4839 | 77.4194 | 77.5694 | 70.8333 | 57.9861 | 59.0726 | 50.4704 | 29.8387 | 51.4583 | 39.0278 | 26.3194 | 52.8898 | 35.4839 | 15.3898
48 | 2.25 | 15 | 57.4597 | 42.1371 | 27.1505 | 73.6607 | 57.1429 | 31.994 | 82.8629 | 64.9194 | 50.8737 | 92.3611 | 82.5 | 70.7639 | 96.371 | 90.7258 | 85.2151 | 94.7222 | 91.9444 | 87.5694 | 98.7231 | 95.4301 | 88.9785 | 93.9516 | 87.9032 | 80.5108 | 86.4583 | 75 | 63.6111 | 72.6478 | 56.7876 | 38.5753 | 62.2917 | 48.6806 | 32.4306 | 56.4516 | 40.9946 | 23.2527
48 | 2.25 | 20 | 57.4597 | 42.1371 | 27.3522 | 73.6607 | 57.1429 | 32.0685 | 82.8629 | 64.9194 | 50.8737 | 92.3611 | 82.5 | 70.7639 | 96.371 | 90.8602 | 85.2151 | 94.9306 | 91.9444 | 87.5694 | 98.7231 | 95.4301 | 89.0457 | 93.9516 | 87.9032 | 80.5108 | 86.4583 | 75.1389 | 63.6806 | 72.6478 | 56.8548 | 38.5753 | 62.3611 | 48.6806 | 32.6389 | 56.4516 | 40.9946 | 23.2527
48 | 2.25 | 25 | 57.4597 | 42.1371 | 27.3522 | 73.6607 | 57.1429 | 32.0685 | 82.8629 | 64.9194 | 50.8737 | 92.3611 | 82.5 | 70.7639 | 96.371 | 90.8602 | 85.2151 | 94.9306 | 91.9444 | 87.5694 | 98.7231 | 95.4301 | 89.0457 | 93.9516 | 87.9032 | 80.5108 | 86.4583 | 75.1389 | 63.6806 | 72.6478 | 56.8548 | 38.5753 | 62.3611 | 48.6806 | 32.6389 | 56.4516 | 40.9946 | 23.2527
48 | 2.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 2.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 2.5 | 6 | 7.0565 | 0 | 0 | 9.5982 | 0 | 0 | 8.4005 | 0 | 0 | 16.3194 | 8.4722 | 0 | 18.75 | 11.3575 | 5.1075 | 22.5694 | 14.0972 | 4.7917 | 18.1452 | 9.4086 | 0 | 21.371 | 8.8038 | 0 | 15.3472 | 0 | 0 | 7.1237 | 0 | 0 | 6.875 | 0 | 0 | 7.5941 | 0 | 0
48 | 2.5 | 8 | 18.2796 | 9.543 | 0 | 23.1399 | 13.3929 | 0 | 31.1828 | 14.6505 | 1.1425 | 42.9861 | 28.6806 | 20.4167 | 46.5726 | 35.9543 | 25 | 54.9306 | 44.2361 | 27.4306 | 52.2849 | 39.1801 | 22.5806 | 50.8737 | 35.0134 | 23.7231 | 36.25 | 28.4722 | 13.8889 | 21.8414 | 12.7016 | 6.4516 | 17.4306 | 8.6806 | 0 | 22.5134 | 9.8118 | 0
48 | 2.5 | 9 | 26.2769 | 16.6667 | 0 | 37.4256 | 24.4792 | 6.7708 | 40.5242 | 28.6962 | 10.2823 | 58.6806 | 47.2222 | 32.2222 | 62.0968 | 53.0914 | 39.7849 | 71.1111 | 60.2083 | 43.125 | 68.414 | 57.1909 | 43.8844 | 68.5484 | 56.5188 | 44.9597 | 47.6389 | 38.6111 | 23.6806 | 29.5699 | 18.8172 | 8.9382 | 25.5556 | 12.6389 | 6.9444 | 33.1989 | 14.9866 | 0
48 | 2.5 | 10 | 40.6586 | 21.2366 | 7.1909 | 46.8622 | 33.1486 | 11.4583 | 55.8468 | 42.4059 | 23.5215 | 75.0694 | 61.4583 | 52.6389 | 79.2339 | 68.0108 | 55.578 | 82.3611 | 73.1944 | 59.5139 | 88.5081 | 73.8575 | 57.9973 | 77.6882 | 68.0108 | 54.6371 | 63.6806 | 49.5833 | 36.9444 | 45.0269 | 28.8978 | 17.2043 | 33.8889 | 23.8194 | 10.625 | 40.457 | 23.8575 | 8.5349
48 | 2.5 | 11 | 47.379 | 31.3172 | 11.0887 | 58.4821 | 46.6518 | 19.2708 | 71.6398 | 53.293 | 37.6344 | 83.3333 | 72.1528 | 61.5278 | 87.7016 | 77.1505 | 68.5484 | 90.9028 | 85.6944 | 74.375 | 96.707 | 86.3575 | 75.672 | 84.9462 | 80.7124 | 68.6156 | 75.2083 | 61.5972 | 44.0972 | 55.0403 | 39.3817 | 25.8065 | 44.2361 | 32.5 | 19.5139 | 48.9247 | 29.6371 | 13.4409
48 | 2.5 | 12 | 55.2419 | 40.8602 | 19.9597 | 71.0565 | 56.3988 | 21.875 | 80.5108 | 60.2823 | 44.2876 | 89.7917 | 81.3889 | 72.3611 | 94.422 | 89.4489 | 78.629 | 94.8611 | 91.0417 | 84.6528 | 98.9247 | 94.6909 | 86.8952 | 94.2876 | 87.164 | 79.8387 | 83.4722 | 71.5278 | 60.9028 | 60.4167 | 51.2097 | 31.5188 | 56.5972 | 42.2222 | 28.0556 | 54.4355 | 39.5833 | 22.5134
48 | 2.5 | 15 | 67.8091 | 46.9758 | 32.5269 | 77.9505 | 61.9048 | 37.2024 | 85.1478 | 72.5806 | 63.172 | 96.0417 | 88.9583 | 83.1944 | 98.0511 | 95.6989 | 90.7258 | 96.8056 | 94.1667 | 91.1111 | 100 | 98.1183 | 91.7339 | 97.6478 | 92.4059 | 84.879 | 90.625 | 80.5556 | 68.8889 | 80.7124 | 62.4328 | 49.5968 | 71.875 | 56.5278 | 38.4028 | 67.2715 | 46.9086 | 29.7715
48 | 2.5 | 20 | 67.8091 | 46.9758 | 32.7285 | 77.9505 | 62.2768 | 37.3512 | 86.7608 | 72.5806 | 63.3737 | 96.0417 | 89.0278 | 83.4028 | 98.3871 | 95.9677 | 90.7258 | 96.875 | 94.1667 | 91.3194 | 100 | 98.1855 | 91.9355 | 97.6478 | 92.4059 | 84.9462 | 90.6944 | 80.6944 | 69.0278 | 80.7796 | 63.1048 | 52.8898 | 73.2639 | 56.6667 | 38.6111 | 67.5403 | 48.1183 | 29.7715
48 | 2.5 | 25 | 67.8091 | 46.9758 | 32.7285 | 77.9505 | 62.2768 | 37.3512 | 86.7608 | 72.5806 | 63.3737 | 96.0417 | 89.0278 | 83.4028 | 98.3871 | 95.9677 | 90.7258 | 96.875 | 94.1667 | 91.3194 | 100 | 98.1855 | 91.9355 | 97.6478 | 92.4059 | 84.9462 | 90.6944 | 80.6944 | 69.0278 | 80.7796 | 63.1048 | 52.8898 | 73.2639 | 56.6667 | 38.6111 | 67.5403 | 48.1183 | 29.7715
48 | 2.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 2.75 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 2.75 | 6 | 7.0565 | 0 | 0 | 10.2679 | 0 | 0 | 8.4005 | 0 | 0 | 16.3194 | 8.4722 | 0 | 18.75 | 11.3575 | 5.1075 | 22.5694 | 14.0972 | 4.7917 | 18.1452 | 9.4086 | 0 | 21.371 | 8.8038 | 0 | 15.3472 | 0 | 0 | 7.1237 | 0 | 0 | 6.875 | 0 | 0 | 7.5941 | 0 | 0
48 | 2.75 | 8 | 18.2796 | 9.543 | 0 | 24.7768 | 13.3929 | 0 | 31.1828 | 14.6505 | 1.1425 | 42.9861 | 28.6806 | 20.625 | 46.5726 | 35.9543 | 25 | 54.9306 | 44.2361 | 27.4306 | 52.2849 | 39.1801 | 22.5806 | 50.8737 | 35.0134 | 23.7231 | 36.25 | 28.4722 | 13.8889 | 21.8414 | 12.7016 | 6.4516 | 17.4306 | 8.8194 | 0 | 22.5806 | 9.8118 | 0
48 | 2.75 | 9 | 26.2769 | 16.6779 | 0 | 37.4256 | 24.5536 | 6.7708 | 40.5242 | 28.7634 | 10.2823 | 58.6806 | 47.2222 | 32.4306 | 62.2312 | 53.0914 | 39.7849 | 71.1111 | 60.2083 | 43.2639 | 68.414 | 57.1909 | 43.8844 | 68.5484 | 56.5188 | 44.9597 | 47.6389 | 38.6111 | 23.6806 | 29.5699 | 19.422 | 8.9382 | 25.5556 | 13.8194 | 6.9444 | 33.1989 | 14.9866 | 0
48 | 2.75 | 10 | 40.9274 | 21.9086 | 7.1909 | 47.0803 | 34.8727 | 11.9792 | 55.914 | 42.8091 | 23.5215 | 75.0694 | 61.5278 | 53.0556 | 79.3011 | 68.0108 | 55.578 | 82.4306 | 73.1944 | 59.5139 | 88.5081 | 73.8575 | 58.0645 | 78.0242 | 68.0108 | 54.6371 | 63.8194 | 49.5833 | 37.0139 | 45.4973 | 29.0323 | 17.2043 | 35.0694 | 25.4167 | 10.625 | 40.6586 | 23.9919 | 8.7366
48 | 2.75 | 11 | 47.7151 | 32.5941 | 11.1559 | 58.8542 | 47.8423 | 19.7173 | 71.9086 | 54.7043 | 38.0376 | 85.3472 | 73.4722 | 61.9444 | 87.9704 | 77.4194 | 68.8172 | 91.0417 | 85.8333 | 74.4444 | 96.8414 | 86.4919 | 75.672 | 84.9462 | 80.7124 | 68.6156 | 75.2778 | 61.6667 | 47.9167 | 55.3091 | 39.7177 | 26.5457 | 45.9722 | 32.8472 | 19.9306 | 49.0591 | 29.7715 | 14.1801
48 | 2.75 | 12 | 56.3172 | 41.1962 | 20.9677 | 71.7185 | 57.8125 | 23.1399 | 80.8468 | 60.8199 | 44.8253 | 91.1111 | 83.2639 | 74.6528 | 94.6237 | 89.7849 | 78.7634 | 95.4167 | 91.5278 | 87.0139 | 99.1263 | 94.7581 | 87.3656 | 94.6237 | 88.3737 | 80.1747 | 84.8611 | 72.9167 | 62.5 | 60.6855 | 52.8898 | 34.2742 | 57.4306 | 42.8472 | 28.4028 | 58.1317 | 39.9866 | 23.2527
48 | 2.75 | 15 | 70.9677 | 53.5618 | 37.0296 | 85.2319 | 69.7763 | 43.2292 | 89.1801 | 76.8145 | 67.2715 | 97.5694 | 91.9444 | 85.4861 | 99.2608 | 97.6478 | 92.4731 | 98.4722 | 96.3889 | 93.2639 | 100 | 98.9919 | 94.4892 | 99.328 | 94.8925 | 88.7769 | 92.8472 | 85.8333 | 77.3611 | 85.0134 | 69.1532 | 56.3844 | 80.2083 | 64.0972 | 41.875 | 72.9839 | 51.2097 | 34.543
48 | 2.75 | 20 | 72.7151 | 55.4435 | 40.1882 | 85.3756 | 72.9167 | 44.5685 | 89.4489 | 78.1586 | 67.6075 | 97.7083 | 93.75 | 85.6944 | 99.3952 | 97.8495 | 92.8091 | 98.4722 | 96.3889 | 93.3333 | 100 | 98.9919 | 94.5565 | 99.328 | 95.1613 | 88.9113 | 92.8472 | 86.0417 | 77.9861 | 85.9543 | 70.4301 | 63.0376 | 80.6944 | 66.5972 | 46.4583 | 73.4543 | 51.8817 | 36.4919
48 | 2.75 | 25 | 72.7151 | 55.4435 | 40.1882 | 85.3756 | 72.9167 | 44.5685 | 89.4489 | 78.1586 | 67.6075 | 97.7083 | 93.75 | 85.6944 | 99.3952 | 97.8495 | 92.8091 | 98.4722 | 96.3889 | 93.3333 | 100 | 98.9919 | 94.5565 | 99.328 | 95.1613 | 88.9113 | 92.8472 | 86.0417 | 77.9861 | 85.9543 | 70.4301 | 63.0376 | 80.6944 | 66.5972 | 46.4583 | 73.4543 | 51.8817 | 36.4919
48 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3 | 6 | 7.0565 | 0 | 0 | 10.2679 | 0 | 0 | 8.4005 | 0 | 0 | 16.3194 | 8.4722 | 0 | 18.75 | 11.3575 | 5.1075 | 22.5694 | 14.0972 | 4.7917 | 18.1452 | 9.4086 | 0 | 21.371 | 8.8038 | 0 | 15.3472 | 0 | 0 | 7.1237 | 0 | 0 | 6.875 | 0 | 0 | 7.5941 | 0 | 0
48 | 3 | 8 | 18.2796 | 10.2218 | 0 | 24.7768 | 13.3929 | 0 | 31.1828 | 14.6505 | 1.1425 | 42.9861 | 28.6806 | 20.625 | 46.5726 | 35.9543 | 25 | 54.9306 | 44.2361 | 27.4306 | 52.2849 | 39.1801 | 22.5806 | 50.8737 | 35.0134 | 23.7231 | 36.25 | 28.4722 | 13.8889 | 21.8414 | 12.7016 | 6.4516 | 17.4306 | 9.2361 | 0 | 22.5806 | 9.8118 | 0
48 | 3 | 9 | 26.2769 | 17.0699 | 0 | 37.4256 | 24.5536 | 6.7708 | 40.5242 | 28.7634 | 10.2823 | 58.6806 | 47.2222 | 33.9583 | 62.2312 | 53.0914 | 39.7849 | 71.1111 | 60.2083 | 43.2639 | 68.414 | 57.1909 | 43.8844 | 68.5484 | 56.5188 | 44.9597 | 47.6389 | 38.6111 | 23.6806 | 29.5699 | 19.5565 | 8.9382 | 25.5556 | 13.8194 | 6.9444 | 33.1989 | 14.9866 | 0
48 | 3 | 10 | 41.129 | 24.8656 | 7.1909 | 47.3009 | 35.5193 | 11.9792 | 55.9812 | 43.2796 | 23.6559 | 75.0694 | 61.5278 | 53.125 | 79.3011 | 68.0108 | 55.578 | 82.4306 | 73.1944 | 59.5139 | 88.5081 | 73.8575 | 58.1317 | 78.1586 | 68.0108 | 54.6371 | 63.9583 | 49.5833 | 37.0139 | 45.5645 | 29.0323 | 17.2043 | 35.0694 | 25.4167 | 11.0417 | 40.6586 | 25.5376 | 8.7366
48 | 3 | 11 | 47.7823 | 32.7285 | 13.2392 | 58.8542 | 47.9167 | 19.7917 | 72.1774 | 55.4435 | 38.3737 | 85.4167 | 73.75 | 62.2917 | 88.0376 | 77.4194 | 68.8844 | 91.1806 | 85.9028 | 75.9028 | 96.8414 | 86.5591 | 75.672 | 84.9462 | 80.7124 | 68.6156 | 75.2778 | 61.6667 | 49.2361 | 55.4435 | 40.457 | 26.6801 | 46.1806 | 33.125 | 19.9306 | 49.1263 | 29.8387 | 14.3145
48 | 3 | 12 | 56.7876 | 41.4651 | 23.9919 | 72.0828 | 58.9286 | 27.6042 | 81.7204 | 61.5591 | 46.4382 | 91.3194 | 83.75 | 75.2778 | 95.1613 | 89.9194 | 79.3683 | 95.9028 | 92.2917 | 87.2917 | 99.1263 | 94.8925 | 87.836 | 94.8253 | 89.1801 | 80.4435 | 85.1389 | 73.4028 | 62.9861 | 64.1801 | 54.1667 | 35.4167 | 57.5694 | 44.0278 | 28.5417 | 58.6022 | 40.1882 | 23.2527
48 | 3 | 15 | 81.3844 | 57.4984 | 46.1022 | 87.0767 | 75.2976 | 52.2321 | 90.5242 | 80.0403 | 73.5215 | 98.4028 | 94.2361 | 87.9167 | 100 | 98.1855 | 94.7581 | 99.7917 | 97.7778 | 95.4167 | 100 | 99.9328 | 95.8333 | 99.664 | 97.379 | 90.5914 | 96.1806 | 88.2639 | 81.1806 | 87.2984 | 77.2177 | 62.9032 | 80.5556 | 68.6111 | 47.0139 | 77.0833 | 61.0887 | 40.8602
48 | 3 | 20 | 84.0726 | 62.7688 | 49.1935 | 87.5154 | 78.9435 | 53.9435 | 92.6075 | 80.6452 | 74.1935 | 99.0278 | 95.2778 | 89.375 | 100 | 99.1935 | 95.5645 | 99.8611 | 97.9861 | 95.6944 | 100 | 100 | 95.9005 | 99.7984 | 97.8495 | 93.2796 | 96.5278 | 89.375 | 81.7361 | 89.5833 | 78.9651 | 68.8844 | 81.7361 | 72.9861 | 52.9861 | 79.7715 | 62.9032 | 47.5134
48 | 3 | 25 | 84.0726 | 62.7688 | 49.1935 | 87.5154 | 78.9435 | 53.9435 | 92.6075 | 80.6452 | 74.1935 | 99.0278 | 95.2778 | 89.375 | 100 | 99.1935 | 95.5645 | 99.8611 | 97.9861 | 95.6944 | 100 | 100 | 95.9005 | 99.7984 | 97.8495 | 93.2796 | 96.5278 | 89.375 | 81.7361 | 89.5833 | 78.9651 | 68.8844 | 81.7361 | 72.9861 | 52.9861 | 79.7715 | 62.9032 | 47.5134
48 | 3.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3.25 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3.25 | 6 | 7.0565 | 0 | 0 | 10.2679 | 0 | 0 | 8.4005 | 0 | 0 | 16.3194 | 8.4722 | 0 | 18.75 | 11.3575 | 5.1075 | 22.5694 | 14.0972 | 4.7917 | 18.1452 | 9.4086 | 0 | 21.371 | 8.8038 | 0 | 15.3472 | 0 | 0 | 7.1237 | 0 | 0 | 6.875 | 0 | 0 | 7.5941 | 0 | 0
48 | 3.25 | 8 | 18.2796 | 10.6183 | 0 | 26.3393 | 13.3929 | 0 | 31.1828 | 14.6505 | 1.1425 | 42.9861 | 28.6806 | 20.625 | 46.5726 | 35.9543 | 25 | 54.9306 | 44.2361 | 27.4306 | 52.2849 | 39.1801 | 22.5806 | 50.8737 | 35.0134 | 23.7231 | 36.25 | 28.4722 | 13.8889 | 21.8414 | 12.7016 | 6.4516 | 17.4306 | 9.2361 | 0 | 22.5806 | 9.8118 | 0
48 | 3.25 | 9 | 26.2769 | 17.0699 | 0 | 37.4256 | 24.5536 | 6.7708 | 40.5242 | 28.7634 | 10.2823 | 58.6806 | 47.2222 | 33.9583 | 62.2312 | 53.0914 | 39.7849 | 71.1111 | 60.2083 | 43.2639 | 68.414 | 57.1909 | 43.8844 | 68.5484 | 56.5188 | 44.9597 | 47.6389 | 38.6111 | 23.6806 | 29.5699 | 19.5565 | 8.9382 | 25.5556 | 15.2778 | 6.9444 | 33.6694 | 14.9866 | 0
48 | 3.25 | 10 | 41.129 | 24.8813 | 7.1909 | 47.9167 | 36.0222 | 11.9792 | 55.9812 | 43.414 | 23.6559 | 75.0694 | 61.5278 | 53.1944 | 79.3011 | 68.0108 | 55.578 | 82.4306 | 73.1944 | 59.5139 | 88.5081 | 73.8575 | 58.1317 | 78.1586 | 68.0108 | 54.6371 | 64.1667 | 49.5833 | 37.0139 | 45.5645 | 29.0323 | 17.2043 | 35.0694 | 25.4167 | 11.0417 | 40.6586 | 25.9409 | 8.7366
48 | 3.25 | 11 | 47.7823 | 32.7285 | 13.3065 | 61.9792 | 47.9167 | 20.9821 | 72.1774 | 55.4435 | 38.4409 | 85.4167 | 73.8194 | 62.4306 | 88.0376 | 77.4194 | 68.8844 | 91.1806 | 85.9722 | 75.9722 | 96.8414 | 86.5591 | 75.672 | 84.9462 | 80.7124 | 68.6156 | 75.2778 | 61.6667 | 49.2361 | 55.4435 | 40.5914 | 26.7473 | 46.1806 | 33.3333 | 19.9306 | 49.1263 | 29.9059 | 14.3817
48 | 3.25 | 12 | 59.207 | 41.6667 | 23.9919 | 73.5119 | 60.5347 | 27.8274 | 81.7876 | 61.8952 | 48.5215 | 91.4583 | 83.8889 | 75.2778 | 95.1613 | 89.9194 | 79.3683 | 96.0417 | 92.2917 | 87.3611 | 99.1263 | 95.0269 | 88.1048 | 94.9597 | 89.4489 | 80.5108 | 85.4167 | 73.75 | 63.0556 | 64.6505 | 54.3683 | 36.7608 | 59.4444 | 44.0278 | 28.5417 | 59.9462 | 40.3226 | 23.2527
48 | 3.25 | 15 | 83.3333 | 60.0806 | 50.4032 | 89.2113 | 76.3393 | 54.9851 | 94.1532 | 80.7796 | 74.664 | 98.9583 | 95.6944 | 92.0833 | 100 | 98.9919 | 96.7742 | 100 | 98.8889 | 95.8333 | 100 | 100 | 96.4382 | 100 | 98.9919 | 94.422 | 96.875 | 90.7639 | 84.0278 | 90.3898 | 79.0323 | 67.0699 | 85.3472 | 73.4028 | 52.2917 | 80.914 | 65.8602 | 43.414
48 | 3.25 | 20 | 86.6263 | 70.4301 | 53.3602 | 90.3274 | 80.9934 | 59.6162 | 96.6398 | 84.0054 | 76.6801 | 99.7917 | 97.2917 | 94.1667 | 100 | 99.9328 | 97.7151 | 100 | 99.1667 | 96.1806 | 100 | 100 | 96.7742 | 100 | 99.328 | 94.8925 | 97.7778 | 92.5694 | 86.0417 | 95.5645 | 82.5269 | 73.6559 | 91.0417 | 77.4306 | 58.9583 | 85.4839 | 70.8333 | 53.4274
48 | 3.25 | 25 | 86.6263 | 70.4301 | 53.3602 | 90.3274 | 80.9934 | 59.6162 | 96.6398 | 84.0054 | 76.6801 | 99.7917 | 97.2917 | 94.1667 | 100 | 99.9328 | 97.7151 | 100 | 99.1667 | 96.1806 | 100 | 100 | 96.7742 | 100 | 99.328 | 94.8925 | 97.8472 | 92.5694 | 86.0417 | 95.5645 | 82.5269 | 73.6559 | 91.0417 | 77.4306 | 58.9583 | 85.4839 | 70.8333 | 53.4274
48 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3.5 | 6 | 7.0565 | 0 | 0 | 10.2679 | 0 | 0 | 8.4005 | 0 | 0 | 16.3194 | 8.4722 | 0 | 18.75 | 11.3575 | 5.1075 | 22.5694 | 14.0972 | 4.7917 | 18.1452 | 9.4086 | 0 | 21.371 | 8.8038 | 0 | 15.3472 | 0 | 0 | 7.1237 | 0 | 0 | 6.875 | 0 | 0 | 7.5941 | 0 | 0
48 | 3.5 | 8 | 18.2796 | 10.6183 | 0 | 26.3393 | 13.3929 | 0 | 31.1828 | 14.6505 | 1.1425 | 42.9861 | 28.6806 | 20.625 | 46.5726 | 35.9543 | 25 | 54.9306 | 44.2361 | 27.4306 | 52.2849 | 39.1801 | 22.5806 | 50.8737 | 35.0134 | 23.7231 | 36.25 | 28.4722 | 13.8889 | 21.8414 | 12.7016 | 6.4516 | 17.4306 | 9.2361 | 0 | 22.5806 | 9.8118 | 0
48 | 3.5 | 9 | 26.2769 | 17.0699 | 0 | 37.4256 | 24.5536 | 6.7708 | 40.5242 | 28.7634 | 10.2823 | 58.6806 | 47.2222 | 33.9583 | 62.2312 | 53.0914 | 39.7849 | 71.1111 | 60.2083 | 43.2639 | 68.414 | 57.1909 | 43.8844 | 68.5484 | 56.5188 | 44.9597 | 47.6389 | 38.6111 | 23.6806 | 29.5699 | 19.5565 | 8.9382 | 25.5556 | 15.2778 | 6.9444 | 33.6694 | 14.9866 | 0
48 | 3.5 | 10 | 41.129 | 24.8813 | 7.1909 | 47.9167 | 36.2377 | 11.9792 | 55.9812 | 43.4812 | 23.6559 | 75.0694 | 61.5278 | 53.1944 | 79.3011 | 68.0108 | 56.6532 | 82.4306 | 73.1944 | 59.5139 | 88.5081 | 73.8575 | 58.1317 | 78.1586 | 68.0108 | 54.6371 | 64.1667 | 49.5833 | 37.0139 | 45.5645 | 29.0323 | 17.2043 | 35.0694 | 25.4167 | 11.0417 | 40.6586 | 25.9409 | 8.7366
48 | 3.5 | 11 | 47.7823 | 32.7285 | 13.3737 | 62.0536 | 47.9167 | 20.9821 | 72.1774 | 55.4435 | 38.4409 | 85.4167 | 73.8194 | 62.4306 | 88.0376 | 77.4194 | 69.3548 | 91.1806 | 85.9722 | 76.0417 | 96.8414 | 86.5591 | 75.672 | 85.1478 | 80.7124 | 68.6156 | 75.2778 | 61.6667 | 49.2361 | 55.4435 | 40.5914 | 26.8817 | 46.1806 | 33.4722 | 19.9306 | 49.1263 | 29.9731 | 14.3817
48 | 3.5 | 12 | 59.2742 | 41.7339 | 23.9919 | 73.6607 | 60.6809 | 28.125 | 81.8548 | 62.164 | 48.5887 | 91.4583 | 84.0972 | 75.2778 | 95.1613 | 89.9194 | 79.8387 | 96.0417 | 92.2917 | 87.3611 | 99.1263 | 95.0941 | 88.172 | 94.9597 | 89.4489 | 80.5108 | 85.4861 | 74.0278 | 63.3333 | 64.7177 | 54.4355 | 38.3065 | 59.5833 | 44.0278 | 28.5417 | 60.1478 | 40.457 | 23.2527
48 | 3.5 | 15 | 84.3414 | 63.1048 | 50.8737 | 90.253 | 78.9511 | 60.1858 | 94.8925 | 85.6855 | 75.2016 | 99.5833 | 97.0139 | 93.1944 | 100 | 99.4624 | 97.8495 | 100 | 99.1667 | 96.3194 | 100 | 100 | 97.1774 | 100 | 99.2608 | 94.9597 | 97.1528 | 93.8889 | 86.1806 | 92.5403 | 79.6371 | 67.8091 | 87.2917 | 74.5139 | 53.4028 | 84.207 | 68.75 | 45.7661
48 | 3.5 | 20 | 90.0538 | 74.664 | 58.7366 | 94.3452 | 86.3095 | 69.8584 | 98.5887 | 88.7769 | 79.8387 | 100 | 99.0972 | 95.4167 | 100 | 100 | 98.8575 | 100 | 99.5139 | 96.8056 | 100 | 100 | 97.8495 | 100 | 100 | 96.2366 | 98.75 | 95.8333 | 88.6111 | 98.3871 | 86.0887 | 77.0161 | 93.8194 | 82.8472 | 68.6806 | 88.8441 | 79.5027 | 58.4677
48 | 3.5 | 25 | 90.0538 | 74.664 | 58.7366 | 94.3452 | 86.3095 | 69.8584 | 98.5887 | 88.7769 | 79.8387 | 100 | 99.0972 | 95.4167 | 100 | 100 | 98.8575 | 100 | 99.5139 | 96.8056 | 100 | 100 | 97.8495 | 100 | 100 | 96.2366 | 98.75 | 95.8333 | 88.6111 | 98.3871 | 86.0887 | 77.0833 | 93.8194 | 82.8472 | 68.6806 | 88.8441 | 79.5027 | 58.4677
48 | 3.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3.75 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3.75 | 6 | 7.0565 | 0 | 0 | 10.2679 | 0 | 0 | 8.4005 | 0 | 0 | 16.3194 | 8.4722 | 0 | 18.75 | 11.3575 | 5.1075 | 22.5694 | 14.0972 | 4.7917 | 18.1452 | 9.4086 | 0 | 21.371 | 8.8038 | 0 | 15.3472 | 0 | 0 | 7.1237 | 0 | 0 | 6.875 | 0 | 0 | 7.5941 | 0 | 0
48 | 3.75 | 8 | 18.2796 | 10.6183 | 0 | 26.3393 | 13.3929 | 0 | 31.1828 | 14.6505 | 1.1425 | 42.9861 | 28.6806 | 20.625 | 46.5726 | 35.9543 | 25 | 54.9306 | 44.2361 | 27.4306 | 52.2849 | 39.1801 | 22.5806 | 50.8737 | 35.0134 | 23.7231 | 36.25 | 28.4722 | 13.8889 | 21.8414 | 12.7016 | 6.4516 | 17.4306 | 9.2361 | 0 | 22.5806 | 9.8118 | 0
48 | 3.75 | 9 | 26.2769 | 17.0699 | 0 | 37.4256 | 24.5536 | 6.7708 | 40.5242 | 28.7634 | 10.2823 | 58.6806 | 47.2222 | 33.9583 | 62.2312 | 53.0914 | 39.7849 | 71.1111 | 60.2083 | 43.2639 | 68.414 | 57.1909 | 43.8844 | 68.5484 | 56.5188 | 44.9597 | 47.6389 | 38.6111 | 23.6806 | 29.5699 | 19.5565 | 8.9382 | 25.5556 | 15.2778 | 6.9444 | 33.6694 | 14.9866 | 0
48 | 3.75 | 10 | 41.129 | 24.8813 | 7.1909 | 47.9167 | 36.3095 | 11.9792 | 55.9812 | 43.4812 | 23.6559 | 75.0694 | 61.5278 | 53.1944 | 79.3011 | 68.0108 | 56.6532 | 82.4306 | 73.1944 | 59.5139 | 88.5081 | 73.8575 | 58.1317 | 78.1586 | 68.0108 | 54.6371 | 64.1667 | 49.5833 | 37.0139 | 45.5645 | 29.0323 | 17.2043 | 35.0694 | 25.4167 | 11.0417 | 40.6586 | 25.9409 | 8.7366
48 | 3.75 | 11 | 47.7823 | 32.7285 | 13.3737 | 62.0536 | 47.9167 | 20.9821 | 72.1774 | 55.4435 | 38.4409 | 85.4167 | 73.8194 | 62.4306 | 88.0376 | 77.4194 | 69.3548 | 91.1806 | 85.9722 | 76.0417 | 96.8414 | 86.5591 | 75.672 | 85.2151 | 80.7124 | 68.6156 | 75.2778 | 61.6667 | 49.2361 | 55.4435 | 40.5914 | 26.8817 | 46.1806 | 33.5417 | 19.9306 | 49.1263 | 29.9731 | 14.3817
48 | 3.75 | 12 | 59.7446 | 41.7339 | 23.9919 | 73.7351 | 60.6809 | 31.7708 | 81.922 | 62.2984 | 48.5887 | 91.4583 | 84.0972 | 75.2778 | 95.1613 | 89.9194 | 79.8387 | 96.0417 | 92.2917 | 87.3611 | 99.1263 | 95.0941 | 88.172 | 94.9597 | 89.4489 | 80.5108 | 85.4861 | 74.0278 | 63.4028 | 64.7177 | 54.4355 | 38.3737 | 59.7222 | 44.0278 | 28.5417 | 60.3495 | 41.1962 | 23.2527
48 | 3.75 | 15 | 84.4758 | 65.3898 | 53.5618 | 91.0714 | 80.1339 | 60.7656 | 95.0941 | 86.5591 | 76.3441 | 99.7917 | 97.0833 | 93.6111 | 100 | 99.7312 | 98.1855 | 100 | 99.3056 | 97.1528 | 100 | 100 | 97.7151 | 100 | 99.4624 | 95.4973 | 97.6389 | 94.0972 | 86.8056 | 92.5403 | 81.4516 | 69.086 | 87.5 | 75.9028 | 55.1389 | 84.543 | 69.0188 | 48.7231
48 | 3.75 | 20 | 91.9355 | 78.4946 | 65.5914 | 96.2798 | 87.2024 | 79.0948 | 99.5296 | 94.086 | 83.5349 | 100 | 99.4444 | 96.3889 | 100 | 100 | 99.5968 | 100 | 100 | 97.8472 | 100 | 100 | 98.5887 | 100 | 100 | 98.2527 | 99.6528 | 97.2222 | 91.4583 | 99.1263 | 90.1882 | 82.7285 | 94.7917 | 88.4722 | 75.1389 | 92.1371 | 82.8629 | 66.6667
48 | 3.75 | 25 | 91.9355 | 78.4946 | 65.5914 | 96.2798 | 87.2024 | 79.0948 | 99.5296 | 94.086 | 83.5349 | 100 | 99.5139 | 96.3889 | 100 | 100 | 99.5968 | 100 | 100 | 97.8472 | 100 | 100 | 98.7903 | 100 | 100 | 98.2527 | 99.6528 | 97.2222 | 91.4583 | 99.1935 | 90.5242 | 82.7285 | 95 | 88.4722 | 75.4167 | 92.1371 | 82.8629 | 66.7339
48 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 4 | 6 | 7.0565 | 0 | 0 | 10.2679 | 0 | 0 | 8.4005 | 0 | 0 | 16.3194 | 8.4722 | 0 | 18.75 | 11.3575 | 5.1075 | 22.5694 | 14.0972 | 4.7917 | 18.1452 | 9.4086 | 0 | 21.371 | 8.8038 | 0 | 15.3472 | 0 | 0 | 7.1237 | 0 | 0 | 6.875 | 0 | 0 | 7.5941 | 0 | 0
48 | 4 | 8 | 18.2796 | 10.6183 | 0 | 26.3393 | 13.3929 | 0 | 31.1828 | 14.6505 | 1.1425 | 42.9861 | 28.6806 | 20.625 | 46.5726 | 35.9543 | 25 | 54.9306 | 44.2361 | 27.4306 | 52.2849 | 39.1801 | 22.5806 | 50.8737 | 35.0134 | 23.7231 | 36.25 | 28.4722 | 13.8889 | 21.8414 | 12.7016 | 6.4516 | 17.4306 | 9.2361 | 0 | 22.5806 | 9.8118 | 0
48 | 4 | 9 | 26.2769 | 17.0699 | 0 | 37.4256 | 24.5536 | 6.7708 | 40.5242 | 28.7634 | 10.2823 | 58.6806 | 47.2222 | 33.9583 | 62.2312 | 53.0914 | 39.7849 | 71.1111 | 60.2083 | 43.2639 | 68.414 | 57.1909 | 43.8844 | 68.5484 | 56.5188 | 44.9597 | 47.6389 | 38.6111 | 23.6806 | 29.5699 | 19.5565 | 8.9382 | 25.5556 | 15.2778 | 6.9444 | 33.6694 | 14.9866 | 0
48 | 4 | 10 | 41.129 | 24.8813 | 7.1909 | 47.9167 | 36.3095 | 11.9792 | 55.9812 | 43.4812 | 23.6559 | 75.0694 | 61.5278 | 53.1944 | 79.3011 | 68.0108 | 56.6532 | 82.4306 | 73.1944 | 59.5139 | 88.5081 | 73.8575 | 58.1317 | 78.1586 | 68.0108 | 54.6371 | 64.1667 | 49.5833 | 37.0139 | 45.5645 | 29.0323 | 17.2043 | 35.0694 | 25.4167 | 11.0417 | 40.6586 | 25.9409 | 8.7366
48 | 4 | 11 | 47.7823 | 32.7285 | 13.3737 | 62.0536 | 47.9167 | 20.9821 | 72.1774 | 55.4435 | 38.4409 | 85.4167 | 73.8194 | 62.4306 | 88.0376 | 77.4194 | 69.3548 | 91.1806 | 85.9722 | 76.0417 | 96.8414 | 86.5591 | 75.672 | 85.2151 | 80.7124 | 68.6156 | 75.2778 | 61.6667 | 49.2361 | 55.4435 | 40.5914 | 26.8817 | 46.1806 | 33.5417 | 19.9306 | 49.1263 | 29.9731 | 14.3817
48 | 4 | 12 | 59.7446 | 41.7339 | 23.9919 | 73.7351 | 60.6809 | 31.7708 | 81.922 | 62.3656 | 48.5887 | 91.4583 | 84.0972 | 75.2778 | 95.1613 | 89.9194 | 79.8387 | 96.0417 | 92.2917 | 87.3611 | 99.1263 | 95.0941 | 88.172 | 94.9597 | 89.4489 | 80.5108 | 85.4861 | 74.0278 | 63.4028 | 64.7177 | 54.4355 | 38.4409 | 59.8611 | 44.0278 | 28.5417 | 60.4839 | 41.1962 | 23.2527
48 | 4 | 15 | 84.6102 | 67.3387 | 54.3011 | 91.4435 | 81.25 | 65.9175 | 95.2957 | 87.2312 | 77.1505 | 99.7917 | 97.3611 | 94.5833 | 100 | 99.7984 | 98.3871 | 100 | 99.3056 | 97.3611 | 100 | 100 | 97.8495 | 100 | 99.5296 | 96.1022 | 97.9861 | 94.7222 | 87.6389 | 92.5403 | 81.9892 | 69.6237 | 88.2639 | 78.5417 | 58.5417 | 84.8118 | 69.5565 | 53.6962
48 | 4 | 20 | 93.3468 | 84.4086 | 69.3548 | 97.9911 | 90.997 | 82.6637 | 99.9328 | 95.4301 | 86.3575 | 100 | 99.7917 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.3952 | 100 | 100 | 99.3952 | 100 | 98.4722 | 93.75 | 99.7984 | 93.9516 | 85.5511 | 97.8472 | 91.1111 | 80.9722 | 93.8844 | 87.0968 | 72.2446
48 | 4 | 25 | 93.3468 | 84.4086 | 69.3548 | 97.9911 | 90.997 | 82.6637 | 99.9328 | 95.4301 | 86.3575 | 100 | 99.8611 | 96.9444 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.6806 | 93.75 | 99.9328 | 94.0188 | 85.6183 | 97.8472 | 91.1806 | 81.0417 | 93.8844 | 87.0968 | 72.3118
72 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5417 | 0 | 0 | 8.871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7957 | 0 | 0 | 10.6944 | 0 | 0 | 9.4086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7957 | 0 | 0 | 10.6944 | 0 | 0 | 9.4086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7957 | 0 | 0 | 10.6944 | 0 | 0 | 9.4086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7957 | 0 | 0 | 10.6944 | 0 | 0 | 9.4086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7957 | 0 | 0 | 10.6944 | 0 | 0 | 9.4086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7957 | 0 | 0 | 10.6944 | 0 | 0 | 9.4086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7957 | 0 | 0 | 10.6944 | 0 | 0 | 9.4086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7957 | 0 | 0 | 10.6944 | 0 | 0 | 9.4086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.75 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.75 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7446 | 0 | 0 | 12.4306 | 0 | 0 | 12.0296 | 0 | 0 | 10.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.75 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.0833 | 0 | 0 | 19.5565 | 8.7366 | 0 | 25.625 | 11.875 | 0 | 20.2957 | 10.0806 | 0 | 24.0591 | 11.4247 | 0 | 11.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.75 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 0 | 21.0349 | 10.8871 | 0 | 27.7778 | 12.7083 | 0 | 22.9839 | 11.9624 | 0 | 24.2608 | 12.0968 | 0 | 11.3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.75 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 0 | 21.1022 | 10.8871 | 0 | 27.7778 | 12.7083 | 0 | 22.9839 | 11.9624 | 0 | 24.2608 | 12.6344 | 0 | 11.3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.75 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 0 | 21.1022 | 10.8871 | 0 | 27.7778 | 12.7083 | 0 | 22.9839 | 11.9624 | 0 | 24.2608 | 12.6344 | 0 | 11.3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.75 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 0 | 21.1022 | 10.8871 | 0 | 27.7778 | 12.7083 | 0 | 22.9839 | 11.9624 | 0 | 24.2608 | 12.6344 | 0 | 11.3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.75 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 0 | 21.1022 | 10.8871 | 0 | 27.7778 | 12.7083 | 0 | 22.9839 | 11.9624 | 0 | 24.2608 | 12.6344 | 0 | 11.3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.75 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 0 | 21.1022 | 10.8871 | 0 | 27.7778 | 12.7083 | 0 | 22.9839 | 11.9624 | 0 | 24.2608 | 12.6344 | 0 | 11.3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.75 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 0 | 21.1022 | 10.8871 | 0 | 27.7778 | 12.7083 | 0 | 22.9839 | 11.9624 | 0 | 24.2608 | 12.6344 | 0 | 11.3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2639 | 0 | 0 | 10.6183 | 0 | 0 | 15.3472 | 0.41667 | 0 | 13.2392 | 0.13441 | 0 | 11.9624 | 0 | 0 | 5.3472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 8 | 0 | 0 | 0 | 11.6071 | 0 | 0 | 10.2823 | 0 | 0 | 18.6806 | 11.25 | 0 | 25.4704 | 15.5242 | 0 | 37.0139 | 22.4306 | 4.6528 | 32.2581 | 18.8844 | 5.578 | 35.6855 | 15.9274 | 0 | 18.4028 | 11.4583 | 0 | 8.6694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 9 | 0 | 0 | 0 | 12.0638 | 0 | 0 | 12.5 | 0 | 0 | 24.9306 | 13.4722 | 0 | 33.4005 | 21.707 | 2.4866 | 40.9028 | 29.8611 | 11.875 | 42.4731 | 23.7231 | 12.2984 | 41.6667 | 24.4624 | 12.0296 | 22.9861 | 14.2361 | 0 | 9.3414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 10 | 0 | 0 | 0 | 12.0638 | 0 | 0 | 13.9113 | 0 | 0 | 27.2917 | 15.5556 | 0 | 36.4247 | 21.7742 | 10.8871 | 43.0556 | 30 | 13.1944 | 45.0941 | 25.6048 | 12.6344 | 42.9435 | 26.0081 | 14.5833 | 25.8333 | 15.0694 | 0 | 9.3414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 11 | 0 | 0 | 0 | 12.0638 | 0 | 0 | 13.9113 | 0 | 0 | 27.3611 | 15.5556 | 0 | 36.4919 | 21.8414 | 10.8871 | 43.0556 | 30.0694 | 13.1944 | 45.0941 | 25.672 | 12.6344 | 43.0108 | 26.0081 | 14.5833 | 25.9028 | 15.0694 | 0 | 9.3414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 12 | 0 | 0 | 0 | 12.0638 | 0 | 0 | 13.9113 | 0 | 0 | 27.3611 | 15.5556 | 0 | 36.4919 | 21.8414 | 10.8871 | 43.0556 | 30.0694 | 13.1944 | 45.0941 | 25.672 | 12.6344 | 43.0108 | 26.0081 | 14.5833 | 25.9028 | 15.0694 | 0 | 9.3414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 15 | 0 | 0 | 0 | 12.0638 | 0 | 0 | 13.9113 | 0 | 0 | 27.3611 | 15.5556 | 0 | 36.4919 | 21.8414 | 10.8871 | 43.0556 | 30.0694 | 13.1944 | 45.0941 | 25.672 | 12.6344 | 43.0108 | 26.0081 | 14.5833 | 25.9028 | 15.0694 | 0 | 9.3414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 20 | 0 | 0 | 0 | 12.0638 | 0 | 0 | 13.9113 | 0 | 0 | 27.3611 | 15.5556 | 0 | 36.4919 | 21.8414 | 10.8871 | 43.0556 | 30.0694 | 13.1944 | 45.0941 | 25.672 | 12.6344 | 43.0108 | 26.0081 | 14.5833 | 25.9028 | 15.0694 | 0 | 9.3414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 25 | 0 | 0 | 0 | 12.0638 | 0 | 0 | 13.9113 | 0 | 0 | 27.3611 | 15.5556 | 0 | 36.4919 | 21.8414 | 10.8871 | 43.0556 | 30.0694 | 13.1944 | 45.0941 | 25.672 | 12.6344 | 43.0108 | 26.0081 | 14.5833 | 25.9028 | 15.0694 | 0 | 9.3414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1.25 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1.25 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.4247 | 0 | 0 | 15.3472 | 2.0833 | 0 | 13.2392 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1.25 | 8 | 11.4247 | 0 | 0 | 15.8482 | 0 | 0 | 18.2124 | 1.8145 | 0 | 22.7778 | 12.9861 | 0 | 29.3683 | 21.371 | 10.0806 | 39.0972 | 26.0417 | 10.2778 | 43.5484 | 22.7151 | 10.0134 | 42.6747 | 16.4651 | 9.7446 | 22.7778 | 14.7917 | 0 | 12.7688 | 0 | 0 | 0.97222 | 0 | 0 | 12.5672 | 0 | 0
72 | 1.25 | 9 | 15.5242 | 0 | 0 | 20.2586 | 10.8272 | 0 | 22.379 | 8.9382 | 0 | 36.5278 | 22.0833 | 12.0139 | 43.2124 | 30.578 | 16.0618 | 50.9028 | 37.2917 | 24.7917 | 58.6022 | 37.2984 | 15.121 | 49.9328 | 32.2581 | 21.2366 | 30.4167 | 17.2917 | 2.4306 | 19.3548 | 6.6532 | 0 | 10.5556 | 0 | 0 | 15.457 | 1.5457 | 0
72 | 1.25 | 10 | 15.5242 | 0 | 0 | 21.4927 | 12.4436 | 0 | 24.1935 | 14.3817 | 0 | 44.9306 | 28.6111 | 15.625 | 51.7473 | 36.828 | 24.5296 | 58.4722 | 44.4444 | 29.7222 | 67.4731 | 47.3118 | 27.0161 | 56.9892 | 37.5672 | 29.0323 | 37.2222 | 23.4722 | 9.4444 | 24.2608 | 8.5349 | 0 | 12.3611 | 0 | 0 | 15.457 | 1.5457 | 0
72 | 1.25 | 11 | 15.5242 | 0 | 0 | 21.6364 | 12.518 | 0 | 28.4946 | 15.5242 | 0 | 49.5833 | 30.1389 | 16.1111 | 55.914 | 37.7016 | 28.0914 | 59.9306 | 46.3194 | 31.3889 | 68.2124 | 48.3871 | 29.0995 | 61.0215 | 41.1962 | 29.7715 | 38.6111 | 23.6111 | 13.4722 | 24.3952 | 8.6694 | 0 | 12.3611 | 0 | 0 | 15.5242 | 1.5457 | 0
72 | 1.25 | 12 | 15.5242 | 0 | 0 | 21.6364 | 12.518 | 0 | 28.4946 | 15.5242 | 0 | 49.5833 | 30.1389 | 16.1111 | 55.9812 | 38.7769 | 28.2258 | 60.0694 | 46.3889 | 31.3889 | 68.2796 | 48.5887 | 29.1667 | 61.0887 | 41.1962 | 29.8387 | 38.6111 | 24.1667 | 13.5417 | 24.3952 | 8.6694 | 0 | 12.3611 | 0 | 0 | 15.5242 | 1.5457 | 0
72 | 1.25 | 15 | 15.5242 | 0 | 0 | 21.6364 | 12.518 | 0 | 28.4946 | 15.5242 | 0 | 49.5833 | 30.1389 | 16.1111 | 55.9812 | 38.7769 | 28.2258 | 60.0694 | 46.4583 | 31.3889 | 68.2796 | 48.5887 | 29.2339 | 61.0887 | 41.1962 | 29.8387 | 38.6111 | 24.1667 | 13.5417 | 24.3952 | 8.6694 | 0 | 12.3611 | 0 | 0 | 15.5242 | 1.5457 | 0
72 | 1.25 | 20 | 15.5242 | 0 | 0 | 21.6364 | 12.518 | 0 | 28.4946 | 15.5242 | 0 | 49.5833 | 30.1389 | 16.1111 | 55.9812 | 38.7769 | 28.2258 | 60.0694 | 46.4583 | 31.3889 | 68.2796 | 48.5887 | 29.2339 | 61.0887 | 41.1962 | 29.8387 | 38.6111 | 24.1667 | 13.5417 | 24.3952 | 8.6694 | 0 | 12.3611 | 0 | 0 | 15.5242 | 1.5457 | 0
72 | 1.25 | 25 | 15.5242 | 0 | 0 | 21.6364 | 12.518 | 0 | 28.4946 | 15.5242 | 0 | 49.5833 | 30.1389 | 16.1111 | 55.9812 | 38.7769 | 28.2258 | 60.0694 | 46.4583 | 31.3889 | 68.2796 | 48.5887 | 29.2339 | 61.0887 | 41.1962 | 29.8387 | 38.6111 | 24.1667 | 13.5417 | 24.3952 | 8.6694 | 0 | 12.3611 | 0 | 0 | 15.5242 | 1.5457 | 0
72 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1.5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.4919 | 0 | 0 | 15.3472 | 4.5139 | 0 | 14.9866 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1.5 | 8 | 15.0538 | 0 | 0 | 16.1458 | 0 | 0 | 20.5645 | 11.0887 | 0 | 28.2639 | 14.4444 | 4.5139 | 36.4919 | 24.7312 | 10.0806 | 41.4583 | 29.8611 | 10.4861 | 44.3548 | 24.664 | 10.2823 | 43.6156 | 17.4731 | 10.6855 | 25.4861 | 16.1806 | 7.0833 | 15.3226 | 0 | 0 | 5.7639 | 0 | 0 | 13.5753 | 0 | 0
72 | 1.5 | 9 | 18.6828 | 0 | 0 | 24.2636 | 12.2075 | 0 | 29.9731 | 12.9704 | 0 | 47.0139 | 30.2778 | 13.4722 | 51.8817 | 37.7688 | 24.664 | 57.2222 | 46.3194 | 28.125 | 62.836 | 42.6747 | 22.1102 | 55.1747 | 36.4247 | 26.9489 | 39.0278 | 26.1806 | 12.4306 | 24.0591 | 9.6774 | 0 | 11.6667 | 0 | 0 | 18.1452 | 10.2823 | 0
72 | 1.5 | 10 | 21.5726 | 6.0484 | 0 | 27.2296 | 15.3274 | 0 | 33.4677 | 19.8253 | 0.94086 | 60.5556 | 36.875 | 25.6944 | 61.6263 | 48.0511 | 33.6694 | 66.0417 | 55 | 41.0417 | 73.5887 | 56.9892 | 39.4489 | 62.9704 | 45.0269 | 36.2231 | 51.1111 | 37.0833 | 21.3889 | 26.0081 | 13.4409 | 3.1586 | 16.3889 | 7.6389 | 0 | 20.9677 | 11.1559 | 0
72 | 1.5 | 11 | 22.7151 | 8.6022 | 0 | 31.1756 | 16.9643 | 0 | 42.7419 | 20.2285 | 11.4247 | 66.3194 | 44.0972 | 30.0694 | 66.5995 | 51.2769 | 41.4651 | 74.5139 | 60.8333 | 47.2222 | 82.1909 | 61.8952 | 48.3871 | 70.6989 | 56.586 | 41.3978 | 55.5556 | 42.5 | 25.3472 | 28.293 | 15.457 | 6.8548 | 18.75 | 10.2083 | 0 | 21.7742 | 11.3575 | 0
72 | 1.5 | 12 | 22.7151 | 8.6022 | 0 | 31.1756 | 16.9643 | 0 | 42.8763 | 21.3038 | 11.4919 | 66.4583 | 45.7639 | 31.8056 | 67.4731 | 56.3844 | 45.4301 | 75.1389 | 61.1806 | 47.5694 | 82.2581 | 62.0968 | 49.664 | 73.9247 | 59.0726 | 43.75 | 56.7361 | 42.7083 | 25.3472 | 30.0403 | 15.457 | 6.8548 | 18.75 | 10.2778 | 0 | 21.7742 | 11.4247 | 0
72 | 1.5 | 15 | 22.7151 | 8.6022 | 0 | 31.1756 | 16.9643 | 0 | 43.0108 | 22.379 | 11.4919 | 66.5278 | 45.8333 | 31.875 | 70.2957 | 56.5188 | 45.5645 | 75.2778 | 61.25 | 47.6389 | 83.3333 | 62.0968 | 49.8656 | 73.9247 | 59.1398 | 43.8172 | 56.7361 | 42.7083 | 25.4167 | 30.1075 | 15.457 | 6.8548 | 18.8889 | 10.2778 | 0 | 21.7742 | 11.4247 | 0
72 | 1.5 | 20 | 22.7151 | 8.6022 | 0 | 31.1756 | 16.9643 | 0 | 43.0108 | 22.379 | 11.4919 | 66.5278 | 45.8333 | 31.875 | 70.2957 | 56.5188 | 45.5645 | 75.2778 | 61.25 | 47.6389 | 83.3333 | 62.0968 | 49.8656 | 73.9247 | 59.1398 | 43.8172 | 56.7361 | 42.7083 | 25.4167 | 30.1075 | 15.457 | 6.8548 | 18.8889 | 10.2778 | 0 | 21.7742 | 11.4247 | 0
72 | 1.5 | 25 | 22.7151 | 8.6022 | 0 | 31.1756 | 16.9643 | 0 | 43.0108 | 22.379 | 11.4919 | 66.5278 | 45.8333 | 31.875 | 70.2957 | 56.5188 | 45.5645 | 75.2778 | 61.25 | 47.6389 | 83.3333 | 62.0968 | 49.8656 | 73.9247 | 59.1398 | 43.8172 | 56.7361 | 42.7083 | 25.4167 | 30.1075 | 15.457 | 6.8548 | 18.8889 | 10.2778 | 0 | 21.7742 | 11.4247 | 0
72 | 1.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1.75 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1.75 | 6 | 0 | 0 | 0 | 0.79023 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.4919 | 0 | 0 | 15.3472 | 4.5139 | 0 | 14.9866 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1.75 | 8 | 15.3898 | 0 | 0 | 16.369 | 2.4425 | 0 | 21.5054 | 11.0887 | 0 | 28.4722 | 14.5139 | 7.2222 | 36.4919 | 26.4785 | 11.9624 | 41.5972 | 29.8611 | 17.5 | 44.7581 | 24.664 | 10.4839 | 44.086 | 22.3118 | 10.6855 | 26.3889 | 16.875 | 7.0833 | 15.3226 | 0 | 0 | 10 | 0 | 0 | 15.0538 | 0 | 0
72 | 1.75 | 9 | 19.1532 | 3.629 | 0 | 25.8621 | 12.5718 | 0 | 31.1828 | 13.1048 | 0 | 48.125 | 30.5556 | 15.2083 | 56.6532 | 40.9274 | 26.2097 | 60.2778 | 49.7917 | 29.0972 | 63.4409 | 44.5565 | 22.2446 | 60.0134 | 43.75 | 29.9059 | 40 | 28.0556 | 12.4306 | 24.328 | 11.2231 | 0 | 12.6389 | 1.25 | 0 | 21.371 | 10.8871 | 0
72 | 1.75 | 10 | 24.8656 | 11.7608 | 0 | 36.1607 | 21.2054 | 0 | 40.3898 | 22.5134 | 10.4839 | 64.8611 | 43.4722 | 27.5694 | 65.3226 | 55.1075 | 44.6909 | 75.2778 | 62.8472 | 45.2083 | 80.4435 | 60.2151 | 40.5242 | 70.6317 | 52.3522 | 39.7849 | 53.125 | 41.5278 | 24.5833 | 27.8898 | 18.0108 | 7.8629 | 20.9028 | 11.0417 | 0 | 29.5027 | 12.164 | 0
72 | 1.75 | 11 | 31.25 | 13.7097 | 0 | 42.8571 | 26.4727 | 11.8304 | 48.5215 | 33.871 | 14.1801 | 71.6667 | 55.2083 | 35.625 | 75.672 | 66.7339 | 49.5296 | 81.3889 | 72.7778 | 55.9028 | 90.8602 | 72.6478 | 59.8118 | 79.0323 | 66.8011 | 49.9328 | 60.9722 | 46.3194 | 31.875 | 35.6183 | 20.9005 | 12.0296 | 30.0694 | 16.9444 | 0 | 31.586 | 13.6425 | 1.6801
72 | 1.75 | 12 | 31.3844 | 15.9274 | 0 | 45.8359 | 26.6933 | 12.423 | 49.5296 | 36.4247 | 18.6828 | 75.2083 | 58.125 | 41.875 | 81.922 | 73.3871 | 65.457 | 82.6389 | 76.5278 | 61.875 | 93.0108 | 82.8629 | 63.1048 | 82.7957 | 70.2957 | 54.5699 | 66.4583 | 51.875 | 37.6389 | 39.3145 | 24.5968 | 13.8441 | 33.6111 | 17.0139 | 10.4167 | 34.6774 | 14.3817 | 1.8817
72 | 1.75 | 15 | 31.3844 | 16.5995 | 0 | 46.0591 | 26.7678 | 12.423 | 49.8656 | 37.3656 | 22.4462 | 75.5556 | 58.5417 | 43.8889 | 84.6774 | 74.1935 | 65.9274 | 83.6111 | 77.6389 | 66.7361 | 93.2796 | 83.0645 | 63.7769 | 82.9973 | 73.1183 | 57.5941 | 70.625 | 53.4722 | 38.1944 | 39.6505 | 26.4785 | 14.0457 | 34.1667 | 17.1528 | 10.4861 | 34.8118 | 14.8522 | 3.8306
72 | 1.75 | 20 | 31.3844 | 16.5995 | 0 | 46.0591 | 26.7678 | 12.423 | 49.8656 | 37.3656 | 22.4462 | 75.5556 | 58.5417 | 43.8889 | 84.6774 | 74.664 | 65.9274 | 83.6111 | 77.6389 | 66.7361 | 93.2796 | 83.0645 | 63.7769 | 82.9973 | 73.1183 | 57.5941 | 70.625 | 53.4722 | 38.1944 | 39.6505 | 26.4785 | 14.0457 | 34.1667 | 17.1528 | 10.4861 | 34.8118 | 14.8522 | 3.8306
72 | 1.75 | 25 | 31.3844 | 16.5995 | 0 | 46.0591 | 26.7678 | 12.423 | 49.8656 | 37.3656 | 22.4462 | 75.5556 | 58.5417 | 43.8889 | 84.6774 | 74.664 | 65.9274 | 83.6111 | 77.6389 | 66.7361 | 93.2796 | 83.0645 | 63.7769 | 82.9973 | 73.1183 | 57.5941 | 70.625 | 53.4722 | 38.1944 | 39.6505 | 26.4785 | 14.0457 | 34.1667 | 17.1528 | 10.4861 | 34.8118 | 14.8522 | 3.8306
72 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2 | 6 | 0 | 0 | 0 | 0.79023 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.4919 | 2.3522 | 0 | 15.3472 | 4.5139 | 0 | 14.9866 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2 | 8 | 15.5242 | 0 | 0 | 16.369 | 7.3661 | 0 | 21.5054 | 11.0887 | 0 | 28.4722 | 14.5139 | 7.3611 | 36.6263 | 26.4785 | 11.9624 | 41.8056 | 30.4167 | 17.8472 | 45.0269 | 24.664 | 10.4839 | 44.086 | 22.3118 | 10.6855 | 26.5972 | 17.2222 | 7.0833 | 15.3226 | 0.067204 | 0 | 10.0694 | 0 | 0 | 15.3226 | 0 | 0
72 | 2 | 9 | 20.6317 | 3.629 | 0 | 26.5805 | 13.2364 | 0 | 31.5188 | 14.3817 | 0 | 49.1667 | 30.625 | 20.7639 | 56.9892 | 41.1962 | 26.6129 | 60.4167 | 50.9028 | 29.1667 | 64.0457 | 44.6909 | 22.2446 | 60.0806 | 45.2285 | 29.9059 | 41.7361 | 29.3056 | 12.4306 | 24.3952 | 13.2392 | 0 | 15.625 | 2.7778 | 0 | 25.4032 | 11.0215 | 0
72 | 2 | 10 | 31.25 | 12.2312 | 0 | 39.8835 | 25.8185 | 0 | 43.9516 | 24.1263 | 11.828 | 66.5972 | 46.25 | 30.2778 | 67.8091 | 57.0565 | 46.1022 | 76.3194 | 64.0972 | 45.5556 | 81.0484 | 61.3575 | 43.3468 | 73.9919 | 54.7043 | 42.0027 | 53.9583 | 42.9167 | 24.7222 | 28.8306 | 21.9086 | 7.8629 | 25.2083 | 13.8194 | 0 | 34.879 | 14.1801 | 0
72 | 2 | 11 | 34.4758 | 18.0108 | 0 | 47.9911 | 30.9934 | 12.6488 | 56.3844 | 42.1371 | 20.5645 | 75.3472 | 58.6806 | 39.9306 | 81.7876 | 68.2796 | 60.0134 | 88.75 | 80.5556 | 59.6528 | 93.414 | 75.5376 | 62.7016 | 82.0565 | 70.6317 | 58.5349 | 64.2361 | 54.2361 | 34.375 | 41.7339 | 26.0081 | 14.3145 | 33.8194 | 19.9306 | 0 | 37.7016 | 20.7661 | 1.6801
72 | 2 | 12 | 37.836 | 23.7231 | 0 | 55.5804 | 38.1696 | 14.042 | 63.2392 | 44.8925 | 26.8817 | 81.5972 | 64.0972 | 50.5556 | 88.9113 | 82.2581 | 69.8253 | 90.3472 | 83.3333 | 75.3472 | 96.1694 | 89.3145 | 73.8575 | 87.4328 | 76.8817 | 65.121 | 74.3056 | 58.1944 | 43.125 | 49.5296 | 31.5188 | 16.3306 | 38.5417 | 25.4167 | 12.2222 | 40.1882 | 28.293 | 2.0161
72 | 2 | 15 | 38.8441 | 26.2769 | 9.207 | 55.878 | 41.2202 | 14.4807 | 65.9274 | 47.7151 | 28.8978 | 83.5417 | 68.3333 | 54.4444 | 91.5323 | 84.8118 | 72.9839 | 91.3889 | 84.7222 | 78.4028 | 96.707 | 89.8522 | 79.5699 | 91.1962 | 78.4946 | 72.4462 | 75.2778 | 63.0556 | 45.5556 | 54.8387 | 39.5161 | 24.2608 | 42.8472 | 30 | 12.3611 | 44.086 | 29.0995 | 11.4247
72 | 2 | 20 | 38.8441 | 26.2769 | 9.207 | 55.878 | 41.2202 | 14.4807 | 65.9274 | 47.7151 | 28.8978 | 83.5417 | 68.3333 | 54.4444 | 91.5323 | 84.8118 | 72.9839 | 91.3889 | 84.7222 | 78.4028 | 96.707 | 89.8522 | 79.7043 | 91.1962 | 78.4946 | 72.4462 | 75.2778 | 63.0556 | 45.5556 | 54.8387 | 39.5161 | 24.2608 | 42.8472 | 30 | 12.3611 | 44.086 | 29.0995 | 11.4247
72 | 2 | 25 | 38.8441 | 26.2769 | 9.207 | 55.878 | 41.2202 | 14.4807 | 65.9274 | 47.7151 | 28.8978 | 83.5417 | 68.3333 | 54.4444 | 91.5323 | 84.8118 | 72.9839 | 91.3889 | 84.7222 | 78.4028 | 96.707 | 89.8522 | 79.7043 | 91.1962 | 78.4946 | 72.4462 | 75.2778 | 63.0556 | 45.5556 | 54.8387 | 39.5161 | 24.2608 | 42.8472 | 30 | 12.3611 | 44.086 | 29.0995 | 11.4247
72 | 2.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2.25 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2.25 | 6 | 0 | 0 | 0 | 0.79023 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.6263 | 2.3522 | 0 | 15.3472 | 4.5139 | 0 | 14.9866 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2.25 | 8 | 15.5242 | 0 | 0 | 17.8212 | 7.5149 | 0 | 21.5054 | 11.0887 | 0 | 28.5417 | 17.2917 | 7.3611 | 36.6263 | 26.4785 | 12.0968 | 41.8056 | 31.25 | 18.4028 | 45.2957 | 24.664 | 10.4839 | 44.086 | 22.3118 | 10.6855 | 26.5972 | 17.2222 | 7.0833 | 15.3226 | 3.8978 | 0 | 10.0694 | 0 | 0 | 15.5914 | 0 | 0
72 | 2.25 | 9 | 20.9677 | 7.4597 | 0 | 26.5805 | 13.2364 | 0 | 31.8548 | 14.3817 | 0 | 50.0694 | 30.625 | 20.9722 | 56.9892 | 41.8011 | 26.6801 | 60.4167 | 51.0417 | 30.9722 | 64.1801 | 44.8253 | 22.2446 | 60.4167 | 45.4973 | 29.9731 | 41.9444 | 29.375 | 12.7083 | 24.3952 | 13.6425 | 0 | 15.625 | 2.7778 | 0 | 25.4704 | 11.0215 | 0
72 | 2.25 | 10 | 31.7876 | 16.8011 | 0 | 41.6692 | 25.8185 | 0 | 44.086 | 26.6129 | 12.9032 | 69.1667 | 50.4167 | 31.8056 | 67.8091 | 58.1989 | 46.7742 | 77.1528 | 65.3472 | 48.9583 | 81.4516 | 61.8952 | 48.6559 | 74.4624 | 55.3091 | 42.0027 | 55.1389 | 43.5417 | 24.7917 | 31.25 | 22.043 | 7.8629 | 26.4583 | 14.1667 | 4.7222 | 35.0806 | 14.3817 | 0
72 | 2.25 | 11 | 40.121 | 20.9677 | 0 | 54.7619 | 31.5784 | 13.0208 | 58.1989 | 45.9677 | 23.5887 | 77.8472 | 64.5833 | 49.0278 | 84.543 | 68.4812 | 60.8871 | 89.5833 | 81.0417 | 62.9861 | 94.9597 | 80.9812 | 67.4731 | 83.1989 | 74.1263 | 59.4086 | 65.1389 | 55.9722 | 36.0417 | 43.1452 | 26.8817 | 15.457 | 38.8194 | 25.625 | 10.2778 | 38.3737 | 23.2527 | 6.6532
72 | 2.25 | 12 | 46.1694 | 30.7124 | 8.9382 | 63.5417 | 45.451 | 21.2054 | 71.1694 | 51.6801 | 32.9973 | 87.5 | 74.1667 | 58.75 | 92.7419 | 85.0134 | 72.2446 | 91.6667 | 86.5972 | 80.2083 | 97.5134 | 91.2634 | 81.4516 | 89.8522 | 83.0645 | 70.9677 | 76.25 | 63.5417 | 47.4306 | 57.0565 | 40.2554 | 22.1102 | 47.4306 | 30.5556 | 15.1389 | 43.078 | 29.5699 | 11.4919
72 | 2.25 | 15 | 52.4194 | 34.879 | 19.1532 | 65.1042 | 53.5714 | 24.256 | 79.9059 | 60.4839 | 40.1882 | 92.3611 | 80.625 | 64.6528 | 95.8333 | 90.3226 | 80.8468 | 94.0972 | 91.6667 | 84.1667 | 98.7231 | 94.7581 | 87.164 | 93.8844 | 85.8199 | 77.3522 | 80.9722 | 73.2639 | 57.3611 | 67.4059 | 52.3522 | 31.8548 | 57.5694 | 39.5833 | 23.2639 | 52.4866 | 36.828 | 16.0618
72 | 2.25 | 20 | 52.4866 | 34.879 | 19.1532 | 65.1042 | 53.5714 | 24.256 | 80.1075 | 60.8199 | 40.1882 | 92.3611 | 80.6944 | 64.6528 | 95.8333 | 90.457 | 80.8468 | 94.7222 | 91.6667 | 84.1667 | 98.7231 | 94.7581 | 87.164 | 93.8844 | 85.8199 | 77.4194 | 81.0417 | 73.2639 | 57.3611 | 67.5403 | 52.4194 | 31.922 | 57.7778 | 40.1389 | 23.3333 | 52.4866 | 36.828 | 16.0618
72 | 2.25 | 25 | 52.4866 | 34.879 | 19.1532 | 65.1042 | 53.5714 | 24.256 | 80.1075 | 60.8199 | 40.1882 | 92.3611 | 80.6944 | 64.6528 | 95.8333 | 90.457 | 80.8468 | 94.7222 | 91.6667 | 84.1667 | 98.7231 | 94.7581 | 87.164 | 93.8844 | 85.8199 | 77.4194 | 81.0417 | 73.2639 | 57.3611 | 67.5403 | 52.4194 | 31.922 | 57.7778 | 40.1389 | 23.3333 | 52.4866 | 36.828 | 16.0618
72 | 2.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2.5 | 6 | 0 | 0 | 0 | 0.79023 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.6263 | 2.3522 | 0 | 15.3472 | 4.5139 | 0 | 14.9866 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2.5 | 8 | 15.5242 | 0 | 0 | 17.8212 | 7.5149 | 0 | 21.5054 | 11.0887 | 0 | 28.5417 | 17.2917 | 7.3611 | 36.6263 | 26.4785 | 12.2984 | 41.8056 | 31.25 | 18.4028 | 45.2957 | 24.664 | 10.4839 | 44.086 | 22.3118 | 10.6855 | 26.5972 | 17.2222 | 7.0833 | 15.3226 | 3.8978 | 0 | 10.0694 | 0 | 0 | 15.9274 | 0 | 0
72 | 2.5 | 9 | 21.2366 | 7.4597 | 0 | 26.5805 | 13.244 | 0 | 32.4597 | 14.3817 | 0 | 50.4861 | 30.7639 | 23.3333 | 56.9892 | 42.2043 | 26.6801 | 60.4167 | 51.0417 | 30.9722 | 64.1801 | 44.8253 | 22.2446 | 60.6183 | 45.5645 | 29.9731 | 42.0833 | 29.4444 | 12.8472 | 24.3952 | 13.6425 | 0 | 15.6944 | 4.3056 | 0 | 25.6048 | 11.0215 | 0
72 | 2.5 | 10 | 33.3333 | 17.0699 | 0 | 41.6692 | 25.8185 | 0 | 44.086 | 27.0833 | 13.0376 | 69.5139 | 52.2222 | 33.0556 | 68.078 | 58.871 | 47.1774 | 77.7778 | 67.3611 | 49.2361 | 81.5188 | 64.0457 | 48.8575 | 74.5296 | 55.5108 | 42.0027 | 55.7639 | 43.8194 | 24.7917 | 32.1237 | 22.1774 | 7.8629 | 26.5278 | 14.1667 | 4.7917 | 35.2151 | 14.3817 | 0
72 | 2.5 | 11 | 41.8011 | 22.043 | 0 | 55.6548 | 31.7272 | 13.4673 | 58.7366 | 46.1022 | 23.7231 | 79.9306 | 66.8056 | 50.2083 | 85.4167 | 69.2204 | 60.9543 | 90.1389 | 82.6389 | 66.1806 | 95.6317 | 84.879 | 67.6075 | 83.5349 | 74.664 | 60.8871 | 66.5278 | 56.7361 | 36.1111 | 48.7903 | 28.7634 | 16.5323 | 39.0972 | 25.6944 | 10.8333 | 39.7177 | 23.4543 | 6.8548
72 | 2.5 | 12 | 49.1263 | 32.6613 | 10.6183 | 67.9315 | 47.5267 | 21.875 | 73.3199 | 54.5699 | 33.0645 | 88.6806 | 75.0694 | 61.25 | 93.9516 | 86.8952 | 77.2177 | 94.375 | 88.75 | 81.6667 | 98.9247 | 93.75 | 81.9892 | 92.6747 | 84.2742 | 73.6559 | 78.8194 | 64.3056 | 48.2639 | 59.0054 | 40.8602 | 24.328 | 49.3056 | 31.6667 | 17.9167 | 44.8925 | 33.871 | 13.4409
72 | 2.5 | 15 | 60.6855 | 44.4892 | 23.9919 | 75.8185 | 58.7054 | 25.9673 | 84.7446 | 72.5134 | 45.2957 | 95.7639 | 86.3194 | 77.5 | 98.0511 | 95.4973 | 88.5753 | 96.5278 | 93.1944 | 88.75 | 100 | 98.1183 | 91.7339 | 97.6478 | 90.9946 | 81.0484 | 88.8889 | 77.5694 | 65.7639 | 76.0081 | 58.4005 | 44.2204 | 62.2917 | 46.4583 | 25.625 | 61.2903 | 44.6909 | 23.6559
72 | 2.5 | 20 | 61.828 | 44.8253 | 23.9919 | 76.1648 | 58.7054 | 26.0417 | 84.8118 | 72.5134 | 45.2957 | 95.7639 | 86.3194 | 77.5 | 98.3871 | 95.6989 | 89.4489 | 96.5278 | 93.3333 | 88.75 | 100 | 98.1855 | 91.9355 | 97.6478 | 91.1962 | 81.0484 | 88.8889 | 77.8472 | 65.7639 | 76.3441 | 59.1398 | 45.7661 | 62.4306 | 46.5278 | 29.7917 | 61.5591 | 44.6909 | 23.6559
72 | 2.5 | 25 | 61.828 | 44.8253 | 23.9919 | 76.1648 | 58.7054 | 26.0417 | 84.8118 | 72.5134 | 45.2957 | 95.7639 | 86.3194 | 77.5 | 98.3871 | 95.6989 | 89.4489 | 96.5278 | 93.3333 | 88.75 | 100 | 98.1855 | 91.9355 | 97.6478 | 91.1962 | 81.0484 | 88.8889 | 77.8472 | 65.7639 | 76.3441 | 59.1398 | 45.7661 | 62.4306 | 46.5278 | 29.7917 | 61.5591 | 44.6909 | 23.6559
72 | 2.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2.75 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2.75 | 6 | 0 | 0 | 0 | 0.79023 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.6263 | 2.3522 | 0 | 15.3472 | 4.5139 | 0 | 14.9866 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2.75 | 8 | 15.5242 | 0 | 0 | 17.8212 | 7.5149 | 0 | 21.5054 | 11.0887 | 0 | 28.5417 | 17.2917 | 7.3611 | 36.6263 | 26.4785 | 12.2984 | 41.8056 | 31.25 | 18.4028 | 45.2957 | 24.664 | 10.4839 | 44.086 | 22.3118 | 10.6855 | 26.5972 | 17.2222 | 7.0833 | 15.3226 | 3.8978 | 0 | 10.0694 | 0 | 0 | 15.9274 | 0 | 0
72 | 2.75 | 9 | 21.371 | 8.871 | 0 | 27.8633 | 13.244 | 0 | 32.5941 | 14.3817 | 0 | 50.5556 | 30.9722 | 23.6111 | 56.9892 | 42.2043 | 26.6801 | 60.4167 | 51.0417 | 30.9722 | 64.1801 | 44.8253 | 22.2446 | 60.6183 | 45.5645 | 29.9731 | 42.0833 | 29.4444 | 13.0556 | 24.3952 | 13.6425 | 0 | 15.6944 | 6.25 | 0 | 25.7392 | 11.0215 | 0
72 | 2.75 | 10 | 34.207 | 17.1371 | 0 | 42.8597 | 26.4881 | 6.8452 | 44.086 | 27.0833 | 13.0376 | 69.5139 | 52.4306 | 33.3333 | 68.2796 | 58.871 | 47.3118 | 77.9167 | 67.5 | 49.2361 | 81.5188 | 64.3145 | 48.8575 | 74.5296 | 55.6452 | 42.0027 | 55.8333 | 43.9583 | 24.7917 | 32.3253 | 23.2527 | 7.8629 | 26.9444 | 14.1667 | 4.8611 | 35.2151 | 14.3817 | 0
72 | 2.75 | 11 | 42.1371 | 22.1102 | 2.2177 | 56.0268 | 39.3576 | 14.0625 | 58.871 | 46.1022 | 23.7231 | 80.2083 | 67.2222 | 52.5694 | 85.4167 | 69.8925 | 60.9543 | 90.4167 | 82.7778 | 66.3194 | 95.6317 | 85.0134 | 67.6075 | 83.6694 | 75.336 | 61.0887 | 66.8056 | 57.4306 | 36.1111 | 49.2608 | 28.7634 | 18.2796 | 40.1389 | 28.2639 | 10.9028 | 40.8602 | 23.7231 | 6.8548
72 | 2.75 | 12 | 50 | 33.9382 | 13.8441 | 68.006 | 50.8185 | 22.247 | 73.6559 | 54.8387 | 34.1398 | 90.3472 | 75.3472 | 61.6667 | 94.2204 | 88.2392 | 77.2849 | 94.7917 | 90.0694 | 81.7361 | 99.1263 | 93.8844 | 84.879 | 92.9435 | 84.4758 | 74.5296 | 79.3056 | 65.8333 | 48.75 | 59.207 | 41.4651 | 26.1425 | 52.6389 | 33.9583 | 17.9861 | 49.0591 | 34.2742 | 15.0538
72 | 2.75 | 15 | 69.7581 | 48.5215 | 34.0054 | 79.9851 | 65.253 | 37.5 | 87.5 | 76.8145 | 56.8548 | 96.6667 | 91.25 | 83.8194 | 99.2608 | 97.5134 | 91.9355 | 98.4722 | 95.4861 | 91.6667 | 100 | 98.9919 | 94.4892 | 99.328 | 94.8925 | 86.2231 | 92.2917 | 83.75 | 71.0417 | 80.8468 | 65.121 | 53.8306 | 72.2222 | 57.0833 | 35.625 | 69.4892 | 49.5296 | 30.5108
72 | 2.75 | 20 | 70.2285 | 51.4113 | 35.6183 | 81.014 | 66.6744 | 44.5685 | 87.9704 | 77.1505 | 56.922 | 96.9444 | 93.4722 | 84.2361 | 99.3952 | 97.8495 | 92.4731 | 98.4722 | 95.4861 | 92.2222 | 100 | 98.9919 | 94.5565 | 99.328 | 95.1613 | 86.2903 | 92.2917 | 85.2083 | 71.1111 | 82.3925 | 67.2715 | 54.9731 | 73.8194 | 58.0556 | 38.3333 | 71.3038 | 50.8065 | 30.578
72 | 2.75 | 25 | 70.2285 | 51.4113 | 35.6183 | 81.014 | 66.6744 | 44.5685 | 87.9704 | 77.1505 | 56.922 | 96.9444 | 93.4722 | 84.2361 | 99.3952 | 97.8495 | 92.4731 | 98.4722 | 95.4861 | 92.2222 | 100 | 98.9919 | 94.5565 | 99.328 | 95.1613 | 86.2903 | 92.2917 | 85.2083 | 71.1111 | 82.4597 | 67.2715 | 54.9731 | 73.8194 | 58.0556 | 38.3333 | 71.3038 | 50.8065 | 30.578
72 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3 | 6 | 0 | 0 | 0 | 0.79023 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.6263 | 2.3522 | 0 | 15.3472 | 4.5139 | 0 | 14.9866 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3 | 8 | 15.5242 | 0 | 0 | 17.8212 | 7.5149 | 0 | 21.5054 | 11.0887 | 0 | 28.5417 | 17.2917 | 7.3611 | 36.6263 | 26.4785 | 12.2984 | 41.8056 | 31.25 | 18.4028 | 45.2957 | 24.664 | 10.4839 | 44.086 | 22.3118 | 10.6855 | 26.5972 | 17.2222 | 7.0833 | 15.3226 | 3.8978 | 0 | 10.0694 | 0 | 0 | 15.9274 | 0 | 0
72 | 3 | 9 | 21.371 | 10.2151 | 0 | 27.8633 | 13.244 | 0 | 32.5941 | 14.3817 | 0 | 50.5556 | 30.9722 | 23.6111 | 56.9892 | 42.2043 | 26.6801 | 60.4167 | 51.0417 | 30.9722 | 64.1801 | 44.8253 | 22.2446 | 60.6183 | 45.5645 | 29.9731 | 42.0833 | 29.4444 | 13.6111 | 24.3952 | 13.6425 | 0 | 15.6944 | 8.2639 | 0 | 25.7392 | 11.0215 | 0
72 | 3 | 10 | 34.3414 | 17.1371 | 0 | 42.8597 | 26.4881 | 6.8452 | 44.086 | 27.0833 | 13.0376 | 69.5139 | 52.4306 | 33.4722 | 68.2796 | 58.871 | 47.379 | 78.125 | 67.5694 | 49.2361 | 81.5188 | 64.3145 | 48.8575 | 74.5296 | 55.6452 | 42.0027 | 55.8333 | 44.9306 | 24.7917 | 32.4597 | 23.2527 | 7.8629 | 26.9444 | 14.1667 | 4.9306 | 35.2151 | 14.3817 | 0
72 | 3 | 11 | 42.4059 | 22.1102 | 2.2849 | 56.8632 | 40.0759 | 14.2113 | 59.0054 | 46.1022 | 23.7903 | 80.2083 | 68.125 | 53.1944 | 85.4167 | 69.8925 | 60.9543 | 90.4861 | 82.7778 | 66.3194 | 95.6317 | 85.0134 | 67.6075 | 83.6694 | 75.4032 | 61.0887 | 67.0139 | 57.5 | 36.1111 | 49.3952 | 30.9812 | 20.4301 | 41.875 | 28.3333 | 10.9028 | 42.0027 | 25.2688 | 6.8548
72 | 3 | 12 | 50.336 | 34.6102 | 13.9113 | 68.006 | 51.0417 | 22.247 | 74.1263 | 55.7796 | 35.8871 | 90.4167 | 77.0833 | 62.0139 | 94.4892 | 88.3065 | 77.4194 | 94.8611 | 91.6667 | 82.0139 | 99.1263 | 93.8844 | 84.9462 | 93.0108 | 84.543 | 74.7312 | 79.7222 | 66.1806 | 53.6806 | 59.543 | 41.5995 | 26.8145 | 52.6389 | 35.625 | 18.0556 | 51.2097 | 34.543 | 15.2554
72 | 3 | 15 | 72.379 | 54.3683 | 37.7688 | 85.8118 | 70.8205 | 49.3534 | 90.0538 | 79.3683 | 62.0296 | 98.4028 | 94.0972 | 85.9722 | 100 | 97.9839 | 94.6237 | 99.7917 | 97.6389 | 94.8611 | 100 | 99.9328 | 95.8333 | 99.664 | 97.379 | 89.3145 | 96.1806 | 86.7361 | 74.5833 | 81.586 | 69.2204 | 58.6694 | 76.875 | 63.0556 | 41.6667 | 71.1694 | 55.914 | 36.2903
72 | 3 | 20 | 72.9167 | 58.4005 | 41.4651 | 86.0273 | 73.7351 | 52.5606 | 92.6075 | 80.0403 | 65.7258 | 99.0278 | 94.6528 | 86.8056 | 100 | 99.1935 | 95.2285 | 99.8611 | 97.9167 | 95.1389 | 100 | 100 | 95.9005 | 99.7984 | 97.8495 | 90.5242 | 96.5278 | 88.6111 | 76.25 | 84.2742 | 73.7903 | 62.4328 | 77.9861 | 65.6944 | 46.3194 | 74.1263 | 59.9462 | 36.6935
72 | 3 | 25 | 72.9167 | 58.4005 | 41.4651 | 86.0273 | 73.7351 | 52.5606 | 92.6075 | 80.0403 | 65.7258 | 99.0278 | 94.6528 | 86.8056 | 100 | 99.1935 | 95.2285 | 99.8611 | 97.9167 | 95.1389 | 100 | 100 | 95.9005 | 99.7984 | 97.8495 | 90.5242 | 96.5278 | 88.6111 | 76.25 | 84.3414 | 73.7903 | 62.4328 | 77.9861 | 65.6944 | 46.3194 | 74.1263 | 59.9462 | 36.6935
72 | 3.25 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3.25 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3.25 | 6 | 0 | 0 | 0 | 0.79023 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.6263 | 2.3522 | 0 | 15.3472 | 4.5139 | 0 | 14.9866 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3.25 | 8 | 15.5242 | 0 | 0 | 17.8212 | 7.5149 | 0 | 21.5054 | 11.0887 | 0 | 28.5417 | 17.2917 | 7.3611 | 36.6263 | 26.4785 | 12.2984 | 41.8056 | 31.25 | 18.4028 | 45.2957 | 24.664 | 10.4839 | 44.086 | 22.3118 | 10.6855 | 26.5972 | 17.2222 | 7.0833 | 15.3226 | 3.8978 | 0 | 10.0694 | 0 | 0 | 15.9274 | 0 | 0
72 | 3.25 | 9 | 21.371 | 10.2151 | 0 | 27.8633 | 13.244 | 0 | 32.5941 | 14.3817 | 0 | 50.5556 | 30.9722 | 23.6111 | 56.9892 | 42.2043 | 26.6801 | 60.4167 | 51.0417 | 30.9722 | 64.1801 | 44.8253 | 22.2446 | 60.6183 | 45.5645 | 29.9731 | 42.0833 | 29.4444 | 13.6111 | 24.3952 | 13.6425 | 0 | 15.6944 | 8.2639 | 0 | 25.7392 | 11.0215 | 0
72 | 3.25 | 10 | 34.3414 | 17.3387 | 0 | 42.8597 | 26.4881 | 6.8452 | 44.086 | 27.0833 | 13.0376 | 69.5139 | 52.4306 | 33.4722 | 68.2796 | 58.871 | 47.379 | 78.125 | 67.5694 | 49.2361 | 81.5188 | 64.3145 | 48.8575 | 74.5296 | 55.6452 | 42.0027 | 55.8333 | 44.9306 | 24.7917 | 32.4597 | 23.2527 | 7.8629 | 26.9444 | 14.1667 | 4.9306 | 35.2151 | 14.3817 | 0
72 | 3.25 | 11 | 42.5403 | 22.1774 | 2.2849 | 57.1557 | 40.5788 | 14.2113 | 59.6102 | 46.1022 | 23.7903 | 80.2083 | 68.125 | 53.6806 | 85.4167 | 69.8925 | 60.9543 | 90.5556 | 82.7778 | 66.3194 | 95.6317 | 85.0134 | 67.6075 | 83.6694 | 75.4032 | 61.0887 | 67.1528 | 57.5 | 36.1111 | 49.3952 | 31.0484 | 20.4301 | 41.9444 | 28.3333 | 10.9028 | 42.2043 | 25.336 | 6.8548
72 | 3.25 | 12 | 50.6048 | 35.5511 | 13.9785 | 68.006 | 51.2649 | 22.247 | 75.8065 | 55.7796 | 35.8871 | 90.4861 | 78.1944 | 62.3611 | 94.6909 | 88.3065 | 77.4194 | 94.9306 | 91.875 | 82.1528 | 99.1263 | 93.8844 | 85.0134 | 93.0108 | 84.543 | 74.7312 | 79.7917 | 66.25 | 53.6806 | 59.6774 | 41.5995 | 26.8817 | 52.6389 | 35.625 | 18.125 | 52.7554 | 34.543 | 15.2554
72 | 3.25 | 15 | 74.1263 | 58.0645 | 40.6586 | 87.1408 | 74.5536 | 50.1437 | 93.5484 | 80.578 | 67.8763 | 98.9583 | 95.1389 | 89.7222 | 100 | 98.9919 | 96.5726 | 100 | 98.8194 | 95.3472 | 100 | 100 | 96.4382 | 100 | 98.9919 | 92.1371 | 96.875 | 88.2639 | 80.4167 | 83.2661 | 75.0672 | 59.4758 | 81.25 | 70.5556 | 43.75 | 76.9489 | 58.6694 | 40.5242
72 | 3.25 | 20 | 80.5108 | 67.8763 | 49.1263 | 87.6462 | 77.6786 | 56.5194 | 96.6398 | 82.5941 | 72.2446 | 99.7917 | 97.2917 | 92.9861 | 100 | 99.9328 | 97.4462 | 100 | 99.1667 | 96.1806 | 100 | 100 | 96.7742 | 100 | 99.328 | 94.8925 | 97.7778 | 91.1111 | 82.3611 | 95.2957 | 82.1237 | 69.4892 | 87.7083 | 74.2361 | 52.5694 | 83.3333 | 64.7177 | 42.4059
72 | 3.25 | 25 | 80.5108 | 67.8763 | 49.1263 | 87.6462 | 77.6786 | 56.5194 | 96.6398 | 82.5941 | 72.2446 | 99.7917 | 97.2917 | 92.9861 | 100 | 99.9328 | 97.4462 | 100 | 99.1667 | 96.1806 | 100 | 100 | 96.7742 | 100 | 99.328 | 94.8925 | 97.8472 | 91.1111 | 82.3611 | 95.2957 | 82.1237 | 69.4892 | 87.7083 | 74.2361 | 52.5694 | 83.3333 | 64.7177 | 42.4059
72 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3.5 | 6 | 0 | 0 | 0 | 0.79023 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.6263 | 2.3522 | 0 | 15.3472 | 4.5139 | 0 | 14.9866 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3.5 | 8 | 15.5242 | 0 | 0 | 17.8212 | 7.5149 | 0 | 21.5054 | 11.0887 | 0 | 28.5417 | 17.2917 | 7.3611 | 36.6263 | 26.4785 | 12.2984 | 41.8056 | 31.25 | 18.4028 | 45.2957 | 24.664 | 10.4839 | 44.086 | 22.3118 | 10.6855 | 26.5972 | 17.2222 | 7.0833 | 15.3226 | 3.8978 | 0 | 10.0694 | 0 | 0 | 15.9274 | 0 | 0
72 | 3.5 | 9 | 21.371 | 10.2151 | 0 | 27.8633 | 13.244 | 0 | 32.5941 | 14.3817 | 0 | 50.5556 | 30.9722 | 23.6111 | 56.9892 | 42.2043 | 26.6801 | 60.4167 | 51.0417 | 30.9722 | 64.1801 | 44.8253 | 22.2446 | 60.6183 | 45.5645 | 29.9731 | 42.0833 | 29.4444 | 13.6111 | 24.3952 | 13.6425 | 0 | 15.6944 | 8.2639 | 0 | 25.7392 | 11.0215 | 0
72 | 3.5 | 10 | 34.3414 | 17.3387 | 0 | 42.8597 | 26.4881 | 6.8452 | 44.086 | 27.0833 | 13.0376 | 69.5139 | 52.4306 | 33.4722 | 68.2796 | 58.871 | 47.379 | 78.125 | 67.5694 | 49.2361 | 81.5188 | 64.3145 | 48.8575 | 74.5296 | 55.6452 | 42.0027 | 55.8333 | 45 | 24.7917 | 32.4597 | 23.2527 | 8.6022 | 26.9444 | 14.1667 | 4.9306 | 35.2151 | 14.3817 | 0
72 | 3.5 | 11 | 42.5403 | 22.1774 | 2.2849 | 57.2301 | 40.7943 | 14.2113 | 59.6102 | 46.1022 | 23.7903 | 80.2083 | 68.125 | 53.6806 | 85.4167 | 69.8925 | 60.9543 | 90.5556 | 82.7778 | 66.3194 | 95.6317 | 85.0134 | 67.6075 | 83.6694 | 75.4032 | 61.0887 | 67.1528 | 57.5 | 36.1111 | 49.664 | 31.0484 | 20.4301 | 41.9444 | 28.6111 | 10.9028 | 42.2715 | 25.4032 | 6.8548
72 | 3.5 | 12 | 50.7392 | 35.5511 | 13.9785 | 68.006 | 51.7113 | 22.247 | 75.9409 | 55.7796 | 35.8871 | 90.5556 | 78.2639 | 63.125 | 94.7581 | 88.3065 | 77.4194 | 94.9306 | 91.875 | 82.2917 | 99.1263 | 93.8844 | 85.0806 | 93.0108 | 84.543 | 74.7312 | 79.8611 | 66.25 | 53.6806 | 59.8118 | 41.5995 | 27.0161 | 52.6389 | 36.3889 | 18.125 | 52.8898 | 34.543 | 15.2554
72 | 3.5 | 15 | 74.3952 | 60.9279 | 40.793 | 89.5833 | 75.9673 | 52.0833 | 94.0188 | 84.9462 | 68.8172 | 99.5833 | 96.6667 | 90.9722 | 100 | 99.4624 | 97.7823 | 100 | 99.1667 | 96.3194 | 100 | 100 | 97.1774 | 100 | 99.2608 | 94.3548 | 97.1528 | 89.1667 | 82.1528 | 88.172 | 78.5618 | 61.4247 | 84.1667 | 71.5972 | 45.4167 | 78.0242 | 60.0134 | 40.793
72 | 3.5 | 20 | 89.2473 | 68.9516 | 54.5027 | 93.2292 | 82.5097 | 58.5565 | 98.5887 | 87.7016 | 76.8145 | 100 | 99.0972 | 95.1389 | 100 | 100 | 98.8575 | 100 | 99.5139 | 96.8056 | 100 | 100 | 97.8495 | 100 | 100 | 96.0349 | 98.75 | 94.9306 | 86.3889 | 98.3871 | 84.2742 | 75.8737 | 91.7361 | 80.2083 | 61.1111 | 87.2312 | 69.2204 | 47.7151
72 | 3.5 | 25 | 89.2473 | 68.9516 | 54.5027 | 93.2292 | 82.5097 | 58.5565 | 98.5887 | 87.7016 | 76.8145 | 100 | 99.0972 | 95.1389 | 100 | 100 | 98.8575 | 100 | 99.5139 | 96.8056 | 100 | 100 | 97.8495 | 100 | 100 | 96.0349 | 98.75 | 94.9306 | 86.3889 | 98.3871 | 84.2742 | 75.8737 | 91.7361 | 80.2083 | 61.1111 | 87.2312 | 69.2204 | 47.7151
72 | 3.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3.75 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3.75 | 6 | 0 | 0 | 0 | 0.79023 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.6263 | 2.3522 | 0 | 15.3472 | 4.5139 | 0 | 14.9866 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3.75 | 8 | 15.5242 | 0 | 0 | 17.8212 | 7.5149 | 0 | 21.5054 | 11.0887 | 0 | 28.5417 | 17.2917 | 7.3611 | 36.6263 | 26.4785 | 12.2984 | 41.8056 | 31.25 | 18.4028 | 45.2957 | 24.664 | 10.4839 | 44.086 | 22.3118 | 10.6855 | 26.5972 | 17.2222 | 7.0833 | 15.3226 | 3.8978 | 0 | 10.0694 | 0 | 0 | 15.9274 | 0 | 0
72 | 3.75 | 9 | 21.371 | 10.2151 | 0 | 27.8633 | 13.244 | 0 | 32.5941 | 14.3817 | 0 | 50.5556 | 30.9722 | 23.6111 | 56.9892 | 42.2043 | 26.6801 | 60.4167 | 51.0417 | 30.9722 | 64.1801 | 44.8253 | 22.2446 | 60.6183 | 45.5645 | 29.9731 | 42.0833 | 29.4444 | 13.6111 | 24.3952 | 13.6425 | 0 | 15.6944 | 8.2639 | 0 | 25.7392 | 11.0215 | 0
72 | 3.75 | 10 | 34.3414 | 17.3387 | 0 | 42.8597 | 26.4881 | 6.8452 | 44.086 | 27.0833 | 13.0376 | 69.5139 | 52.4306 | 33.4722 | 68.2796 | 58.871 | 47.379 | 78.125 | 67.5694 | 49.2361 | 81.5188 | 64.3145 | 48.8575 | 74.5296 | 55.6452 | 42.0027 | 55.8333 | 45.0694 | 24.7917 | 32.4597 | 23.2527 | 8.6022 | 26.9444 | 14.1667 | 4.9306 | 35.2151 | 14.3817 | 0
72 | 3.75 | 11 | 42.5403 | 22.1774 | 2.2849 | 57.2301 | 41.0817 | 14.2113 | 59.6102 | 46.1022 | 23.7903 | 80.2083 | 68.125 | 53.6806 | 85.4167 | 69.8925 | 60.9543 | 90.5556 | 82.7778 | 66.3194 | 95.6317 | 85.0134 | 67.6075 | 83.6694 | 75.4032 | 61.0887 | 67.1528 | 57.5 | 36.1111 | 49.664 | 31.0484 | 20.4301 | 41.9444 | 28.6111 | 10.9028 | 42.2715 | 25.4032 | 6.8548
72 | 3.75 | 12 | 50.8737 | 35.5511 | 13.9785 | 68.006 | 51.7113 | 22.247 | 75.9409 | 55.7796 | 35.8871 | 90.5556 | 78.2639 | 63.125 | 94.8253 | 88.3065 | 77.4194 | 95 | 91.875 | 82.4306 | 99.1263 | 93.8844 | 85.1478 | 93.0108 | 84.9462 | 74.7312 | 79.9306 | 66.25 | 53.6806 | 59.879 | 41.5995 | 27.0833 | 52.6389 | 36.4583 | 18.125 | 52.957 | 34.543 | 15.2554
72 | 3.75 | 15 | 76.8817 | 61.3988 | 42.7419 | 90.3607 | 76.1905 | 52.5862 | 94.0188 | 85.9543 | 69.5565 | 99.7917 | 97.0139 | 91.1111 | 100 | 99.7312 | 98.1855 | 100 | 99.3056 | 97.1528 | 100 | 100 | 97.5134 | 100 | 99.4624 | 94.8925 | 97.1528 | 90.2778 | 83.6111 | 88.3065 | 78.8978 | 61.6935 | 85.2778 | 72.6389 | 47.5694 | 78.8978 | 61.1559 | 42.2043
72 | 3.75 | 20 | 90.0538 | 76.0081 | 58.9382 | 96.2798 | 85.509 | 67.9598 | 99.5296 | 91.6667 | 80.4435 | 100 | 99.4444 | 96.1806 | 100 | 100 | 99.5968 | 100 | 100 | 97.8472 | 100 | 100 | 98.5887 | 100 | 100 | 97.4462 | 99.6528 | 96.5278 | 89.5833 | 99.1263 | 88.9785 | 78.4274 | 94.5139 | 82.3611 | 66.9444 | 90.8602 | 75.6048 | 56.9892
72 | 3.75 | 25 | 90.0538 | 76.0081 | 58.9382 | 96.2798 | 85.509 | 67.9598 | 99.5296 | 91.7339 | 80.4435 | 100 | 99.5139 | 96.1806 | 100 | 100 | 99.5968 | 100 | 100 | 97.8472 | 100 | 100 | 98.7903 | 100 | 100 | 97.4462 | 99.6528 | 96.5972 | 89.5833 | 99.1935 | 89.4489 | 78.4274 | 94.5139 | 82.4306 | 66.9444 | 90.9946 | 75.6048 | 57.0565
72 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 4 | 6 | 0 | 0 | 0 | 0.79023 | 0 | 0 | 0 | 0 | 0 | 8.3333 | 0 | 0 | 11.6263 | 2.3522 | 0 | 15.3472 | 4.5139 | 0 | 14.9866 | 0.67204 | 0 | 12.7016 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 4 | 8 | 15.5242 | 0 | 0 | 17.8212 | 7.5149 | 0 | 21.5054 | 11.0887 | 0 | 28.5417 | 17.2917 | 7.3611 | 36.6263 | 26.4785 | 12.2984 | 41.8056 | 31.25 | 18.4028 | 45.2957 | 24.664 | 10.4839 | 44.086 | 22.3118 | 10.6855 | 26.5972 | 17.2222 | 7.0833 | 15.3226 | 3.8978 | 0 | 10.0694 | 0 | 0 | 15.9274 | 0 | 0
72 | 4 | 9 | 21.371 | 10.2151 | 0 | 27.8633 | 13.244 | 0 | 32.5941 | 14.3817 | 0 | 50.5556 | 30.9722 | 23.6111 | 56.9892 | 42.2043 | 26.6801 | 60.4167 | 51.0417 | 30.9722 | 64.1801 | 44.8253 | 22.2446 | 60.6183 | 45.5645 | 29.9731 | 42.0833 | 29.4444 | 13.6111 | 24.3952 | 13.6425 | 0 | 15.6944 | 8.2639 | 0 | 25.7392 | 11.0215 | 0
72 | 4 | 10 | 34.3414 | 17.3387 | 0 | 42.8597 | 26.4881 | 6.8452 | 44.086 | 27.0833 | 13.0376 | 69.5139 | 52.4306 | 33.4722 | 68.2796 | 58.871 | 47.379 | 78.125 | 67.5694 | 49.2361 | 81.5188 | 64.3145 | 48.8575 | 74.5296 | 55.6452 | 42.0027 | 55.8333 | 45.0694 | 24.7917 | 32.4597 | 23.2527 | 8.6022 | 26.9444 | 14.1667 | 4.9306 | 35.2151 | 14.3817 | 0
72 | 4 | 11 | 42.5403 | 22.1774 | 2.2849 | 57.2301 | 41.2972 | 14.2113 | 59.6102 | 46.1022 | 23.7903 | 80.2083 | 68.125 | 53.6806 | 85.4167 | 69.8925 | 60.9543 | 90.5556 | 82.7778 | 66.3194 | 95.6317 | 85.0134 | 67.6075 | 83.6694 | 75.4032 | 61.0887 | 67.1528 | 57.5 | 36.1111 | 49.664 | 31.0484 | 20.4301 | 41.9444 | 28.6111 | 10.9028 | 42.2715 | 25.4032 | 6.8548
72 | 4 | 12 | 50.9409 | 35.5511 | 13.9785 | 68.006 | 52.3373 | 22.247 | 75.9409 | 55.7796 | 35.8871 | 90.5556 | 78.2639 | 63.125 | 94.8253 | 88.3065 | 77.4194 | 95 | 91.875 | 82.4306 | 99.1263 | 93.8844 | 85.2151 | 93.0108 | 84.9462 | 74.7312 | 79.9306 | 66.25 | 53.6806 | 59.9462 | 41.5995 | 27.0833 | 52.6389 | 36.4583 | 18.125 | 52.957 | 34.543 | 15.2554
72 | 4 | 15 | 76.9489 | 63.1048 | 43.1452 | 90.5044 | 76.4881 | 52.9454 | 94.1532 | 87.0968 | 70.6989 | 99.7917 | 97.1528 | 91.3194 | 100 | 99.7984 | 98.3871 | 100 | 99.3056 | 97.3611 | 100 | 100 | 97.6478 | 100 | 99.5296 | 95.1613 | 97.2222 | 90.9722 | 83.75 | 88.7097 | 79.0995 | 61.828 | 85.9722 | 73.125 | 47.5694 | 79.0995 | 61.2903 | 43.2124
72 | 4 | 20 | 91.4651 | 80.578 | 63.3737 | 97.9911 | 89.2113 | 78.4483 | 99.9328 | 95.4301 | 82.8629 | 100 | 99.7917 | 96.875 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.3952 | 100 | 100 | 99.3952 | 100 | 98.125 | 91.0417 | 99.7984 | 91.3306 | 84.8118 | 97.8472 | 89.1667 | 75.4167 | 93.078 | 83.8038 | 64.1129
72 | 4 | 25 | 91.4651 | 82.1909 | 63.3737 | 97.9911 | 89.3601 | 78.4483 | 99.9328 | 95.4301 | 82.8629 | 100 | 99.8611 | 96.875 | 100 | 100 | 99.9328 | 100 | 100 | 99.0278 | 100 | 100 | 99.664 | 100 | 100 | 99.3952 | 100 | 98.125 | 91.1111 | 99.9328 | 92.4059 | 84.8118 | 97.8472 | 89.3056 | 75.4167 | 93.078 | 83.8038 | 64.1801