## Test plan Electric Machines
Test plan Electric Machines
Author
E.J. Schilpzand
Registration number
27.09.25X1 sub 01
Date
Sep. 17, 2025
Version
0.2.1
Status
Definitive
Section
HHNK PAO
Total Pages
40

## 1. Machine Test Document
Machine Test Requirements
Torque measurement or calculated (1)
Machine test performed with:
- torque measurement | X
- calculated torque
Variable Frequency Drive (VFD) (1)
Machine tests performed:
- without VFD
- with VFD from test bench | X
- with new VFD of end-user HHNK
Machine Testing Witnesses (1)
Witnesses machine testing of end-user HHNK:
- No
- Yes | X | (2 persons HHNK)
(1) : If not otherwise selected the preferred choice is: torque measurement, machine test with new HHNK VSD and test witnessed by HHNK.
Abbreviations in Test Plan
N.A. = Not Applicable
N.I. = Not Inspected
N.T. = Not Tested
This Test Plan has been drawn up for testing one electrical machine.
If multiple machines are supplied, copy the Test Plan and apply it repeatedly.

## 1.1 Project Information
1.1 Project |  |  | 1.4 Test location
Project name | Gemaal De Helsdeur |  | Company name
Pump number | P1 |  | Visiting address
Motor type |  |  | Postal address
Serial number |  |  | Telephone
Motor description |  |  | e-mail
Power |  | kW | Website
Speed | 79 | rpm | Order nr.
1.2 Manufacturer |  |  | 1.5 Customer
Company name |  |  | Company name
Visiting address |  |  | Visiting address
Postal address |  |  | Postal address
Telephone |  |  | Telephone
e-mail |  |  | e-mail
Website |  |  | Website
Order nr |  |  | Order nr.
1.3 Supplier |  |  | 1.6 End customer
Company name |  |  | Company name | Hoogheemraadschap Hollands Noorderkwartier (HHNK)
Visiting address |  |  | Visiting address | Stationsplein 136, 1703 WC Heerhugowaard, Nederland
Postal address |  |  | Postal address | Postbus 250, 1700 AG Heerhugowaard, Nederland
Telephone |  |  | Telephone | +31(0)72-582 8282
e-mail |  |  | e-mail | n.a.
Website |  |  | Website | www.hhnk.nl
Order nr. |  |  | Order nr.

## 1.2 Test approval
Function | Name and signature | Signature | Company | Place and Date
Electric machine measured by |  |  | Bakker
Electric machine test approved by supplier |  |  | Bakker
Electric machine test approved by tester of test location |  |  | DAC DirectDrives
Electric machine test approved by customer |  |  | BWM
Electric machine test approved by end customer |  |  | HHNK
Company stamp test location | Test Status
Not - approved Approved

## 2.1 Test Protocols
|  | Mandatory Tests IM | Mandatory Tests PM | IEC-34-1 | Test Sequence |  | previous test doc.
3.1 | Visual Inspection | X | X | R | 1 |  | 4.1
3.2 | Basic Tests | X | X | R | 2 |  | 4.2
3.3 | Insulation resistance (cold) | X | X | R | 3 |  | 4.3.1 +4.3
3.4 | Winding resistance method (cold) | X | X | R | 4 |  | 4.4
3.5 | Resistance measurement PT-100 (cold) | X | X | R | 5 |  | 4.4
3.6 | Resistance PTC stop (cold) | X | X | R | 6 |  | 8.1
3.7 | Resistance PTC warning (cold) | X | X | R | 7 |  | 8.2
3.8 | Insulation AC High Potential Test (AC HiPot) | X | X | R | 8 |  | 4.5.1 +4.5
3.9 | BEMF measurement (cold) | - | X | - | 9 | only in case of PM machine | 4.6
3.10 | Overspeed test | X | X | R | 10 |  | 4.7
3.11 | Temperature Rise Test ETD (cold & hot) | X | X | R | 11 |  | 4.12
3.12 | Temperature Rise Test Bearings (cold & hot) | X | X | R | 12 |  | 4.14
3.13 | Winding resistance method (hot) | X | X | R | 13 |  | 4.15
3.14 | Calculated winding temperature rise test | X | X | R | 14 |  | 4.13
3.15 | Load test | X | X | R | 15 |  | 4.9
3.16 | No-load test | X | X | R | 16 |  | 4.11
3.17 | Vibration test | X | X | R | 17 |  | 4.18
3.18 | Noise test | X | X | R | 18 |  | 4.19
3.19 | Locked rotor test | X | - | R | 19 | only in case of IM machine | 4.8
3.20 | BEMF measurement (hot) | - | X | - | 20 | only in case of PM machine | 4.16
3.21 | Insulation tests (hot) | X | X | R | 21 |  | 4.17
3.22 | Resistance measurement PT-100 (hot) | X | X | R | 22 |  | 4.4
-
(a) Mandatory Tests to perform are depending on machine type: IM = Induction Machine, PM = Permanent Magnet Machine (Surface Mounted);
(b) Non-Salient;
(c) X = Mandatory test that has been carried out, depents on IM or PM.
(d) IEC-34, refers to the comparable tests according to norm NEN EN IEC 60034-1, R = Routine Test, T=Type Test, - = not specified.

## 3.1.1 Visual Inspection
3.1.1.1 Check values nameplate
Check values nameplate | Imposed |  |  | Remarks | Pass | Fail | N.A. | N.I.
Fabricate
Type
Serial number
Voltage | 500 |  | V
Current | 0 |  | A
PF | 0.95 |  | - | 100% full load
Efficiency | 94 |  | % | 100% full load
Frequency | 0 |  | Hz
Power |  |  | kW
Speed | 79 |  | rpm
Connection | Y |  | -
Rated torque (full load) | 68500 |  | Nm
3.1.1.2 Check specifications
Check specifications | Imposed |  |  | Remarks | Pass | Fail | N.A. | N.I.
Frame material
Cooling medium | air
Cooling type |  | IC416 - TEFV - Totally Enclosed Force Ventilated (ventilated with independent fan)
Paint colour | RAL-1005
Honey Yellow
3.1.1.3 Check parts position
Check parts position | Imposed |  |  | Remarks | Pass | Fail | N.A. | N.I.
Main terminal box | drawing …..
Aux. terminal box | drawing …..
Heater | drawing …..
Cool Fan | drawing …..
Cool Fan Motor | drawing …..
Lubrication points | drawing …..
Vibration measuring points | drawing …..
Mounting arrangement | IM-3011 / IM-V1

## 3.1.2 Visual Inspection
3.1.2.1 Check dimensions
Check dimensions | Imposed | Remarks | Pass | Fail | N.A. | N.I.
Main terminal box | drawing …..
Main cable glands | drawing….
Aux. terminal box | drawing …..
Aux. cable glands | drawing….
Motor outer dimensions | drawing …..
Motor frame | drawing …..
Flange | drawing …..
Shaft coupling | drawing …..
Heater | drawing …..
Cool Fan | drawing …..
Cool Fan Motor | drawing …..
Lubrication points | drawing …..
3.1.2.2 Check housing protection
Check housing protection | Imposed | Remarks | Pass | Fail | N.A. | N.I.
Main terminal box | >=IP-55
Aux. terminal box | >=IP-55
Motor | >=IP-23
Heater | >=IP-23
Cool Fan Motor | >=IP-23
3.1.2.3 Check terminal coding
Check terminal coding | Imposed | Remarks | Pass | Fail | N.A. | N.I.
Main terminal box | drawing …..
Aux. terminal box | drawing …..

## 3.1.3 Visual Inspection
3.1.3.1 Check bearings
Check bearings | Imposed | Remarks | Pass | Fail | N.A. | N.I.
Bearing DE
Bearing NDE
Bearing NDE insulated
Bearings filled with lubrication
Shaft grounding ring
3.1.3.2 Check for damage and/or production errors
Check for damage and/or production errors | Remarks |  | Pass | Fail | N.A. | N.I.
Main terminal box
Main cable glands
Aux. terminal box
Aux. cable glands
Motor outer dimensions
Motor frame
Flange
Shaft coupling
Heater
Cool Fan
Cool Fan Motor
Lubrication points
3.1.3.3 Check machine design
Check machine design | Remarks |  | Pass | Fail | N.A. | N.I.
Rs (mOhm)
Ld (mH)
Lq (mH)
Design with skewed PM? (Y/N) | PM only, to reduce cogging torque
Design with Halbach array PM? (Y/N) | PM only, to reduce cogging torque

## 3.2. Basic Tests
3.2.1 Check weight and inertia measurements
Check weight and inertia measurements | Imposed |  | Remarks | Pass | Fail | N.A. | N.I.
Total weight of the machine |  | kg | max. lifting weight crane
Total weight of the rotor |  | kg
Moment of inertia rotor |  | Kgm^2
3.2.2 Check Rotor shaft is sufficiently centred
Check Rotor shaft is sufficiently centred | Remarks |  |  | Pass | Fail | N.A. | N.I.
Is the rotor shaft mechanically centred?
Is the rotor shaft magnetically centred?
Note:
Pumpstation De Helsdeur: Max. lifting weight crane 12,5 ton. (12.500 kg)

## 3.3 Insulation Resistance Cold
Test Voltage | 1000 | VDC
Norm Insulation Resistance >= | 100 | MΩ
Stator Winding phase-phase | Riso(MΩ) |  |  | Temperature Measurement Stator phase-ground | Riso(MΩ)
U-V |  |  |  | PT100 U-PE (main)
V-W |  |  |  | PT100 V-PE (main)
W-V |  |  |  | PT100 W-PE (main)
Stator Winding phase-ground | Riso(MΩ) |  |  | Temperature Measurement Stator phase-ground | Riso(MΩ)
U-PE |  |  |  | PT100 U-PE (spare)
V-PE |  |  |  | PT100 V-PE (spare)
W-PE |  |  |  | PT100 W-PE (spare)
Thermal protection phase-PE | Riso(MΩ) |  |  | Temperature Measurement Bearings phase-ground | Riso(MΩ)
PTC stop (main) |  |  |  | PT100 DE - PE (main)
PTC stop (spare) |  |  |  | PT100 DE - PE (spare)
PTC warning (main) |  |  |  | PT100 NDE - PE (main)
PTC warning (spare) |  |  |  | PT100 NDE - PE (spare)
Auxiliaries Fan stator winding phase-phase | Riso(MΩ) |  |  | Auxiliaries Heater phase-ground | Riso(MΩ)
U-V |  |  |  | heater L1-PE
V-W |  |  |  | -
W-V |  |  |  | -
Auxiliaries Fan stator winding phase-PE | Riso(MΩ) |  |  | Auxiliaries | Riso(MΩ)
U-PE |  |  |  | -
V-PE |  |  |  | -
W-PE |  |  |  | -
Insulation resistance (cold)
Pass | Fail | N.T. | N.A.

## 3.4 Resistance Winding Cold
Rs stator winding phases, cold |  |  |  | Tolerance |  | Test Results
| Rs, Measured | Rs, Calculated | Rs, Imposed | Calculated | Imposed
| mW @ Ta | mW @ Ts | mW | % | % | Pass | Fail | N.T. | N.A.
U1 - U2 |  | 0 | 0 |  | 5
V1 - V2 |  | 0 | 0 |  | 5
W1 - W2 |  | 0 | 0 |  | 5
| Ta Tambient | Ts Tstandard
| 0C | 0C |  |  | Winding material |  | k
|  | 20 |  |  | Cu |  | 235

## 3.5 RTD PT-100 Cold
Tambient |  | 0C |  | 100 | W
Fault class | F0,1 | -
IEC 60751
R0 | 100 | W | Fault class | 0.1 | 0.0017
A | 0.0039083 | - | F0,1 | 0.1 | 0.0017 | F0,1 class B 1/3 DIN
B | -5.775e-07 | - | F0,15 | 0.15 | 0.002 | F0,15 class A
C, t < 0 0C | -4.183e-12 | - | F0,3 | 0.3 | 0.005 | F0,3 class B
C, t >= 0 0C | 0 | - | F0,6 | 0.6 | 0.01 | F0,6 class 2B
Temperature | R Measured |  | T Calculated (0C) | Tolerance (0C) | Tolerance (0C) | PT-100 Test
measurement | (W)
[6 empty] | Pass | Fail | N.T. | N.A.
PT100 U1 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 U2 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 V1 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 V2 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 W1 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 W2 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 DE1 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 DE2 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 NDE1 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 NDE2 |  |  | -246.861 | 0.1 | -246,96/-246,76
RTD = Resistance Temperature Detector

## 3.6 PTC stop
PTC TNF = nominal trip temperature.
To check the proper functioning of the triplet PTC, measurements at both lower and higher operating temperatures are sufficient!
If in doubt, see the table for proper PTC operation.
Inspection Results PTC wire colours
(Stop)
PTC STOP sensor | Temperature values |  | PTC Wire Colours Triplet |  | Pass | Fail | N.T. | N.A.
TNF switch temperature, Statorwinding (main) | 145 | 0C | black-white
TNF switch temperature, Statorwinding (spare) | 145 | 0C | black-white
(each phase, in serie U, V, W)
Test Results PTC resistance
(Stop, main)
Resistance PTC STOP sensor, main | Temperature (0C) | Measu- ring voltage (VDC) | Single PTC (W) | Triple PTC (W) | Pass | Fail | N.T. | N.A.
PTC stop (main) | 25 | 0.2 | 100 | 300
PTC stop (spare) | 25 | 0.2 | 250 | 750
Resistance, PTC TNF - 50C (max) | 140 | 2.5 | 250 | 750
Resistance, PTC TNF (typ) | 145 | 2.5 | 1000 | 3000
Resistance, PTC TNF + 50C (min) | 150 | 2.5 | 1330 | 3990
Resistance, PTC TNF + 150C (min) | 160 | 7.5 | 4000 | 12000
Test Results PTC resistance
(Stop, spare)
Resistance PTC STOP sensor, spare | Temperature (0C) | Measu- ring voltage (VDC) | Single PTC (W) | Triple PTC (W) | Pass | Fail | N.T. | N.A.
Type-A, Resistance PTC 250C (max) | 25 | 0.2 | 100 | 300
Type-B, Resistance PTC 250C (max) | 25 | 0.2 | 250 | 750
Resistance, PTC TNF - 50C (max) | 140 | 2.5 | 250 | 750
Resistance, PTC TNF (typ) | 145 | 2.5 | 1000 | 3000
Resistance, PTC TNF + 50C (min) | 150 | 2.5 | 1330 | 3990
Resistance, PTC TNF + 150C (min) | 155 | 7.5 | 4000 | 12000

## 3.7 PTC warning
PTC TNF = nominal trip temperature.
To check the proper functioning of the triplet PTC, measurements at both lower and higher operating temperatures are sufficient!
If in doubt, see the table for proper PTC operation.
Inspection Results PTC wire colours
(Warning)
PTC Warning sensor | Temperature values |  | PTC Wire Colours Triplet |  | Pass | Fail | N.T. | N.A.
TNF switch temperature, Statorwinding (main) | 130 | 0C | blue-blue
TNF switch temperature, Statorwinding (spare) | 130 | 0C | blue-blue
(each phase, in serie U, V, W)
Test Results PTC resistance
(Warning, main)
Resistance PTC Warning sensor, main | Temperature (0C) | Measu- ring voltage (VDC) | Single PTC (W) | Triple PTC (W) | Pass | Fail | N.T. | N.A.
PTC stop (main) | 25 | 0.2 | 100 | 300
PTC stop (spare) | 25 | 0.2 | 250 | 750
Resistance, PTC TNF - 50C (max) | 125 | 2.5 | 250 | 750
Resistance, PTC TNF (typ) | 130 | 2.5 | 1000 | 3000
Resistance, PTC TNF + 50C (min) | 135 | 2.5 | 1330 | 3990
Resistance, PTC TNF + 150C (min) | 145 | 7.5 | 4000 | 12000
Test Results PTC resistance
(Warning, spare)
Resistance PTC Warning sensor, spare | Temperature (0C) | Measu- ring voltage (VDC) | Single PTC (W) | Triple PTC (W) | Pass | Fail | N.T. | N.A.
Type-A, Resistance PTC 250C (max) | 25 | 0.2 | 100 | 300
Type-B, Resistance PTC 250C (max) | 25 | 0.2 | 250 | 750
Resistance, PTC TNF - 50C (max) | 125 | 2.5 | 250 | 750
Resistance, PTC TNF (typ) | 130 | 2.5 | 1000 | 3000
Resistance, PTC TNF + 50C (min) | 135 | 2.5 | 1330 | 3990
Resistance, PTC TNF + 150C (min) | 140 | 7.5 | 4000 | 12000

## 3.8 Insulation HiPot AC
Rated voltage windings | 500 | VAC |  | Test Voltage Percentage | 100 | %
Test voltage auxiliaries | 1500 | VAC |  | 100% first time, 80% repetitive
Description | Test Voltage IEC34-1 |  | Test Time | Test Voltage
Statorwinding | 2000 | VAC | 60 sec | Test Voltage 100% = 2000VAC
Auxiliarias | 1500 | VAC | 15 sec | Test Voltage 100% = 1500VAC
Stator Winding phase-phase | HiPot(AC) |  |  | Temperature Measurement Stator phase-ground | HiPot(AC)
U-V |  |  |  | PT100 U-PE (main)
V-W |  |  |  | PT100 V-PE (main)
W-V |  |  |  | PT100 W-PE (main)
Stator Winding phase-ground | HiPot(AC) |  |  | Temperature Measurement Stator phase-ground | HiPot(AC)
U-PE |  |  |  | PT100 U-PE (spare)
V-PE |  |  |  | PT100 V-PE (spare)
W-PE |  |  |  | PT100 W-PE (spare)
Thermal protection phase-PE | HiPot(AC) |  |  | Temperature Measurement Bearings phase-ground | HiPot(AC)
PTC stop (main) |  |  |  | PT100 DE - PE (main)
PTC stop (spare) |  |  |  | PT100 DE - PE (spare)
PTC warning (main) |  |  |  | PT100 NDE - PE (main)
PTC warning (spare) |  |  |  | PT100 NDE - PE (spare)
Auxiliaries Fan stator winding phase-phase | HiPot(AC) |  |  | Auxiliaries Heater phase-ground | HiPot(AC)
U-V |  |  |  | heater L1 - PE
V-W |  |  |  | -
W-V |  |  |  | -
Auxiliaries Fan stator winding phase-PE | HiPot(AC) |  | Insulation resistance (cold) | HiPot (AC)
U-PE
V-PE |  |  | Pass | Fail | N.T. | N.A.
W-PE

## 3.9 BEMF(Cold)
Ubemf specification | BEMF test, only in case of PM machine
Ubemf (cold) | 0 | V | at | 1000 | rpm
rated speed | 79 | rpm
|  |  | Tol. Min |  | Tol Max
At rated rpm | Typical |  | -10 | % | 2 | %
Ubemf at 79 rpm | 0 | V | 0 | V | 0 | V
Upk (peak) | 0 | V | 0 | V | 0 | V
Upk-pk | 0 | V | 0 | V | 0 | V
With measured speed | Typical |  | Tol. Min |  | Tol. Max
Ubemf at 0 rpm | 0 | V | 0 | V | 0 | V
Upk (peak) | 0 | V | 0 | V | 0 | V
Upk-pk | 0 | V | 0 | V | 0 | V
Voltage and speed measured
Measured Upk-pk |  | V |  | measured |  | rpm
Upk (peak) | 0 | V |  | calc. | 0 | Hz
Ubemf | 0 | V
Speed | Typical |  |  |  | Measured
rated frequency | 0 | Hz |  | measured |  | Hz
pole pairs | 0 | pp. |  | calc. | 0 | pp.
rated speed | #DIV/0! | rpm |  | calc. | 0 | rpm
w | #DIV/0! | rad/s |  | calc. | 0 | rad/s
Ke = Upk / w | #DIV/0! | V.s/rad |  | calc. | 0 | V.s/rad
T period | #DIV/0! | msec |  | calc. | 0 | msec
BEMF (cold)
Pass | Fail | N.T. | N.A.

## 3.10 Overspeed Test
Mechanical test how the machine performs at a higher speed and measurement Bemf.
Fig. 3.9: Mechanical overspeed test and BEMF.
Description | Test speed (%) | n (rpm) | Test speed (rpm) | Test time (s)
IEC 60034-1
Overspeed test | 120 | 79 | 94.8 | 120
Test | Measured speed (rpm) | Norm test speed (rpm) | Overspeed
|  |  | Pass | Fail
Overspeed |  | 94.8
|  |  | N.A. | N.I.

## 3.11 Temperature Rise Test ETD
Embedded temperature detector method (ETD)
The temperature is determined by means of temperature detectors (e.g. resistance thermometers, RTD = Resistance Temperature Detector, PT-100) built into the machine during construction, at points which are inaccessible after the machine is completed.
RTD stator winding phases, cold | T Measured |  | Temperature Rise Test ETD
(0C)
U1 - U2 |  |  | Pass | Fail | N.T. | N.A.
V1 - V2
W1 - W2
Ta Tambient, cold
RTD stator winding phases, hot | T Measured
| (0C) |  | Powered by VFD | VFD = Variable Frequency Drive
U1 - U2 |  |  | (y/n)
V1 - V2 |  |  | y
W1 - W2
Ta Tambient, hot
ETD-method stator winding temperature rise test | DQu temperature rise stator winding by PT100(hot) minus PT100(cold) | Maxium rise temperature imposed | DQv + ta absolute temperature stator winding | DQv + ta absolute temperature stator winding
| (0C) | (0C) | (0C) ta cold | (0C) ta hot
U1 - U2 | 0 | 90 | 0 | 0
V1 - V2 | 0 | 90 | 0 | 0
W1 - W2 | 0 | 90 | 0 | 0

## 3.12 Temp. Rise Test Bearings
Embedded temperature detector method (ETD) or Thermometer method (without ETD on bearings)
The temperature is determined by means of temperature detectors (e.g. resistance thermometers, RTD = Resistance Temperature Detector, PT-100) built into the machine during construction, at points which are inaccessible after the machine is completed. Or the temperature is determined by thermometers applied (RTD, PT-100 or thermocouples) to accessible surfaces of the completed machine.
RTD stator winding phases, cold | T Measured |  | Temperature Rise Test ETD
(0C)
Drive End (DE) |  |  | Pass | Fail | N.T. | N.A.
Non Drive end (NDE)
Ta Tambient, cold
Note:
RTD stator winding phases, hot | T Measured |  | Bearing temperature directly measured after temperature rise test.
| (0C) |  | - Drive End (DE);
Drive End (DE) |  |  | - Non Drive End (NDE).
Non Drive end (NDE)
Ta Tambient, hot
ETD-method stator winding temperature rise test | DQu temperature rise bearings by PT100(hot) minus PT100(cold) | Maxium temperature imposed | DQv + ta absolute temperature bearings | DQv + ta absolute temperature bearings
| (0C) | (0C) | (0C) ta cold | (0C) ta hot
Drive End (DE) | 0 | 100 | 0 | 0
Non Drive end (NDE) | 0 | 100 | 0 | 0

## 3.13 Resistance Winding Hot
Rs stator winding phases, hot |  |  |  | Tolerance |  | Test Results
| Rs, Measured | Rs, Calculated | Rs, Imposed | Calculated | Imposed
| mW @ Ta | mW @ Ts | mW | % | % | Pass | Fail | N.T. | N.A
U1 - U2 |  | 0 | 0 |  | 10
V1 - V2 |  | 0 | 0 |  | 10
W1 - W2 |  | 0 | 0 |  | 10
| Ta Tambient | Ts Tstandard
|  | 0C |  |  | Winding material |  | k
|  | 20 |  |  | Cu |  | 235

## 3.14 Winding Rise Test Calc
Resistance Winding Test
| see 3.4 Cold | see 3.13 Hot
Rs stator winding phases |  |  | Temperature Rise |  | Test Results
| Rs, Measured | Rs, Measured | Calculated | Imposed
| mW @ T1 | mW @ T2 | 0C | 0C | Pass | Fail | N.T. | N.A.
U1 - U2 |  |  |  | 90
V1 - V2 |  |  |  | 90
W1 - W2 |  |  |  | 90
| Powered by VFD |  | VFD = Variable Frequency Drive
(y/n)
y
| Tambient | Tambient
| T1 Cold | T2 Hot
| 0C | 0C |  | Winding material |  | k
| 0 | 0 |  | Cu |  | 235

## 3.15.1 Load Test 1
Load Test 1
Power calculation factor
Pass | Fail | N.T. | N.A. |  |  | Pin VSD |  | 0.57735 | x | Machine load test 1: 25%, 50%, 75%, 100% and 110% of rated power at rated speed.
[6 empty] | Pin motor |  | 0.57735 | x
Pin VSD
Load | Load | Speed | Speed | [13 empty] | Tolerance (U.I.PF versus P)
(%) | (kW) | (Hz) | (rpm) | UL1(V) | UL2(V) | UL3(V) | IL1(A) | IL2(A) | IL3(A) | COS jL1(-) | COS jL2(-) | COS jL3(-) | PinL1(kW) | PinL2(kW) | PinL3(kW) | Pin (kW) | Tol. U(%) | Tol. V(%) | Tol. W(%)
25 | 141.6727 | 0 | 79 | [12 empty] | 0
50 | 283.3455 | 0 | 79 | [12 empty] | 0
75 | 425.0182 | 0 | 79 | [12 empty] | 0
100 | 566.691 | 0 | 79 | [12 empty] | 0
110 | 623.3601 | 0 | 79 | [12 empty] | 0
Pin Motor
Load | Load | Speed | Speed | [13 empty] | Tolerance (U.I.PF versus P)
(%) | (kW) | (Hz) | (rpm) | UU(V) | UV(V) | Uw(V) | IU(A) | IV(A) | Iw(A) | COS jU(-) | COS jV(-) | COS jW(-) | PinU(kW) | PinV(kW) | PinW(kW) | Pin (kW) | Tol. U(%) | Tol. V(%) | Tol. W(%)
25 | 141.6727 | 0 | 79 | [12 empty] | 0
50 | 283.3455 | 0 | 79 | [12 empty] | 0
75 | 425.0182 | 0 | 79 | [12 empty] | 0
100 | 566.691 | 0 | 79 | [12 empty] | 0
110 | 623.3601 | 0 | 79 | [12 empty] | 0
Pout Motor
Load | Load | Speed | Speed | Imposed | Measured | Measured | Calc. | Calc. | Calc. | Calc. | Imposed | [5 empty] | Tolerance (asymetric current)
(%) | (kW) | (Hz) | (rpm) | T(Nm) | T(Nm) | n(rpm) | n(rad/s) | Pn out(kW) | Pn in(kW) | h (%) | h motor (%) | Efficiency | Pout>=Pr | T >= Tr | Ir(A) | h vfd (%) | IU(A) | IV(A) | Iw(A)
25 | 141.6727 | 0 | 79 | 17125 |  |  | 0 | 0 | 0 | 0 | 91 | fail | fail | fail | 0 |  | #DIV/0! | #DIV/0! | #DIV/0!
50 | 283.3455 | 0 | 79 | 34250 |  |  | 0 | 0 | 0 | 0 | 92 | fail | fail | fail | 0 |  | #DIV/0! | #DIV/0! | #DIV/0!
75 | 425.0182 | 0 | 79 | 51375 |  |  | 0 | 0 | 0 | 0 | 93 | fail | fail | fail | 0 |  | #DIV/0! | #DIV/0! | #DIV/0!
100 | 566.691 | 0 | 79 | 68500 |  |  | 0 | 0 | 0 | 0 | 94 | fail | fail | fail | 0 |  | #DIV/0! | #DIV/0! | #DIV/0!
110 | 623.3601 | 0 | 79 | 75350 |  |  | 0 | 0 | 0 | 0 | 93 | fail | fail | fail | 0 |  | #DIV/0! | #DIV/0! | #DIV/0!

## 3.15.2 Load Test 2
Load Test 2
Power calculation factor
Pass | Fail | N.T. | N.A. |  |  | Pin VSD |  | 0.57735 | x | Machine load test 2: Five load and speed points selected from pumpcurve.
[6 empty] | Pin motor |  | 0.57735 | x
Pin VSD
Load | Load | Speed | Speed | [13 empty] | Tolerance (U.I.PF versus P)
(%) | (kW) | (Hz) | (rpm) | UL1(V) | UL2(V) | UL3(V) | IL1(A) | IL2(A) | IL3(A) | COS jL1(-) | COS jL2(-) | COS jL3(-) | PinL1(kW) | PinL2(kW) | PinL3(kW) | Pin (kW) | Tol. U(%) | Tol. V(%) | Tol. W(%)
5.0068 | 28.3733 | 0 | 22.3 | [12 empty] | 0
18.6542 | 105.7115 | 0 | 39.9 | [12 empty] | 0
31.1673 | 176.6224 | 0 | 49.9 | [12 empty] | 0
54.7916 | 310.4993 | 0 | 59.9 | [12 empty] | 0
100 | 566.691 | 0 | 79 | [12 empty] | 0
Pin Motor
Load | Load | Speed | Speed | [13 empty] | Tolerance (U.I.PF versus P)
(%) | (kW) | (Hz) | (rpm) | UU(V) | UV(V) | Uw(V) | IU(A) | IV(A) | Iw(A) | COS jU(-) | COS jV(-) | COS jW(-) | PinU(kW) | PinV(kW) | PinW(kW) | Pin (kW) | Tol. U(%) | Tol. V(%) | Tol. W(%)
5.0068 | 28.3733 | 0 | 22.3 | [12 empty] | 0
18.6542 | 105.7115 | 0 | 39.9 | [12 empty] | 0
31.1673 | 176.6224 | 0 | 49.9 | [12 empty] | 0
54.7916 | 310.4993 | 0 | 59.9 | [12 empty] | 0
100 | 566.691 | 0 | 79 | [12 empty] | 0
Pout Motor
Load | Load | Speed | Speed | Imposed | Measured | Measured | Calc. | Calc. | Calc. | Calc. | Imposed | [5 empty] | Tolerance (asymetric current)
(%) | (kW) | (Hz) | (rpm) | T(Nm) | T(Nm) | n(rpm) | n(rad/s) | Pn out(kW) | Pn in(kW) | h (%) | h motor(%) | Efficiency | Pout>=Pr | T >= Tr | Ir(A) | h vfd (%) | IU(A) | IV(A) | Iw(A)
5.0068 | 28.3733 | 0 | 22.3 | 12150 |  |  | 0 | 0 | 0 | 0 | 90.8498 | fail | fail | fail | 0 |  | #DIV/0! | #DIV/0! | #DIV/0!
18.6542 | 105.7115 | 0 | 39.9 | 25300 |  |  | 0 | 0 | 0 | 0 | 90.4404 | fail | fail | fail | 0 |  | #DIV/0! | #DIV/0! | #DIV/0!
31.1673 | 176.6224 | 0 | 49.9 | 33800 |  |  | 0 | 0 | 0 | 0 | 91.935 | fail | fail | fail | 0 |  | #DIV/0! | #DIV/0! | #DIV/0!
54.7916 | 310.4993 | 0 | 59.9 | 49500 |  |  | 0 | 0 | 0 | 0 | 92.6437 | fail | fail | fail | 0 |  | #DIV/0! | #DIV/0! | #DIV/0!
100 | 566.691 | 0 | 79 | 68500 |  |  | 0 | 0 | 0 | 0 | 94 | fail | fail | fail | 0 |  | #DIV/0! | #DIV/0! | #DIV/0!

## 3.16 No-Load Test
No-Load Test
Pass | Fail | N.T. | N.A.
Pin VSD (grid) | [6 empty] | Pin Motor
U0(%) |  | 80 | 90 | 100 | 110 |  | U0(%) |  | 80 | 90 | 100 | 110
U0(V) |  | 400 | 450 | 500 | 550 |  | U0(V) |  | 400 | 450 | 500 | 550
f(Hz) | [6 empty] | f(Hz)
n(rpm) | [6 empty] | n(rpm)
UL1(V) | [6 empty] | UU(V)
UL2(V) | [6 empty] | UV(V)
UL3(V) | [6 empty] | Uw(V)
IL1(A) | [6 empty] | IU(A)
IL2(A) | [6 empty] | IV(A)
IL3(A) | [6 empty] | Iw(A)
COS jL1(-) | [6 empty] | COS jU(-)
COS jL2(-) | [6 empty] | COS jV(-)
COS jL3(-) | [6 empty] | COS jW(-)
PinL1(W) | [6 empty] | PinU(W)
PinL2(W) | [6 empty] | PinV(W)
PinL3(W) | [6 empty] | PinW(W)
PL (W) | 0 | 0 | 0 | 0 | 0 | 0 | Pm (W) | 0 | 0 | 0 | 0 | 0 | 0
PL (W) | 0 | 0 | 0 | 0 | 0 | 0 | Pm (W) | 0 | 0 | 0 | 0 | 0 | 0
Io(A)
P0(W)
Rs(mΩ)
RFe(Ω) |  |  | Calculated resistance for core loses. |  |  |  | Ld(mH)
Xm(Ω) |  |  | Calculated resistance for magnetic reactance. |  |  |  | Lq(mH)

## 3.17.1 Vibration test
Description | Value | Unit
Speed during measurement | 79 | rpm
Vibration severity class | B | -
Shaft height H |  | mm
Maximum velocity value <= | 1.5 | V rms (mm/s)
Machine installation (free or rigid) | rigid | -
Test rig, machine on floor or free shaft hanging in crane (preferably). | machine on floor | -
Machine position during measurement is always horizontal, regardless of the installation setup at the end customer. | horizontal | -
Vibration severity grades | Machine installation | Shaft height H (mm)
|  | 56 £ H £ 132 | H > 132
|  | Vrms (mm/s) | Vrms (mm/s)
A | Free suspension | 2.8 | 2.8
| Rigid clamping | - | 2.3
B | Free suspension | 1.1 | 1.8
| Rigid clamping | - | 1.5
Table 3.17.2: Vibration limits for maximum vibration severity in terms of vibration velocity (Vrms) for the shaft height H.
Table 3.17.1: Imposed vibration parameters for testing.

## 3.17.2 Vibration test
Measuring point | Vibration no-load forced cool fan on | Vrms(mm/s) | Vibration no-load forced cool fan off | Vrms(mm/s)
1 Axial DE
2 Top DE
3 Right side seen from shaft, halfway at DE
4 Right side seen from shaft, halfway at NDE
5 Top NDE
Vibration Test
| Pass | Fail | N.T. | N.A.
The vibration measurement of the machine is measured according to the standard NEN-EN-IEC 60034-14, edition 2018, without load (no-load) and rigid or free suspension (see table 3.17.1).
Fig. 3.17: Vibration test set up (DE = Drive End, NDE = Non Drive End).
Table 3.17.3: Measured vibrations.

## 3.18.1 Noise test
Description | Value | Unit
Speed during measurement | 79 | rpm
Imposed maximum value Lpa | 76 | dB(A)
Tolerance maximum value Lpa | 2 | dB(A)
Maximum value always < 80 dBa (with VSD) | 78 | dB(A)
Cooling type |  | -
Cooling description
Machine position during measurement (vertical / horizontal) | horizontal | -
Table 3.18.1: Imposed noise parameters for testing.
The noise measurement of the machine is measured with an A-weighted pressure level Lpa (dBa). The noise measurement takes place at 6 different measuring points around the machine at a distance of 1 meter from the outside. The measurement is carried out at no load with a nominal speed. If forced cooling is present, noise will be measured with forced cooling switched on and off.

## 3.18.2 Noise test
Measuring point distance 1 meter | Noise no-load forced cool fan on | Lpa (dBa) | Noise no-load forced cool fan off | Lpa (dBa)
1 Axial DE
2 Top DE
3 Top NDE
4 Axial NDE
5 Left side seen from shaft, halfway, between DE and NDE.
6 Right side seen from shaft, halfway, between DE and NDE.
7 Background, machine switched off
Noise Test
| Pass | Fail | N.T. | N.A.
Fig. 3.18: Noise test set up (DE = Drive End, NDE = Non Drive End).
Table 3.18.2: Measured noises
LA = level of acoustic pressure (dBa), d = 1 m.

## 3.19 Locked Rotor Test
Locked Rotor Test (aka: Blocked Rotor Test, Short-Circuit Test), only in case of IM Machines.
It determines torque, motor characteristics and short-circuit current at normal voltage.
Procedure
1 | Connect circuit diagram
2 | Block Rotor
3 | Apply low voltage to stator (start with 0V)
4 | Measure voltage, current, power, cos phi and frequency
5 | Increase voltage in small steps till rated current
Rated current
Ir(A)
Rated voltage
Ur(V)
500
br = blocked rotor
Isc = short circuit current at rated voltage
Pbr = W1 + W2
| Ubr(V) | Ibr(A) | Isc(kA) | W1(W) | W2(W) | Pbr(W) | Cos j (-) | f(Hz)

## 3.20 BEMF(Hot)
Ubemf specification | BEMF test, only in case of PM machine
Ubemf (hot) | 0 | V | at | 1000 | rpm
rated speed | 79 | rpm
|  |  | Tol. Min |  | Tol Max
At rated rpm | Typical |  | -10 | % | 2 | %
Ubemf at 79 rpm | 0 | V | 0 | V | 0 | V
Upk (peak) | 0 | V | 0 | V | 0 | V
Upk-pk | 0 | V | 0 | V | 0 | V
With measured speed | Typical |  | Tol. Min |  | Tol. Max
Ubemf at 0 rpm | 0 | V | 0 | V | 0 | V
Upk (peak) | 0 | V | 0 | V | 0 | V
Upk-pk | 0 | V | 0 | V | 0 | V
Voltage and speed measured
Measured Upk-pk |  | V |  | measured |  | rpm
Upk (peak) | 0 | V |  | calc. | 0 | Hz
Ubemf | 0 | V
Speed | Typical |  |  |  | Measured
rated frequency | 0 | Hz |  | measured |  | Hz
pole pairs | 0 | pp. |  | calc. | 0 | pp.
rated speed | #DIV/0! | rpm |  | calc. | 0 | rpm
w | #DIV/0! | rad/s |  | calc. | 0 | rad/s
Ke = Upk / w | #DIV/0! | V.s/rad |  | calc. | 0 | V.s/rad
T period | #DIV/0! | msec |  | calc. | 0 | msec
BEMF (hot)
Pass | Fail | N.T. | N.A.

## 3.21 Insulation Resistance Hot
Test Voltage | 1000 | VDC
Norm Insulation Resistance >= | 100 | MΩ
Stator Winding phase-phase | Riso(MΩ) |  |  | Temperature Measurement Stator phase-ground | Riso(MΩ)
U-V |  |  |  | PT100 U-PE (main)
V-W |  |  |  | PT100 V-PE (main)
W-V |  |  |  | PT100 W-PE (main)
Stator Winding phase-ground | Riso(MΩ) |  |  | Temperature Measurement Stator phase-ground | Riso(MΩ)
U-PE |  |  |  | PT100 U-PE (spare)
V-PE |  |  |  | PT100 V-PE (spare)
W-PE |  |  |  | PT100 W-PE (spare)
Thermal protection phase-PE | Riso(MΩ) |  |  | Temperature Measurement Bearings phase-ground | Riso(MΩ)
PTC stop (main) |  |  |  | PT100 DE - PE (main)
PTC stop (spare) |  |  |  | PT100 DE - PE (spare)
PTC warning (main) |  |  |  | PT100 NDE - PE (main)
PTC warning (spare) |  |  |  | PT100 NDE - PE (spare)
Auxiliaries Fan stator winding phase-phase | Riso(MΩ) |  |  | Auxiliaries Heater phase-ground | Riso(MΩ)
U-V |  |  |  | heater L1 - PE
V-W |  |  |  | -
W-V |  |  |  | -
Auxiliaries Fan stator winding phase-PE | Riso(MΩ) |  |  | Auxiliaries | Riso(MΩ)
U-PE |  |  |  | -
V-PE |  |  |  | -
W-PE |  |  |  | -
Insulation resistance (hot)
Pass | Fail | N.T. | N.A.

## 3.22 RTD PT-100 Hot
Tambient |  | 0C |  | 100 | W
Fault class | F0,1 | -
IEC 60751
R0 | 100 | W | Fault class | 0.1 | 0.0017
A | 0.0039083 | - | F0,1 | 0.1 | 0.0017 | F0,1 class B 1/3 DIN
B | -5.775e-07 | - | F0,15 | 0.15 | 0.002 | F0,15 class A
C, t < 0 0C | -4.183e-12 | - | F0,3 | 0.3 | 0.005 | F0,3 class B
C, t >= 0 0C | 0 | - | F0,6 | 0.6 | 0.01 | F0,6 class 2B
Temperature | R Measured |  | T Calculated (0C) | Tolerance (0C) | Tolerance (0C) | PT-100 Test
measurement | (W)
[6 empty] | Pass | Fail | N.T. | N.A.
PT100 U1 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 U2 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 V1 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 V2 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 W1 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 W2 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 DE1 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 DE2 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 NDE1 |  |  | -246.861 | 0.1 | -246,96/-246,76
PT100 NDE2 |  |  | -246.861 | 0.1 | -246,96/-246,76
RTD = Resistance Temperature Detector

## Annex 1.1 Spec. Machine
Machine type |  |  | Electrical machine data
Manufacture |  |  | Rated power |  | kW
Machine Type |  |  | Rated voltage | 500 | V
International Standard | NEN-EN-IEC 60034-1 |  | Rated frequency | 0 | Hz
AC or DC machine | AC |  | Pole pairs |  | pp.
Number of phases | 3 |  | Angular velocity | 8.2729 | rad/s
Speed rotor | Synchronous / Asynchronous |  | Rated stator current | 0 | A
Type of Motor |  |  | Starting current | 0 | %
|  |  | BEMF (cold) | 0 | V@1000rpm
Location |  |  | BEMF (cold) | 0 | V@79rpm
Installation machine | indoor |  | BEMF (hot) | 0 | V@1000rpm
Min. ambient temperature | -20 | 0C | BEMF (hot) | 0 | V@79rpm
Max. ambient temperature | 40 | 0C | Number of poles | 0 | poles
Max. attitude above sealevel | 1000 | m | Rs, cold | 0 | mΩ (phase)
Humidity | < 95 | % | Ld, cold | 0 | mH (phase)
|  |  | Lq, cold | 0 | mH (phase)
Mechanical machine data |  |  | Rs,hot | 0 | mΩ (phase)
Rated speed | 79 | rpm | Ld, hot | 0 | mH (phase)
Rated torque (full load) | 68500 | Nm | Lq, hot | 0 | mH (phase)
Starting torque | 110 | % | Stator connection | Y | -
Break-down torque | 130 | % | Stator winding material (Cu or Al) | Cu | -
Direction of rotation | both ways | - | Insulation system | VPI system | -
Moment of inertia |  | Kgm^2 | Line voltage | 500 | V
Weight rotor (approx.) |  | Kg | Line frequency | 50 | Hz
Temperature
ATEX |  |  | Insulation class | H => 180 | 0C
ATEX class | No |  | Temperature rise class | B => 130 | 0C
Efficiency machine |  |  | Powerfactor (PF)
Efficiency, 100% load | 94 | % | PF, 100% load | 0.95 | -
Efficiency, 75% load | 93 | % | PF, 75% load | 0.85 | -
Efficiency, 50% load | 92 | % | PF, 50% load | 0.72 | -
Efficiency, 25% load | 91 | % | PF, 25% load | 0.6 | -
Efficiency Class | n.a.

## Annex 1.2 Spec. Machine
Frame
Frame material
Frame size H |  | mm
Flange size
Foot size | n.a.
Mouting arrangement (new) | IM-3011
Mouting arrangement (old) | IM-V1
Motor protection | >=IP-23
Terminal box protection | >=IP-55
Cable Glands
Main power cable glands | drawing….
Auxiliary cable glands | drawing….
Bearing data
Bearing manufacturer
Bearing type Drive End
Bearing code Drive End
Lubrication bearings (amount of grease/operating hours)
Bearing type Non Drive End
Bearing code Non Drive End
Lubrication bearings (amount of grease/operating hours)
Bearing NDE insulated
Bearing lubrication
Axial load on Drive End |  | kN
Radial load on Drive End |  | kN
Shaft grounding ring
Vibration & noise
Vibration severity | 1.5 | V rms (mm/s)
Vibration class | B
Noise Level LpA at 1 m on VFD < | 78 | dB(A)

## Annex 1.3 Spec. Machine
Machine Load data |  |  | Painting
Application machine | centrifugal pump |  | Painting system | Corrosivity cat. C3
Connection with application | rigid / flexible coupling |  | Painting RAL-color | RAL-1005
Torque characterisitic | quadratic |  | Painting color | Honey Yellow
Starting methode | Variable Frequncy Drive (VFD)
Operation methode | Variable Frequency Drive (VFD) |  | Variabel Speed Drive (VSD)
Number of starts (cold) | 15 | x/h | Prefered control mode sensorless | vector or scalar
Number of starts (hot) | 15 | x/h | Min. switching frequency | 3.6 | kHz
Load class | S1 |  | Max. switching frequency | 6 | kHz
Auxiliaries
Fan |  |  | Temperature measurement bearings
Coolant medium | air |  | ND Bearing PT100 | PT100
Cooling type |  |  | ND Bearing PT100 (spare) | PT100
Cooling type desciption |  |  | NDE Bearing PT100 | PT100
Voltage Fan | 500 | V | NDE Bearing PT100 (spare) | PT100
Current Fan |  | A
Power Fan |  | W
Heating |  |  | Vibration monitoring
Anti-condensation heater |  |  | ND, axes: Hor., Vert. , Axiaal | No
Voltage heater |  | V | NDE, axes: Hor., Vert. , Axiaal | No
Power heater |  | W
Additional specifications for predictive maintenance
Temperature Protection PTC |  |  | nr. slots |  | -
Stator winding U, V, W, STOP | PTC (2x 3x in series) T= 145 | 0C | nr. rotor bars |  | -
Stator winding U, V, W, Warning | PTC (2x 3x in series) T= 130 | 0C | nr. permanent magnets |  | -
|  |  | nr. rows of PM magnets |  | -
Statorwinding Temperature Measurement |  |  | type permanent magnets (PM) |  | -
U, V, W, (hotspot, main, winding end), main | PT100 (set 1x each phase) |  | PM maximum temperature |  | 0C
U, V, W, (hotspot, main, winding end), spare | PT100 (set 1x each phase) |  | PM Currie temperature |  | 0C
|  |  | PM mounting intern / surface |  | -
|  |  | PM mounting line / skewed |  | -

## Annex 2
List of used instruments
| Tag | Serial Number | Measurement | Instrument | Type | Calibration | Accuracy | Test | Remarks
certificate + expiration date
Power analyser 1
U, I, f, PF, S, P, Q
Current clamp L1
Current clamp L2
Current clamp L3
Power analyser 2
suitable for PWM
U, I, f, PF, S, P, Q
Current clamp U
Current clamp V
Current clamp W
Power analyser 3
suitable for PWM
U, I, f, PF, S, P, Q
Current clamp U
Current clamp V
Current clamp W
Temperature datalogger PT100
Multi meter 1
Multi meter 2
Mili ohmmeter Rs
Multi meter
4-wire terminal
Insulation (Megger)
Insulation (PI+DAR)
Dielectric strength tester
Torque transducer
Speed transducer
Clock (time)
Temperature
Sound meter
Vibration meter

## Annex 3.1 Specifications VFD
Description | Value | Unit | Remarks
Fabricaat | Danfoss-VACON |  | Vectorcontrol
Bescherming omhuizing | IP-00 | - | in cabinet IP-54
Bouwvorm | 2x NXN-0650-6-X0T0-NSV 1x NXI-1150-5-A0T0-ISG | - | 12-pulsige brug
Serie nr. |  | -
Nominale netspanning | 500 | V | 500vac
Nominale ingangstroom | 2x 461 | A | Dd0Dy5
Max. voorbeveiliging | 2x 461 | A
Nominale stroom (normaal) | 909 | A | (normaal bedrijf)
Nominaal vermogen (normaal) | 630 | kW
Overbelasting (normaal) | 110 | % | 1 min. elke 10 min.
Nominale stroom (zwaar) |  | A
Nominaal vermogen(zwaar) | 630 | kW
Overbelasting (zwaar) | 110 | % | 1 min. elke 10 min.
Maximale uitgangsstroom | 1150 | A | bij 400C omgeving
Nominale ingangsfrequentie | 50 | Hz
Schakelfrequentie uitgang | 3.6 | kHz | max. 6kHz
Control algoritme | Vector control or Scalar control | - | closed loop sensor less (PM) or V/Hz (IM)
Bedieningspaneel | ja | -
EMC filter | ja | -
Common Mode Filter | ja | -
Optiekaart | ja | - | IO

## Annex 3.2 Specifications VFD
Settings machine data
Description | Parameter | Value | Unit | Remarks
Taal |  |  |  | 1e Dutch, 2e English
Motor Selectie
Aandrijfmodus |  |  |  | Vacon
Rotatie |  | rechtsom + linksom |  | rechtsom
Netspanning |  | 500 | V
Motor spanning |  | 500 | V
Motor frequentie |  |  | Hz
Motor vermogen |  | 630 | kW | Standaard Pnom x
1 – 110%
Motor stroom |  |  | A | Standaard Inom x
25 – 110%
Motor toerental |  |  | rpm | 40 - 80 rpm
Motor polen |  |  | polen
Motor geluid |  |  | kHz
PWM schakelfrequentie |  | 3.6 | kHz | max. 6kHz
Fase volgorde |  |  | - | normal U, V, W
Settings PM-machine
Description | Parameter | Value | Unit | Remarks
Encoder |  | off | - | uitgeschakeld
Motor type |  |  | -
Tegen EMK |  |  | V | @.... rpm
Rs |  |  | Ohm/fase
Lsd |  |  | mH/fase
Lsq |  |  | mH/fase

## Annex 4 PT100
Temperature (°C) | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
−40 | 84.271 | 84.667 | 85.063 | 85.458 | 85.853 | 86.248 | 86.643 | 87.038 | 87.433 | 87.828
−30 | 88.222 | 88.617 | 89.011 | 89.405 | 89.799 | 90.193 | 90.587 | 90.98 | 91.374 | 91.767
−20 | 92.16 | 92.553 | 92.946 | 93.339 | 93.732 | 94.125 | 94.517 | 94.91 | 95.302 | 95.694
−10 | 96.086 | 96.478 | 96.87 | 97.262 | 97.653 | 98.045 | 98.436 | 98.827 | 99.218 | 99.609
0 | 100 | 100.391 | 100.781 | 101.172 | 101.562 | 101.953 | 102.343 | 102.733 | 103.123 | 103.513
10 | 103.902 | 104.292 | 104.681 | 105.071 | 105.46 | 105.849 | 106.238 | 106.627 | 107.016 | 107.404
20 | 107.793 | 108.181 | 108.57 | 108.958 | 109.346 | 109.734 | 110.122 | 110.509 | 110.897 | 111.284
30 | 111.672 | 112.059 | 112.446 | 112.833 | 113.22 | 113.607 | 113.994 | 114.38 | 114.767 | 115.153
40 | 115.539 | 115.925 | 116.311 | 116.697 | 117.083 | 117.469 | 117.854 | 118.24 | 118.625 | 119.01
50 | 119.395 | 119.78 | 120.165 | 120.55 | 120.934 | 121.319 | 121.703 | 122.087 | 122.471 | 122.855
60 | 123.239 | 123.623 | 124.007 | 124.39 | 124.774 | 125.157 | 125.54 | 125.923 | 126.306 | 126.689
70 | 127.072 | 127.454 | 127.837 | 128.219 | 128.602 | 128.984 | 129.366 | 129.748 | 130.13 | 130.511
80 | 130.893 | 131.274 | 131.656 | 132.037 | 132.418 | 132.799 | 133.18 | 133.561 | 133.941 | 134.322
90 | 134.702 | 135.083 | 135.463 | 135.843 | 136.223 | 136.603 | 136.982 | 137.362 | 137.741 | 138.121
100 | 138.5 | 138.879 | 139.258 | 139.637 | 140.016 | 140.395 | 140.773 | 141.152 | 141.53 | 141.908
110 | 142.286 | 142.664 | 143.042 | 143.42 | 143.797 | 144.175 | 144.552 | 144.93 | 145.307 | 145.684
120 | 146.061 | 146.438 | 146.814 | 147.191 | 147.567 | 147.944 | 148.32 | 148.696 | 149.072 | 149.448
130 | 149.824 | 150.199 | 150.575 | 150.95 | 151.326 | 151.701 | 152.076 | 152.451 | 152.826 | 153.2
140 | 153.575 | 153.95 | 154.324 | 154.698 | 155.072 | 155.446 | 155.82 | 156.194 | 156.568 | 156.941
150 | 157.315 | 157.688 | 158.061 | 158.435 | 158.808 | 159.18 | 159.553 | 159.926 | 160.298 | 160.671
160 | 161.043 | 161.415 | 161.787 | 162.159 | 162.531 | 162.903 | 163.274 | 163.646 | 164.017 | 164.388
170 | 164.76 | 165.131 | 165.501 | 165.872 | 166.243 | 166.614 | 166.984 | 167.354 | 167.724 | 168.095
180 | 168.465 | 168.834 | 169.204 | 169.574 | 169.943 | 170.313 | 170.682 | 171.051 | 171.42 | 171.789
190 | 172.158 | 172.527 | 172.895 | 173.264 | 173.632 | 174 | 174.368 | 174.736 | 175.104 | 175.472
200 | 175.84 | 176.207 | 176.575 | 176.942 | 177.309 | 177.676 | 178.043 | 178.41 | 178.777 | 179.143
210 | 179.51 | 179.876 | 180.242 | 180.609 | 180.975 | 181.34 | 181.706 | 182.072 | 182.438 | 182.803
220 | 183.168 | 183.534 | 183.899 | 184.264 | 184.628 | 184.993 | 185.358 | 185.722 | 186.087 | 186.451
230 | 186.815 | 187.179 | 187.543 | 187.907 | 188.271 | 188.634 | 188.998 | 189.361 | 189.724 | 190.088
240 | 190.451 | 190.813 | 191.176 | 191.539 | 191.901 | 192.264 | 192.626 | 192.988 | 193.35 | 193.712
250 | 194.074 | 194.436 | 194.798 | 195.159 | 195.521 | 195.882 | 196.243 | 196.604 | 196.965 | 197.326
260 | 197.686 | 198.047 | 198.407 | 198.768 | 199.128 | 199.488 | 199.848 | 200.208 | 200.568 | 200.927
270 | 201.287 | 201.646 | 202.006 | 202.365 | 202.724 | 203.083 | 203.442 | 203.8 | 204.159 | 204.517
280 | 204.876 | 205.234 | 205.592 | 205.95 | 206.308 | 206.666 | 207.024 | 207.381 | 207.739 | 208.096

## Specification machine
Machine specification
Machine type
Manufacture
Serial number
Machine Type
| International Standard | NEN-EN-IEC 60034-1
| AC or DC machine | AC
| Number of phases | 3
| Speed rotor | Synchronous / Asynchronous
Type of Motor
Location
| Installation machine | indoor
| Min. ambient temperature | -20 | 0C
| Max. ambient temperature | 40 | 0C
| Max. attitude above sealevel | 1000 | m
| Humidity | < 95 | %
Machine Load data
| Application machine | centrifugal pump
| Connection with application | rigid / flexible coupling
| Torque characterisitic | quadratic
| Starting methode | Variable Frequncy Drive (VFD)
| Operation methode | Variable Frequency Drive (VFD)
| Number of starts (cold) | 15 | x/h
| Number of starts (hot) | 15 | x/h | Pin | 0 | kW |  | Pout | 0 | kW
| Load class | S1
Electrical machine data
Pr | Rated power |  | kW |  |  |  | Tolerance (negative) |  | Tolerance (positive) |  |  | Tolerance (negative) |  | Tolerance (positive)
Ur | Rated voltage | 500 | V |  |  | IEC-34-1: Zone A | -5 | % | 5 | % | IEC-34-1: Zone B | -10 | % | 10 | %
fr | Rated frequency |  | Hz |  |  | IEC-34-1: Zone A | -2 | % | 2 | % | IEC-34-1: Zone B | -5 | % | 3 | %
| Pole pairs |  | pp.
w | Angular velocity | 8.2729 | rad/s
Ir | Rated stator current |  | A |  | 0 | A |  |  |  |  | 0 | kW
| Starting current |  | % |  | 0 | A | Tolerance (negative) |  | Tolerance (positive)
Uemf | BEMF (cold) |  | V | at | 1000 | rpm | -10 | % | 2 | % | used by 3.9
Uemf | BEMF (cold) | 0 | V | at | 79 | rpm | used by 3.9
- | Number of poles |  | poles |  | 0 | pole pairs (pp.) | Tolerance (negative) |  | Tolerance (positive)
Uemf | BEMF (hot) |  | V | at | 1000 | rpm | -10 | % | 2 | % | used by 3.20
Uemf | BEMF (hot) | 0 | V | at | 79 | rpm | used by 3.20
| Rs, cold |  | mW (phase) | Rs,hot |  | mW (phase) | used by 3.4 and 3.13
| Ld, cold |  | mH (phase) | Ld, hot |  | mH (phase)
| Lq, cold |  | mH (phase) | Lq, hot |  | mH (phase)
| Stator connection | Y | -
| Stator winding material (Cu or Al) | Cu | -
| Insulation system | VPI system | -
VFD extra HHNK marge
UL1,L2,L3 | Line voltage | 500 | V | [8 empty] | 10 | 0K => 0C
fL | Line frequency | 50 | Hz
[7 empty] | Class | Hotspot margin | Max. permissble temp rise | Nominal Ambient(C) | Max. winding temperature | HHNK VFD max. permissble temp rise | Max. winding temp. VFD
| Temperature Rise | [6 empty] | 0K => 0C | 0K => 0C | 0C | 0C | 0K => 0C | 0C
| Insulation class | H | - |  | 180 | 0C | B | 10 | 80 | 40 | 130 | 90 | 140
| Temperature rise class | B | - |  | 130 | 0C | F | 10 | 105 | 40 | 155 | 115 | 165
| Safety margin | 50 | 0C |  |  |  | H | 15 | 125 | 40 | 180 | 135 | 190
| HHNK, max. allowed temp-rise without VSD | 80 | 0C
| HHNK max. allowed temp-rise with VSD | 90 | 0C
| Efficiency machine |  |  | Powerfactor (PF)
| Efficiency, 100% load | 94 | % | PF, 100% load | 0.95 | -
| Efficiency, 75% load | 93 | % | PF, 75% load | 0.85 | -
| Efficiency, 50% load | 92 | % | PF, 50% load | 0.72 | -
| Efficiency, 25% load | 91 | % | PF, 25% load | 0.6 | -
| Efficiency Class | n.a.
| Mechanical machine data |  |  | electric speed |  | mechanical speed |  | n | #DIV/0! | % | 157.5 | kW
n | Rated speed | 79 | rpm | 0 | rad/sec | #VALUE! | rad/sec | T | 0 | Nm | 19038.1546 | Nm
Tn | Rated torque (full load) | 68500 | Nm |  |  | 8.2729 | rad/sec
Ts | Starting torque | 110 | % | 75350 | Nm
Tk | Break-down torque | 130 | % | 89050 | Nm
| Direction of rotation | both ways | - | clock wise / anti clock wise, machine viewed from drive end, rotation is clockwise, if L1/U, L2/V, L3/W
J | Moment of inertia |  | Kgm^2
| Weight machine (approx.) |  | Kg
| Weight rotor (approx.) |  | Kg
Frame
Frame material
| Frame size H |  | mm
Flange size
| Foot size | n.a.
| Mouting arrangement (new) | IM-3011
| Mouting arrangement (old) | IM-V1
| Motor protection | >=IP-23
| Terminal box protection | >=IP-55
Cable Glands
| Main power cable glands | drawing….
| Auxiliary cable glands | drawing….
Bearing data
Bearing manufacturer
Bearing type Drive End
Bearing code Drive End
Lubrication bearings (amount of grease/operating hours)
Bearing type Non Drive End
Bearing code Non Drive End
Lubrication bearings (amount of grease/operating hours)
Bearing NDE insulated
Bearing lubrication
| Axial load on Drive End |  | kN
| Radial load on Drive End |  | kN
Shaft grounding ring
Vibration & noise
| Vibration severity | 1.5 | V rms (mm/s)
| Vibration class | B | -
| Noise Level LpA at 1 m on VFD < | 78 | dB(A)
Vibration monitoring
| ND, axes: Hor., Vert. , Axiaal | No
| NDE, axes: Hor., Vert. , Axiaal | No
Variabel Speed Drive (VSD)
| Prefered control mode sensorless | vector or scalar |  | PM: vector or DTC | IM: scalar or vector or DTC
| Min. switching frequency | 3.6 | kHz
| Max. switching frequency | 6 | kHz
Auxiliaries
Fan
| Coolant medium | air
Cooling type
Cooling type desciption
| Voltage Fan | 500 | V
| Current Fan |  | A
| Power Fan |  | W
Heating
Anti-condensation heater
| Voltage heater |  | V
| Power heater |  | W
| Temperature Protection PTC | Values
| Stator winding U, V, W, STOP | PTC (2x 3x in series)
| Stator winding U, V, W, Warning | PTC (2x 3x in series)
Wire Colours Triplet
| TNF switch temperature, Statorwinding (stop) | 145 | 0C | each phase, in serie U, V, W | black-white | used by 3.6 |  |  | Values PTC DIN 44 081 & 44
| TNF switch temperature, Statorwinding (stop, spare) | 145 | 0C | each phase, in serie U, V, W | black-white | used by 3.6
| Lower rated warning temperature (5, 10 or 15 0C) | 15 | 0C | HHNK typical = 15 0C |  |  |  |  | TNF (0C) |  | Wire Colour of Pairs & Triplets
| TNF switch temperature, Statorwinding (warning) | 130 | 0C | each phase, in serie U, V, W | blue-blue | used by 3.7 |  |  | 60 |  | white-grey
| TNF switch temperature, Statorwinding (warning, spare) | 130 | 0C | each phase, in serie U, V, W | blue-blue | used by 3.7 |  |  | 70 |  | white-brown
[9 empty] | 80 |  | white-white
|  | T stator winding (0C) -STOP | -WARNING | Measuring voltage (VDC) | Single PTC (W) | Triple PTC (W) |  |  | 90 |  | green-green
| Type-A, Resistance PTC 250C (max) | 25 | 25 | 0.2 | 100 | 300 |  |  | 95 |  | black-red
| Type-B, Resistance PTC 250C (max) | 25 | 25 | 0.2 | 250 | 750 |  |  | 100 |  | red-red
| Resistance, PTC TNF - 50C (max) | 140 | 125 | 2.5 | 250 | 750 |  |  | 110 |  | brown-brown
| Resitance, PTC TNF (typ) | 145 | 130 | 2.5 | 1000 | 3000 |  |  | 115 |  | brown-red
| Resistance, PTC TNF + 50C (min) | 150 | 135 | 2.5 | 1330 | 3990 |  |  | 120 |  | grey-grey
| Resistance, PTC TNF + 150C (min) | 155 | 145 | 7.5 | 4000 | 12000 |  |  | 125 |  | grey-red
[9 empty] | 130 |  | blue-blue
| Temperature Measurement | [7 empty] | 140 |  | blue-white
[9 empty] | 145 |  | black-white
| Statorwinding Temperature Measurement | [7 empty] | 150 |  | black-black
| U, V, W, (hotspot, main, winding end), main | PT100 (set 1x each phase) | [6 empty] | 155 |  | black-blue
| U, V, W, (hotspot, main, winding end), spare | PT100 (set 1x each phase) | [6 empty] | 160 |  | blue-red
[9 empty] | 170 |  | green-white
| Temperature measurement bearings | [7 empty] | 180 |  | red-white
| ND Bearing PT100 | PT100
| ND Bearing PT100 (spare) | PT100
| NDE Bearing PT100 | PT100
| NDE Bearing PT100 (spare) | PT100
ATEX
| ATEX class | No
Painting
| Painting system | Corrosivity cat. C3
| Painting RAL-color | RAL-1005
| Painting color | Honey Yellow
Additional specifications for predictive maintenance
| nr. slots |  | -
| nr. rotor bars |  | -
| nr. permanent magnets |  | -
| nr. rows of PM magnets |  | -
| type permanent magnets (PM) |  | -
| PM maximum temperature |  | 0C
| PM Currie temperature |  | 0C
| PM mounting intern / surface |  | -
| PM mounting line / skewed |  | -
| PM mounting Hallbach array Y/N |  | -
Print PDF for inspection
| Automatic OK off | TRUE
| Number of pages | 40
| Test specifications IEC 34 | Test value
| Standard resistance temperature | 20 | 0C | IEC34 | used by 3.4 and 3.13
| Maximum Temperature Rise | 80 | 0C | IEC34 used for 3.14 | used by 3.14
| Maximum Temperature Rise with VSD | 90 | 0C | IEC34 + HHNK requirement | used by 3.14
| Tolerance Resistance measurement cold | 5 | % |  | used by 3.4
| Tolerance Resistance measurement hot | 10 | % |  | used by 3.13
0

## Settings (no)load
3.15.1 Load-1 |  |  |  | Electrical Load Machine Test (1/4, 1/2, 3/4, full load, over load)
Torque | 68500 |  | Nm | P Load | Power | Speed | Speed | Speed | Torque |  | h Imposed | h Imposed
Speed | 79 |  | rpm | (%) | kW | Hz | rpm | rad/s | Nm |  | % | %
Pole Pairs | 0 |  | poles | 25 | 141.6727 | 0 | 79 | 8.2729 | 17125 |  | 91
Rated current | 0 |  | A | 50 | 283.3455 | 0 | 79 | 8.2729 | 34250 |  | 92
|  |  |  | 75 | 425.0182 | 0 | 79 | 8.2729 | 51375 |  | 93
|  |  |  | 100 | 566.691 | 0 | 79 | 8.2729 | 68500 |  | 94
|  |  |  | 110 | 623.3601 | 0 | 79 | 8.2729 | 75350 |  | 93
3.15.2 Load-2
Electrical Load Machine Test (selected operation points)
Torque | 68500 |  | Nm
Speed | 79 |  | rpm
Ref. power full load |  | 566.691 | kW
|  |  |  | P Load | Power | Speed | Speed | Speed | Torque |  | h Imposed | h Imposed
Torque (Nm) | Speed (Rad) |  |  | (%) | kW | Hz | rpm | rad/s | Nm |  | % | %
12150 | 22.3 |  |  | 5.0068 | 28.3733 | 0 | 22.3 | 2.3353 | 12150 |  | 90.8498
25300 | 39.9 |  |  | 18.6542 | 105.7115 | 0 | 39.9 | 4.1783 | 25300 |  | 90.4404
33800 | 49.9 |  |  | 31.1673 | 176.6224 | 0 | 49.9 | 5.2255 | 33800 |  | 91.935
49500 | 59.9 |  |  | 54.7916 | 310.4993 | 0 | 59.9 | 6.2727 | 49500 |  | 92.6437
68500 | 79 |  |  | 100 | 566.691 | 0 | 79 | 8.2729 | 68500 |  | 94
3.16 No-Load
Voltage | 500 |  | V
Point 1 |  | Point 2 |  | Point 3 |  |  | Point 4 |  |  | Point 5 |  | Point 6
Un(%) |  | Un(%) |  | Un(%) |  |  | Un(%) |  |  | Un(%) |  | Un(%)
| % | 80 | % | 90 | % |  | 100 | % |  | 110 | % |  | %
| V | 400 | V | 450 | V |  | 500 | V |  | 550 | V |  | V

## Notes
Notes
Version | 0.2.1
1.1 | Use of Excel version test plan
The electric motor supplier is permitted to use this digital version freely.
Despite the utmost care taken in preparing this document, errors may occur.
Supplier is requested to report errors.
HHNK is not liable for any errors in this test plan.
See the attached documents and specifications for the requirements for the electric machine.
HHNK reserves the right to apply modified test plans within the agreed framework of the contract.
1.2 | Recommendation:
First complete:
- Machine Specification worksheet. -> green and blue fields.
Second complete:
- Settings (no)load worksheet.
Third:
- Leave automatic connections intact.
1.3 | Protection
Worksheets are protected by default. Input fields (green and blue) are fillable. No password has been applied
1.4 | PDF Print
Print pages 1 through 40 to a PDF Test file from Excel.
1.5 | Latest revisions 0.2. -> 0.2.1
1.5.1 | term VSD changed to VFD (Variable Frequency Drive)
1.5.2 | 3.1.3.3. extra design checks
Machine parameters Rs, Ld and Lq are checked
The checks are intended to ask how the manufacturer limits the cogging torque on PM machines?
1.5.3 | 3.2 max lift weight 12,5 ton 12500kg
1.5.4 | 3.6 + 3.7 PTC,
Check the PTC at minimum and maximum operating temperatures.
Only complete the table if you are unsure about the PTC's operation.
1.5.5 | Updated 3.15.1, 3.15.2 and 3.16
new values and calculations under the hood
1.5.6. | Annex 1.1 Machine specifications display cold and hot values machine.