## Revision log
Revision log |  |  | Annex 4a
The main/ relevant updates related to a new revision are listed below. Minor editorial updates are not listed below.
The line or cell numbers refer to this revision, they could differ from a previous revision due to addition or removal of lines
Revision | Date | Tab | Explanation
1
1
1
1
1
1
1
1
1
2
2
2
2
3
3
4
4

## Cycle times & prices
Cycle times and prices benthic survey Doordewind
Project: | Benthic Survey - Doordewind Wind Farm Zone
Tenderer:
Originator:
I. Doordewind Wind Farm Zone Geotechnical Investigation Area and Number of Tests
Offshore Scope |  |  |  |  | Total Number | Short name
Seabed samples |  |  |  |  | 40 | GS
Visual inspection |  |  |  |  | 15 | VI
eDNA water sampling |  |  |  |  | 40
II. Planning Survey (excluding weather) |  |  | Unit | Cycle | Qty | Total (days) | (end) date
Key dates
1 | COMMENCEMENT DATE WORK set by CLIENT | [5 empty] | 2026-11-15
Preparation
2a | 1st revision of project documentation (PQP, PEP) = Contract award date | [5 empty] | 2026-11-15
2b | CLIENT Review 1st revision project documentation (PQP, PEP) |  | days | 7 |  |  | 2026-12-05
2c | 2nd revision of project documentation (PQP, PEP) |  | days | 7 |  |  | 2026-12-12
2d | CLIENT Review 2nd revision project documentation (PQP, PEP) |  | days | 7 |  |  | 2026-12-19
2e | Finalise project documentation (incl additional revisions/review rounds and ALARP clearance) |  | days | 7 |  |  | 2026-12-26
2f | Days between finalization project documentation and start mobilization ( before 3a) |  | days | 7 |  |  | 2027-01-02
Field work
3a | CONTRACTOR's Expected start of Mobilisation (between CLIENT approval of project documentation and latest date) |  | latest | 2027-05-01 | Fill in date; INVALID IF COLOURED RED: |  | 2027-02-01
3b | Mobilisation, including transit to site, testing and set up; MIN: 2 days / MAX: 14 days |  | days | 4 |  |  | 2027-02-05
3c | Total duration survey ¦ Offshore completion date excluding WAITING ON WEATHER |  | days | 10 |  |  | 2027-02-15
3d | Offshore completion date ¦ Including WAITING ON WEATHER calculated by CONTRACTOR (J66) |  | days | Fill in days |  | 9 | 2027-02-24
Explanation for difference between WOW calculated by CLIENT and WOW according to TENDERER.
Data Processing and report
4a | OFFSHORE COMPLETION DATE (including WAITING ON WEATHER) | [5 empty] | 2027-02-24
4b | Delivery of 1st version "Benthic Survey Operations Field Report" (days after OFFSHORE COMPLETION DATE) (days after 4a) |  | days | 14 |  |  | 2027-03-10
4c | CLIENT review of 1st revision "Benthic Survey Operations Field Report" |  | days | 14 |  |  | 2027-03-24
4d | Delivery of Final Version of "Benthic Survey Operations Field Report" |  | days | 14 |  |  | 2027-04-07
4e | CLIENT Review of Final Version of "Benthic Survey Operations Field Report" |  | days | 7 |  |  | 2027-04-14
4f | Acceptance of Final Version of "Benthic Survey Operations Field Report" |  | days | 14 |  |  | 2027-04-28
4g | Delivery of 1st Version "Environmental baseline report" including draft data package | [5 empty] | 2027-09-01
4h | CLIENT review of 1st Version "Environmental baseline report" |  | days | 14 |  |  | 2027-09-15
4i | Delivery of 2nd Version "Environmental baseline report" including all lab test results |  | days | 14 |  |  | 2027-09-29
4j | CLIENT review of 2nd Version "Environmental baseline report" |  | days | 14 |  |  | 2027-10-13
4k | Delivery of Final Version Environmental baseline report before |  | days | 14 |  |  | 2027-10-27
4l | CLIENT Review of Final Version Environmental baseline report before |  | days | 7 |  |  | 2027-11-03
4m | Key Milestone: Acceptance of Final Version Environmental baseline report (before 15-12-2027) | 2027-12-15 | days | 14 | Calculated date; INVALID IF COLOURED RED: |  | 2027-11-17
Total time from start of contract till reporting end date | [5 empty] | 367 | days
IV. Rates Geotechnical Site Survey - DDW IA
ITEM |  |  |  | Unit Rate | Unit | Qty | Price
1 | Mobilisation/demobilisation of vessel(s), survey equipment and personnel to site
1.1 | Mob/demob vessels and equipment |  |  | 45000 | Lump sum | 1 | 45000
2 | Survey Operations incl transit from and to site excluding WOW
2.1 | Offshore benthic sample |  |  | 150 | /sample | 40 | 6000
2.2 | Offshore eDNA sample |  |  | 1000 | /sample | 40 | 40000
2.3 | Visual seabed survey |  |  | 500 | /location | 15 | 7500
2.4 | Re-try eDNA or benthic sample on CLIENT request (outside of retest requirements from SoW) |  |  | 3000 | /location | 6 | 18000
3 | Lab Testing
Lab tests on the grab samples
3.1 | Particle size analysis (including fines) |  |  | 150 | /test | 40 | 6000
3.2 | Chemical testing (As, Cd, Cr, Cu, Hg, Ni, Pb, Zn, PAH, TOC) |  |  | 500 | /set of tests | 20 | 10000
3.3 | Macrofauna |  |  | 1000 | /test | 40 | 40000
Lab tests on the eDNA water samples
3.4 | eDNA analysis |  |  | 700 | /test | 40 | 28000
4 | Reporting
4.1 | Benthic Survey Operations Field Report |  |  | 9000 | Lump sum | 1 | 9000
4.2 | Environmental baseline report |  |  | 3000 | Lump sum | 1 | 3000
5 | Waiting on Weather
5.1 | Waiting on Weather allowance |  |  | 15000 | /day | 9 | 135000
6 | Other
6.1 | Any activities required for the purpose of seabed clearance measures in accordance with CS-OOO regulations for seabed sampling locations |  |  | 100 | /location | 40 | 4000
V. INPUT FOR ASSESSMENT OF THE OFFER
INPUT FOR ASSESSMENT OF THE PRICE CRITERION - Fixed prices/rates
Price for executing the survey including WAITING ON WEATHER |  | Survey works |  |  |  |  | 216500
|  | Allowance for WOW |  |  |  |  | 135000
TOTAL | [6 empty] | 351500
|  | Max. number of points that can be awarded |  |  |  | 20
|  | Minimum Price (determined by CLIENT) |  |  |  | 400000
|  | Maximum Price (determined by CLIENT) |  |  |  | 800000
|  | Points gained for the TOTAL PRICE proposed: |  |  |  | EXCLUSION | Points
TOTAL POINTS GAINED BY TENDERER | [5 empty] | EXCLUSION | Points
VI. ADDITIONAL EXPLANATORY NOTES
IN CASE A CELL`OR TEXT FILLED IN BY BIDDER IN THIS ANNEX 4a IS COLORED RED AS SHOWN IN THIS CELL THE PROPOSAL IS NOT VALID.
All numbers indicated in green are starting points set by CLIENT and should not be changed by TENDERER.
All yellow cells are to be filled in by TENDERER and will form part of the PRICING SCHEDULE / CONTRACT PRICE as included in Annex 6 - Contract Section III (Remuneration), and/or KEY DATES as included in Annex 6 - Contract Section IV (Scope of Work). All quantities will be used for assessment purposes and will also be the basis for determining the final CONTRACT PRICE and KEY DATES for these activities to be carried out under the CONTRACT. IN CASE THE BLUE TEXT TURNS RED, THIS MEANS THAT TENDERER ENTERED A VALUE OUTSIDE THE ALLOWABLE RANGES. This colour coding is for convenience only; the TENDERER is responsible for ensuring that the correct values are submitted by the TENDERER.
TENDERER pricing shall be based on the vessel supplied in Annex 3 and the PEP. Change of vessel after approval of the CLIENT shall not affect the price set in this Annex 4. TENDERER may carry out the surveys with the amount of vessels it deems necessary and there is no need to specify which vessel shall perform what scope. The combination of survey equipment items to be run from the vessels shall be compliant with the Annex 6 - Contract Section IV (Scope of Work) At CONTRACT award, the values specified in this Annex 4 shall be taken over in Annex 6 - Contract Section III (Remuneration)
TENDERER may propose multiple vessels including equipment for the execution of the survey works. The overall limiting operational conditions will need to be specified by TENDERER for the whole proposed fleet, including equipment. CLIENT will only use the given vessel characteristics to prepare a comparative adverse weather calculation based on the average of all vessels. This calculation will only be used by CLIENT for reference and as cross-check of TENDERER's proposed WAITING ON WEATHER. TENDERER shall specify the number of WAITING ON WEATHER days to be included and if this deviates significantly from the calculated value, an explanation shall be provided as part of the tender submission. These days will be taken as the WAITING ON WEATHER ALLOWANCE DAYS in Annex 6 - Contract Section IIIa (Remuneration) The values in this section will ONLY be used by CLIENT to calculate weather downtime compensation when (a part of) the fleet is not able to work due to weather. In case of reported waiting on weather of (part of ) the fleet, the individual vessel characteristics on workability will be used to calculate any possible compensation for this waiting on weather.
TENDERER shall specify the cycle times for executing the works. Key dates are set by the CLIENT due to schedule requirements. At CONTRACT award these dates will be taken over in Annex 6 - Contract Section IV (Scope of Work) / Table 1 Please note that Liquidated Damages/ mala become applicable in case CONTRACTOR fails to meet Key Dates as per Annex 6 - Contract Section III (Remuneration), Chapter 5 (Bonus and malus)
All costs associated with extra work caused by unforeseen circumstances e.g. mechanical breakdowns, re-positioning, bump-overs, following equipment failure etc. are not chargeable under the operational or weather standby rates and are assumed to be considered in the total project execution duration and price.
Lump sum for activities related to dissemination of results (item 6.8) shall be paid upon completion of the webinar and Project Site Description, in accordance with Annex 6 - Contract Section IIIa (Remuneration)
TENDERER shall specify the allowance for WAITING ON WEATHER for the Lumpsum including weather. This WAITING ON WEATHER ALLOWANCE shall cover all WEATHER DOWNTIME that could be encountered during the execution of the works. At Contract award the values specified in Annex 4 shall be taken over in Annex 6 - Contract Section III (Remuneration)
The TENDERER gains points when able to complete the works below the set maximum price. The number of points that are awarded is determined through linear interpolation between the minimum and maximum price.
The weather downtime days as specified by the TENDERER are included in the calculation of the OFFSHORE COMPLETION DATES and the consequential reporting and deliverable milestones as set by CLIENT. IN CASE THIS DATE IS LATER THAN THE ULTIMATE DUE DATE SET BY THE CLIENT THIS CELL IS COLORED RED. THIS MEANS THE PROPOSAL NOT VALID!
Note on I9: [Opmerkingenthread] U kunt deze opmerkingenthread lezen in uw versie van Excel. Eventuele wijzigingen aan de thread gaan echter verloren als het bestand wordt geopend in een nieuwere versie van Excel. Meer informatie: https://go.microsoft.com/fwlink/?linkid=870924 Opmerking: Depends on TNO outcome