## Cycle times & prices
VIRTUAL CYCLE TIME & PRICE GEOPHYSICAL SURVEY FOR ASSESSMENT
Project: | WOZFB26001 Lot 2: Geophysical Survey Search Area 6/7 3DUHRS Campaign
Company:
Originator:
Note
I. Survey Scope Search Area 6/7 Lot 2
Investigation area (Sa 6/7 Lot2) |  | 1025 |  | km2 |  |  | I.0
II. Vessels used for which equipment & Limiting condition and required weather window |  | Hs (m) | Vw (m/s) | Ww (hrs)
Vessel name(s) | [6 empty] | II.0 | 1 1 | Hs [m] | Vw [m/s] | Ww [hr]
| Sa 67 GP Lot 2 ¦ MBES: Multi Beam Echo Sounder ¦ 3DUHRS: 3D Ultra High Resolution | [7 empty] | 0.25 | 2 | 1
III. Cycle times |  | Unit | Cycle | Qty | Total (days) | (end) date |  |  | 0.75 | 6 | 4
Key dates | [6 empty] | III.0 |  | 1 | 8 | 6
1 | COMMENCEMENT DATE CONTRACT |  |  |  |  | 2027-02-08 |  |  | 1.25 | 9 | 12
Preparation | [8 empty] | 1.5 | 10 | 18
2a | 1st revision of project documentation | days | 21 |  |  | 2027-03-01 |  |  | 1.75 | 11 | 24
2b | Review 1st revision project documentation | days | 14 |  |  | 2027-03-15 |  |  | 2 | 12 | 48
2c | 2nd revision of project documentation | days | 14 |  |  | 2027-03-29 |  |  | 2.25 | 15 | 72
2d | Review 2nd revision project documentation | days | 14 |  |  | 2027-04-12 |  |  |  | 20
2e | Finalize project documentation (incl additional revisions/review rounds i.a.) | days | 7 |  |  | 2027-04-19 |  |  |  | 25
2f | Minimum number of days between finalization project documentation and start mobilization | days | 2 |  |  | 2027-04-21
2g | Technical Kick-off Meeting (TKOM) 3 weeks before mobilisation
Field work | [8 empty] | 0
3a | Start of Mobilisation Earliest 21-04-2027 |  |  | INVALID IF COLOURED RED: |  |  | III.3 |  | 2024-03-01
3b | Mobilisation MIN: 2 days / MAX: 7 days | days |  |  |  | 0
3c | Testing (and transit to site) MIN: 1 day / MAX: 7 days | days |  |  |  | 0
3d | Lot 2 survey duration - Sa67-IA ¦ MBES ¦ 3DUHRS | days |  |  |  | 0 | III.4
3e | Offshore completion date ¦ Excluding WAITING ON WEATHER |  |  |  |  | 0
3f | Offshore completion date ¦ Including WAITING ON WEATHER calculated by CONTRACTOR: MAX: 80 days |  | INVALID IF COLOURED RED: |  |  | 0 |  | 80.01
Data processing and reporting | [7 empty] | 1 1
4a | OFFSHORE COMPLETION DATE (including WAITING ON WEATHER) |  |  |  |  | 0 |  | 1 1
4b | Delivery of offshore processed survey data (incl. WoW): MIN: 8 WEEKS / MAX 15 WEEKS | processing time: days |  | INVALID IF COLOURED RED: |  | 0
4c | Field (operations) Report (days after OFFSHORE COMPLETION DATA) MAX: 5 WEEKS | days |  |  |  | 0 |  | 1 1 1
4d | Finalisation of data processing and interpretation (workshop with CLIENT) At latest two (2) weeks before 1st revision of Draft version of Final Interpretation Report |  | 14 |  |  | 0 |  | 1 1 1
4e | Issue 1st revision of Draft version of Final Interpretation Report - Search Area 6/7 - including all raw / processed / interpretated digital data (days after offshore completion date) MIN: 10 WEEKS / MAX 20 WEEKS | days |  |  |  | 0 | III.8 | 1 1 1
4f | Client Review of 1st revision of Draft version of Final Interpretation Report - Search Area 6/7 | days | 21 |  |  | 1900-01-20 |  | 1 1
4g | Issue 2nd revision of Draft version of Final Interpretation Report - Search Area 6/7 - including all raw / processed / interpretated digital data MIN: 3 WEEKS / MAX: 6 WEEKS | days |  |  |  | 1900-01-20 |  | 1 1 1
4h | Client review of 2nd revision of Draft version of Final Interpretation Report - Search Area 6/7 | days | 14 |  |  | 1900-02-03 |  | 1 1
4i | Issue Final Interpretation Report - Search Area 6/7 including all raw / processed / interpretated digital data MIN: 7 days / MAX: 14 days | days |  | INVALID IF COLOURED RED: |  | 1900-02-03 |  | 1 1 1
TOTAL DURATION CYCLE TIME INCLUDING WEATHER |  |  |  |  | -46391 | days
IV. Rates Geophysical Survey SA 6/7 Wind Farm Zone 3DUHRS Campaign - SA 6/7
ITEM |  |  | Unit Rate | Unit | Estimated Qty | Price
1 | Mob/Demob of vessel(s), survey equipment and personnel to site
1.1 | Mob/Demob of vessel(s), survey equipment and personnel to site |  |  | Lump sum | 1 | 0
2 | Survey Operations: incl transit from to site excluding WOW
2.1 | Sa67-IA ¦ MBES ¦ 3DUHRS - Acquisition and (fast-track) processing |  |  | /km2 | 1025 | 0 | IV.1
2.2 | Extra port call upon Client request |  |  | /port call | 1 | 0
3 | REPORTING
3.1 | Final (Operations) Report 3D survey data ¦ MBES ¦3DUHRS ¦ obtained under 2.1 |  |  | Lump Sum | 1 | 0
3.2 | Full set of Final Interpretation Report(s), drawings, preliminary ground model (PGM) & digital data (including: complete raw & processed datasets, PGM including Lot 1 MBES, SBP & GIS integration, digital & HDD delivery) |  |  | Lump Sum | 1 | 0
4 | Waiting on Weather
4.1 | Waiting on Weather |  |  | /day | 0 | 0
5 | Other
5.1 | Project meetings to be held in Clients offices (Utrecht or The Hague) |  |  | /meeting | 5 | 0
5.2 | Activities related to dissemination of results (webinars and Project site Description) |  |  | Lump Sum | 1 | 0
V. INPUT FOR ASSESSMENT OF THE OFFER
INPUT FOR ASSESSMENT OF THE PRICE CRITERION - Fixed prices/rates | [6 empty] | V.0
TOTAL PRICE for assessment |  | INVALID IF COLOURED RED: |  |  | 0
|  | Max. number of points that can be awarded |  |  | 20
|  | Minimum Price (determined by CLIENT) |  |  | 30000000
|  | Maximum Price (determined by CLIENT) |  |  | 44000000
|  | Points gained for the TOTAL PRICE proposed: |  |  | 0 | Points
Note on J8: All numbers indicated in green are starting points set by CLIENT. All blue values within the yellow filled are to be provided by CONTRACTOR, and will form part of the PRICING SCHEDULE / CONTRACT PRICE as included in Annex [5] - Contract Section III (Remuneration), and/or KEY DATES as included in Annex [4] - Key Dates. All quantities will be used for assessment purposes and will also be the basis for determining the final CONTRACT PRICE and KEY DATES for these activities to be carried out under the CONTRACT.
Note on J10: CONTRACTOR to provide limiting operational conditions (Hs(m), Vw(m/s)) and minimum required weather window(Ww[hrs]) to perform the survey for the vessel(s) proposed.
Note on J13: CONTRACTOR shall specify the cycle times for executing the works by filling in the yellow cells. Please note that Liquidated Damages become applicable in case CONTRACTOR fails to meet Key Dates 4i (Annex [4] - Key Dates) as per Annex [5] - Contract Section II (Conditions of Contract)- Clause 42!
Note on J24: Actual mobilisation can move forward should project documentation be approved sooner. In case the finalisation date of the project documentation is later than 7 days before the start of the mobilization, this cell is coloured red. This means that the time allowed for preparation is estimated to be not sufficient in relation to the planned mobilisation date!
Note on J27: The survey area is set by the CLIENT. The survey might be acquired in multiple vessels and/or in multiple passes. In the Project Execution Plan the CONTRACTOR should provide schedule in which the survey area is fully covered and the indicated survey time is justified based on the number of vessels, number of passes, and speed (km2/day).
Note on I32: [Opmerkingenthread] U kunt deze opmerkingenthread lezen in uw versie van Excel. Eventuele wijzigingen aan de thread gaan echter verloren als het bestand wordt geopend in een nieuwere versie van Excel. Meer informatie: https://go.microsoft.com/fwlink/?linkid=870924 Opmerking: Set conditional formatting.
Note on J35: For key dates 4e: please note that CLIENT has set a minimum duration of 10 and a maximum of 20 weeks after the OFFSHORE COMPLETION DATE for issuing the first revision of the final geophysical report.
Note on I39: [Opmerkingenthread] U kunt deze opmerkingenthread lezen in uw versie van Excel. Eventuele wijzigingen aan de thread gaan echter verloren als het bestand wordt geopend in een nieuwere versie van Excel. Meer informatie: https://go.microsoft.com/fwlink/?linkid=870924 Opmerking: Set conditional formatting.
Note on J47: To be invoiced per completed & Client-approved block. Size requirements of blocks are described in the scope of work, and exact sizes to be offered in the PEP and to be approved by the Client.
Note on J59: The number of points that can be awarded is determined through linear interpolation between the minimum and maximum price as described in the tender document. In case the total price offered is lower than the minimum or higher than the maximum price the proposal is rejected

## Key Dates
in green, bold and underlined key date for which contractor is liable for liquidated damages in case of failure to complete these dates
No. | Description | Date
1 | COMMENCEMENT DATE CONTRACT | 2027-02-08
2e | Finalize project documentation (incl additional revisions/review rounds i.a.) | 2027-04-19
3a | Start of Mobilisation | 0
3f | Offshore completion date ¦ Including WAITING ON WEATHER calculated by CONTRACTOR: MAX: 80 days | 0
4c | Field (operations) Report (days after OFFSHORE COMPLETION DATA) MAX: 5 WEEKS | 0
4e | Issue 1st revision of Draft version of Final Interpretation Report - Search Area 6/7 - including all raw / processed / interpretated digital data (days after offshore completion date) MIN: 10 WEEKS / MAX 20 WEEKS | 0
4g | Issue 2nd revision of Draft version of Final Interpretation Report - Search Area 6/7 - including all raw / processed / interpretated digital data MIN: 3 WEEKS / MAX: 6 WEEKS | 1900-01-20
4i | Issue Final Interpretation Report - Search Area 6/7 including all raw / processed / interpretated digital data MIN: 7 days / MAX: 14 days | 1900-02-03